## G1 - Investment
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
SECTION G: INVESTMENT MONITORING
Table G1: Summary - Investment
|  |  |  | 10 | 20 | 30 | 40 | 50 |  | 70 | 80 | 90
Line | Description | Units | Field | Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Forecast Report Year | Forecast Post | Forecast Total Financed in
Ref. |  |  | Type
|  |  |  | Pre 2015 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021 | SR15-21
Capital Maintenance
G1.01 | Water Service Infrastructure | £m | I | 0 | 81.0064 | 115.369 | 144.7113 | 92.0429 | 65.6423 | 85.1301 | 54.0311 | 637.9331
G1.02 | Water Service Non-Infrastructure | £m | I | 0 | 71.562 | 75.5229 | 80.3842 | 103.5682 | 99.9926 | 149.5899 | 0 | 580.6197
G1.03 | Wastewater Service Infrastructure | £m | I | 0 | 30.3748 | 36.0646 | 35.4999 | 65.5601 | 47.1958 | 49.4785 | 0 | 264.1737
G1.04 | Wastewater Service Non-Infrastructure | £m | I | 0 | 49.7278 | 58.7796 | 72.4917 | 66.9728 | 85.4434 | 81.694 | 0 | 415.1093
G1.05 | Management and General | £m | I | 0 | 27.3818 | 52.4878 | 61.3964 | 53.308 | 46.7574 | 42.3296 | 0 | 283.6609
G1.06 | Total Capital Maintenance | £m | C | 0 | 260.0528 | 338.2239 | 394.4834 | 381.452 | 345.0314 | 408.222 | 54.0311 | 2181.4966
Growth
G1.07 | Growth in the Water Network | £m | I | 0 | 3.4002 | 7.1083 | 7.8359 | 9.2609 | 14.1751 | 23.2977 | 14.4125 | 79.4904
G1.08 | Growth in the Wastewater Network | £m | I | 0 | 9.8958 | 10.2296 | 15.3008 | 36.5216 | 40.4668 | 24.3521 | 5 | 141.7667
G1.09 | Water Reasonable Cost Contributions | £m | I | 0 | 8.1987 | 7.2182 | 6.7422 | 10.4484 | 6.3965 | 9.8035 | 0 | 48.8075
G1.10 | Wastewater Reasonable Cost Contributions | £m | I | 0 | 8.6536 | 10.4298 | 9.8565 | 18.229 | 9.9867 | 13.9867 | 0 | 71.1424
G1.11 | Service Relocations Water | £m | I | 0 | 15.0386 | 12.4052 | 9.3689 | 7.7994 | 6.1906 | 4.8386 | 0 | 55.6413
G1.12 | Service Relocations Wastewater | £m | I | 0 | 4.8054 | 4.9606 | 3.4735 | 1.8201 | 2.4883 | 6.8569 | 0 | 24.4049
G1.13 | Total Growth Expenditure | £m | C | 0 | 49.9923 | 52.3517 | 52.5778 | 84.0795 | 79.704 | 83.1354 | 19.4125 | 421.2532
Q&SIV Enhancement Expenditure
G1.14 | Improving drinking water quality compliance and reliability | £m | I | 9.2909 | 18.0605 | 46.4015 | 56.587 | 66.1801 | 85.5489 | 79.0434 | 137.8427 | 498.955
G1.15 | Improving drinking water availability and resilience of service | £m | I | 3.3164 | 10.9888 | 14.5593 | 18.0362 | 32.3414 | 28.216 | 23.1926 | 28.4851 | 159.136
G1.16 | Protecting and enhancing the environment | £m | I | 8.9269 | 14.9754 | 24.8366 | 41.472 | 31.3306 | 36.5887 | 37.4989 | 106.5474 | 302.1766
G1.17 | Reducing flooding and pollution from sewers | £m | I | 21.1556 | 24.1093 | 15.6515 | 15.2364 | 15.9917 | 28.618 | 50.8458 | 47.3234 | 218.9318
G1.18 | Improving the customer experience | £m | I | 0.9286 | 1.8248 | 6.1398 | 5.2653 | 4.9185 | 9.3076 | 11.9564 | 0.53827 | 40.8793
G1.19 | Climate Change | £m | I | 0.23491 | 0.15567 | 0.41575 | 0.34953 | 0.039188 | 0.31889 | 1.2836 | 0.044152 | 2.8417
G1.20 | Reducing long term cost of service | £m | I | 2.9412 | 4.7829 | 4.4047 | 2.9306 | 1.628 | 1.5767 | 3.0861 | 0.77332 | 22.1236
G1.21 | Total Q&SIV Enhancement Expenditure | £m | C | 46.7946 | 74.8973 | 112.4092 | 139.8772 | 152.4295 | 190.1749 | 206.9067 | 321.5545 | 1245.0439
Q&SIV Enhancement - IR18
G1.22 | Total remaining IR18 Unallocated Investment | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Q&SIIIa & Q&SIIIb Completion Expenditure
G1.23 | Total OMG180 Completion Expenditure | £m | I | 0 | 72.5889 | 96.2254 | 34.7908 | 29.664 | 25.8855 | 16.0204 | 15.8195 | 290.9944
G1.24 | Total Non OMG180 Completion Expenditure | £m | I | 0 | 4.1527 | 27.0091 | 24.4577 | 11.5081 | 5.4411 | 1.1793 | 0.43752 | 74.1855
G1.25 | Total Completion Expenditure | £m | C | 0 | 76.7416 | 123.2345 | 59.2485 | 41.1721 | 31.3266 | 17.1997 | 16.257 | 365.18
Q&SV Early Start
G1.26 | Total Q&SV Early Start Enhancement Expenditure | £m | I | 0 | 0.030115 | 0.49126 | 0.47506 | 0.80004 | 18.3602 | 27 | 0 | 47.1567
Total Additional Operating Expenditure
G1.27 | Additional Operating Expenditure from Capital Maintenance | £m | I | 0 | 0.97566 | 0.75877 | 0.41055 | 0.43433 | 0.7358 | 1.9717 | 1.2187 | 6.5055
G1.28 | Additional Operating Expenditure from Water Growth | £m | I | 0 | 0 | 0.025756 | 0.0040854 | 0.0025373 | 0.050724 | 0.013101 | 0.00077064 | 0.096974
G1.29 | Additional Operating Expenditure from Wastewater Growth | £m | I | 0 | 0 | 0 | 0 | 0 | 0.017705 | 0.093037 | 0.41527 | 0.52601
G1.30 | Additional Operating Expenditure from Improving drinking water quality compliance and reliability | £m | I | 0 | 0 | 0 | 0.008662 | 0.07916 | 0.38221 | 0.098499 | 0.25787 | 0.8264
G1.31 | Additional Operating Expenditure from Improving drinking water availability and resilience of service | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0.0055833 | 0.0079614 | 0.013545
G1.32 | Additional Operating Expenditure from Protecting and enhancing the environment | £m | I | 0 | 0 | 0 | 0 | 0.207 | 0.50596 | 0.02555 | 0.12933 | 0.86784
G1.33 | Additional Operating Expenditure from Reducing flooding and pollution from sewers | £m | I | 0 | 0.0054 | 0 | 0 | 0 | 0 | 0.026555 | 0.024536 | 0.056491
G1.34 | Additional Operating Expenditure from Improving the customer experience | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0.21367 | 0.11811 | 0.33178
G1.35 | Additional Operating Expenditure from Climate Change | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.36 | Additional Operating Expenditure from Reducing long term cost of service | £m | I | 0 | 0 | 0 | 0.11 | 0 | 0 | -0.080645 | -0.91935 | -0.89
G1.37 | Additional Operating Expenditure from IR18 | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.38 | Additional Operating Expenditure from Completion | £m | I | 0 | 0.20123 | 0.63448 | 0.23556 | 0.25855 | 0.20122 | 0.15658 | 0.22396 | 1.9116
G1.39 | Additional Operating Expenditure from Q&SV Early Start | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.40 | Total Additional Operating Expenditure | £m | C | 0 | 1.1823 | 1.419 | 0.76886 | 0.98157 | 1.8936 | 2.5237 | 1.4771 | 10.2461
Grants and Capital Contributions
G1.41 | Grants for infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.42 | Grants for non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.43 | Contributions to infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.44 | Contributions to non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.45 | Contributions to service relocations - Water | £m | I | 0 | -10.7902 | -6.5168 | -7.3147 | -4.6331 | -5.9057 | -7.4625 | 0 | -42.6231
G1.46 | Contributions to service relocations - Wastewater | £m | I | 0 | -5.5586 | -3.3571 | -3.7682 | -1.7827 | -3.0027 | -3.7077 | 0 | -21.1769
G1.47 | “Infrastructure charge" contributions for infrastructure assets | £m | I | 0 | -1.7095 | -14.871 | -7.0921 | -20.084 | -27.38 | -2.0633 | 0 | -73.2
G1.48 | Total Capital Contributions | £m | C | 0 | -18.0583 | -24.745 | -18.1751 | -26.4998 | -36.2883 | -13.2335 | 0 | -137
Expenditure Totals
G1.49 | Capital Maintenance Expenditure | £m | C | 0 | 260.0528 | 338.2239 | 394.4834 | 381.452 | 345.0314 | 408.222 | 54.0311 | 2181.4966
G1.50 | Growth Expenditure | £m | C | 0 | 49.9923 | 52.3517 | 52.5778 | 84.0795 | 79.704 | 83.1354 | 19.4125 | 421.2532
G1.51 | Q&SIV Enhancement Expenditure | £m | C | 46.7946 | 74.8973 | 112.4092 | 139.8772 | 152.4295 | 190.1749 | 206.9067 | 321.5545 | 1245.0439
G1.52 | Q&SIIIa & Q&SIIIb Completion Expenditure | £m | C | 0 | 76.7416 | 123.2345 | 59.2485 | 41.1721 | 31.3266 | 17.1997 | 16.257 | 365.18
G1.53 | Q&SV Early Start Expenditure | £m | C | 0 | 0.030115 | 0.49126 | 0.47506 | 0.80004 | 18.3602 | 27 | 0 | 47.1567
G1.54 | Gross Capital Investment | £m | C | 46.7946 | 461.7141 | 626.7105 | 646.6619 | 659.9331 | 664.5971 | 742.4639 | 411.2551 | 4260.1303
G1.55 | Total Capital Contributions | £m | C | 0 | -18.0583 | -24.745 | -18.1751 | -26.4998 | -36.2883 | -13.2335 | 0 | -137
G1.56 | Net Capital Investment | £m | C | 46.7946 | 443.6558 | 601.9656 | 628.4868 | 633.4333 | 628.3087 | 729.2304 | 411.2551 | 4123.1303
G1.57 | Total Additional Operating Expenditure | £m | C | 0 | 1.1823 | 1.419 | 0.76886 | 0.98157 | 1.8936 | 2.5237 | 1.4771 | 10.2461
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G2 - Q&SIV Outputs
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
SECTION G: INVESTMENT MONITORING
Table G2: Summary - Outputs
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90
Line | Description | Units | Field | Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Forecast Report Year | Forecast Post | Forecast Total Financed in
Ref. |  |  | Type
|  |  |  | Pre 2016 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021 | SR15-21
Growth
G2.1 | Strategic Capacity - Water Treatment [WG1] | Pe | I | 0 | 0 | 14677 | 0 | 0 | 0 | 1272 | 33000 | 15949
G2.2 | Strategic Capacity - Wastewater Treatment [SG1] | Pe | I | 0 | 1351 | 792 | 3188 | 671 | 6651 | 34335 | 0 | 46988
G2.3 | Strategic Water Network Capacity (Infrastructure Charge) [WG5 ] | Pe | I | 0 | 1920 | 12758 | 10705 | 2058 | 0 | 3254 | 0 | 30695
G2.4 | Strategic Wastewater Network Capacity (Infrastructure Charge) [SG5 ] | Pe | I | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Q&SIV Enhancements - Drinking Water Quality
G2.5 | Number of water treatment works improved | No. | I | 0 | 0 | 1 | 3 | 6 | 4 | 5 | 11 | 19
G2.6 | Number of zones made compliant with iron & manganese standards | No. | I | 0 | 0 | 0 | 4 | 34 | 19 | 7 | 18 | 64
G2.7 | Number of enhancements to improve reliability of supply (catchments and treatment) | No. | I | 0 | 2 | 1 | 5 | 4 | 6 | 16 | 20 | 34
G2.8 | Number of enhancements to improve reliability of supply (networks and storage) | No. | I | 0 | 1 | 10 | 2 | 9 | 28 | 29 | 8 | 79
G2.9 | Distribution mains cleaned (km) | Km | I | 0 | 0 | 0 | 106.06 | 458.24 | 1580.37 | 2062.088 | 2451.3494 | 4206.758
G2.10 | Water supply resilience strategy and improvements made | No. | I | 0 | 4 | 3 | 1 | 4 | 2 | 3 | 2 | 17
G2.11 | Number of zones with improved security of supply (SOSI) | No. | I | 0 | 1 | 0 | 0 | 3 | 2 | 1 | 4 | 7
G2.12 | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | I | 0 | 3 | 74 | 195 | 188 | 101 | 130 | 2 | 691
G2.13 | Number of water quality etc studies to inform future periods | No. | I | 0 | 12 | 74 | 134 | 43 | 24 | 75 | 0 | 362
G2.14 | 2010-15 outputs planned to complete in the 2015-21 period | No. | I | 0 | 2 | 4 | 2 | 5 | 4 | 1 | 4 | 18
Q&SIV Enhancements - Environment
G2.15 | Number of WWTWs improved to meet UWWTD | No. | I | 1 | 5 | 1 | 8 | 6 | 2 | 2 | 1 | 25
G2.16 | Number of waste water networks improved to meet UWWTD | No. | I | 0 | 4 | 13 | 5 | 7 | 9 | 7 | 13 | 45
G2.17 | Number of improvements required to meet UWWTD - Glasgow completion | No. | I | 0 | 24 | 12 | 15 | 10 | 8 | 10 | 6 | 79
G2.18 | Number of improvements required to meet the Water Framework Directive | No. | I | 0 | 1 | 0 | 0 | 1 | 1 | 5 | 23 | 8
G2.19 | Number of revised Bathing Waters Directive studies | No. | I | 0 | 0 | 0 | 8 | 0 | 2 | 1 | 0 | 11
G2.20 | Number of studies and catchments to meet the requirements of the Flood Risk Management Act | No. | I | 0 | 0 | 13 | 52 | 75 | 62 | 15 | 1 | 217
G2.21 | Number of environmental studies to inform future periods | No. | I | 0 | 0 | 5 | 28 | 33 | 46 | 16 | 2 | 128
G2.22 | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | I | 0 | 10 | 9 | 8 | 4 | 7 | 53 | 5 | 91
G2.23 | 2010-15 outputs planned to complete in the 2015-21 period | No. | I | 0 | 7 | 1 | 4 | 1 | 1 | 0 | 1 | 14
G2.24 | Number of improvements to dams to meet the requirements of the Flood Risk Management Act | No. | I | 0 | 6 | 4 | 7 | 19 | 9 | 9 | 0 | 54
Q&SIV Enhancements - Supporting Economic Development
G2.25 | Number of climate change vulnerability assessments | No. | I | 0 | 4 | 50 | 3 | 2 | 51 | 13 | 0 | 123
G2.26 | Improvements in renewable power and energy efficiency | Gwh | I | 0.52 | 0.423 | 7.051 | 2.6592 | 6.918 | 0 | 0 | 0 | 17.5712
Q&SIV Enhancements - Output Monitoring Group - Annual Measures
G2.27 | Number of lead communication pipes replaced | No. | I | 0 | 1343 | 1350 | 1169 | 1551 | 1458 | 0 | 0 | 6871
G2.28 | Assessment of levels of pressure for all customers and number of improvements if low levels of service are found | No. | I | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
G2.29 | Improve response times to reduce average duration of short term interruptions to supply | No. | I | 0 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
G2.30 | Number of water efficiency advice and water saving packs provided (to 2% of customer base) | No. | I | 0 | 0 | 233 | 6684 | 18362 | 18295 |  |  | 43574
G2.31 | Number of internal flooding improvements | No. | I | 0 | 47 | 39 | 54 | 101 | 62 |  |  | 303
G2.32 | Number of internal flooding improvements - completion programme | No. | I | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
G2.33 | Number of external flooding investigations and improvements | No. | I | 0 | 29 | 22 | 49 | 45 | 28 |  |  | 173
G2.34 | % of customers covered by flood resilience assessments | No. | I | 0 | n/a | 66.4% | 66.4% | 66.4% | 78.55% | TBC | TBC | TBC
G2.35 | Number of surface water management investigations | No. | I | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
G2.36 | Number of connections for new households and businesses | No. | I | 0 | 19803 | 22844 | 23914 | 24459 | 25213 |  |  | 116233
G2.37 | New water & waste water capacity for 73,290 people | No. | I | 0 | 1351 | 15469 | 3188 | 671 | 6651 | 35607 | 0 | 62937
G2.38 | Number of developer constructed assets (Part 2&3) adopted | No. | I | 0 | 25 | 416 | 838 | 834 | 1443 |  |  | 3556
G2.39 | Number of first time non domestic meters installed | No. | I | 0 | 4069 | 3313 | 2586 | 2825 | 2405 |  |  | 15198
G2.40 | Number of statutory requirements to relocate services for transport infrastructure projects | No. | I | 0 | 77 | 59 | 60 | 40 | 14 |  |  | 250
G2.41 | Improved contact management and proactive communication | No. | I | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
G2.42 | Number of wholesale meter accuracy improvements | No. | I | 0 | 7729 | 10441 | 13868 | 15562 | 17737 | 0 | 0 | 65337
G2.43 | Number of Strategic Mains Diversions | No. | I | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 4
Q&SIIIa & Q&SIIIb Delivery projects
G2.44 | Q&SIIIa projects remaining | No. | I | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
G2.45 | Q&SIIIb projects remaining | No. | I | 36 | 14 | 8 | 3 | 2 | 1 | 0 | 0
G2.46 | Q&S3b Km of Mains Rehabilitated remaining | Km | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G3 -Serviceability
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
SECTION G: INVESTMENT MONITORING
Table G3: Monitoring Serviceability
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 | 160 | 170
Line | Description | Units | Field | Ministerial Target 2015-21 | Baseline Delivery Plan Target Mar 2015 | Actual March 2015 | Delivery Plan Target Mar 2016 | Actual March 2016 | Delivery Plan Target Mar 2017 | Actual March 2017 | Delivery Plan Target Mar 2018 | Actual March 2018 | Delivery Plan Target Mar 2019 | Actual March 2019 | Delivery Plan Target Mar 2020 | Actual March 2020 | Delivery Plan Target Mar 2021 | Forecast March 2021 | Delivery Plan Target Post Mar 2021 | Forecast Post March 2021
Ref. |  |  | Type
Drinking Water Quality Indicators
G3.1 | Number of failing zones for iron | Nr | I | n/a | n/a | 16 | n/a | 21 | n/a | 18 | n/a | 25 | n/a | 29 | n/a | 21 | n/a
G3.2 | Number of failing zones for manganese | Nr | I | n/a | n/a | 14 | n/a | 11 | n/a | 7 | n/a | 9 | n/a | 15 | n/a | 10 | n/a
G3.3 | Number of microbiological failures at WTWs | Nr | I | n/a | 38 | 40 | n/a | 16 | n/a | 33 | n/a | 22 | n/a | 24 | n/a | 32 | n/a
G3.4 | Number of Customer Contacts relating to Taste | Nr | I | 5000 | n/a | 2671 | 5000 | 2691 | 5000 | 2526 | 5000 | 2503 | 5000 | 2224 | 5000 | 2027 | 5000
G3.5 | Number of Customer Contacts relating to Discolouration | Nr | I | 10000 | n/a | 9211 | 10000 | 6325 | 10000 | 5973 | 10000 | 4744 | 10000 | 6101 | 10000 | 7111 | 10000
Environment Serviceability Indicators
G3.6 | Number of failing WWTW | Nr | I | 5 | 18 | 3 | 5 | 6 | 5 | 4 | 5 | 0 | 5 | 2 | 5 | 3 | 5
G3.7 | Number of sludge treatment facilities improved to comply with safe sludge matrix | Nr | I | n/a | 2 | 2 | n/a | 8 | n/a | 8 | 8 | 9 | 8 | 11 | 8 | 11 | 8
G3.8 | Maximum number of UIDs | Nr | I | n/a | n/a | 791 | n/a | 761 | n/a | 738 | n/a | 720 | n/a | 704 | n/a | 686 | n/a
G3.9 | Number of pollution incidents | Nr | I | 330 | 548 | 249 | 330 | 260 | 330 | 239 | 330 | 193 | 330 | 227 | 330 | 229 | 330
G3.10 | Total number of Pollution incidents (sewerage) | Nr | I | n/a | n/a | 249 | 329 | 257 | 329 | 238 | 329 | 191 | 329 | 219 | 329 | 223 | 329
G3.11 | Serious pollution incidents (sewerage) Cat 1 & 2 | Nr | I | n/a | n/a | 8 | 13 | 10 | 13 | 12 | 13 | 5 | 13 | 9 | 13 | 5 | 13
G3.12 | Serious pollution incidents (water) Cat 1 | Nr | I | n/a | n/a | 1 | 1 | 3 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1
G3.13 | Discharge permit compliance | % | I | n/a | n/a | 99.49% | n/a | 98.98% | n/a | 99.32% | n/a | 100% | n/a | 99.67% | n/a | 99.5% | n/a
G3.14 | Satisfactory sludge disposal | % | I | 100% | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
G3.15a | Greenhouse gas (GHG) emissions (ktCO2e) | ktCO2e | I | n/a | n/a | 379* | n/a | 404* | n/a | 352 | n/a | 315 | n/a | 272 | n/a | 254 | n/a
G3.15b | Scope 1: All direct emissions (process,onsite combustion of fossil fuels and vehicles owned or leased) | tC02e | I | [12 empty] | 29
G3.15c | Scope 2: emissions associated with the production of the grid electricity used (Renewable export netted) | tC02e | I | [12 empty] | 109
G3.15d | Scope 3: indirect emissions, including business travel, outsourced activities (e.g. PFI) | tC02e | I | [12 empty] | 115
G3.15e | Carbon intensity ratios for water services (tonnes per Ml) | tC02e/ML | I | [12 empty] | 0.1
G3.15f | Carbon intensity ratios for wastewater services (tonnes per Ml) | tCO2e/ML | I | [12 empty] | 0.19
G3.15g | Renewable electricity generated | GWh | I | [12 empty] | 39.62
G3.15h | Renewable electricity exported | GWh | I | [12 empty] | 22.3
G3.15i | Renewable electricity used | GWh | I | [12 empty] | 16.4
G3.15j | Reduction in energy use from efficiency projects | GWh | I | [12 empty] | 6.3
G3.15k | Annual electricity usage (regulatory operational usage) | GWh | I | [12 empty] | 441.3
Customer Service Serviceability Indicators
G3.16 | Properties on the low pressure register | Nr | I | 100 | 240 | 46 | 100 | 47 | 100 | 45 | 100 | 45 | 100 | 51 | 100 | 37 | 100
G3.17 | Properties with unplanned interruptions to supply > 12 hrs | Nr | I | <1,000 | 684 | 563 | <1,000 | 716 | <1,000 | 648 | <1,000 | 552 | <1,000 | 357 | <1,000 | 302 | <1,000
G3.17a | Properties with unplanned interruptions to supply > 6 hrs | Nr | I | 13000 | n/a | n/a | 13000 | 6434 | 13000 | 6027 | 13000 | 6393 | 13000 | 4989 | 13000 | 5604 | 13000
G3.18 | Number of hours lost due to water supply interruptions for three hours or longer | Hrs/prop | I | n/a | n/a | 0.2763 | n/a | 0.26106 | n/a | 0.2607 | n/a | 0.386 | n/a | 0.391 | n/a | 0.3 | n/a
G3.19 | Bursts per 1,000km of mains | Nr | I | n/a | 188 | 160 | n/a | 140.2219 | n/a | 137.3576 | n/a | 157 | n/a | 172 | n/a | 150 | n/a
G3.20 | Properties at risk of internal sewer flooding | Nr | I | 370 | 341 | 302 | 370 | 334 | 370 | 315/381 | >370 | 373 | 370 | 307 | 370 | 281 | 370
G3.21 | Properties internally flooded due to other causes | Nr | I | n/a | 1270 | 367 | n/a | 389 | n/a | 328 | n/a | 346 | n/a | 369 | n/a | 341 | n/a
G3.22 | Properties internally flooded due to overloaded sewers | Nr | I | n/a | n/a | 54 | n/a | 95 | n/a | 121 | n/a | 63 | n/a | 129 | n/a | 131 | n/a
G3.23 | Incidents of internal sewer flooding for properties that have flooded within the last ten years | Nr | I | n/a | n/a | 156 | n/a | 243 | n/a | 241 | n/a | 202 | n/a | 125 | n/a | 119 | n/a
G3.24 | Properties at risk of external sewer flooding | Nr | I | <5,000 | n/a | 3708 | <5,000 | 3693 | <5,000 | 3699 | <5,000 | 3701 | <5,000 | 3698 | <5,000 | 3703 | <5,000
G3.25 | Incidents of external sewer flooding due to other causes | Nr | I | 13000 | n/a | 10768 | 13000 | 9981 | 13000 | 8565 | 13000 | 7498 | 13000 | 8169 | 13000 | 8921 | 13000
G3.26 | Incidents of external sewer flooding due to overloaded sewers | Nr | I | 400 | n/a | 227 | 400 | 349 | 400 | 159 | 400 | 120 | 400 | 116 | 400 | 407 | 400
G3.27 | The Overall Satisfaction level (from the customer service questionnaire) | % | I | n/a | >78% | 92% | n/a | 89.51% | n/a | 90.7% | n/a | 91.5% | n/a | 92.32% | n/a | 93.29% | n/a
G3.28 | The maximum number of 'second tier' complaints referred to Scottish Public Services Ombudsman | Nr | I | n/a | <121 | 4 | n/a | 1 | n/a | 2 | n/a | 3 | n/a | 0 | n/a | 1 | n/a
G3.29 | The number of telephone contacts relating to drinking water quality | Nr | I | n/a | <24,168 | 14150 | n/a | 11667 | n/a | 10563 | n/a | 9309 | n/a | 10193 | n/a | 10658 | n/a
G3.30 | The Overall Performance Assessment (OPA) Score (In Year Value) | Nr | I | 380-385 | 380 | 400 | 380 | 393 | 381 | 398.38 | 382 | 406 | 383 | 403 | 384 | 402 | 385
G3.31 | The Overall Performance Assessment (OPA) Score (Period Average) | Nr | I | 382.5 | n/a | 370 | 382.5 | 393 | 382.5 | 396.16 | 382.5 | 399 | 382.5 | 400 | 382.5 | 400 | 382.5
G3.32 | The average annual level of leakage | Ml/d | I | 575 | 600 | 543.993 | 575 | 499.63 | 575 | 494.7575 | 575 | 491.979 | 575 | 492 | 575 | 464.4 | 575
G3.33 | Household Customer Experience Measure (HCEM) | Nr | I | >82.60 | n/a | 82.6 | >82.60 | 84.32 | >82.60 | 85.88 | >82.60 | 86.36 | >82.60 | 87.54 | >82.60 | 88.02 | >82.60
G3.34 | Non-Household Customer Experience Measure (nHHCEM) | Nr | I | n/a | n/a | n/a | n/a | n/a | n/a | 83.92 | n/a | 77.5 | n/a | 81.74 | n/a | 85.19 | n/a
G3.35 | High Esteem Test | % | I | n/a | n/a | n/a | n/a | 78.6% | n/a | 76.4% | n/a | 76.4% | n/a | 78.1% | n/a | 77.6% | n/a
G3.36 | Wholesale Key Performance Indicator (KPI's) | % | I | 95% | 95% | 92% | 95% | 90.96% | 95% | 91.92% | 95% | 97.6% | 95% | 98.4% | 95% | 98.1% | 95%
Resilience of supply
G3.37 | Water Available for Supply Index: % of Population covered by 1:40 level of Service | % | I | n/a | n/a | 88.9% | n/a | 87.3% | n/a | 86.8% | n/a | 86.74% | n/a | 86.71% | n/a | 86.6% | n/a
G3.38 | Water Available for Supply Index: % of Population covered by 1:100 level of Service | % | I | n/a | n/a | 71.5% | n/a | 77.3% | n/a | 82.2% | n/a | 70.1% | n/a | 71.35% | n/a | 75.85% | n/a
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G4 - OMD Inputs
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
SECTION G: INVESTMENT MONITORING
Table G4: OMD Inputs including Q&SIIIa&b Project Sign-Offs
Q&SIV Enhancements - Drinking Water Quality - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.1 | Number of water treatment works improved | DW2, DW3B, DW3C, DW23, DW25, DW25P, DW25T | 30 | 1 | 11.9 | 1 | No. | I | 15 | 18 | 20 | 25 | 26 | 27 | 27 | 27 | 27 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
[6 empty] | 2 | Zones | I | 1 | 1 | 2 | 10 | 10 | 14 | 14 | 16 | 17 | 17 | 18 | 22 | 22 | 22 | 23 | 26 | 26 | 28 | 28 | 29 | 29 | 29 | 29 | 30 | 30
[6 empty] | 3 | Zones | I | 0 | 0 | 1 | 8 | 8 | 13 | 13 | 16 | 16 | 17 | 18 | 22 | 22 | 22 | 22 | 24 | 26 | 27 | 28 | 29 | 29 | 29 | 29 | 30 | 30
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 5 | 8 | 12 | 13 | 16 | 16 | 16 | 16 | 17 | 18 | 18 | 20 | 21 | 21 | 25 | 25
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 6 | 10 | 10 | 12 | 13 | 14 | 16 | 16 | 17 | 19 | 19
G4.2 | Number of zones made compliant with iron & manganese standards | DW5 | 82 | 2 | 6.9 | 1 | No. | I | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 65 | 65 | 65 | 72 | 72 | 72 | 72 | 72 | 72 | 81 | 82 | 82 | 82 | 82 | 82 | 82
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 23 | 28 | 39 | 39 | 51 | 51 | 56 | 56 | 57 | 62 | 64 | 64 | 67 | 70 | 70 | 80 | 80 | 81 | 81 | 81 | 82 | 82
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 1 | 20 | 27 | 36 | 50 | 51 | 56 | 56 | 57 | 62 | 64 | 64 | 67 | 70 | 70 | 79 | 79 | 79 | 81 | 81 | 81 | 81
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 14 | 20 | 30 | 42 | 45 | 49 | 55 | 58 | 60 | 60 | 64 | 64 | 64 | 65 | 78 | 78
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 10 | 10 | 17 | 38 | 41 | 47 | 47 | 57 | 58 | 60 | 64 | 64 | 64
G4.3 | Number of enhancements to improve reliability of supply (catchments and treatment) | WR1, DW25P | 54 | 3 | 5.9 | 1 | No. | I | 4 | 5 | 6 | 17 | 21 | 23 | 28 | 36 | 38 | 40 | 41 | 47 | 49 | 49 | 51 | 51 | 52 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 7 | 8 | 9 | 10 | 15 | 16 | 16 | 20 | 28 | 28 | 30 | 34 | 35 | 39 | 39 | 41 | 45 | 46 | 52 | 52 | 53 | 53
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 6 | 8 | 9 | 9 | 15 | 16 | 16 | 17 | 24 | 25 | 29 | 30 | 33 | 38 | 39 | 40 | 44 | 44 | 47 | 50 | 52 | 52
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 5 | 7 | 9 | 9 | 13 | 13 | 13 | 16 | 16 | 17 | 19 | 21 | 24 | 26 | 30 | 35 | 38 | 38
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 6 | 8 | 8 | 8 | 9 | 12 | 13 | 14 | 14 | 18 | 23 | 26 | 30 | 34 | 34
G4.4 | Number of enhancements to improve reliability of supply (networks and storage) | DW25D, DW25P, DW25T | 87 | 4 | 2.1 | 1 | No. | I | 1 | 4 | 14 | 28 | 29 | 41 | 42 | 61 | 61 | 61 | 61 | 85 | 85 | 86 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87
[6 empty] | 2 | Zones | I | 0 | 0 | 2 | 9 | 10 | 19 | 19 | 28 | 28 | 29 | 39 | 63 | 63 | 64 | 66 | 81 | 83 | 83 | 84 | 85 | 87 | 87 | 87 | 87 | 87
[6 empty] | 3 |  | I | 0 | 0 | 1 | 8 | 10 | 18 | 18 | 21 | 27 | 27 | 28 | 48 | 62 | 64 | 65 | 66 | 80 | 83 | 83 | 84 | 84 | 87 | 87 | 87 | 87
[6 empty] | 4 |  | I | 0 | 0 | 1 | 3 | 4 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 23 | 34 | 36 | 37 | 42 | 47 | 47 | 54 | 71 | 74 | 79 | 82 | 82
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 1 | 3 | 10 | 10 | 11 | 11 | 12 | 13 | 13 | 14 | 14 | 22 | 22 | 29 | 41 | 42 | 50 | 56 | 72 | 75 | 79 | 79
G4.5 | Distribution mains cleaned (km) | DW25D, DW25FS | 6658 | 5 | 5.8 | 1 | Km | I | 114.02 | 506.98 | 1499.85 | 2111.55 | 2329.65 | 3201.39 | 3529.23 | 3529.23 | 3529.23 | 3529.23 | 3529.23 | 3529.23 | 4447.8187 | 4576.8007 | 5871.8974 | 5931.8974 | 5931.8974 | 6490.3074 | 6490.3074 | 6658.1074 | 6658.1074 | 6658.1074 | 6658.1074 | 6658.1074 | 6658.1074
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 398.65 | 398.65 | 488.26 | 488.26 | 706.33 | 744.24 | 934.31 | 1590.93 | 1891.14 | 2635.64 | 3529.23 | 3778.73 | 3778.73 | 4576.8007 | 4786.3791 | 5931.8974 | 6490.3074 | 6490.3074 | 6490.3074 | 6490.3074 | 6658.1074 | 6658.1074
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 108.02 | 309.83 | 332.69 | 359.41 | 653.07 | 713 | 842.94 | 1025.55 | 1590.93 | 1912.72 | 2258.11 | 3374.24 | 3778.73 | 3778.73 | 5004.4855 | 5004.4855 | 6490.3074 | 6490.3074 | 6490.3074 | 6490.3074 | 6490.3074 | 6490.3074
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 153.13 | 291.75 | 300.63 | 522.94 | 561.08 | 621.4 | 658.37 | 1435.02 | 2191.32 | 2569.04 | 3283.608 | 3750.878 | 3754.578 | 3838.73 | 3988.3085 | 5169.5891 | 5169.5891
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.76 | 106.06 | 362.48 | 362.48 | 445.24 | 564.3 | 723.86 | 1125.51 | 1242.22 | 2144.67 | 2420.196 | 2656.366 | 3291.958 | 4206.758 | 4206.758
G4.6 | Water supply resilience strategy and improvements made | CS16WR | 19 | 6 | 7.5 | 1 | No. | I | 2 | 4 | 6 | 11 | 11 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
[6 empty] | 2 | Zones | I | 1 | 1 | 3 | 8 | 8 | 9 | 9 | 10 | 13 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 19 | 19 | 19 | 19
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 8 | 8 | 9 | 9 | 9 | 13 | 13 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 19 | 19 | 19 | 19
[6 empty] | 4 | Zones | I | 1 | 1 | 1 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | 17 | 17 | 17
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 17 | 17
G4.7 | Number of zones with improved security of supply (SOSI) | WG4 | 11 | 7 | 2.9 | 1 | No. | I | 2 | 2 | 3 | 5 | 5 | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 9 | 11 | 11
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 11 | 11
[6 empty] | 4 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
[6 empty] | 5 | Zones | I | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7
G4.8 | Number of security measures and improvements to the infrastructure of critical reservoirs | DW9A, DW9D, DW9F, DW9H | 693 | 8 | 4.6 | 1 | No. | I | 633 | 689 | 689 | 689 | 689 | 690 | 690 | 691 | 692 | 692 | 692 | 692 | 692 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693
[6 empty] | 2 | Zones | I | 30 | 86 | 86 | 292 | 292 | 292 | 292 | 323 | 324 | 447 | 447 | 575 | 575 | 576 | 692 | 692 | 692 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693
[6 empty] | 3 | Zones | I | 30 | 86 | 86 | 292 | 292 | 292 | 292 | 321 | 323 | 324 | 447 | 575 | 575 | 576 | 691 | 692 | 692 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 3 | 3 | 5 | 41 | 139 | 139 | 156 | 240 | 345 | 351 | 368 | 451 | 542 | 559 | 564 | 639 | 663 | 670 | 674 | 691 | 691 | 691
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 3 | 3 | 5 | 41 | 77 | 139 | 145 | 176 | 272 | 279 | 339 | 355 | 460 | 469 | 557 | 557 | 561 | 575 | 637 | 667 | 691 | 691
G4.9 | Number of water quality etc studies to inform future periods | CS16S, DW2_S, DW25PS, DW25TS, DW3C_S, | 362 | 18 | 1.7 | 1 | No. | I | 232 | 341 | 342 | 342 | 342 | 342 | 342 | 342 | 353 | 353 | 353 | 358 | 361 | 361 | 361 | 361 | 361 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
[6 empty] | 2 | Zones | I | 27 | 49 | 189 | 341 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 352 | 356 | 356 | 358 | 359 | 360 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
[6 empty] | 3 | Zones | I | 27 | 49 | 188 | 341 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 352 | 352 | 356 | 357 | 358 | 360 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 12 | 12 | 40 | 59 | 113 | 117 | 154 | 185 | 252 | 252 | 302 | 302 | 307 | 307 | 320 | 320 | 349 | 355 | 355 | 362 | 362 | 362
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 12 | 12 | 18 | 36 | 86 | 106 | 138 | 138 | 220 | 220 | 220 | 220 | 263 | 263 | 278 | 278 | 287 | 358 | 359 | 359 | 362 | 362
G4.10 | 2010-15 outputs planned to complete in the 2015-21 period | DW5, DW13, DW23, DW25 | 22 | 19 | 4.1 | 1 | No | I | 18 | 20 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 2 | Zones | I | 13 | 14 | 16 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 3 |  | I | 13 | 14 | 14 | 17 | 17 | 17 | 17 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 4 |  | I | 1 | 3 | 3 | 4 | 4 | 4 | 6 | 8 | 8 | 8 | 9 | 11 | 11 | 13 | 13 | 15 | 16 | 16 | 17 | 17 | 17 | 18 | 18 | 19 | 19
[6 empty] | 5 | Zones | I | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 13 | 13 | 15 | 16 | 17 | 17 | 17 | 18 | 18 | 18
Q&SIV Enhancements - Environment - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.11 | Number of WWTWs improved to meet UWWTD | EC01A, EC10A | 26 | 9 | 6.7 | 1 | No. | I | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 2 | Zones | I | 6 | 6 | 7 | 18 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 23 | 23 | 23 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 3 | Zones | I | 6 | 6 | 6 | 14 | 18 | 18 | 18 | 18 | 18 | 19 | 21 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26
[6 empty] | 4 | Zones | I | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 10 | 15 | 18 | 18 | 19 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 26 | 26
[6 empty] | 5 | Zones | I | 4 | 5 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 15 | 15 | 17 | 19 | 21 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 25 | 25
G4.12 | Number of waste water networks improved to meet UWWTD | CS11, EC01B,EC01C, EC01F, EC10B | 58 | 10 | 6.8 | 1 | No. | I | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 49 | 49 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58
[6 empty] | 2 | Zones | I | 1 | 8 | 14 | 28 | 28 | 28 | 30 | 31 | 32 | 34 | 35 | 35 | 40 | 40 | 44 | 45 | 45 | 45 | 46 | 55 | 55 | 55 | 58 | 58 | 58
[6 empty] | 3 | Zones | I | 1 | 6 | 10 | 19 | 28 | 28 | 28 | 31 | 31 | 33 | 34 | 35 | 35 | 40 | 42 | 44 | 44 | 44 | 44 | 54 | 54 | 54 | 58 | 58 | 58
[6 empty] | 4 | Zones | I | 0 | 2 | 4 | 7 | 7 | 13 | 17 | 17 | 18 | 20 | 21 | 23 | 23 | 25 | 25 | 29 | 29 | 38 | 38 | 38 | 42 | 43 | 45 | 49 | 49
[6 empty] | 5 | Zones | I | 0 | 0 | 4 | 4 | 7 | 7 | 7 | 17 | 17 | 17 | 19 | 22 | 23 | 23 | 25 | 29 | 29 | 29 | 36 | 38 | 42 | 42 | 43 | 45 | 45
G4.13 | Number of improvements required to meet UWWTD - Glasgow completion | EC01B, EC04B, EC10B | 85 | 20 | 15.7 | 1 | No. | I | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
[6 empty] | 2 | Zones | I | 38 | 38 | 38 | 56 | 56 | 60 | 63 | 63 | 64 | 65 | 67 | 69 | 70 | 71 | 72 | 78 | 78 | 80 | 81 | 85 | 85 | 85 | 85 | 85 | 85
[6 empty] | 3 | Zones | I | 31 | 37 | 37 | 47 | 51 | 53 | 58 | 62 | 62 | 64 | 66 | 68 | 70 | 70 | 70 | 73 | 74 | 76 | 77 | 84 | 84 | 84 | 85 | 85 | 85
[6 empty] | 4 | Zones | I | 3 | 8 | 23 | 27 | 27 | 29 | 32 | 37 | 43 | 46 | 52 | 53 | 56 | 57 | 58 | 64 | 65 | 66 | 67 | 71 | 71 | 71 | 76 | 81 | 81
[6 empty] | 5 | Zones | I | 0 | 6 | 7 | 24 | 25 | 25 | 29 | 36 | 36 | 41 | 43 | 51 | 51 | 52 | 56 | 61 | 62 | 65 | 65 | 69 | 71 | 71 | 72 | 79 | 79
G4.14 | Number of improvements required to meet the Water Framework Directive | EC10A, WR1, WR2A | 31 | 11 | 1.8 | 1 | No. | I | 12 | 12 | 12 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 23 | 23 | 23 | 26 | 27 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 15 | 15 | 21 | 21 | 21 | 21 | 26 | 27 | 28 | 29 | 30 | 30
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 21 | 21 | 21 | 21 | 22 | 22 | 26 | 26 | 27 | 27
[6 empty] | 4 | Zones | I | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 6 | 7 | 8 | 8
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 7 | 8 | 8
G4.15 | Number of revised Bathing Waters Directive studies | EC16, EC16A, EC16B | 11 | 12 | 1.2 | 1 | No. | I | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 9 | 9 | 9 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 10 | 10 | 10 | 10 | 11 | 11
G4.16 | Number of studies and catchments to meet the requirements of the Flood Risk Management Act | CS16D | 218 | 13 | 1.3 | 1 | No. | I | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 2 | Zones | I | 0 | 5 | 17 | 55 | 177 | 187 | 201 | 216 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 3 | Zones | I | 0 | 0 | 6 | 47 | 166 | 187 | 193 | 210 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 23 | 29 | 44 | 55 | 71 | 83 | 103 | 115 | 147 | 167 | 178 | 188 | 208 | 212 | 216 | 217 | 218 | 218
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 16 | 38 | 51 | 65 | 73 | 91 | 101 | 140 | 151 | 162 | 179 | 202 | 206 | 211 | 214 | 217 | 217
G4.17 | Number of environmental studies to inform future periods | EC01D, EC01G, EC06C, EC08C, EC10D, EC10E, EC10H, EC21, LA01_S, WR1A, WR2B | 130 | 14 | 2.8 | 1 | No. | I | 98 | 123 | 123 | 123 | 123 | 123 | 123 | 126 | 126 | 126 | 126 | 127 | 127 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 2 | Zones | I | 9 | 10 | 11 | 31 | 56 | 93 | 109 | 122 | 125 | 125 | 126 | 126 | 126 | 126 | 126 | 128 | 129 | 129 | 129 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 3 | Zones | I | 9 | 9 | 10 | 21 | 37 | 78 | 98 | 116 | 125 | 125 | 126 | 126 | 126 | 126 | 126 | 128 | 128 | 129 | 129 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 7 | 10 | 23 | 36 | 42 | 51 | 68 | 87 | 93 | 101 | 105 | 121 | 123 | 125 | 128 | 129 | 129
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 6 | 16 | 33 | 35 | 35 | 42 | 66 | 78 | 93 | 106 | 112 | 118 | 119 | 125 | 128 | 128
G4.18 | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | EC08A, EC23A, LA01, WQ01D, WQ01E | 96 | 15 | 2.5 | 1 | No. | I | 15 | 18 | 38 | 38 | 39 | 39 | 40 | 40 | 42 | 43 | 43 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96
[6 empty] | 2 | Zones | I | 9 | 10 | 11 | 12 | 21 | 26 | 27 | 29 | 29 | 36 | 36 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 94 | 95 | 95 | 95 | 95 | 95 | 95
[6 empty] | 3 | Zones | I | 9 | 10 | 11 | 12 | 21 | 25 | 26 | 28 | 29 | 36 | 36 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 94 | 94 | 95 | 95 | 95 | 95
[6 empty] | 4 | Zones | I | 6 | 7 | 10 | 11 | 11 | 11 | 11 | 20 | 21 | 22 | 27 | 28 | 29 | 29 | 31 | 31 | 35 | 35 | 35 | 38 | 38 | 42 | 68 | 93 | 93
[6 empty] | 5 | Zones | I | 4 | 5 | 6 | 10 | 10 | 10 | 10 | 19 | 19 | 20 | 22 | 27 | 28 | 28 | 29 | 31 | 31 | 31 | 31 | 38 | 38 | 38 | 42 | 91 | 91
G4.19 | 2010-15 outputs planned to complete in the 2015-21 period | EC16, WG4, WR1 | 15 | 21 | 3.3 | 1 | No. | I | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
[6 empty] | 2 | Zones | I | 8 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15
[6 empty] | 3 | Zones | I | 5 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15
[6 empty] | 4 | Zones | I | 0 | 0 | 1 | 7 | 7 | 8 | 8 | 10 | 10 | 10 | 10 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 7 | 7 | 7 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14
G4.20 | Number of improvements to dams to meet the requirements of the Flood Risk Management Act | WR6 | 54 | 26 | 0.6 | 1 | No. | I | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 2 | Zones | I | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 3 | Zones | I | 0 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 6 | 6 | 7 | 8 | 11 | 11 | 16 | 16 | 25 | 27 | 32 | 35 | 40 | 47 | 48 | 48 | 48 | 52 | 53 | 54 | 54 | 54
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 6 | 6 | 7 | 8 | 10 | 10 | 10 | 13 | 17 | 18 | 22 | 24 | 36 | 36 | 43 | 44 | 45 | 49 | 53 | 53 | 54 | 54
Q&SIV Enhancements -Supporting Economic Development - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.21 | Number of climate change vulnerability assessments | CC3S, CC4S, CC4W, CC5S, CC7S | 123 | 17 | 1.5 | 1 | No. | I | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 2 | Zones | I | 3 | 55 | 55 | 55 | 55 | 55 | 57 | 57 | 57 | 111 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 3 | Zones | I | 3 | 55 | 55 | 55 | 55 | 55 | 57 | 57 | 57 | 109 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 4 | 6 | 31 | 54 | 54 | 55 | 55 | 56 | 59 | 59 | 59 | 59 | 81 | 98 | 98 | 110 | 110 | 122 | 122 | 123 | 123 | 123
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 4 | 6 | 31 | 54 | 54 | 54 | 55 | 55 | 57 | 57 | 57 | 57 | 59 | 79 | 91 | 91 | 110 | 111 | 112 | 112 | 123 | 123
G4.22 | Improvements in renewable power and energy efficiency | I2S_WNI, I2S_WWNI | 17.5 | 16 | 2.5 | 1 | Gwh | I | 2.273 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 2 | Zones | I | 1.85 | 1.85 | 2.273 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 3 | Zones | I | 0.52 | 1.11 | 1.11 | 12.6042 | 12.6042 | 12.6042 | 12.6042 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 4 | Zones | I | 0.52 | 0.52 | 0.52 | 6.824 | 6.864 | 6.914 | 7.684 | 8.298 | 9.829 | 9.949 | 10.9747 | 11.8682 | 13.1612 | 13.3332 | 13.3332 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 5 | Zones | I | 0.52 | 0.52 | 0.52 | 0.943 | 0.943 | 0.943 | 0.943 | 7.994 | 9.829 | 9.829 | 10.4997 | 10.6532 | 12.6862 | 13.3332 | 13.3332 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G5 - Growth
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
SECTION G: INVESTMENT MONITORING
Table G5: Growth
|  |  |  | 10 |  | 20 |  | 30 |  | 40 |  | 50 |  | 60 | 70
Line | Line Title | Units | Field | Report Year |  | Report Year |  | Report Year |  | Report Year |  | Report Year |  | Forecast Year | Forecast Post
No. |  |  | Type
|  |  |  | 2015-16 |  | 2016-17 |  | 2017-18 |  | 2018-19 |  | 2019-20 |  | 2020-21 | 2021
Growth expenditure (gross)
G5.1 | Expenditure for reasonable cost contributions - household - water | £m | I | 8.2148 |  | 7.2236 |  | 6.6699 |  | 10.4821 |  | 6.4053 |  | 9.7799 | 0
G5.2 | Expenditure for reasonable cost contributions - non-household - water | £m | I | -0.016061 |  | -0.0053652 |  | 0.072344 |  | -0.03366 |  | -0.0088256 |  | 0.023565 | 0
G5.3 | Total expenditure on reasonable cost contributions - water | £m | C | 8.1987 |  | 7.2182 |  | 6.7422 |  | 10.4484 |  | 6.3965 |  | 9.8035 | 0
G5.4 | Expenditure for reasonable cost contributions - household - wastewater | £m | I | 8.6536 |  | 10.3839 |  | 9.8368 |  | 18.2287 |  | 9.988 |  | 14.0177 | 0
G5.5 | Expenditure for reasonable cost contributions - non-household - wastewater | £m | I | 0 |  | 0.045892 |  | 0.019743 |  | 0.00035978 |  | -0.001211 |  | -0.030993 | 0
G5.6 | Total expenditure on reasonable cost contributions - wastewater | £m | C | 8.6536 |  | 10.4298 |  | 9.8565 |  | 18.229 |  | 9.9867 |  | 13.9867 | 0
G5.7 | Total expenditure on reasonable cost Contributions - water and wastewater | £m | C | 16.8523 |  | 17.648 |  | 16.5987 |  | 28.6775 |  | 16.3832 |  | 23.7902 | 0
G5.8 | Expenditure on Part 3 strategic capacity - water | £m | I | 1.0214 |  | 1.982 |  | 4.8333 |  | 5.7422 |  | 10.7068 |  | 14.5048 | 0
G5.9 | Expenditure on Part 3 strategic capacity - wastewater | £m | I | 2.5455 |  | 4.131 |  | 6.4918 |  | 13.8471 |  | 11.5936 |  | 6.9255 | 0
G5.10 | Total expenditure on Part 3 strategic capacity - water and wastewater | £m | C | 3.5668 |  | 6.113 |  | 11.3251 |  | 19.5893 |  | 22.3003 |  | 21.4303 | 0
G5.11 | Expenditure on Part 4 assets - water | £m | I | 2.3788 |  | 5.1263 |  | 3.0026 |  | 3.5187 |  | 3.4683 |  | 8.7929 | 14.4125
G5.12 | Expenditure on Part 4 assets - wastewater | £m | I | 7.3503 |  | 6.0986 |  | 8.8089 |  | 22.6745 |  | 28.8732 |  | 17.4267 | 5
G5.13 | Total expenditure on Part 4 assets - water and wastewater | £m | C | 9.7291 |  | 11.2249 |  | 11.8115 |  | 26.1931 |  | 32.3415 |  | 26.2195 | 19.4125
G5.14 | Total gross expenditure on growth - (RCC + Part 3 strategic capacity + Part 4) | £m | C | 30.1483 |  | 34.9858 |  | 39.7354 |  | 74.4599 |  | 71.0251 |  | 71.44 | 19.4125
Service Relocations
G5.15 | Service Relocations Water | £m | I | 15.0386 |  | 12.4052 |  | 9.3689 |  | 7.7994 |  | 6.1906 |  | 4.8386 | 0
G5.16 | Service Relocations Wastewater | £m | I | 4.8054 |  | 4.9606 |  | 3.4735 |  | 1.8201 |  | 2.4883 |  | 6.8569 | 0
G5.17 | Service Relocations Water Contributions | £m | I | -10.7902 |  | -6.5168 |  | -7.3147 |  | -4.6331 |  | -5.9057 |  | -7.4625 | 0
G5.18 | Service Relocations Wastewater Contributions | £m | I | -5.5586 |  | -3.3571 |  | -3.7682 |  | -1.7827 |  | -3.0027 |  | -3.7077 | 0
G5.19 | Net Service Relocations | £m | C | 3.4952 |  | 7.4919 |  | 1.7595 |  | 3.2037 |  | -0.22941 |  | 0.52525 | 0
Growth income (Infrastructure charge)
G5.20 | Water household infrastructure charge income | £m | I | 6.5083 |  | 7.5061 |  | 8.0983 |  | 8.4815 |  | 8.8808 |  | 8.9049 | 0
G5.21 | Water non-household infrastructure charge income | £m | I | 0.18903 |  | 0.21293 |  | 0.053823 |  | 0.106 |  | 0.18323 |  | 0.1113 | 0
G5.22 | Wastewater household infrastructure charge income | £m | I | 5.0938 |  | 6.4276 |  | 7.3153 |  | 7.8088 |  | 8.4648 |  | 8.1926 | 0
G5.23 | Wastewater non-household infrastructure charge income | £m | I | 0.077305 |  | 0.057785 |  | 0.027592 |  | 0.017794 |  | 0.039702 |  | 0.018608 | 0
G5.24 | Total infrastructure charge income | £m | C | 11.8684 |  | 14.2044 |  | 15.495 |  | 16.4142 |  | 17.5685 |  | 17.2274 | 0
Growth expenditure (net of income)
G5.25 | Total net growth expenditure | £m | C | 21.7751 |  | 28.2733 |  | 25.9998 |  | 61.2495 |  | 53.2271 |  | 54.7378 | 19.4125
Growth - properties and populations
G5.26 | Number of new household properties connected to the water network | Nr | I | 19244 |  | 22214 |  | 23756 |  | 24157.029 |  | 24703 |  | 25363 | 0
G5.27 | Number of new non-household properties connected to the water network | Nr | I | 559 |  | 630 |  | 158 |  | 301.8949 |  | 510 |  | 317 | 0
G5.28 | Total number of new properties connected to the water network | Nr | C | 19803 |  | 22844 |  | 23914 |  | 24458.9239 |  | 25213 |  | 25680 | 0
G5.29 | Number of new household properties connected to the wastewater network | Nr | I | 15061 | 0.78263 | 19022 | 0.85631 | 21459 | 0.90331 | 22241.0463 | 0.92069 | 23546 | 0.95316 | 23333.96 | 0
G5.30 | Number of new non-household properties connected to the wastewater network | Nr | I | 229 |  | 171 |  | 81 |  | 50.6804 |  | 110 |  | 53 | 0
G5.31 | Total number of new properties connected to the wastewater network | Nr | C | 15290 |  | 19193 |  | 21540 |  | 22291.7268 |  | 23656 |  | 23386.96 | 0
G5.32 | Number of new household properties receiving reasonable cost contributions - water | Nr | I | 14393 |  | 15914 |  | 13807 |  | 14948.7873 |  | 11564 |  | 17656.4698 | 0
G5.33 | Number of new non-household properties receiving reasonable cost contributions - water | Nr | I | 0 |  | 0 |  | 150 |  | -78.3154 |  | 0 |  | 90 | 0
G5.34 | Total number of properties receiving reasonable cost contributions - water part 2 & 3 | Nr | C | 14393 |  | 15914 |  | 13957 |  | 14870.4719 |  | 11564 |  | 17746.4698 | 0
G5.35 | Number of new household properties receiving reasonable cost contributions - wastewater | Nr | I | 11211 |  | 12961 |  | 7469 |  | 12159.3207 |  | 10832 |  | 15202.3004 | 0
G5.36 | Number of new non-household properties receiving reasonable cost contributions - wastewater | Nr | I | 0 |  | 57 |  | 15 |  | 15.1585 |  | 0 |  | 695 | 0
G5.37 | Total number of properties receiving reasonable cost contributions - wastewater part 2 & 3 | Nr | C | 11211 |  | 13018 |  | 7484 |  | 12174.4791 |  | 10832 |  | 15897.3004 | 0
G5.38 | Number of household property infrastructure charge payments - water | Nr | I | 19244 |  | 22214 |  | 23756 |  | 24157.029 |  | 24703 |  | 25363 | 0
G5.39 | Number of non-household property infrastructure charge payments - water | Nr | I | 559 |  | 630 |  | 158 |  | 301.8949 |  | 510 |  | 317 | 0
G5.40 | Total number of infrastructure charge payments - water | Nr | C | 19803 |  | 22844 |  | 23914 |  | 24458.9239 |  | 25213 |  | 25680 | 0
G5.41 | Number of household property infrastructure charge payments - wastewater | Nr | I | 15061 |  | 19022 |  | 21459 |  | 22241.0463 |  | 23546 |  | 23333.96 | 0
G5.42 | Number of non-household property infrastructure charge payments - wastewater | Nr | I | 229 |  | 171 |  | 81 |  | 50.6804 |  | 110 |  | 53 | 0
G5.43 | Total number of property infrastructure charge - wastewater | Nr | C | 15290 |  | 19193 |  | 21540 |  | 22291.7268 |  | 23656 |  | 23386.96 | 0
G5.44 | Additional population equivalent served from new part 4 investment - water | Pe | I | 0 |  | 14677 |  | 0 |  | 0 |  | 0 |  | 1272 | 33000
G5.45 | Additional population equivalent served from new part 4 investment - wastewater | Pe | I | 1351 |  | 792 |  | 3188 |  | 671 |  | 6651 |  | 34335 | 0
Prepared by: …………………………………….……………………………….. |  |  | Date: ……………………
Checked by: …………………………….………………………………………….. |  |  | Date: ……………………
Authorised by:

## G6 - Project Analysis
SCOTTISH WATER
[12 empty] | Prepared by: …………………………………….……………………………….. |  |  |  | Date: ……………………
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
[12 empty] | Checked by: …………………………….………………………………………….. |  |  |  | Date: ……………………
SECTION G : INVESTMENT PLAN | [11 empty] | Authorised by: Mark Dickson
Table G6: Project Analysis - Actuals & Forecast - Water & Wastewater
[9 empty] | Include all projects with expenditure in the price control period | [5 empty] | Edition | 8
Regulatory Outputs
[55 empty] | OMG-01 | OMG-02 | OMG-03 | OMG-04 | OMG-05 | OMG-06 | OMG-07 | OMG-08 | OMG-09 | OMG-10 | OMG-11 | OMG-12 | OMG-13 | OMG-14 | OMG-15 | OMG-16 | OMG-17 | OMG-18 | OMG-19 | OMG-20 | OMG-21 | OMG-22 | OMG-23 | OMG-24 | OMG-25 | OMG-26 | OMG-27 | OMG-28 | OMG-29 | OMG-30 | OMG-31 | OMG-32 | OMG-33 | OMG-34 | OMG-35 | OMG-36 | OMG-37 | OMG-38 | OMG-39 | OMG-40 | OMG-41 | OMG-42 | OMG-43 | OMG-44 | OMG-45 | OMG-46 | OMG-47 | OMG-48 | OMG-49 | OMG-50
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105
Project Autocode | Project Title | Q&S Period (3b,4, IR18,5) | Programme Grouping (1) | Programme Grouping (2) | Programme Grouping (3) | Programme Grouping (4) | Water or wastewater project (primary purpose) | Technical Expression - Sign-off Owner | Accountability | Programme Grouping | Current Project Status Code | Forecast MS1 Date | Forecast MS2 Date | Forecast MS3 Date | Forecast MS4 Date | Forecast MS5 Date | Project location - Local Authority | Expenditure Pre 2015-16 | Actual Expenditure 2015-16 | Actual Expenditure 2016-17 | Actual Expenditure 2017-18 | Actual Expenditure 2018-19 | Forecast Expenditure 2019-20 | Forecast Expenditure 2020-21 | Total Q&SIV period expenditure to 2020-21 | Post 2020-21 expenditure | Project Grand Total expenditure | Table K Budget allocation | Grants for infrastructure assets | Grants for non-infrastructure assets | Contributions to infrastructure assets | Contributions to non-infrastructure assets | Impact of project on OPEX - additional operating expediture | Regulatory sign off required | Driver 1 | Driver 1 % allocation | Driver 2 | Driver 2 % allocation | Driver 3 | Driver 3 % allocation | Driver 4 | Driver 4 % allocation | Driver 5 | Driver 5 % allocation | Driver 6 | Driver 6 % allocation | Driver 7 | Driver 7 % allocation | Driver 8 | Driver 8 % allocation | Driver 9 | Driver 9 % allocation | Driver 10 | Driver 10 % allocation | Number of water treatment works made compliant with water quality standards | Number of water supply zones made compliant with iron and manganese standards | Water quality completion programme | Number of raw water catchments where reliability is improved | Number of enhancements to networks and treated water storage to improve reliability of supply | Length of distribution mains refurbished | Water supply resilience strategy and the number of improvements made. | Improvements to Drought Resilience | DWSP | Number of improvements required to meet SEMD requirements | Number of improvements to dams to meet the obligations of the FRMA | Number of lead communication pipes replaced | Number of improvements in the infrastructure of critical – reservoirs | Number of properties where low pressure issues are addressed’ | Average duration of short term interruptions in supply | Number of water efficiency advice and water saving packs provided (to 2% of customer base) | Number of improvements delivered to meet UWWTD: above ground works | Number of improvements delivered to meet UWWTD: below ground networks | Number of improvements delivered to meet UWWTD: Glasgow scheme | Number of improvements to meet the WFD | Number of improvements to meet the rBWD | Number of catchments improved to meet the Flood Risk Management Act (FRMA) | Number of studies to prepare for future investment periods | Number of Sludge Management sites investigated and / or improved | Develop a national strategy on the Priority Substances Directive | Number of improvements to meet the Habitats Directive | Number of improvements required under the Compliance Assessment Scheme | Number of improvements required by Scot. Gov’t to protect the water environment | Number of improvements required by SEPA and LAs to reduce odour nuisance | Number of properties removed from the internal flooding register | Number of internal flooding improvements - completion programme | Number of external flooding investigations and improvements | % of customers covered by flood resilience assessments | Number of surface water management investigations | Number of reasonable cost contributions made to connect new households and businesses - water | Number of RCC made to connect new households and businesses - waste water | Delivery of new waste water capacity for 58,000 people | Number of developer constructed assets (Part 2&3) adopted | Number of first time non domestic meters installed | Number of projects completed under statutory requirements to relocate services for transport infrastructure projects | Improved contact management and proactive communication | Number of wholesale meters | Renewable power generation | Reduction in energy usage | Number of vulnerability assessments and monitoring improvements to support Climate Change mitigation and reduction | Number of Research & Innovation projects completed | Number of water quality studies to prepare for future investment periods | OMG-48 (not used) | Strategic Mains Diversions | OMG-50 (not used)
500707 | (Longforgan) Station Road WWPS 1995 NO316293 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-06-12 | 2017-12-20 | 2018-03-29 | 2020-09-30 | 2020-09-30 | Perth and Kinross | 0 | 21000 | 32778 | 223222 | 470506 | 126307.08 | 29328.92 | 903142 | 2500 | 905642 | 0 |  |  |  |  | 1280 |  | CM_WWNI | 100%
503268 | 1 Waverley Road Dalkeith - Sewer Replacement | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-06-21 | 2028-01-14 | 2028-04-17 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 13971.73 | 13971.73 | 253028.3 | 267000.03 | 0 | [6 empty] | CM_WWI | 100%
501813 | 13 Carleton Cresent Glenrothes - Replace Pipe Bridge pipework | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-04-28 | 2018-03-14 | 2018-03-26 | 2018-06-29 | 2018-06-29 | Fife | 0 | 0 | 6606.12 | 25859.88 | 52613.32 | 0.68 | 0 | 85080 | 0 | 85080 | 0 | [6 empty] | CM_WWI | 100%
500058 | 152 to 158 Busby Road Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-11-30 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | East Renfrewshire | 192.99 | 34807.01 | 3000 | 4000 | 164.1 | 0 | 835.9 | 42807.01 | 0 | 43000 | 120964.87 | [6 empty] | CS15A | 100%
503367 | 1989-1 - Plumtree Place Galashiels | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-11-23 | 2021-09-23 | 2021-12-10 | 2022-08-24 | 2022-11-24 | Scottish Borders | 0 | 0 | 0 | 0 | 46000 | 51045.73 | 34190.31 | 131236.04 | 168763.96 | 300000 | 196097.17 | [6 empty] | CS11A | 100%
503392 | 1990-1 - Rinkvale Cottages Hawick | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2021-12-08 | 2022-03-24 | 2022-12-06 | 2023-03-08 | Scottish Borders | 0 | 0 | 0 | 0 | 46000 | 45675.72 | 49832.28 | 141508 | 158492 | 300000 | 196097.17 | [6 empty] | CS11A | 100%
401087 | 2010- 2015 Asset Disposals (Finance) | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | [5 empty] | Scottish Water Wide | 13710.93 | -1703.83 | 0 | 83.18 | 1949.4 | 49.17 | -2088.85 | -1710.93 | 0 | 12000 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
503523 | 2019 Generator Replacement (Energy Programme) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-05-07 | 2019-05-07 | 2020-02-25 | 2020-12-01 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 131720 | 168280 | 300000 | 0 | 300000 | 0 | [6 empty] | CM_WSNI | 100%
503524 | 2019 Small Value Capital Maintenance Works (Energy Programme) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-04-04 | 2019-04-04 | 2020-08-25 | 2021-02-23 | 2021-03-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 50364 | 54636 | 105000 | 0 | 105000 | 0 | [6 empty] | CM_WSNI | 100%
503770 | 218-2- Mossbeath Crescent Uddingston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-07-28 | 2022-06-28 | 2022-09-15 | 2023-04-19 | 2023-06-12 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 55805.39 | 76336.89 | 132142.28 | 167857.72 | 300000 | 196097.17 | [6 empty] | CS11A | 100%
500928 | 248 Sauchie Road Crieff | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2015-10-26 | 2016-07-15 | 2020-07-31 | 2020-12-17 | 2020-12-18 | Perth and Kinross | 0 | 8367.68 | 58778.32 | 52031.1 | 111037.1 | 74785.79 | 2792000 | 3096999.99 | 0 | 3096999.99 | 317062.04 | [6 empty] | CS15A | 50% | CS11A | 50%
503467 | 35 Montrose Street Clydebank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2019-04-02 | 2019-04-02 | 2019-06-03 | 2019-09-04 | 2019-09-04 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 361861.15 | 0 | 361861.15 | 0 | 361861.15 | 0 | [6 empty] | CM_WWI | 100%
501582 | 49 Ardrossan Road Saltcoats Connection Realignment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-05-04 | 2017-09-29 | 2018-01-22 | 2018-03-26 | 2018-03-26 | North Ayrshire | 0 | 0 | 74411 | 185822 | 14767 | 0 | 0 | 275000 | 0 | 275000 | 0 | [6 empty] | CM_WWI | 100%
501435 | 500100 - Balmore WTW - Network Risk | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-04-01 | 2016-07-25 | 2016-07-26 | 2016-09-30 | 2016-09-30 | East Dunbartonshire | 0 | 0 | 776.72 | 0 | 0 | 0 | 0.28 | 777 | 0 | 777 | 822776.29 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501440 | 500109 - Corrie WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2017-03-01 | 2017-03-02 | 2017-03-31 | 2017-03-31 | North Ayrshire | 0 | 0 | 930.57 | 268.83 | 0 | 0 | 0 | 1199.4 | 0 | 1199.4 | 438946.64 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501418 | 500122 - Ness WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2017-04-28 | 2018-12-10 | 2018-12-18 | 2021-06-30 | 2021-08-31 | Na H-Eileanan an Iar | 0 | 0 | 96266.67 | 469886.82 | 573399.93 | 2873739.62 | 2640840 | 6654133.04 | 60578.98 | 6714712.02 | 1020606.26 |  |  |  |  | 12500 |  | DW25P | 100% | bar: Regulatory Outputs OMG-04
501436 | 500788 - Alexandria WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2021-05-31 | 2021-06-30 | West Dunbartonshire | 0 | 0 | 20408.28 | 1704.25 | 7688.77 | 320.28 | -320.28 | 29801.3 | 0 | 29801.3 | 501784.73 | [6 empty] | CM_WSNI | 16.11% | DW25P | 83.89% | bar: Regulatory Outputs OMG-04
501421 | 500793 - Carrick Castle WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-03-08 | 2019-06-26 | 2019-06-26 | 2020-12-31 | 2021-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 514.26 | 140.03 | 2192.4 | -1023.12 | 1823.57 | 0 | 1823.57 | 141622.2 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501419 | 500799 - Sewer flooding Customer Risk Assessment | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWD | Flood Assessments | MS3 | 2017-03-03 | 2019-07-31 | 2019-09-16 | 2021-04-23 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 135738.62 | 266210.21 | 235051.17 | 307238.27 | 193243.76 | 1137482.03 | 5704.96 | 1143186.99 | 980565.38 | [6 empty] | CS15E | 100%
501439 | 500902 - Improving resilience of supplies - Newmore | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2017-01-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 2197.89 | 0 | 0 | 0 | 0 | 2197.89 | 0 | 2197.89 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
501791 | 501121 - Service Relocations Water | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MSU | 2021-04-15 |  |  | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3204033.63 | 3204033.63 | 0 | 3204033.63 | 0 |  |  | 42623051.76 |  |  |  | CS23W | 100%
501796 | 501122 - Service Relocations Wastewater | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MSU | 2021-04-15 |  |  | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4317662.61 | 4317662.61 | 0 | 4317662.61 | 2614273.27 |  |  | 21176948.24 |  |  |  | CS23S | 100%
501806 | 501143 - Sewer Catchment Modelling to Develop External Flooding Needs - Solutions | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-09-28 | 2022-03-14 | 2022-07-15 | 2023-10-12 | 2024-01-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 34005.36 | 34005.36 | 2338493.62 | 2372498.98 | 120964.87 | [6 empty] | CS15A | 100%
501805 | 501144 - Sewer Catchment Modelling to Develop Internal Flooding Needs - Solutions | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-09-28 | 2022-03-14 | 2022-07-15 | 2023-10-12 | 2024-01-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 34005.36 | 34005.36 | 2338493.62 | 2372498.98 | 9297166.67 | [6 empty] | CS11A | 100%
502046 | 50531 UID Lyle Road PS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2013-02-02 | 2017-01-26 | 2017-03-21 | 2017-09-30 | 2018-01-31 | North Lanarkshire | 0 | 65.42 | 9690.21 | 31906.51 | 0.01 | 0 | 1000 | 42662.15 | 0 | 42662.15 | 42442.63 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
503584 | 59052 - Event and Duration Monitoring Phase 1 - East | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-08-29 | 2021-07-15 | 2021-11-22 | 2022-09-09 | 2022-12-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 50890 | 102427.05 | 153317.05 | 573682.93 | 726999.98 | 284605.17 | [6 empty] | CS29 | 100%
503583 | 59052 - Event and Duration Monitoring Phase 1 - North | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-08-27 | 2020-12-14 | 2021-03-29 | 2021-10-18 | 2021-12-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 7863.39 | 123397 | 131260.39 | 155739.57 | 286999.96 | 284605.17 | [6 empty] | CS29 | 100%
503585 | 59052 - Event and Duration Monitoring Phase 1 - South | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-08-27 | 2021-04-30 | 2021-08-19 | 2022-02-22 | 2022-05-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 11387.42 | 58147.58 | 69535 | 81464.99 | 150999.99 | 284605.17 | [6 empty] | CS29 | 100%
503339 | 671-2 - Bridgend Stewarton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-06-23 | 2021-06-11 | 2021-08-26 | 2022-03-29 | 2022-06-29 | East Ayrshire | 0 | 0 | 0 | 0 | 20000 | 59637.65 | 62532.37 | 142170.02 | 157829.96 | 299999.98 | 196097.17 | [6 empty] | CS11A | 100%
503428 | 719-1 Queen Street Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-22 | 2021-12-27 | 2022-04-28 | 2022-12-21 | 2023-03-23 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 45000 | 90000 | 20990.28 | 155990.28 | 1044009.69 | 1199999.97 | 196097.17 | [6 empty] | CS11A | 100%
503398 | 719-2 Noblehill Place Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-09-22 | 2021-09-20 | 2021-12-20 | 2022-08-12 | 2022-11-14 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 49000 | 59354.72 | 59251.01 | 167605.73 | 732394.27 | 900000 | 196097.17 | [6 empty] | CS11A | 100%
503604 | 719-3 Bellevue Street Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-09-17 | 2021-08-24 | 2021-11-11 | 2022-07-06 | 2022-08-29 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 42683.47 | 3681.53 | 46365 | 28635.07 | 75000.07 | 196097.17 | [6 empty] | CS11A | 100%
502809 | 722131 Leny Street Glasgow g20 7sh Developer payment | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2017-07-10 | 2017-07-10 | 2017-11-21 | 2017-12-04 | 2017-12-04 | Glasgow City | 0 | 0 | 0 | 239291.31 | 0 | 0 | 0 | 239291.31 | 0 | 239291.31 | 470181.23 | [6 empty] | WG5 | 100%
503335 | A76 New Cumnock Wall Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-20 | 2018-10-25 | 2018-10-25 | 2019-01-22 | 2019-01-22 | Renfrewshire | 0 | 0 | 0 | 0 | 105333 | 37935.02 | 0 | 143268.02 | 0 | 143268.02 | 43684.09 | [6 empty] | CS23W | 100%
403650 | A96 Corridor - Foul Drainage | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2014-02-03 | 2014-03-24 | 2014-03-24 | 2019-02-20 | 2019-02-20 | Highland | 1400000 | 0 | -426630.55 | 1251663.32 | 5737181.62 | 0 | 0 | 6562214.39 | 0 | 7962214.39 | 0 |  |  |  |  | 17705 |  | SG5 | 100%
402736 | Aberargie WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-06-11 | 2013-05-16 | 2013-10-28 | 2014-02-26 | 2014-02-26 | Perth and Kinross | 205340.87 | 3635 | 181.62 | 41.37 | 0 | 0 | 0 | 3857.99 | 0 | 209198.86 | 0 | [6 empty] | SG1 | 100%
401379 | Aberchirder South Street - Sewer Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-09-24 | 2012-10-29 | 2015-01-19 | 2015-03-13 | 2015-03-13 | Aberdeenshire | 50142 | -46590.69 | 0 | 0 | 0 | 0 | 0 | -46590.69 | 0 | 3551.31 | 196097.17 | [6 empty] | CS11 | 100%
403781 | Aberchirder WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-01-10 | 2019-06-28 | 2019-09-30 | 2021-07-20 | 2021-07-20 | Aberdeenshire | 11188 | 26952.58 | 6246.1 | 5733.84 | 144320.68 | 253261.87 | 875616.13 | 1312131.2 | 46966.67 | 1370285.87 | 0 |  |  |  |  | 5570 |  | SG1 | 100%
503203 | Aberdeen- Aberdeenshire WW Growth Strategic Study | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-08-19 | 2023-11-23 | 2024-03-21 | 2024-11-06 | 2025-02-06 | Aberdeen City | 0 | 0 | 0 | 0 | 322752.25 | 162386.94 | 131451.32 | 616590.51 | 124939.01 | 741529.52 | 136478.56 | [6 empty] | SG1 | 100%
403478 | Aberdeen Area Water Network Model | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-07-02 | 2013-10-21 | 2013-10-21 | 2014-12-18 | 2015-01-21 | Aberdeenshire | 428744 | -10603.49 | 0 | 0 | 0 | 0 | 0 | -10603.49 | 0 | 418140.51 | 0 | [6 empty] | WG5 | 100%
403788 | Aberdeen Greenwell Road (International Base) Sewer Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-10-21 | 2014-11-21 | 2015-01-14 | 2015-07-21 |  | Aberdeen City | 105136 | 4169 | 1430.86 | -1974.49 | 0 | 0 | 0 | 3625.37 | 0 | 108761.37 | 0 | [6 empty] | CM_WWI | 100%
402477 | Aberdeen Integrated Catchment Study (Nigg and Persley Sewer Catchment Areas) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-02-20 | 2013-02-20 | 2015-03-26 | 2015-03-30 | Scottish Water Wide | 1447201 | 121043 | -25526.68 | 15675.73 | 0 | 0 | 0 | 111192.05 | 0 | 1558393.05 | 102155 | [6 empty] | CS16S | 100%
46262 | Aberdeen Mannofield No1 TWP Refurb - TWP000443 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-03 | 2010-09-27 | 2013-01-21 | 2013-07-31 |  | Aberdeen City | 742687.29 | -30786.58 | 0 | 0 | 0 | 0 | 4450.04 | -26336.54 | 0 | 716350.75 | 0 | [6 empty] | CM_WSNI | 100%
501094 | Aberdeen Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2015-09-30 | 2016-07-20 | 2016-07-25 | 2019-03-31 | 2019-12-31 | Aberdeen City | 0 | 4738 | 79992.21 | 13869.79 | 21400 | 1348.29 | 6151.71 | 127500 | 0 | 127500 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
500814 | Aberdeenshire and Aberdeen City Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-13 | 2015-12-11 | 2015-12-11 | 2018-02-01 | 2018-02-01 | Aberdeenshire | 0 | 49031.93 | 1973.87 | -7925.99 | 0 | 0 | 0.01 | 43079.82 | 0 | 43079.82 | 120964.87 | [6 empty] | CS15A | 100%
501095 | Aberdeenshire Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-09-26 | 2016-09-28 | 2019-03-31 | 2019-12-31 | Aberdeenshire | 0 | 3730 | 45232.36 | 20237.64 | 24800 | 10083.46 | -583.46 | 103500 | 0 | 103500 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
402969 | Aberfoyle Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-26 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Stirling | 37520 | 363.29 | 0 | 0 | 0 | 0 | 0 | 363.29 | 0 | 37883.29 | 0 | [6 empty] | CM_WSI | 100%
503078 | Aberfoyle SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-01-15 | 2019-01-15 | Stirling | 0 | 0 | 0 | 8884.13 | 6769.84 | 0 | 0.03 | 15654 | 0 | 15654 | 0 | [6 empty] | CM_WWI | 100%
500916 | Aberfoyle Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-09-28 | 2018-03-22 | 2018-03-27 | 2020-03-31 | 2019-06-28 | Stirling | 0 | 10485 | 67740.26 | 145567.74 | 714755.29 | 291960.36 | 0 | 1230508.65 | 0 | 1230508.65 | 0 | [6 empty] | CM_WSI | 100%
500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-26 | 2019-05-17 | Moray | 0 | 8751 | 15597 | 27193 | 22659 | 8434 | 0 | 82634 | 0 | 82634 | 16944.76 | [6 empty] | EC01G | 22.69% | CS16D | 37.97% | EC01D | 39.33%
400946 | Aberlour High Street - Internal Flooding Programme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-05-31 | 2013-09-12 | 2013-09-30 | 2014-08-08 | 2014-03-31 | Moray | 1811330 | 1376.14 | -12031.84 | 7328.87 | 0 | 0 | 731.49 | -2595.34 | 0 | 1808734.66 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
45537 | Abington STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-23 | 2011-10-12 | 2012-08-30 | 2012-11-26 | South Lanarkshire | 764146.75 | 38434.37 | 0 | 0 | 0 | 0 | 0 | 38434.37 | 0 | 802581.12 | 0 | [6 empty] | WQ01 | 100%
400092 | Aboyne (Tanarside) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-11-04 | 2011-03-29 | 2011-07-18 | 2012-06-25 | 2012-09-25 | Aberdeenshire | 1620884.6 | -1887.58 | 0 | 0 | -3702.6 | 0 | 3096.61 | -2493.57 | 0 | 1618391.03 | 0 | [6 empty] | DW23 | 100%
502958 | Aboyne WwTW - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2017-11-29 | 2020-10-19 | 2021-01-25 | 2021-11-29 | 2021-11-29 | Aberdeenshire | 0 | 0 | 0 | 28353.13 | 26629.88 | 112841.94 | 651064.84 | 818889.79 | 450885.75 | 1269775.54 | 0 | [6 empty] | CM_WWNI | 100%
500722 | Aboyne WWTW CM | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-24 | 2018-08-24 | 2018-08-23 | 2018-08-23 | 2018-08-23 | Aberdeenshire | 0 | 36204 | 34571.42 | 16338.91 | 860.16 | 0 | -634.6 | 87339.89 | 0 | 87339.89 | 136478.56 | [6 empty] | SG1 | 100%
503100 | ABV Incentivisation Actual | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2018-07-09 | 2018-07-09 | 2020-03-24 |  | 2022-11-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 95356.2 | -756228.17 | 2558520.77 | 1897648.8 | 3102351.2 | 5000000 | 249897794.16 | [6 empty] | SR15_RSK_EHR | 9.369e-11% | SR15_CMA_MAG | 0.03513% | SR15_CMA_WSNI | 0.2861% | SR15_SED_INFC | 0.4283% | SR15_ENV_WFD | 0.5862% | SR15_SED_SCAP | 1.322% | SR15_ENV_UWWD | 1.612% | SR15_ENV_ENVS | 1.63% | SR15_ENV_RBWD | 1.741% | SR15_CMP_LATE | 1.818%
502227 | AC Water Mains Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2016-05-12 | 2016-09-15 | 2016-10-21 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 0 | 33697.12 | 9185.86 | -829.11 | 0 | -652.6 | 41401.27 | 0 | 41401.27 | 0 | [6 empty] | CM_M&G | 100%
500673 | Access to SW Systems | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-03 | 2017-03-16 | 2017-03-16 | 2017-01-16 |  | Scottish Water Wide | 0 | 60205.5 | 83.72 | 0 | 0 | 0 | 0 | 60289.22 | 0 | 60289.22 | 0 | [6 empty] | CM_M&G | 100%
501059 | Acharacle WTW GAC Units | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-10-08 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | Highland | 0 | 1689.39 | 0 | 0 | 0 | 0 | 0 | 1689.39 | 0 | 1689.39 | 0 | [6 empty] | CM_WSNI | 100%
502845 | Achiltibuie WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 20930.23 | 956.55 | -21463.56 | 0 | 423.22 | 0 | 423.22 | 136478.56 | [6 empty] | WG1 | 100%
45300 | Achmore WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-03-01 | 2011-08-15 | 2012-07-03 | 2012-09-24 | Highland | 1496054.78 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 1496124.78 | 0 | [6 empty] | DW23 | 100%
403590 | Addition of Dunbar East BW Culverted Watercourse Investigation | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-27 | 2014-05-23 | 2014-06-02 | 2014-12-19 | 2015-03-27 | East Lothian | 55258 | -18430.19 | 0 | 0 | 0 | 0 | 0 | -18430.19 | 0 | 36827.81 | 0 | [6 empty] | EC16 | 100%
403592 | Addition of Fisherrow Sands Bathing Water Study | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-27 | 2014-09-30 | 2014-09-30 | 2016-09-30 | 2016-10-31 | City of Edinburgh | 231036 | 159888 | 62253.21 | 6233.45 | -6233.45 | 0 | 0 | 222141.21 | 0 | 453177.21 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
402688 | Additional Security requirements at 3 regraded water assets | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-11-19 | 2016-02-02 | 2015-04-14 | 2015-04-14 | 2015-04-14 | Scottish Water Wide | 149291.88 | -11135.82 | 0 | 0 | 0 | 0 | 0 | -11135.82 | 0 | 138156.06 | 0 | [6 empty] | DW9A | 100%
500791 | Additional Water Quality Sampling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-10-30 | 2015-10-30 | 2016-05-06 | 2018-04-11 | 2018-04-11 | Scottish Water Wide | 0 | 8028 | 0 | 0 | -7992.86 | 0 | 0 | 35.14 | 0 | 35.14 | 0 | [6 empty] | CM_WSNI | 100%
403916 | Address Update | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2014-09-03 | 2015-02-16 | 2015-02-18 | 2015-10-15 | 2015-10-15 | Scottish Water Wide | 335925 | 139459.14 | 7022.5 | 0 | 0 | 0 | -4943.84 | 141537.8 | 0 | 477462.8 | 152726 | [6 empty] | CS20 | 100%
402506 | Adpro Security Equipment Replacement - Bradan Dam Comms. link replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-06 | 2012-09-24 | 2013-11-25 | 2016-12-01 |  | Scottish Water Wide | 29728.86 | 4683.4 | -15513.26 | 0 | 0 | 0 | 0 | -10829.86 | 0 | 18899 | 0 | [6 empty] | CM_WSNI | 100%
404110 | ADPRO Security Video Handling System Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-24 | 2015-06-10 | 2015-09-07 | 2017-01-20 | 2017-01-20 | Scottish Water Wide | 0 | 233134 | 12140 | 0 | -709.46 | 0 | 0 | 244564.54 | 0 | 244564.54 | 0 | [6 empty] | CM_WSNI | 100%
402462 | Advanced Scheduler Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-20 | 2013-01-22 | 2013-01-22 | 2016-02-17 |  | Scottish Water Wide | 1652053 | 57744.73 | 0 | 0 | 0 | 0 | 0 | 57744.73 | 0 | 1709797.73 | 0 | [6 empty] | CM_M&G | 100%
403657 | Afaria Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-01-10 | 2014-01-10 | 2014-01-10 | 2015-02-09 |  | Scottish Water Wide | 256705 | 6426.06 | 0 | 0 | 0 | 0 | 0 | 6426.06 | 0 | 263131.06 | 0 | [6 empty] | CM_M&G | 100%
34813 | Afton Bradan Penwhapple WRZ-WFD Compliance | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-15 | 2012-09-25 | 2012-11-01 | 2013-03-18 | 2013-03-18 | Scottish Water Wide | 484317 | 4453.16 | 361.52 | 0 | 0 | 0 | 0 | 4814.68 | 0 | 489131.68 | 706365 | [6 empty] | WR1 | 100%
501273 | Afton Lorg Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | East Ayrshire | 0 | 0 | 12014.76 | 7849.5 | 17327.94 | -27706.37 | -9484.83 | 1 | 0 | 1 | 0 | [6 empty] | I2S_WI | 100%
46242 | Afton Reservoir - Repairs to Bridge and Valvetower | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-01-08 | 2010-11-22 | 2011-03-31 | 2014-03-28 | 2014-03-28 | East Ayrshire | 1191831.77 | -555.3 | 0 | 0 | 0 | 0 | 0 | -555.3 | 0 | 1191276.47 | 0 | [6 empty] | CM_WSI | 100%
501274 | Afton Scottish Power OHL | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS4 | 2021-02-05 | 2021-02-11 | 2021-03-25 | 2019-12-17 | 2021-03-29 | East Ayrshire | 0 | 0 | 19382.03 | 20968.07 | 9569.12 | 43.06 | -49961.28 | 1 | 0 | 1 | 0 | [6 empty] | I2S_WI | 100%
501278 | Afton Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2020-07-22 | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-07-23 | East Ayrshire | 0 | 0 | 120635.21 | 68964.99 | -104358.88 | -32566.06 | -52674.26 | 1 | 0 | 1 | 0 | [6 empty] | I2S_WI | 100%
402951 | Afton WTW - SCADA - PLC Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-09-28 | 2013-10-22 | 2013-11-18 | 2014-10-27 |  | East Ayrshire | 263017 | 24 | 251.96 | 0 | 0 | 0 | 0 | 275.96 | 0 | 263292.96 | 0 | [6 empty] | CM_WSNI | 100%
502651 | Afton WTW_Ayrshire_THM Research and Investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-02-21 | 2019-12-10 | 2020-03-18 | 2021-11-30 | 2022-02-28 | South Ayrshire | 0 | 0 | 0 | 8155.11 | 73764.1 | 316404.8 | 611037.87 | 1009361.88 | 270164.13 | 1279526.01 | 279835.22 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500650 | Agile Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-08-19 | 2016-08-29 | 2016-08-29 | 2018-06-14 | 2018-06-14 | Scottish Water Wide | 0 | 283087 | 660952.64 | 621341.6 | -18146.91 | 0 | 0.01 | 1547234.34 | 0 | 1547234.34 | 0 | [6 empty] | CM_M&G | 100%
402658 | Agile Working | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-05-31 | 2014-05-19 | 2014-05-19 | 2014-03-20 |  | Scottish Water Wide | 1712711.83 | 506.26 | 0 | 0 | 0 | 0 | 0 | 506.26 | 0 | 1713218.09 | 0 | [6 empty] | CM_M&G | 100%
502710 | Aiginis Knock Lewis Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | Na H-Eileanan an Iar | 0 | 0 | 0 | 2607.67 | 0 | 0 | 0.33 | 2608 | 0 | 2608 | 0 | [6 empty] | CM_WWI | 100%
45810 | Aird Tong SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-03-21 | 2014-02-03 | 2014-03-31 | 2014-03-31 | Na H-Eileanan an Iar | 1262685.36 | -18435.15 | 0 | 0 | 0 | 0 | 0 | -18435.15 | 0 | 1244250.21 | 7894 | [6 empty] | WQ01C | 100%
502378 | Airth DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-12-23 | 2028-01-12 | 2028-02-15 | 2028-07-13 | 2028-10-13 | Falkirk | 0 | 0 | 3082.93 | 8720.43 | 8319.69 | 4381.04 | 0 | 24504.09 | 479281.29 | 503785.38 | 0 | [6 empty] | CM_WSNI | 100%
30009 | Airth STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-08 | 2012-01-09 | 2012-03-20 | 2013-07-15 | 2013-10-09 | Falkirk | 2021289.87 | 1874.96 | 0 | 0 | 0 | 0 | 0 | 1874.96 | 0 | 2023164.83 | 141140.1 | [6 empty] | CM_WWNI | 5% | SG1 | 15% | EC01A | 80%
502874 | Albany Terrace Perth | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-12-20 | 2018-10-25 | 2018-12-12 | 2019-01-31 | 2019-01-31 | Perth and Kinross | 0 | 0 | 0 | 13775.94 | 68915.06 | 2843.18 | 541.82 | 86076 | 0 | 86076 | 0 | [6 empty] | CM_WWI | 100%
500204 | Albert Rd WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-05-01 | 2017-04-28 | 2017-05-02 | 2018-03-06 | 2018-03-06 | City of Edinburgh | 0 | 205000 | 331514 | 1494098 | -5095.88 | -18705.8 | 0 | 2006810.32 | 0 | 2006810.32 | 0 | [6 empty] | CM_WWNI | 100%
503433 | Alemoor Drawdown Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-10-04 | 2021-10-11 | 2022-01-27 | 2022-11-16 | 2023-02-16 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 18058.54 | 35580.29 | 53638.83 | 501246.74 | 554885.57 | 0 | [6 empty] | CM_WSI | 100%
501208 | Alexandria WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2018-04-30 | 2018-06-30 | West Dunbartonshire | 0 | 0 | 445.09 | 9044.16 | -9489.25 | 0 | 1 | 1 | 0 | 1 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
500723 | Alford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS2 | 2017-08-28 | 2020-03-31 | 2020-08-24 | 2021-07-23 | 2021-10-25 | Aberdeenshire | 0 | 34493.38 | 59294.5 | 26842.33 | 10146.94 | 179416.32 | 1279785.36 | 1589978.83 | 160021.24 | 1750000.07 | 136478.56 | [6 empty] | SG1 | 100%
401936 | Allander Park Bearsden - Infrastructure Growth | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2011-09-12 | 2015-09-11 | 2015-09-14 | 2015-10-23 |  | East Dunbartonshire | 101213 | -2732.23 | 0 | 0 | 0 | 0 | 4919.23 | 2187 | 0 | 103400 | 0 | [6 empty] | SG5 | 100%
502690 | Allanfearn PFI - Odour Improvement Plan | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWD | Odour | MS7 | 2015-08-01 | 2016-03-01 | 2016-03-01 | 2016-03-31 | 2017-07-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 12873.24 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
503319 | Allanfearn WwTW - PFI SR 21 - Post Concession Expiry Investment Review | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-07-19 | 2028-11-08 | 2029-03-08 | 2030-06-06 | 2030-09-06 | Highland | 0 | 0 | 0 | 0 | 70513.86 | 38109.38 | 27693.52 | 136316.76 | 4363683.21 | 4499999.97 | 0 | [6 empty] | CM_WWNI | 100%
30011 | Allers (East Kilbride) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2012-02-21 | 2012-02-21 | 2014-06-11 | 2014-07-02 | South Lanarkshire | 4577775.74 | 32363.33 | -6590.11 | 0 | 0 | 0 | 0 | 25773.22 | 0 | 4603548.96 | 13100.66 | [6 empty] | EC10A | 10.34% | EC01A | 25.02% | EC04A | 25.02% | CM_WWNI | 39.63%
402221 | Allers Sludge Storage and Phase 2 M-E refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2011-09-27 | 2011-09-27 | 2011-10-10 | 2019-09-19 |  | South Lanarkshire | 732771.85 | 296.49 | 112.5 | 667.84 | 0 | 0 | 0 | 1076.83 | 0 | 733848.68 | 0 | [6 empty] | CM_WWNI | 100%
403883 | Alliance Mobilisation - Consultancy Support | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2014-07-24 | 2014-10-02 | 2014-10-02 | 2018-09-03 | 2018-09-03 | Scottish Water Wide | 449856 | 136096 | -41186.42 | 139635.92 | -139635.92 | 0 | 0 | 94909.58 | 0 | 544765.58 | 0 | [6 empty] | CM_M&G | 100%
45302 | Alligin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-17 | 2011-07-22 | 2013-03-22 | 2013-04-10 | Highland | 232842.88 | -137.68 | 0 | 0 | 0 | 0 | 0 | -137.68 | 0 | 232705.2 | 0 | [6 empty] | DW13 | 100%
502739 | All-mains model build and maintenance Water Yr 3 to 6 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-05-31 | 2018-03-23 | 2018-05-11 |  | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 459488.53 | 690864.93 | 683298.65 | 40609 | 1874261.11 | 86012.24 | 1960273.35 | 0 | [6 empty] | CM_WSI | 100%
500111 | Alloa DOA (DOA000269) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-06-18 | 2018-07-20 | Clackmannanshire | 0 | 10830 | 51324 | 55724.67 | 5685.03 | 0 | -0.01 | 123563.69 | 0 | 123563.69 | 277404.61 | [6 empty] | CS16D | 100%
402874 | Alloa Drainage Network EPI Resolution Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-12-21 | 2016-02-15 | 2016-02-01 | 2016-02-19 |  | Clackmannanshire | 67374 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 68034 | 0 | [6 empty] | CM_WWI | 100%
501159 | Alloa STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-07 | 2018-12-31 | 2019-06-14 | 2021-12-20 | 2022-03-22 | Clackmannanshire | 0 | 0 | 54819.57 | 236259.02 | 680414.51 | 1241717.9 | 666440 | 2879651 | 1113686 | 3993337 | 0 | [6 empty] | CM_WWNI | 100%
500195 | Allt Sanna Pearl Mussels Habitats Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-14 | 2016-03-21 | 2016-11-30 | 2017-02-28 | Angus | 0 | 11755 | 29014.14 | 8298.07 | 442.47 | 0 | 0 | 49509.68 | 0 | 49509.68 | 14757 | [6 empty] | EC08C | 100% | bar: Regulatory Outputs OMG-23
503234 | Allt Sanna WFPM | Q&S4 | Protecting and enhancing the environment | Habitats Directive |  |  | Wastewater |  | SWMD | Habitats Directive | MS2 | 2018-06-29 | 2019-12-18 | 2021-06-21 | 2021-12-20 | 2022-03-22 | Highland | 0 | 0 | 0 | 0 | 88200.69 | 63021.59 | 5495.4 | 156717.68 | 534918.96 | 691636.64 | 479915.76 | [6 empty] | EC08D | 100%
400723 | Almondbank WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2013-03-18 | 2013-05-21 | 2013-11-15 | 2013-11-15 | Perth and Kinross | 251977 | -6059.86 | 0 | 0 | 0 | 0 | 0 | -6059.86 | 0 | 245917.14 | 0 | [6 empty] | SG1 | 100%
504758 | Alness and Invergordon STC - Lime Plant Modifcations | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | - | 0 | 0 | 0 | 0 | 0 | 817.76 | 0 | 817.76 | 0 | 817.76 | 0 | [6 empty] | CM_WWNI | 100%
500189 | Alness and Invergordon WWTW Odour Upgrade | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWD | Odour | MS7 | 2015-03-16 | 2015-10-02 | 2015-10-02 | 2015-03-31 | 2015-10-31 | Highland | 0 | 0.07 | 0 | -318.33 | 0 | 0 | 318.33 | 0.07 | 0 | 0.07 | 2490.44 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
500854 | Alnwickhill B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-03-31 | 2018-03-23 | 2018-06-14 | 2019-03-31 | 2019-09-30 | City of Edinburgh | 0 | 22932.61 | 23674.39 | 51034.96 | 209635.39 | 85340.02 | 0 | 392617.37 | 0 | 392617.37 | 830064.37 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 44.46
501387 | Alnwickhill PRV | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWMD | Energy efficiency | MS7 | 2016-09-26 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | City of Edinburgh | 0 | 0 | 309793 | 59612 | -24636.57 | 0 | 0 | 344768.43 | 0 | 344768.43 | 0 | [6 empty] | I2S_WI | 18.62% | CM_WSI | 81.38%
403410 | Alnwickhill PRV Hydro | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2015-02-18 | 2015-02-23 | 2015-02-24 | 2015-02-24 | City of Edinburgh | 1763.37 | 0 | 0 | 275.63 | 0 | 0 | -269 | 6.63 | 0 | 1770 | 0 | [6 empty] | CC1W | 100%
502401 | Alnwickhill Revcovery Project | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-12-13 | 2016-12-13 | 2017-02-15 | 2018-07-20 | 2018-07-20 | City of Edinburgh | 0 | 0 | 556674 | 2046423.88 | 136945.93 | 16540.12 | 309.18 | 2756893.11 | 4843.74 | 2761736.85 | 0 | [6 empty] | CM_WSI | 100%
501222 | Alves WWPS Rising Main | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2015-11-18 | 2020-12-14 | 2021-03-11 | 2021-11-10 | 2022-02-21 | Moray | 0 | 5969.18 | 23718.82 | 2768.29 | 0 | 2955.71 | 179175.14 | 214587.14 | 1648441.86 | 1863029 | 0 | [6 empty] | SR21_WW | 100%
402202 | Alyth WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-07-01 | 2013-07-24 | 2013-09-30 | 2015-03-27 | 2015-03-27 | Angus | 2016856 | 483832 | -79.17 | 1887.66 | 0 | 0 | 0 | 485640.49 | 0 | 2502496.49 | 0 | [6 empty] | SG1 | 100%
403864 | AM - BIP - IDP Development Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-31 | 2015-02-26 | 2015-02-26 | 2017-09-01 |  | Scottish Water Wide | 898925 | 1069828 | 246951 | -117775.09 | 0 | 0 | 0 | 1199003.91 | 0 | 2097928.91 | 0 | [6 empty] | CM_M&G | 100%
505551 | Amey Bypass N Upper Braes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-09 | 2020-06-29 | 2020-10-05 | 2020-11-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 7130.84 | 101869.14 | 108999.98 | 0 | 108999.98 | 0 | [6 empty] | CM_WSNI | 100%
505548 | Amey Bypasses East Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-09 | 2020-06-29 | 2020-10-05 | 2020-11-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 11560.71 | 151439.29 | 163000 | 0 | 163000 | 0 | [6 empty] | CM_WSNI | 100%
505549 | Amey Bypasses North Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-09 | 2020-06-29 | 2020-10-05 | 2020-11-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 10743.39 | 142256.61 | 153000 | 0 | 153000 | 0 | [6 empty] | CM_WSNI | 100%
502258 | Amlaird - Gorbals TWPS and Drumboy Hill DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WWINF | Exceptional Capital Maintenance | MS5 | 2016-06-17 | 2016-06-17 | 2016-07-01 | 2018-09-28 | 2018-09-28 | East Renfrewshire | 0 | 0 | 20899687 | 2303097 | 1491496 | 379335 | 360828 | 25434443 | 2586 | 25437029 | 0 | [6 empty] | SR15_EXC_EXC | 100%
503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-03-10 | 2022-01-11 | East Ayrshire | 0 | 0 | 0 | 0 | 821924 | 2735201.37 | 1275827.29 | 4832952.66 | 120059 | 4953011.66 | 0 | [6 empty] | DW5FS | 5.91% | DW5MR | 94.09%
502607 | Amlaird RSZ Cleaning - Mains Conditioning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2018-06-28 | 2018-12-20 | 2019-03-28 | 2019-12-31 | 2020-05-31 | East Ayrshire | 0 | 0 | 46347 | 250250.91 | 135664.1 | 78253.18 | 51582.95 | 562098.14 | 2714.88 | 564813.02 | 528018.37 | [6 empty] | DW5MC | 100% | [18 empty] | Regulatory Outputs OMG-06: 36.366
503069 | Amlaird WR1 Mitigation Loch Goin | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2018-02-12 | 2018-02-12 | 2018-06-13 | 2020-11-19 | 2020-11-20 | North Ayrshire | 0 | 0 | 0 | 21602.31 | 93852.26 | 204450.84 | 162394.59 | 482300 | 2700 | 485000 | 4507587.62 | [6 empty] | DW25P | 100%
402614 | Amlaird WTW Essential Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2019-06-07 |  | East Ayrshire | 841384 | 31616 | 62477.35 | 66188.06 | 0 | 0 | 0 | 160281.41 | 0 | 1001665.41 | 0 | [6 empty] | CM_WSNI | 100%
403572 | AMR Project Phase 7 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 2015-07-31 |  | Scottish Water Wide | 568891.54 | 8644.95 | 0 | 0 | 0 | 0 | 0 | 8644.95 | 0 | 577536.49 | 0 | [6 empty] | CM_M&G | 100%
504100 | Ancrum WWTW Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-06-30 | 2020-06-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 25461.71 | -461.71 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WWNI | 100%
500919 | Angus Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-06-30 | 2016-07-01 | 2017-09-11 | 2017-09-11 | Angus | 0 | 8951.12 | 62105.02 | -51525 | 0 | 0 | 0 | 19531.14 | 0 | 19531.14 | 120964.87 | [6 empty] | CS15A | 100%
503385 | Anguston ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | Aberdeenshire | 0 | 0 | 0 | 0 | 64479.98 | 0 | -3173.83 | 61306.15 | 0 | 61306.15 | 136478.56 | [6 empty] | SG1 | 100%
500114 | Annan DOA (DOA000111) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-03-21 | 2019-08-28 | Dumfries and Galloway | 0 | 30381 | 102008.99 | 55979.53 | 9737 | 9347.33 | 0.1 | 207453.95 | 0 | 207453.95 | 42765.7 | [6 empty] | EC01G | 7.97% | EC01D | 39.2% | CS16D | 52.83%
500113 | Anstruther Billowness DOA (DOA000254) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-12-11 | 2019-03-22 | Fife | 0 | 21739 | 31819.52 | 51739.48 | 15842 | -10831.74 | -0.03 | 110308.23 | 0 | 110308.23 | 4768.64 | [6 empty] | CS16D | 50% | EC01D | 50%
503576 | Anthony Road Largs Rail Sewer Crossing | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2020-10-26 | 2021-11-01 | 2021-12-27 | 2022-07-25 | 2022-09-15 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 43918.96 | 111337.3 | 155256.26 | 409743.8 | 565000.06 | 0 | [6 empty] | CM_WWI | 100%
502626 | Applecross WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-06-16 | 2033-08-30 | 2034-08-04 | 2034-11-06 | Highland | 0 | 0 | 20930.23 | 415.9 | 1196.3 | -19769.44 | 0 | 2772.99 | 0 | 2772.99 | 136478.56 | [6 empty] | WG1 | 100%
501922 | Application Integration and Service Architecture Refresh 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2020-05-29 | 2020-05-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 459619.24 | 1078763.73 | 22170.38 | 1560553.35 | 0 | 1560553.35 | 0 | [6 empty] | CM_M&G | 100%
500587 | Application Platforms Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-01-18 | 2016-08-22 | 2016-08-22 | 2017-10-12 | 2017-04-20 | Scottish Water Wide | 0 | 196259 | 17838.39 | 27739.32 | 0 | 0 | 0 | 241836.71 | 0 | 241836.71 | 0 | [6 empty] | CM_M&G | 100%
403797 | Applications Remediation and Packaging Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-06-11 | 2014-06-11 | 2014-06-26 | 2015-03-12 |  | Scottish Water Wide | 2012615 | -15928.57 | 0 | 0 | 0 | 0 | 0 | -15928.57 | 0 | 1996686.43 | 0 | [6 empty] | CM_M&G | 100%
500435 | Arbroath Dangerpoint WWPS NO644406 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-04-30 | 2017-10-18 | 2018-03-06 | 2019-09-23 | 2019-09-23 | Angus | 0 | 36000 | 35530 | 336259 | 246268 | 47546.45 | 0 | 701603.45 | 2399.55 | 704003 | 0 | [6 empty] | CM_WWNI | 30% | CM_WWI | 70%
500989 | ARCS | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2016-05-12 | 2016-05-12 | 2016-05-12 |  | Scottish Water Wide | 0 | 62742.86 | 0 | 0 | 0 | 0 | 0 | 62742.86 | 0 | 62742.86 | 0 | [6 empty] | CM_M&G | 100%
503760 | Ardeonaig Intake Structure | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-04-28 | 2019-10-04 | 2020-01-15 | 2020-09-17 | 2020-11-10 | Stirling | 0 | 0 | 0 | 0 | 0 | 342475.77 | 22740.84 | 365216.61 | 4783.39 | 370000 | 0 | [6 empty] | CM_WSI | 100%
500115 | Ardersier DOA (DOA000501) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-17 | 2015-11-30 | 2016-01-12 | 2017-02-28 | 2017-07-31 | Highland | 0 | 49955 | 86901.95 | -3667.97 | 0 | 0 | 3796.41 | 136985.39 | 0 | 136985.39 | 558366.35 | [6 empty] | CS15 | 33.33% | CS16D | 33.33% | CS11 | 33.33% | bar: Regulatory Outputs OMG-22
501290 | Ardersier WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2015-12-24 | 2018-05-31 | 2018-06-26 | 2021-03-08 | 2021-06-01 | Highland | 0 | 33462 | 284751.32 | 487405.34 | 5031420.48 | 4188617.86 | 1993207 | 12018864 | 60355 | 12079219 | 136478.56 |  |  |  |  | 255440 |  | SG1 | 100%
500649 | Ardersier WWTW - Outfall Extension | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS5 | 2015-06-30 | 2018-11-07 | 2018-12-10 | 2019-06-30 | 2020-03-31 | Highland | 0 | 61832 | 345821.35 | 613713.65 | 2668752 | 606481 | 0 | 4296600 | 400 | 4297000 | 0 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-48
500012 | Ardersier WwTW - UV | Q&S4 | Protecting and enhancing the environment | Habitats Directive |  |  | Wastewater |  | NONINF | Habitats Directive | MS6 | 2015-06-17 | 2016-11-30 | 2016-12-07 | 2017-11-30 | 2018-01-31 | Highland | 0 | 88006 | 841003.84 | 1509147.92 | -1647243.3 | -105322.46 | 181.32 | 685773.32 | 0 | 685773.32 | 266250.97 | [6 empty] | EC08A | 100% | bar: Regulatory Outputs OMG-26
45305 | Ardfern (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2011-05-16 | 2011-10-24 | 2011-12-07 | Argyll and Bute-North Argyll | 41157.73 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 41169.73 | 0 | [6 empty] | DW13 | 100%
502316 | Ardfern WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | Argyll and Bute-North Argyll | 0 | 0 | 26143.02 | 3238.09 | 1237.31 | 20063.5 | -6853.01 | 43828.91 | 0 | 43828.91 | 136478.56 | [6 empty] | WG1 | 100%
501183 | Ardgay Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-23 | 2019-03-12 | 2018-02-01 | 2019-01-28 | 2019-01-28 | Glasgow City | 0 | 0 | 52000 | 35130.28 | -87129.28 | 0 | 0 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11A | 100%
402632 | Ardgour - Growth Project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2012-06-11 | 2014-01-21 | 2014-02-03 | 2015-03-31 | 2015-05-31 | Highland | 840340 | 69475 | -5975.51 | -1387.53 | 0 | 0 | 0 | 62111.96 | 0 | 902451.96 | 1830849.77 | [6 empty] | SG5 | 100% | [18 empty] | Regulatory Outputs OMG-17: 3
501330 | Ardgowan WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-05-11 | 2017-07-27 | 2017-10-30 | 2018-03-30 | 2018-03-30 | Inverclyde | 0 | 0 | 49217 | 830835 | 43922 | 0 | 0 | 923974 | 0 | 923974 | 0 | [6 empty] | CM_WWNI | 100%
500121 | Ardoch DOA (DOA000707) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2020-01-27 | 2020-03-23 | West Dunbartonshire | 0 | 17396 | 68936 | 218548.35 | 150000 | 36306.51 | 28813.14 | 520000 | 0 | 520000 | 174619.77 | [6 empty] | EC01G | 10.86% | EC01D | 40.15% | CS16D | 48.99%
501158 | Ardoch STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-12-14 | 2018-10-15 | 2018-10-22 | 2020-11-05 | 2021-02-01 | West Dunbartonshire | 0 | 20690 | 258206.33 | 175176.19 | 506094.22 | 1323648.2 | 239439.88 | 2523254.82 | 48638.17 | 2571892.99 | 0 |  |  |  |  | 40330 |  | CM_WWNI | 100%
503416 | Ardross WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-01-13 | 2021-07-29 | 2021-12-15 | 2023-02-21 | 2023-05-24 | Highland | 0 | 0 | 0 | 0 | 60503.3 | 32206.69 | 68050.13 | 160760.12 | 246307.73 | 407067.85 | 136478.56 | [6 empty] | SG1 | 100%
501187 | Ardvourlie WTW - Intake | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-06-28 | 2016-08-08 | 2018-02-09 | 2018-02-09 | Na H-Eileanan an Iar | 0 | 3276 | 19316.83 | 60691.04 | -781.14 | 0 | 0 | 82502.73 | 0 | 82502.73 | 0 | [6 empty] | CM_WSI | 100%
503721 | Ardvourlie WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-03-22 | 2023-08-21 | 2023-12-15 | 2024-12-10 | 2025-03-11 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 35040 | 35040 | 964959.96 | 999999.96 | 136478.56 | [6 empty] | SG1 | 100%
403552 | Argyle Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS6 | 2013-09-25 | 2018-11-29 | 2018-11-30 | 2019-05-27 | 2019-05-27 | Glasgow City | 65107.01 | 39892.99 | 27387 | 33994.12 | 128616.36 | 1592.3 | 0 | 231482.77 | 0 | 296589.78 | 986533.93 | [6 empty] | CS11A | 5.715% | CS11 | 94.28%
503587 | Argyll SCADA - Ardrishaig | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2019-10-02 | 2020-03-26 | 2020-03-27 | 2020-12-09 | 2021-03-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 338316 | 596029.6 | 934345.6 | 56184.4 | 990530 | 0 | [6 empty] | CM_WSNI | 100%
503586 | Argyll SCADA - Tarbert | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2019-10-02 | 2020-03-26 | 2020-03-27 | 2020-09-30 | 2020-11-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 351605 | 567930.7 | 919535.7 | 8410.3 | 927946 | 0 | [6 empty] | CM_WSNI | 100%
500793 | Argyll SCADA Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-06-28 | 2020-08-17 | 2020-10-27 | 2022-01-24 | 2022-06-15 | Argyll and Bute-North Argyll | 0 | 0 | 13644.19 | 225569.48 | 65768.43 | 61791.93 | 871907.78 | 1238681.81 | 1100237.49 | 2338919.3 | 0 | [6 empty] | CM_WSNI | 100%
500906 | Argyll-Bute and West Dumbartonshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-10-14 | Argyll and Bute-Cowal & Bute | 0 | 4940.33 | 679.91 | 0 | 0 | 0 | 0 | 5620.24 | 0 | 5620.24 | 120964.87 | [6 empty] | CS15A | 100%
500224 | Arinagour Coll - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-20 | 2016-03-30 | 2016-06-28 | 2017-12-31 | 2018-06-30 | Argyll and Bute-North Argyll | 0 | 561.48 | 28073.18 | 17720.18 | 1653.3 | 545.39 | -545.39 | 48008.14 | 0 | 48008.14 | 221514.54 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
505075 | Arinagour SEP - replacement outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2093.02 | 0 | 2093.02 | 0 | 2093.02 | 0 | [6 empty] | CM_WWI | 100%
502315 | Arinagour WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2019-06-28 | 2019-06-28 | Argyll and Bute-North Argyll | 0 | 0 | 25265.2 | 43741.87 | 4014.31 | -19843.5 | 0 | 53177.88 | 0 | 53177.88 | 136478.56 | [6 empty] | WG1 | 100%
500821 | Arkleston Road Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-24 | 2015-09-22 | 2015-09-23 | 2018-03-07 | 2018-03-07 | Renfrewshire | 0 | 44095.56 | 8998.91 | -3488.7 | 0 | 0 | 0 | 49605.77 | 0 | 49605.77 | 120964.87 | [6 empty] | CS15A | 100%
501548 | Arklet Hydro Scheme | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-12-24 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | Falkirk | 0 | 5923 | 61503.07 | 0 | 0 | 0 | 0.25 | 67426.32 | 0 | 67426.32 | 832227.31 | [6 empty] | I2S_WI | 100%
500670 | Armadale (Phase 2) Sewer Infrastructure Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2019-12-03 | 2019-12-03 | East Lothian | 0 | 409914 | -208778.24 | 0 | 273.23 | 37.41 | -13.78 | 201432.62 | 0 | 201432.62 | 1830849.77 | [6 empty] | SG5 | 100%
501713 | Armadale and Blackridge WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2016-07-19 | 2020-04-06 | 2020-06-01 | 2020-11-06 | 2021-02-12 | West Lothian | 0 | 0 | 15078 | 9922 | 0 | 11561 | 163777.08 | 200338.08 | 0 | 200338.08 | 0 | [6 empty] | SR21_WW | 100%
30028 | Armadale STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2010-09-20 | 2011-03-17 | 2013-03-18 | 2013-03-18 | West Lothian | 1579435.98 | 508.04 | 0 | 0 | 0 | 0 | -0.02 | 508.02 | 0 | 1579944 | 0 | [6 empty] | CM_WWNI | 50% | EC01A | 50%
403997 | Arnisdale WTW - Water Quality Upgrade - Cartridge & UV Option | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-12-23 | 2016-01-29 | 2016-05-03 | 2017-02-13 | 2017-03-22 | Highland | 24239 | 95460 | 368953.18 | 2495.22 | 894.07 | 0 | 0 | 467802.47 | 0 | 492041.47 | 717180 | [6 empty] | DW23 | 100%
502370 | Arnisdale WTW Crypto Risk Mitigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2019-06-28 | 2019-06-28 | Highland | 0 | 0 | 5006.46 | 28996.65 | 2038.63 | 19038.06 | 0 | 55079.8 | 0 | 55079.8 | 0 | [6 empty] | CM_WSNI | 100%
46849 | Arnisdale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2016-04-01 | 2014-09-17 | 2014-11-04 | 2014-11-04 | Highland | 238767.23 | -2 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 238765.23 | 0 | [6 empty] | DW23 | 100%
503470 | Arnold Clark - Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2019-04-03 | 2019-04-03 | 2019-05-08 | 2019-09-04 | 2019-09-04 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 628037.83 | 0 | 628037.83 | 0 | 628037.83 | 0 | [6 empty] | CM_WWI | 100%
501721 | ARROCHAR RWP NN299038 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-07-07 | 2028-04-21 | 2028-08-25 | 2029-01-04 | 2029-04-06 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12073.01 | 12073.01 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
401323 | Asbestos Inspections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-09-13 | 2011-02-04 | 2011-04-01 | 2017-01-31 |  | Scottish Water Wide | 1029421 | 50407 | 6006.06 | 0 | 0 | 0 | 0 | 56413.06 | 0 | 1085834.06 | 0 | [6 empty] | CM_M&G | 100%
503835 | Ashfield Land - Topgolf Cambuslang - Glasgow Sludge Main Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | GW1 |  | 2020-05-25 | 2020-07-15 | 2021-03-02 | 2021-03-03 | - | 0 | 0 | 0 | 0 | 0 | 1308.41 | 0 | 1308.41 | 0 | 1308.41 | 2614273.27 | [6 empty] | CS23S | 100%
30030 | Ashgill STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-06-28 | 2010-09-06 | 2011-12-22 | 2012-01-10 | South Lanarkshire | 1787178.82 | 189.37 | 0 | 0 | 0 | 0 | 0 | 189.37 | 0 | 1787368.19 | 0 | [6 empty] | CM_WWNI | 19.63% | EC04A | 80.37%
503405 | Ashgillhead Road Ashgill | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS4 | 2018-10-12 | 2019-08-27 | 2020-01-13 | 2020-03-25 | 2020-07-07 | South Lanarkshire | 0 | 0 | 0 | 0 | 40178 | 334063.56 | 832.44 | 375074 | 0 | 375074 | 204193.13 | [6 empty] | CS11 | 100%
403435 | Ashgillhead Road Graham Place Ashgill | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-04-16 | 2019-03-06 | 2019-03-06 | 2019-01-14 | 2019-01-14 | South Lanarkshire | 120677.02 | 7647.98 | 24700 | 33318.87 | 24566.06 | 3084.84 | -3057.02 | 90260.73 | 0 | 210937.75 | 0 | [6 empty] | CM_WWI | 28% | CS11A | 72%
501620 | Assess Risk Of Low Pressure To All Customers | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWD | Pressure | MS7 | 2016-02-12 | 2016-07-14 | 2016-08-15 | 2018-02-23 | 2018-04-16 | Scottish Water Wide | 0 | 319.15 | 30478.26 | 104552.28 | -1250.6 | 0 | 1518.92 | 135618.01 | 0 | 135618.01 | 233555.83 | [6 empty] | CS1B | 100%
403915 | Asset Capacity View | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2014-12-10 | 2015-03-09 | 2015-03-10 | 2015-05-15 | 2015-08-06 | Scottish Water Wide | 124054 | -6078.08 | 0 | 0 | 0 | 0 | -353 | -6431.08 | 0 | 117622.92 | 0 | [6 empty] | CS18W | 100%
400661 | Asset Lifecycle Planning | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-02 | 2012-05-23 | 2012-05-23 | 2014-04-11 |  | Scottish Water Wide | 7108827.57 | 0 | 0 | 145.57 | 0 | 0 | -145.57 | 0 | 0 | 7108827.57 | 0 | [6 empty] | CM_M&G | 100%
500053 | Asset Renewal - Stodswell DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-13 | 2016-07-13 | 2016-07-14 | 2016-07-28 | 2016-07-28 | Dundee City | 0 | 2012.48 | 471.18 | 0 | 0 | 0 | 0.34 | 2484 | 0 | 2484 | 0 | [6 empty] | CM_WSI | 100%
505244 | Assynt CWT Scour telemetry and building condition investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-19 | 2020-08-06 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 766.91 | 0 | 766.91 | 0 | 766.91 | 0 | [6 empty] | CM_WSNI | 100%
503089 | Assynt WOA - Cromarty SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-15 | 2022-09-16 | 2023-01-13 | 2024-01-04 | 2024-04-05 | Highland | 0 | 0 | 0 | 21827.48 | 25729.12 | 940 | -496.6 | 48000 | 951999.97 | 999999.97 | 0 | [6 empty] | CM_WSNI | 100%
403558 | Assynt WOA - Dingwall North Link Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-08-27 | 2014-08-20 | 2014-08-27 | 2015-12-21 | 2015-12-21 | Highland | 155920 | 280688 | 6104.95 | -3553.68 | 0 | 0 | 0 | 283239.27 | 0 | 439159.27 | 0 | [6 empty] | WG5 | 100%
503063 | Assynt WOA - Maryburgh Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-05-27 | 2028-04-19 | 2028-07-07 | 2029-04-09 | 2029-07-10 | Highland | 0 | 0 | 0 | 21627.78 | 139841.99 | -136537.85 | 0 | 24931.92 | 3775068.11 | 3800000.03 | 0 | [6 empty] | CM_WSI | 100%
403171 | Assynt WOA - Removal of Small Diameter AC Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-11 | 2013-03-11 | 2013-07-15 | 2016-03-25 |  | Highland | 734085 | 169803 | 14576.17 | 463.98 | 0 | 0 | 0 | 184843.15 | 0 | 918928.15 | 0 | [6 empty] | CM_WSI | 100%
500753 | Assynt WOA -Mulbuie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-08-27 | 2027-09-29 | 2027-11-23 | 2028-01-03 | 2028-03-28 | Highland | 0 | 95506 | 39579.88 | 589.87 | 446.09 | 3650.51 | 0 | 139772.35 | 1315227.63 | 1454999.98 | 0 | [6 empty] | CM_WSNI | 100%
502833 | Assynt WOA- Newmore Primary School Iron Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 | Highland | 0 | 0 | 0 | 20520.17 | 2247.8 | 0 | 0 | 22767.97 | 0 | 22767.97 | 0 | [6 empty] | CM_WSI | 100%
503402 | Assynt WOA Rosemarkie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-07-13 | 2028-11-03 | 2029-06-21 | 2029-09-21 | Highland | 0 | 0 | 0 | 0 | 24279.1 | 4641.94 | 7078.95 | 35999.99 | 714000.01 | 750000 | 0 | [6 empty] | CM_WSNI | 100%
500789 | Assynt WTW - CWT Additional Storage | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | NONINF | Supply Resilience | MS4 | 2015-09-17 | 2017-12-22 | 2017-12-22 | 2020-03-12 | 2020-07-31 | Highland | 0 | 126145 | 212052.45 | 1043502.58 | 3865138.5 | 1386085.43 | -77.96 | 6632846 | 102543.53 | 6735389.53 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
32111 | Assynt WTW - Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2005-09-20 | 2008-03-28 | 2008-08-18 | 2010-04-30 | 2011-03-31 | Highland | 19237618.42 | 0.58 | 29 | 0 | 0 | 0 | -0.58 | 29 | 0 | 19237647.42 | 0 | [6 empty] | DW13 | 13.25% | DW3B | 13.25% | DW3J | 13.25% | DW4A | 13.25% | WSNI | 20% | WG1 | 27%
503258 | Athelstaneford WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-01 | 2028-09-13 | 2029-01-15 | 2030-01-09 | 2030-04-11 | East Lothian | 0 | 0 | 0 | 0 | 80855.55 | 8356.93 | -1831.91 | 87380.57 | 54619.43 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
501551 | ATOM Holding Line - SWD | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-14 |  |  | 2021-04-14 | 2021-04-14 | Scottish Water Wide | 0 | 91261.68 | -90741.92 | -519.76 | 0 | 0 | 3883869.24 | 3883869.24 | 0 | 3883869.24 | 0 | [6 empty] | CM_WWI | 100%
503622 | Auchenback Treated Water Pump Station (TWP) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-08-26 | 2020-02-26 | 2020-02-26 | 2021-09-20 | 2021-11-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 22391.3 | 534403.62 | 556794.92 | 263205.06 | 819999.98 | 1027811.08 | [6 empty] | DW25P | 100%
503662 | Auchenback WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-06-25 | 2022-03-14 | 2022-07-14 | 2024-02-07 | 2024-04-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 33585.28 | 74459.72 | 108045 | 791954.98 | 899999.98 | 0 | [6 empty] | CM_WSNI | 100%
402178 | Auchengaich Reservoir Valve Tower Access Bridge Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-27 | 2012-06-18 | 2014-12-08 | 2014-12-08 | Argyll and Bute-North Argyll | 350229.84 | -2299.18 | 0 | 0 | 0 | 0 | 0 | -2299.18 | 0 | 347930.66 | 0 | [6 empty] | CM_WSI | 100%
501224 | Auchengate Dundonald Camp Replacement of Sewage Pumping Station and Rising Main | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS6 | 2016-02-22 | 2016-11-21 | 2016-11-29 | 2018-03-27 | 2018-03-27 | North Ayrshire | 0 | 74252 | 100211.8 | 293385 | 177 | 43687.45 | -2006.45 | 509706.8 | 0 | 509706.8 | 0 | [6 empty] | SG6 | 100%
503221 | Auchleven North ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-07-07 | 2021-12-27 | 2022-04-22 | 2023-04-19 | 2023-07-20 | Aberdeen City | 0 | 0 | 0 | 0 | 80312.1 | 28838.9 | 53854.82 | 163005.82 | 372471.25 | 535477.07 | 136478.56 | [6 empty] | SG1 | 100%
505138 | Auchnacloich mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-02-12 |  | 2021-02-19 | 2021-02-19 | Highland | 0 | 0 | 0 | 0 | 0 | 9008.86 | -658.39 | 8350.47 | 0 | 8350.47 | 0 | [6 empty] | CM_WSI | 100%
503162 | Auchneel WTW - Lime to Caustic | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2018-08-27 | 2018-08-27 | 2020-10-05 | 2021-06-24 | 2021-09-24 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 37074.77 | 75374.99 | 247511.51 | 359961.27 | 115038.72 | 474999.99 | 0 | [6 empty] | CM_WSNI | 100%
404090 | Auchterarder Water Mains Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 2020-08-04 | 2020-08-04 | Perth and Kinross | 0 | 96394 | 4000 | 922630.13 | 0 | 0 | 0 | 1023024.13 | 0 | 1023024.13 | 0 | [6 empty] | WG5 | 100%
503282 | Auldgirth WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-01-15 | 2029-05-18 | 2030-05-16 | 2030-08-16 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 74149.38 | 5976.45 | 0 | 80125.83 | 61874.16 | 141999.99 | 136478.56 | [6 empty] | SG1 | 100%
502846 | Aultbea WTW Growth - SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-12-05 | 2034-04-04 | 2035-03-30 | 2035-07-02 | Highland | 0 | 0 | 0 | 20930.23 | 2496.43 | -18754.4 | 0 | 4672.26 | 0 | 4672.26 | 136478.56 | [6 empty] | WG1 | 100%
501188 | Aviemore WTW - Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-07-29 | 2016-11-28 | 2017-08-29 | 2017-08-29 | Highland | 0 | 8324 | 731271.07 | 189546.62 | 17719.66 | 0 | 0 | 946861.35 | 0 | 946861.35 | 0 | [6 empty] | CM_WSNI | 100%
502562 | Aviemore WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-10-27 | 2028-05-11 | 2028-09-04 | 2029-08-23 | 2029-11-23 | Highland | 0 | 0 | 0 | 11848.31 | 1899.58 | 53889.19 | 26467.9 | 94104.98 | 9979495.18 | 10073600.16 | 136478.56 | [6 empty] | WG1 | 100%
404069 | Aviemore WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2015-03-09 | 2018-01-31 | 2018-10-31 | 2020-07-20 | 2020-07-21 | Highland | 2936.05 | 146656.95 | 365789.82 | 451304.76 | 1134971.62 | 1187468.81 | 213265.99 | 3499457.95 | 0 | 3502394 | 0 |  |  |  |  | 177.84 |  | SG1 | 100%
505031 | Aviemore WwTW 2005 - Inlet Screen Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 196.26 | 0 | 196.26 | 0 | 196.26 | 0 | [6 empty] | CM_WWNI | 100%
402228 | Avondale VC and Trunk Main Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2011-07-29 | 2012-02-14 | 2012-04-10 | 2020-05-12 |  | Falkirk | 870005 | -290488 | 19584.27 | 53384.96 | 149760.77 | 14267.2 | 11729 | -41761.8 | 1030.32 | 829273.52 | 0 | [6 empty] | CM_WSI | 100%
501799 | AVSE PFI Edinburgh WwTW Grade 5 HC Sewer Ph2 Central & East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2017-04-28 | 2019-01-29 | 2019-03-11 | 2019-09-30 | 2019-09-30 | City of Edinburgh | 0 | 0 | 4742.5 | 13656.5 | 52483 | 29118 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWI | 100%
401207 | Ayr Cluster 1 Delivery Maybole Road | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2011-07-06 | 2011-08-29 | 2013-03-28 |  | South Ayrshire | 1661943.78 | 35525.22 | 0.26 | 120084.49 | 0 | -130317.11 | 0 | 25292.86 | 0 | 1687236.64 | 0 | [6 empty] | CM_WSI | 100%
503507 | Ayr Cluster 1 Delivery Maybole Road - Additional Costs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2019-04-04 | 2019-04-04 | 2019-04-24 | 2019-04-26 | 2019-04-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 138856.4 | 0 | 138856.4 | 0 | 138856.4 | 0 | [6 empty] | CM_WSI | 100%
400288 | Ayr Cluster 3 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2011-11-21 | 2012-02-06 | 2013-02-07 |  | Inverclyde | 629609 | 0 | -34550.53 | 27.28 | 0 | 0 | 95.72 | -34427.53 | 0 | 595181.47 | 0 | [6 empty] | CM_WSI | 100%
401500 | Ayr Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-15 | 2012-03-26 | 2012-04-30 | 2015-03-26 |  | All West Unitary Authorities | 396128 | 3750 | -1395.66 | 0 | 0 | 0 | 1395.94 | 3750.28 | 0 | 399878.28 | 0 | [6 empty] | CM_WSI | 100%
503393 | Ayr Shore Road SPS - Emergency Repairs to Transfer Pumps and Wet Well Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2018-10-02 | 2018-10-02 | 2018-10-15 | 2021-01-14 | 2021-01-15 | South Ayrshire | 0 | 0 | 0 | 0 | 1244866.77 | 295564.52 | 215899.11 | 1756330.4 | 2189.01 | 1758519.41 | 0 | [6 empty] | CM_WWNI | 100%
33957 | Ayr SPS - Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2007-03-27 | 2008-02-12 | 2008-04-14 | 2010-03-31 |  | South Ayrshire | 8357062.73 | 48495.27 | 102708.9 | 0 | 0 | 0 | 0 | 151204.17 | 0 | 8508266.9 | 0 | [6 empty] | WWI | 3.82% | WWNI | 96.18%
500704 | Ayre Road WWPS 1997 HY448112 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-06-12 | 2027-04-01 | 2027-04-02 | 2027-04-02 | 2027-04-02 | Orkney Islands | 0 | 56471 | 29804 | 31758.11 | 5554.53 | -154.14 | 0 | 123433.5 | 0 | 123433.5 | 0 | [6 empty] | CM_WWNI | 100%
502834 | Ayrshire Bathing Water Solution Development (IR18) | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS3 | 2020-04-07 | 2020-05-18 | 2019-12-09 | 2021-04-12 | 2021-07-13 | East Ayrshire | 0 | 0 | 0 | 148647.66 | 278937.35 | 194052.43 | 14989.34 | 636626.78 | 83373.23 | 720000.01 | 2277461.36 | [6 empty] | EC16B | 100%
500523 | Ayrshire Strategic Resilience | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS0 | 2016-11-02 | 2020-07-20 | 2020-08-04 | 2023-03-28 | 2023-06-30 | South Ayrshire | 0 | 331276.92 | 292053.08 | 753269 | 750440.04 | 3902464.03 | 18092662.73 | 24122165.8 | 50877834.2 | 75000000 | 0 | [6 empty] | SR15_EXC_EXC | 100% | bar: Regulatory Outputs OMG-07
502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS5 | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-27 | 2019-03-29 | East Ayrshire | 0 | 0 | 1776359 | 41280859 | 14894029.84 | 2280402.37 | -17276.77 | 60214373.44 | 0 | 60214373.44 | 0 | [6 empty] | SR15_EXC_EXC | 100%
403887 | Ayrshire Water Mains Refurbishment - Afton | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2014-07-10 | 2015-01-23 | 2015-01-26 | 2016-08-12 |  | East Ayrshire | 1500715 | 2698535 | 666534 | -26022 | -157670.29 | -13685.22 | 340.75 | 3168032.24 | 0 | 4668747.24 | 0 | [6 empty] | CM_WSI | 100%
403889 | Ayrshire Water Mains Refurbishment - Bradan A | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2014-07-10 | 2015-05-25 | 2015-06-25 | 2018-08-20 |  | South Ayrshire | 114943.4 | 3927523.6 | 3535670 | 2542941.82 | 244235.1 | 159095.51 | 0 | 10409466.03 | 0 | 10524409.43 | 0 | [6 empty] | CM_WSI | 100%
403888 | Ayrshire Water Mains Refurbishment - Bradan B | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2014-07-10 | 2015-12-03 | 2015-12-07 | 2018-07-30 |  | South Ayrshire | 298158.19 | 1864758.81 | 5341320 | 4501579.63 | 135118.22 | 436.9 | 0 | 11843213.56 | 0 | 12141371.75 | 0 | [6 empty] | CM_WSI | 100%
403890 | Ayrshire Water Mains Refurbishment - Dougliehill | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2014-07-10 | 2015-03-30 | 2015-04-16 | 2017-05-10 |  | Inverclyde | 146251 | 718528 | 79562.03 | -21334.5 | -267080.25 | 23967.74 | 0 | 533643.02 | 0 | 679894.02 | 0 | [6 empty] | CM_WSI | 100%
403891 | Ayrshire Water Mains Refurbishment - Kaim Lochwinnoch | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2014-07-10 | 2015-03-30 | 2015-03-30 | 2017-05-18 |  | Renfrewshire | 615298 | 1495271 | 199767.38 | -39500.79 | -160426.72 | 21963.22 | 0 | 1517074.09 | 0 | 2132372.09 | 0 | [6 empty] | CM_WSI | 100%
403863 | Ayrshire Water Quality Sampling - Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-11 | 2014-06-11 | 2014-06-11 | 2017-03-09 |  | South Ayrshire | 9350 | 40650 | -43941.21 | -1071.73 | 0 | 0 | 0 | -4362.94 | 0 | 4987.06 | 0 | [6 empty] | CM_WSI | 100%
403568 | Baberton Square Juniper Green Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2013-08-30 | 2015-01-20 | 2015-01-26 | 2015-03-30 | 2015-03-30 | City of Edinburgh | 143194 | 16786.07 | -0.01 | 783.45 | 0 | 0 | 0 | 17569.51 | 0 | 160763.51 | 372507.62 | [6 empty] | CS11 | 100%
502600 | Back Tolsta- Main out form North Lochs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2016-05-18 | 2019-09-30 | 2019-09-30 | 2021-09-23 | 2021-12-23 | Na H-Eileanan an Iar | 0 | 0 | 0 | 232046 | 573417.96 | 3072300.04 | 4463445.47 | 8341209.47 | 989796.53 | 9331006 | 3022704.59 | [6 empty] | DW25P | 10% | DW3B | 90% | bar: Regulatory Outputs OMG-01
500795 | Backies RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-25 | 2019-02-15 | Highland | 0 | 89774 | 110985.97 | 186230.4 | 80328.35 | 29586.34 | -3729.47 | 493175.59 | 0 | 493175.59 | 810447.22 | [6 empty] | DW5FS | 100%
403721 | Backies WOA - Bridge of Horn SR Outlet Rehab - Pitfure and Knockarthur WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-12 | 2014-05-27 | 2014-06-30 | 2015-01-05 |  | Highland | 309486.23 | 811.81 | 342.64 | 0 | 0 | 0 | 0 | 1154.45 | 0 | 310640.68 | 0 | [6 empty] | CM_WSI | 100%
403383 | Backies WOA - Golspie Secondary Link Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-07 | 2013-05-13 | 2013-09-18 | 2014-05-12 |  | Highland | 332839 | 0 | -159.47 | 0 | 0 | 0 | 0 | -159.47 | 0 | 332679.53 | 0 | [6 empty] | CM_WSI | 100%
403199 | Backies WOA - Navidale Helmsdale Rehab-Network Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-12-17 | 2014-02-21 | 2014-06-30 | 2017-09-26 |  | Highland | 322176 | 23702 | 35688.92 | 20303.5 | -49.17 | 0 | 0 | 79645.25 | 0 | 401821.25 | 0 | [6 empty] | CM_WSI | 100%
504389 | Backies WOA - Park Terrace Brora - Quality & UITS Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-01-22 | 2020-09-03 | 2021-01-12 | 2021-01-14 | Highland | 0 | 0 | 0 | 0 | 0 | 300 | 135700 | 136000 | 0 | 136000 | 0 | [6 empty] | WSI | 100%
501259 | Backies WOA Brora Dalchalm & Victoria Road Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-02-19 | 2018-10-24 | 2018-10-29 | 2020-12-04 | 2020-12-04 | Highland | 0 | 1308.41 | 2087 | 69137.59 | 833023.6 | 278974.21 | 2663.82 | 1187194.63 | 37521 | 1224715.63 | 0 | [6 empty] | CM_WSI | 100%
501198 | Backies WTW Dosing & Chemical Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-04-25 | 2027-05-25 | 2027-08-04 | 2028-04-24 | 2028-07-25 | Highland | 0 | 0 | 86866.37 | 0 | 0 | 101.4 | -26.2 | 86941.57 | 749058.63 | 836000.2 | 0 | [6 empty] | CM_WSNI | 100%
402905 | Backies WTW Loch Lunndaidh RWM Rehab and Abstraction Chamber Replace | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-11 | 2013-07-17 | 2013-10-28 | 2015-02-09 |  | Highland | 782545.41 | 7794.59 | -3471.12 | 0 | 0 | 0 | 0 | 4323.47 | 0 | 786868.88 | 0 | [6 empty] | CM_WSI | 100%
402276 | Backies WTW Replacement Lime Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-11 | 2013-11-25 | 2014-03-31 | 2015-01-16 |  | Highland | 540209.07 | 337.5 | 277.23 | 0 | 0 | 0 | 0 | 614.73 | 0 | 540823.8 | 0 | [6 empty] | CM_WSNI | 100%
403266 | Backlog of missing M&E plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-01 | 2013-07-03 | 2013-07-03 | 2016-08-01 |  | All East Unitary Authorities | 438898 | -26250.02 | 60 | 0 | 0 | 0 | 0 | -26190.02 | 0 | 412707.98 | 0 | [6 empty] | CM_WWI | 100%
500956 | Backup Restore and Archive | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-05 | 2016-09-29 | 2016-09-29 | 2017-11-15 |  | Scottish Water Wide | 0 | 165092 | 1079630.52 | 152559.98 | 0 | 0 | 0 | 1397282.5 | 0 | 1397282.5 | 0 | [6 empty] | CM_M&G | 100%
401361 | Backwater Reservoir Spillway Joint Sealant Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-10 | 2015-06-25 | 2015-06-03 | 2017-03-01 | 2017-06-09 | Angus | 296794 | 724855 | 68348.69 | 1190.99 | -1006.02 | 0 | 0 | 793388.66 | 0 | 1090182.66 | 0 | [6 empty] | CM_WSI | 100%
502844 | Badachro WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2027-04-02 | 2028-08-24 | 2028-12-22 | 2020-03-31 | 2030-03-21 | Highland | 0 | 0 | 0 | 21033.13 | 687.48 | 0 | -20361.16 | 1359.45 | 0 | 1359.45 | 136478.56 | [6 empty] | WG1 | 100%
501197 | Badachro WTW Intake Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-11-30 | 2016-12-08 | 2018-09-07 | 2018-09-07 | Highland | 0 | 9849 | 60703.23 | 162325.13 | 37101.64 | -6572.92 | 0 | 263406.08 | 0 | 263406.08 | 0 | [6 empty] | CM_WSI | 100%
45307 | Badachro WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-11 | 2011-07-22 | 2012-01-19 | 2012-03-14 | Highland | 176835.3 | -135.35 | 0 | 0 | 0 | 0 | 0 | -135.35 | 0 | 176699.95 | 0 | [6 empty] | DW13 | 100%
502843 | Badcaul WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2027-04-02 | 2033-10-20 | 2034-02-17 | 2020-03-31 | 2035-05-17 | Highland | 0 | 0 | 0 | 20930.23 | 902.22 | -20280.63 | 0 | 1551.82 | 0 | 1551.82 | 136478.56 | [6 empty] | WG1 | 100%
500226 | Badentinan - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-09-30 | 2020-09-30 | Moray | 0 | 1449 | 0 | 43421 | 63943.12 | 434248.89 | 6396.29 | 549458.3 | 0 | 549458.3 | 835826.18 | [6 empty] | DW5FS | 10.4% | DW5 | 89.6% | bar: Regulatory Outputs OMG-02
500844 | Badentinan RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-23 | 2021-03-31 | Moray | 0 | 19062.39 | 9488.15 | 41920.38 | 219638.01 | 145889.56 | 57916.81 | 493915.3 | -1230.43 | 492684.87 | 1051546.41 | [6 empty] | DW5FS | 100%
403197 | Badentinan Wellfield Control Panel Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2013-08-19 | 2013-11-01 | 2015-02-20 |  | Moray | 936364 | 44163.16 | 812.76 | 0 | 0 | 0 | 0 | 44975.92 | 0 | 981339.92 | 0 | [6 empty] | CM_WSNI | 100%
503419 | Badentinan WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2018-10-31 | 2021-06-07 | 2021-09-21 | 2022-12-20 | 2023-03-23 | Moray | 0 | 0 | 0 | 0 | 34589.25 | -8727.56 | 1593.53 | 27455.22 | 136351.05 | 163806.27 | 0 | [6 empty] | CM_WSNI | 100%
501218 | Badentinan WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2018-03-28 | 2020-09-28 | 2020-12-14 | 2021-06-26 | 2021-09-13 | Aberdeenshire | 0 | 4604.65 | 1324.77 | 6865.27 | 872.11 | 10495.62 | 42471.59 | 66634.01 | 32333.24 | 98967.25 | 319550.12 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
46256 | Badinsgill Reservoir - Various repairs | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-11-13 | 2010-06-28 | 2010-11-02 | 2012-02-14 |  | Scottish Borders | 280871.42 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 280871.55 | 0 | [6 empty] | CM_WSI | 100%
501526 | Bairdsknowe SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-12-22 | 2028-07-07 | 2028-08-07 | 2029-03-30 | 2029-07-02 | East Renfrewshire | 0 | 0 | 2612.08 | 52.07 | -27.84 | 3387.63 | 0 | 6023.94 | 339041.14 | 345065.08 | 0 | [6 empty] | CM_WSNI | 100%
402853 | Balaclava Quay - Shore Street Fraserburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-08-26 | 2014-08-26 | 2014-08-29 | 2014-09-01 | Aberdeenshire | 22777.22 | -571.18 | 0 | 0 | 0 | 0 | 0 | -571.18 | 0 | 22206.04 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502760 | Balado ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | Perth and Kinross | 0 | 0 | 0 | 34831.63 | 14.27 | 0 | -14.27 | 34831.63 | 0 | 34831.63 | 136478.56 | [6 empty] | SG1 | 100%
45547 | Balbeggie STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-03-24 | 2011-07-25 | 2012-03-22 | 2012-03-27 | Perth and Kinross | 491171.2 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 491201.92 | 0 | [6 empty] | WQ01 | 100%
503320 | Balbeggie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-09-23 | 2024-03-14 | 2024-07-10 | 2025-07-08 | 2025-10-08 | Perth and Kinross | 0 | 0 | 0 | 0 | 79559.16 | 5106.35 | 30960.62 | 115626.13 | 2884373.86 | 2999999.99 | 136478.56 | [6 empty] | SG1 | 100%
400056 | Balfron STW Refurb STW002010 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | Stirling | 30347.9 | 1.1 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 30349 | 0 | [6 empty] | CM_WWNI | 100%
401585 | Balgray Reservoir - Seepage QH | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-08 | 2011-05-03 | 2011-06-13 | 2014-01-17 | 2014-01-17 | East Renfrewshire | 443245 | -532.49 | 0 | 0 | 0 | 0 | 0 | -532.49 | 0 | 442712.51 | 0 | [6 empty] | CM_WSI | 100%
503601 | Balivanich WwTW - Replacement Dewaterer | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2020-07-23 | 2021-08-17 | 2021-11-18 | 2022-06-20 | 2022-08-18 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 733.74 | -733.74 | 0 | 299999.99 | 299999.99 | 0 | [6 empty] | CM_WWNI | 100%
503401 | Balkiellie TWS - QUALITY (Reduction of risk identified in Drinking Water Safety Plan - Transmission) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS7 | 2019-02-07 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2020-04-13 | Angus | 0 | 0 | 0 | 0 | 37986.64 | -29284.19 | 56297.55 | 65000 | 0 | 65000 | 466277.79 | [6 empty] | DW25T | 100%
500845 | Ballachulish RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-11-04 | 2016-03-25 | 2017-01-02 | 2018-03-31 | 2018-06-30 | Highland | 0 | 3166.17 | 9897.5 | 37880.89 | 0 | 0 | 140.85 | 51085.41 | 0 | 51085.41 | 15535.81 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 39.24
501064 | Ballater WTW - Source | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-07-02 | 2028-12-07 | 2029-04-04 | 2030-03-25 | 2030-06-17 | Aberdeenshire | 0 | 16952.66 | 1001.08 | 272.7 | 631.84 | 0 | 17.37 | 18875.65 | 981124.34 | 999999.99 | 0 | [6 empty] | CM_WSI | 100%
503270 | Ballater WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-06-17 | 2023-10-31 | 2024-03-04 | 2025-02-28 | 2025-06-02 | Aberdeenshire | 0 | 0 | 0 | 0 | 79664.11 | 5416.78 | 35795.8 | 120876.69 | 2879123.36 | 3000000.05 | 136478.56 | [6 empty] | SG1 | 100%
403586 | Ballo Reservoir - Emergency Valve Tower Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-25 | 2014-02-12 | 2014-02-12 | 2016-09-26 | 2014-08-05 | Scottish Water Wide | 836876 | 16443 | 5128.34 | 48.04 | 0 | 0 | 0 | 21619.38 | 0 | 858495.38 | 0 | [6 empty] | CM_WSI | 100%
502870 | Ballygrant WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2027-04-02 | 2033-10-13 | 2034-02-03 | 2035-01-26 | 2035-04-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21238 | 1850.55 | -19376.24 | 0 | 3712.31 | 0 | 3712.31 | 136478.56 | [6 empty] | WG1 | 100%
402008 | Balmaha | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-05-27 | 2014-07-31 | 2014-09-08 | 2015-03-11 | 2015-03-23 | Stirling | 744278.86 | -1397.43 | 36.75 | 0 | 0 | 0 | 0 | -1360.68 | 0 | 742918.18 | 85083 | [6 empty] | WQ01 | 100%
503108 | Balmaha WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-04-28 | 2022-07-26 | 2022-11-17 | 2023-07-05 | 2023-10-05 | Stirling | 0 | 0 | 0 | 30976.74 | 52621.46 | 53165.33 | -44933 | 91830.53 | 1908169.46 | 1999999.99 | 136478.56 | [6 empty] | SG1 | 100%
505276 | Balmedie Eventide SPS - Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 188.79 | 0 | 188.79 | 0 | 188.79 | 0 | [6 empty] | CM_WWNI | 100%
502813 | Balmedie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-03-08 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Aberdeenshire | 0 | 0 | 0 | 67136.2 | 15448.8 | 33214.61 | 31200.39 | 147000 | 4755060 | 4902060 | 136478.56 | [6 empty] | SG1 | 100%
500002 | Balmichael RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2020-02-17 | 2020-09-30 | North Ayrshire | 0 | 44466 | 14100 | 71361 | 130509.27 | 53423.75 | -1124.94 | 312735.08 | 0 | 312735.08 | 1048999.43 | [6 empty] | DW5FS | 100%
502094 | Balmichael WTW | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-05-22 | 2019-05-22 | 2019-09-26 | 2019-09-27 | 2019-09-27 | North Ayrshire | 0 | 16326 | 1157.27 | 0 | 833.51 | -9538.49 | 0 | 8778.29 | 0 | 8778.29 | 0 | [6 empty] | CM_WSI | 100%
502564 | Balmichael WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-04-06 | 2021-12-06 | 2021-12-06 | 2022-08-26 | 2022-11-28 | North Ayrshire | 0 | 0 | 20930.23 | 1679.04 | 6320.73 | 14086.16 | 6876.38 | 49892.54 | 950107.44 | 999999.98 | 136478.56 | [6 empty] | WG1 | 100%
46837 | Balmichael WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-09-14 | 2011-10-17 | 2015-08-20 | 2016-12-20 | North Ayrshire | 3449705.96 | 79678.71 | 16329.86 | -2539.08 | 0 | 0 | 0 | 93469.49 | 0 | 3543175.45 | 81535 |  |  |  |  | 50776.88 |  | DW23 | 100%
501196 | Balmoor (Forehill WTW) RWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-09-23 | 2018-02-26 | 2018-02-26 | 2018-03-06 | 2018-03-06 | Aberdeenshire | 0 | 6087.85 | 17675.82 | -1294.42 | 0 | 0 | 0 | 22469.25 | 0 | 22469.25 | 0 | [6 empty] | CM_WSNI | 100%
500846 | Balmore A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-09-24 | 2020-09-24 | North Lanarkshire | 0 | 12698.42 | 12928.34 | 14062.57 | 144909.81 | 15867.19 | 1581.65 | 202047.98 | 0 | 202047.98 | 701949.75 | [6 empty] | DW5FS | 100%
500847 | Balmore C5 South RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-07-27 | 2018-09-28 | 2018-10-01 | 2019-01-31 | 2019-08-31 | Glasgow City | 0 | 27600 | 11361.76 | 124769.24 | 351996.39 | -137051.88 | -0.01 | 378675.5 | 0 | 378675.5 | 1140801.77 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 5.44
500227 | Balmore E - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-07 | 2020-01-31 | West Lothian | 0 | 6098 | 30706.71 | 31617.25 | 18440.5 | 184572.96 | 4189.13 | 275624.55 | 0 | 275624.55 | 1096553.94 | [6 empty] | DW5FS | 29.49% | DW5MR | 70.51%
500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2019-12-23 | 2020-03-31 | West Lothian | 0 | 104446 | 1064630 | 1792108 | 946308.69 | 241491.05 | 5440.77 | 4154424.51 | 0 | 4154424.51 | 2734927.74 | [6 empty] | DW5 | 100%
500848 | Balmore F RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-01 | 2019-05-14 | West Lothian | 0 | 5413.63 | 8820.37 | 760.73 | 113256.16 | 4034.81 | 1063.26 | 133348.96 | 0 | 133348.96 | 217432.61 | [6 empty] | DW5FS | 100%
400109 | Balmore Gowanbank Pumps Crawhill Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2010-02-23 | 2010-02-22 | 2010-11-15 | 2012-09-26 |  | Falkirk | 2225356 | 197289 | 1219597.9 | 1633871.74 | 799552.75 | 3232.59 | 0 | 3853543.98 | 0 | 6078899.98 | 0 | [6 empty] | CM_WSI | 100%
502430 | Balmore Pipe Bridges | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2018-01-22 | 2021-06-21 | 2021-09-23 | 2022-06-06 | 2022-09-06 | East Dunbartonshire | 0 | 0 | 23738.26 | 20517.34 | 84319.04 | 216095.09 | 973583.87 | 1318253.6 | 6681746.41 | 8000000.01 | 0 | [6 empty] | SR21_WA | 100%
502783 | Balmore Pipebridge Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-09-06 | 2018-12-20 | 2019-01-15 | 2021-03-18 | 2021-06-18 | Glasgow City | 0 | 0 | 0 | 85000 | 397484.24 | 953166.18 | 214879.65 | 1650530.07 | 5166.66 | 1655696.73 | 0 | [6 empty] | CM_WSI | 100%
501082 | Balmore South Region Tweed WOA Dechmont WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-28 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | West Lothian | 0 | 14760 | -11329.46 | 1973.72 | 0 | 0 | -0.26 | 5404 | 0 | 5404 | 0 | [6 empty] | CM_WSI | 100%
501081 | Balmore South Region Tweed WOA East Craigs WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-06 | 2028-07-17 | 2028-08-28 | 2029-03-28 | 2029-06-28 | West Lothian | 0 | 59472 | -12687 | 0 | -2719 | 2931.93 | -935.3 | 46062.63 | 273468.19 | 319530.82 | 0 | [6 empty] | CM_WSI | 100%
500035 | Balmore WTW - Filter Refurbishment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS6 | 2016-04-01 | 2017-03-22 | 2017-03-22 | 2019-12-31 | 2020-03-20 | East Dunbartonshire | 0 | 500406 | 654504.78 | 1503828.33 | 1530676.44 | 102612.45 | 33969.58 | 4325997.58 | 8170.42 | 4334168 | 929845.93 | [6 empty] | CM_WSNI | 8.53% | DW25P | 91.47% | bar: Regulatory Outputs OMG-04
502550 | Balmore WTW - Garbethill & Drumbow SRs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2018-04-30 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | North Lanarkshire | 0 | 0 | 0 | 17909.57 | 455.88 | 0 | 0 | 18365.45 | 0 | 18365.45 | 929845.93 | [6 empty] | DW25P | 100%
401053 | Balmore WTW Filter Refurb Media Replacement | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | [5 empty] | East Dunbartonshire | 0 | 0 | 0 | 0 | 206.4 | 0 | 0 | 206.4 | 0 | 206.4 | 0 | [6 empty] | CM_WSNI | 100%
502210 | Balquhidder WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-05-11 | 2016-09-13 | 2016-09-13 | 2017-05-05 | 2017-10-11 | Stirling | 0 | 0 | 44.15 | 0 | 0 | 0 | 0 | 44.15 | 0 | 44.15 | 270378.76 | [6 empty] | DW25P | 100%
402600 | Banchory Raemoir Rd WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2012-12-13 | 2013-01-21 | 2013-10-01 |  | All East Unitary Authorities | 87764 | -395.66 | 0 | 0 | 0 | 0 | 0 | -395.66 | 0 | 87368.34 | 0 | [6 empty] | CM_WWNI | 100%
501021 | Banchory WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2018-01-09 | 2020-04-28 | 2020-05-18 | 2022-02-17 | 2022-05-20 | Aberdeenshire | 0 | 43768.74 | 76143.85 | 51038.96 | 397233.62 | 510192.87 | 1515971.83 | 2594349.87 | 2813987.13 | 5408337 | 136478.56 | [6 empty] | CM_WWNI | 4% | SG1 | 96%
402856 | Bank Street Cupar | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-08-28 | 2014-10-27 | 2015-01-28 | 2015-02-02 | Fife | 140163 | 17498.16 | 0 | 0 | 0 | 0 | 0 | 17498.16 | 0 | 157661.16 | 4199.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503930 | Bannockburn SST Replacement Storm Return Screw Pump | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2020-11-22 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 7042.06 | 92957.94 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWI | 100%
501160 | Barassie SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2015-12-10 | 2017-03-28 | 2017-06-30 | 2019-07-22 | 2019-07-22 | South Ayrshire | 0 | 9030.91 | 262407.05 | 871421.04 | 793882 | 39030 | 0 | 1975771 | 2400 | 1978171 | 0 | [6 empty] | CM_WWNI | 100%
502896 | Barcraigs Drawdown Capacity Enhancement (MIoS) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-09-18 | 2020-08-17 | 2020-10-19 | 2021-06-22 | 2021-09-20 | Renfrewshire | 0 | 0 | 0 | 21315.78 | 7847.15 | 92259.55 | 1400110.02 | 1521532.5 | 478467.59 | 2000000.09 | 0 | [6 empty] | CM_WSI | 100%
402358 | Barcraigs Impounding Resevoir - Resmix System | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-20 | 2012-03-28 | 2012-04-27 | 2013-06-26 |  | Renfrewshire | 418100 | 867.57 | 0 | 0 | 0 | 0 | 0 | 867.57 | 0 | 418967.57 | 0 | [6 empty] | CM_WSI | 100%
46244 | Barcraigs Longpark embankment - Valve Chamber | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-12-11 | 2010-09-29 | 2010-10-28 | 2011-01-19 |  | Renfrewshire | 30696.12 | 5455.88 | 0 | 0 | 0 | 0 | 0 | 5455.88 | 0 | 36152 | 0 | [6 empty] | CM_WSI | 100%
500655 | Barmore Road Tarbert | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2018-04-27 | 2020-02-04 | 2020-05-04 | 2021-06-09 | 2021-07-09 | Argyll and Bute-North Argyll | 0 | 72873 | 95043 | 51084 | 300327 | 849749.62 | 1082482.65 | 2451559.27 | 146594.18 | 2598153.45 | 204193.13 | [6 empty] | CS11 | 100%
403274 | Barnton Grove - Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-01-23 | 2014-11-27 | 2015-01-09 | 2015-03-20 | 2015-03-20 | City of Edinburgh | 474654 | -20869 | -0.02 | -1638.26 | 0 | 0 | 0 | -22507.28 | 0 | 452146.72 | 204193.13 | [6 empty] | CS11 | 100%
505303 | Barra DSR - Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | [6 empty] | CM_WSNI | 100%
402635 | Barrasie Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-04-16 | 2013-01-03 | 2013-03-11 | 2014-12-05 |  | South Ayrshire | 1640969 | 21228 | -31370.16 | 0 | 0 | 0 | -17.75 | -10159.91 | 0 | 1630809.09 | 0 | [6 empty] | CM_WWI | 100%
403303 | Barrcraigs Reservoir Pipe through dam failure risk | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2013-02-27 | 2014-08-25 | 2014-10-20 | 2017-11-10 | 2017-11-10 | Renfrewshire | 685659.82 | 478168.51 | 541097.8 | 132308.8 | -24695.52 | 35327.08 | 86.37 | 1162293.04 | 0 | 1847952.86 | 0 | [6 empty] | CM_WSI | 100%
502392 | Barrhead South SDO | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-05-16 | 2017-05-16 | 2017-08-07 | 2021-05-26 | 2021-05-26 | East Renfrewshire | 0 | 0 | 0 | 196261.68 | 0 | 0 | 519565.48 | 715827.16 | 684172.79 | 1399999.95 | 470181.23 | [6 empty] | WG5 | 100%
500116 | Bathgate DOA (DOA000537) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS7 | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2019-03-27 | 2020-01-08 | West Lothian | 0 | 18657 | 155319 | 122816 | 33504 | 28831 | -8760.15 | 350366.85 | 0 | 350366.85 | 277404.61 | [6 empty] | CS16D | 100%
503330 | Bathgate Flood Minimisation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2027-04-01 | 2028-06-14 | 2028-06-22 | 2028-08-02 | 2028-11-02 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 498999.99 | 499999.99 | 0 | [6 empty] | SR21_WA | 100%
30087 | Bathgate STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2010-12-17 | 2011-03-28 | 2012-09-24 | 2012-10-05 | West Lothian | 1993686.17 | 3399.44 | 0 | 0 | 0 | 0 | 0 | 3399.44 | 0 | 1997085.61 | 0 | [6 empty] | CM_WWNI | 20% | EC04A | 80%
502183 | Bathgate Trunk Main - Alternative Mains Feed | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-11-01 | 2022-01-31 | 2022-04-01 | 2023-11-30 | 2023-12-01 | West Lothian | 0 | 20930.23 | 86269.77 | 488747.23 | 162411.49 | 3400.5 | 7488.5 | 769247.72 | 8458071.24 | 9227318.96 | 0 | [6 empty] | CM_WSI | 100%
502242 | Bathgate Trunk Main - Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-06-01 | 2016-08-31 | 2016-08-31 | 2017-03-28 | 2017-03-28 | West Lothian | 0 | 0 | 721017.38 | -20051 | -6188.84 | 77.96 | -0.01 | 694855.49 | 0 | 694855.49 | 0 | [6 empty] | CM_WSI | 100%
502184 | Bathgate Trunk Main Burst Contral | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-03-22 | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 | West Lothian | 0 | 1308.41 | 32669.13 | 355.8 | 64894.76 | 10511.43 | 488.57 | 110228.1 | 0 | 110228.1 | 0 | [6 empty] | CM_WSI | 100%
500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | Scottish Water Wide | 475.02 | 4034.98 | 57396 | 33031.95 | -11809.66 | 0 | 0 | 82653.27 | 0 | 83128.29 | 0 | [6 empty] | EC16 | 100%
49391 | Bathing Waters Programme Holding Line | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MSU | 2016-11-30 | 2017-08-20 | 2017-11-30 | 2019-04-30 | 2019-07-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19133207.65 | [6 empty] | EC02B | 100%
502778 | Battery Park Coarse Screens CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-06-16 | 2019-07-31 | 2019-11-07 | 2020-05-15 | 2020-05-15 | Inverclyde | 0 | 0 | 0 | 3394.85 | 91391.33 | 753631.83 | 145322 | 993740.01 | 3393 | 997133.01 | 0 | [6 empty] | CM_WWNI | 100%
501352 | Battery Park WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-08-31 | 2018-09-05 | 2018-10-10 | 2021-01-29 | 2021-01-29 | Inverclyde | 0 | 0 | 27067 | 271229 | 1618405 | 3308728 | 253355 | 5478784 | 27401 | 5506185 | 0 |  |  |  |  | -67680 |  | CM_WWNI | 100%
500849 | Bayhead Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-06-01 | 2018-06-27 | 2019-02-04 | 2019-06-30 | 2020-01-27 | Na H-Eileanan an Iar | 0 | 4021.83 | 1480.39 | 30733.78 | 88301.99 | 40972.98 | 261.95 | 165772.92 | 0 | 165772.92 | 178298.2 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 65.25
503673 | Beasdale SR10 Completion | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-08-26 | 2015-12-23 | 2016-01-22 | 2019-12-31 | 2019-12-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3232.32 | 3232.32 | 1767.68 | 5000 | 184123.25 | [6 empty] | DW23 | 100% | bar: Regulatory Outputs OMG-03
500690 | Beasdale WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2015-08-26 | 2015-12-23 | 2016-01-22 | 2016-06-23 | 2016-06-24 | Highland | 0 | 336686 | -336686 | 4962.01 | 3000.98 | 0 | 0 | 7962.99 | 0 | 7962.99 | 184123.25 | [6 empty] | DW23 | 100%
45309 | Beasdale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2013-04-01 | 2013-04-02 | 2016-04-01 | Highland | 47621.11 | 22.5 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 47643.61 | 0 | [6 empty] | DW13 | 100%
502369 | Beasdale WTW UV Alterations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-08-26 | 2015-12-23 | 2016-01-22 |  |  | Highland | 0 | 0 | 0 | 2029.38 | 1977.41 | 10649.88 | 2402.37 | 17059.04 | 574229.95 | 591288.99 | 0 | [6 empty] | CM_WSNI | 100%
402857 | Beeches Ladybank Cupar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2012-12-04 | 2013-01-18 | 2015-08-13 | 2015-08-13 | Fife | 42581.6 | -42580.6 | 662.24 | 0 | 0 | -0.01 | 0.01 | -41918.36 | 0 | 663.24 | 204193.13 | [6 empty] | CS11 | 100%
502709 | Beeslack House Pipe Bridge Penicuik | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | Midlothian | 0 | 0 | 0 | 2609.3 | 0 | 0 | -0.3 | 2609 | 0 | 2609 | 0 | [6 empty] | CM_WWI | 100%
500118 | Beeswing DOA (DOA000135) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-08 | 2017-04-04 | 2017-04-04 | Dumfries and Galloway | 0 | 19644 | -2009 | -2696.49 | 41.28 | 0 | 0 | 14979.79 | 0 | 14979.79 | 72047.27 | [6 empty] | CS11 | 100%
402992 | Bell Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-06-03 | 2013-10-25 | 2013-10-25 | Glasgow City | 103140 | -7519.29 | 0 | 0 | 0 | 0 | 0 | -7519.29 | 0 | 95620.71 | 14.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503546 | Belleisle Golf Course CSO Bathing Water Improvement | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | WWINF | Revised Bathing Waters Directive | MS1 | 2019-07-09 | 2020-05-18 | 2020-07-20 | 2021-02-17 | 2021-05-25 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 275965 | 1382631.5 | 1658596.5 | 16753.5 | 1675350 | 2277461.36 | [6 empty] | EC16B | 100%
501527 | Bellsbank High SR Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-28 | 2028-01-25 | 2028-05-30 | 2028-10-09 | 2029-01-09 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145956.97 | 145956.97 | 0 | [6 empty] | CM_WSNI | 100%
503141 | Belmore Tank WSZ - Faslane Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-02 | 2028-02-17 | 2028-04-28 | 2028-11-24 | 2029-02-26 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 7836.28 | 2332.72 | 2314.25 | 6236.77 | 18720.02 | 371279.98 | 390000 | 0 | [6 empty] | CM_WSI | 100%
501209 | Belmore WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS4 | 2017-12-22 | 2018-11-28 | 2019-03-18 | 2020-01-24 | 2020-04-30 | Argyll and Bute-Cowal & Bute | 0 | 12558.14 | 7317.87 | 59031.48 | 201345.51 | 609311 | 17796.08 | 907360.08 | 3436.92 | 910797 | 834383.36 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500855 | Benbecula RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-07-25 | 2018-06-27 | 2019-02-18 | 2019-06-30 | 2019-12-31 | Na H-Eileanan an Iar | 0 | 4692.29 | 1846.8 | 14611.16 | 90096.62 | 33077.43 | 0 | 144324.3 | 0 | 144324.3 | 270193.45 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 75.09
403045 | Benbecula Zone - Ardmore Iron Specials Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2013-01-14 | 2013-09-04 |  | Na H-Eileanan an Iar | 183184.99 | 1634 | 0 | 0 | 0 | 0 | 0 | 1634 | 0 | 184818.99 | 0 | [6 empty] | CM_WSI | 100%
503539 | Bertha Park - Growth - Plan Stage | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW1 | 2020-07-06 | 2021-03-15 | 2021-06-17 | 2022-01-26 | 2022-04-28 | Perth and Kinross | 0 | 0 | 0 | 0 | 48304.07 | 167582.16 | 491061.52 | 706947.75 | 9301052.27 | 10008000.02 | 470181.23 | [6 empty] | WG5 | 100%
503303 | Bertha Park - Perth | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2018-08-14 | 2018-08-14 | 2019-07-10 | 2022-01-21 | 2022-01-21 | Perth and Kinross | 0 | 0 | 0 | 0 | 3742.77 | 3656.65 | -460.84 | 6938.58 | -1299.9 | 5638.68 | 470181.23 | [6 empty] | WG5 | 100%
502766 | Bertha Park Perth - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-10-15 | 2023-11-02 | 2024-03-04 | 2025-02-20 | 2025-05-23 | Perth and Kinross | 0 | 0 | 0 | 83645 | 46696.24 | 194835.09 | 150338.61 | 475514.94 | 42524485.08 | 43000000.02 | 136478.56 | [6 empty] | SG1 | 100%
500951 | Bespoke Application Development Platform Refresh | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2015-09-30 | 2016-05-16 | 2016-05-16 | 2018-11-22 |  | Scottish Water Wide | 0 | 119842 | 485188.83 | 759734.71 | -165162.03 | 0 | 0 | 1199603.51 | 0 | 1199603.51 | 0 | [6 empty] | CM_M&G | 50% | CM_WSI | 50%
403796 | Beyond Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-15 | 2014-10-15 | 2014-11-06 | 2015-03-12 |  | Scottish Water Wide | 1007215 | -17927.06 | 0 | 0 | 0 | 0 | 0 | -17927.06 | 0 | 989287.94 | 0 | [6 empty] | CM_M&G | 100%
500051 | Biggar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS6 | 2016-09-30 | 2018-09-06 | 2018-09-24 | 2019-05-29 | 2019-05-29 | South Lanarkshire | 0 | 46503.28 | 24619.39 | 251268.59 | 856184.64 | 51108.1 | 0 | 1229684 | 9769 | 1239453 | 136478.56 | [6 empty] | SG1 | 100%
501654 | BIGGAR WWTW 2002 NT049369 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | Scottish Borders | 0 | 0 | 0 | 26344.16 | 1774.5 | 0 | 0 | 28118.66 | 0 | 28118.66 | 0 | [6 empty] | CM_WWNI | 100%
402498 | Birgham WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-04-18 | 2014-01-29 | 2014-03-13 | 2014-09-15 | 2014-09-15 | Scottish Borders | 519000 | 432.06 | 0 | 0 | 0 | 0 | 0 | 432.06 | 0 | 519432.06 | 0 | [6 empty] | SG1 | 100%
505935 | Black Cart Water Aesthetic Study - SR21 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MSU | 2020-04-01 | 2020-12-07 | 2021-04-13 | 2021-10-12 | 2022-01-12 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 457.14 | 0 | 457.14 | 0 | 457.14 | 0 | [6 empty] | SR21_WW | 100%
500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-08-27 | 2019-08-01 | Dumfries and Galloway | 0 | 4000 | 12763.62 | 144074.67 | 21594.73 | 30170.56 | 0 | 212603.58 | 0 | 212603.58 | 1905549.22 | [6 empty] | DW5FS | 100%
503426 | Black Esk & Kettleton WRZ - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2020-06-29 | 2021-06-07 | 2021-08-12 | 2022-04-20 | 2022-07-21 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 274342 | 274342 | 825657.94 | 1099999.94 | 0 | [6 empty] | WG1 | 100%
502358 | Black Esk & Winterhope WOA - Gretna Water Supply | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | NONINF | Strategic Capacity | MS0 | 2018-11-21 | 2020-06-30 | 2020-07-06 | 2021-11-01 | 2022-04-01 | Dumfries and Galloway | 0 | 0 | 69147.69 | 24322.57 | 100348.34 | 348767.8 | 1995739 | 2538325.4 | 3131412.6 | 5669738 | 470181.23 | [6 empty] | WG5 | 44.3% | WG1 | 55.7%
500797 | Black Esk RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2019-12-23 | 2021-02-26 | Dumfries and Galloway | 0 | 133210 | 8719.89 | 218976.11 | 136142.64 | 257139.91 | 0 | 754188.55 | 0 | 754188.55 | 1267638.63 | [6 empty] | DW5FS | 100%
500799 | Black Esk Winterhope RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2015-09-30 | 2017-09-29 | 2017-10-11 | 2019-06-30 | 2020-01-24 | Dumfries and Galloway | 0 | 20929 | -1919 | 124172.58 | 163697.38 | 33083.53 | 1499.96 | 341463.45 | 0 | 341463.45 | 291348.7 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 56.19
501140 | Black Esk WOA Birsca WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-05-27 | 2021-10-25 | 2021-11-22 | 2023-11-15 | 2024-02-15 | Dumfries and Galloway | 0 | 76680 | 41139.01 | 283992 | 188963.21 | 2705.73 | -2455.73 | 591024.22 | 6549861.63 | 7140885.85 | 0 | [6 empty] | CM_WSI | 100%
501136 | Black Esk WOA Birset Dalton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501134 | Black Esk WOA Birset WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501135 | Black Esk WOA Burnswark WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501131 | Black Esk WOA Canonbie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501142 | Black Esk WOA Castlemilk WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501130 | Black Esk WOA Clunie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501143 | Black Esk WOA Douglashall WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501132 | Black Esk WOA Eskdale WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 49.5 | 0 | 49.5 | 0 | [6 empty] | CM_WSI | 100%
501133 | Black Esk WOA Jockstown WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501141 | Black Esk WOA Kerrbush WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 81 | -81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501129 | Black Esk WOA Langholm WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501137 | Black Esk WOA Leakaims WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 81 | -81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501138 | Black Esk WOA Shieldhill WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-04 | 2021-12-06 | 2022-01-13 | 2022-10-28 | 2022-10-28 | Dumfries and Galloway | 0 | 97776 | -10683 | 104803 | 100550.44 | -27033.69 | 14675.4 | 280088.15 | 1594615.04 | 1874703.19 | 0 | [6 empty] | CM_WSI | 100%
503047 | Black Esk WTW - CWT short circuiting | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-05-25 | 2023-08-01 | 2023-11-22 | 2024-08-02 | 2024-11-04 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376999.95 | 376999.95 | 0 | [6 empty] | CM_WSNI | 100%
503049 | Black Esk WTW - RGF valves and MEICA | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2014-03-31 | 2016-03-23 | 2016-03-28 | 2017-11-30 | 2021-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 17631.55 | 248528.11 | -457.68 | 20258.72 | 285960.7 | 214098 | 500058.7 | 0 | [6 empty] | CM_WSNI | 100% | bar: Regulatory Outputs OMG-01
46196 | Black Isle Service Reservoir Rationalisation | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-08-12 | 2011-03-22 | 2011-05-02 | 2011-08-29 |  | Highland | 402081.62 | -0.69 | 0 | 0 | 0 | 0 | 0 | -0.69 | 0 | 402080.93 | 0 | [6 empty] | CM_WSNI | 100%
401008 | Blackford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2014-02-27 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | Perth and Kinross | 141079 | 257403 | 212180.64 | -9871.74 | 72.86 | -13440.37 | 13104.58 | 459448.97 | 0 | 600527.97 | 0 | [6 empty] | SG1 | 100%
30097 | Blackridge STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-06-28 | 2010-10-04 | 2012-03-16 | 2012-03-23 | West Lothian | 5265641.6 | 1720.87 | 0 | 0 | 0 | 0 | 0 | 1720.87 | 0 | 5267362.47 | 0 | [6 empty] | CM_WWNI | 8.955% | EC10A | 30.35% | EC04A | 60.7%
501709 | Blackridge WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-02 | 2016-06-29 | West Lothian | 0 | 0 | 1674.42 | 138.65 | 61.22 | 0 | -200.29 | 1674 | 0 | 1674 | 0 | [6 empty] | CM_WWI | 100%
401345 | Blackstand WSZ Low Pressure Enhancement WSZ000184 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-12-13 | 2013-02-25 | 2014-09-04 | 2013-09-30 | Highland | 80825 | -1758.88 | 98.34 | 0 | 0 | 0 | 0 | -1660.54 | 0 | 79164.46 | 72 | [6 empty] | CS1 | 100%
500120 | Blackwood DOA (DOA000598) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2017-04-30 | 2017-07-31 | South Lanarkshire | 0 | 51658 | 53991 | 6357.43 | 123.84 | 0 | 0.16 | 112130.43 | 0 | 112130.43 | 72047.27 | [6 empty] | CS11 | 44.65% | CS16D | 55.35% | bar: Regulatory Outputs OMG-22
502815 | Blackwood WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-04-09 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | South Lanarkshire | 0 | 0 | 0 | 80034.79 | 17145.69 | 31731.78 | 12882.29 | 141794.55 | 1858205.5 | 2000000.05 | 136478.56 | [6 empty] | SG1 | 100%
503502 | Blairdardie (Rotherwood) Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-05-03 | 2022-02-14 | 2022-04-22 | 2022-09-06 | 2022-12-07 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 6198.34 | 6198.34 | 685781.69 | 691980.03 | 0 | [6 empty] | CM_M&G | 100%
503231 | Blairgowrie WwTW - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-01-28 | 2019-01-28 | 2019-05-31 | 2021-02-01 | 2021-02-01 | Perth and Kinross | 0 | 0 | 0 | 0 | 184249.6 | 209658.22 | 61896.33 | 455804.15 | 2354 | 458158.15 | 0 | [6 empty] | CM_WWNI | 100%
502818 | Blairgowrie WwTW - Investigation and Scope Definition for Potential | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-02-02 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Perth and Kinross | 0 | 0 | 0 | 64892.94 | 24485.8 | 21353.59 | 31267.69 | 142000.02 | 2494840.24 | 2636840.26 | 136478.56 | [6 empty] | SG1 | 100%
502931 | Blairgowrie WwTW - Sludge Thickener | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-10-31 | 2018-08-23 | 2019-03-11 | 2020-07-30 | 2020-07-30 | Perth and Kinross | 0 | 0 | 0 | 6800 | 286583.53 | 181582.1 | 16327.87 | 491293.5 | 2869.48 | 494162.98 | 0 | [6 empty] | CM_WWNI | 100%
400062 | Blairingone WwTW Upgrade WQ01 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-08-31 | 2012-02-21 | 2012-08-07 | 2013-02-14 | 2013-03-21 | Clackmannanshire | 933359.83 | -755.31 | 0 | 0 | 0 | 0 | 15.36 | -739.95 | 0 | 932619.88 | 1000.61 | [6 empty] | CM_WWNI | 10% | WQ01 | 90%
501565 | Blairlinnans Main Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2016-02-10 | 2016-08-31 | 2016-09-26 | 2019-03-18 | 2019-03-18 | West Dunbartonshire | 0 | 5514 | 563128.15 | 634631 | 1018492 | 2874.26 | -0.02 | 2224639.39 | 0 | 2224639.39 | 0 | [6 empty] | CM_M&G | 100%
503600 | Blairlinnans Milton Pipeline Emergency Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2020-04-01 | 2020-03-19 | 2020-01-06 | 2020-08-20 | 2020-08-20 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 3800000 | 1069019.54 | 4869019.54 | 0 | 4869019.54 | 0 | [6 empty] | CM_WSI | 100%
503408 | Blairlinnans PSC TM Monitoring | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS0 | 2020-02-20 | 2021-05-24 | 2021-08-10 | 2022-05-12 | 2022-08-12 | West Dunbartonshire | 0 | 0 | 0 | 0 | 32148.84 | 55370.33 | 78603.33 | 166122.5 | 2995423.73 | 3161546.23 | 37600000 | [6 empty] | SR15_EXC_EXC | 100%
501215 | Blairlinnans WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-21 | 2016-09-08 | 2016-09-09 | 2016-09-30 | 2016-09-30 | Inverclyde | 0 | 3341.78 | 2231.83 | 0 | 341.04 | 0 | 0 | 5914.65 | 0 | 5914.65 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
505145 | Blairlinnans WTW - final sample tap access improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-06-30 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 1685 | 118 | 1803 | 0 | 1803 | 0 | [6 empty] | WSNI | 100%
503575 | Blairlinnans WTW - SCADA replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-09-09 | 2019-09-09 | 2019-09-23 | 2020-10-08 | 2021-03-03 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 436706.5 | 63048.71 | 499755.21 | 244.8 | 500000.01 | 0 | [6 empty] | CM_WSNI | 100%
502565 | Blairnamarrow WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2020-08-05 | 2020-08-31 | 2020-08-31 | 2021-09-07 | 2021-09-08 | Moray | 0 | 0 | 20930.23 | 2988.95 | 89869.85 | 87210.97 | 0 | 201000 | 0 | 201000 | 136478.56 | [6 empty] | WG1 | 100%
403139 | Blairnamarrow WTW to Tomintoul - Replacement Water Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-12 | 2013-06-28 | 2013-09-02 | 2014-11-15 |  | Moray | 447551 | -7274 | 3744.23 | 0 | 0 | 0 | 0 | -3529.77 | 0 | 444021.23 | 0 | [6 empty] | CM_WSI | 100%
403934 | Blairythan Terrace (Foveran) ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS1 | 2017-06-20 | 2020-06-29 | 2020-08-10 | 2021-08-23 | 2021-11-24 | Aberdeenshire | 2745 | 38205.19 | 21927.45 | 28903.36 | 254723.97 | 130785.86 | 927826.46 | 1402372.29 | 586382.72 | 1991500.01 | 0 |  |  |  |  | 11650 |  | SG1 | 100%
500770 | Blantyre Farm Road Uddingston Replace Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-24 | 2017-12-21 | 2018-02-26 | 2018-12-20 | 2018-12-20 | South Lanarkshire | 0 | 26795 | 98510 | 420695 | 505938 | 6303.76 | -147.76 | 1058094 | 0 | 1058094 | 0 | [6 empty] | CM_WWI | 100%
500694 | Bo ness WWTW NT022813 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-08-25 | 2018-11-30 | 2018-12-18 | 2020-10-06 | 2020-11-30 | Falkirk | 0 | 38324 | 261068.37 | 130952.12 | 517779.64 | 1136329.52 | 233176.26 | 2317629.91 | 108478.09 | 2426108 | 0 |  |  |  |  | 21630 |  | CM_WWNI | 100%
500864 | Boardhouse WTW - Auto Coagulation Control | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2015-08-10 | 2017-05-31 | 2017-08-02 | 2018-03-31 | 2020-05-01 | Orkney Islands | 0 | 1337.86 | 24414.31 | 227533.02 | 46839.46 | 2535.1 | 0 | 302659.75 | 0 | 302659.75 | 456504.91 | [6 empty] | DW25P | 5% | DW3C | 95% | bar: Regulatory Outputs OMG-01
300016 | Boardhouse WTW - Kirbister WTW Provision of Chloramination | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-05-23 | 2011-09-20 | 2011-10-31 | 2012-08-15 | 2013-07-25 | Orkney Islands | 3535272.03 | -430 | 0 | 0 | 0 | 0 | 0 | -430 | 0 | 3534842.03 | 5597 | [6 empty] | DW3 | 100%
502235 | Boardhouse WTW - Network Dead Ends | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2016-11-18 | 2017-10-31 | 2017-10-31 | 2019-02-28 | 2019-02-28 | Orkney Islands | 0 | 0 | 38463.2 | 52908.8 | 196782.38 | 327.09 | -421.59 | 288059.88 | 0 | 288059.88 | 0 | [6 empty] | DW25D | 100%
501570 | Boardhouse WTW - Quality (Reduction of risks identified in Drinking Water Safety Plan) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2016-03-25 | 2017-09-28 | 2017-10-23 | 2018-01-31 | 2019-09-30 | Orkney Islands | 0 | 4696.28 | 5496.43 | 52309.95 | 11395.94 | 15.39 | 731.94 | 74645.93 | 21.52 | 74667.45 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502186 | Boardhouse WTW - SR Dead Zones | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-09-21 | 2016-09-30 | 2016-11-07 | 2019-09-30 | 2019-09-30 | Orkney Islands | 0 | 2093 | 82392.9 | 5583.41 | 2339.54 | 29288.78 | 3302.37 | 125000 | 0 | 125000 | 466277.79 |  |  |  |  | 2350 |  | DW25T | 100%
502388 | Boardhouse WTW- Filter Remedial Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-01-26 | 2022-04-13 | 2022-08-16 | 2023-03-22 | 2023-06-22 | Orkney Islands | 0 | 0 | 10046.51 | 3142.96 | 5111.2 | 12578.31 | 50784.77 | 81663.75 | 418336.26 | 500000.01 | 0 | [6 empty] | CM_WSNI | 100%
400258 | Boardhouse WTW Wastewater Treatment Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-01-25 | 2010-03-11 | 2011-10-10 | 2017-09-29 |  | Orkney Islands | 283940 | 571 | 512.74 | 0 | 0 | 0 | 0.26 | 1084 | 0 | 285024 | 0 | [6 empty] | CM_WSNI | 100%
400815 | Boat of Garten WwTW - Growth | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-05-03 | 2013-11-18 | 2013-11-25 | 2015-06-10 | 2015-06-10 | Highland | 4883648.21 | 440694.64 | 12963.31 | -1080.77 | 0 | 0 | 0 | 452577.18 | 0 | 5336225.39 | 16065.69 | [6 empty] | CS11A | 1.982% | CM_WWI | 2.972% | SG1 | 95.05%
403284 | Bogend Farm - Mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-08 | 2013-03-19 | 2013-03-19 | 2013-09-13 |  | West Lothian | 176014 | -17.57 | 0 | 0 | 0 | 0 | 700 | 682.43 | 0 | 176696.43 | 0 | [6 empty] | CM_WSI | 100%
501528 | Bomains TWS Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-07-22 | 2028-07-03 | 2028-11-06 | 2029-06-21 | 2029-09-21 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617604.02 | 1617604.02 | 0 | [6 empty] | CM_WSNI | 100%
502427 | Bonchester Bridge WwTW Outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2017-06-19 | 2017-09-18 | 2017-10-02 | 2017-12-31 | 2018-01-31 | Scottish Borders | 0 | 0 | 4280.32 | 26271.92 | 16632.76 | -2185 | 0 | 45000 | 0 | 45000 | 30997.67 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
45405 | Bonchester WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2012-09-10 | 2013-05-29 | 2013-08-22 | Scottish Borders | 1002209.01 | -18746.08 | 0 | 0 | 0 | 0 | 0 | -18746.08 | 0 | 983462.93 | 47047 | [6 empty] | DW23 | 100%
500798 | Bonkle Bridge Newmains Replace Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-24 | 2017-09-12 | 2018-03-26 | 2018-11-29 | 2018-11-29 | South Lanarkshire | 0 | 62345 | 94301 | 204917.34 | 215947.66 | 36085 | 0 | 613596 | 0 | 613596 | 0 | [6 empty] | CM_WWI | 100%
500800 | Bonnycraig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-05-14 | 2019-12-19 | Scottish Borders | 0 | 15247.21 | 31202.93 | 40058.29 | 121580.63 | 20588.24 | 2971.94 | 231649.24 | 0 | 231649.24 | 203777.52 | [6 empty] | DW5FS | 100%
500244 | Bonnycraig WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-02-26 | 2018-03-27 | 2018-03-27 | 2020-12-31 | 2021-02-28 | Scottish Borders | 0 | 30177.5 | 322708.87 | 901046.7 | 300533.11 | 1636784.82 | 406577.36 | 3597828.36 | 393.64 | 3598222 | 494989.85 |  |  |  |  | 36252 |  | CM_WSNI | 50% | DW25P | 50% | bar: Regulatory Outputs OMG-04
502714 | Bonnycraig WTW - UV Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-05-12 | 2017-05-12 | 2017-10-01 | 2020-08-14 | 2020-11-16 | Scottish Borders | 0 | 0 | 0 | 452474.31 | 8736.03 | 2097.03 | -172.24 | 463135.13 | 0 | 463135.13 | 0 |  |  |  |  | 5000 |  | CM_WSNI | 100%
502570 | Bonnycraig WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWMD | Strategic Capacity | GW1 | 2020-07-06 | 2020-07-20 | 2020-07-08 | 2020-09-02 | 2020-09-03 | Scottish Borders | 0 | 0 | 20930.23 | 80868.29 | 185035.64 | 953208.08 | -956785.24 | 283257 | 0 | 283257 | 136478.56 | [6 empty] | WG1 | 100%
46268 | Borehole Remedial Actions Programme | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-17 | 2010-12-17 | 2011-01-26 | 2013-12-23 |  | Scottish Water Wide | 1507464.71 | 3356.88 | 0 | 0 | 0 | 0 | 0 | 3356.88 | 0 | 1510821.59 | 0 | [6 empty] | CM_WSNI | 100%
501394 | Boreholes - Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-06-29 | 2017-06-29 | 2017-10-16 | 2019-08-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 42885.71 | 974265.44 | 509895.68 | 18840.74 | 1419.08 | 1547306.65 | 1125.63 | 1548432.28 | 0 | [6 empty] | CM_WSI | 100%
501462 | Boreholes - Phase 3 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-09-29 | 2028-05-15 | 2028-09-07 | 2029-08-28 | 2029-11-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552316.03 | 1552316.03 | 0 | [6 empty] | CM_WSI | 100%
500939 | Bothwell Road Hamilton Overland Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2018-04-30 | 2018-09-28 | 2019-03-19 | 2019-03-19 | South Lanarkshire | 0 | 44364 | 34062 | 214724 | 927963 | -49407 | 0 | 1171706 | 2500 | 1174206 | 0 | [6 empty] | CM_WWI | 100%
503415 | Bothwell Sewer - Replacement of approximatly 130m of 600mm | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 2020-11-13 | 2020-11-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 32834.84 | 613525.42 | 200524.69 | 846884.95 | 5019.03 | 851903.98 | 0 | [6 empty] | CM_WWI | 100%
30107 | Bothwellbank STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2010-09-20 | 2010-11-29 | 2014-10-21 | 2015-01-05 | South Lanarkshire | 1948423.25 | 1623.02 | -1742.01 | 0 | 0 | 0 | 0 | -118.99 | 0 | 1948304.26 | 1307.35 | [6 empty] | CM_WWNI | 20% | EC01A | 80%
502307 | Bothwellbank WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-12-02 | 2028-06-13 | 2028-10-03 | 2029-05-15 | 2029-08-15 | South Lanarkshire | 0 | 0 | 35014.7 | 690.59 | 5572.45 | 23109.49 | 9612.76 | 73999.99 | 926000.08 | 1000000.07 | 136478.56 | [6 empty] | SG1 | 100%
403750 | Bothwellbank WwTW Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-04-03 | 2014-04-03 | 2014-07-30 | 2017-02-22 |  | South Lanarkshire | 352139 | 115361 | -38421.14 | 0 | 0 | 0 | 0 | 76939.86 | 0 | 429078.86 | 0 | [6 empty] | CM_WWNI | 100%
500729 | Boughden Braes Lesmahagow Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-08-21 | 2028-01-03 | 2028-03-29 | 2028-10-23 | 2029-01-23 | Scottish Water Wide | 0 | 5306 | 95727 | 120208 | -23350 | -3037.91 | 3134.86 | 197987.95 | 840579.03 | 1038566.98 | 0 | [6 empty] | CM_WWI | 100%
403404 | Boughden Braes Sewer Collapse - Undertake Sewer Diversion Works | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-05 | 2013-10-24 | 2013-11-18 | 2013-12-09 | 2014-03-21 | South Lanarkshire | 89207 | -618.32 | 0 | 0 | 0 | 0 | 0 | -618.32 | 0 | 88588.68 | 0 | [6 empty] | CM_WWI | 100%
501513 | BOWHOUSE WWPS NS934805 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-06-29 | 2017-12-20 | 2018-03-26 | 2020-04-01 | 2020-04-01 | Falkirk | 0 | 0 | 85352 | 205270 | 814546.02 | 88777.74 | 161.24 | 1194107 | 0 | 1194107 | 0 | [6 empty] | CM_WWNI | 100%
501814 | Bowhouse WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-08-31 | 2016-09-29 | Fife | 0 | 10640.68 | 6602.48 | 0 | 0 | 0 | 0 | 17243.16 | 0 | 17243.16 | 136478.56 | [6 empty] | SG1 | 100%
500898 | Bowling Reservoir Breach FRMA | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS7 | 2015-06-30 | 2015-06-30 | 2015-07-31 | 2017-08-31 | 2017-10-31 | West Dunbartonshire | 0 | 7000 | 330140.57 | 81493.7 | 0 | -170.26 | 0 | 418464.01 | 0 | 418464.01 | 980126.37 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-11
503379 | Bowmore WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-06-09 | 2023-04-18 | 2023-08-21 | 2024-02-09 | 2024-05-13 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 66783.08 | 7075.32 | 0 | 73858.4 | 1926141.59 | 1999999.99 | 136478.56 | [6 empty] | SG1 | 100%
401333 | Bradan A - Iron & Manganese Distribution WQ Improvements - Guiltreehill Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2013-02-13 | 2013-12-19 | South Ayrshire | 6347735.04 | 8822.96 | 745.43 | 0 | 0 | 0 | 0 | 9568.39 | 0 | 6357303.43 | 37166.91 | [6 empty] | DW5 | 46.23% | CM_WSI | 53.77%
401334 | Bradan A - Iron & Manganese Distribution WQ Improvements - Knockjarder Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS5 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2018-03-31 | 2019-03-31 | South Ayrshire | 7858175 | -565446.03 | 26323.18 | 91419.67 | 548242.66 | 674239.68 | -115676.19 | 659102.97 | 8036.52 | 8525314.49 | 64301.47 | [6 empty] | CM_WSI | 17.82% | DW5 | 82.18% | bar: Regulatory Outputs OMG-03
401335 | Bradan B - Iron - Manganese Distribution WQ Improvements - Irvine Cluster | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2018-08-31 | 2019-03-31 | South Ayrshire | 9254841 | -292999.35 | 19123.95 | 76176.06 | 24037.1 | -8330060.49 | 0 | -8503722.73 | 0 | 751118.27 | 0 | [6 empty] | CM_WSI | 100% | bar: Regulatory Outputs OMG-03
401336 | Bradan B - Iron - Manganese Distribution WQ Improvements - Kilmarnock Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2012-04-30 | 2013-06-25 | South Ayrshire | 2784173 | 27722 | -146080.1 | 0 | 0 | 0 | 0 | -118358.1 | 0 | 2665814.9 | 22187 | [6 empty] | DW5 | 41.48% | CM_WSI | 58.52%
500005 | Bradan Incident - Pipe Bridge Testing & Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-04-24 | 2019-02-12 | 2019-02-25 | 2019-04-30 | 2019-04-30 | South Ayrshire | 0 | 89898 | 203683.62 | 272171.38 | 207426 | -1098.16 | 12000 | 784080.84 | 0 | 784080.84 | 0 | [6 empty] | CM_WSI | 100%
403942 | Bradan Interim Resilience | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-09-25 | 2016-03-29 | 2016-04-04 | 2017-03-16 |  | South Ayrshire | 335975.53 | 464830.47 | 82986.42 | 66897.06 | 0 | 0 | 0 | 614713.95 | 0 | 950689.48 | 0 | [6 empty] | CM_WSI | 100%
500040 | Bradan RSZ Cleaning Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-04-13 | 2016-09-23 | 2016-09-26 | 2021-03-25 | 2021-08-12 | South Ayrshire | 0 | 312710 | 139433 | 627304 | 357720.08 | 212753.3 | 141148.5 | 1791068.88 | 363649.27 | 2154718.15 | 2266445.18 | [6 empty] | DW5FS | 100%
403309 | Bradan trunk main Cathodic protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS1 | 2013-06-06 | 2020-07-20 | 2020-07-20 | 2020-10-09 |  | South Ayrshire | 24000 | 37122.47 | 8892.53 | 142104 | 113520 | -8138.23 | 0 | 293500.77 | 0 | 317500.77 | 0 | [6 empty] | CM_WSI | 100%
500685 | Bradan Trunk Mains Permanent Bypasses | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-07-09 | 2028-02-14 | 2028-03-14 | 2028-06-05 | 2028-06-05 | South Ayrshire | 0 | 416098 | 92035 | -10000 | 27820 | 12424.28 | 0 | 538377.28 | 818098.69 | 1356475.97 | 0 | [6 empty] | CM_WSI | 100%
501178 | Bradan WOA Amlaird WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-25 | 2028-02-02 | 2028-04-03 | 2028-10-13 | 2029-01-15 | East Ayrshire | 0 | 0 | 20152.97 | 0 | 14304.76 | -804.9 | 544.17 | 34197 | 737408 | 771605 | 0 | [6 empty] | CM_WSI | 100%
503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-10-07 | 2021-11-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 816462.8 | 1851157.37 | 2667620.17 | 1197080.84 | 3864701.01 | 3607589.06 | [6 empty] | DW5MR | 100%
503632 | Bradan WQ Improvement Pennyburn Road DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2020-03-04 | 2021-03-15 | 2021-04-05 | 2022-07-04 | 2023-06-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 45151.98 | 174589.26 | 219741.24 | 1837258.79 | 2057000.03 | 0 | [6 empty] | SR21_WA | 100% | bar: Regulatory Outputs OMG-02
504434 | Bradan WTW - Top and Bottom Generator Install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-03-25 | 2020-12-07 | 2021-03-11 | 2021-08-26 | 2021-08-27 | - | 0 | 0 | 0 | 0 | 0 | 47067.18 | -47067.18 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 100%
500709 | Bradan WTW CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2015-07-16 | 2017-03-30 | 2017-03-30 | 2022-01-31 | 2022-03-31 | South Ayrshire | 0 | 35821 | -6582.56 | 57931.55 | 165906.79 | 786390.22 | 2330524 | 3369991 | 992660.73 | 4362651.73 | 1184912.67 | [6 empty] | CM_WSNI | 25.99% | DW25P | 74.01% | bar: Regulatory Outputs OMG-04
403316 | Bradan WTW Essential Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-03-25 | 2013-03-25 | 2013-04-02 | 2018-12-10 | 2018-12-10 | South Ayrshire | 980000 | 116583 | 47995.52 | 34000 | -14902.4 | -1605.18 | 0 | 182070.94 | 0 | 1162070.94 | 0 | [6 empty] | CM_WSNI | 100%
502960 | Bradan WTW Filter Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS4 | 2017-11-07 | 2018-07-13 | 2018-07-13 | 2019-12-24 | 2020-04-17 | South Ayrshire | 0 | 0 | 0 | 222976.29 | 4227444.63 | 2620332.56 | -332.46 | 7070421.02 | 145113.03 | 7215534.05 | 0 | [6 empty] | CM_WSNI | 100%
46266 | Bradan WTW Refurb - WTW000028 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-11-20 | 2010-11-26 | 2011-02-28 | 2014-09-16 | 2015-11-02 | South Ayrshire | 1007295.56 | 1382.64 | -362 | 0 | 0 | 0 | 0 | 1020.64 | 0 | 1008316.2 | 0 | [6 empty] | CM_WSNI | 100%
502412 | Bradan WTW Water Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2015-07-16 | 2017-03-13 | 2017-03-27 | 2020-09-18 | 2020-10-02 | South Ayrshire | 0 | 0 | 1151164.05 | 11277843.69 | 2270210.3 | 140076.56 | 0 | 14839294.6 | 256467.4 | 15095762 | 5863925.46 |  |  |  |  | 48000 |  | DW25PS | 33.33% | DW25P | 33.33% | DW2_S | 33.33%
403407 | Braeface Difgen | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS6 | 2013-03-01 | 2013-03-01 | 2017-03-27 | 2018-03-31 | 2018-04-30 | Stirling | 758220.29 | 54797.71 | -4385 | 824054.75 | 325972.81 | 90578.8 | 9421.19 | 1300440.26 | 0 | 2058660.55 | 832227.31 | [6 empty] | CC1W | 100% | [18 empty] | Regulatory Outputs OMG-43: 0.74
501185 | Braehead Larkhall SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-05-31 | 2017-09-15 | 2018-02-09 | 2018-11-30 | 2018-11-30 | South Lanarkshire | 0 | 0 | 106074 | 719318 | 905838 | 9806 | 0 | 1741036 | 0 | 1741036 | 0 | [6 empty] | CM_WWNI | 100%
502557 | Braemar WTW - Interruptions to Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-05-17 | 2029-02-27 | 2029-05-23 | 2029-12-24 | 2030-03-25 | Aberdeenshire | 0 | 0 | 0 | 57911.7 | 12332.11 | 2810.24 | -2396.04 | 70658.01 | 669342.02 | 740000.03 | 0 | [6 empty] | CM_WSNI | 100%
501210 | Braemar WTW QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2017-03-20 | 2018-03-13 | 2018-07-27 | 2018-11-30 | 2019-03-31 | Aberdeenshire | 0 | 1440 | 25259.9 | 12692.1 | 157760.52 | 2059.87 | 1219.06 | 200431.45 | 450.91 | 200882.36 | 44350.8 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
45312 | Braemar WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-23 | 2011-07-22 | 2012-01-19 | 2012-03-14 | Aberdeenshire | 202516.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202516.79 | 0 | [6 empty] | DW13 | 100%
503322 | Braemar WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-05-01 | 2019-05-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 64479.32 | 0 | 0.01 | 64479.33 | 0 | 64479.33 | 136478.56 | [6 empty] | SG1 | 100%
500875 | Braes Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-08-18 | 2017-07-25 | 2018-02-28 | 2018-05-31 | 2019-12-31 | Highland | 0 | 969 | 1179.65 | 3727.09 | 9278.21 | -344.83 | 0 | 14809.12 | 0 | 14809.12 | 20559.44 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.05
500934 | Brechin - Montrose Street Sewer - Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2015-10-07 | 2016-07-21 | 2016-08-26 | 2019-05-07 | 2019-05-07 | Angus | 0 | 515113 | 781423.75 | 1282268.43 | 768277.25 | 138099.23 | 1104.89 | 3486286.55 | 841.8 | 3487128.35 | 0 | [6 empty] | CM_WWI | 100%
500123 | Brechin DOA (DOA000645) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-11-29 | 2019-03-29 | Angus | 0 | 14782 | 19950 | 5490 | 7156 | -3181.16 | 1771.39 | 45968.23 | 0 | 45968.23 | 10344.04 | [6 empty] | EC01G | 39.74% | CS16D | 60.26%
500969 | Brechin Sewers Cluster | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-10-13 | 2020-12-14 | 2021-03-05 | 2021-09-30 | 2022-01-17 | Angus | 0 | 3478.79 | 146.15 | 45.7 | 9.11 | 44216.25 | 77301.53 | 125197.53 | 383291.56 | 508489.09 | 0 | [6 empty] | CM_WWI | 100%
45673 | Brechin STC Refurb - STC000075 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2010-12-21 | 2011-05-09 | 2013-03-28 |  | Angus | 451850.43 | 6 | 0 | 0 | 0 | 0 | 41.25 | 47.25 | 0 | 451897.68 | 0 | [6 empty] | CM_WWNI | 100%
30115 | Brechin STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-11-12 | 2010-12-23 | 2011-03-07 | 2013-11-29 | 2013-12-12 | Angus | 2585102.49 | 234536.1 | 0 | 0 | 0 | 0 | 0 | 234536.1 | 0 | 2819638.59 | 3028.69 | [6 empty] | EC01A | 40% | CM_WWNI | 60%
502885 | Brechin WwTP SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-08-26 | 2028-11-30 | 2029-03-28 | 2030-06-24 | 2030-09-24 | Angus | 0 | 0 | 0 | 47918.17 | 5647.33 | 12139.9 | 25913.46 | 91618.86 | 658381.21 | 750000.07 | 0 | [6 empty] | CM_WWNI | 100%
503564 | Brechin WwTW - Bio Filter Media Filter | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS2 | 2019-10-02 | 2019-10-02 | 2020-10-26 | 2021-11-10 | 2021-11-11 | Angus | 0 | 0 | 0 | 0 | 0 | 135851.49 | 335438.53 | 471290.02 | 178710.02 | 650000.04 | 136478.56 | [6 empty] | SG1 | 100%
502333 | Brechin WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-07-20 | 2022-10-10 | 2023-01-30 | 2023-09-11 | 2023-12-12 | Angus | 0 | 0 | 45288.41 | 16165.98 | 45692.12 | 12670.79 | -1103.62 | 118713.68 | 5881286.24 | 5999999.92 | 136478.56 | [6 empty] | SG1 | 100%
500856 | Bressay Shetland RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-06-01 | 2017-05-31 | 2017-08-07 | 2019-01-31 | 2019-08-31 | Shetland Islands | 0 | 1178.51 | 926.64 | 8874.98 | 18247.5 | 10334.04 | 0 | 39561.67 | 0 | 39561.67 | 50429.66 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 17.99
502775 | Bridge of Orchy - First Time Provision | Q&S4 | Supporting economic development | First Time Provision |  |  | Water |  | WINF | First Time Provision | MS0 | 2020-02-21 | 2022-02-14 | 2022-06-06 | 2023-11-17 | 2024-02-15 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 12118.64 | 117033.87 | 66296.73 | 243525.24 | 438974.48 | 3311025.54 | 3750000.02 | 1084027.07 | [6 empty] | WG3 | 100%
403068 | Bridge Street Cadell Place Bathgate Fauldhouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-21 | 2014-07-15 | 2014-07-16 | 2015-03-30 | 2015-03-30 | West Lothian | 511864 | 16096 | -0.47 | -12652.83 | 0 | 0 | 0 | 3442.7 | 0 | 515306.7 | 204193.13 | [6 empty] | CS11 | 100%
402691 | Bridgend Water Supply - WQ Fe Failures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-31 | 2013-09-24 | 2013-11-12 | 2014-11-04 |  | Aberdeenshire | 308442 | 8312 | -1648.43 | 0 | 0 | 0 | 0 | 6663.57 | 0 | 315105.57 | 0 | [6 empty] | CM_WSI | 100%
503295 | Broadford WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-04-12 | 2021-12-06 | 2022-04-05 | 2023-03-31 | 2023-07-03 | Highland | 0 | 0 | 0 | 0 | 20233.02 | -19648.22 | 0 | 584.8 | 0 | 584.8 | 136478.56 | [6 empty] | WG1 | 100%
30119 | Broadford WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2011-10-17 | 2013-08-08 | 2015-03-06 | Highland | 232609.57 | 1846.82 | 0 | 0 | 0 | 0 | 0 | 1846.82 | 0 | 234456.39 | 957 | [6 empty] | DW13 | 100%
501834 | Broadside - Glenhead Trunk Main Rehabilitation | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-07-15 | 2028-03-22 | 2028-06-19 | 2029-01-17 | 2029-04-19 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439829.81 | 439829.81 | 0 | [6 empty] | CM_WSI | 100%
402822 | Broadside to Braeface mains replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-11 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Falkirk | 52290 | -1735.32 | 0 | 0 | 0 | 0 | 0 | -1735.32 | 0 | 50554.68 | 0 | [6 empty] | CM_WSI | 100%
401973 | Brockloch - Bradan WOA 250 mm HPPE Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-12 | 2016-03-31 | 2016-10-10 | 2017-10-06 |  | South Ayrshire | 34191 | 41708 | 83421 | -19430.88 | 0 | 0 | 0 | 105698.12 | 0 | 139889.12 | 0 | [6 empty] | CM_WSI | 100%
503382 | Brodick WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-04-09 | 2022-02-16 | 2022-06-21 | 2022-12-12 | 2023-03-14 | North Ayrshire | 0 | 0 | 0 | 0 | 64237.59 | 9628.18 | 67086.01 | 140951.78 | 1048.22 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
403430 | Broomhill Avenue Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-18 | 2014-11-04 | 2014-11-04 | 2015-03-27 | 2015-03-27 | Aberdeenshire | 600114 | 120977 | 0.48 | -1155.86 | 0 | 0 | 0 | 119821.62 | 0 | 719935.62 | 204193.13 | [6 empty] | CS11A | 100%
500117 | Brora DOA (DOA000456) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-19 | 2016-03-30 | 2016-08-31 | 2019-07-31 | 2019-12-31 | Highland | 0 | 23507 | 3106 | 44279 | 40324 | 47725.88 | 10303.12 | 169245 | 0 | 169245 | 84112.7 | [6 empty] | EC01G | 14.83% | EC01D | 85.17% | bar: Regulatory Outputs OMG-23
300021 | Brownscroft Cottage Drainage | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-03-30 | 2011-08-30 | 2011-10-10 | 2012-02-20 |  | Aberdeenshire | 36835.17 | -642.63 | 0 | 0 | 0 | 0 | 0 | -642.63 | 0 | 36192.54 | 0 | [6 empty] | WWI | 100%
503511 | Bruce Embankment SPS Storm Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2020-04-01 | 2020-02-04 | 2020-03-09 | 2021-01-25 | 2020-10-09 | Fife | 0 | 0 | 0 | 0 | 0 | 538526.6 | 290257.56 | 828784.16 | 1792.71 | 830576.87 | 0 | [6 empty] | CM_WWNI | 100%
402990 | Brunswick Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-11-18 | 2014-01-23 | 2014-01-23 | Glasgow City | 20060 | -316.06 | 0 | 0 | 0 | 0 | 0 | -316.06 | 0 | 19743.94 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402644 | Buchanan St SPS - Noise Issue | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-18 | 2012-06-18 | 2012-07-30 | 2017-01-02 |  | North Ayrshire | 649024.58 | 94390.42 | 7115.59 | 0 | 0 | 0 | 0 | 101506.01 | 0 | 750530.59 | 0 | [6 empty] | CM_WWNI | 100%
504375 | Buchanan Street WWPS - SPSO Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-12-31 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 26376.7 | 53623.3 | 80000 | 0 | 80000 | 0 | [6 empty] | CM_WWNI | 100%
502864 | Buchanan Street WwPS - SPSO Structural Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2017-08-28 | 2018-02-23 | 2018-02-26 | 2020-01-08 | 2020-04-01 | North Ayrshire | 0 | 0 | 0 | 143775.04 | 19624.97 | 19600 | -3500 | 179500.01 | 0 | 179500.01 | 0 | [6 empty] | CM_WWNI | 100%
46245 | Buittle Reservoir - Freeboard | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-12-11 | 2010-10-04 | 2010-09-27 | 2011-02-01 | 2011-02-01 | Dumfries and Galloway | 129350.3 | 1.68 | 0 | 0 | 0 | 0 | 0 | 1.68 | 0 | 129351.98 | 0 | [6 empty] | CM_WSI | 100%
500027 | Bunessan WOA - Iona Subsea Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-11-22 | 2017-06-21 | 2017-06-21 | 2017-06-21 | 2017-06-21 | Argyll and Bute-North Argyll | 0 | 502.5 | 911.25 | 0 | 0 | 0 | 0 | 1413.75 | 0 | 1413.75 | 0 | [6 empty] | CM_WSI | 100%
500642 | Bunessan WOA Iona Subsea Crossing (Clamshell Option) | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-06-23 | 2015-10-23 | 2016-03-14 | 2016-02-29 | 2016-03-31 | Argyll and Bute-North Argyll | 0 | 709154 | 480481.06 | 4453.63 | 675.33 | 0 | 0 | 1194764.02 | 0 | 1194764.02 | 1823900.39 | [6 empty] | CS16WR | 1.674% | CM_WSI | 98.33% | bar: Regulatory Outputs OMG-07
500911 | Bunessan WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-11-24 | 2016-03-25 | 2016-03-25 | 2016-03-31 | 2016-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 118939.73 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500786 | Burncrooks Reservoir - Improve Stability of Retaining Wall | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-08-14 | 2016-03-07 | 2016-04-25 | 2016-05-03 | 2016-05-03 | Stirling | 0 | 238924.93 | 272.45 | 0 | 0 | 0 | 0 | 239197.38 | 0 | 239197.38 | 0 | [6 empty] | CM_WSI | 100%
502556 | Burncrooks Round CWT capital maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-11-21 | 2019-06-27 | 2019-08-12 | 2020-11-26 | 2021-02-16 | Stirling | 0 | 0 | 14408.37 | 23098.84 | 14095.14 | 37844.49 | 51019.84 | 140466.68 | 680.1 | 141146.78 | 0 |  |  |  |  | 184.51 |  | CM_WSNI | 100%
500697 | Burncrooks Supply Zone - Ortho Non Compliance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-07-15 | 2016-06-28 | 2016-07-22 | 2016-08-30 | 2016-08-30 | Stirling | 0 | 2490 | 284341.33 | -831.33 | -102.16 | 0 | 0 | 285897.84 | 0 | 285897.84 | 0 | [6 empty] | CM_WSNI | 100%
503548 | Burncrooks WTW - Installation & Commissioning of Poly Activated Carbon Dosing | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-04-01 | 2020-04-13 | 2020-08-17 | 2021-04-20 | 2021-07-21 | Stirling | 0 | 0 | 0 | 0 | 0 | 796.61 | 96490.95 | 97287.56 | 2712.44 | 100000 | 0 | [6 empty] | CM_WSNI | 100%
502132 | Burncrooks WTW Quality THM Compliance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2016-03-17 | 2019-03-29 | 2019-03-29 | 2021-10-28 | 2022-01-27 | Stirling | 0 | 19141.6 | 189820.4 | 758551.95 | 5045526.27 | 15036021.52 | 10480777.53 | 31529839.27 | 1609405.33 | 33139244.6 | 12083867.62 |  |  |  |  | -143000 |  | WR1 | 2.01% | DW25P | 5.05% | CM_WSNI | 43.27% | DW2 | 49.67%
403900 | Burncrooks WTW Quality THM Compliance and Capital | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-06-01 | 2016-07-01 | Stirling | 576.81 | 48350.75 | -48927.56 | 0 | 0 | 0 | 0 | -576.81 | 0 | 2.2737e-12 | 242037.57 | [6 empty] | WR1 | 100%
402998 | Burnmouth to Lamberton Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-22 | 2013-09-24 | 2014-02-07 | 2014-07-04 |  | Scottish Borders | 393397.08 | 3518.12 | 0 | 0 | 0 | 0 | 0 | 3518.12 | 0 | 396915.2 | 0 | [6 empty] | CM_WSI | 100%
402848 | Burnside Cottage Long Road Avoch | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-23 | Highland | 204996 | -32318 | -172677 | 0 | 0 | 0 | 0 | -204995 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
503122 | Burnside Gate Hamilton | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2019-02-08 | 2020-09-21 | 2020-12-21 | 2021-06-10 | 2021-06-10 | South Lanarkshire | 0 | 0 | 0 | 266.18 | 188327.82 | 123108.35 | 338490.06 | 650192.41 | 68316.52 | 718508.93 | 0 | [6 empty] | CM_WWI | 100%
502579 | Burnside Place Coalburn Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 2017-03-15 | 2017-03-15 | South Lanarkshire | 0 | 0 | 2209.57 | 228.35 | 212.9 | 0 | -245.82 | 2405 | 0 | 2405 | 0 | [6 empty] | CM_WWI | 100%
45789 | Burnside Road SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-12-12 | 2012-02-13 | 2013-03-28 | 2013-03-29 | Dundee City | 730464.48 | -3196.05 | 0 | 0 | 0 | 0 | 0 | -3196.05 | 0 | 727268.43 | 3394.95 | [6 empty] | WQ01B | 5% | CM_WWNI | 25% | WQ01C | 70%
500233 | Burrelton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS1 | 2018-09-04 | 2020-04-20 | 2020-07-01 | 2021-04-13 | 2021-04-13 | Perth and Kinross | 0 | 51135.77 | 46906.81 | 27162.89 | 57031.53 | 251504.47 | 1129683.09 | 1563424.56 | 149338.49 | 1712763.05 | 136478.56 |  |  |  |  | 6810 |  | SG1 | 100%
500049 | Busby WWPS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2012-12-31 | 2016-12-20 | 2017-02-06 | 2017-12-31 | 2018-01-31 | East Renfrewshire | 0 | 61000 | 239240 | 194480 | 0 | -11086.49 | 0.49 | 483634 | 0 | 483634 | 20016.79 | [6 empty] | EC01F | 20.58% | CM_WWNI | 79.42% | bar: Regulatory Outputs OMG-18
500674 | Business Insights | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-05 | 2018-02-28 | 2018-02-28 | 2020-06-15 |  | Scottish Water Wide | 0 | 216302 | 531415 | 1123073.78 | 1238451.23 | 1281607.6 | 419006.6 | 4809856.21 | 0 | 4809856.21 | 0 |  |  |  |  | 382000 |  | CM_M&G | 100%
500588 | Business Systems 2015 Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-25 | 2018-01-31 | 2018-01-31 | 2020-05-15 | 2020-05-15 | Scottish Water Wide | 0 | 297862 | 493380.36 | 394478.48 | 9868.61 | 118371.2 | 18092 | 1332052.65 | 0 | 1332052.65 | 0 | [6 empty] | CM_M&G | 100%
502587 | Buskhead Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-27 | 2027-11-24 | 2028-02-10 | 2028-06-26 | 2028-09-26 | Angus | 0 | 0 | 5320 | 7880.79 | 1220.12 | 1359.6 | -1359.6 | 14420.91 | 722212.04 | 736632.95 | 0 | [6 empty] | CM_WSI | 100%
503608 | BW Sewer Misconnection Remediation | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2019-09-30 | 2019-09-30 | 2019-11-18 | 2020-10-27 | 2021-02-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 195000 | 84999.99 | 279999.99 | 0 | 279999.99 | 0 | [6 empty] | EC16 | 100%
504882 | Bypass Interventions West B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-03 | 2020-03-02 | 2020-12-16 | 2020-12-17 | - | 0 | 0 | 0 | 0 | 0 | 15444.73 | 0 | 15444.73 | 0 | 15444.73 | 0 | [6 empty] | CM_WSNI | 100%
505661 | C19 Digital Preparations | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2020-04-28 | 2020-06-08 | 2020-06-15 | 2020-12-11 | 2020-12-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 228131.54 | 0 | 228131.54 | 0 | 228131.54 | 0 | [6 empty] | CM_M&G | 100%
503529 | Caaf MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-06-12 | 2019-06-12 | 2019-07-15 | 2021-01-20 | 2021-02-17 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 762424.2 | 142652.49 | 905076.69 | 3050.12 | 908126.81 | 0 |  |  |  |  | 2370 |  | CM_WSI | 100%
403893 | Caaf Reservoir Breach (transfer from 402179) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-07-10 | 2015-01-29 | 2015-04-06 | 2018-10-22 | 2018-10-22 | North Ayrshire | 108014.75 | 543674.25 | 34079 | 255500.42 | 13282.46 | 0 | 0 | 846536.13 | 0 | 954550.88 | 0 | [6 empty] | CM_WSI | 100%
402179 | Caaf Reservoir Freeboard Improvement Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-14 | 2015-04-17 | 2014-08-14 | 2014-08-14 | 2014-08-14 | North Ayrshire | 735726 | 51.8 | 0 | 0 | 0 | 0 | 0 | 51.8 | 0 | 735777.8 | 0 | [6 empty] | CM_WSI | 100%
401376 | Caddonfoot (Clovenfords) WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-11-08 | 2012-05-02 | 2012-08-27 | 2013-12-19 | 2013-12-19 | Scottish Borders | 1719185.32 | 1833.26 | 0 | 0 | 0 | 0 | 0 | 1833.26 | 0 | 1721018.58 | 0 | [6 empty] | SG1 | 100%
403910 | Cairnfield WSZ Main Out | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS6 | 2014-10-24 | 2015-09-21 | 2015-11-30 | 2018-09-26 | 2018-09-26 | Aberdeen City | 13417 | 33649 | 9509.63 | 3052 | 147064.9 | 12963.62 | 309.2 | 206548.35 | 0 | 219965.35 | 0 | [6 empty] | WG5 | 100%
501567 | Cairnton RWI Pump - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-03-29 | 2021-10-25 | 2022-02-10 | 2023-05-10 | 2023-08-10 | Aberdeen City | 0 | 5023.26 | 35993.26 | 59273.57 | 22834.85 | 77673.13 | 76371.6 | 277169.67 | 1489340.43 | 1766510.1 | 0 | [6 empty] | CM_WSI | 100%
404096 | Calderwood Infrastructure Charge Funding | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2016-10-13 | 2017-03-02 | West Lothian | 351960.59 | 5921.41 | 64118.12 | 0 | 0 | 0 | 0 | 70039.53 | 0 | 422000.12 | 0 | [6 empty] | WG5 | 100%
402876 | California Drainage Network EPI Resolution | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2012-12-21 | 2017-06-30 | 2017-08-21 | 2018-05-30 |  | Falkirk | 26923 | 28893.64 | 114175.36 | 322796 | 42200.92 | 25.08 | 0 | 508091 | 0 | 535014 | 0 | [6 empty] | CM_WWI | 100%
402875 | Callander Drainage Network EPI Resolution Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-11 | 2016-02-29 | 2016-02-18 | 2016-02-19 |  | Stirling | 88246 | 8283.31 | 0 | 0 | 0 | 0 | 700.07 | 8983.38 | 0 | 97229.38 | 0 | [6 empty] | CM_M&G | 24% | CM_WWI | 76%
503307 | Callander WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-21 | 2030-06-19 | 2030-09-19 | Stirling | 0 | 0 | 0 | 0 | 28915.3 | 6540.98 | 0 | 35456.28 | 106543.72 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
500232 | Callanish WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2015-09-08 | 2015-09-08 | 2015-09-08 | 2015-08-19 | 2015-09-08 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG1 | 100%
501720 | Cambuslang SPS 2 RM - Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2019-03-13 | 2020-03-18 | 2020-04-06 | 2020-09-28 | 2021-01-12 | Glasgow City | 0 | 0 | 6731.42 | 0 | 11432.22 | 252781.95 | 1244400.81 | 1515346.4 | 8540.51 | 1523886.91 | 0 | [6 empty] | CM_WWI | 100%
501161 | Cambuslang SPS No.1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-11 | 2017-06-05 | 2017-11-09 | 2018-10-31 | 2018-10-31 | Glasgow City | 0 | 1126 | 114705 | 508928 | 144232 | 2500 | 0 | 771491 | 0 | 771491 | 0 | [6 empty] | CM_WWNI | 100%
501162 | Cambuslang SPS No.2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-17 | 2017-06-05 | 2017-11-09 | 2019-02-27 | 2019-02-27 | Glasgow City | 0 | 858.64 | 92229.36 | 517442 | 188650 | 24067 | 1608 | 824855 | 0 | 824855 | 0 | [6 empty] | CM_WWNI | 100%
501112 | Campbeltown WOA Auchencorvie SDN | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2016-08-25 | 2021-03-10 | 2019-06-28 | 2019-06-28 | 2019-06-28 | Argyll and Bute-North Argyll | 0 | 18000 | 55006.2 | 553 | 0 | -4536.68 | -1446.03 | 67576.49 | 0 | 67576.49 | 0 | [6 empty] | CM_WSNI | 100%
403331 | Campbeltown WOA Southend Rehab - 6inch AC | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-19 | 2013-02-19 | 2013-03-01 | 2013-08-09 |  | Argyll and Bute-North Argyll | 631330.27 | 5661.45 | 0 | 0 | 0 | 0 | 0 | 5661.45 | 0 | 636991.72 | 0 | [6 empty] | CM_WSI | 100%
505698 | Campbeltown WTW - pH Correction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-01-25 | 2023-12-12 | 2024-05-21 | 2025-12-02 | 2026-03-04 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 18243.09 | 18243.09 | 981756.9 | 999999.99 | 0 | [6 empty] | WSNI | 100%
502978 | Campbeltown WwTW - Replacement Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-06-21 | 2028-06-02 | 2028-09-29 | 2029-05-11 | 2029-08-13 | Highland | 0 | 0 | 0 | 31695.59 | 1005.99 | 14461.37 | 16877.52 | 64040.47 | 1935959.51 | 1999999.98 | 0 | [6 empty] | CM_WWNI | 100%
46246 | Camphill Reservoir - Drawdown facilities | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-01-05 | 2011-06-23 | 2011-07-22 | 2012-01-25 | 2012-01-25 | North Ayrshire | 284478.74 | 3.55 | 0 | 0 | 0 | 0 | 0 | 3.55 | 0 | 284482.29 | 0 | [6 empty] | CM_WSI | 100%
503061 | Camphill Spillway Improvements and Drawdown Capacity Enhancement | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2020-06-29 | 2021-08-09 | 2021-12-10 | 2023-11-14 | 2024-02-14 | North Ayrshire | 0 | 0 | 0 | 6402.7 | 0 | 18380.26 | 69657.05 | 94440.01 | 655559.88 | 749999.89 | 821666.8 | [6 empty] | CS22 | 100%
503736 | Camphill to Bradan 21 Inch Main - Survey and Remedial Works | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MSU | 2020-04-01 | 2021-03-01 | 2021-05-10 | 2021-12-06 | 2022-01-27 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 75932.32 | 75932.32 | 424067.69 | 500000.01 | 5863925.46 | [6 empty] | DW2_S | 50% | DW25P | 50%
502136 | Camphill WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2017-11-10 | 2017-11-30 | 2017-07-31 | 2019-03-31 | North Ayrshire | 0 | 0 | 802.96 | 1239.68 | 85.17 | 0 | 0 | 2127.81 | 0 | 2127.81 | 37826.8 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
402204 | Camphill WTW - Roof Collapse Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-07-19 | 2011-09-21 | 2011-10-17 | 2012-02-21 |  | North Ayrshire | 141431.12 | 374.85 | 0 | 0 | 0 | 0 | 0.15 | 375 | 0 | 141806.12 | 0 | [6 empty] | CM_WSNI | 100%
502785 | Camps Bridge - recycled project | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-02-28 | 2021-10-11 | 2022-04-07 | 2022-08-03 | 2023-03-21 | South Lanarkshire | 0 | 0 | 0 | 10670.11 | 19896.12 | 92541.6 | 98531.99 | 221639.82 | 586360.17 | 807999.99 | 0 | [6 empty] | CM_WSI | 100%
500016 | Camps DIR - Access Bridge | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-05-08 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-07-31 | South Lanarkshire | 0 | 35428 | 52345.52 | -84612.51 | 76069.91 | -77451.87 | -1779.04 | 0.01 | 0 | 0.01 | 0 | [6 empty] | CM_M&G | 100%
502735 | Camps Road Carnock | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-10-20 | 2019-02-21 | 2019-04-23 | 2020-06-18 | 2020-06-18 | Fife | 0 | 0 | 0 | 22566 | 100133 | 237342 | 0 | 360041 | 0 | 360041 | 0 | [6 empty] | CM_WWI | 100%
501275 | Camps Windfarm | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU | 2019-12-05 | 2020-01-09 | 2019-12-05 | 2019-12-11 | 2019-12-11 | - | 0 | 0 | 41062.04 | -11907.62 | -19022.56 | -10131.86 | 0 | -3.638e-12 | 0 | -3.638e-12 | 0 | [6 empty] | I2S_WI | 100%
500038 | Camps WTW - Part refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2027-04-01 | 2027-08-03 | 2027-09-13 | 2027-12-14 | South Lanarkshire | 0 | 61609 | 148634.01 | 7216.62 | 0 | 0 | 0 | 217459.63 | 0 | 217459.63 | 0 | [6 empty] | CM_WSNI | 100%
505057 | Camusterrach DOA - Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-03-10 |  |  |  | - | 0 | 0 | 0 | 0 | 0 | 2289.72 | 32710.28 | 35000 | 0 | 35000 | 0 | [6 empty] | CM_WWI | 100%
504891 | Canal Road Inverurie DOA - Sewer Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-02-17 | 2020-09-11 | 2020-11-20 | 2020-11-23 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 9053.83 | 110946.18 | 120000.01 | 0 | 120000.01 | 0 | [6 empty] | WWI | 100%
402123 | Cannich ST Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-27 | 2013-09-17 | 2013-10-21 | 2014-03-26 | 2014-03-26 | Highland | 490340 | 1445.71 | 0 | 0 | 0 | 0 | 0 | 1445.71 | 0 | 491785.71 | 0 | [6 empty] | SG1 | 100%
403465 | Canonbie ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-04-15 | 2015-04-23 | 2015-02-12 | 2015-02-12 | 2015-02-12 | Dumfries and Galloway | 660977.3 | 365.46 | 0 | 0 | 0 | 0 | 0 | 365.46 | 0 | 661342.76 | 0 | [6 empty] | SG1 | 100%
403943 | Canonbie WwTW - Upgrade Growth (Transfer from 403465) | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2014-12-19 | 2019-08-26 | 2019-09-30 | 2021-08-30 | 2021-11-30 | Dumfries and Galloway | 79731 | 254057 | 309429 | 502245 | 296718 | 1890846.27 | 3176160.92 | 6429456.19 | 58981.81 | 6568169 | 0 |  |  |  |  | 41210 |  | SG1 | 100%
500597 | Cap Inv Alliance Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1774532.76 | 1929016.3 | 1814460.46 | 1506491.79 | 1436329.2 | 2027202.32 | 10488032.83 | 330009.68 | 10818042.51 | 0 | [6 empty] | CM_OVH | 100%
500598 | Cap Inv Asset Management Director SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 274139.35 | 499417.02 | 550632.43 | 1273989.17 | 748788.58 | 740908.06 | 4087874.61 | 120612.94 | 4208487.55 | 0 | [6 empty] | CM_OVH | 100%
500599 | Cap Inv Capital Projects Completion SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 203924.34 | 201080.54 | -263805.04 | 0 | 0 | 39897.98 | 181097.82 | 6495.02 | 187592.84 | 0 | [6 empty] | CM_OVH | 100%
500600 | Cap Inv Commercial SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1049362.04 | 1633223.89 | 2100086.67 | 2488812.12 | 1766393.17 | 2110700.69 | 11148578.58 | 343602.43 | 11492181.01 | 0 | [6 empty] | CM_OVH | 100%
500601 | Cap Inv Controller of Cap Inv SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 185856.56 | 9600.99 | 34494.69 | 31329.22 | -58016.19 | 74959.69 | 278224.96 | 12202.72 | 290427.68 | 0 |  |  |  |  | 7362 |  | CM_OVH | 100%
500602 | Cap Inv Managed Delivery SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1215211.18 | 1348764.06 | 940614.85 | 837785.73 | 801273.05 | 1257975.49 | 6401624.36 | 204786.7 | 6606411.06 | 0 | [6 empty] | CM_OVH | 100%
500603 | Cap Inv Portfolio Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 3480760.2 | 4556197.16 | 4912233.18 | 4815935.25 | 4444058.73 | 5120981.48 | 27330166 | 833648.17 | 28163814.17 | 0 | [6 empty] | CM_OVH | 100%
500604 | Cap Inv Procurement & Supply Chain SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1194333.15 | 1340614.23 | 1597066.93 | 1747431.29 | 1482306.32 | 1701951.67 | 9063703.59 | 277061.92 | 9340765.51 | 0 | [6 empty] | CM_OVH | 100%
500605 | Cap Inv Specialist Services Commercial SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 297039.97 | 1038702.22 | 1634463.49 | 1345474.6 | 1396267.64 | 1273739.61 | 6985687.53 | 207352.98 | 7193040.51 | 0 | [6 empty] | CM_OVH | 100%
500596 | Cap Inv Specialist Services Non-Comm SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 328648.62 | 274894.56 | 208045.43 | 245244.82 | 212520.32 | 315390.93 | 1584744.68 | 42423.05 | 1627167.73 | 0 |  |  |  |  | 1 |  | CM_OVH | 100%
400736 | CAP MAINT SR10 PRV REPLACEMENT EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-21 | 2011-04-01 | 2015-07-02 |  | Scottish Water Wide | 667304.77 | 50190.75 | 827.2 | 0 | 0 | 0 | 0 | 51017.95 | 0 | 718322.72 | 0 | [6 empty] | CM_WSI | 100%
400735 | CAP MAINT SR10 PRV REPLACEMENT WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-21 | 2010-04-21 | 2016-10-06 |  | Scottish Water Wide | 440186 | 12505.69 | 0 | 0 | 0 | 0 | 0 | 12505.69 | 0 | 452691.69 | 0 | [6 empty] | CM_WSI | 100%
400397 | Cap Maint Water Infra Invercannie Aqueduct | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS5 | 2001-02-25 | 2005-01-21 | 2005-02-21 | 2018-10-08 | 2018-10-08 | Aberdeen City | -0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | [6 empty] | WSI | 100%
400753 | Capital Maintenance SR10 Service Reservoir Control East Leakage Delivery Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-06-15 |  | Scottish Water Wide | 524000 | -15665.75 | 0 | 0 | 0 | 0 | 0 | -15665.75 | 0 | 508334.25 | 0 | [6 empty] | CM_WSI | 100%
400754 | Capital Maintenance SR10 Service Reservoir Control West Leakage Delivery Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-06-21 | 2015-06-15 |  | Scottish Water Wide | 176973 | -671.15 | 0 | 0 | 0 | 0 | 0 | -671.15 | 0 | 176301.85 | 0 | [6 empty] | CM_WSI | 100%
30532 | Carbarns (Wishaw) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-02-19 | 2010-06-28 | 2010-10-04 | 2012-03-22 | 2012-03-26 | North Lanarkshire | 8631398.41 | 14242.54 | -14364.54 | 0 | 0 | 0 | 0 | -122 | 0 | 8631276.41 | 136478.56 | [6 empty] | SG1 | 4.005% | EC10A | 6.014% | EC04A | 18.65% | EC01A | 23.4% | CM_WWNI | 47.93%
500806 | Carbarns WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2016-07-19 | 2017-08-28 | 2017-06-12 | 2017-06-12 | 2017-06-12 | North Lanarkshire | 0 | 10836.78 | 91986.07 | 21321.91 | 0 | 0 | 0 | 124144.76 | 0 | 124144.76 | 136478.56 | [6 empty] | SG1 | 100%
502584 | Carbarns WwTW - Inlet Screen Replacement | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-03-07 | 2018-10-03 | 2018-10-15 | 2021-02-01 | 2021-02-01 | North Lanarkshire | 0 | 0 | 4285.05 | 146534.61 | 696721.61 | 842614.59 | 185413.43 | 1875569.29 | 26302.45 | 1901871.74 | 136478.56 | [6 empty] | SG1 | 100%
500857 | Carbost Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-08-17 | 2017-06-25 | 2018-02-02 | 2018-04-30 | 2018-12-31 | Highland | 0 | 978.55 | 911.7 | 8342.19 | 14327.03 | -1821.45 | -757.93 | 21980.09 | 0 | 21980.09 | 4035.65 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 13.25
502627 | Carbost WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2027-04-02 | 2030-11-01 | 2031-01-06 | 2020-03-31 | 2032-03-17 | Highland | 0 | 0 | 20930.23 | 291.13 | 2187.97 | -17356.48 | 0 | 6052.85 | 0 | 6052.85 | 136478.56 | [6 empty] | WG1 | 100%
403528 | Cardowan Drive Stepps Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-07-12 | 2014-09-30 | 2014-11-10 | 2015-03-27 | 2015-03-27 | Glasgow City | 298317 | -36304.44 | 74.61 | 0.01 | 66026.5 | 0 | 0.32 | 29797 | 0 | 328114 | 204193.13 | [6 empty] | CS11 | 100%
45562 | Cardrona STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-02-07 | 2011-05-09 | 2011-11-10 | 2011-11-17 | Scottish Borders | 519365.92 | 78.34 | 0 | 0 | 0 | 0 | 0 | 78.34 | 0 | 519444.26 | 0 | [6 empty] | WQ01 | 19.75% | CM_WWNI | 80.25%
502824 | Cardrona WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-02 | 2028-07-19 | 2028-11-09 | 2029-10-30 | 2030-01-30 | Scottish Borders | 0 | 0 | 0 | 74056.35 | 14864.16 | 17434.57 | 0 | 106355.08 | 893644.87 | 999999.95 | 136478.56 | [6 empty] | SG1 | 100%
502222 | Carfin Improvement Plan - Rollout of Network Access System | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2016-08-15 | 2016-08-15 | 2016-11-16 | 2017-07-20 | 2017-07-20 | Scottish Water Wide | 0 | 0 | 566760 | -58287.71 | 0 | 0 | 0 | 508472.29 | 0 | 508472.29 | 0 | [6 empty] | CM_M&G | 100%
501554 | Carfin Incident - MD interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-12-23 | 2015-12-23 | 2016-04-27 | 2021-01-28 | 2021-01-28 | Scottish Water Wide | 0 | 400509 | 338338 | 7093756.8 | 1278126.75 | 23839.55 | 30359.12 | 9164929.22 | 3192.34 | 9168121.56 | 0 | [6 empty] | CM_WSI | 100%
501555 | Carfin Incident - SWD interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2020-02-25 | 2017-12-15 | Scottish Water Wide | 0 | 81 | 758928.19 | 173329.75 | 30761.06 | -131899.62 | 0 | 831200.38 | 0 | 831200.38 | 0 | [6 empty] | CM_WSI | 100%
502398 | Carfin Incident Plan - Consultancy Support | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-27 | 2021-09-20 | 2021-09-21 | 2022-04-25 | 2022-04-25 | Scottish Water Wide | 0 | 0 | 99300 | 1834927.88 | 336393.97 | 120165.21 | 107532.74 | 2498319.8 | 1680.19 | 2499999.99 | 0 | [6 empty] | CM_M&G | 100%
501212 | Cargen Borehole WTW - Improving WQ in Network (OMG5) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-28 | 2016-03-04 | 2016-03-07 | 2016-03-31 | 2016-06-30 | Dumfries and Galloway | 0 | 2527 | -2092.11 | 0 | 0 | 0 | 0 | 434.89 | 0 | 434.89 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501151 | Cargenbridge SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-06-14 | 2018-04-30 | 2018-10-18 | 2020-05-14 | 2020-05-14 | Dumfries and Galloway | 0 | 0 | 35966 | 306274 | 928796 | 484476.89 | 19624.11 | 1775137 | 2400 | 1777537 | 0 | [6 empty] | CM_WWNI | 100%
402933 | Carloway WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-10-23 | 2013-12-23 | 2015-05-18 | 2018-04-01 | 2018-04-01 | Na H-Eileanan an Iar | 38035 | 3315 | 90811.13 | 204932.6 | -169.48 | -107.56 | 0 | 298781.69 | 0 | 336816.69 | 0 | [6 empty] | SG1 | 100%
403342 | Carluke (Mauldslie) - Overland sewer pipelines and pipebridges | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2013-08-20 | 2013-08-20 | 2015-10-15 | 2015-11-11 | South Lanarkshire | 1975828 | 36754 | 5977.45 | -26818.82 | 30.96 | 0 | 0 | 15943.59 | 0 | 1991771.59 | 0 | [6 empty] | CM_WWI | 100%
501163 | Carmyle SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-12-02 | 2017-06-05 | 2017-11-09 | 2019-02-27 | 2019-02-27 | Glasgow City | 0 | 1438 | 74837 | 515613 | 163895 | 5204.45 | 83.55 | 761071 | 0 | 761071 | 0 | [6 empty] | CM_WWNI | 100%
502240 | Carmyle SPS Rising Main | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2020-09-30 | 2021-08-09 | 2021-10-25 | 2022-06-08 | 2022-09-12 | Glasgow City | 0 | 0 | 9332.07 | 1681.32 | 0 | 2382.69 | 6603.93 | 20000.01 | 0 | 20000.01 | 0 | [6 empty] | SR21_WW | 100%
404089 | Carnac SPS - Main MCC Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-01-20 | 2015-03-27 | 2015-09-07 | 2016-06-16 |  | Highland | 12787.39 | 283932.61 | -35613.94 | 0 | 0 | 0 | 0 | 248318.67 | 0 | 261106.06 | 0 | [6 empty] | CM_WWNI | 100%
503079 | Carnethie Street Rosewell | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2020-05-13 | 2021-04-08 | 2021-07-01 | 2022-01-26 | 2022-04-28 | Midlothian | 0 | 0 | 0 | 9700.06 | 7036.58 | 23541.25 | 189725.34 | 230003.23 | 589444.77 | 819448 | 0 | [6 empty] | CM_WWI | 100%
503828 | Carnoustie Ravensby Rd SW Flap Valve (SVCD-MD) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2019-12-04 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 17651.03 | 0 | 17651.03 | 0 | 17651.03 | 0 | [6 empty] | CM_WWI | 100%
502367 | Carradale TWP Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-05-05 | 2021-02-01 | 2021-03-25 | 2021-05-03 | 2021-05-11 | Argyll and Bute-North Argyll | 0 | 0 | 17507.18 | 13935.17 | 687.06 | 0 | 0 | 32129.41 | 0 | 32129.41 | 0 | [6 empty] | CM_WSNI | 100%
503240 | Carradale WTW Treatment Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-02-01 | 2028-04-25 | 2029-01-24 | 2029-04-24 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 4790.28 | 37148.26 | 12291.96 | 54230.5 | 1445769.35 | 1499999.85 | 0 | [6 empty] | CM_WSNI | 100%
45315 | Carradale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2013-03-22 | 2013-09-06 | Argyll and Bute-North Argyll | 267842.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267842.49 | 0 | [6 empty] | DW13 | 100%
505028 | Carrbridge WwTW - RAS/SAS Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 261.68 | 0 | 261.68 | 0 | 261.68 | 0 | [6 empty] | CM_WWNI | 100%
502598 | Carron Valley CWTs Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS5 | 2017-06-30 | 2018-06-28 | 2018-07-16 | 2019-05-30 | 2019-05-30 | Falkirk | 0 | 0 | 1709.09 | 178429.55 | 1015727.85 | 10204.51 | 0 | 1206071 | 0 | 1206071 | 0 | [6 empty] | CM_WSNI | 100%
502276 | Carron Valley IOS Works | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS4 | 2017-04-04 | 2018-07-30 | 2018-08-06 | 2020-03-12 | 2020-04-01 | Stirling | 0 | 0 | 8222.26 | 17414.74 | 836163.79 | 85533.83 | 1409.4 | 948744.02 | 1500 | 950244.02 | 620599.9 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-13
503250 | Carron Valley RSZ Cleaning Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-06-21 | 2019-09-11 | 2021-03-31 | 2022-06-30 | Stirling | 0 | 0 | 0 | 0 | 541245 | 725018.24 | 566365.76 | 1832629 | 0 | 1832629 | 1464613.17 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 344.7394
502605 | Carron Valley RSZ Cleaning - Mains Conditioning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-06-11 | 2019-08-02 | 2021-04-30 | 2021-07-31 | Stirling | 0 | 0 | 46297 | 189763.03 | 154348.98 | 259526.19 | 645152.72 | 1295087.92 | 1986.15 | 1297074.07 | 3353220.77 | [6 empty] | DW5MC | 100% | [18 empty] | Regulatory Outputs OMG-06: 175.2
501089 | Carron Valley WOA Banton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2016-04-13 | 2018-09-06 | 2018-09-17 | 2019-02-11 | 2019-02-11 | Falkirk | 0 | 6048 | 5410.17 | 70355.83 | 335435.14 | 5550.61 | -2781.76 | 420017.99 | 0 | 420017.99 | 0 | [6 empty] | CM_WSI | 100%
500013 | Carron Valley WOA Beltmoss WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-19 | 2028-03-16 | 2028-05-19 | 2029-01-22 | 2029-04-04 | Falkirk | 716 | 24477 | 2326 | 0 | 13742 | -6050.12 | 6116.05 | 40610.93 | 314040.1 | 355367.03 | 0 | [6 empty] | CM_WSI | 100%
501088 | Carron Valley WOA Drumtrocher WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-13 | 2028-03-09 | 2028-05-12 | 2029-01-15 | 2029-04-17 | Falkirk | 0 | 0 | 10138.89 | 3861.11 | 5778 | -4607.75 | 4607.75 | 19778 | 719146.29 | 738924.29 | 0 | [6 empty] | CM_WSI | 100%
501087 | Carron Valley WOA Little Denny WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500105 | Carron Valley WOA Parkhead WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-04-13 | 2017-01-25 | 2017-01-25 | 2018-02-21 | 2018-02-21 | Falkirk | 0 | 40069 | 644286 | 351224 | 327051.01 | -54909.93 | 0 | 1307720.08 | 0 | 1307720.08 | 0 | [6 empty] | CM_WSI | 100%
500061 | Carron Valley WTW - Broadside Landfill | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2027-06-10 | 2027-08-05 | 2028-11-27 | 2028-11-27 | Falkirk | 0 | 45283 | 55525.4 | -5579.15 | -1545.93 | -1619.83 | 5342.99 | 97406.48 | 1465597.21 | 1563003.69 | 0 | [6 empty] | CM_WSNI | 100%
505553 | Carsphairn Auto Shutdown Low Chlorine | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS4 | 2020-03-19 |  |  | 2020-03-31 | 2021-06-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 215.3 | 0 | 215.3 | 0 | 215.3 | 214171.41 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500478 | Carsphairn WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2016-12-13 | 2018-03-30 | 2018-08-13 |  |  | Dumfries and Galloway | 0 | 11106.06 | 19425.05 | 18815.94 | 61230.85 | 199821.05 | 43165.77 | 353564.72 | 54121.91 | 407686.63 | 214171.41 | [6 empty] | DW25P | 100%
30136 | Carstairs Village STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-15 | 2010-12-30 | 2011-02-14 | 2011-12-21 | 2012-03-02 | North Lanarkshire | 1317525.88 | 1380.88 | 0 | 0 | 0 | 0 | 0 | 1380.88 | 0 | 1318906.76 | 0 | [6 empty] | EC04A | 100%
500052 | Carstairs Village WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-07-07 | 2019-08-30 | 2020-01-13 | 2021-04-27 | 2021-04-28 | South Lanarkshire | 0 | 54006.59 | 101633.03 | 403261 | 378898.83 | 803459.82 | 2983434.2 | 4724693.47 | 1926192.53 | 6650886 | 136478.56 |  |  |  |  | 15850 |  | SG1 | 100%
400067 | Cartland ST Zero Carbon Pilot Plant | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-09-24 | 2012-01-24 | 2012-02-06 | 2013-03-01 | 2013-03-27 | South Lanarkshire | 1669686.31 | 89751.58 | -29024.87 | 0 | 0 | 0 | 0 | 60726.71 | 0 | 1730413.02 | 0 |  |  |  |  | 16632 |  | EC10A | 33.33% | SG3 | 33.33% | EC04A | 33.33%
502169 | Cartmoor Burn Scone | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-05-06 | 2017-02-03 | 2017-03-17 | 2017-06-30 | 2017-06-30 | Perth and Kinross | 0 | 0 | 79196 | 65961 | 8549.36 | -2236.47 | 530.11 | 152000 | 0 | 152000 | 0 | [6 empty] | CM_WWI | 100%
500119 | Castle Douglas DOA (DOA000097) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-25 | 2017-08-30 | Dumfries and Galloway | 0 | 24256 | 106458.72 | 7380.49 | -2383.68 | 0 | 0 | 135711.53 | 0 | 135711.53 | 52680.68 | [6 empty] | CS16D | 50% | EC01D | 50%
503314 | Castle Douglas WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 29390.39 | 0 | 0 | 29390.39 | 0 | 29390.39 | 136478.56 | [6 empty] | SG1 | 100%
404117 | Castle House Meeting Rms Refurbishment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-07-10 | 2015-08-19 | Fife | 80000 | 5617.98 | 0 | 0 | 0 | 0 | 0 | 5617.98 | 0 | 85617.98 | 0 | [6 empty] | CM_M&G | 100%
501657 | Castle St-Mount Pleasant Rothesay - Relay sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-06-29 | 2017-05-25 | 2017-05-29 | 2018-03-14 | 2018-03-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 9173.02 | 139370.48 | -36968.98 | -7266.58 | 0 | 104307.94 | 0 | 104307.94 | 0 | [6 empty] | CM_WWI | 100%
500991 | Castle Street Dingwall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-10-21 | 2017-05-09 | 2017-06-30 | 2018-04-30 | 2018-04-30 | Highland | 0 | 10755 | 94268 | 153803 | 15554.63 | 0 | 0 | 274380.63 | 0 | 274380.63 | 0 | [6 empty] | CM_WWI | 100%
400058 | Castlegreen SPS Refurb SPS000108 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2012-01-24 | 2012-04-23 | 2013-01-16 |  | West Dunbartonshire | 876403.11 | -52.2 | 0 | 0 | 0 | 0 | 0 | -52.2 | 0 | 876350.91 | 0 | [6 empty] | CM_WWNI | 100%
501529 | Castlemilk High SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2016-12-23 | 2018-03-09 | 2018-04-04 | 2019-01-31 | 2019-01-31 | Glasgow City | 0 | 0 | 3385.88 | 160839.22 | 774041.83 | -79573.73 | 1608.13 | 860301.33 | 0 | 860301.33 | 0 | [6 empty] | CM_WSNI | 100%
402775 | Cat 2 Access improvements at 8nr package SPS - North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-07-16 | 2013-06-19 | 2013-10-16 | 2016-03-21 |  | Highland | 657779 | 87436 | -22476.02 | 0 | 0 | 0 | 0 | 64959.98 | 0 | 722738.98 | 0 | [6 empty] | CM_WWI | 100%
500031 | Catchment Assessment Study for Drinking Water Quality Protection | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-01 | 2017-07-14 | Scottish Water Wide | 153.33 | 126569.65 | 38277.02 | 8613.7 | -10136.01 | 0 | 0 | 163324.36 | 0 | 163477.69 | 300888.64 | [6 empty] | DW25PS | 100%
502967 | Catherinefield Road SPS RM | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | Dumfries and Galloway | 0 | 0 | 0 | 12576.16 | 13056.58 | 0 | 0 | 25632.74 | 0 | 25632.74 | 0 | [6 empty] | CM_WWI | 100%
501588 | Cathodic Protection Dunblane to North Third | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-08 | 2027-11-10 | 2027-12-30 | 2028-07-26 | 2028-10-26 | Falkirk | 0 | 0 | 3865.55 | 0 | 2000.09 | 295.34 | 0 | 6160.98 | 283054.12 | 289215.1 | 0 | [6 empty] | CM_WSI | 100%
501812 | Cathodic Protection Quarter to Millhall Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-08 | 2027-11-10 | 2027-12-30 | 2028-07-26 | 2028-10-26 | Falkirk | 0 | 0 | 13522.28 | -8206.31 | 2000.31 | 365.85 | 0 | 7682.13 | 351970.61 | 359652.74 | 0 | [6 empty] | CM_WSI | 100%
30138 | Catrineholm (Catrine) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-07-01 | 2011-07-25 | 2016-09-29 | 2016-03-29 | East Ayrshire | 1939092.84 | 2222069.07 | 828721 | -391.78 | -5747.28 | 0 | 0 | 3044651.01 | 0 | 4983743.85 | 1055613.09 | [6 empty] | CM_WWNI | 25% | EC04A | 75%
401912 | Causewayend Private Water Supply Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-22 | 2011-09-05 | 2011-09-05 | 2012-07-31 | 2015-06-22 | West Lothian | 112498 | 23216 | 17662.7 | -1450.13 | 0 | 0 | -24.78 | 39403.79 | 0 | 151901.79 | 0 | [6 empty] | DW10 | 100%
500303 | CC Dom Wastewater Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 254224.19 | 544716.15 | 692967.54 | 1268171.26 | 886475.95 | 880202.97 | 4526758.06 | 0 | 4526758.06 | 591600.75 | [6 empty] | SG2 | 100%
500304 | CC Dom Wastewater Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-04-30 | 2021-04-30 | Aberdeenshire | 0 | 2020013.3 | 1091246.23 | 310401.06 | 1678995.2 | 698595.31 | 1038028.93 | 6837280.03 | 239581.23 | 7076861.26 | 591600.75 | [6 empty] | SG2 | 100%
500305 | CC Dom Wastewater Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Angus | 0 | 21522.26 | 16661.26 | 479084.16 | 162543.39 | 2874.93 | 150422.3 | 833108.3 | 0 | 833108.3 | 591600.75 | [6 empty] | SG2 | 100%
500306 | CC Dom Wastewater Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | 98082.67 | 76627.67 | 128.21 | 29777.78 | 45084.97 | 249701.3 | 0 | 249701.3 | 591600.75 | [6 empty] | SG2 | 100%
500307 | CC Dom Wastewater Borders (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 9514.16 | 26792.35 | 30109.49 | 358603.49 | 171153.48 | 131360.12 | 727533.09 | 0 | 727533.09 | 591600.75 | [6 empty] | SG2 | 100%
500308 | CC Dom Wastewater Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 54538.61 | 30267.08 | 222971.46 | 37093.97 | 610.64 | 76123.08 | 421604.84 | 0 | 421604.84 | 591600.75 | [6 empty] | SG2 | 100%
500309 | CC Dom Wastewater Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 28905.21 | 150914.7 | 47019.63 | 17885.22 | 64091.33 | 68044.21 | 376860.3 | 0 | 376860.3 | 591600.75 | [6 empty] | SG2 | 100%
500310 | CC Dom Wastewater Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 66288.53 | 94544.33 | 58972.54 | 302518.83 | 67275.67 | 125572.96 | 715172.86 | 0 | 715172.86 | 591600.75 | [6 empty] | SG2 | 100%
500311 | CC Dom Wastewater East Ayrshire(2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 280489.15 | 321981.45 | 92805.26 | 91502.54 | 151961.81 | 206841.06 | 1145581.27 | 0 | 1145581.27 | 591600.75 | [6 empty] | SG2 | 100%
500312 | CC Dom Wastewater East Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 56046.76 | 1040136.62 | 124499.1 | 885950.63 | 421320.98 | 320101.55 | 2848055.64 | 0 | 2848055.64 | 591600.75 | [6 empty] | SG2 | 100%
500314 | CC Dom Wastewater East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 75241.12 | 218545.95 | 158046.77 | 2332741.98 | 31012.91 | 657167.21 | 3472755.94 | 0 | 3472755.94 | 591600.75 | [6 empty] | SG2 | 100%
500315 | CC Dom Wastewater Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 242058.68 | 859110.26 | 622915.13 | 1412193.36 | 518165.34 | 742130.88 | 4396573.65 | 0 | 4396573.65 | 591600.75 | [6 empty] | SG2 | 100%
500316 | CC Dom Wastewater Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 685598.42 | 283684.21 | 183599.29 | 1658746.26 | 190739.44 | 661538.6 | 3663906.22 | 0 | 3663906.22 | 591600.75 | [6 empty] | SG2 | 100%
500317 | CC Dom Wastewater Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Fife | 0 | 150300.27 | 340500.72 | 358938.91 | 800041.95 | 523761 | 342020.7 | 2515563.55 | 0 | 2515563.55 | 591600.75 | [6 empty] | SG2 | 100%
500318 | CC Dom Wastewater Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 682112.31 | 892085.69 | 991262.39 | 904494.88 | 1038583.18 | 968155.3 | 5476693.75 | 0 | 5476693.75 | 591600.75 | [6 empty] | SG2 | 100%
500319 | CC Dom Wastewater Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Highland | 0 | 1030869.59 | 689020.41 | -29432.39 | 543262.7 | 1095294.01 | 714617.78 | 4043632.1 | 0 | 4043632.1 | 591600.75 | [6 empty] | SG2 | 100%
500320 | CC Dom Wastewater Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 257553.29 | 240311.07 | 16405.55 | 74627.52 | 110268.56 | 147075.23 | 846241.22 | 0 | 846241.22 | 591600.75 | [6 empty] | SG2 | 100%
500321 | CC Dom Wastewater Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 384664.79 | 871358.43 | 588529.28 | 569016.61 | 940721.52 | 739080.97 | 4093371.6 | 0 | 4093371.6 | 591600.75 | [6 empty] | SG2 | 100%
500322 | CC Dom Wastewater Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Moray | 0 | 807072.06 | 33976.31 | -14445.99 | 134255.05 | 35619.66 | 219562.72 | 1216039.81 | 0 | 1216039.81 | 591600.75 | [6 empty] | SG2 | 100%
500323 | CC Dom Wastewater Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | 185611.68 | 19525.26 | 0 | -0.27 | 45199.63 | 250336.3 | 0 | 250336.3 | 591600.75 | [6 empty] | SG2 | 100%
500324 | CC Dom Wastewater North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 268608.65 | 43792.6 | 223003.54 | 67380.08 | 0 | 132817.01 | 735601.88 | 0 | 735601.88 | 591600.75 | [6 empty] | SG2 | 100%
500325 | CC Dom Wastewater North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 592093.94 | 582885.44 | 422669.22 | 1138659.03 | 713779.03 | 752846.75 | 4202933.41 | 0 | 4202933.41 | 591600.75 | [6 empty] | SG2 | 100%
500326 | CC Dom Wastewater Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 20133.36 | 199627.9 | 23049.18 | 24305.76 | 67768.77 | 83135.37 | 418020.34 | 0 | 418020.34 | 591600.75 | [6 empty] | SG2 | 100%
500327 | CC Dom Wastewater Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 72711.5 | 521075.4 | 177505 | 101391.53 | 257313.02 | 248982.27 | 1378978.72 | 0 | 1378978.72 | 591600.75 | [6 empty] | SG2 | 100%
500328 | CC Dom Wastewater Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 131987.72 | 317456.35 | 73537.99 | 258213.93 | 661714.99 | 305023.52 | 1747934.5 | 0 | 1747934.5 | 591600.75 | [6 empty] | SG2 | 100%
500329 | CC Dom Wastewater Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 50395.99 | 59317.6 | 0 | 9283.71 | 15224.69 | 29574.35 | 163796.34 | 0 | 163796.34 | 591600.75 | [6 empty] | SG2 | 100%
500330 | CC Dom Wastewater South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 53428.95 | 72710.97 | 28707.71 | 245389.72 | 0.29 | 88187.94 | 488425.58 | 0 | 488425.58 | 591600.75 | [6 empty] | SG2 | 100%
500331 | CC Dom Wastewater South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | -103318.83 | 677623.79 | 538167.65 | 1036275.47 | 735061.42 | 691645.29 | 3575454.79 | 0 | 3575454.79 | 591600.75 | [6 empty] | SG2 | 100%
500332 | CC Dom Wastewater Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 46253.97 | 285817.68 | 571397.51 | -91748.37 | 37336.79 | 187080.46 | 1036138.04 | 0 | 1036138.04 | 591600.75 | [6 empty] | SG2 | 100%
500333 | CC Dom Wastewater West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 123410.3 | 58898.69 | 182041.61 | 106368.85 | 31282.88 | 110610.69 | 612613.02 | 0 | 612613.02 | 591600.75 | [6 empty] | SG2 | 100%
500334 | CC Dom Wastewater West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 124195.87 | 1002145.24 | 782055.56 | 853864.72 | 37878.59 | 666968.87 | 3467108.85 | 0 | 3467108.85 | 591600.75 | [6 empty] | SG2 | 100%
500367 | CC Dom Water Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 375481.16 | 547820.36 | 195990.97 | 340791.95 | 385113.72 | 389830.71 | 2235028.87 | 0 | 2235028.87 | 233661.75 | [6 empty] | WG2 | 100%
500368 | CC Dom Water Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 760768.23 | 700523.79 | 458756.96 | 723835.15 | 1408647.09 | 888799.69 | 4941330.91 | 0 | 4941330.91 | 233661.75 | [6 empty] | WG2 | 100%
500369 | CC Dom Water Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Angus | 0 | 59694.27 | 158331 | 57680.31 | 129778.42 | 15514.22 | 82680.51 | 503678.73 | 0 | 503678.73 | 233661.75 | [6 empty] | WG2 | 100%
500370 | CC Dom Water Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | 74804.16 | 232.19 | 59517.92 | 7935.02 | 31560.09 | 174049.38 | 0 | 174049.38 | 233661.75 | [6 empty] | WG2 | 100%
500371 | CC Dom Water Borders (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 73618.17 | 178059.23 | 21456.88 | 148962.38 | 71862.14 | 92381.23 | 586340.03 | 0 | 586340.03 | 233661.75 | [6 empty] | WG2 | 100%
500372 | CC Dom Water Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 10173.05 | 100112.37 | 70834.04 | 32170.29 | 46757.57 | 57298.57 | 317345.89 | 0 | 317345.89 | 233661.75 | [6 empty] | WG2 | 100%
500373 | CC Dom Water Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 35570.14 | 105679.16 | 12935.6 | 65029.22 | 25205.59 | 53989.4 | 298409.11 | 0 | 298409.11 | 233661.75 | [6 empty] | WG2 | 100%
500374 | CC Dom Water Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 103943.99 | 277335.46 | -684.57 | 107572.73 | 141570.93 | 128902.04 | 758640.58 | 0 | 758640.58 | 233661.75 | [6 empty] | WG2 | 100%
500375 | CC Dom Water East Ayrshire(2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 164251.4 | 191074.94 | 54880.3 | 114398.04 | 65109.83 | 123275.13 | 712989.64 | 0 | 712989.64 | 233661.75 | [6 empty] | WG2 | 100%
500376 | CC Dom Water East Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 74255.24 | 59107.84 | 170608.06 | 130369.06 | 148313.47 | 72254.77 | 654908.44 | 0 | 654908.44 | 233661.75 | [6 empty] | WG2 | 100%
500313 | CC Dom Water East Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 481890.8 | 615184.71 | 384161.33 | 564471.02 | 222885.21 | 547814.08 | 2816407.15 | 0 | 2816407.15 | 591600.75 | [6 empty] | SG2 | 100%
500377 | CC Dom Water East Lothian (2015-18) - 5003770000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 166882.23 | 914100.22 | 84550.17 | 353801.48 | 180009.09 | 366425.4 | 2065768.59 | 0 | 2065768.59 | 233661.75 | [6 empty] | WG2 | 100%
500378 | CC Dom Water East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 87873.85 | 190420.97 | -18786.08 | 97657.74 | 57466.02 | 91359.7 | 505992.2 | 0 | 505992.2 | 233661.75 | [6 empty] | WG2 | 100%
500379 | CC Dom Water Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 366936.26 | 949991.89 | 420888.69 | 793237.75 | 487619.08 | 541063.88 | 3559737.55 | 0 | 3559737.55 | 233661.75 | [6 empty] | WG2 | 100%
500380 | CC Dom Water Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 560808.56 | 131548.21 | 161399.41 | 1143452.34 | 76031.89 | 417269.82 | 2490510.23 | 0 | 2490510.23 | 233661.75 | [6 empty] | WG2 | 100%
500381 | CC Dom Water Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | Fife | 0 | 272632.63 | 512547.8 | 364422.41 | 370969.47 | 254236.53 | 372278.98 | 2147087.82 | 0 | 2147087.82 | 233661.75 | [6 empty] | WG2 | 100%
500382 | CC Dom Water Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 372677.09 | 613249.84 | 191630.13 | 643297.68 | 286988.95 | 435576.79 | 2543420.48 | 0 | 2543420.48 | 233661.75 | [6 empty] | WG2 | 100%
500383 | CC Dom Water Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Highland | 0 | 246372.47 | 312008.04 | 220747.74 | 547777.28 | 609151.53 | 413169.74 | 2349226.8 | 0 | 2349226.8 | 233661.75 | [6 empty] | WG2 | 100%
500384 | CC Dom Water Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 17540.78 | 72535.9 | -8796.47 | 36096.22 | 19105.23 | 25510.2 | 161991.86 | 0 | 161991.86 | 233661.75 | [6 empty] | WG2 | 100%
500385 | CC Dom Water Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 238339.11 | 510078.81 | 232535 | 521933.89 | 90288.63 | 300036.42 | 1893211.86 | 0 | 1893211.86 | 233661.75 | [6 empty] | WG2 | 100%
500386 | CC Dom Water Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | Moray | 0 | 442268.06 | 166783.43 | 51252.99 | 235777.03 | 51359.62 | 208758.19 | 1156199.32 | 0 | 1156199.32 | 233661.75 | [6 empty] | WG2 | 100%
500387 | CC Dom Water Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | 21859.87 | 3171.82 | 1132.69 | 0 | 5765.02 | 31929.4 | 0 | 31929.4 | 233661.75 | [6 empty] | WG2 | 100%
500388 | CC Dom Water North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 62489.6 | 117012.01 | 33780.97 | 96012.94 | 85435.63 | 68293.59 | 463024.74 | 0 | 463024.74 | 233661.75 | [6 empty] | WG2 | 100%
500389 | CC Dom Water North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 150190.61 | 640013.63 | 313693.63 | 805911.21 | 84463.47 | 454273.14 | 2448545.69 | 0 | 2448545.69 | 233661.75 | [6 empty] | WG2 | 100%
500390 | CC Dom Water Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 11093.41 | 44233.26 | -2628.72 | 48179.5 | -23252.78 | 17103.74 | 94728.41 | 0 | 94728.41 | 233661.75 | [6 empty] | WG2 | 100%
500391 | CC Dom Water Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 127705.48 | 287620.14 | 177599.35 | 240068.85 | 360236.98 | 254760.85 | 1447991.65 | 0 | 1447991.65 | 233661.75 | [6 empty] | WG2 | 100%
500392 | CC Dom Water Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 137377.62 | 270137.4 | 202499.3 | 749409.84 | 580831.7 | 443431.78 | 2383687.64 | 0 | 2383687.64 | 233661.75 | [6 empty] | WG2 | 100%
500393 | CC Dom Water Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 43760.67 | 43568.91 | -27414.04 | 5070.97 | -0.15 | 14319.05 | 79305.41 | 0 | 79305.41 | 233661.75 | [6 empty] | WG2 | 100%
500394 | CC Dom Water South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 98713.77 | 163263.59 | -36603.53 | 114910.17 | -38437.18 | 66508.61 | 368355.43 | 0 | 368355.43 | 233661.75 | [6 empty] | WG2 | 100%
500395 | CC Dom Water South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | 151888.6 | 537900.98 | 594934.31 | 714887.57 | 666422.22 | 560790.88 | 3226824.56 | 0 | 3226824.56 | 233661.75 | [6 empty] | WG2 | 100%
500396 | CC Dom Water Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 101982.96 | 143246.93 | 151660.38 | 143210.32 | 13999.93 | 122813.35 | 676913.87 | 0 | 676913.87 | 233661.75 | [6 empty] | WG2 | 100%
500397 | CC Dom Water West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 105166.84 | 45809.65 | 43540.57 | 52103.31 | 23449.35 | 59506.91 | 329576.63 | 0 | 329576.63 | 233661.75 | [6 empty] | WG2 | 100%
500398 | CC Dom Water West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 336950.81 | 526884.38 | 807970.26 | 222566.64 | 123822.47 | 448887.29 | 2467081.85 | 0 | 2467081.85 | 0 | [6 empty] | WG2 | 100%
500335 | CC Non-Dom Wastewater Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 0 | -102.67 | 102.67 | -23389.85 | 0 | -41852 | -65241.85 | 0 | -65241.85 | 591600.75 | [6 empty] | SG2 | 100%
500336 | CC Non-Dom Wastewater Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 0 | 24558.86 | -12183.44 | -12323.23 | -52.19 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500337 | CC Non-Dom Wastewater Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Angus | 0 | 0 | 8362.42 | -4094.23 | -4181.21 | -86.98 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500338 | CC Non-Dom Wastewater Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500339 | CC Non-Dom Wastewater Borders (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 0 | -10.82 | 10.82 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500403 | CC Non-Dom Wastewater Borders (2015-18) - 5004030000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 0 | 15.95 | 82.29 | 316.36 | -414.6 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500340 | CC Non-Dom Wastewater Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500341 | CC Non-Dom Wastewater Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 0 | 9546.06 | -4778.54 | -4767.52 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500342 | CC Non-Dom Wastewater Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 0 | 0 | 36.32 | 0 | -36.32 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500343 | CC Non-Dom Wastewater East Ayrshire(2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 1.01 | 0 | 1.01 | 591600.75 | [6 empty] | SG2 | 100%
500344 | CC Non-Dom Wastewater East Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500345 | CC Non-Dom Wastewater East Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500346 | CC Non-Dom Wastewater East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500347 | CC Non-Dom Wastewater Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 0 | -77.31 | 321.54 | 0 | -241.94 | -1.31 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500348 | CC Non-Dom Wastewater Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 0 | 50.1 | -50.1 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500349 | CC Non-Dom Wastewater Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500350 | CC Non-Dom Wastewater Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 0 | 3575.22 | -1721.61 | -1787.61 | -66 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500351 | CC Non-Dom Wastewater Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500352 | CC Non-Dom Wastewater Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500353 | CC Non-Dom Wastewater Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 0 | 0 | 75 | 0 | -75 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500354 | CC Non-Dom Wastewater Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Moray | 0 | 0 | 0 | 180 | 0 | -180 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500355 | CC Non-Dom Wastewater Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | -39 | 39 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500356 | CC Non-Dom Wastewater North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 0 | -111.94 | 439.69 | 0 | -327.75 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500357 | CC Non-Dom Wastewater North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500358 | CC Non-Dom Wastewater Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500359 | CC Non-Dom Wastewater Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500360 | CC Non-Dom Wastewater Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500361 | CC Non-Dom Wastewater Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500362 | CC Non-Dom Wastewater South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500363 | CC Non-Dom Wastewater South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | 0 | 0 | 0 | 6053.6 | 0 | 10832.01 | 16885.61 | 0 | 16885.61 | 591600.75 | [6 empty] | SG2 | 100%
500364 | CC Non-Dom Wastewater Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 0 | -25.33 | 170.12 | 0 | -144.79 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500365 | CC Non-Dom Wastewater West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500366 | CC Non-Dom Wastewater West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 591600.75 | [6 empty] | SG2 | 100%
500399 | CC Non-Dom Water Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 0 | 22026.88 | 2729.99 | -19118.95 | 0 | 2544.09 | 8182.01 | 0 | 8182.01 | 233661.75 | [6 empty] | WG2 | 100%
500400 | CC Non-Dom Water Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 0 | -2166.62 | 25940.47 | -9661.61 | 0 | 5706.76 | 19819 | 0 | 19819 | 233661.75 | [6 empty] | WG2 | 100%
500401 | CC Non-Dom Water Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Angus | 0 | 0 | 0 | 0 | 1854.03 | 0 | -1853.05 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500402 | CC Non-Dom Water Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | -142.68 | 1934.9 | -862.53 | -929.69 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500404 | CC Non-Dom Water Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 0 | 0 | 68.05 | 0 | -68.05 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500405 | CC Non-Dom Water Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 0 | 4.2 | 942.78 | 1412.56 | 0 | -2358.56 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500406 | CC Non-Dom Water Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 0 | -115.55 | 2906.02 | -1977.02 | -813.45 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500407 | CC Non-Dom Water East Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 0 | 0 | 740.59 | 499.77 | 0 | -1239.38 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500408 | CC Non-Dom Water East Dumbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 0 | -85.65 | 159.32 | 0 | -73.67 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500409 | CC Non-Dom Water East Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 0 | -142.59 | 627.25 | 58 | -542.66 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500410 | CC Non-Dom Water East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 0 | 62.66 | -62.66 | 386.8 | -773.6 | 387.78 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500411 | CC Non-Dom Water Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 0 | -451.54 | 1053.09 | 1846.32 | 0 | -2446.89 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500412 | CC Non-Dom Water Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 0 | 125.32 | -125.32 | 74.27 | -74.27 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500413 | CC Non-Dom Water Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Fife | 0 | 0 | -225.54 | 1415.71 | 427.9 | 0 | -1617.09 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500414 | CC Non-Dom Water Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 0 | -295.63 | 5478.32 | 2132.81 | 0 | 3102.51 | 10418.01 | 0 | 10418.01 | 233661.75 | [6 empty] | WG2 | 100%
500415 | CC Non-Dom Water Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Highland | 0 | 490 | -198.54 | 591.19 | 1412.89 | 0 | -2294.56 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500416 | CC Non-Dom Water Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 317.76 | -49.63 | 113.07 | 456.67 | -837.87 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500417 | CC Non-Dom Water Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 0 | -197.14 | 197.14 | 350.22 | -350.22 | 1.01 | 1.01 | 0 | 1.01 | 233661.75 | [6 empty] | WG2 | 100%
500418 | CC Non-Dom Water Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Moray | 0 | 0 | 109.55 | 3993.17 | -2661.49 | 0 | -1440.25 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500419 | CC Non-Dom Water Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | -105.46 | 445.08 | 265.51 | -605.13 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500420 | CC Non-Dom Water North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 0 | -103.35 | 729.13 | 114.4 | -740.18 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500421 | CC Non-Dom Water North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 0 | 62.66 | 67.29 | 1123.14 | 0 | -1252.11 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500422 | CC Non-Dom Water Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 0 | 0 | 0 | 45.7 | -45.7 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500423 | CC Non-Dom Water Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 0 | -314.7 | 3295.43 | -2681.98 | -298.75 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500424 | CC Non-Dom Water Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 0 | 0 | 0 | 1877.47 | 0 | -1876.49 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500425 | CC Non-Dom Water Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 0 | 0 | 0 | 77.55 | -77.55 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500426 | CC Non-Dom Water South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 0 | 0 | 173.06 | 477.66 | -650.72 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500427 | CC Non-Dom Water South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | 0 | -359.7 | 439.51 | 1006.1 | 0 | -1084.93 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500428 | CC Non-Dom Water Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 0 | -212.17 | 997.72 | 180.16 | -965.71 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500429 | CC Non-Dom Water West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 0 | 0 | 758.29 | 250.59 | 0 | -1007.9 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
500430 | CC Non-Dom Water West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 0 | 12.7 | 395.43 | 155.66 | -563.79 | 0.98 | 0.98 | 0 | 0.98 | 233661.75 | [6 empty] | WG2 | 100%
400226 | CC Non-Domestic WasteWater Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 0 | 0 | 0 | 41001.33 | 40875.6 | 0 | 0 | 81876.93 | 0 | 81876.93 | 0 | [6 empty] | SG2 | 100%
400229 | CC Non-Domestic WasteWater Argyll and Bute | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Argyll and Bute-North Argyll | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | [6 empty] | SG2 | 100%
400233 | CC Non-Domestic WasteWater Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | [6 empty] | SG2 | 100%
400234 | CC Non-Domestic WasteWater East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 0 | 0 | 0 | 120 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400238 | CC Non-Domestic WasteWater Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 0 | 0 | -73.96 | 73.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400240 | CC Non-Domestic WasteWater Fife | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Fife | 0 | 0 | 0.74 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0.74 | 0 | [6 empty] | SG2 | 100%
400241 | CC Non-Domestic WasteWater Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400248 | CC Non-Domestic WasteWater North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400162 | CC Non-Domestic Water Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 15805.15 | -15805.15 | 51.93 | -13400.17 | 0 | 0 | 29153.39 | 0 | 0 | 15805.15 | 0 | [6 empty] | WG2 | 100%
400163 | CC Non-Domestic Water Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeenshire | 55.15 | -55.15 | -12323.23 | 15079.31 | -5512.16 | 0 | 55 | -2756.23 | 0 | -2701.08 | 0 | [6 empty] | WG2 | 100%
400164 | CC Non-Domestic Water Angus | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | Angus | 0 | 0 | -4181.21 | 4181.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400168 | CC Non-Domestic Water Dumfries and Galloway | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dumfries and Galloway | 1008.78 | -1008.78 | -4713.89 | 4713.89 | 0 | 0 | 1008.78 | 0 | 0 | 1008.78 | 0 | [6 empty] | WG2 | 100%
400169 | CC Non-Domestic Water Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 0 | 0 | -51.09 | 4044.39 | -7986.6 | 0 | 0 | -3993.3 | 0 | -3993.3 | 0 | [6 empty] | WG2 | 100%
400170 | CC Non-Domestic Water East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400172 | CC Non-Domestic Water East Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Lothian | 0 | 0 | 51.93 | -51.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400173 | CC Non-Domestic Water East Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400174 | CC Non-Domestic Water Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 0 | 0 | 53.62 | -53.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400177 | CC Non-Domestic Water Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 0 | 0 | -1787.61 | 1787.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400178 | CC Non-Domestic Water Highland | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Highland | 0 | 0 | 104.26 | 195.04 | 0 | 0 | 0 | 299.3 | 0 | 299.3 | 0 | [6 empty] | WG2 | 100%
400182 | CC Non-Domestic Water Na H-Eileanan an Iar | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Na H-Eileanan an Iar | 61.34 | 0 | 62.66 | -124 | 0 | 0 | 61.34 | 0 | 0 | 61.34 | 0 | [6 empty] | WG2 | 100%
400184 | CC Non-Domestic Water North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 0 | 0 | -11.65 | 11.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400186 | CC Non-Domestic Water Perth and Kinross | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 0 | 0 | 62.66 | -62.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400190 | CC Non-Domestic Water South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Lanarkshire | 0 | 0 | 62.96 | -62.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400192 | CC Non-Domestic Water West Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400193 | CC Non-Domestic Water West Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS6 | 2010-03-31 |  | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400194 | CC WasteWater Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 645202.78 | -120 | -198754.89 | 49424.59 | 149450.3 | 0 | 0.22 | 0.22 | 0 | 645203 | 0 | [6 empty] | SG2 | 100%
400195 | CC WasteWater Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeenshire | 4439801.95 | -135 | -308500.05 | 270842.55 | 37417.5 | 0 | 375.05 | 0.05 | 0 | 4439802 | 0 | [6 empty] | SG2 | 100%
400196 | CC WasteWater Angus | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Angus | 811134.81 | -121.16 | -4219.1 | -142979.72 | 147319.98 | 0 | 0.19 | 0.19 | 0 | 811135 | 0 | [6 empty] | SG2 | 100%
400197 | CC WasteWater Argyll and Bute | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Argyll and Bute-North Argyll | 385341.75 | 0 | 75.96 | 0 | -128.21 | 0 | 52.5 | 0.25 | 0 | 385342 | 0 | [6 empty] | SG2 | 100%
400198 | CC WasteWater Borders | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Scottish Borders | 904594.34 | -240 | 0 | 195 | -213.56 | 0 | 258.22 | -0.34 | 0 | 904594 | 0 | [6 empty] | SG2 | 100%
400199 | CC WasteWater Clackmannan | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Clackmannanshire | 123262.65 | -47.95 | 0 | -75821.97 | 75869.92 | 0 | 0.35 | 0.35 | 0 | 123263 | 0 | [6 empty] | SG2 | 100%
400200 | CC WasteWater Dumfries and Galloway | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dumfries and Galloway | 1160392.46 | -120 | 0 | 0 | -18.02 | 0 | 137.56 | -0.46 | 0 | 1160392 | 0 | [6 empty] | SG2 | 100%
400201 | CC WasteWater Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 537363.9 | 0 | 23174.69 | -23174.69 | 0 | 0 | 0.1 | 0.1 | 0 | 537364 | 0 | [6 empty] | SG2 | 100%
400202 | CC WasteWater East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 1320355.31 | 0 | -22374.34 | 22618.17 | -363.83 | 0 | 119.69 | -0.31 | 0 | 1320355 | 0 | [6 empty] | SG2 | 100%
400203 | CC WasteWater East Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Dunbartonshire | 294546.85 | 0 | -58430.09 | 58430.09 | 0 | 245058.8 | -245058.65 | 0.15 | 0 | 294547 | 0 | [6 empty] | SG2 | 100%
400204 | CC WasteWater East Lothian | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Lothian | 524744.49 | 0 | -55300.94 | 29371.14 | 25929.8 | 0 | -0.49 | -0.49 | 0 | 524744 | 0 | [6 empty] | SG2 | 100%
400205 | CC WasteWater East Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Renfrewshire | 556219.32 | 0 | -11874.36 | 12242.36 | -368 | 0 | -0.32 | -0.32 | 0 | 556219 | 0 | [6 empty] | SG2 | 100%
400206 | CC WasteWater Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 1833388.1 | 0 | -301097.78 | 350903.21 | -50128.47 | 0 | 322.94 | -0.1 | 0 | 1833388 | 0 | [6 empty] | SG2 | 100%
400207 | CC WasteWater Falkirk | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Falkirk | 1665249.56 | 0 | -103404.58 | 103404.58 | 0 | 0 | 0.44 | 0.44 | 0 | 1665250 | 0 | [6 empty] | SG2 | 100%
400208 | CC WasteWater Fife | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Fife | 2628158.85 | 0 | -36249.94 | 36384.94 | -255 | 0 | 120.15 | 0.15 | 0 | 2628159 | 0 | [6 empty] | SG2 | 100%
400209 | CC WasteWater Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 1708218.33 | -900 | -39275.1 | -138558.92 | 178469.57 | 0 | 264.12 | -0.33 | 0 | 1708218 | 0 | [6 empty] | SG2 | 100%
400210 | CC WasteWater Highland | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Highland | 2526715.38 | 0 | -149013.25 | 121138.75 | 27874.5 | -25145.14 | 25144.76 | -0.38 | 0 | 2526715 | 0 | [6 empty] | SG2 | 100%
400211 | CC WasteWater Inverclyde | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Inverclyde | 480370.59 | 0 | -16910.01 | 16910.01 | 0 | 0 | 0.41 | 0.41 | 0 | 480371 | 0 | [6 empty] | SG2 | 100%
400212 | CC WasteWater Midlothian | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Midlothian | 1866126.33 | 0 | -84908.97 | 103443.41 | -18534.44 | 0 | -0.33 | -0.33 | 0 | 1866126 | 0 | [6 empty] | SG2 | 100%
400213 | CC WasteWater Moray | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Moray | 820705.08 | -8 | 120 | 0 | -112 | 0 | -0.08 | -0.08 | 0 | 820705 | 0 | [6 empty] | SG2 | 100%
400214 | CC WasteWater Na H-Eileanan an Iar | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Na H-Eileanan an Iar | 91019.96 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0.04 | 0 | 91020 | 0 | [6 empty] | SG2 | 100%
400215 | CC WasteWater North Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 1188743.7 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0 | 1188744 | 0 | [6 empty] | SG2 | 100%
400216 | CC WasteWater North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 4389311.79 | -453.34 | -116379.9 | 88297.39 | 28535.85 | -116410.86 | 116411.07 | 0.21 | 0 | 4389312 | 0 | [6 empty] | SG2 | 100%
400217 | CC WasteWater Orkney Islands | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Orkney Islands | 191435.15 | 0 | -3274.15 | 3274.15 | 0 | 0 | -0.15 | -0.15 | 0 | 191435 | 0 | [6 empty] | SG2 | 100%
400218 | CC WasteWater Perth and Kinross | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 1119987.02 | -120 | -49460.52 | 46312.91 | 3267.61 | 0 | -0.02 | -0.02 | 0 | 1119987 | 0 | [6 empty] | SG2 | 100%
400219 | CC WasteWater Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Renfrewshire | 916586.78 | 0 | -68843.18 | 69201.88 | -367.54 | 0 | 9.06 | 0.22 | 0 | 916587 | 0 | [6 empty] | SG2 | 100%
400220 | CC WasteWater Shetland Islands | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Shetland Islands | 105388.02 | 48593.2 | -48593.2 | 0 | 0 | 0 | -0.02 | -0.02 | 0 | 105388 | 0 | [6 empty] | SG2 | 100%
400221 | CC WasteWater South Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Ayrshire | 522741.26 | 60 | 3719.43 | -3599.43 | -188 | 0 | 7.74 | -0.26 | 0 | 522741 | 0 | [6 empty] | SG2 | 100%
400222 | CC WasteWater South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Lanarkshire | 5203100.88 | -48593.2 | -190209.94 | 109802.15 | 128930.27 | 123423.3 | -123352.46 | 0.12 | 0 | 5203101 | 0 | [6 empty] | SG2 | 100%
400223 | CC WasteWater Stirling | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Stirling | 876227.43 | 0 | 0 | -81607.23 | 81607.23 | 0 | -0.43 | -0.43 | 0 | 876227 | 0 | [6 empty] | SG2 | 100%
400224 | CC WasteWater West Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Dunbartonshire | 629488.04 | 970.48 | -15973.4 | 9647.77 | 5355.15 | 2533.02 | -2533.06 | -0.04 | 0 | 629488 | 0 | [6 empty] | SG2 | 100%
400225 | CC WasteWater West Lothian | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Lothian | 1781393.84 | 0 | -241683.55 | 378765.97 | -137322.42 | 0 | 240.16 | 0.16 | 0 | 1781394 | 0 | [6 empty] | SG2 | 100%
400130 | CC Water Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 602219.62 | 109098 | -177069.04 | 58754.47 | 9348.96 | 0 | 0 | 132.39 | 0 | 602352.01 | 0 | [6 empty] | WG2 | 100%
400131 | CC Water Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeenshire | 2579408.49 | 141116.83 | -254073.28 | 109137.58 | 3091.82 | 0 | 726.56 | -0.49 | 0 | 2579408 | 0 | [6 empty] | WG2 | 100%
400132 | CC Water Angus | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Angus | 420625.65 | 39054 | -65339.95 | 31652.7 | -3581.08 | 0 | -1785.32 | 0.35 | 0 | 420626 | 0 | [6 empty] | WG2 | 100%
400134 | CC Water Borders | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Scottish Borders | 468068.58 | 32618.54 | -84900.07 | 53337.35 | -1439.89 | 0 | 384.49 | 0.42 | 0 | 468069 | 0 | [6 empty] | WG2 | 100%
400135 | CC Water Clackmannan | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Clackmannanshire | 137638.4 | 9863 | -19797.51 | -4878.09 | 14812.6 | 0 | -0.4 | -0.4 | 0 | 137638 | 0 | [6 empty] | WG2 | 100%
400136 | CC Water Dumfries and Galloway | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dumfries and Galloway | 386310.47 | 37398.03 | -64344.43 | 25836.49 | 698.6 | 0 | 410.84 | -0.47 | 0 | 386310 | 0 | [6 empty] | WG2 | 100%
400133 | CC Water Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Argyll and Bute-North Argyll | 101248.09 | 9357.56 | -14729.49 | 5919.83 | -547.9 | 509.62 | -509.71 | -0.09 | 0 | 101248 | 0 | [6 empty] | WG2 | 100%
400137 | CC Water Dundee City - 4001370000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 138755.3 | 17014 | -79227.05 | 65140.08 | -2927.03 | 0 | -0.3 | -0.3 | 0 | 138755 | 0 | [6 empty] | WG2 | 100%
400138 | CC Water East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 386826.37 | 31578 | -88779.22 | 57201.22 | 0 | 0 | -0.37 | -0.37 | 0 | 386826 | 0 | [6 empty] | WG2 | 100%
400139 | CC Water East Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Dunbartonshire | 795837.97 | 58903.97 | -26300.03 | -51945.57 | 17552.57 | 0 | 1789.09 | 0.03 | 0 | 795838 | 0 | [6 empty] | WG2 | 100%
400140 | CC Water East Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Lothian | 398452.4 | 44080 | -338418.85 | 294833.47 | -1450.88 | 0 | 955.86 | -0.4 | 0 | 398452 | 0 | [6 empty] | WG2 | 100%
400141 | CC Water East Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Renfrewshire | 270590.47 | 25292 | -97209.86 | 61894.97 | 9959.71 | 0 | 62.71 | -0.47 | 0 | 270590 | 0 | [6 empty] | WG2 | 100%
400142 | CC Water Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 1157931.44 | 128814 | -333612.93 | 181144.03 | 25698.17 | 0 | -2043.71 | -0.44 | 0 | 1157931 | 0 | [6 empty] | WG2 | 100%
400143 | CC Water Falkirk | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Falkirk | 941192.69 | 57398 | -2447.5 | -58773.24 | 3614.76 | 0 | 208.29 | 0.31 | 0 | 941193 | 0 | [6 empty] | WG2 | 100%
400144 | CC Water Fife | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Fife | 1005678.27 | 81652.08 | -125041.41 | 44964.39 | -3609.67 | 0 | 2034.34 | -0.27 | 0 | 1005678 | 0 | [6 empty] | WG2 | 100%
400145 | CC Water Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 1554091.97 | 127372 | -244326.86 | 116677.62 | 145.5 | 0 | 131.77 | 0.03 | 0 | 1554092 | 0 | [6 empty] | WG2 | 100%
400147 | CC Water Inverclyde | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Inverclyde | 170845.8 | 10052 | -44621.8 | 34569.8 | 0 | 0 | 0.2 | 0.2 | 0 | 170846 | 0 | [6 empty] | WG2 | 100%
400146 | CC Water Midlothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Highland | 1641396.02 | 91700.49 | -109838.86 | -3486.95 | 20930.56 | 0 | 694.74 | -0.02 | 0 | 1641396 | 0 | [6 empty] | WG2 | 100%
400148 | CC Water Midlothian - 4001480000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Midlothian | 6064127.31 | 85130 | -161879.55 | 95364.14 | -19119.9 | 0 | 505 | -0.31 | 0 | 6064127 | 0 | [6 empty] | WG2 | 100%
400150 | CC Water Na H-Eileanan an Iar | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Na H-Eileanan an Iar | 48969.15 | 1577.57 | -1440 | -104 | -33.57 | 0 | -0.15 | -0.15 | 0 | 48969 | 0 | [6 empty] | WG2 | 100%
400149 | CC Water North Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Moray | 808713.57 | 32897.99 | -61268.74 | 36311.03 | -7288.66 | 0 | -651.19 | 0.43 | 0 | 808714 | 0 | [6 empty] | WG2 | 100%
400151 | CC Water North Ayrshire - 4001510000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Ayrshire | 509894.72 | 25990 | -43203.66 | 16590.28 | 524.4 | 0 | 99.26 | 0.28 | 0 | 509895 | 0 | [6 empty] | WG2 | 100%
400152 | CC Water North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 1108414.75 | 97132 | -168925.96 | 71422.19 | 114.98 | 0 | 257.04 | 0.25 | 0 | 1108415 | 0 | [6 empty] | WG2 | 100%
400153 | CC Water Orkney Islands | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Orkney Islands | 88474.77 | 11156.85 | -16465.21 | 5961.51 | -741.6 | 0 | 88.68 | 0.23 | 0 | 88475 | 0 | [6 empty] | WG2 | 100%
400154 | CC Water Perth and Kinross | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 354294.87 | 29642.4 | -97366.67 | 67742.51 | -509.86 | -1114 | 1605.75 | 0.13 | 0 | 354295 | 0 | [6 empty] | WG2 | 100%
400155 | CC Water Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Renfrewshire | 462500.09 | 59129.46 | -83199.14 | 22319.73 | 1688.33 | 0 | 61.53 | -0.09 | 0 | 462500 | 0 | [6 empty] | WG2 | 100%
400156 | CC Water Shetland Islands | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Shetland Islands | 83911.64 | 6369.59 | -25988.92 | 19933.4 | -314.07 | 0 | 0.36 | 0.36 | 0 | 83912 | 0 | [6 empty] | WG2 | 100%
400157 | CC Water South Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Ayrshire | 208279.15 | 18900 | -71314.56 | 53122.83 | -1319.15 | 0 | 610.73 | -0.15 | 0 | 208279 | 0 | [6 empty] | WG2 | 100%
400158 | CC Water South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Lanarkshire | 1139178.19 | 57800.51 | -106378.26 | 3159.79 | 45328.47 | -253490.26 | 253579.56 | -0.19 | 0 | 1139178 | 0 | [6 empty] | WG2 | 100%
400159 | CC Water Stirling | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Clackmannanshire | 216448.68 | 20149.14 | -51784.25 | 22568.32 | 8876.15 | 0 | 190.96 | 0.32 | 0 | 216449 | 0 | [6 empty] | WG2 | 100%
400160 | CC Water West Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Dunbartonshire | 290437.66 | 22886 | -17529.43 | -38839.6 | 33483.03 | 0 | 0.34 | 0.34 | 0 | 290438 | 0 | [6 empty] | WG2 | 100%
400161 | CC Water West Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Lothian | 951240.54 | 93318 | -165404.13 | 80364.69 | -8157.91 | 0 | -120.65 | -2.1885e-12 | 0 | 951240.54 | 0 | [6 empty] | WG2 | 100%
502191 | CCTV Phase 2A Ayrshire Inverclyde and Renfrewshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2016-09-20 | 2018-01-17 | 2018-02-26 | 2020-01-28 | 2020-03-02 | Scottish Water Wide | 0 | 0 | 3427.06 | 191062.89 | 416163.05 | -2494 | 1265.02 | 609424.02 | 575.95 | 609999.97 | 0 | [6 empty] | CM_WWI | 100%
502404 | CCTV Phase 2B Dalmarnock North & South Lanarkshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-04-28 | 2018-06-21 | 2018-08-31 | 2020-04-01 | 2020-05-13 | South Lanarkshire | 0 | 0 | 1807.55 | 12425.55 | 732232.9 | -4976 | 0 | 741490 | 1728 | 743218 | 0 | [6 empty] | CM_WWI | 100%
502405 | CCTV Phase 2C West Highland Aberdeenshire & Moray | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2017-04-28 | 2018-03-27 | 2018-05-31 | 2020-01-30 | 2020-03-01 | Aberdeenshire | 0 | 0 | 1674.42 | 88929.58 | 565647 | -251 | 0 | 656000 | 0 | 656000 | 0 | [6 empty] | CM_WWI | 100%
502641 | CCTV Phase 3A Falkirk & West Lothian | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-01-30 | 2018-12-05 | 2019-05-13 | 2020-05-29 | 2020-05-29 | West Lothian | 0 | 0 | 6630.7 | 10429.17 | 139380.13 | 365823 | 0 | 522263 | 2400 | 524663 | 0 | [6 empty] | CM_WWI | 100%
502642 | CCTV Phase 3B West Highland & Argyle & Bute | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-01-30 | 2018-10-26 | 2019-01-31 | 2020-05-26 | 2020-05-26 | Highland | 0 | 0 | 4420.47 | 11454.23 | 159542.3 | 262272 | 0 | 437689 | 2400 | 440089 | 0 | [6 empty] | CM_WWI | 100%
502643 | CCTV Phase 3C North Highland | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-03-29 | 2019-03-05 | 2019-07-08 | 2020-05-11 | 2020-05-12 | Highland | 0 | 0 | 4420.47 | 6005.08 | 63639.2 | 277747.26 | -0.01 | 351812 | 1900 | 353712 | 0 | [6 empty] | CM_WWI | 100%
503046 | CCTV Phase 4A Stirlingshire and Clackmannanshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-10-26 | 2019-08-19 | 2020-01-13 | 2020-10-26 | 2021-02-09 | Stirling | 0 | 0 | 0 | 5261.77 | 4207.2 | 207164.41 | 146978.42 | 363611.8 | 5478.2 | 369090 | 0 | [6 empty] | CM_WWI | 100%
503201 | CCTV Phase 4B (Dumfries Borders East & Mid Lothian) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-07-27 | 2019-07-22 | 2019-10-14 | 2020-07-03 | 2020-10-02 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 48847.9 | 218521.1 | 88804 | 356173 | 12216 | 368389 | 0 | [6 empty] | CM_WWI | 100%
503411 | CCTV Phase 4C Fife Perth & Kinross Dundee and Angus | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-04-17 | 2021-03-22 | 2021-06-24 | 2022-02-16 | 2022-05-19 | Fife | 0 | 0 | 0 | 0 | 15023.15 | 13733.91 | 242737.59 | 271494.65 | 556102.37 | 827597.02 | 0 | [6 empty] | SR21_WW | 100%
403614 | CCTV Sewer Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-12-19 | 2014-04-30 | 2014-06-09 | 2016-03-30 | 2018-02-08 | Scottish Water Wide | 682168 | 359296.72 | 25137.03 | 0 | 0 | 0 | 1398.25 | 385832 | 0 | 1068000 | 0 | [6 empty] | CM_WWI | 100%
402858 | Central Bar Market Street St. Andrews | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2013-09-18 | 2013-12-19 | 2014-06-13 | 2014-06-13 | Fife | 2279102 | -7665 | -882.94 | 0 | 0 | 0 | 0 | -8547.94 | 0 | 2270554.06 | 538.2 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403344 | Central Borders Trunk Main Capacity | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-25 | 2014-09-10 | 2014-10-06 | 2015-07-17 |  | Scottish Borders | 65921 | 2170.65 | 0 | 0 | 0 | 0 | 0 | 2170.65 | 0 | 68091.65 | 0 | [6 empty] | CM_WSI | 100%
502585 | Ceres Burn Crossing Ceres | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | Fife | 0 | 0 | 2930.23 | 1575.13 | 0 | 0 | -641.36 | 3864 | 0 | 3864 | 0 | [6 empty] | CM_WWI | 100%
502394 | Chapleton Development Infrastructure Funding | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2017-02-21 | 2017-02-21 | 2017-03-01 | 2020-10-12 | 2020-10-12 | Aberdeenshire | 0 | 0 | 911064 | 0 | -425507.3 | 0.01 | 0 | 485556.71 | 0 | 485556.71 | 0 | [6 empty] | SG5 | 100%
402076 | Charging At Vacant Properties | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-06-16 | 2011-06-16 | 2011-07-05 | 2015-03-31 |  | Scottish Water Wide | 11231.71 | -457.76 | 0 | 0 | 0 | 0 | 0 | -457.76 | 0 | 10773.95 | 0 | [6 empty] | CS20 | 100%
401562 | Charleston Low Pressure Enhancement WSZ000362 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-11-02 | 2011-12-15 | 2012-03-12 | 2014-03-17 | 2013-09-30 | Fife | 74079.7 | 238.67 | 217.89 | 0 | 0 | 0 | 2.74 | 459.3 | 0 | 74539 | 94 | [6 empty] | CS1 | 100%
502084 | Charlotte St SPS rising main - Relay Rising Main | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-08 | 2027-11-19 | 2028-02-02 | 2028-09-01 | 2028-12-04 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 738.16 | 738.16 | 490248.81 | 490986.97 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
502847 | Chemical Dosing Programme - Phase 1 - Braemar WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-08-24 | 2021-07-19 | 2021-11-18 | 2022-08-30 | 2022-11-29 | Aberdeenshire | 0 | 0 | 0 | 0 | 6451.26 | 6899.21 | 2819.52 | 16169.99 | 33361.24 | 49531.23 | 0 | [6 empty] | CM_WSNI | 100%
502848 | Chemical Dosing Programme - Phase 1 - Castle Moffat WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-21 | 2021-07-19 | 2021-11-29 | 2022-08-22 | 2022-11-22 | East Lothian | 0 | 0 | 0 | 0 | 5548 | 761.49 | 15694.6 | 22004.09 | 616005.86 | 638009.95 | 0 | [6 empty] | CM_WSNI | 100%
502849 | Chemical Dosing Programme - Phase 1 - Daer WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-13 | 2021-07-19 | 2021-11-22 | 2022-05-30 | 2022-05-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 6980.42 | -2806.03 | 52694.75 | 56869.14 | 140130.84 | 196999.98 | 0 | [6 empty] | CM_WSNI | 100%
502850 | Chemical Dosing Programme - Phase 1 - East sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-08-28 | 2021-04-12 | 2021-08-12 | 2022-05-23 | 2022-08-23 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 13698 | 12183.85 | 149201.76 | 175083.61 | 467158.93 | 642242.54 | 0 | [6 empty] | CM_M&G | 33.98% | CM_WSNI | 66.02%
502851 | Chemical Dosing Programme - Phase 1 - Forehill WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-02-15 | 2021-05-17 | 2022-03-21 | 2022-06-14 | Aberdeenshire | 0 | 0 | 0 | 5902 | 15839.97 | 15623.26 | 16092.3 | 53457.53 | 60159.09 | 113616.62 | 0 | [6 empty] | CM_WSNI | 100%
502852 | Chemical Dosing Programme - Phase 1 - Glenconvinth WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2020-11-09 | 2021-02-22 | 2021-11-01 | 2022-02-01 | Highland | 0 | 0 | 0 | 5994.49 | 9735.19 | 2178.01 | 241070.54 | 258978.23 | 454376.01 | 713354.24 | 0 | [6 empty] | CM_WSNI | 100%
502853 | Chemical Dosing Programme - Phase 1 - Glendevon WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-04-12 | 2021-04-16 | 2022-04-15 | 2022-07-25 | Fife | 0 | 0 | 0 | 13267.6 | 107717.07 | 256409.83 | 366303.95 | 743698.45 | 559550.43 | 1303248.88 | 0 | [6 empty] | CM_WSNI | 100%
502854 | Chemical Dosing Programme - Phase 1 - Glenfarg WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-08-24 | 2021-04-12 | 2021-08-12 | 2022-05-24 | 2022-08-24 | Fife | 0 | 0 | 0 | 0 | 6591.66 | 8640.56 | 22131.31 | 37363.53 | 76462.7 | 113826.23 | 0 | [6 empty] | CM_WSNI | 100%
502855 | Chemical Dosing Programme - Phase 1 - Milnathort WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2018-08-20 | 2021-04-12 | 2021-08-12 | 2022-02-24 | 2022-05-26 | Perth and Kinross | 0 | 0 | 0 | 0 | 6952.29 | 7189.8 | 22142 | 36284.09 | 106030.04 | 142314.13 | 0 | [6 empty] | CM_M&G | 100%
502858 | Chemical Dosing Programme - Phase 1 - North sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-11-23 | 2020-09-22 | 2020-07-08 |  | 2021-10-12 | All North Unitary Authorities | 0 | 0 | 0 | 13308.69 | 5197.11 | 3975.51 | 513200.06 | 535681.37 | 377894.05 | 913575.42 | 0 |  |  |  |  | 20119 |  | CM_M&G | 21.7% | CM_WSNI | 78.3%
502861 | Chemical Dosing Programme - Phase 1 - Rawburn WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-20 | 2021-07-19 | 2021-11-22 | 2022-09-05 | 2022-09-05 | Scottish Borders | 0 | 0 | 0 | 0 | 6005.89 | -1505.29 | 36499.4 | 41000 | 267000.09 | 308000.09 | 0 | [6 empty] | CM_WSNI | 100%
502860 | Chemical Dosing Programme - Phase 1 - Shotts STW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2018-11-20 | 2020-11-16 | 2021-04-05 | 2022-02-28 | 2022-02-28 | North Lanarkshire | 0 | 0 | 0 | 0 | 8243.17 | 23343.34 | 117473.17 | 149059.68 | 271940.33 | 421000.01 | 0 | [6 empty] | CM_M&G | 100%
502859 | Chemical Dosing Programme - Phase 1 - South sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-13 | 2021-07-19 | 2021-11-22 | 2022-05-27 | 2022-05-27 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 5369.59 | -3353.15 | 12983.55 | 14999.99 | 134499.97 | 149499.96 | 0 |  |  |  |  | 100456 |  | CM_M&G | 8.629% | CM_WSNI | 91.37%
502857 | Chemical Dosing Programme - Phase 1 - Turriff WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-01-18 | 2021-04-19 | 2022-02-21 | 2022-05-17 | Aberdeenshire | 0 | 0 | 0 | 9408.24 | 52011.24 | 3855.79 | 271840.56 | 337115.83 | 395430.85 | 732546.68 | 0 | [6 empty] | CM_WSNI | 100%
502856 | Chemical Dosing Programme - Phase 1 - West sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2017-11-15 | 2020-03-31 | 2020-07-13 | 2021-02-26 | 2021-05-31 | All West Unitary Authorities | 0 | 0 | 0 | 80449.88 | -9315.36 | 79816.05 | 33282.81 | 184233.38 | 500729.86 | 684963.24 | 0 | [6 empty] | CM_M&G | 25% | CM_WSNI | 75%
402671 | Chemical Dosing System HS Review | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-05-16 | 2013-07-31 | 2013-07-31 | 2014-09-25 |  | Scottish Water Wide | 1896620 | 4181.91 | -534.6 | 0 | 0 | 0 | 0 | 3647.31 | 0 | 1900267.31 | 0 | [6 empty] | CM_M&G | 100%
503242 | Chemical Storage tanks Investigations- Pan Scotland | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2018-09-13 | 2020-02-28 | 2020-08-11 | 2021-08-11 | 2021-08-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 351102.33 | 549316.7 | 666353.24 | 1566772.27 | 433227.74 | 2000000.01 | 0 | [6 empty] | CM_M&G | 100%
504448 | Chemical Tank Remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 |  | 2020-08-31 | 2020-09-18 | 2020-12-29 | 2021-01-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 16514.31 | 0 | 16514.31 | 0 | 16514.31 | 0 | [6 empty] | CM_WSNI | 100%
503227 | Chirnside WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-02 | 2023-01-13 | 2023-05-10 | 2024-05-06 | 2024-08-06 | Scottish Borders | 0 | 0 | 0 | 0 | 85886 | 32213.47 | 22705.52 | 140804.99 | 1435265.05 | 1576070.04 | 136478.56 | [6 empty] | SG1 | 100%
402849 | Church Street Lossiemouth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-04 | 2014-11-28 | 2014-12-01 | 2015-03-27 | 2015-03-27 | Moray | 875097 | 12381.68 | 178.02 | 0 | 0 | 0 | 0 | 12559.7 | 0 | 887656.7 | 204193.13 | [6 empty] | CS11A | 100%
400088 | CID Overheads for SR10-15 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2009-12-18 | 2009-12-18 | 2011-10-06 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -2985513.38 | -117957.33 | 0 | 60.28 | 0 | 32.58 | 0 | -117864.47 | 0 | -3103377.85 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
401028 | CID QS IIIA Land Cost run-offs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2010-04-21 | 2012-02-28 | 2012-03-01 | 2015-11-03 |  | Scottish Water Wide | 865439 | 2184.12 | 0 | 262.72 | 0 | 0 | -262.72 | 2184.12 | 0 | 867623.12 | 0 | [6 empty] | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
502299 | CIP - Funding Provision for Byelaws Compliance Officers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-09-09 | 2016-09-09 | 2016-11-02 | 2017-09-19 | 2017-09-19 | Scottish Water Wide | 0 | 0 | 164559.45 | 117899.73 | 0 | 0 | 0 | 282459.18 | 0 | 282459.18 | 0 | [6 empty] | CM_WSI | 100%
502773 | CIP - ICC Network Access Resources | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-09-20 | 2017-09-20 | 2017-09-29 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 78446 | 222045.67 | 159489.46 | 229852.29 | 689833.42 | 10166.58 | 700000 | 0 | [6 empty] | CM_WSI | 100%
502223 | CIP - Valve Inspection & Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS3 | 2016-07-21 | 2016-07-21 | 2016-11-02 | 2021-04-22 | 2021-04-22 | Scottish Water Wide | 0 | 0 | 789224.56 | 1173962.45 | 1215484.74 | 729541.99 | 548071.38 | 4456285.12 | 44020.92 | 4500306.04 | 0 | [6 empty] | CM_WSI | 33.33% | CM_M&G | 66.67%
400806 | CITY RAIN NET - IMPROVED RAINFALL MONITORING IN URBAN AREAS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS6 | 2010-05-05 | 2010-05-05 | 2010-05-05 | 2020-01-28 |  | Scottish Water Wide | 166238 | 786.98 | 0 | 0 | 0 | 0 | 0 | 786.98 | 0 | 167024.98 | 0 | [6 empty] | CM_WWI | 100%
502417 | Clachan Pipe Bridges | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-06-29 | 2018-10-25 | 2019-07-03 | 2019-12-16 | 2020-04-01 | Argyll and Bute-North Argyll | 0 | 0 | 4202.33 | 12934.93 | 38586.49 | 65674.21 | 764.89 | 122162.85 | 161.23 | 122324.08 | 0 | [6 empty] | CM_WWI | 100%
500925 | Clackmannanshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | Clackmannanshire | 0 | 6000 | 793.41 | 0 | 0 | 0 | 0 | 6793.41 | 0 | 6793.41 | 120964.87 | [6 empty] | CS15A | 100%
502932 | Cladich WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-07-28 | 2033-11-25 | 2034-11-21 | 2035-02-21 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21179.77 | 1106.24 | -19575.67 | 0 | 2710.34 | 0 | 2710.34 | 136478.56 | [6 empty] | WG1 | 100%
402863 | Claire Street Newmains Wishaw | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-08-15 | 2014-09-30 | 2014-11-03 | 2016-08-12 | 2016-08-12 | North Lanarkshire | 324755 | -12655 | 5000 | 0 | 40102.86 | 0 | 0.14 | 32448 | 0 | 357203 | 204193.13 | [6 empty] | CS11 | 100%
402854 | Claredon Place Dunblane | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2012-08-15 | 2020-03-05 | 2020-06-03 | 2020-06-10 | 2020-07-07 | Stirling | 39648.83 | 2030.17 | 43927.91 | 30393.09 | 49747.29 | 16672.78 | -3978.14 | 138793.1 | 0 | 178441.93 | 196097.17 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502357 | Clatto & Lintrathen Hydro Generator Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-11-27 | 2016-11-27 | 2017-08-01 | 2018-06-26 | 2018-06-26 | Dundee City | 0 | 0 | 129000 | 226612.19 | -49650 | 0 | 0 | 305962.19 | 0 | 305962.19 | 0 | [6 empty] | CM_WSNI | 100%
501616 | Clatto 40inch & 48inch Raw Water Mains - Air & Scour Valves | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-12-09 | 2028-09-05 | 2028-12-01 | 2029-04-16 | 2029-07-17 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142050.03 | 142050.03 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
501711 | Clatto 40inch & 48inch Raw Water Mains - Pipe Bridges | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-03 | 2027-11-29 | 2028-03-29 | 2028-08-11 | 2028-11-09 | East Lothian | 0 | 0 | 10169.61 | 24820.81 | 14989.58 | 0 | 0 | 49980 | 1845794.03 | 1895774.03 | 0 | [6 empty] | CM_WSI | 100%
500062 | Clatto East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-14 | 2018-12-19 | Dundee City | 0 | 405493 | 1254291 | 114503 | 13965.24 | 47560.31 | -386.66 | 1835425.89 | 0 | 1835425.89 | 365786.94 | [6 empty] | DW5 | 100%
500802 | Clatto East RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2015-11-23 | 2016-09-30 | 2017-01-11 | 2019-01-31 | 2019-06-30 | Dundee City | 0 | 29821 | 176000.51 | 140878.08 | 204431.31 | 7764.94 | 0.01 | 558895.85 | 0 | 558895.85 | 541547.32 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 89.61
500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS6 | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2019-03-28 | 2019-09-02 | Dundee City | 332.03 | 306152.97 | 831400 | 2530470 | 1721070.28 | 45985.96 | 0 | 5435079.21 | 0 | 5435411.24 | 2932407.97 | [6 empty] | CM_WSI | 16.77% | DW5 | 83.23%
500803 | Clatto West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-11-23 | 2017-12-20 | 2018-03-26 | 2019-03-31 | 2020-02-29 | Dundee City | 0 | 55736 | 80652.12 | 178133.13 | 223430.24 | 50360.09 | -884.63 | 587426.95 | 0 | 587426.95 | 771983.06 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 116.11
500067 | Clatto WOA Balbeuchley WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-03-11 | 2017-05-24 | 2017-08-10 | 2020-12-31 | 2021-01-05 | Perth and Kinross | 0 | 73000 | 65144 | 878108 | 585257.9 | 572954.89 | 219045.76 | 2393510.55 | 0 | 2393510.55 | 0 | [6 empty] | CM_WSI | 100%
501202 | Clatto WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2016-02-11 | 2027-07-07 | 2027-07-08 | 2028-06-30 | 2028-08-11 | Dundee City | 0 | 14109 | 159419.88 | -1838.88 | -4586.03 | 0 | 0 | 167103.97 | 0 | 167103.97 | 0 | [6 empty] | CM_WSNI | 100%
502270 | Clatto WTW CM - Water champ and RGF 6 & 10 refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-06-15 | 2028-09-04 | 2028-12-29 | 2029-08-10 | 2029-11-12 | Dundee City | 0 | 0 | 10190.5 | 454.79 | 5575.53 | 0 | -0.01 | 16220.81 | 234455.2 | 250676.01 | 0 | [6 empty] | CM_WSNI | 100%
45620 | Clatto WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-04-01 | 2013-05-01 | 2013-12-30 | Dundee City | 604974.56 | -609.16 | 0 | 0 | 0 | 0 | 0 | -609.16 | 0 | 604365.4 | 1236 | [6 empty] | DW1A | 100%
404070 | Clay Crescent EPI | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-12-09 | 2014-12-09 | 2014-12-09 | 2017-07-03 |  | North Lanarkshire | 579203.01 | 25945.99 | 0 | -25945.99 | 0 | 0 | 0 | 0 | 0 | 579203.01 | 0 | [6 empty] | CM_WWI | 100%
503961 | Clay Crescent sewer cleaning | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-04 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 44102.56 | 39299.73 | 83402.29 | 0 | 83402.29 | 52345447.02 | [6 empty] | WWI | 100%
400721 | Cleghorn ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2014-05-22 | 2014-06-02 | 2015-03-19 | 2015-03-19 | South Lanarkshire | 338093.74 | 31002.26 | 2676.95 | 5077.65 | 0 | 0 | 0 | 38756.86 | 0 | 376850.6 | 0 | [6 empty] | SG1 | 100%
502928 | Clerkland Bridge - Pipe replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-11-13 | 2018-09-05 | 2019-06-24 | 2020-02-25 | 2020-04-15 | East Ayrshire | 0 | 0 | 0 | 6921.17 | 49583.09 | 536088.55 | 510.31 | 593103.12 | 1896.87 | 594999.99 | 0 | [6 empty] | CM_WSI | 100%
502871 | Cliasmol WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2027-04-30 | 2033-11-10 | 2034-03-03 | 2035-02-23 | 2035-05-28 | Na H-Eileanan an Iar | 0 | 0 | 0 | 21238 | 1111.63 | -19082.67 | 0.01 | 3266.97 | 0 | 3266.97 | 136478.56 | [6 empty] | WG1 | 100%
500097 | Climate Change Impacts - Wastewater System Vulnerability | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWMD | Climate Change | MS7 | 2015-03-31 | 2016-11-29 | 2016-11-30 | 2017-12-31 | 2018-02-28 | Scottish Water Wide | 0 | 6176 | 37820.8 | 113010.85 | -133871.42 | 133467.7 | 0.03 | 156603.96 | 0 | 156603.96 | 229645.78 | [6 empty] | CC4S | 100% | bar: Regulatory Outputs OMG-45
500099 | Climate Change Impacts - Water Treatment Vulnerability | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWMD | Climate Change | MS7 | 2015-03-31 | 2016-11-29 | 2016-11-30 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 1498 | 27962.87 | 30084.31 | 1345.99 | 0 | -0.03 | 60891.14 | 0 | 60891.14 | 54751.77 | [6 empty] | CC4W | 100% | bar: Regulatory Outputs OMG-45
500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS3 | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-08 | 2021-03-26 | Scottish Water Wide | 0 | 1798 | 150 | 28984.72 | 13160.62 | 164437.37 | 167651.58 | 376182.29 | 7424.25 | 383606.54 | 482736.04 | [6 empty] | CC4W | 100%
500098 | Climate Change Risk Assessments | Q&S4 | Climate Change | Climate Change |  |  | General |  | SWD | Climate Change | MS7 | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-14 | 2016-03-30 | Scottish Water Wide | 0 | 20843.73 | 10622.38 | 0 | 0 | 0 | 0 | 31466.11 | 0 | 31466.11 | 68045.58 | [6 empty] | CC4S | 50% | CC4W | 50%
500093 | Climate Change Trend Data Storage System | Q&S4 | Climate Change | Climate Change |  |  | General |  | SWD | Climate Change | MS7 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | Scottish Water Wide | 0 | 4186.05 | 71.18 | 0 | 0 | 0 | 0 | 4257.23 | 0 | 4257.23 | 81600.61 | [6 empty] | CC4S | 50% | CC4W | 50%
500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS7 | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-28 | 2019-08-29 | Scottish Water Wide | 0 | 10465.12 | 871.87 | 30086.3 | 97914.71 | 36594.86 | 0.03 | 175932.89 | 0 | 175932.89 | 931439.43 | [6 empty] | CC4S | 100%
500091 | Climate Change Trends Monitoring B Corrosion and Sulphide | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS7 | 2015-09-30 | 2015-12-21 | 2015-12-21 | 2018-11-30 | 2019-05-14 | Scottish Water Wide | 0 | 17558.09 | 11550 | 667.91 | 4724 | -11441.73 | -97.74 | 22960.53 | 0 | 22960.53 | 166180.02 | [6 empty] | CC4S | 100%
500094 | Climate Change Trends Monitoring C Groundwater | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-24 | 2016-05-20 | Scottish Water Wide | 0 | 418.6 | 0 | 0 | 0 | 0 | 0 | 418.6 | 0 | 418.6 | 0 | [6 empty] | CC4W | 100%
500719 | Clinterty WWTW 1960-1970 NJ832110 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-06-30 | 2017-04-06 | 2017-05-02 | 2018-07-11 | 2018-07-11 | Aberdeen City | 0 | 69870 | 182475.89 | 665982.11 | 16672 | 0 | 0 | 935000 | 0 | 935000 | 0 | [6 empty] | CM_WWI | 5.5% | CM_WWNI | 94.5%
402631 | Clochandighter to Stranog TM Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-04-16 | 2012-08-01 | 2012-09-03 | 2013-08-07 |  | Aberdeen City | 396613 | -1837.82 | 0 | 0 | 0 | 0 | 0 | -1837.82 | 0 | 394775.18 | 0 | [6 empty] | CM_WSI | 100%
501304 | Cloud Capacity | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-10 | 2016-06-02 | 2016-06-02 | 2017-11-15 | 2017-11-15 | Scottish Water Wide | 0 | 69734 | 208440.13 | 104835.58 | 0 | 0 | 0 | 383009.71 | 0 | 383009.71 | 0 | [6 empty] | CM_M&G | 100%
401383 | Clovenfords Smithy Row - Sewer Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-24 | 2012-07-16 | 2012-10-29 | 2013-06-24 | 2013-06-24 | Highland | 232257 | -2072.3 | 0 | 0 | 0 | 0 | 0 | -2072.3 | 0 | 230184.7 | 1229.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
500885 | Clunas RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 2518.66 | 181.34 | 11378 | -11073.87 | 0 | 0.01 | 3004.14 | 0 | 3004.14 | 205473.42 | [6 empty] | DW5FS | 100%
45791 | Cluny SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-06-28 | 2011-11-14 | 2012-09-06 | 2012-11-26 | Fife | 495961.95 | 312.49 | 0 | 0 | 0 | 0 | 0 | 312.49 | 0 | 496274.44 | 0 | [6 empty] | WQ01B | 14.53% | WQ01C | 85.47%
400122 | Clyde Cluster 1 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-26 | 2012-10-29 | 2015-03-25 |  | Glasgow City | 4403337 | -48209 | -73606.87 | 121.32 | 0 | 0 | 0 | -121694.55 | 0 | 4281642.45 | 0 | [6 empty] | CM_WSI | 100%
400123 | Clyde Cluster 2 Capital maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-26 | 2012-10-29 | 2014-03-24 |  | Glasgow City | 1171462.37 | 710.63 | -1472.26 | 0 | 0 | 0 | 0 | -761.63 | 0 | 1170700.74 | 0 | [6 empty] | CM_WSI | 100%
501717 | Clydeside Expressway - Sewer Investigations | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-27 | 2017-01-27 | 2017-01-27 | 2016-12-06 | 2017-01-27 | Glasgow City | 0 | 0 | 1674.42 | 0 | 0 | 0 | 0 | 1674.42 | 0 | 1674.42 | 0 | [6 empty] | CM_WWI | 100%
500718 | CM Asbestos Management Yrs 1 & 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-06-01 | 2021-06-01 | Scottish Water Wide | 0 | 149946.61 | 215079.39 | 265717.1 | 410769.93 | 495552.14 | 148654.74 | 1685719.91 | 0 | 1685719.91 | 0 | [6 empty] | CM_M&G | 100%
401390 | CM DI Meter Verification Programme SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-09-20 | 2010-10-07 | 2011-05-02 | 2015-09-04 |  | Scottish Water Wide | 301994.4 | 32301.34 | 0 | 0 | 0 | 0 | 0 | 32301.34 | 0 | 334295.74 | 0 | [6 empty] | CM_WSI | 100%
505349 | CM North Loch Glass Spillway Survey | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-03-11 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Highland | 0 | 0 | 0 | 0 | 0 | 1635.51 | 23364.49 | 25000 | 0 | 25000 | 821666.8 | [6 empty] | CS22 | 100%
402705 | CM Start Early Wastewater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-05-16 | 2015-05-07 | 2015-05-07 | 2015-04-09 |  | Scottish Water Wide | 190000 | 705.72 | 0 | 0 | 0 | 0 | 0 | 705.72 | 0 | 190705.72 | 0 | [6 empty] | CM_WWNI | 100%
402703 | CM Start Early Water | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-05-16 | 2013-10-11 | 2013-10-14 | 2017-03-17 |  | Scottish Water Wide | 1650000 | 50000 | -10890.65 | 0 | 0 | 0 | 0 | 39109.35 | 0 | 1689109.35 | 0 | [6 empty] | CM_WWNI | 100%
503985 | CM Woodhill Rd DMA - St Mungos Street Bishopbriggs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-01-05 |  | 2020-08-06 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 98614.05 | 143229.66 | 241843.71 | 0 | 241843.71 | 0 | [6 empty] | WSNI | 100%
501632 | CMA Market Releases | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2021-03-15 |  | Scottish Water Wide | 0 | 0 | 201299.1 | 177872 | 560710 | -110858.63 | 293041.64 | 1122064.11 | 0 | 1122064.11 | 0 | [6 empty] | CM_M&G | 100%
402071 | CMA System changes - March Release | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-03-29 | 2011-03-29 | 2011-04-01 | 2016-08-08 |  | Scottish Water Wide | 983867 | 13080.11 | 0 | 0 | 0 | 0 | 0 | 13080.11 | 0 | 996947.11 | 35117 | [6 empty] | CS20 | 100%
403350 | CMAP Customer Service Delivery Identified Sewer Rehabilitation Phase 4 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-04-29 | 2013-04-29 | 2013-05-22 | 2014-11-14 |  | Scottish Water Wide | 822926.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822926.35 | 0 | [6 empty] | CM_WWI | 100%
403351 | CMAP Customer Service Delivery Identified Sewer Rehabilitation Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-03-18 | 2013-07-01 | 2015-06-25 |  | Scottish Water Wide | 1630000 | -31971.24 | 0 | 0 | 0 | 0 | 31971.24 | 0 | 0 | 1630000 | 0 | [6 empty] | CM_WWI | 100%
403904 | CMC Aviemore WwTW Package Centrifuge Dewatering Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-09-15 | 2015-01-19 | 2016-09-19 | 2017-05-29 |  | Highland | 69877 | 348919 | 160228 | 24653.64 | 15056.15 | 0 | 0.01 | 548856.8 | 0 | 618733.8 | 0 | [6 empty] | CM_WWNI | 100%
403748 | CMC DI Metering Pilot | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-24 | 2014-02-24 | 2014-04-09 | 2016-03-10 |  | Scottish Water Wide | 327673.97 | 34007.2 | 0 | 0 | 0 | 0 | 0 | 34007.2 | 0 | 361681.17 | 0 | [6 empty] | CM_WSI | 100%
403615 | CMC Energy Improvement Prog Accelerated Energy Consumption Reduction Prog (W & WW) | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWMD | Non OMG180 | MS7 | 2013-12-18 | 2013-12-18 | 2014-02-03 | 2016-12-14 |  | Scottish Water Wide | 3424237 | -31727.02 | -44475 | 302.29 | 0 | 0 | 0 | -75899.73 | 0 | 3348337.27 | 2687972 | [6 empty] | ESP | 100%
402441 | CMC Health and Safety - Lifting Chain Compliance Programme | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-11-10 | 2012-10-31 | 2012-11-19 | 2017-05-29 |  | Scottish Water Wide | 1238293 | 13139.3 | 104.91 | 44.59 | 0 | 0 | 0 | 13288.8 | 0 | 1251581.8 | 0 | [6 empty] | CM_M&G | 100%
403375 | CMC HL Non Complex Projects 2013-15 South Wastewater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-28 | 2019-02-14 |  | All South Unitary Authorities | 3653315 | 431465 | -30591.53 | 27723.83 | 11685.39 | -943.79 | 0.02 | 439338.92 | 0 | 4092653.92 | 0 | [6 empty] | CM_WWI | 100%
403378 | CMC HL Non Complex Projects 2013-15 West Wastewater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-22 | 2017-03-06 |  | All West Unitary Authorities | 2988090 | 737457 | -56711.58 | -3822.02 | 63.87 | 0 | 0 | 676987.27 | 0 | 3665077.27 | 0 | [6 empty] | CM_WWI | 100%
403371 | CMC HL Non Complex Projects 2014-15 North Wastewater | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2014-05-15 | 2014-05-16 |  | All North Unitary Authorities | 9820.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9820.49 | 0 | [6 empty] | CM_WWI | 100%
404021 | CMC Ness Area Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-11-26 | 2014-11-26 | 2015-01-12 | 2015-07-30 |  | All North Unitary Authorities | 99599 | 197893.81 | 0 | 0 | 0 | 0 | 0 | 197893.81 | 0 | 297492.81 | 0 | [6 empty] | CM_WSI | 100%
403627 | CMC Programme Line for RCC | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-11-13 | 2013-11-13 | 2014-05-06 | 2019-05-08 |  | Scottish Water Wide | 142968 | 3874 | 3026.98 | 4472.98 | 902.08 | 1969.74 | 0 | 14245.78 | 0 | 157213.78 | 0 | [6 empty] | CM_WSI | 100%
30148 | Coalburn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-06-28 | 2010-09-20 | 2012-02-01 | 2012-03-12 | South Lanarkshire | 3371144.21 | 1198.09 | 0 | 0 | 0 | 0 | 0 | 1198.09 | 0 | 3372342.3 | 0 | [6 empty] | CM_WWNI | 26.6% | EC04A | 33.84% | EC10A | 39.56%
400073 | Cobden Street WwPS Refurb SPS001318 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-06 | 2011-03-30 | 2011-09-19 | 2012-09-05 |  | Angus | 678633.81 | 75.52 | 0 | 0 | 0 | 0 | 0 | 75.52 | 0 | 678709.33 | 0 | [6 empty] | CM_WWNI | 100%
503133 | Cochno SR - New Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-04-02 | 2028-06-01 | 2028-10-04 | 2029-05-16 | 2029-08-16 | West Dunbartonshire | 0 | 0 | 0 | 0 | 11932.82 | 33284.81 | -1298.13 | 43919.5 | 241604.76 | 285524.26 | 0 | [6 empty] | CM_WSNI | 100%
403221 | Cochno SR - Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | Glasgow City | 138508.25 | 550.84 | 0 | 0 | 0 | 0 | 1864.03 | 2414.87 | 0 | 140923.12 | 0 | [6 empty] | CM_WSNI | 100%
403065 | Cockmuir SR and TWP - Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-11-22 | 2014-10-01 | 2014-10-01 | 2014-10-21 |  | Glasgow City | 157857.02 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 157873.02 | 0 | [6 empty] | CM_WSNI | 100%
403565 | Colinsburgh WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-08-27 | 2016-12-15 | 2016-12-15 | 2016-12-16 | 2016-12-16 | Fife | 41656 | 46642.9 | 46237.73 | 0 | 0 | 0 | 0 | 92880.63 | 0 | 134536.63 | 0 | [6 empty] | SG1 | 100%
503831 | Colintraive BPT - inlet main relocation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-22 |  |  |  | - | 0 | 0 | 0 | 0 | 0 | 539.85 | -539.85 | 0 | 0 | 0 | 0 | [6 empty] | WSI | 100%
502313 | Coll RWM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-06-28 | 2019-06-28 | Argyll and Bute-North Argyll | 0 | 0 | 5133.26 | 923.31 | 42.58 | -4248.62 | 0 | 1850.53 | 0 | 1850.53 | 0 | [6 empty] | CM_WSI | 100%
402934 | Coll-Garyguirm ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-10-23 | 2013-12-18 | 2017-02-02 | 2017-02-07 | 2017-02-07 | Na H-Eileanan an Iar | 39672 | 33359 | -21609.79 | 0 | 0 | 0 | 0 | 11749.21 | 0 | 51421.21 | 0 | [6 empty] | SG1 | 100%
403170 | Comely Bank Edinburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-11-26 | 2013-05-20 | 2013-06-25 | 2013-10-23 | 2013-10-23 | City of Edinburgh | 40917 | -3265.08 | 0 | 0 | 0 | 0 | 0 | -3265.08 | 0 | 37651.92 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
300025 | Commerce Road Stranraer - Surface Water Management Plan | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-09-05 | 2011-09-05 | 2011-10-19 | 2012-03-16 | 2011-03-14 | Dumfries and Galloway | 35891.52 | -2843.7 | 0 | 0 | 0 | 0 | 0 | -2843.7 | 0 | 33047.82 | 0 | [6 empty] | EC01D | 100%
505498 | Commissioners Rd PRV A & B Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-05 |  | 2020-09-01 | 2020-10-31 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 1308.41 | 18691.59 | 20000 | 0 | 20000 | 0 | [6 empty] | WSNI | 100%
504991 | Complex Bypass Pilot | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-04-01 | 2020-03-03 |  | 2021-02-04 | 2021-05-07 | - | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 186000 | 0 | 186000 | 0 | [6 empty] | CM_WSNI | 100%
401202 | Compliance with Lead Regulations Comms Pipes - East Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-07-19 | 2010-12-17 | 2011-01-24 | 2014-06-20 | 2014-07-31 | All East Unitary Authorities | 1318698 | 646 | -818.25 | 0 | 0 | 0 | 0 | -172.25 | 0 | 1318525.75 | 2500 | [6 empty] | DW1A | 100%
401204 | Compliance with Lead Regulations Comms Pipes - North Cluster 2 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-07-19 | 2010-12-17 | 2011-01-24 | 2014-03-28 | 2014-03-31 | All North Unitary Authorities | 496352 | 240 | -753.63 | 0 | 0 | 0 | 0 | -513.63 | 0 | 495838.37 | 898 | [6 empty] | DW1A | 100%
400069 | Compliance with SEPA Matrix for WwTW Flow Monitoring WQ01A | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2011-09-21 | 2011-09-23 | 2015-03-30 | 2015-03-30 | Scottish Water Wide | 3463779.75 | 4733.51 | 0 | 323.47 | 0 | 0 | 0 | 5056.98 | 0 | 3468836.73 | 42643 | [6 empty] | WQ01A | 100%
500589 | Compute and Storage Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-01 | 2016-11-09 | 2016-11-09 | 2017-06-30 | 2017-06-30 | Scottish Water Wide | 0 | 386941.66 | 270481.57 | 38834.74 | -2789.45 | 0 | 2789.45 | 696257.97 | 0 | 696257.97 | 0 | [6 empty] | CM_M&G | 100%
403413 | Condition Monitoring Feasibility-Scoping Study | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2013-05-24 | 2020-07-09 | 2020-07-10 | 2021-09-27 | 2021-10-22 | Scottish Water Wide | 50000 | 0 | 0 | 0 | -48780.49 | 8504.63 | 75444.56 | 35168.7 | 14830.78 | 99999.48 | 0 | [6 empty] | WSI | 0.25% | WSNI | 0.25% | WWNI | 0.25% | WWI | 99.25%
502631 | Condition Surveys Forrest Rd TM Cumbernauld | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-06-15 | 2018-02-28 | 2018-05-18 | 2018-11-12 | 2018-11-12 | North Lanarkshire | 0 | 0 | 0 | 227319 | 78536.08 | 51.97 | -0.02 | 305907.03 | 0 | 305907.03 | 0 | [6 empty] | CM_WSI | 100%
503325 | Condition Surveys -Mains Park loop Erskine Dechmont TM & Megget E RWM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2018-07-31 | 2019-03-19 | 2019-04-24 | 2019-12-12 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 34513.01 | 110744.86 | -183 | 145074.87 | 0 | 145074.87 | 0 | [6 empty] | CM_WSI | 100%
502377 | Connel ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | Highland | 0 | 0 | 46062.91 | 16468.81 | 340.06 | 0 | 0 | 62871.78 | 0 | 62871.78 | 136478.56 | [6 empty] | SG1 | 100%
502794 | Conon Bridge WwTW - Compliance Risk Reduction | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-07-08 | 2028-01-12 | 2028-05-10 | 2028-09-14 | 2028-12-15 | Highland | 0 | 0 | 0 | 20817.18 | 537.73 | 7349.91 | 8382.44 | 37087.26 | 962912.74 | 1000000 | 0 | [6 empty] | CM_WWNI | 100%
502923 | Consultants Onsite Plans | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2021-03-31 | 2022-07-01 | 2022-10-17 | 2023-06-05 | 2023-09-05 | Scottish Water Wide | 0 | 0 | 0 | 227947.58 | 9243.4 | 243538.67 | 19270.35 | 500000 | 0 | 500000 | 0 | [6 empty] | WR6 | 100%
402850 | Corbiehall Boness | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-08-20 | 2014-09-30 | 2015-01-13 | 2015-03-24 | 2015-03-24 | West Lothian | 295629 | 40885.66 | 204.5 | -1631.25 | 0 | 0 | 0.09 | 39459 | 0 | 335088 | 204193.13 | [6 empty] | CS11 | 100%
500957 | Core Infrastructure and Capabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-24 | 2017-03-01 | 2017-03-01 | 2018-03-28 |  | Scottish Water Wide | 0 | 416746 | 2445157.22 | 1950165.12 | -31285.66 | 0 | -1335.08 | 4779447.6 | 0 | 4779447.6 | 0 | [6 empty] | CM_M&G | 100%
503321 | Cornceres WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-10-25 | 2029-02-28 | 2030-02-26 | 2030-05-29 | Fife | 0 | 0 | 0 | 0 | 78524.5 | 3454.5 | 0 | 81979 | 60021 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
504502 | Corpach Beach pumping station - rising main repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-02-05 |  | 2020-04-01 |  | - | 0 | 0 | 0 | 0 | 0 | 11322.16 | -61.53 | 11260.63 | 0 | 11260.63 | 0 | [6 empty] | CM_WWNI | 100%
500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-09-27 | 2020-01-07 | Highland | 0 | 10844 | 16121 | 7511 | 62607 | 33072.13 | 0.04 | 130155.17 | 0 | 130155.17 | 27758.39 | [6 empty] | EC01G | 23.78% | EC01D | 32.91% | CS16D | 43.31%
46334 | Corpach WWTW - STW001632 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-13 | 2015-04-30 | 2015-02-12 | 2015-02-12 |  | Highland | 513456.45 | 33.08 | 0 | 0 | 0 | 0 | 0 | 33.08 | 0 | 513489.53 | 0 | [6 empty] | CM_WWNI | 100%
503326 | Corpach WwTW - WwTW DOA rationalisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2022-03-09 | 2028-01-05 | 2028-04-03 | 2029-04-27 | 2029-07-30 | Highland | 0 | 0 | 0 | 0 | 21764.56 | 6185.94 | 16081.5 | 44032 | 1955947.96 | 1999979.96 | 0 | [6 empty] | CM_WWI | 100%
403918 | Corpach WwTW (transfer from 046334) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2014-10-10 | 2017-11-22 | 2018-01-29 | 2019-06-10 |  | Highland | 2005.85 | 184042.15 | 77833 | 792790 | 617312 | 22285.3 | 0 | 1694262.45 | 2499.7 | 1698768 | 0 | [6 empty] | CM_WWNI | 100%
500621 | Corporate Comms SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 927543.35 | 1113164.28 | 1235000.8 | 1253028.3 | 1341151.18 | 1219781.32 | 7089669.23 | 198569.03 | 7288238.26 | 0 | [6 empty] | CM_OVH | 100%
403272 | Corporate Risk Reduction - Assessment of pipelines crossing gas and oil pipes | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-28 | 2014-04-29 | 2014-04-29 | 2014-05-06 |  | Scottish Water Wide | 15537.85 | 0 | 47.45 | 0 | 0 | 0 | -47.45 | 0 | 0 | 15537.85 | 0 | [6 empty] | CM_WSI | 100%
501029 | Corporate Web Site Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-23 | 2016-05-16 | 2016-05-16 | 2019-11-14 | 2020-03-02 | Scottish Water Wide | 0 | 10154 | 456629.5 | 339687.6 | 218106.4 | 147010.6 | 0.01 | 1171588.11 | 0 | 1171588.11 | 0 | [6 empty] | CM_M&G | 100%
504478 | Corran Sep replacement outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-02-05 | 2020-08-13 | 2020-11-19 | 2020-12-17 | - | 0 | 0 | 0 | 0 | 0 | 1000 | 29000 | 30000 | 0 | 30000 | 0 | [6 empty] | CM_WWI | 100%
400719 | Corrie Terrace ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2011-11-10 | 2012-09-28 | 2013-02-19 | 2013-02-19 | North Ayrshire | 279753 | 25360 | -8232.95 | 0 | 0 | 0 | -88.93 | 17038.12 | 0 | 296791.12 | 136478.56 | [6 empty] | SG1 | 100%
30154 | Corsehouse WTW - Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2005-11-03 | 2007-04-11 | 2007-04-11 | 2011-03-31 | 2013-12-23 | East Ayrshire | 10950532.62 | 13484.3 | 0 | 0 | 0 | 0 | 0.08 | 13484.38 | 0 | 10964017 | 0 | [6 empty] | WSNI | 6% | DW13 | 18.8% | DW2 | 18.8% | DW3C | 18.8% | DW3G | 18.8% | DW4A | 18.8%
502708 | Corserig Crescent Kirkconnel | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2017-10-23 | 2019-07-31 | 2019-10-14 | 2020-03-31 | 2020-08-04 | Scottish Borders | 0 | 0 | 0 | 30066.08 | 194303.92 | 989580 | 28654.67 | 1242604.67 | 0 | 1242604.67 | 0 | [6 empty] | CM_WWI | 100%
501047 | Cost and Investment Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-18 | 2016-04-11 | 2016-04-11 | 2018-01-24 |  | Scottish Water Wide | 0 | 104225 | 271529.32 | 0 | 0 | 0 | 0 | 375754.32 | 0 | 375754.32 | 0 | [6 empty] | CM_M&G | 100%
501898 | Cost Investment Intelligence Project - EES & SWISS Strategic Refresh Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-03-01 | 2019-09-30 | 2019-09-30 | 2020-08-14 |  | Scottish Water Wide | 0 | 0 | 294324.8 | 1279591.97 | -419395.69 | 2029341.28 | 1564404.65 | 4748267.01 | 0 | 4748267.01 | 0 | [6 empty] | CM_M&G | 100%
502306 | Cotlandhill SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-09-12 | 2029-01-10 | 2029-12-31 | 2030-04-02 | Dumfries and Galloway | 0 | 0 | 37591.29 | 4800.23 | 18870.7 | 35542.75 | 195.03 | 97000 | 2268999.99 | 2365999.99 | 0 | [6 empty] | CM_WSNI | 100%
403357 | Coulter Reservoir - IoS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-04 | 2015-09-22 | 2015-11-09 | 2016-03-23 | 2016-09-01 | South Lanarkshire | 9239 | 255761 | 23865.75 | -2386.58 | 0 | 0 | 0 | 277240.17 | 0 | 286479.17 | 0 | [6 empty] | CM_WSI | 100%
500805 | Coulter RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2015-10-28 | 2017-07-21 | 2017-08-14 | 2018-03-31 | 2018-06-30 | South Lanarkshire | 0 | 31000 | 369.43 | 188786.38 | 21571.48 | -510.17 | 510.17 | 241727.29 | 0 | 241727.29 | 529906.83 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 84.44
503056 | Coulter WOA -Water Crossing and Bank Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-02 | 2028-02-03 | 2028-04-21 | 2029-01-22 | 2029-04-24 | South Lanarkshire | 0 | 0 | 0 | 23260.53 | 13691.1 | 1855.28 | -791.7 | 38015.21 | 1108984.79 | 1147000 | 0 | [6 empty] | CM_WSI | 100%
402855 | Coupar Angus Road Dundee | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-07-07 | 2014-07-21 | 2014-09-23 | 2014-09-23 | Dundee City | 68615 | 150 | -249.92 | 0 | 0 | 0 | 250 | 150.08 | 0 | 68765.08 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503232 | Coupar Angus WwTW - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2019-01-28 | 2019-01-28 | 2019-05-31 | 2020-03-31 | 2020-03-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 140375.9 | 270645.09 | 3939.73 | 414960.72 | 794.07 | 415754.79 | 0 | [6 empty] | CM_WWNI | 100%
30157 | Coursington (Motherwell) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2011-12-20 | 2012-02-29 | 2015-01-26 | 2015-03-30 | North Lanarkshire | 2189671.29 | -260.38 | 1653.56 | 0 | 0 | 0 | 0 | 1393.18 | 0 | 2191064.47 | 56088.91 | [6 empty] | CM_WWNI | 25% | EC04A | 75%
503542 | Coursington WWTW Chemical Dosing | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS5 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2019-03-31 | 2019-03-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 27672.9 | 353082.67 | 42244.43 | 423000 | 0 | 423000 | 604657.61 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
502754 | Cove Spine Waste Water Infrastructure | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Wastewater |  | SWD | DWQ Reliability | MS3 | 2017-07-12 | 2017-07-12 | 2017-10-17 | 2020-07-23 | 2020-07-23 | Aberdeen City | 0 | 0 | 0 | 109508.13 | 0 | -1415.53 | 1415.53 | 109508.13 | 0 | 109508.13 | 2573576.81 | [6 empty] | DW25P | 22.92% | SG5 | 77.08%
502755 | Cove Spine Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2021-01-29 | 2021-01-29 | Aberdeen City | 0 | 0 | 0 | 5011.28 | 58814.2 | -615.83 | 615.83 | 63825.48 | 0 | 63825.48 | 470181.23 | [6 empty] | WG5 | 100%
501947 | Cove WwTW Long Sea Outfall | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2016-03-29 | 2027-12-06 | 2028-01-31 | 2028-06-06 | 2028-09-06 | Scottish Borders | 0 | 785 | 10943 | -4000.44 | 0 | 0 | 0 | 7727.56 | 342538.44 | 350266 | 0 | [6 empty] | SR21_WW | 100%
46175 | Cowdenbeath Storm Tank SPS Refurb - SPS001511 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2010-12-23 | 2011-03-18 | 2012-10-03 |  | Fife | 3032171.08 | 190 | 0 | 0 | 0 | 0 | 0 | 190 | 0 | 3032361.08 | 0 | [6 empty] | CM_WWNI | 100%
402177 | Cowgill Lower Spillway Pitching Repair and CCTV of Outlet Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-09-05 | 2012-11-16 | 2014-03-26 | 2014-03-26 | South Lanarkshire | 336527.8 | 984.52 | 0 | 0 | 0 | 0 | 0 | 984.52 | 0 | 337512.32 | 0 | [6 empty] | CM_WSI | 100%
500721 | Cowlairs Infrastructure Improvement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-12-14 | 2016-03-29 | 2016-04-02 | 2019-12-19 | 2020-07-29 | Glasgow City | 0 | 403500 | 325728.74 | 1055.77 | 9842.74 | 122663.71 | -152509.96 | 710281 | 0 | 710281 | 0 | [6 empty] | CM_WWI | 100%
500892 | Cowsrieve Service Reservoir | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | WINF | Infra Charge | MS0 | 2019-02-28 | 2020-12-21 | 2021-01-21 | 2022-08-23 | 2022-11-22 | Aberdeenshire | 0 | 23824.63 | 13707.34 | 80228.18 | 9017.79 | 258429.1 | 1071411.79 | 1456618.83 | 2381382.23 | 3838001.06 | 470181.23 | [6 empty] | WG5 | 100%
30397 | Coylton (Joppa) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 2015-03-12 | South Ayrshire | 803468.51 | 12 | -5643.07 | 0 | 0 | 0 | 0 | -5631.07 | 0 | 797837.44 | 4095.91 | [6 empty] | EC04A | 100%
503279 | Coylton WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-08-26 | South Ayrshire | 0 | 0 | 0 | 0 | 77202.87 | 0 | 0 | 77202.87 | 0 | 77202.87 | 136478.56 | [6 empty] | SG1 | 100%
403936 | Coylton WwTW (Transfer from 030397) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS6 | 2009-05-15 | 2016-09-28 | 2017-01-23 | 2017-10-30 | 2017-10-30 | East Ayrshire | 47684 | 152230 | 1132068.88 | 2838971.48 | 201095.15 | -8377.67 | -59.6 | 4315928.24 | 0 | 4363612.24 | 1198319.6 |  |  |  |  | 11000 |  | EC04A | 50% | CM_WWNI | 50%
502957 | Craigend Outfall Perth | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-05-13 | 2019-05-13 | Perth and Kinross | 0 | 0 | 0 | 6440.28 | 25472.16 | 2667.6 | -2267.03 | 32313.01 | 0 | 32313.01 | 0 | [6 empty] | CM_WWI | 100%
502877 | Craigend Overland Sewer Scotlandwell | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-09-09 | 2021-07-23 | 2021-10-08 | 2022-05-11 | 2022-08-11 | Perth and Kinross | 0 | 0 | 0 | 16501.61 | 13539.97 | 2555.68 | 59422.75 | 92020.01 | 507980.02 | 600000.03 | 0 | [6 empty] | SR21_WW | 100%
403323 | Craigendunton Reservoir - Spillway & other remedial works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-05-07 | 2014-12-17 | 2014-12-17 | 2015-08-25 | 2015-08-25 | East Ayrshire | 203413 | 203087 | 0 | -693.62 | 0 | 0 | 0 | 202393.38 | 0 | 405806.38 | 0 | [6 empty] | CM_WSI | 100%
500774 | Craigengillan Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-27 | 2017-12-21 | 2018-02-26 | 2018-07-18 | 2018-07-18 | East Ayrshire | 0 | 4000 | 75402.21 | 296040.79 | 250151.03 | 37127.97 | 0 | 662722 | 0 | 662722 | 0 | [6 empty] | CM_WWI | 100%
502159 | Craighead Raw Water Springs - Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-06-20 | 2016-06-20 | 2016-06-20 | 2016-05-26 | 2016-06-20 | Aberdeenshire | 0 | 0 | 20930.23 | 0 | 0 | 0 | 0 | 20930.23 | 0 | 20930.23 | 0 | [6 empty] | CM_WSI | 100%
500896 | Craighead WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-10-27 | 2020-06-08 | 2020-06-22 | 2021-12-17 | 2022-02-18 | Aberdeenshire | 0 | 64413.05 | 378292.91 | 92578.51 | 112542.02 | 1161705.59 | 7933593.97 | 9743126.05 | 6107957.76 | 15851083.81 | 0 | [6 empty] | CM_WSNI | 100%
502645 | Craighouse WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-08-27 | 2033-03-24 | 2033-06-07 | 2034-05-17 | 2034-08-17 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21594.1 | 1821.56 | -19140.72 | 0 | 4274.94 | 0 | 4274.94 | 136478.56 | [6 empty] | WG1 | 100%
404008 | Craiglockhart Drive South Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2014-12-04 | 2015-08-31 | 2015-10-19 | 2016-09-07 | 2016-10-03 | City of Edinburgh | 71964 | 858071.55 | 87464.45 | 0 | -6875.79 | 0 | 0.79 | 938661 | 0 | 1010625 | 204193.13 | [6 empty] | CS11 | 100%
500893 | Craigmaddie and Milngavie VT Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-10-04 | 2020-09-14 | 2020-10-01 | 2021-10-05 | 2022-01-05 | East Dunbartonshire | 0 | 11086.02 | 42349.12 | 692.25 | 2891.45 | 11038.72 | 691784.13 | 759841.69 | 374158.59 | 1134000.28 | 0 | [6 empty] | CM_WSI | 100%
500231 | Craignure Mull - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-23 | 2016-04-25 | 2016-10-03 | 2017-02-28 | 2017-10-31 | Argyll and Bute-North Argyll | 0 | 604.07 | 9907.51 | 1531.96 | 1138.46 | -808.96 | 0 | 12373.04 | 0 | 12373.04 | 11989.73 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500858 | Craignure Mull RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-03-31 | 2017-06-25 | 2017-06-30 | 2018-03-29 | 2018-12-11 | Argyll and Bute-North Argyll | 0 | 2040.25 | 1994.75 | 10024.31 | 6946.55 | -3343.87 | 31.42 | 17693.41 | 0 | 17693.41 | 11393.23 | [6 empty] | DW5FS | 100%
500633 | Craignure TTU Provision | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-06-09 | 2015-07-20 | 2015-08-03 | 2015-11-02 | 2015-12-17 | Argyll and Bute-North Argyll | 0 | 1835327.61 | 13397.06 | 2462.45 | 0 | 108.15 | -108.15 | 1851187.12 | 0 | 1851187.12 | 638845.62 | [6 empty] | CS16WR | 100%
45029 | Craignure WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2012-11-07 | 2013-11-20 | 2015-10-27 | 2015-10-27 | Argyll and Bute-North Argyll | 7472159.47 | 151595.78 | 2195.38 | -51425.15 | 0 | 0 | 0 | 102366.01 | 0 | 7574525.48 | 423659.52 | [6 empty] | WG1 | 25% | DW23 | 75%
503376 | Crail Kilminning WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-04-18 | 2028-08-21 | 2029-02-09 | 2029-05-14 | Fife | 0 | 0 | 0 | 0 | 77571.46 | 5044.68 | 0 | 82616.14 | 59383.87 | 142000.01 | 136478.56 | [6 empty] | SG1 | 100%
500992 | Crail Kilminning WWTW - screen replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-07 | 2017-01-31 | 2017-03-21 | 2017-12-11 | 2017-12-11 | Fife | 0 | 919 | 52148.14 | 184096.85 | -1058.67 | 238.39 | 661.62 | 237005.33 | 0 | 237005.33 | 0 | [6 empty] | CM_WWNI | 100%
501251 | Crathie WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-11-10 | 2028-01-19 | 2028-05-23 | 2029-08-17 | 2029-11-19 | Aberdeenshire | 0 | 18868.52 | 92874.81 | 0 | 0 | -4660.92 | 5081.72 | 112164.13 | 2387339.89 | 2499504.02 | 0 | [6 empty] | CM_WSNI | 100%
45319 | Crathie WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-08-27 | 2011-03-16 | 2005-02-21 | 2011-07-12 | 2011-03-14 | Aberdeenshire | 50042.19 | 4.37 | 0 | 0 | 0 | 0 | 0 | 4.37 | 0 | 50046.56 | 0 | [6 empty] | DW13 | 100%
400093 | Creetown Catchment UID Improvements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2012-03-14 | 2012-04-16 | 2015-09-11 | 2014-10-01 | Dumfries and Galloway | 3699596 | -214980 | 2874.91 | -6871.24 | 0 | 0 | -21.47 | -218997.8 | 0 | 3480598.2 | 18.46 | [6 empty] | CM_WWI | 3% | CS11A | 7% | EC01B | 90%
503337 | Crianlarich Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-03 | 2028-03-17 | 2028-06-05 | 2029-01-01 | 2029-04-03 | Stirling | 0 | 0 | 0 | 0 | 7233.49 | 408.48 | 0 | 7641.97 | 352358.04 | 360000.01 | 0 | [6 empty] | CM_WSI | 100%
502977 | Crieff Road Aberfeldy | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2018-03-29 | 2018-11-08 | 2019-04-08 | 2019-08-26 | 2019-08-26 | Perth and Kinross | 0 | 0 | 0 | 8520.81 | 46727.19 | 78454 | 0 | 133702 | 1788 | 135490 | 0 | [6 empty] | CM_WWI | 100%
401340 | Crimond Crimongorth WSZ Low Pressure Enhancement WSZ000442 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-03-21 | 2012-08-27 | 2015-03-27 | 2014-03-31 | Aberdeenshire | 187812 | 8626.93 | 668.23 | 0 | 0 | 0 | 0 | 9295.16 | 0 | 197107.16 | 0 | [6 empty] | CS1 | 100%
500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-05-13 | 2021-05-13 | Scottish Water Wide | 0 | 865651.6 | 2635142.06 | 1113436.65 | 790634.3 | 1438510.37 | 0 | 6843374.98 | 61261.09 | 6904636.07 | 821666.8 | [6 empty] | CS22 | 100%
503093 | Critical Reservoir Assets (works to prevent MIOS) Years 4 - 6 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW2 | 2021-03-15 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 821666.8 | [6 empty] | CS22 | 100%
502786 | CRM Integration | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2019-03-04 | 2019-03-04 | Scottish Water Wide | 0 | 0 | 0 | 416407.83 | 718410.49 | 0 | 0 | 1134818.32 | 0 | 1134818.32 | 0 | [6 empty] | CM_M&G | 100%
402474 | Crocketford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-12-19 | 2014-02-24 | 2014-02-27 | 2016-04-27 | 2016-05-20 | Dumfries and Galloway | 2083096.6 | 531766.4 | 212679 | -1142.83 | 0 | 0 | 0 | 743302.57 | 0 | 2826399.17 | 0 | [6 empty] | CM_WWNI | 8.919% | SG1 | 91.08%
503042 | Cromarty Sutors WwTW - Replacement Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-06-21 | 2028-05-24 | 2028-09-15 | 2029-04-27 | 2029-07-30 | Highland | 0 | 0 | 0 | 31203.1 | 664.69 | 14727.79 | 17234.35 | 63829.93 | 2436170.04 | 2499999.97 | 0 | [6 empty] | CM_WWNI | 100%
500493 | Crossapol Tiree Septic Tank | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2015-06-16 | 2015-11-16 | 2015-11-17 | 2017-02-13 | 2017-02-13 | Highland | 0 | 94.75 | 0 | 0 | 0 | 0 | 0 | 94.75 | 0 | 94.75 | 1104204.13 | [6 empty] | EC01A | 100%
45807 | Crossford Nethan Foot SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-07-28 | 2011-09-05 | 2012-06-20 | 2012-06-29 | South Lanarkshire | 865891.06 | 22.22 | 0 | 0 | 0 | 0 | 0 | 22.22 | 0 | 865913.28 | 0 | [6 empty] | WQ01C | 100%
502403 | Crossford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-08-20 | 2022-02-04 | 2022-06-09 | 2023-05-30 | 2023-08-30 | South Lanarkshire | 0 | 0 | 31033.94 | 34245.79 | 30578.15 | 56024.67 | 319374.77 | 471257.32 | 24565.45 | 495822.77 | 136478.56 | [6 empty] | SG1 | 100%
503088 | Crossgates WSZ - Forteviot Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-03 | 2028-03-03 | 2028-07-06 | 2029-02-01 | 2029-05-04 | Perth and Kinross | 0 | 0 | 0 | 18614.12 | 2769.88 | 6496.06 | 0 | 27880.06 | 1063116.42 | 1090996.48 | 0 | [6 empty] | CM_WSI | 100%
501400 | Crosswood WTW | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-04-13 | 2028-08-17 | 2029-04-03 | 2029-07-04 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | [6 empty] | CM_WSNI | 100%
403907 | Crowlista WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-03-30 | 2017-02-17 | 2017-02-17 | 2017-02-20 | 2017-02-20 | Na H-Eileanan an Iar | 365.85 | 12550.15 | 32787.12 | 486.4 | 0 | 0 | 0 | 45823.67 | 0 | 46189.52 | 136478.56 | [6 empty] | SG1 | 100%
502817 | Croy WwTW - Investigation and Scope Definition for Potential Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-05-10 | 2022-08-26 | 2022-12-19 | 2023-12-07 | 2024-03-08 | Highland | 0 | 0 | 0 | 39079.11 | 2454.6 | 17298.79 | 12791.3 | 71623.8 | 1928376.2 | 2000000 | 136478.56 | [6 empty] | SG1 | 100%
505029 | Croy WwTW - Replace Washwater System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 | 2020-07-14 | 2021-04-07 | 2021-05-05 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 6329.49 | 0 | 6329.49 | 0 | 6329.49 | 0 | [6 empty] | CM_WWNI | 100%
501726 | Crumhaugh Trunk Mains System Rehabilitation | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-23 | 2028-06-01 | 2028-08-29 | 2029-03-29 | 2029-06-29 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965939.96 | 965939.96 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
500620 | CSD Customer Service SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 40337 | 53069.86 | 50922.05 | 51657.75 | 615604.93 | -224890 | 586701.59 | -36610 | 550091.59 | 0 | [6 empty] | CM_OVH | 100%
500632 | CSD Health & Safety SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 345715.43 | 400937.3 | 453239.93 | 800824.86 | 1582460.2 | 187113.81 | 3770291.53 | 30460.38 | 3800751.91 | 0 | [6 empty] | CM_OVH | 100%
500472 | CSO treatment - Wetlands study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-31 | 2016-02-05 | 2016-03-28 | 2020-01-29 | 2020-03-12 | South Lanarkshire | 0 | 46326 | 40332 | 39378.09 | 43963.91 | 53000 | 0 | 223000 | 0 | 223000 | 196736.15 | [6 empty] | EC10E | 100% | bar: Regulatory Outputs OMG-23
46265 | Cults Pitfodels TWP Refurb - TWP000440 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-03 | 2010-09-27 | 2011-09-26 | 2012-09-21 |  | Aberdeen City | 738943.5 | 3901.84 | -3901.84 | 0 | 0 | 0 | 0 | 0 | 0 | 738943.5 | 0 | [6 empty] | CM_WSNI | 100%
403069 | Culzean Drive Newarthill Motherwell Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-21 | 2014-06-20 | 2014-07-21 | 2015-03-31 | 2015-03-31 | North Lanarkshire | 1143423 | 56391 | 576.37 | 0 | 0 | 0 | 0 | 56967.37 | 0 | 1200390.37 | 204193.13 | [6 empty] | CS11 | 100%
501564 | Cumnock - Glenmuir Water Road Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2016-04-25 | 2018-09-28 | 2018-10-29 | 2019-05-31 | 2019-05-31 | North Ayrshire | 0 | 0 | 12366.29 | 35867.71 | 536689.45 | 47930.28 | 200 | 633053.73 | 0 | 633053.73 | 0 | [6 empty] | CM_WSI | 100%
400808 | Cumnock (Underwood) STC Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-05-31 | 2012-09-26 | 2012-11-13 | 2014-06-27 |  | East Ayrshire | 1054658.77 | -23446.33 | -19.68 | 0 | 0 | 0 | 0 | -23466.01 | 0 | 1031192.76 | 0 |  |  |  |  | 17000 |  | CM_WWNI | 100%
402220 | Cumnock STC - Upgrade of existing caustic dosing system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-07-19 | 2013-02-25 | 2013-05-13 | 2014-06-27 |  | East Ayrshire | 511013.57 | 346.95 | 0 | 0 | 0 | 0 | 1 | 347.95 | 0 | 511361.52 | 0 |  |  |  |  | 16219 |  | CM_WWNI | 100%
403380 | Cumnock STC Sludge Cake Storage Area | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-15 | 2014-03-04 | 2014-08-06 | 2015-01-28 |  | East Ayrshire | 254257 | -3080.9 | 0 | 0 | 0 | 0 | 0 | -3080.9 | 0 | 251176.1 | 0 | [6 empty] | CM_WWNI | 100%
502599 | Cumnock STC Sludge Digestors Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-02-21 | 2017-02-21 | 2017-07-25 | 2017-11-28 | 2017-11-28 | East Ayrshire | 0 | 0 | 17284.98 | 420615.02 | 86 | 914 | 0 | 438900 | 0 | 438900 | 0 | [6 empty] | CM_WWI | 100%
402966 | Cuninghill Avenue Inverurie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-01 | 2014-09-22 | 2014-10-06 | 2015-02-27 | 2015-02-27 | Aberdeenshire | 403795 | 11273.18 | 163.19 | 0 | 0 | 0 | 0 | 11436.37 | 0 | 415231.37 | 204193.13 | [6 empty] | CS11A | 100%
501816 | Cupar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Fife | 0 | 0 | 16572.1 | 25925.36 | 0 | 0 | 0 | 42497.46 | 0 | 42497.46 | 136478.56 | [6 empty] | SG1 | 100%
500915 | Cushnie TWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-10-29 | 2027-04-26 | 2027-04-26 | 2027-04-26 | 2027-04-26 | Aberdeenshire | 0 | 3493.49 | 55289.57 | -19213.4 | 15660.3 | 586.15 | -1837.02 | 53979.09 | 0 | 53979.09 | 0 | [6 empty] | CM_WSNI | 100%
500645 | Customer 2015 Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-01 | 2015-12-16 | 2015-12-16 | 2019-03-04 | 2018-02-28 | Scottish Water Wide | 0 | 732572.3 | 229609.75 | 272363.53 | 1121444.11 | 0 | 0 | 2355989.69 | 0 | 2355989.69 | 0 | [6 empty] | CM_M&G | 100%
500647 | Customer Connections SR15 Programme | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-06-01 | 2021-06-01 | Scottish Water Wide | 0 | 843078.31 | 857302.45 | 187208.99 | 548113.99 | 354117.41 | 537981.71 | 3327802.86 | 19175.16 | 3346978.02 | 233661.75 | [6 empty] | WG2 | 100%
402935 | Customer Experience Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-08-05 | 2013-08-05 | 2013-07-24 | 2014-06-11 |  | Scottish Water Wide | 589597.82 | 0 | 0 | 3023.37 | 0 | 0 | -3023.37 | 0 | 0 | 589597.82 | 0 | [6 empty] | CM_M&G | 100%
403482 | Customer Experience Improvements Strand 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-10-17 | 2015-06-24 | 2015-06-24 | 2015-06-15 |  | Scottish Water Wide | 392.77 | -154.77 | 0 | 0 | 0 | 0 | 0 | -154.77 | 0 | 238 | 0 | [6 empty] | CM_M&G | 100%
401920 | Customer Requested Lead Pipe removal | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2011-07-29 | 2012-01-24 | 2012-02-06 | 2016-05-18 | 2016-06-22 | Scottish Water Wide | 2607539.13 | 339301.87 | -307532.11 | 0 | 0 | 0 | 0 | 31769.76 | 0 | 2639308.89 | 0 | [6 empty] | DW1C | 100%
402588 | Customer Satisfaction Focused Delivery CID WWI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-21 | 2012-03-21 | 2012-04-04 | 2016-12-19 |  | All East Unitary Authorities | 434110 | 0 | -2641.95 | 97.55 | 0 | 0 | -137.91 | -2682.31 | 0 | 431427.69 | 0 | [6 empty] | CM_WWI | 100%
503342 | CVT - FOP Field Response Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2019-03-05 | 2019-03-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 165740.98 | 0 | 0 | 165740.98 | 0 | 165740.98 | 0 | [6 empty] | CM_M&G | 100%
502354 | CVT - FOP Scientific Vans | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-03 | 2016-11-03 | 2017-01-04 | 2017-03-23 | 2017-03-23 | Scottish Water Wide | 0 | 0 | 193364 | 4500.4 | 0 | 0 | 0 | 197864.4 | 0 | 197864.4 | 0 | [6 empty] | CM_M&G | 100%
503341 | CVT - FOP Scientific Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2019-04-17 | 2019-04-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 12170.73 | 553902.49 | -0.22 | 566073 | 0 | 566073 | 0 | [6 empty] | CM_M&G | 100%
502215 | CVT - Heavy Goods Vehicle Asset Replacement 2016-17 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2017-09-27 | 2017-09-27 | Scottish Water Wide | 0 | 0 | 3748560 | -49337 | 0 | 0 | 0 | 3699223 | 0 | 3699223 | 0 | [6 empty] | CM_M&G | 100%
502686 | CVT - Heavy Goods Vehicle Asset Replacement 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-29 | 2017-05-29 | 2017-07-03 | 2018-10-10 | 2018-10-10 | Scottish Water Wide | 0 | 0 | 0 | 3496926.74 | 2384801.83 | 8238.34 | 0.27 | 5889967.18 | 0 | 5889967.18 | 0 | [6 empty] | CM_M&G | 100%
503142 | CVT - Heavy Goods Vehicle Asset Replacement 2018-19 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-03-27 | 2018-03-27 | 2018-04-02 | 2019-05-27 | 2019-05-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2111015.02 | -830413.78 | 0 | 1280601.24 | 0 | 1280601.24 | 0 | [6 empty] | CM_M&G | 100%
503633 | CVT - Heavy Goods Vehicle Asset Replacement 2019-20 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2020-08-24 | 2020-08-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1253572.53 | 0 | 1253572.53 | 0 | 1253572.53 | 0 | [6 empty] | CM_M&G | 100%
503762 | CVT - Heavy Goods Vehicle Asset Replacement 2020-21 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2021-08-20 | 2021-08-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 20780.49 | 997635.51 | 1018416 | 0 | 1018416 | 0 | [6 empty] | CM_M&G | 100%
502198 | CVT - Light Commercial Vehicle Asset Replacement 2016-17 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2017-09-27 | 2017-09-27 | Scottish Water Wide | 0 | 0 | 6077169 | 187783.02 | -14965.85 | 0 | 0 | 6249986.17 | 0 | 6249986.17 | 0 | [6 empty] | CM_M&G | 100%
502687 | CVT - Light Commercial Vehicle Asset Replacement 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-29 | 2017-05-29 | 2017-07-03 | 2018-11-05 | 2018-11-05 | Scottish Water Wide | 0 | 0 | 0 | 6126142.57 | 2963663.34 | -565137.46 | 0.01 | 8524668.46 | 0 | 8524668.46 | 0 | [6 empty] | CM_M&G | 100%
503143 | CVT - Light Commercial Vehicle Asset Replacement 2018-19 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-03-27 | 2018-03-27 | 2018-04-02 | 2019-05-27 | 2019-05-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 5344998 | 78218.07 | 0 | 5423216.07 | 0 | 5423216.07 | 0 | [6 empty] | CM_M&G | 100%
503568 | CVT - Light Commercial Vehicle Asset Replacement 2019-20 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2020-08-27 | 2020-08-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 3769011.8 | 0 | 3769011.8 | 0 | 3769011.8 | 0 | [6 empty] | CM_M&G | 100%
503763 | CVT - Light Commercial Vehicle Asset Replacement 2020-21 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2021-08-23 | 2021-08-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 70851.59 | 3804433.41 | 3875285 | 0 | 3875285 | 0 | [6 empty] | CM_M&G | 100%
502214 | CVT - Plant Equipment Asset Replacement 2016-17 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2017-09-27 | 2017-09-27 | Scottish Water Wide | 0 | 0 | 318679 | -24827.13 | 1484.13 | -1224 | 1224 | 295336 | 0 | 295336 | 0 | [6 empty] | CM_M&G | 100%
502688 | CVT - Plant Equipment Asset Replacement 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-22 | 2017-05-22 | 2017-06-01 | 2018-06-19 | 2018-06-19 | Scottish Water Wide | 0 | 0 | 0 | 399843.99 | 48147.78 | 0 | 0 | 447991.77 | 0 | 447991.77 | 0 | [6 empty] | CM_M&G | 100%
503144 | CVT - Plant Equipment Asset Replacement 2018-19 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-03-26 | 2018-03-26 | 2018-04-02 | 2019-04-24 | 2019-04-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1014947.06 | -202561.38 | 0 | 812385.68 | 0 | 812385.68 | 0 | [6 empty] | CM_M&G | 100%
503569 | CVT - Plant Equipment Asset Replacement 2019-20 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2020-08-24 | 2020-07-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 762133.33 | -183369.17 | 578764.16 | 0 | 578764.16 | 0 | [6 empty] | CM_M&G | 100%
503764 | CVT - Plant Equipment Asset Replacement 2020-21 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2021-08-25 | 2021-08-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 7707.32 | 134832 | 142539.32 | 0 | 142539.32 | 0 | [6 empty] | CM_M&G | 100%
502287 | CVT - Wastewater Tankers | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2017-01-19 | 2017-02-15 | Scottish Water Wide | 0 | 0 | 819534 | 0 | 0 | 0 | 0 | 819534 | 0 | 819534 | 0 | [6 empty] | CM_M&G | 100%
502753 | CVT -Telematics Project 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-22 | 2017-05-22 | 2017-06-01 | 2018-12-19 | 2018-12-19 | Scottish Water Wide | 0 | 0 | 0 | 276867.74 | 47802.5 | 0 | 0 | 324670.24 | 0 | 324670.24 | 0 | [6 empty] | CM_M&G | 100%
503711 | CWA - Post-Project Land Liabilities | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-09-30 | 2019-09-30 | 2020-01-28 | 2021-07-14 | 2021-08-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 104690.11 | 408297.5 | 512987.61 | 17012.4 | 530000.01 | 0 | [6 empty] | CM_WSI | 100%
503101 | CWA Incentivisation Actual | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MS2 | 2018-07-09 | 2018-07-09 | 2020-03-24 |  | 2022-11-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2310165.4 | 2511179.05 | 290185.63 | 5111530.08 | -111530.08 | 5000000 | 357611656.01 | [6 empty] | SR15_CMP_LATE | 0.08285% | SR15_CMA_MAG | 0.3149% | WG3 | 0.6015% | SR15_SED_INFC | 0.9059% | SR15_CMP_PLAN | 2.046% | SR15_DWA_SOSI | 2.336% | SR15_SED_SCAP | 2.36% | SR15_SED_NRSW | 3.202% | SR21_SS | 3.707% | SR15_DWQ_REL | 4.568%
402350 | CWG External Flooding Lethamhill Road Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-03-27 | 2012-10-29 | 2013-11-08 | 2013-11-08 | Glasgow City | 985456 | -7545.57 | 0 | 0 | 0 | 0 | 0 | -7545.57 | 0 | 977910.43 | 25 | [6 empty] | CS15 | 100%
402349 | CWG Internal and External Flooding at Fullarton Avenue Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-03-27 | 2013-03-28 | 2014-01-22 | 2014-01-22 | Glasgow City | 1146942 | 0 | 0 | 0 | -4653.36 | 0 | 0 | -4653.36 | 0 | 1142288.64 | 0 | [6 empty] | CS11A | 50% | CS15 | 50%
34562 | D/S - Non Domestic Water - Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
34574 | D/S - Non Domestic Water - South Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | South Ayrshire | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | [6 empty] | WG2 | 100%
503238 | Daer Clarifier Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-01-26 | 2022-07-01 | 2022-10-21 | 2023-10-17 | 2024-01-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 62472.15 | 34530.59 | 173745.86 | 270748.6 | 1730674.84 | 2001423.44 | 0 | [6 empty] | CM_WSNI | 100%
500807 | Daer Coulter RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-09-30 | 2017-03-23 | 2017-03-28 | 2018-03-31 | 2018-06-30 | South Lanarkshire | 0 | 20200 | 28708.15 | 112380.59 | 49259.1 | 0 | 0 | 210547.84 | 0 | 210547.84 | 220398.43 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 37.01
501179 | DAER CWT NS975097 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS1 | 2015-10-30 | 2027-06-23 | 2027-06-24 | 2027-11-10 | 2028-02-10 | South Lanarkshire | 0 | 19618 | 139667.88 | 67484 | -71469.17 | 0 | 0 | 155300.71 | 0 | 155300.71 | 645915.7 | [6 empty] | DW25T | 100%
403741 | Daer IoS Drainage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-03-19 | 2014-11-17 | 2015-02-03 | 2016-05-10 | 2016-06-08 | Scottish Water Wide | 88085 | 180591 | -36656 | -460.02 | 0 | 0 | 0 | 143474.98 | 0 | 231559.98 | 0 | [6 empty] | CM_WSI | 100%
501276 | Daer Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | South Lanarkshire | 0 | 0 | 500.62 | 5050.75 | 284.22 | 39134.17 | -44968.76 | 1 | 0 | 1 | 0 | [6 empty] | I2S_WI | 100%
501670 | DAER WOA - Stablewood Pipe Bridge - H&S upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2017-10-27 | 2021-03-29 | 2021-07-06 | 2022-04-25 | 2022-07-25 | South Lanarkshire | 0 | 0 | 7135.19 | 21492.19 | 93983.11 | 35918.9 | 127042.75 | 285572.14 | 701280.89 | 986853.03 | 0 | [6 empty] | CM_M&G | 50% | CM_WSI | 50%
501239 | Daer WOA Camps WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-06-29 | 2018-08-31 | 2018-05-29 | 2020-09-01 | 2020-09-01 | South Lanarkshire | 0 | 322649 | -230766 | 261499.24 | 2563825.06 | 739367.1 | 66492.44 | 3723066.84 | 0 | 3723066.84 | 0 | [6 empty] | CM_WSI | 100%
501124 | Daer WOA Crawford WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501121 | Daer WOA Daer WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2016-04-11 | 2018-02-05 | 2018-02-06 | 2018-11-29 | 2018-11-29 | South Lanarkshire | 0 | 55800 | 1291 | 496512 | 1365663.23 | 145065.38 | -505.39 | 2063826.22 | 0 | 2063826.22 | 0 | [6 empty] | CM_WSI | 100%
501240 | Daer WOA Douglas Moor WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501238 | Daer WOA East Rogerton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501123 | Daer WOA Hirst WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501122 | Daer WOA Muirkirk WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-14 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501241 | Daer WOA Udston WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
502772 | Daer WRZ SR Residual Chorine Monitors | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2018-02-26 | 2019-03-07 | 2019-07-29 | 2021-01-19 | 2021-04-20 | North Lanarkshire | 0 | 0 | 0 | 28483.23 | 54576.58 | 70957.49 | 215791.05 | 369808.35 | 54122.14 | 423930.49 | 442547.58 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501219 | Daer WTW - Improving WQ in Network (OMG5) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2016-03-30 | 2018-10-31 | 2018-12-10 | 2020-09-30 | 2020-10-31 | South Lanarkshire | 0 | 24826.32 | 78122.11 | 61176.98 | 206443.93 | 490110.18 | 434026.45 | 1294705.97 | 15415.52 | 1310121.49 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
503374 | Dairsie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-19 | 2023-03-28 | 2023-07-31 | 2024-01-19 | 2024-04-22 | Fife | 0 | 0 | 0 | 0 | 78298.42 | 65318.01 | 1265918.5 | 1409534.93 | 649906.95 | 2059441.88 | 136478.56 | [6 empty] | SG1 | 100%
501107 | Dalbeattie Catchment Study (DAS) | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-12-19 | 2016-12-19 | 2017-01-24 | 2017-01-24 | Dumfries and Galloway | 0 | 600 | 14811.19 | -434 | 0 | 0 | 0 | 14977.19 | 0 | 14977.19 | 9525.18 | [6 empty] | EC01D | 100%
46326 | Dalbeattie STW - STW000217 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-09 | 2012-01-17 | 2012-01-25 | 2016-03-10 |  | Dumfries and Galloway | 7453224.62 | 236247.16 | -34829.52 | -22895.13 | 0 | 0 | 0 | 178522.51 | 0 | 7631747.13 | 0 | [6 empty] | CM_WWNI | 100%
46851 | Dalchreichart WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-06-05 | 2012-08-13 | 2013-06-14 | 2016-04-01 | Highland | 1475368.72 | -22610.64 | 0 | 0 | 0 | 0 | 0 | -22610.64 | 0 | 1452758.08 | 2603 | [6 empty] | DW23 | 100%
504329 | Dalderse WWTW - FST 2 Scraper Bridge refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-12-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 6325.24 | 164674.78 | 171000.02 | 0 | 171000.02 | 0 | [6 empty] | CM_WWNI | 100%
503306 | Dalderse WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-06 | 2023-09-26 | 2024-01-25 | 2025-01-20 | 2025-04-22 | Falkirk | 0 | 0 | 0 | 0 | 28174.04 | 6730.84 | 74324.01 | 109228.89 | 1890771.12 | 2000000.01 | 136478.56 | [6 empty] | SG1 | 100%
501579 | DALDERSE WWTW 1966 NS903822 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-09-05 | 2020-04-06 | 2019-11-25 | 2021-05-28 | 2021-08-27 | Falkirk | 0 | 0 | 134375.2 | 345738.22 | 195180.5 | 2259205.32 | 3871827.79 | 6806327.03 | 1410752.97 | 8217080 | 0 |  |  |  |  | 91180 |  | CM_WWNI | 100%
502654 | DALDOWIE - Cluster 1 - AIRDRIE 130M S-O SPORTS CENTRE CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-12-17 | 2028-01-05 | 2028-03-28 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 0 | 202623.77 | 133376.23 | 21784.21 | 7041.72 | 364825.93 | 25950.07 | 390776 | 177138.89 | [6 empty] | EC01F_ID | 100%
502661 | DALDOWIE - Cluster 10 - 7 Bell St-east O Hattonrig Rd | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2020-04-01 | 2020-04-01 | 2020-01-30 | 2019-12-02 | 2020-04-01 | North Lanarkshire | 0 | 0 | 0 | 79632.03 | 80367.97 | -40076.76 | 0 | 119923.24 | 0 | 119923.24 | 177138.89 | [6 empty] | EC10B_ID | 100%
502663 | DALDOWIE - Cluster 11 - Spindlehowe Rd-New Edinburgh Uddingston | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-12-17 | 2027-07-23 | 2027-10-14 | 2028-11-07 | 2029-02-07 | North Lanarkshire | 0 | 0 | 0 | 132239.88 | 72760.12 | 113989 | 93709.78 | 412698.78 | 3505985.19 | 3918683.97 | 354277.77 | [6 empty] | EC01F_ID | 48.39% | EC10B_ID | 51.61%
502662 | DALDOWIE - Cluster 12 - Uddingston E-O Pond-n-o Glasgow Zoo CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-12-17 | 2028-01-05 | 2028-03-28 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 0 | 105016.39 | 76983.61 | 3000 | 0 | 185000 | 7425294 | 7610294 | 177138.89 | [6 empty] | EC01F_ID | 100%
502363 | DALDOWIE - Cluster 13 - 3 HERMISTON PL DUAL MANHOLE | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS5 | 2019-12-02 | 2019-12-02 | 2019-09-23 | 2019-09-23 | 2019-09-23 | North Lanarkshire | 0 | 0 | 59085.93 | 35914.07 | 350.56 | 2442.64 | -116.66 | 97676.54 | 0 | 97676.54 | 177138.89 | [6 empty] | EC01F_ID | 100%
502664 | DALDOWIE - Cluster 14 - Hattonrigg Rd - Cronin Place Dual Manhole | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-07-31 | 2027-02-01 | 2027-04-12 | 2028-01-03 | 2028-04-04 | North Lanarkshire | 0 | 0 | 0 | 102613.92 | 52887.08 | 92371 | 48634.1 | 296506.1 | 923179.9 | 1219686 | 354277.77 | [6 empty] | EC01F_ID | 48.78% | EC10B_ID | 51.22%
502665 | DALDOWIE - Cluster 15 - Coatbridge Sykeside Sps CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-08-02 | 2028-01-05 | 2028-03-28 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 0 | 52101.75 | 28898.25 | 24000 | 5.95 | 105005.95 | 496811.05 | 601817 | 354277.77 | [6 empty] | EC01F_ID | 28.57% | EC01B_ID | 71.43%
502666 | DALDOWIE - Cluster 16 - Coatbridge Shawhead Sps CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-07-31 | 2027-02-01 | 2027-04-12 | 2027-08-27 | 2027-11-29 | North Lanarkshire | 0 | 0 | 0 | 51897.82 | 35053.18 | 71469 | 21402.05 | 179822.05 | 390177.95 | 570000 | 354277.77 | [6 empty] | EC01F_ID | 47.44% | EC01B_ID | 52.56%
502667 | DALDOWIE - Cluster 17 - Coatbridge Hagmill Road Sps CSO -EO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-08-09 | 2028-01-05 | 2028-02-03 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 0 | 58533.13 | 23466.87 | 13336.58 | 582.93 | 95919.51 | 604803.52 | 700723.03 | 354277.77 | [6 empty] | EC01F_ID | 24.73% | EC01B_ID | 75.27%
502668 | DALDOWIE - Cluster 18 - Airdrie Park 40m Sw 97 Alexander St | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-08-02 | 2028-01-05 | 2028-03-28 | 2029-08-24 | 2029-11-26 | North Lanarkshire | 0 | 0 | 0 | 136000 | 83000 | 11000 | 4.08 | 230004.08 | 724304.92 | 954309 | 177138.89 | [6 empty] | EC01F_ID | 100%
502655 | DALDOWIE - Cluster 2 - Chapelhall Burniebrae Storm Tk CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-07-31 | 2028-01-05 | 2028-03-28 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 0 | 87081 | 96919 | 21000 | 0.58 | 205000.58 | 203174.42 | 408175 | 354277.77 | [6 empty] | EC01F_ID | 3.125% | EC10B_ID | 96.88%
502656 | DALDOWIE - Cluster 3 - Airdrie Nw Of Monkland Bridge CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-07-30 | 2020-11-30 | 2021-02-24 | 2022-07-25 | 2022-10-25 | North Lanarkshire | 0 | 0 | 0 | 93000 | 41000 | 15103.4 | 134896.6 | 284000 | 0 | 284000 | 354277.77 | [6 empty] | EC01F_ID | 25.68% | EC10B_ID | 74.32%
502364 | DALDOWIE - Cluster 4 - CALDERBANK FORGE ROW WWPS 2003 NS772630 Calderbank 56 Woodhall Ave CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-08-19 | 2028-01-19 | 2028-03-28 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 50737.41 | 27262.59 | 67000 | 18000 | 1.52 | 163001.52 | 698071.48 | 861073 | 177138.89 | [6 empty] | EC01B_ID | 100%
502657 | DALDOWIE - Cluster 5 - Tannochside 110m SE Rosebank CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2020-04-30 | 2022-01-07 | 2022-03-31 | 2023-12-12 | 2024-03-13 | North Lanarkshire | 0 | 0 | 0 | 237098.77 | 149065.24 | 24342.51 | 297.49 | 410804.01 | 989196.02 | 1400000.03 | 354277.77 | [6 empty] | EC01F_ID | 38.57% | EC10B_ID | 61.43%
502658 | DALDOWIE - Cluster 6 - Uddingston Daldowie Crematorium No1 CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2020-05-29 | 2022-01-07 | 2022-03-31 | 2023-12-12 | 2024-03-13 | North Lanarkshire | 0 | 0 | 0 | 75726.18 | 43273.83 | 20384.97 | -7282.98 | 132102 | 2267897.99 | 2399999.99 | 354277.77 | [6 empty] | EC01F_ID | 6.25% | EC10B_ID | 93.75%
502659 | DALDOWIE - Cluster 8 - Uddingston 4 Lady Jane Gate CSO | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-10-03 | 2028-01-07 | 2028-03-28 | 2028-09-05 | 2028-12-06 | North Lanarkshire | 0 | 0 | 0 | 85996.95 | 87003.05 | -8444.7 | 1.24 | 164556.54 | 423473.62 | 588030.16 | 177138.89 | [6 empty] | EC01F_ID | 100%
502660 | DALDOWIE - Cluster 9 - Bellshill 11 Holytown Rd-leander Cres | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-10-03 | 2027-07-23 | 2027-10-14 | 2028-11-08 | 2029-02-08 | South Lanarkshire | 0 | 0 | 0 | 192169.01 | 141830.99 | 53347 | 37653 | 425000 | 823816 | 1248816 | 354277.77 | [6 empty] | EC01F_ID | 10.98% | EC10B_ID | 89.02%
500816 | Daldowie Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-27 | 2016-06-03 | 2016-06-06 | 2018-06-20 | 2018-06-20 | Glasgow City | 0 | 127000 | 82027.42 | -123027.42 | 4179.42 | 0 | 0 | 90179.42 | 0 | 90179.42 | 120964.87 | [6 empty] | CS15A | 100%
500495 | Daldowie WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-09-17 | 2018-08-30 | 2018-08-30 | 2018-08-30 | 2018-08-30 | South Lanarkshire | 0 | 3426.08 | 42006.07 | 31030.87 | -76212.7 | 86.12 | -263.57 | 72.87 | 0 | 72.87 | 0 | [6 empty] | CM_WWNI | 100%
501829 | Daldowie WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-06-15 | 2020-08-24 | 2021-02-24 | 2021-02-25 | South Lanarkshire | 0 | 0 | 6398.15 | 0 | 0 | 15314.85 | 634044.25 | 655757.25 | 36474.81 | 692232.06 | 0 | [6 empty] | SR21_WW | 100%
402926 | Dalgety bay Sewer -Release Ph 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-13 | 2013-02-08 | 2013-04-12 | 2016-12-14 |  | Fife | 831253 | 19333 | -34509.55 | 385.13 | 0 | 0 | 0.01 | -14791.41 | 0 | 816461.59 | 0 | [6 empty] | CM_WWI | 100%
400070 | Dalgety Bay SPS Refurb SPS002983 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-06 | 2011-10-17 | 2012-02-13 | 2012-10-03 |  | Fife | 452125.42 | 475 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 452600.42 | 0 | [6 empty] | CM_WWNI | 100%
46330 | Dalgrain Grangemouth SPS - SPS001527 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-29 | 2011-08-29 | 2011-08-26 | 2013-09-23 |  | Falkirk | 1217196.16 | -406.44 | 0 | 0 | 0 | 0 | 0 | -406.44 | 0 | 1216789.72 | 0 | [6 empty] | CM_WWNI | 100%
400514 | Dalkeith Jarnac Court - Internal Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-03-31 | 2012-03-20 | 2012-04-30 | 2013-03-25 | 2013-03-25 | Midlothian | 96979 | -126.02 | 0 | 0 | 0 | 0 | 0 | -126.02 | 0 | 96852.98 | 106.8 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503982 | Dall Terrace Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-11-26 |  | 2020-04-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2854.93 | 0 | 2854.93 | 0 | 2854.93 | 0 | [6 empty] | CM_WSI | 100%
501402 | DALMACOULTER DSR NS767679 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-03-30 | 2019-03-12 | 2019-03-29 | 2020-11-04 | 2020-11-24 | North Lanarkshire | 0 | 0 | 0 | 7684.05 | 288020.67 | 1392156.53 | 708783 | 2396644.25 | 173384.12 | 2570028.37 | 1882113.51 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503412 | Dalmacoulter WSZ Trunk Main Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS0 | 2020-03-31 | 2020-10-12 | 2020-10-30 | 2022-06-30 | 2022-09-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 97009.29 | 263239.21 | 1178381.83 | 1538630.33 | 1750620.91 | 3289251.24 | 539345.26 | [6 empty] | DW5 | 100% | [18 empty] | Regulatory Outputs OMG-06: 83.9
45321 | Dalmally (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2012-10-24 | 2012-12-11 | Argyll and Bute-North Argyll | 185708.62 | 170.38 | 0 | 0 | 0 | 0 | 0 | 170.38 | 0 | 185879 | 0 | [6 empty] | DW13 | 100%
502322 | Dalmally WOA - Stronmilchan Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-09-13 | 2017-04-24 | 2017-05-02 | 2017-05-08 | 2017-05-08 | Argyll and Bute-North Argyll | 0 | 0 | 15221.97 | 1453.01 | 0 | 0 | 0 | 16674.98 | 0 | 16674.98 | 0 | [6 empty] | CM_WSI | 100%
500817 | Dalmarnock Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-24 | 2015-12-08 | 2015-12-09 | 2017-09-11 | 2017-09-11 | Glasgow City | 0 | 23668.9 | 30784.26 | 1367.05 | 118.75 | 0 | 0 | 55938.96 | 0 | 55938.96 | 120964.87 | [6 empty] | CS15A | 100%
504916 | Dalmarnock Sludge WWPS - Relocation of Hydraulic Power Packs H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-02-28 | 2020-10-12 | 2021-02-16 | 2021-08-17 | 2021-11-17 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 344.48 | 0 | 344.48 | 0 | 344.48 | 0 | [6 empty] | CM_WWNI | 100%
30186 | Dalmarnock STW Refurb - STW000222 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2011-09-23 | 2011-09-23 | 2012-03-20 |  | Glasgow City | 731914.11 | 63.12 | 0 | 0 | 0 | 0 | 0 | 63.12 | 0 | 731977.23 | 0 | [6 empty] | CM_WWNI | 100%
503269 | Dalmarnock WWTW Improvements | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2021-03-31 | 2021-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 9452152 | 3104190.6 | 13054774.4 | 25611117 | 6411744.9 | 32022861.9 | 11105602.59 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
503701 | Dalmarnock WwTW STW000222 - Asset Cleaning Project & Control of Odours | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-10-03 | 2019-11-29 | 2020-01-07 | 2021-04-15 | 2021-04-16 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 611075.58 | 632605.65 | 1243681.23 | 81318.77 | 1325000 | 0 | [6 empty] | CM_WWI | 100%
502826 | Dalmeny WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-01 | 2018-08-01 | 2018-07-31 | 2018-07-31 | 2018-07-31 | City of Edinburgh | 0 | 0 | 0 | 74702.5 | -48454.2 | 0 | 0 | 26248.3 | 0 | 26248.3 | 136478.56 | [6 empty] | SG1 | 100%
402643 | Dalmoak SPS pumps and screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-07-13 | 2013-01-07 | 2013-03-15 | 2017-12-14 |  | West Dunbartonshire | 510258 | 85000 | 70001 | 310707.78 | 1033.23 | -319.66 | 0 | 466422.35 | 0 | 976680.35 | 0 | [6 empty] | CM_WWNI | 100%
500804 | Dalmuir Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-27 | 2019-03-29 | 2019-04-15 | 2019-04-15 | 2019-04-15 | Glasgow City | 0 | 75100 | 155575.08 | 97355.2 | 74943.1 | 7627.01 | -397.14 | 410203.25 | 0 | 410203.25 | 120964.87 | [6 empty] | CS15A | 100%
402620 | Dalmuir PFI | Q&S3B | Completion | PFI |  |  | Wastewater |  | SWD | PFI | MS3 | 2012-03-27 | 2013-10-23 | 2013-11-25 | 2020-09-11 |  | West Dunbartonshire | 17774429.59 | 3562731.52 | 1045417.97 | 1711010.83 | 65363.63 | 889403.4 | 0 | 7273927.35 | 0 | 25048356.94 | 4181829.69 | [6 empty] | PFI | 100%
402841 | Dalmuir Sludge Pumping Station - Health and Safety Project | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-08-24 | 2013-08-09 | 2013-10-08 | 2015-02-24 |  | West Dunbartonshire | 390289.36 | 1339.4 | -619.9 | 100.88 | 0 | 0 | 0.26 | 820.64 | 0 | 391110 | 0 | [6 empty] | CM_M&G | 100%
503473 | Dalmuir to Erskine Sludge Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-13 | 2019-02-13 | 2019-03-06 | 2020-10-29 | 2021-03-25 | Renfrewshire | 0 | 0 | 0 | 0 | 934807.88 | 2426399.59 | 28213.82 | 3389421.29 | 38029.89 | 3427451.18 | 0 | [6 empty] | CM_WWI | 100%
503530 | Dalmuir to Erskine WWTW Sludge Main Replacement - Historic Reactive Costs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 | 2019-05-21 | 2019-05-21 | 2020-04-08 | 2020-03-17 | 2022-02-08 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 52710 | 0 | 52710 | 0 | 52710 | 0 | [6 empty] | CM_WWI | 100%
503531 | Dalmuir to Erskine WWTW Sludge Main Replacement - Reactive Costs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 | 2019-05-21 | 2019-05-21 | 2020-04-08 | 2020-03-17 | 2022-02-08 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 150848.01 | 0 | 150848.01 | 0 | 150848.01 | 0 | [6 empty] | CM_WWI | 100%
503229 | Dalmuir Wastewater Strategy Review | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2019-03-25 | 2019-03-25 | 2021-09-10 | 2021-12-13 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 105966.42 | 283780.61 | 344921.98 | 734669.01 | 171182.29 | 905851.3 | 0 | [6 empty] | CM_WWI | 100% | bar: Regulatory Outputs OMG-23
501776 | Dalmuir WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-06-29 | 2020-09-07 | 2021-03-10 | 2021-03-11 | West Dunbartonshire | 0 | 0 | 12538.58 | 17.8 | 0 | 75143.62 | 185702.5 | 273402.5 | 14873.54 | 288276.04 | 0 | [6 empty] | SR21_WW | 100%
501603 | DALRYMPLE WWTW NS353141 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-19 | 2020-04-06 | 2020-10-13 | 2021-06-04 | 2021-09-06 | South Ayrshire | 0 | 0 | 39427.59 | 139582.28 | -24523.99 | 251999.12 | 1270585.44 | 1677070.44 | 647425.36 | 2324495.8 | 0 | [6 empty] | CM_WWNI | 100%
501289 | Dalscone WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-10-14 | 2016-10-14 | Dumfries and Galloway | 0 | 0 | 59031.7 | 114.37 | 36.43 | 0 | 0 | 59182.5 | 0 | 59182.5 | 0 | [6 empty] | CM_WWNI | 100%
500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2019-01-31 | 2019-06-18 | Dumfries and Galloway | 0 | 11549 | 32755.28 | 49515.73 | 35034 | -1008.62 | -0.01 | 127845.38 | 0 | 127845.38 | 51074.46 | [6 empty] | EC01G | 7.61% | CS16D | 33.61% | EC01D | 58.78%
503058 | Dalscone WwTW - Replace Percolating Filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-07-08 | 2028-10-25 | 2029-02-15 | 2030-05-21 | 2030-08-21 | Dumfries and Galloway | 0 | 0 | 0 | 27469.33 | 60096.74 | 56754.06 | 621.49 | 144941.62 | 2355058.38 | 2500000 | 0 | [6 empty] | CM_WWNI | 100%
404135 | Dalwhinnie WTW - TTU | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS3 | 2016-03-31 | 2019-03-28 | 2019-03-29 | 2021-06-18 | 2021-09-08 | Highland | 0 | 0 | 0 | 113265.2 | 680912.36 | 796319.77 | 2473905.84 | 4064403.17 | 573003.38 | 4637406.55 | 0 |  |  |  |  | 50.25 |  | DW25 | 100% | bar: Regulatory Outputs OMG-03
404102 | Dalwhinnie WTW Q&S IIIb Additional Requirements | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS7 | 2016-03-31 | 2018-01-24 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Highland | 0 | 25960.89 | 102140.32 | 5148.73 | 0 | 110.82 | -340.66 | 133020.1 | 0 | 133020.1 | 0 | [6 empty] | DW25 | 100%
402605 | Danger Point WWPS - Arbroath | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2016-02-26 | 2016-03-01 | 2015-08-04 |  | All East Unitary Authorities | 99973 | -39088.42 | 0 | 26.8 | 0 | 0 | -26.8 | -39088.42 | 0 | 60884.58 | 0 | [6 empty] | CM_M&G | 100%
403658 | Darnley Mains Development - Trunk Mains Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2014-01-29 | 2014-09-30 | 2014-09-30 | 2021-01-18 |  | East Renfrewshire | 2061305 | -21500 | -62816.62 | -228033.83 | 105288.86 | 144119.34 | 0 | -62942.25 | 2740186.25 | 4738549 | 0 | [6 empty] | CM_WSI | 100%
501078 | Data and Application Integration | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-29 | 2016-03-29 | 2016-03-29 | 2017-10-12 | 2017-10-12 | Scottish Water Wide | 0 | 1634947 | -590672.14 | 389651.61 | 0 | 0 | 0 | 1433926.47 | 0 | 1433926.47 | 0 | [6 empty] | CM_M&G | 100%
502788 | Davidston Dam Raw Water Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2027-12-06 | 2028-02-29 | 2028-07-31 | 2028-10-31 | Moray | 0 | 0 | 0 | 5739.53 | 3860.47 | 0 | 0 | 9600 | 190400 | 200000 | 0 | [6 empty] | CM_WSI | 40% | CM_WSNI | 60%
500976 | DC LAN Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-02-15 | 2017-01-31 | 2017-01-31 | 2018-03-28 | 2018-03-28 | Scottish Water Wide | 0 | 164128 | 1079965.71 | 82591.67 | 9532.08 | 0 | -2844.8 | 1333372.66 | 0 | 1333372.66 | 0 | [6 empty] | CM_M&G | 100%
501822 | Dean Street Stewarton - Pipe Bridge replace pipework | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2017-05-30 | 2020-08-24 | 2020-11-30 | 2021-03-04 | 2021-03-05 | East Ayrshire | 0 | 0 | 6296.59 | 1860.82 | 125.79 | 1186.49 | 29090.38 | 38560.07 | 904.98 | 39465.05 | 0 | [6 empty] | CM_WWI | 100%
504962 | Deanston WWTW - Major Mechanical refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-01-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 40000 | 0 | [6 empty] | CM_WWNI | 100%
502629 | Dechmont WSZ - A89 trunk main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-04-13 | 2022-02-28 | 2022-05-11 | 2022-12-12 | 2023-03-14 | East Lothian | 0 | 0 | 18070.09 | 7703.23 | 12626.68 | 0 | 0 | 38400 | 761600.04 | 800000.04 | 0 | [6 empty] | CM_WSI | 100%
502225 | Denholm WWTW Access Road | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2016-06-13 | 2016-08-30 | 2016-09-12 | 2017-01-10 | 2017-05-05 | Scottish Borders | 0 | 0 | 942638.79 | 48186 | 0 | -628.12 | 0 | 990196.67 | 0 | 990196.67 | 0 | [6 empty] | CM_M&G | 100%
403406 | Denny Difgen | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-03-28 | 2013-03-28 | Stirling | 1007399.77 | 32228.23 | 52411 | 14528.79 | 0 | 0 | 0 | 99168.02 | 0 | 1106567.79 | 2947 | [6 empty] | CC1W | 100%
30196 | Denny STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-02-09 | 2010-11-15 | 2010-11-16 | 2011-07-27 | 2011-09-13 | Falkirk | 503650.63 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 503658.13 | 0 | [6 empty] | EC01A | 26.53% | CM_WWNI | 73.47%
500699 | Dervaig WOA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-11 | 2015-08-13 | 2015-08-25 | 2016-04-29 | 2016-04-29 | Argyll and Bute-North Argyll | 0 | 432864 | 578.74 | -892.54 | 0 | 0 | 0 | 432550.2 | 0 | 432550.2 | 0 | [6 empty] | CM_WSI | 100%
36801 | Designated Site W-Bridge Bridge Scoping Works | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-01-30 | 2010-01-26 | 2010-02-05 | 2010-07-21 | 2010-07-21 | Falkirk | 717171.38 | 288.8 | 0 | 0 | 0 | 0 | 0 | 288.8 | 0 | 717460.18 | 0 | [6 empty] | DW9 | 100%
403070 | Desktop Refresh Project IT Enablement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-11-07 | 2014-06-11 | 2014-06-11 | 2016-12-15 |  | Scottish Water Wide | 8318677 | 192753 | 176015.03 | -5005.04 | 0 | 0 | 0 | 363762.99 | 0 | 8682439.99 | 0 | [6 empty] | CM_M&G | 100%
501549 | Develop and Retrofit Attenuation Roof Drainage Study | Q&S4 | Reducing flooding and pollution from sewers | Surface Water |  |  | Wastewater |  | SWD | Surface Water | MS7 | 2015-12-23 | 2015-12-23 | 2015-12-31 | 2017-02-08 | 2017-03-01 | Scottish Water Wide | 0 | 14746 | 18147.06 | -2427.56 | 0 | 0 | 0 | 30465.5 | 0 | 30465.5 | 44865.02 | [6 empty] | CS15C | 100%
402381 | Developer Connections Improvement Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-06 | 2012-03-13 | 2012-03-13 | 2014-12-03 |  | Scottish Water Wide | 7392794 | -2824.02 | 0 | 0 | 0 | 0 | 0 | -2824.02 | 0 | 7389969.98 | 0 | [6 empty] | CM_M&G | 100%
503071 | Developer Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-07-12 | 2019-01-21 | 2019-01-21 | 2020-05-01 | 2020-05-04 | Scottish Water Wide | 0 | 0 | 0 | 52065.37 | 4676726.47 | 4516432.2 | 337775.65 | 9582999.69 | 0 | 9582999.69 | 0 |  |  |  |  | 169000 |  | CM_M&G | 100%
34299 | Developer Services - Wastewater - Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Aberdeen City | 1449470.45 | -8222.3 | 0 | 0 | 0 | 0 | 0 | -8222.3 | 0 | 1441248.15 | 0 | [6 empty] | SG2 | 100%
34283 | Developer Services - Wastewater - Dumfries & Galloway | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Dumfries and Galloway | 1483009.38 | 0 | 0 | 50 | -50 | 0 | 0 | 0 | 0 | 1483009.38 | 0 | [6 empty] | SG2 | 100%
34310 | Developer Services - Wastewater - Fife | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Fife | 5101908.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5101908.73 | 0 | [6 empty] | SG2 | 100%
34302 | Developer Services - Wastewater - Highland | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Highland | 3062146.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3062146.64 | 0 | [6 empty] | SG2 | 100%
34295 | Developer Services - Wastewater - North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | North Lanarkshire | 5552571.17 | 0 | 15245.45 | -15245.45 | 0 | 0 | 0 | 0 | 0 | 5552571.17 | 0 | [6 empty] | SG2 | 100%
34298 | Developer Services - Wastewater - South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | South Lanarkshire | 4101443.71 | 0 | 0 | 0 | 53.23 | -53.23 | 0 | 0 | 0 | 4101443.71 | 0 | [6 empty] | SG2 | 100%
34261 | Developer Services - Water - Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Aberdeenshire | 2362342.39 | 0 | 0 | 15 | -15 | 0 | 0 | 0 | 0 | 2362342.39 | 0 | [6 empty] | WG2 | 100%
33782 | Developer Services - Water - Argyll & Bute | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Argyll and Bute | 77914.14 | 0 | 723 | 0 | -723 | 0 | 0 | 0 | 0 | 77914.14 | 0 | [6 empty] | WG2 | 100%
33776 | Developer Services - Water - Borders | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Scottish Borders | 535758.6 | 50.87 | -50.87 | -0.01 | 0.01 | 0 | 0 | 0 | 0 | 535758.6 | 0 | [6 empty] | WG2 | 100%
33777 | Developer Services - Water - Dumfries & Galloway | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Dumfries and Galloway | 532969.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532969.39 | 0 | [6 empty] | WG2 | 100%
34270 | Developer Services - Water - Falkirk | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Falkirk | 942078.55 | 52.84 | -52.84 | 0 | 0 | 0 | 0 | 0 | 0 | 942078.55 | 0 | [6 empty] | WG2 | 100%
34271 | Developer Services - Water - Fife | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Fife | 1937816.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937816.48 | 0 | [6 empty] | WG2 | 100%
33786 | Developer Services - Water - Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Glasgow City | 1679396.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679396.48 | 0 | [6 empty] | WG2 | 100%
34263 | Developer Services - Water - Highland | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Highland | 1431260.07 | -233.26 | 0 | 0 | 0 | 0 | 0 | -233.26 | 0 | 1431026.81 | 0 | [6 empty] | WG2 | 100%
33789 | Developer Services - Water - North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | North Lanarkshire | 1247591.02 | 0 | 0 | 0.39 | -0.39 | 0 | 0 | 0 | 0 | 1247591.02 | 0 | [6 empty] | WG2 | 100%
402094 | Developing the QSIV Investment Plan | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-31 | 2011-08-29 | 2011-09-06 | 2016-01-30 |  | Scottish Water Wide | 3436890.58 | 519210.42 | -7982.66 | 0 | 0 | 0 | 7982.79 | 519210.55 | 0 | 3956101.13 | 0 | [6 empty] | QS4EQS | 50% | QS4EQW | 50%
500508 | Development of a National Substance Strategy (PSD) | Q&S4 | Protecting and enhancing the environment | Priority Substances Directive |  |  | Wastewater |  | SWMD | Priority Substances Directive | MS5 | 2015-06-02 | 2015-09-18 | 2015-09-18 | 2020-01-27 | 2020-03-12 | Scottish Water Wide | 0 | 458869 | 681131 | 485000 | 222501.64 | 125908.46 | 60378.9 | 2033789 | 0 | 2033789 | 2958548.45 | [6 empty] | EC23A | 100% | bar: Regulatory Outputs OMG-25
500706 | Development of Renewable Energy Projects | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWD | Renewable power | MS5 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 366968.14 | 176715.18 | 170867.12 | 226449.56 | 63367.47 | -22867.47 | 981500 | 218500 | 1200000 | 832227.31 | [6 empty] | I2S_WI | 100% | [18 empty] | Regulatory Outputs OMG-43: 4.227
500666 | DG2401 High St Gatehouse of Fleet | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-05-09 | 2019-05-09 | Dumfries and Galloway | 0 | 79001 | 6405.19 | 30848.92 | -116254.11 | 0 | 0 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
501569 | Dhu Loch WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2016-08-26 | 2016-08-29 | 2019-02-28 | 2019-12-31 | Argyll and Bute-Cowal & Bute | 0 | 65.42 | 1268.97 | 40.43 | 1383.85 | 559.78 | -559.78 | 2758.67 | 0 | 2758.67 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
505059 | Dhu Loch WTW - inlet flash mixer No1 replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2021-03-31 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 120.7 | 1724.28 | 1844.98 | 0 | 1844.98 | 0 | [6 empty] | CM_WSNI | 100%
502649 | Dhu Loch_Argyll and Bute_THM Research and Investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-02-27 | 2020-01-31 | 2020-03-23 | 2022-01-31 | 2022-04-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 38519.49 | 300045.5 | 1454006.01 | 4852518.97 | 6645089.97 | -9024.97 | 6636065 | 2549769.68 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500070 | DI - Meter Verification | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-02-27 | 2015-04-01 | 2015-04-01 | 2017-06-19 | 2017-06-19 | Scottish Water Wide | 0 | 69516 | 102084.13 | -4846.61 | 0 | 0 | 0 | 166753.52 | 0 | 166753.52 | 0 | [6 empty] | CM_WSI | 100%
500069 | DI - Replacement Meters Verification Chambers Bypasses and Redundant DI Site Tidy Up | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-03-18 | 2015-04-20 | 2015-06-19 | 2021-07-05 | 2021-10-05 | Scottish Water Wide | 0 | 457723 | 416289.3 | 531464.32 | 1726519.73 | 925966.88 | 116509.85 | 4174473.08 | 24526.92 | 4199000 | 0 | [6 empty] | CM_WSI | 100%
500071 | DI - Reporting & Zone Hosting | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-24 | 2015-03-24 | 2021-05-12 | 2021-05-12 | Scottish Water Wide | 0 | 133771 | 131429 | 112618.74 | 119900.18 | 122571.48 | 129509.6 | 749800 | 0 | 749800 | 0 | [6 empty] | CM_WSI | 100%
400799 | DI Meter Verification Chambers SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-30 | 2010-08-02 | 2015-09-30 |  | Scottish Water Wide | 1949140 | 12539.98 | 0 | 0 | 0 | 0 | 0 | 12539.98 | 0 | 1961679.98 | 0 | [6 empty] | CM_WSI | 100%
502399 | DI Meter Verification Program | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-11-29 | 2016-11-29 | 2017-03-15 | 2021-05-12 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 15983.03 | 94168.97 | 135798.91 | 137648.1 | 130500 | 514099.01 | 0 | 514099.01 | 0 | [6 empty] | CM_WSI | 100%
400763 | DI SYSTEMS REPORTING - ZONE HOSTING SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-06-08 |  | Scottish Water Wide | 671126.59 | -1226 | 0 | 0 | 0 | 0 | 0 | -1226 | 0 | 669900.59 | 0 | [6 empty] | CM_WSI | 100%
502836 | Diabeg WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-10-20 | 2034-02-17 | 2035-02-14 | 2035-05-17 | Highland | 0 | 0 | 0 | 21346.13 | 0 | -20630.78 | 0 | 715.35 | 0 | 715.35 | 136478.56 | [6 empty] | WG1 | 100%
46833 | Diabeg WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-10 | 2011-06-21 | 2011-10-24 | 2011-12-07 | Highland | 40031.2 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 40061.92 | 0 | [6 empty] | DW13 | 100%
403556 | Digital Platform - Asset Tagging & Data Cleanse Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-10-11 | 2014-01-14 | 2014-01-14 | 2015-12-01 |  | Scottish Water Wide | 1439810 | -82934.47 | 0 | 0 | 0 | 0 | 0 | -82934.47 | 0 | 1356875.53 | 0 | [6 empty] | CM_M&G | 100%
505064 | Dingwall WwTW - Decant pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | [6 empty] | CM_WWNI | 100%
505789 | DIR North CM Loch an Duin Spillway and Scour | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS2 |  | 2020-03-24 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2633.29 | 37366.72 | 40000.01 | 0 | 40000.01 | 821666.8 | [6 empty] | CS22 | 100%
505928 | DIR North CM Skye Maintenance 2020 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS2 |  | 2020-04-01 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 0 | 35000 | 821666.8 | [6 empty] | CS22 | 100%
505414 | Discontinuance of Loch Craisg | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-03-04 | 2020-10-08 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 394.67 | 74605.33 | 75000 | 0 | 75000 | 821666.8 | [6 empty] | CS22 | 100%
505415 | Discontinuance of Loch Crocach | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-03-04 | 2020-10-08 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 11448.6 | 163551.4 | 175000 | 0 | 175000 | 821666.8 | [6 empty] | CS22 | 100%
505412 | Discontinuance of Loch Mor | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-03-04 | 2020-10-08 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 40000 | 821666.8 | [6 empty] | CS22 | 100%
503621 | Disinfection Improvements - Delivery of High Priority Significant Improvements Ph 1 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-08-29 | 2021-07-05 | 2021-09-27 | 2023-03-10 | 2023-05-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 32930.68 | 701851.52 | 734782.2 | 15868217.72 | 16602999.92 | 1027811.08 | [6 empty] | DW25P | 100%
503423 | Disinfection Improvements - Development of High Priority Significant Improvements Group 1 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-02-07 | 2019-04-30 | 2019-05-15 | 2021-10-25 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 43733.65 | 142771.08 | 335988.88 | 522493.61 | 110004.64 | 632498.25 | 1577402.67 | [6 empty] | DW25P_ID | 100%
503623 | Disinfection Improvements - Development of High Priority Significant Improvements Group 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-08-26 | 2020-02-26 | 2020-02-26 | 2021-08-10 | 2021-08-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 69016.67 | 703011.15 | 772027.82 | 47972.21 | 820000.03 | 250727.71 | [6 empty] | DW25P | 100%
8488 | Disposals | Q&S2 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS4 |  |  |  | 2004-03-31 |  | Scottish Water Wide | -7365.25 | 0 | 0 | 0 | 983.96 | -251 | 0 | 732.96 | 0 | -6632.29 | 0 | [6 empty] | WM3 | 100%
45127 | Distribution Water Quality Rehab - Afton RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2009-03-24 | 2010-09-14 | 2010-10-18 | 2016-11-30 | 2017-03-31 | All West Unitary Authorities | 6251083.65 | 104516.65 | 189117.24 | 68991.88 | 40264.33 | 181269.14 | 3730.86 | 587890.1 | 0 | 6838973.75 | 38317.76 | [6 empty] | CM_WSI | 38.37% | DW5 | 61.63% | bar: Regulatory Outputs OMG-03
45132 | Distribution Water Quality Rehab - Ashgrove RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-30 | 2012-09-24 | 2014-10-27 | 2014-12-19 | North Ayrshire | 2638525 | 0 | 583.11 | 0 | 0 | 0 | 160 | 743.11 | 0 | 2639268.11 | 1816.93 | [6 empty] | CM_WSI | 5.24% | DW5 | 94.76%
45145 | Distribution Water Quality Rehab - Blairlinnans North RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-08-16 | 2011-05-19 | 2011-09-08 | 2012-06-27 | West Dunbartonshire | 224125.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224125.02 | 0 | [6 empty] | DW5 | 100%
45151 | Distribution Water Quality Rehab - Burncrooks RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-12-24 | 2011-03-31 | 2015-12-10 | 2015-12-10 | West Dunbartonshire | 2664465.4 | -269374.4 | -1252.74 | -14592.1 | 15588.26 | 195.78 | -195.78 | -269630.98 | 0 | 2394834.42 | 94791.2 | [6 empty] | CM_WSI | 30% | DW5 | 70%
404130 | Distribution Water Quality Rehab - Burncrooks RSZ - Transfer Project | Q&S3B | Completion | Non OMG180 |  |  | Water |  | WINF | Non OMG180 | MS6 | 2015-08-26 | 2016-12-20 | 2017-02-06 | 2018-03-31 | 2019-03-31 | West Dunbartonshire | 0 | 5209 | 117704 | 449809 | -52608.34 | 3445.83 | 0 | 523559.49 | 0 | 523559.49 | 0 | [6 empty] | CM_WSI | 1.347% | DW5 | 98.65% | bar: Regulatory Outputs OMG-03
45155 | Distribution Water Quality Rehab - Carron Valley A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-10-15 | 2015-08-31 | 2016-08-31 | Falkirk | 3804649 | 176790 | 17935.94 | -1399.27 | 0 | 0 | 0 | 193326.67 | 0 | 3997975.67 | 218881.51 | [6 empty] | CM_WSI | 15.35% | DW5 | 84.65% | bar: Regulatory Outputs OMG-03
45160 | Distribution Water Quality Rehab - Corsehouse RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-31 | 2013-05-13 | 2014-07-24 | 2015-06-23 | North Ayrshire | 1533921.62 | 4112.84 | 35.5 | 0 | 0 | 0 | 0 | 4148.34 | 0 | 1538069.96 | 1394.04 | [6 empty] | CM_WSI | 44.61% | DW5 | 55.39%
45163 | Distribution Water Quality Rehab - Daer A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-09-17 | 2016-03-31 | 2017-04-30 | South Lanarkshire | 4236875 | 611992 | 56682.7 | 23881 | -2673.9 | 0 | 0 | 689881.8 | 0 | 4926756.8 | 43297.57 | [6 empty] | CM_WSI | 32.12% | DW5 | 67.88% | bar: Regulatory Outputs OMG-03
45165 | Distribution Water Quality Rehab - Daer Camps RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-08-20 | 2015-03-31 | 2015-03-31 | South Lanarkshire | 1346759.31 | 24793.57 | -39.53 | 0 | 0 | 0 | 0 | 24754.04 | 0 | 1371513.35 | 10808.76 | [6 empty] | CM_WSI | 41.77% | DW5 | 58.23%
46921 | Distribution Water Quality Rehab - Dougliehill RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-09-22 | 2010-10-25 | 2011-07-27 | 2013-02-28 | Inverclyde | 1470427 | -4096 | -208733.04 | 0 | 0 | 0 | 0 | -212829.04 | 0 | 1257597.96 | 11674.59 | [6 empty] | CM_WSI | 20.26% | DW5 | 79.74%
45173 | Distribution Water Quality Rehab - Fairmilehead A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-09-09 | 2010-09-20 | 2012-05-15 | 2015-03-30 | City of Edinburgh | 770298 | -1421 | 0 | 0 | 0 | 0 | 0 | -1421 | 0 | 768877 | 1245.58 | [6 empty] | CM_WSI | 16.96% | DW5 | 83.04%
45179 | Distribution Water Quality Rehab - Gartcarron RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-10-15 | 2016-12-31 | 2018-03-31 | Stirling | 2271787.36 | 1222345.64 | 847483.74 | 545021.88 | 85549.44 | 44469.07 | -18364.12 | 2726505.65 | 0 | 4998293.01 | 230536.61 | [6 empty] | DW5 | 45.59% | CM_WSI | 54.41% | bar: Regulatory Outputs OMG-03
46935 | Distribution Water Quality Rehab - Glassford RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2012-05-21 | 2012-08-06 | 2014-09-17 | 2015-02-17 | South Lanarkshire | 151575 | -550.59 | 0 | 0 | 0 | 0 | 3 | -547.59 | 0 | 151027.41 | 2266.2 | [6 empty] | DW5 | 43% | CM_WSI | 57%
45186 | Distribution Water Quality Rehab - Greenock RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-30 | 2012-08-20 | 2014-12-01 | 2016-11-30 | Inverclyde | 3419495 | 0 | -32448.31 | 0 | 0 | 0 | 324.5 | -32123.81 | 0 | 3387371.19 | 362.93 | [6 empty] | DW5 | 5.929% | CM_WSI | 94.07%
46937 | Distribution Water Quality Rehab - Kaim Lochwinnoch RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-10-11 | 2011-04-22 | 2017-01-31 | 2017-03-31 | Renfrewshire | 1561928 | 0 | 0.37 | -53466.09 | 0 | 0 | 1440.63 | -52025.09 | 0 | 1509902.91 | 12057.35 | [6 empty] | DW5 | 43.36% | CM_WSI | 56.64% | bar: Regulatory Outputs OMG-03
46172 | Distribution Water Quality Rehab - Kirbister Orkney RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS3 | 2009-03-24 | 2012-10-31 | 2013-05-06 | 2021-06-30 | 2021-10-31 | Orkney Islands | 3792639 | 986828 | 127646.49 | 213229.99 | 10270.64 | 241385.88 | 604454 | 2183815 | 4160 | 5980614 | 475091.89 | [6 empty] | DW5 | 42.53% | CM_WSI | 57.47% | bar: Regulatory Outputs OMG-03
45197 | Distribution Water Quality Rehab - Lintrathen RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-09-14 | 2011-04-14 | 2015-03-31 | 2015-12-31 | Shetland Islands | 997307 | 18158 | -57.62 | 0 | 0 | 0 | 0 | 18100.38 | 0 | 1015407.38 | 10352.43 | [6 empty] | CM_WSI | 42% | DW5 | 58% | bar: Regulatory Outputs OMG-03
45200 | Distribution Water Quality Rehab - Mannofield South RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-10-31 | 2013-02-18 | 2015-08-31 | 2016-02-29 | Aberdeen City | 5033316 | -7124 | -0.16 | -3901.49 | 0 | 0 | 0 | -11025.65 | 0 | 5022290.35 | 95759.64 | [6 empty] | CM_WSI | 26% | DW5 | 74% | bar: Regulatory Outputs OMG-03
45201 | Distribution Water Quality Rehab - Marchbank A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-08-16 | 2011-08-15 | 2013-12-11 | 2014-03-28 | West Lothian | 1698138 | -283.69 | -79.06 | 0 | 0 | 0 | 0 | -362.75 | 0 | 1697775.25 | 1547.52 | [6 empty] | CM_WSI | 38% | DW5 | 62%
45211 | Distribution Water Quality Rehab - Muirdykes RSZ - Phase 1 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2011-09-30 | 2011-09-30 | 2013-03-29 | 2014-02-17 | Renfrewshire | 3709218.83 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 3709219.38 | 0 | [6 empty] | CM_WSI | 31.93% | DW5 | 68.07%
45217 | Distribution Water Quality Rehab - Penwhirn RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-03-24 | 2010-08-16 | 2010-09-06 | 2012-02-23 | 2014-02-17 | Dumfries and Galloway | 3349210.88 | 0 | -96098.51 | 0 | 0 | 0 | 96098.51 | 0 | 0 | 3349210.88 | 0 | [6 empty] | DW5 | 39% | CM_WSI | 61%
46923 | Distribution Water Quality Rehab - Rawburn RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-08-16 | 2010-09-27 | 2015-03-24 | 2016-03-31 | Scottish Borders | 4779276 | 45890 | -189436.84 | 5229.5 | 0 | 0 | 0 | -138317.34 | 0 | 4640958.66 | 36476.67 | [6 empty] | DW5 | 48.81% | CM_WSI | 51.19%
45223 | Distribution Water Quality Rehab - Roberton RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-08-16 | 2011-02-22 | 2013-01-08 | 2014-05-15 | Scottish Borders | 2202529.46 | 0 | 0 | 0 | 34496.31 | -51744.46 | 17248.15 | 0 | 0 | 2202529.46 | 0 | [6 empty] | CM_WSI | 45.67% | DW5 | 54.33%
45228 | Distribution Water Quality Rehab - Spynie RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-10-11 | 2011-01-10 | 2012-12-19 | 2013-03-27 | Moray | 4737473 | -723.66 | 0 | 0 | 0 | 0 | 1.17 | -722.49 | 0 | 4736750.51 | 980 | [6 empty] | CM_WSI | 23.62% | DW5 | 76.38%
500077 | DMA FLA - DMA Leak Detection Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-09 | 2015-03-25 | 2015-03-25 | 2021-05-04 | 2021-05-04 | Scottish Water Wide | 0 | 280000 | 245000 | 208138 | 241224 | 204582 | 210058 | 1389002 | 0 | 1389002 | 0 | [6 empty] | CM_WSI | 100%
500076 | DMA FLA - DMA Meter Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-04-28 | 2021-04-28 | Scottish Water Wide | 0 | 420000 | 417476.54 | 389816.46 | 430256.81 | 488165.19 | 272214 | 2417929 | 0 | 2417929 | 0 | [6 empty] | CM_WSI | 100%
500072 | DMA FLA - DMA Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-05-12 | 2021-05-12 | Scottish Water Wide | 0 | 664230.74 | 835769.26 | 535148 | 912187.63 | 685355.37 | 636123 | 4268814 | 0 | 4268814 | 0 | [6 empty] | CM_WSI | 100%
500073 | DMA FLA - DMA-FLA Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-04-28 | 2021-04-28 | Scottish Water Wide | 0 | 540000 | 610000 | 445035 | 436250 | 401593 | 447468 | 2880346 | 0 | 2880346 | 0 | [6 empty] | CM_WSI | 100%
500078 | DMA Optimisation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-26 | 2015-03-26 | 2015-03-26 | 2021-04-28 | 2021-04-28 | Scottish Water Wide | 0 | 245000 | 10000 | 46823 | 14527 | 26293 | 48130 | 390773 | 0 | 390773 | 0 | [6 empty] | CM_WSI | 100%
503689 | Dodside Pumping Station Air conditioning | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MSU | 2020-02-03 | 2021-01-04 | 2021-04-28 | 2021-09-07 | 2021-10-29 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 4901.77 | 23028.23 | 27930 | 42070 | 70000 | 753145.45 | [6 empty] | CS12 | 100%
501530 | Dodside SR Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-07 | 2030-01-11 | 2030-08-28 | 2030-11-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633253.01 | 633253.01 | 0 | [6 empty] | CM_WSNI | 100%
46410 | Dodside SR Refurb - TWS000252 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-19 | 2011-12-29 | 2011-12-19 |  | Glasgow City | 58082.24 | -517.53 | 0 | 0 | 0 | 0 | 0 | -517.53 | 0 | 57564.71 | 0 | [6 empty] | CM_WSNI | 100%
502929 | Doms Documentation Refresh | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2018-05-25 | 2018-05-25 | Scottish Water Wide | 0 | 0 | 0 | 93355.75 | 36953.35 | 0 | 0 | 130309.1 | 0 | 130309.1 | 0 | [6 empty] | CM_M&G | 100%
401215 | Don Cluster 1 - Scalloway to Tingwall | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2013-02-28 | 2013-03-20 | 2013-12-03 |  | Shetland Islands | 544688 | -496.83 | 0 | 0 | 0 | 0 | 0 | -496.83 | 0 | 544191.17 | 0 | [6 empty] | CM_WSI | 100%
501049 | Don Large Middle Ground Scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-10-05 | 2016-09-22 | 2017-03-20 | 2018-03-26 | 2018-03-26 | Aberdeen City | 0 | 22441 | 75432.21 | 205354.85 | 12275.11 | 572.47 | 1850.43 | 317926.07 | 77.1 | 318003.17 | 0 | [6 empty] | CM_WSI | 100%
400095 | Dornoch UID Improvements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2012-12-07 | 2013-01-17 | 2013-06-03 | 2013-09-18 | Highland | 295059 | -1471.84 | 0 | 0 | 0 | 0 | 0 | -1471.84 | 0 | 293587.16 | 0 | [6 empty] | EC03B | 100%
502273 | Dougliehill and Greenock WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS2 | 2018-09-17 | 2020-03-27 | 2020-08-24 | 2021-01-31 | 2021-03-31 | Inverclyde | 0 | 0 | 8916.28 | 0 | 12155.73 | 42774.8 | 211233.01 | 275079.82 | 814.14 | 275893.96 | 0 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
501573 | Dougliehill WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2017-01-20 | 2017-03-20 | 2017-03-20 | 2020-10-31 | 2020-12-31 | Inverclyde | 0 | 3348.84 | 522.86 | -55.04 | 833.51 | 0 | 0 | 4650.17 | 0 | 4650.17 | 182982.34 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
45559 | Doune STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2012-06-11 | 2012-08-08 | 2013-03-22 | 2013-03-22 | Stirling | 626942.67 | -9.29 | 0 | 0 | 0 | 0 | 0 | -9.29 | 0 | 626933.38 | 998.39 | [6 empty] | CM_WWNI | 10% | WQ01 | 90%
500250 | Doune to Callander Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-04-20 | 2021-10-25 | 2021-11-08 | 2022-09-27 | 2023-06-19 | Stirling | 0 | 67869 | 102191 | -72633 | 117343.48 | 0 | 0 | 214770.48 | 2835499.77 | 3050270.25 | 0 | [6 empty] | CM_WSI | 100%
502822 | Doune WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Falkirk | 0 | 0 | 0 | 81094.05 | 931.2 | 0 | -690.94 | 81334.31 | 0 | 81334.31 | 136478.56 | [6 empty] | SG1 | 100%
500726 | Dovecot Park Aberdour Relay SW Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-09-07 | 2016-03-25 | 2016-06-20 | 2016-09-28 | 2016-09-28 | Fife | 0 | 12476.17 | 91182.83 | 0 | 956.11 | 0 | 0.89 | 104616 | 0 | 104616 | 0 | [6 empty] | CM_WWI | 100%
403945 | DR & Business Continuity | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-03 | 2015-06-30 | 2015-06-30 | 2015-06-30 |  | Scottish Water Wide | 246316 | 11479.29 | 0 | 0 | 0 | 0 | 0 | 11479.29 | 0 | 257795.29 | 0 | [6 empty] | CM_M&G | 100%
45324 | Drimnin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2013-03-18 | 2013-09-06 | Highland | 299550.24 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 299549.24 | 0 | [6 empty] | DW13 | 100%
401315 | Drongan STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-30 | 2012-02-21 | 2012-06-18 | 2015-01-27 | 2015-02-10 | South Ayrshire | 2911721.34 | 5831.36 | 2633.52 | 5 | 0 | 0 | 0 | 8469.88 | 0 | 2920191.22 | 218124 | [6 empty] | CM_WWNI | 19.99% | EC04A | 80.01%
503543 | Drongan WwTW Bathing Water Improvement | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | WWINF | Revised Bathing Waters Directive | MS1 | 2019-07-09 | 2020-05-18 | 2020-07-27 | 2021-02-18 | 2021-05-26 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 312131.84 | 3216338.84 | 3528470.68 | 47762.33 | 3576233.01 | 2277461.36 | [6 empty] | EC16B | 100%
503627 | Drought Operations - North Area 2019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2019-08-13 | 2019-08-13 | 2019-09-10 | 2020-03-25 | 2020-04-01 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 188074.31 | 0.01 | 188074.32 | 0 | 188074.32 | 0 | [6 empty] | CM_WSNI | 100%
500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS3 | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-09-14 | 2020-09-15 | Scottish Water Wide | 0 | 83503.85 | 60196.32 | 58417.52 | 82781.6 | 111629.18 | 354643.88 | 751172.35 | 0 | 751172.35 | 640245.27 | [6 empty] | WR7 | 100%
500056 | Drought Resilience - Improved Hydrological Information | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS3 | 2016-01-12 | 2016-05-18 | 2016-05-20 | 2020-12-14 | 2021-03-22 | Scottish Water Wide | 0 | 55970 | 146030 | 101000 | 104400 | 121386.43 | 119483.74 | 648270.17 | 1729.83 | 650000 | 530117.3 | [6 empty] | WG4A | 100%
500669 | Drought Resilience Improved Hydrological Information Bathymetry Surveys | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2015-07-15 | 2015-08-31 | 2015-10-05 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 117700 | 253028.76 | 479202.4 | 0 | 0 | 0 | 849931.16 | 0 | 849931.16 | 530117.3 | [6 empty] | WG4A | 100%
500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS3 | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-12-18 | 2021-03-22 | Scottish Water Wide | 0 | 29053.58 | 9978.47 | 37004.15 | 9049.99 | 63086.82 | 216174.3 | 364347.31 | 6743.72 | 371091.03 | 530117.3 | [6 empty] | WG4A | 100%
502968 | Drum Sewer Infiltration | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-08-10 | 2021-06-11 | 2021-09-06 | 2022-04-08 | 2022-07-11 | Perth and Kinross | 0 | 0 | 0 | 8263.62 | 4696.21 | 34798.12 | 71285.06 | 119043.01 | 262157 | 381200.01 | 0 | [6 empty] | SR21_WW | 100%
502259 | Drum WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-19 | 2016-09-29 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG1 | 100%
502842 | Drumbeg WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2027-04-02 | 2033-10-20 | 2034-02-17 | 2020-03-31 | 2035-05-17 | Highland | 0 | 0 | 0 | 20930.23 | 2492.6 | -17415.56 | 0.01 | 6007.28 | 0 | 6007.28 | 136478.56 | [6 empty] | WG1 | 100%
46848 | Drumfearn WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-02-28 | 2011-06-06 | 2013-03-22 | 2013-11-21 | Highland | 768115.59 | 669.83 | 0 | 0 | 0 | 0 | 0 | 669.83 | 0 | 768785.42 | 0 | [6 empty] | DW23 | 100%
502759 | Drumlithie WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-05-23 | 2019-05-23 | Aberdeenshire | 0 | 0 | 0 | 53034.17 | 56265.15 | -21862.51 | -363.79 | 87073.02 | 0 | 87073.02 | 136478.56 | [6 empty] | SG1 | 100%
502332 | Drumnadrochit WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-12-18 | 2021-02-25 | 2021-06-02 | 2022-05-12 | 2022-07-06 | Highland | 0 | 0 | 21363.18 | 6387.56 | 25217.76 | 45696.1 | 167413.56 | 266078.16 | 957857.86 | 1223936.02 | 136478.56 | [6 empty] | SG1 | 100%
400738 | Drumoak WwTP Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-09-21 | 2012-01-23 | 2012-05-04 | 2013-02-20 | 2013-02-20 | Aberdeenshire | 502604 | -5891.95 | 0 | 0 | 0 | 0 | 0 | -5891.95 | 0 | 496712.05 | 0 | [6 empty] | CM_WWNI | 14.6% | SG1 | 85.4%
403911 | Drumoak-Banchory Strategic Water Mains Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 2016-09-08 | 2016-09-08 | Aberdeenshire | 1165662.55 | 0 | 1601.53 | 0 | 0 | 0 | 1601.53 | 3203.06 | 0 | 1168865.61 | 0 | [6 empty] | WG5 | 100%
500679 | Drumore Road Killearn | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-01-21 | 2019-01-21 | Stirling | 0 | 121951 | -28962.9 | 26026.61 | -119013.71 | 0 | 0 | 1 | 0 | 1 | 45708.96 | [6 empty] | CS11 | 100%
505096 | Drumossie Meter chamber investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-12 | 2020-08-13 | 2021-04-02 | 2021-04-30 | Highland | 0 | 0 | 0 | 0 | 0 | 890.02 | 3903.49 | 4793.51 | 206.48 | 4999.99 | 0 | [6 empty] | WSI | 100%
503526 | Drymen WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2020-04-01 | 2020-04-06 | 2020-04-13 | 2020-04-09 | 2020-04-10 | Stirling | 0 | 0 | 0 | 0 | 59441.86 | 26515.88 | 11821.81 | 97779.55 | 0 | 97779.55 | 136478.56 | [6 empty] | SG1 | 100%
505388 | DSEAR Amlaird WTW PAC Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-28 |  |  |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 44.12 | 39955.88 | 40000 | 0 | 40000 | 0 | [6 empty] | WSNI | 100%
503592 | DSEAR Compliance (Desktop) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2019-06-28 | 2019-06-28 | 2020-03-16 | 2024-03-27 | 2024-06-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1026699.76 | 570719.45 | 1597419.21 | 2402580.92 | 4000000.13 | 0 | [6 empty] | CM_M&G | 100%
503278 | Dufftown WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-18 | 2023-08-01 | 2023-12-04 | 2024-11-29 | 2025-03-03 | Moray | 0 | 0 | 0 | 0 | 78150.66 | 9577.52 | 39618.42 | 127346.6 | 872653.38 | 999999.98 | 136478.56 | [6 empty] | SG1 | 100%
501355 | Dufftown WWTW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-22 | 2016-10-13 | 2016-10-10 | 2016-09-28 | 2016-09-28 | Moray | 0 | 378.72 | 3835.28 | -115.21 | 0 | 0.38 | -0.17 | 4099 | 0 | 4099 | 0 | [6 empty] | CM_WWI | 100%
501716 | Dumbarton Road Glasgow - Clean out sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2017-03-29 | 2018-08-28 | 2018-09-24 | 2019-09-30 | 2019-09-30 | Glasgow City | 0 | 0 | 4171 | 16019 | 147347 | 55682 | 0 | 223219 | 0 | 223219 | 0 | [6 empty] | CM_WWI | 100%
502901 | Dumfries and Galloway - Area Strategy Study | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2018-08-23 | 2018-02-27 | 2019-06-24 | 2020-04-30 | 2020-07-17 | Dumfries and Galloway | 0 | 0 | 0 | 17156.64 | 90581.25 | 87663.67 | 3972.43 | 199373.99 | 0 | 199373.99 | 136478.56 | [6 empty] | SG1 | 100%
500924 | Dumfries and Galloway Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-08-11 | 2017-08-11 | 2017-07-18 | 2017-07-18 | Dumfries and Galloway | 0 | 7000 | 1000 | -897 | 0 | 0 | 0 | 7103 | 0 | 7103 | 120964.87 | [6 empty] | CS15A | 100%
502218 | Dumfries Garroch Loaning Wastewater Pump Station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2016-09-29 | 2016-09-29 | 2017-03-07 | 2020-08-25 | 2020-08-26 | Dumfries and Galloway | 0 | 0 | 23282.36 | 29.76 | 0 | 232635.29 | 98052.6 | 354000.01 | 0 | 354000.01 | 0 | [6 empty] | CM_WWNI | 100%
502962 | Dumfries Loganbarns - Storm Pumps-MCC Construction Design Package | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2018-04-20 | 2018-04-20 | 2018-08-23 | 2020-01-04 | 2020-04-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 179111.53 | 235794.91 | 9438.03 | 424344.47 | 2069.36 | 426413.83 | 0 | [6 empty] | CM_WWNI | 100%
402035 | Dunbar New TWS | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2011-05-26 | 2012-12-19 | 2013-01-21 | 2014-04-30 | 2014-04-30 | East Lothian | 1655701.16 | 2080.84 | -426.2 | 0 | 0 | 0 | 0 | 1654.64 | 0 | 1657355.8 | 0 | [6 empty] | CM_WSNI | 50% | WG5 | 50%
502331 | Dunbar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-06-08 | 2022-11-07 | 2023-03-02 | 2024-02-23 | 2024-05-27 | East Lothian | 0 | 0 | 31014.87 | 6183.27 | 3814.71 | 97634.1 | 70556.85 | 209203.8 | 2890696.28 | 3099900.08 | 136478.56 | [6 empty] | SG1 | 100%
504528 | Dunbar WWTW Incident | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-01-10 | 2020-06-22 | 2020-07-06 | 2021-01-28 | 2021-01-28 | East Lothian | 0 | 0 | 0 | 0 | 0 | 750000 | 300000 | 1050000 | 0 | 1050000 | 0 | [6 empty] | CM_WWNI | 100%
503171 | Dunbar WwTW PLC-SCADA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2018-07-31 | 2018-07-31 | 2018-08-20 | 2018-09-28 | 2018-09-28 | East Lothian | 0 | 0 | 0 | 0 | 302841.12 | 0 | 0 | 302841.12 | 0 | 302841.12 | 0 | [6 empty] | CM_WWNI | 100%
502379 | Dunblane Glen Road DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-12-22 | 2018-03-26 | 2018-05-07 | 2020-07-09 | 2020-10-01 | Stirling | 0 | 0 | 6537.58 | 19236.2 | 85288.76 | 13069.54 | 36903.34 | 161035.42 | 1426.9 | 162462.32 | 0 | [6 empty] | CM_WSNI | 100%
500237 | Dunblane WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 2016-09-05 | 2016-09-05 | Stirling | 0 | 41093.15 | 80.7 | 0 | 0 | 0 | 0 | 41173.85 | 0 | 41173.85 | 136478.56 | [6 empty] | SG1 | 100%
502344 | Dundee - Baldovie Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-10-31 | 2018-11-21 | 2018-11-23 | 2018-11-26 | 2018-11-26 | Dundee City | 0 | 0 | 13271.03 | 42513.89 | 6501.53 | 0 | 0 | 62286.45 | 0 | 62286.45 | 0 | [6 empty] | CM_WWI | 100%
403257 | Dundee Flow Control Valves Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-18 | 2017-01-10 | 2017-01-16 | 2017-01-17 |  | Dundee City | 29690 | 12840 | 3638.04 | 0 | 0 | 0 | 0 | 16478.04 | 0 | 46168.04 | 0 | [6 empty] | CM_WWI | 100%
402478 | Dundee Integrated Catchment Study (Tay PFI Sewer Catchment Areas) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-01-11 | 2013-01-11 | 2015-07-17 | 2015-08-31 | Scottish Water Wide | 1219702 | 22503 | 35819.6 | 0 | -1645.26 | 0 | 0 | 56677.34 | 0 | 1276379.34 | 116934 | [6 empty] | CS16S | 100%
503403 | Dundee Sewer Gates Surveys Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2027-05-28 | 2028-03-09 | 2028-05-26 | 2028-12-28 | 2029-03-30 | Dundee City | 0 | 0 | 0 | 0 | 10562.95 | 1186.8 | -419.79 | 11329.96 | 142835.01 | 154164.97 | 0 | [6 empty] | CM_WWI | 100%
502429 | Dundee Tesco SPS Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 2017-05-12 | 2017-05-12 | Dundee City | 0 | 0 | 4019 | 2880.01 | 35.22 | 0 | -4387.23 | 2547 | 0 | 2547 | 0 | [6 empty] | CM_WWI | 100%
30238 | Dunecht STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-09 | 2010-12-21 | 2011-09-19 | 2012-05-10 | 2012-05-31 | Aberdeenshire | 542444.18 | 1780.2 | 0 | 0 | 0 | 0 | 0 | 1780.2 | 0 | 544224.38 | 0 | [6 empty] | CM_WWNI | 100%
46384 | Dunfermline Eastern Expansion (DEX) | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2009-08-14 | 2011-03-02 | 2011-03-11 | 2012-10-15 | 2012-12-10 | Fife | 3199346 | -7318.43 | 0 | 0 | 0 | 0 | 0 | -7318.43 | 0 | 3192027.57 | 470181.23 | [6 empty] | WG5 | 100%
502372 | Dunfermline STC - Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2016-11-25 | 2017-01-31 | 2017-02-27 | 2017-11-24 | 2017-11-24 | Fife | 0 | 0 | 995828.08 | 1962781.37 | 153489.46 | 5746.39 | 14741.56 | 3132586.86 | 0 | 3132586.86 | 0 |  |  |  |  | 57960 |  | CM_WWNI | 100%
46746 | Dunfermline STW - Enhancement of Sludge Treatment Facilities | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2011-10-18 | 2011-10-18 | 2012-03-23 | 2012-03-31 | Fife | 759944.01 | 620.39 | 0 | 0 | 0 | 0 | 0 | 620.39 | 0 | 760564.4 | 0 | [6 empty] | EC06 | 100%
502949 | Dunfermline Wellwood Waste Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2018-01-10 | 2018-01-10 | 2018-05-31 | 2020-09-29 | 2020-09-29 | Fife | 0 | 0 | 0 | 73140.19 | 420008.81 | 27.55 | 372293.15 | 865469.7 | 252530.34 | 1118000.04 | 0 | [6 empty] | SG5 | 100%
500965 | Dunfermline WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-10-05 | 2018-08-31 | 2018-08-31 | 2020-05-22 | 2020-08-24 | Fife | 0 | 53894.37 | 177451.74 | 173730.92 | 550048.92 | 1926823.21 | 5904.71 | 2887853.87 | 27500.13 | 2915354 | 0 |  |  |  |  | 35000 |  | CM_WWNI | 100%
503213 | Dunfermline WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-10-27 | 2023-04-18 | 2023-08-10 | 2024-08-06 | 2024-11-06 | Fife | 0 | 0 | 0 | 0 | 15513.66 | 16052.84 | 102189.04 | 133755.54 | 1371244.54 | 1505000.08 | 136478.56 | [6 empty] | SG1 | 100%
45546 | Dunkeld STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-03-24 | 2011-06-27 | 2012-03-23 | 2012-03-27 | Perth and Kinross | 505350.33 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 505381.05 | 0 | [6 empty] | CM_WWNI | 21.67% | WQ01 | 78.33%
502910 | Dunlop Road Stewarton Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-11-14 | 2017-11-14 | 2017-12-01 | 2020-11-03 | 2020-11-03 | East Ayrshire | 0 | 0 | 0 | 19364.49 | 0 | 0 | 215510.03 | 234874.52 | 101125.48 | 336000 | 470181.23 | [6 empty] | WG5 | 100%
404000 | Dunnet WWTW Outfall and PAA Dosing de-commissioning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-03-03 | 2019-07-02 | 2019-09-23 | 2020-04-01 | 2020-04-01 | Highland | 509.68 | 131402.32 | 44109 | 3327 | 134638 | 3345876 | 62102 | 3721454.32 | 2500 | 3724464 | 0 | [6 empty] | CM_WWNI | 100%
500812 | Dunning and Aberuthven DMA Station Road Mains Rhab | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-09-16 | 2029-05-09 | 2029-09-11 | 2031-04-07 | 2031-07-08 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79661.9 | 79661.9 | 0 | [6 empty] | CM_WSI | 100%
503375 | Dunning WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-04-18 | 2028-08-21 | 2029-02-09 | 2029-05-14 | Perth and Kinross | 0 | 0 | 0 | 0 | 77822.42 | 5025.04 | 0 | 82847.46 | 59152.55 | 142000.01 | 136478.56 | [6 empty] | SG1 | 100%
501271 | Dunnswood DOA (DOA000557) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS5 | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2019-03-27 | 2020-01-08 | North Lanarkshire | 0 | 20938 | 185376 | 132088 | 74776 | 32361.07 | -7820.35 | 437718.72 | 0 | 437718.72 | 287748.65 | [6 empty] | EC01G | 0.4899% | CS16D | 99.51%
30241 | Dunnswood STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2011-06-28 | 2011-08-23 | 2013-12-09 | 2014-01-14 | North Lanarkshire | 11639043.34 | -13327.86 | 555.62 | 0 | 0 | 0 | 0 | -12772.24 | 0 | 11626271.1 | 410929.63 | [6 empty] | CM_WWNI | 2.952% | SG1 | 6.868% | EC10A | 23.96% | EC01A | 32.93% | EC04A | 33.29%
500128 | Dunoon DOA (DOA002568) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-03 | 2017-07-21 | Argyll and Bute-Cowal & Bute | 0 | 96713 | 138490.05 | 34186.35 | 123.84 | 0 | 0.16 | 269513.4 | 0 | 269513.4 | 72047.27 | [6 empty] | CS11 | 42.57% | CS16D | 57.43%
503558 | Dunoon WwTW Rock Stabilisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-10-03 | 2019-10-03 | 2019-12-09 | 2020-05-14 | 2020-05-15 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 460727.05 | 580.65 | 461307.7 | 2419.35 | 463727.05 | 0 | [6 empty] | CM_M&G | 100%
500130 | Dunragit DOA (DOA000090) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-01 | 2017-04-28 | 2017-04-28 | Dumfries and Galloway | 0 | 15635 | -2752.89 | -2772.35 | 0 | 0 | 0 | 10109.76 | 0 | 10109.76 | 72047.27 | [6 empty] | CS11 | 100%
502628 | Dunvegan Osedale WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2030-11-01 | 2031-01-07 | 2031-12-16 | 2032-03-17 | Highland | 0 | 0 | 20930.23 | 457.49 | 2229.43 | -18617.25 | 0 | 4999.9 | 0 | 4999.9 | 136478.56 | [6 empty] | WG1 | 100%
500745 | Durley Dene Crescent Bridge of Earn Kintillo - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 0 | 23000 | 26411.54 | 20558.25 | 312.26 | -73760.42 | 3479.37 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500730 | Durris WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-06-01 | 2021-12-13 | 2022-02-07 | 2022-07-22 | 2022-09-26 | Aberdeenshire | 0 | 22957.9 | 45941.32 | 44775.98 | 6238.5 | 13309.39 | -4295.95 | 128927.14 | 21072.82 | 149999.96 | 136478.56 | [6 empty] | SG1 | 100%
500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-19 | 2017-07-31 | Scottish Water Wide | 0 | 702341 | 483956.81 | 514143.51 | 217874.03 | 31822.17 | -2821.3 | 1947316.22 | 0 | 1947316.22 | 239185.39 | [6 empty] | DW5A | 100%
404122 | Dyce Drive water Infra Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-09-08 | 2017-01-18 | Aberdeen City | 0 | 386989.63 | 114122.16 | 0 | 0 | 0 | 0 | 501111.79 | 0 | 501111.79 | 0 | [6 empty] | WG5 | 100%
500474 | Dynamic Wastewater Treatment Control Prototype | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS5 | 2015-04-30 | 2015-07-22 | 2015-07-27 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 56700 | 73300 | 0 | -5639.04 | 0 | 6993.04 | 131354 | 0 | 131354 | 34072.29 | [6 empty] | CC3S | 100%
504087 | E TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-02-07 | 2021-11-08 | 2022-03-09 | 2023-06-02 | 2023-06-02 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3451.96 | 545032.67 | 548484.63 | 184073.51 | 732558.14 | 0 | [6 empty] | CM_WSNI | 100%
404100 | E&M Planned Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2015-01-27 | 2015-02-26 | 2015-02-26 | 2016-11-03 | 2016-11-03 | Scottish Water Wide | 769247 | 301073 | 1409.55 | 0 | 0 | 0 | 0 | 302482.55 | 0 | 1071729.55 | 0 | [6 empty] | WSNI | 50% | WWNI | 50%
403745 | E034 - Ajd. No15. Invergarry Quadrant PS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2014-03-17 | 2016-02-17 | 2016-03-07 | 2016-03-31 | 2016-04-30 | East Renfrewshire | 2769.81 | 9020.77 | 8476.42 | -55.2 | -1158.86 | 0 | 0.06 | 16283.19 | 0 | 19053 | 385248.68 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
500659 | E1009 - Orchard Brae Gardens Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW1 | 2020-11-30 | 2021-11-03 | 2022-01-24 | 2022-08-09 | 2022-11-07 | City of Edinburgh | 0 | 27200 | 30185.26 | 44114.74 | 51500 | 137832.4 | 59167.6 | 350000 | 0 | 350000 | 1262549.87 | [6 empty] | CS11 | 100%
500661 | E1010 - Craigleith Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2020-02-10 | 2020-12-14 | 2021-01-25 | 2022-03-25 | 2022-06-27 | City of Edinburgh | 0 | 30125 | 36128.94 | 23746.06 | 133538.67 | 219214.33 | 1641227.32 | 2083980.32 | 1853019.68 | 3937000 | 0 | [6 empty] | CS11 | 100%
500634 | E1014 - Haymarket Terrace | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-06-29 | 2017-09-27 | 2017-10-08 | 2018-08-30 | 2018-08-30 | Scottish Water Wide | 0 | 339906.11 | 13031.89 | 2677684 | 287101 | 14004 | 3272.98 | 3334999.98 | 0 | 3334999.98 | 204193.13 | [6 empty] | CS11A | 100%
501114 | E1047 -Meadowbank Ave | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2019-04-24 | 2019-06-12 | 2019-04-26 | 2019-04-26 | City of Edinburgh | 0 | 227849 | 40991.89 | -146750.84 | 707.42 | -9523.41 | 0 | 113274.06 | 0 | 113274.06 | 204193.13 | [6 empty] | CS11 | 100%
503609 | E1049 - Comiston Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-16 | 2021-11-19 | 2022-02-01 | 2022-08-29 | 2022-11-25 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 53853.4 | 68484.59 | 122337.99 | 177662.05 | 300000.04 | 204193.13 | [6 empty] | CS11 | 100%
503594 | E1050 Marchmont Road - Warrender Park Road Edinburgh (Recycled) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-04-24 | 2021-04-19 | 2021-08-19 | 2022-07-29 | 2022-09-21 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 141218.66 | 730276.14 | 871494.8 | 5758178.2 | 6629673 | 400290.3 | [6 empty] | CS11 | 27.27% | CS11A | 72.73%
500299 | E117 - Brown Street Armadale | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2019-04-30 | 2020-06-01 | 2020-07-13 | 2021-03-16 | 2021-03-16 | West Lothian | 0 | 51910 | 50307 | 29816.15 | 39466.85 | 202792 | 1150663.27 | 1524955.27 | 106899.35 | 1631854.62 | 325158 | [6 empty] | CS11 | 34.85% | CS15A | 65.15%
500667 | E1272 - Mayfield Nicolton Road Rumford Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-01-17 | 2019-03-28 | 2019-03-28 | 2019-01-16 | 2019-01-16 | Falkirk | 0 | 70514 | 55002.86 | 33324.11 | -157983.87 | -230.16 | -625.94 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500995 | E1280 - Station Road Brightons Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-20 | 2018-03-27 | 2018-03-27 | 2018-02-13 | 2018-02-13 | Falkirk | 0 | 22430 | 41053.04 | 14661.87 | 293.39 | 434.36 | -434.36 | 78438.3 | 0 | 78438.3 | 204193.13 | [6 empty] | CS11 | 100%
500665 | E1282 - Carronflats Road Grangemouth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2018-06-13 | 2020-01-09 | 2020-03-31 | 2021-04-02 | 2021-06-25 | Falkirk | 0 | 42857 | 31078.83 | 18077.17 | 204675 | 505718 | 1509661.22 | 2312067.22 | 63460.11 | 2375527.33 | 464547.5 | [6 empty] | CS11 | 100%
503571 | E1287 - Claredon Place Dunblane | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2019-07-08 | 2020-08-24 | 2020-11-30 | 2021-08-23 | 2021-11-23 | Stirling | 0 | 0 | 0 | 0 | 0 | 265224 | 2272127.2 | 2537351.2 | 763773.8 | 3301125 | 400290.3 | [6 empty] | CS11 | 25% | CS11A | 75%
500680 | E1336 Seabegs Road Bonnybridge | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW0 | 2020-11-23 | 2021-10-25 | 2022-01-06 | 2022-10-12 | 2023-01-10 | Falkirk | 0 | 107555 | -6059.86 | 15504.86 | 26000 | 102280 | 36688.07 | 281968.07 | 800031.93 | 1082000 | 355339.9 | [6 empty] | CS11 | 100%
501118 | E1340 - Corbiehall Boness Phase 2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2018-02-27 | 2018-02-27 | Falkirk | 0 | 35985 | 33299.51 | 22502.49 | -91786.01 | 2200.93 | -2200.92 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
501541 | E1359 - Avonbridge Inn Falkirk Road Avonbridge Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-03-28 | 2019-03-28 | Falkirk | 0 | 21930 | 4421.24 | 1506.36 | -27856.6 | 0 | 0 | 1 | 0 | 1 | 196097.17 | [6 empty] | CS11A | 100%
503327 | E1383 - Seaview Row Pittenweem | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-11-09 | 2022-07-08 | 2022-07-11 | 2023-01-20 | 2023-03-03 | Fife | 0 | 0 | 0 | 0 | 123324.23 | 34838.37 | 24917.03 | 183079.63 | 391920.32 | 574999.95 | 196097.17 | [6 empty] | CS11A | 100%
500996 | E1401 - Kinnessburn Road St Andrews Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-09-22 | 2018-02-22 | 2018-02-23 | 2018-02-22 | 2018-02-22 | Fife | 0 | 24530 | 29007.06 | 5463.44 | -58904.42 | 8944.08 | -9039.16 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500059 | E1420 - Burnside Auchtermuchty Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2015-10-07 | 2018-03-27 | 2018-03-27 | 2018-03-28 | 2018-03-28 | Fife | 0 | 83434 | 58219.13 | 70933.87 | 89904.46 | -1.01 | 22.02 | 302512.47 | 0 | 302512.47 | 707465.16 | [6 empty] | CS11 | 100%
501117 | E1425 Nos. 3 & 5 Beeches Ladybank Cupar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS4 | 2017-09-26 | 2020-04-06 | 2020-04-13 | 2020-01-28 | 2020-04-01 | Angus | 0 | 99657 | 35295.04 | 19667.17 | -154452.66 | 1723.5 | -1889.05 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
502362 | E1429 2& 8 Drummochy Road Lower Largo | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-09-15 | 2022-08-16 | 2022-11-03 | 2023-06-07 | 2023-09-05 | Fife | 0 | 0 | 0 | 0 | 44000 | 9186.51 | 62054.85 | 115241.36 | 484758.64 | 600000 | 196097.17 | [6 empty] | CS11A | 100%
501190 | E1441 - High Street Kirkcaldy Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-29 | 2019-03-19 | 2019-03-19 | 2019-01-21 | 2019-01-21 | Fife | 0 | 22430 | 24592.69 | 17977.31 | 1495.95 | 0 | 0 | 66495.95 | 0 | 66495.95 | 204193.13 | [6 empty] | CS11 | 100%
502349 | E1448 Park Road Roysth Dunfermline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-09-01 | 2022-05-10 | 2022-06-02 | 2022-07-06 | 2022-10-06 | Fife | 0 | 0 | 0 | 0 | 44000 | 22238.99 | 31477.19 | 97716.18 | 802283.77 | 899999.95 | 196097.17 | [6 empty] | CS11A | 100%
501019 | E1460 - Yetholm Park Dunfermline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2018-10-26 | 2020-03-31 | 2020-05-26 | 2021-01-19 | 2021-01-19 | Fife | 0 | 21930 | 61223.86 | 29097.89 | 140478.14 | 198143.42 | 606099.18 | 1056972.49 | 7900.14 | 1064872.63 | 204193.13 | [6 empty] | CS11 | 100%
500696 | E1539 - Featherhall Crescent Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2018-04-10 | 2018-02-06 | 2018-02-06 | 2018-02-06 | City of Edinburgh | 0 | 37390 | 29380.72 | -66770.72 | 0 | 0 | 1 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500300 | E1549 - Drumbrae South Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2018-12-17 | 2018-12-17 | 2018-07-05 | 2018-07-05 | City of Edinburgh | 0 | 30000 | 66063.67 | 24936.33 | -120999 | 0 | 0 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
503333 | E1614 - Margaret Walk Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-15 | 2021-11-01 | 2021-12-29 | 2022-09-20 | 2022-12-21 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 49000 | 95634.8 | 31067.49 | 175702.29 | 424297.68 | 599999.97 | 196097.17 | [6 empty] | CS11A | 100%
500997 | E1646 - Falkirk Road Avonbridge Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-02-26 | 2019-02-26 | Falkirk | 0 | 21930 | 26959.06 | 58110.94 | 26468.7 | -133173.85 | -293.85 | 1 | 0 | 1 | 196097.17 | [6 empty] | CS11A | 100%
500792 | E1700 SR15 Aberchirder Flooding Project | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2015-10-01 | 2016-07-20 | 2016-10-24 | 2017-03-30 | 2017-03-30 | Aberdeenshire | 0 | 95302.39 | 474632.61 | 61373 | 11346.37 | 0 | 0.63 | 642655 | 0 | 642655 | 204193.13 | [6 empty] | CS11 | 100%
500658 | E2 - 144 Comiston Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2020-05-04 | 2020-05-04 | 2019-09-25 | 2019-09-25 | 2019-09-25 | City of Edinburgh | 0 | 36500 | 29973.22 | 22526.78 | -83089.49 | -3244.29 | -2665.22 | 1 | 0 | 1 | 440892.73 | [6 empty] | CS11 | 100%
500657 | E4 - Mountcastle Drive Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS6 | 2017-03-31 | 2017-07-21 | 2017-07-24 | 2017-11-15 | 2017-11-15 | City of Edinburgh | 0 | 33500 | 43336.73 | 101790.47 | 0 | 0 | 0 | 178627.2 | 0 | 178627.2 | 688771.38 | [6 empty] | CS11 | 100%
500131 | Eaglesfield DOA (DOA000112) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-28 | 2015-11-02 | 2016-12-31 | 2017-07-31 | Dumfries and Galloway | 0 | 48451 | 48679.75 | 243.66 | 61.92 | 0 | 0.08 | 97436.41 | 0 | 97436.41 | 72047.27 | [6 empty] | CS11 | 46.39% | CS16D | 53.61% | bar: Regulatory Outputs OMG-22
30247 | Eaglesham STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-06-09 | 2010-11-16 | 2011-03-31 | 2015-06-02 | 2015-06-02 | East Renfrewshire | 2191314.21 | 151832 | -27667.31 | 1973.27 | 0 | 0 | 835.3 | 126973.26 | 0 | 2318287.47 | 0 | [6 empty] | CM_WWNI | 100%
500859 | Earlish Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-08-19 | 2017-07-25 | 2018-03-26 | 2018-06-30 | 2018-12-31 | Highland | 0 | 830.84 | 889.12 | 10545.98 | 31627.31 | -12919.23 | 0 | 30974.02 | 0 | 30974.02 | 33902.12 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 12.6
46834 | Earlish Uig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-05-23 | 2011-10-24 | 2011-12-07 | Highland | 36466.91 | 1.25 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 36468.16 | 0 | [6 empty] | DW13 | 100%
502620 | Earlish WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2024-05-01 | 2025-11-27 | 2026-01-29 | 2027-01-28 | 2027-04-30 | Highland | 0 | 0 | 20930.23 | 291.13 | 2591.75 | 30467.47 | -41839.42 | 12441.16 | 0 | 12441.16 | 136478.56 | [6 empty] | WG1 | 100%
402503 | Earlsburn No1 and No 2 Reservoirs - Interests of safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-02 | 2012-10-30 | 2012-11-19 | 2013-12-10 | 2013-12-10 | Stirling | 506565 | -5027.11 | 0 | 0 | 0 | 0 | 0 | -5027.11 | 0 | 501537.89 | 0 | [6 empty] | CM_WSI | 100%
402959 | Earlsburn Road Lenzie Kirkintilloch Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2015-02-10 | 2015-02-16 | 2015-05-22 | 2015-05-22 | East Dunbartonshire | 255590 | 105419.3 | 4987.11 | -4252.11 | 0 | 0 | 0 | 106154.3 | 0 | 361744.3 | 204193.13 | [6 empty] | CS11 | 100%
501500 | Earlston WwTW | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-04-18 | 2018-09-26 | 2018-11-26 | 2020-05-12 | 2020-08-11 | Scottish Borders | 0 | 0 | 175824.43 | 128158.76 | 244937.45 | 525010.55 | 22240.61 | 1096171.8 | 53194.94 | 1149366.74 | 136478.56 |  |  |  |  | 16720 |  | SG1 | 100%
501592 | EARLSTON WWTW 1959 NT573382 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-06-09 | 2018-09-27 | 2018-11-26 | 2020-10-08 | 2021-01-07 | Scottish Borders | 0 | 0 | 75107.07 | 346589.02 | 538459.69 | 1630877.54 | 524280.63 | 3115313.95 | 34317.24 | 3149631.19 | 0 |  |  |  |  | 16720 |  | CM_WWNI | 100%
502426 | Earlston WwTW Outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2017-06-19 | 2017-09-18 | 2017-09-21 | 2018-03-31 | 2018-03-31 | Scottish Borders | 0 | 0 | 3869.46 | 32462.3 | 23138.15 | 832.09 | 0 | 60302 | 0 | 60302 | 30997.67 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
502640 | Early scoping for Wastewater- Water Growth - post 2021 delivery | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-04-19 | 2022-02-25 | 2022-06-21 | 2022-11-01 | 2023-02-01 | Scottish Water Wide | 0 | 0 | 42118.71 | 120870.69 | -72368.28 | -36978.08 | -64.58 | 53578.46 | -27859.95 | 25718.51 | 136478.56 | [6 empty] | SG1 | 100%
502930 | Easdale - Seaview Cottage ST (Option 1A Part 1) | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS2 | 2012-09-17 | 2019-07-22 | 2021-01-04 | 2021-01-31 | 2021-04-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 11714.07 | 100753.94 | 208320.36 | 19741.64 | 340530.01 | 222175.63 | 562705.64 | 455015.39 |  |  |  |  | 2480 |  | EC01A | 100% | bar: Regulatory Outputs OMG-17
501316 | East SPS MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-05-31 | 2018-07-20 | 2018-10-15 | 2020-05-15 | 2020-08-19 | Scottish Water Wide | 0 | 0 | 55664 | 107649 | 1636959 | 178707 | 9654 | 1988633 | 2400 | 1991033 | 0 | [6 empty] | CM_WWNI | 100%
500923 | East Ayrshire and South Ayrshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-02-15 | 2017-02-15 | 2017-02-07 | 2017-02-15 | East Ayrshire | 0 | 5000 | 1687.39 | 35.36 | 0 | 0 | 0 | 6722.75 | 0 | 6722.75 | 120964.87 | [6 empty] | CS15A | 100%
501586 | East Burn Sewer Kirkcaldy - Repair sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2016-07-19 | 2028-02-09 | 2028-04-05 | 2028-07-10 | 2028-10-10 | Fife | 0 | 0 | 11799 | -8628.34 | 0 | 0 | 0 | 3170.66 | 104630.34 | 107801 | 0 | [6 empty] | SR21_WW | 100%
500132 | East Calder DOA (DOA000529) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-22 | 2016-03-22 | 2018-05-31 | 2018-07-31 | West Lothian | 0 | 68167 | 328852.05 | 97035.32 | -1248 | 2716.06 | -0.03 | 495522.4 | 0 | 495522.4 | 72047.27 | [6 empty] | CS11 | 10.86% | CS16D | 89.14% | bar: Regulatory Outputs OMG-22
505360 | East CM Glenlatterach IOS Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-02-26 |  | 2020-10-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1000 | 218999.97 | 219999.97 | 0 | 219999.97 | 0 | [6 empty] | CM_WSI | 100%
502791 | East Garleton Farm 10 AC Main (Athelstaneford) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-04-02 | 2028-01-17 | 2028-04-13 | 2028-11-08 | 2029-02-08 | East Lothian | 0 | 0 | 0 | 31400 | 31600 | 0 | 0 | 63000 | 489640.06 | 552640.06 | 0 | [6 empty] | CM_WSI | 100%
400076 | East Kilbride Dual Manhole System Upgrades | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2011-07-28 | 2011-08-22 | 2013-02-20 | 2013-09-30 | South Lanarkshire | 1714911 | -3246.93 | 0 | 0 | 0 | 0 | 0 | -3246.93 | 0 | 1711664.07 | 0 | [6 empty] | EC04D | 100%
402988 | East King Street Helensburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-23 | 2014-07-01 | 2014-07-18 | 2015-03-18 | 2015-03-18 | Argyll and Bute-Cowal & Bute | 1347271 | 80471 | -24999.66 | -46643.91 | 0 | 0 | 0 | 8827.43 | 0 | 1356098.43 | 204193.13 | [6 empty] | CS11 | 100%
400762 | East Leak Detection Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | City of Edinburgh | 465000 | -41243.42 | 0 | 0 | 0 | 0 | 0 | -41243.42 | 0 | 423756.58 | 0 | [6 empty] | CM_WSI | 100%
500229 | East Linton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS2 | 2018-08-03 | 2020-04-03 | 2020-07-06 | 2022-05-06 | 2022-05-09 | East Lothian | 0 | 39725.61 | 15077.35 | 42278.79 | 102800.01 | 603635.68 | 1423046.56 | 2226564 | 1814208.98 | 4040772.98 | 136478.56 | [6 empty] | CM_WWNI | 4% | SG1 | 96%
500921 | East Lothian Midlothian and West Lothian Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | East Lothian | 0 | 6000 | -529.59 | 35.36 | 0 | 0 | 0 | 5505.77 | 0 | 5505.77 | 120964.87 | [6 empty] | CS15A | 100%
402976 | East PH 2 - WW Lumphinnans Hydrobrake | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-26 | 2013-05-27 | 2013-07-17 | 2013-12-20 |  | Fife | 123879 | -1242.71 | 0 | 0 | 0 | 0 | 0 | -1242.71 | 0 | 122636.29 | 0 | [6 empty] | CM_WWI | 100%
403036 | East Ph 2 East Bylaw Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-05-17 | 2015-05-25 | 2015-06-22 | 2015-12-22 |  | Shetland Islands | 17398 | 111316 | 0.39 | -276.29 | 0 | 0 | 0 | 111040.1 | 0 | 128438.1 | 0 | [6 empty] | CM_WWI | 100%
403031 | East Ph 2 North Queensferry Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-06 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 722 | 0 | -355.98 | 0 | 0 | 0 | 0 | -355.98 | 0 | 366.02 | 0 | [6 empty] | CM_WWI | 100%
403035 | East Ph 2 Saline Intrusion in pumping stations in Orkney-Shetland | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-22 | 2016-06-24 | 2016-06-24 | 2016-06-28 |  | Orkney Islands | 4544 | 8939.14 | 442.86 | 0 | 0 | 0 | 0 | 9382 | 0 | 13926 | 0 | [6 empty] | CM_WWNI | 100%
402974 | East Ph2 - River Ore Pollution Trunk sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-15 | 2016-12-11 | 2016-04-01 | 2016-12-13 |  | Fife | 26237 | 108541 | 60232.09 | 0 | 0 | 0 | 0 | 168773.09 | 0 | 195010.09 | 0 | [6 empty] | CM_WWI | 100%
403003 | East Ph2 -Torphins network infiltration | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-30 | 2016-12-11 | 2016-12-12 | 2016-12-12 |  | Aberdeenshire | 14556 | 2933 | -2851.37 | 0 | 0 | 0 | 0 | 81.63 | 0 | 14637.63 | 0 | [6 empty] | CM_WWI | 100%
402973 | East phase 2- Dysart SPS Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-26 | 2016-03-14 | 2016-03-17 | 2016-09-16 |  | Fife | 1000 | 4785.9 | 0 | 0 | 0 | 0 | 0 | 4785.9 | 0 | 5785.9 | 0 | [6 empty] | CM_WWI | 100%
400629 | East Pollution Hotspots Phase 1A | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-03-02 | 2012-05-25 | 2013-03-18 |  | All East Unitary Authorities | 213408 | 7727.53 | 0 | 0 | 0 | 0 | 0 | 7727.53 | 0 | 221135.53 | 0 | [6 empty] | CM_WWI | 100%
400628 | East Pollution Hotspots Phase 1B | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-03-28 | 2012-09-11 | 2013-03-18 |  | All East Unitary Authorities | 300970 | 4744.13 | 0 | 0 | 0 | 0 | 0 | 4744.13 | 0 | 305714.13 | 0 | [6 empty] | CM_WWI | 100%
500015 | East Rogerton TWS - Tower Roofs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-05-08 | 2017-11-24 | 2018-01-30 | 2019-03-06 | 2019-03-06 | South Lanarkshire | 0 | 64060 | 144225.01 | 225743.59 | 766388.24 | 17360.93 | 0 | 1217777.77 | 452.54 | 1218230.31 | 0 | [6 empty] | CM_WSNI | 100%
503373 | East Wemyss WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-01-16 | 2019-01-16 | Fife | 0 | 0 | 0 | 0 | 74030.64 | 0 | -3919.29 | 70111.35 | 0 | 70111.35 | 136478.56 | [6 empty] | SG1 | 100%
402978 | East WWI Ph 2 - Arbroath John Street West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-07-20 | 2016-07-20 | 2016-07-20 |  | Angus | 3142 | 44.69 | 40.93 | 0 | 0 | 0 | -19.94 | 65.68 | 0 | 3207.68 | 0 | [6 empty] | CM_WWI | 100%
402982 | East WWI Ph 2 - Haugh Road Burntisland Storm Pump Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-02-19 | 2016-04-27 | 2016-07-07 | 2016-07-07 | Fife | 224.88 | 45069.01 | 93018.52 | 313.66 | -1455.43 | 0 | 0.36 | 136946.12 | 0 | 137171 | 0 | [6 empty] | CM_WWI | 100%
402984 | East WWI Ph 2 - Methil Day Care Centre | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-02-19 | 2016-04-27 | 2016-07-31 | 2016-07-31 | Fife | 5349.96 | 32642.04 | 77500 | 0 | 3913.64 | 0 | 867.36 | 114923.04 | 0 | 120273 | 0 | [6 empty] | CM_WWI | 100%
402975 | East WWI ph 2 - River Ore Trunk sewer Jamphalars Cardenden | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-09 | 2013-08-26 | 2013-10-14 | 2014-04-08 |  | Fife | 35597 | 418.72 | -385.56 | 0 | 0 | 0 | 0 | 33.16 | 0 | 35630.16 | 0 | [6 empty] | CM_WWI | 100%
402983 | East WWI Ph 2 St Andrews DOA PIF | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 1000 | 0 | -411.71 | 0 | 0 | 0 | 0 | -411.71 | 0 | 588.29 | 0 | [6 empty] | CM_WWI | 100%
402985 | East WWI Ph 2 Woodhaven Pier | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 732 | 1000 | -620.48 | 0 | 0 | 0 | 0 | 379.52 | 0 | 1111.52 | 0 | [6 empty] | CM_WWI | 100%
402979 | East WWI Ph2 - Balmerino ST | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 894 | 0 | -502.29 | 0 | 0 | 0 | 0 | -502.29 | 0 | 391.71 | 0 | [6 empty] | CM_WWI | 100%
402980 | East WWI Ph2 - Glovers Wynd Earlesferrry | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Fife | 6960 | 1054.97 | 0 | 0 | 0 | 0 | 0 | 1054.97 | 0 | 8014.97 | 0 | [6 empty] | CM_WWI | 100%
402972 | East WWI Ph2 Lower Largo | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 2514 | 0 | -491.7 | 0 | 0 | 0 | 0 | -491.7 | 0 | 2022.3 | 0 | [6 empty] | CM_WWI | 100%
402971 | East WWI Ph2 WWI - 295 Cowdenbeath High Street | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-06-06 | 2016-07-15 | 2016-11-02 |  | Fife | 224.88 | 37453.12 | 133708 | -0.28 | -4015.14 | 0 | 0.42 | 167146.12 | 0 | 167371 | 0 | [6 empty] | CM_WWI | 100%
402604 | East WWPSs HS Access Issues | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2015-01-08 | 2015-05-29 | 2016-09-26 |  | All East Unitary Authorities | 280394 | 687878 | 136053.91 | 0 | -2386.22 | 0 | 0 | 821545.69 | 0 | 1101939.69 | 0 | [6 empty] | CM_M&G | 100%
501318 | East WWTW MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2016-07-07 | 2018-07-31 | 2018-09-25 | 2020-02-13 | 2020-06-19 | All East Unitary Authorities | 0 | 0 | 22116.32 | 265307.96 | 695088.78 | 117338.52 | 6340.74 | 1106192.32 | 3457.71 | 1109650.03 | 0 | [6 empty] | CM_WWNI | 100%
502762 | Eastern Stirling Villages - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-06-23 | 2023-07-25 | 2023-11-13 | 2026-01-09 | 2026-01-12 | Stirling | 0 | 0 | 0 | 199470.48 | 71241.53 | 316451.83 | -46850.07 | 540313.77 | 44459686.23 | 45000000 | 136478.56 | [6 empty] | SG1 | 100%
501249 | Eastriggs - Rigg Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-12-07 | 2027-04-14 | 2027-05-20 | 2027-08-04 | 2027-11-04 | Dumfries and Galloway | 0 | 21096 | 17517.2 | 1390.57 | 0 | 17061.63 | 0 | 57065.4 | 357672.78 | 414738.18 | 0 | [6 empty] | CM_WSI | 100%
500125 | Eastriggs DOA (DOA000853) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-27 | 2016-08-25 | 2018-11-30 | 2019-03-31 | Dumfries and Galloway | 0 | 9973 | 27292.27 | 71585.73 | 15154.66 | -6859.44 | -0.03 | 117146.19 | 0 | 117146.19 | 62699.33 | [6 empty] | EC01G | 9.54% | EC01D | 90.46% | bar: Regulatory Outputs OMG-23
501101 | EC01G Aesthetic Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-08-31 | 2016-10-03 | 2018-07-31 | 2019-03-31 | Scottish Water Wide | 0 | 1129 | 24269.31 | 29965.47 | 4513.28 | 0 | 0.01 | 59877.07 | 0 | 59877.07 | 10344.04 | [6 empty] | EC01G | 100% | [18 empty] | Regulatory Outputs OMG-23: 6
503281 | Ecclefechan WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-01-15 | 2029-05-18 | 2030-05-16 | 2030-08-16 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 79101.97 | 5658 | 0 | 84759.97 | 57240.03 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
505271 | Echt STW - Septic Tank Overflow & Recirculation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 155.48 | 0 | 155.48 | 0 | 155.48 | 56717112.68 | [6 empty] | WWNI | 100%
402230 | Echt WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-06-28 | 2013-10-24 | 2014-01-09 | 2015-03-04 | 2015-03-04 | Aberdeenshire | 1706967 | 17055 | 9149.9 | 48827.06 | 0 | 0 | 0 | 75031.96 | 0 | 1781998.96 | 0 | [6 empty] | SG1 | 100%
503313 | Eddleston WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-07-22 | 2022-01-17 | 2022-05-20 | 2023-05-15 | 2023-08-15 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 91433.53 | 51705.39 | 143138.92 | 1856861.11 | 2000000.03 | 136478.56 | [6 empty] | SG1 | 100%
502612 | Edgar Road SPS Rising Main Elgin | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2020-12-09 | 2021-10-04 | 2021-12-20 | 2022-07-19 | 2022-10-19 | Moray | 0 | 0 | 9623.72 | 812.95 | 598.05 | 3638.48 | 50487.61 | 65160.81 | 413839.25 | 479000.06 | 0 | [6 empty] | CM_WWI | 100%
501104 | Edinburgh DAS Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-01 | 2019-01-23 | City of Edinburgh | 0 | 591 | 12353.81 | 28250.19 | 18872.46 | 0 | 0 | 60067.46 | 0 | 60067.46 | 172900.96 | [6 empty] | EC01D | 15.25% | EC01G | 31.12% | EC10E | 53.63%
400948 | Edinburgh Haymarket Terrace - Internal Flooding Programme | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2010-05-31 | 2013-10-18 | 2015-10-19 | 2015-10-19 | 2015-10-19 | City of Edinburgh | 126235.14 | -126234.15 | -7832.14 | 1897.01 | 0 | 0 | 5935.14 | -126234.14 | 0 | 1 | 0 | [6 empty] | CS11A | 100%
501311 | Edinburgh High Consequence Sewer Rehab Ph1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-17 | 2017-01-31 | 2017-02-06 | 2019-05-31 | 2019-05-31 | City of Edinburgh | 0 | 9734 | 390061 | 525183 | 800846 | 462.82 | 16250.89 | 1742537.71 | 4462.29 | 1747000 | 0 | [6 empty] | CM_WWI | 100%
500819 | Edinburgh Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-03-28 | 2017-03-28 | 2016-12-02 | 2017-03-28 | City of Edinburgh | 0 | 5092.83 | 1913.91 | 532 | 0 | 0 | 0 | 7538.74 | 0 | 7538.74 | 120964.87 | [6 empty] | CS15A | 100%
402479 | Edinburgh Integrated Catchment Study (AVSE PFI - Edinburgh Sewer Catchment Area) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-04-30 | 2013-04-30 | 2016-08-30 | 2016-11-07 | Scottish Water Wide | 1241862 | 92738.46 | 69372.54 | 29997 | 26793.75 | 0 | 0 | 218901.75 | 0 | 1460763.75 | 106014 | [6 empty] | CS16S | 100%
502961 | Edinburgh Rising Mains project | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2020-12-01 | 2028-02-02 | 2028-04-18 | 2028-11-13 | 2029-02-13 | City of Edinburgh | 0 | 0 | 0 | 20048.62 | 80188.07 | 60780.87 | -11612.2 | 149405.36 | 350594.71 | 500000.07 | 0 | [6 empty] | CM_WWI | 100%
503772 | Edinburgh Strategic Growth Investigation | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-10-02 | 2021-05-17 | 2021-09-16 | 2022-04-13 | 2022-06-06 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 208684.13 | 68204.77 | 276888.9 | 583111.12 | 860000.02 | 136478.56 | [6 empty] | SG1 | 100%
501096 | Edinburgh Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-09-26 | 2016-09-28 | 2018-10-31 | 2019-07-31 | City of Edinburgh | 0 | 3837 | 34236.82 | 39826.18 | 15100 | -5018.55 | 0 | 87981.45 | 0 | 87981.45 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
503034 | Edzell Rural DMA - North Water Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-06-29 | 2028-04-17 | 2028-07-18 | 2029-02-19 | 2029-05-22 | Aberdeenshire | 0 | 0 | 0 | 12453.61 | 16346.39 | 77255.84 | -51.43 | 106004.41 | 0 | 106004.41 | 0 | [6 empty] | CM_WSI | 100%
502819 | Edzell WwTW - Investigation and Scope Definition for Potential Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2019-09-12 | 2019-09-12 | Angus | 0 | 0 | 0 | 63338.94 | 12729.93 | -42340.54 | 0 | 33728.33 | 0 | 33728.33 | 136478.56 | [6 empty] | SG1 | 100%
500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-20 | 2020-01-31 | Shetland Islands | 0 | 604.56 | 31705.62 | 47595.16 | 6062.66 | 23726.07 | -21726.07 | 87968 | 0 | 87968 | 608770.69 | [6 empty] | DW5FS | 100%
505114 | Eela Water - Raw water main replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-18 | 2020-09-28 | 2021-02-18 | 2020-10-30 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 10166.69 | 139633.3 | 149799.99 | 0 | 149799.99 | 0 | [6 empty] | CM_WSI | 100%
500860 | Eela Water Shetland RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-06-03 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Shetland Islands | 0 | 16989.46 | 10147.45 | 7415.4 | 0 | 0 | 0 | 34552.31 | 0 | 34552.31 | 870817.86 | [6 empty] | DW5FS | 100%
501256 | Eela Water WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-01 | 2028-02-29 | 2028-07-03 | 2028-10-31 | 2029-01-31 | Shetland Islands | 0 | 1684.21 | 18090.52 | 11568.76 | 800.88 | 23159.71 | -2414.07 | 52890.01 | 2269910.46 | 2322800.47 | 0 | [6 empty] | CM_WSNI | 100%
501091 | Eela Water WTW QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-11-02 | 2018-02-28 | 2018-03-28 | 2020-09-30 | 2020-12-31 | Shetland Islands | 0 | 3448.91 | 58429.83 | 402540.72 | 1229484.01 | 365545.31 | 40542.03 | 2099990.81 | 32711.19 | 2132702 | 53220.96 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500030 | Eela WTW to Sullom Voe | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS3 | 2016-08-01 | 2018-06-29 | 2018-09-28 | 2020-12-18 | 2021-03-31 | Shetland Islands | 0 | 160186.88 | 55510.12 | 61639 | 2011383.72 | 3274515.61 | 1416008.55 | 6979243.88 | 89801.12 | 7069045 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
503578 | EFOS - Ford Avenue Dreghorn Irvine | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-18 | 2022-08-03 | 2022-12-06 | 2024-07-01 | 2024-08-22 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 47707.35 | 52292.65 | 100000 | 100000.01 | 200000.01 | 120964.87 | [6 empty] | CS15A | 100%
503693 | EFOS - High Road Saltcoats | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-01-18 | 2022-08-26 | 2022-12-29 | 2024-07-24 | 2024-09-16 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 32243.83 | -11603.83 | 20640 | 179360.04 | 200000.04 | 120964.87 | [6 empty] | CS15A | 100%
503626 | EFOS - Meadowpark and Belmont Road Ayr | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-01-25 | 2022-09-02 | 2023-01-05 |  | 2024-09-23 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 34989.67 | 165010.33 | 200000 | 0 | 200000 | 120964.87 | [6 empty] | CS15A | 100%
502912 | EFOS - Meadowpark Ayr | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS5 | 2021-04-20 | 2021-12-06 | 2019-09-30 |  | 2019-09-30 | South Ayrshire | 0 | 0 | 0 | 0 | 6000 | 19314.69 | 48920.91 | 74235.6 | 764.39 | 74999.99 | 120964.87 | [6 empty] | CS15A | 100%
503615 | EFOS - Middlepart Crescent Saltcoats | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-18 | 2022-08-26 | 2022-12-29 | 2024-07-24 | 2024-09-16 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 46024.69 | 53975.31 | 100000 | 100000.02 | 200000.02 | 120964.87 | [6 empty] | CS15A | 100%
503692 | EFOS - Russell Street Hamilton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-10 | 2022-09-20 | 2023-01-23 | 2024-08-16 | 2024-10-09 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 35590 | 902.31 | 36492.31 | 163507.66 | 199999.97 | 120964.87 | [6 empty] | CS15A | 100%
503506 | EFOS - STAMPERLAND GARDENS CLARKSTON | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-31 | 2021-09-24 | 2021-12-16 | 2022-05-04 | 2022-08-04 | East Renfrewshire | 0 | 0 | 0 | 0 | 41860.47 | 24008.1 | 46131.43 | 112000 | 87999.98 | 199999.98 | 120964.87 | [6 empty] | CS15A | 100%
503391 | EFOS - 1968-2 Lawers Square Penicuik | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-23 | 2021-10-20 | 2022-02-03 | 2022-07-29 | 2022-10-31 | Midlothian | 0 | 0 | 0 | 0 | 29000 | 48282.06 | 22717.91 | 99999.97 | 100000 | 199999.97 | 120964.87 | [6 empty] | CS15A | 100%
502955 | EFOS - A8 East Hamilton Street Greenock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-07-10 | 2021-02-08 | 2021-03-30 | 2021-11-03 | 2022-02-03 | Inverclyde | 0 | 0 | 0 | 6000 | 21000 | 87380.72 | 479552.33 | 593933.05 | 1906066.96 | 2500000.01 | 120964.87 | [6 empty] | CS15A | 100%
502700 | EFOS - Aulton Way Montrose | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-08-09 | 2022-04-04 | 2022-06-15 | 2022-10-31 | 2023-01-31 | Angus | 0 | 0 | 0 | 57000 | 16000 | 10688.81 | 5827.41 | 89516.22 | 110483.8 | 200000.02 | 120964.87 | [6 empty] | CS15A | 100%
503625 | EFOS - Barron Terrace and Waggon Road Leven Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-22 | 2022-09-01 | 2023-01-04 | 2024-07-30 | 2024-09-20 | Fife | 0 | 0 | 0 | 0 | 0 | 25555.4 | 45444.6 | 71000 | 28999.97 | 99999.97 | 120964.87 | [6 empty] | CS15A | 100%
503368 | EFOS - Bayview Court Cullen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-06-02 | 2022-01-27 | 2022-05-13 | 2022-11-07 | 2023-02-07 | Moray | 0 | 0 | 0 | 0 | 11000 | 24235.14 | 62174.28 | 97409.42 | 2590.59 | 100000.01 | 120964.87 | [6 empty] | CS15A | 100%
502699 | EFOS - Cheapside Street Eaglesham | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-08-16 | 2018-08-16 | Renfrewshire | 0 | 0 | 0 | 34931.28 | 15511.35 | 846.75 | -605.02 | 50684.36 | 0 | 50684.36 | 120964.87 | [6 empty] | CS15A | 100%
503552 | EFOS - Colston Rd_Meadowside Gdns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2021-10-20 | 2022-01-11 | 2022-07-11 | 2022-10-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 39289.03 | 32710.99 | 72000.02 | 127999.98 | 200000 | 120964.87 | [6 empty] | CS15A | 100%
503860 | EFOS - Crow Wood Terrace Chryston - W1000 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2020-02-28 | 2020-12-14 | 2021-02-01 | 2022-02-11 | 2022-05-09 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 190443 | 346475.97 | 536918.97 | 1368344.65 | 1905263.62 | 0 | [6 empty] | CS15 | 100%
502913 | EFOS - Cumbrae Road Saltcoats | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-05-13 | 2021-12-29 | 2022-03-21 | 2022-08-03 | 2022-10-27 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 7000 | 53842.3 | 13753.17 | 74595.47 | 125404.48 | 199999.95 | 120964.87 | [6 empty] | CS15A | 100%
503694 | EFOS - Deepdene Road Bearsden (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-20 | 2022-08-30 | 2023-01-02 | 2024-07-26 | 2024-09-18 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 29445.26 | 70554.73 | 99999.99 | 100000.02 | 200000.01 | 120964.87 | [6 empty] | CS15A | 100%
503696 | EFOS - Dunbeath and Windsor Avenues Newton Mearns (Shieldhall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-18 | 2022-08-03 | 2022-12-06 | 2024-07-01 | 2024-08-22 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 26530 | 73470.02 | 100000.02 | 100000.03 | 200000.05 | 120964.87 | [6 empty] | CS15A | 100%
502693 | EFOS - Glovers Wynd Earlsferry | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-18 | 2018-05-18 | 2018-04-25 | 2018-05-18 | 2018-05-18 | Fife | 0 | 0 | 0 | 8000 | -5087.05 | 0 | 0 | 2912.95 | 0 | 2912.95 | 120964.87 | [6 empty] | CS15A | 100%
503210 | EFOS - Holm Road Stewarton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-11-02 | 2021-10-18 | 2022-01-06 | 2022-08-09 | 2022-11-09 | East Ayrshire | 0 | 0 | 0 | 0 | 11000 | 47157.35 | 41842.63 | 99999.98 | 0 | 99999.98 | 120964.87 | [6 empty] | CS15A | 100%
502920 | EFOS - Inveroran Drive Bearsden | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-03-11 | 2021-11-10 | 2022-01-31 | 2022-06-15 | 2022-09-08 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 20000 | 55000.01 | 75000.01 | 124999.98 | 199999.99 | 120964.87 | [6 empty] | CS15A | 100%
503598 | EFOS - Kirkview and Laightoun Court Cumbernauld (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-29 | 2021-12-30 | 2022-03-18 | 2022-10-04 | 2023-01-03 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 69543.31 | 71526.93 | 141070.24 | 58929.76 | 200000 | 120964.87 | [6 empty] | CS15A | 100%
502761 | EFOS - Leven Road Coatbridge | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-11-27 | 2021-07-12 | 2021-08-13 | 2021-11-18 | 2021-11-19 | North Lanarkshire | 0 | 0 | 0 | 84150.78 | 46849.22 | 48770.38 | 35194.72 | 214965.1 | 2165034.91 | 2380000.01 | 120964.87 | [6 empty] | CS15A | 100%
502697 | EFOS - Montrose Avenue Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-14 | 2018-08-14 | Glasgow City | 0 | 0 | 0 | 90079.44 | 10276.26 | 0 | 0 | 100355.7 | 0 | 100355.7 | 120964.87 | [6 empty] | CS15A | 100%
503612 | EFOS - Poplar Avenue Newton Mearns (Shieldhall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-18 | 2022-08-03 | 2022-12-06 | 2024-07-01 | 2024-08-22 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 42382.18 | -2382.18 | 40000 | 159999.98 | 199999.98 | 120964.87 | [6 empty] | CS15A | 100%
503338 | EFOS - Prestwick Strategic Study | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-09-23 | 2022-06-29 | 2022-09-09 | 2023-01-24 | 2023-04-26 | North Ayrshire | 0 | 0 | 0 | 0 | 45000 | 346469.33 | 121238.6 | 512707.93 | 45292.07 | 558000 | 120964.87 | [6 empty] | CS15A | 100%
502918 | EFOS - Queen Elizabeth Court Clydebank | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-07-21 | 2022-03-08 | 2022-05-27 | 2022-10-11 | 2023-01-04 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 61500 | 75000 | 120964.87 | [6 empty] | CS15A | 100%
503597 | EFOS - Ranfurly Road Bridge of Weir (Erskine) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-07 | 2022-08-31 | 2023-01-03 | 2024-07-29 | 2024-09-19 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 43872.73 | 56127.28 | 100000.01 | 100000 | 200000.01 | 120964.87 | [6 empty] | CS15A | 100%
502916 | EFOS - Riverside Road Galston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-05-13 | 2021-12-29 | 2022-03-21 | 2022-08-03 | 2022-10-27 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 8000 | 52258.8 | 13919.36 | 74178.16 | 821.87 | 75000.03 | 120964.87 | [6 empty] | CS15A | 100%
503192 | EFOS - Station Road and Churchill Place Kilbarchan | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-04-06 | 2022-02-21 | 2022-05-19 | 2022-12-21 | 2023-03-23 | Renfrewshire | 0 | 0 | 0 | 0 | 20000 | 40851.23 | 38546.48 | 99397.71 | 602.29 | 100000 | 120964.87 | [6 empty] | CS15A | 100%
503438 | EFOS - W688 Rhindmuir Road Baillieston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-04-09 | 2021-12-09 | 2022-03-11 | 2022-09-08 | 2022-12-09 | Glasgow City | 0 | 0 | 0 | 0 | 42435.12 | 27564.88 | 75000 | 145000 | 55000 | 200000 | 120964.87 | [6 empty] | CS15A | 100%
502694 | EFOS - Waggon Road Leven | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-18 | 2018-05-18 | 2018-04-25 | 2018-05-18 | 2018-05-18 | Fife | 0 | 0 | 0 | 6000 | -5243.45 | 0 | 0 | 756.55 | 0 | 756.55 | 120964.87 | [6 empty] | CS15A | 100%
502922 | EFOS - Waverley Drive Airdrie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-07-14 | 2021-04-08 | 2021-05-14 | 2021-06-11 | 2021-06-11 | North Lanarkshire | 0 | 0 | 0 | 84000 | 53000 | 38550 | 107450 | 283000 | 3455000 | 3738000 | 120964.87 | [6 empty] | CS15A | 100%
503766 | EFOS - Wrangholm Drive Motherwell | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-18 | 2021-09-15 | 2021-12-01 | 2022-04-14 | 2022-06-07 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 28899.76 | 71100.25 | 100000.01 | 0 | 100000.01 | 120964.87 | [6 empty] | CS15A | 100%
503695 | EFOS 281-1 - Main Street Bridge of Weir (Erskine) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-18 | 2022-08-03 | 2022-12-06 | 2024-07-01 | 2024-08-22 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 39550 | 60449.98 | 99999.98 | 100000.03 | 200000.01 | 120964.87 | [6 empty] | CS15A | 100%
300022 | Electronic - Physical Security improvements at water Assets | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-22 | 2015-08-05 | 2015-01-16 | 2015-04-14 | 2014-12-01 | Scottish Water Wide | 104313.6 | -3953.47 | 0 | 0 | 0 | 0 | 0 | -3953.47 | 0 | 100360.13 | 0 | [6 empty] | DW9 | 100%
46844 | Elgol WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-05-25 | 2012-06-28 | 2012-08-02 | 2012-09-05 | Highland | 200866.84 | 13656.76 | -6822.72 | 0 | 0 | 0 | 0 | 6834.04 | 0 | 207700.88 | 0 | [6 empty] | DW23 | 100%
503214 | Elie ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-07-18 | 2023-12-29 | 2024-04-26 | 2025-04-23 | 2025-07-24 | Fife | 0 | 0 | 0 | 0 | 84764.25 | 8244.81 | 217354.57 | 310363.63 | 6644636.45 | 6955000.08 | 136478.56 | [6 empty] | SG1 | 100%
404098 | ELL - Factors Affecting ALC Performance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-01-28 | 2015-02-05 | 2015-02-05 | 2015-04-24 | 2015-04-24 | Scottish Water Wide | 19822.04 | 2882.23 | 0 | 0 | 0 | 0 | 0 | 2882.23 | 0 | 22704.27 | 0 | [6 empty] | CM_WSI | 100%
402489 | ELL Comparisons with other parts of the UK | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-12-16 | 2013-11-27 | 2013-12-06 | 2013-12-03 |  | Scottish Water Wide | 15808.39 | 0 | 0 | 0 | -0.05 | 0 | 0 | -0.05 | 0 | 15808.34 | 0 | [6 empty] | CM_WSI | 100%
502250 | Ellipse Enhancements for Loggers | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-08 | 2016-07-08 | 2017-03-02 | 2018-06-22 | 2018-06-22 | Scottish Water Wide | 0 | 0 | 16773 | 17840 | 6711.42 | 0 | 0 | 41324.42 | 0 | 41324.42 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
403902 | Ellon WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2014-10-20 | 2019-06-27 | 2019-06-28 | 2021-04-23 | 2021-07-16 | Aberdeenshire | 34032 | 142378 | 431194.61 | 454746.84 | 725974.47 | 2885775.52 | 4397458.69 | 9037528.13 | 1263910.87 | 10335471 | 0 |  |  |  |  | 76330 |  | SG1 | 100%
45031 | Elphin At Knockan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-06-22 | 2011-07-11 | 2012-12-11 | 2013-01-21 | Highland | 1705909 | 105.53 | 30.25 | 0 | 0 | 0 | 0 | 135.78 | 0 | 1706044.78 | 0 | [6 empty] | DW23 | 100%
503354 | Emergency Drought Operations - Picketlaw WTW | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-08-13 | 2018-08-28 | 2018-08-30 | 2019-07-09 | 2019-07-09 | East Renfrewshire | 0 | 0 | 0 | 0 | 580000 | -37363.55 | -277.25 | 542359.2 | 0 | 542359.2 | 0 | [6 empty] | CM_WSI | 100%
502635 | Energy Efficiency - Power Reduction at WTW due to reduction in Leakage. | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS7 | 2018-11-23 | 2018-11-23 | 2018-12-13 | 2018-12-14 | 2018-12-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 36.43 | -36.43 | 0 | 0 | 0 | 0 | 0 | [6 empty] | I2S_WNI | 100%
500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS3 | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2021-02-26 | 2021-02-26 | Scottish Water Wide | 0 | 49919 | 43692.27 | 163137.85 | 43555.73 | 65153.1 | -13457.96 | 351999.99 | 0 | 351999.99 | 94753.86 | [6 empty] | I2S_WNI | 100%
500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS3 | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 139847.22 | 1892905.78 | 855491.91 | 618236.55 | 778312.24 | 653191.12 | 4937984.82 | 27215.22 | 4965200.04 | 2561825.24 |  |  |  |  | -1000000 |  | I2S_WWNI | 100%
403296 | Energy Improvement Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-02-04 | 2013-11-18 | 2013-11-19 | 2015-10-30 |  | Scottish Water Wide | 2179530 | -90527.29 | 0 | 0 | 0 | 0 | 87.18 | -90440.11 | 0 | 2089089.89 | 0 | [6 empty] | CM_M&G | 100%
500001 | Enhanced Contact Management System | Q&S4 | Improving the customer experience | Contact Management |  |  | Wastewater |  | SWD | Contact Management | MS7 | 2015-09-07 | 2016-11-01 | 2016-11-01 | 2019-03-04 | 2019-03-04 | Scottish Water Wide | 532206 | 1492056 | 4070208.94 | 3324387.47 | 163296.15 | 29280.4 | 0 | 9079228.96 | 0 | 9611434.96 | 5679259.76 | [6 empty] | CM_M&G | 33.33% | CS21W | 33.33% | CS21S | 33.33%
503517 | Enhanced Odour Mitigations - Boat of Garten WwTW | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS3 | 2019-02-18 | 2019-02-18 | 2019-02-22 | 2021-05-11 | 2021-08-11 | Highland | 0 | 0 | 0 | 0 | 65833.73 | 937010.31 | -81045.72 | 921798.32 | 128201.68 | 1050000 | 12873.24 |  |  |  |  | 15000 |  | CS2 | 100%
45046 | Enhancement of Borehole Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-27 | 2010-11-25 | 2011-03-14 | 2014-12-15 | 2015-02-17 | Scottish Water Wide | 2247100.9 | -1260.15 | 1282.33 | 0 | 0 | 0 | 0 | 22.18 | 0 | 2247123.08 | 13366 | [6 empty] | DW9B | 100%
46874 | Enhancement of Physical Security at GRP housed alarm panels | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-02-25 | 2012-08-29 | 2012-11-26 | 2015-01-20 | 2015-01-22 | Scottish Water Wide | 3245931.28 | 11260.46 | -1901.75 | 0 | 0 | 0 | 0 | 9358.71 | 0 | 3255289.99 | 11403 | [6 empty] | DW9E | 100%
500225 | Enhancement of Physical Security Vulnerable Point | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-27 | 2017-06-29 | 2017-07-24 | 2018-06-30 | 2018-10-31 | Scottish Water Wide | 167.15 | 752.34 | 11455.51 | 428699.92 | 110928.61 | 1009.38 | 289.58 | 553135.34 | 28.65 | 553331.14 | 273508.41 | [6 empty] | DW9D | 100% | bar: Regulatory Outputs OMG-10
500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-27 | 2017-06-30 | Scottish Water Wide | 504.83 | 70671.17 | 335813.36 | 46072.45 | -11444.17 | 448.66 | 1435.46 | 442996.93 | 0 | 443501.76 | 46637.54 | [6 empty] | DW9F | 100%
502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-03 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 4814.14 | 1962.24 | 0 | 0 | 0 | 6776.38 | 0 | 6776.38 | 182288.97 | [6 empty] | DW9F | 100%
501641 | Enhancement of security at vulnerable points - Phase 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS4 | 2015-03-31 | 2018-10-31 | 2019-03-06 | 2020-01-19 | 2020-07-20 | Scottish Water Wide | 0 | 0 | 13397.32 | 150802.68 | 432865.14 | 1174507.11 | 12900.08 | 1784472.33 | 3659.41 | 1788131.74 | 273508.41 | [6 empty] | DW9D | 100% | bar: Regulatory Outputs OMG-10
500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-16 | 2017-06-30 | Scottish Water Wide | 393.93 | 89765.07 | 343522.2 | 45628.04 | -18227.96 | 486.3 | 713.7 | 461887.35 | 0 | 462281.28 | 135651.43 | [6 empty] | DW9F | 100%
502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS5 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-06-12 | 2019-09-02 | Scottish Water Wide | 0 | 0 | 0 | 3978892.39 | 6524810.52 | 153591.86 | 18351.84 | 10675646.61 | 20653.5 | 10696300.11 | 273508.41 | [6 empty] | CM_WSNI | 50% | DW9D | 50%
45045 | Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2014-10-15 | 2014-11-03 | 2016-03-30 | 2016-03-30 | Scottish Water Wide | 2067970.45 | -7525.44 | -21729.24 | 0 | 0 | 0 | 0 | -29254.68 | 0 | 2038715.77 | 296598 | [6 empty] | DW9A | 100%
45047 | Enhancement of WTW Security (Installation of trial water pollution monitors) - SWW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU |  | 2017-02-06 | 2017-06-02 | 2018-03-19 | 2018-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197588.15 | [6 empty] | DW9C | 100%
402490 | Enhancement of WTW Security Phase 1 Sites | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-09 | 2012-03-13 | 2012-03-13 | 2013-06-10 | 2013-10-30 | Scottish Water Wide | 380616.69 | -38224.37 | 0 | 0 | 0 | 0 | 0 | -38224.37 | 0 | 342392.32 | 5189 | [6 empty] | DW9A | 100%
500066 | Enhancement of WWTW Security | Q&S4 | Protecting and enhancing the environment | Scottish Government Requirements |  |  | Wastewater |  | SWD | Scottish Government Requirements | MS7 | 2016-06-08 | 2016-06-08 | 2015-12-21 | 2016-06-08 | 2016-06-08 | Scottish Water Wide | 0 | 21139.53 | 0 | 0 | 0 | 0 | 0 | 21139.53 | 0 | 21139.53 | 0 | [6 empty] | EC21A | 100%
503824 | E-NI-14112019-Glassiebarns TWS-New Inlet Valve controller (5246) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2727.56 | 41.76 | 2769.32 | 0 | 2769.32 | 0 | [6 empty] | CM_WSNI | 100%
503820 | E-NI-W-13112019-Lomondhills WTW-Spare ortho Pump (5245) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2356.7 | -874.13 | 1482.57 | 0 | 1482.57 | 0 | [6 empty] | CM_WSNI | 100%
503832 | E-NI-W-14112019-Gamekeepers Road TWP-Renew roof (5251) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 2833.36 | -862.08 | 1971.28 | 0 | 1971.28 | 0 | [6 empty] | CM_WSNI | 100%
503864 | E-NI-WW-15112019-PETERHEAD BUCHANHAVEN WWPS-ROTORK REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1217.23 | -411.93 | 805.3 | 0 | 805.3 | 0 | [6 empty] | CM_WWNI | 100%
503819 | E-NI-WW-31102019-KEITH WWTW-NETWORK INFILTRATION | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 | 2020-03-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 95567.26 | -35934.51 | 59632.75 | 0 | 59632.75 | 0 | [6 empty] | CM_WWI | 100%
503846 | E-NI-WW-4112019-GARDENSTOWN WWTW-SHT REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 27626.51 | 0 | 27626.51 | 0 | 27626.51 | 0 | [6 empty] | CM_WWNI | 100%
500953 | Enterprise Management Tool Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-10 | 2016-11-01 | 2016-11-01 | 2017-06-23 |  | Scottish Water Wide | 0 | 33727 | 627257.6 | 11967.07 | 0 | 0 | 1510.5 | 674462.17 | 0 | 674462.17 | 0 | [6 empty] | CM_M&G | 100%
501303 | Environment Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-04-14 | 2017-01-27 | 2017-01-27 | 2017-05-22 | Scottish Water Wide | 0 | 87463 | 32450.58 | 0 | 0 | 0 | 0 | 119913.58 | 0 | 119913.58 | 0 | [6 empty] | CM_M&G | 100%
49013 | Environmental Programme Risk | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS3 |  |  | 2010-04-01 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6016549.9 | [6 empty] | EC04B | 100%
502336 | Environmental Studies - Development Costs | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-03-31 | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2021-06-07 | Scottish Water Wide | 0 | 0 | 82563.99 | 13120.33 | 0 | 14387.24 | 39928.44 | 150000 | 0 | 150000 | 10344.04 | [6 empty] | EC01G | 100%
402923 | EP Volunteer Database | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-08-24 | 2012-08-24 | 2012-09-03 | 2013-06-07 |  | Scottish Water Wide | 11021.46 | 0 | 0 | 356.48 | 0 | 0 | -356.48 | 0 | 0 | 11021.46 | 0 | [6 empty] | CM_M&G | 100%
502206 | ePay | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-08-29 | 2017-06-16 | Scottish Water Wide | 0 | 0 | 30553.57 | 0 | 0 | 0 | 0 | 30553.57 | 0 | 30553.57 | 0 | [6 empty] | CM_M&G | 100%
402440 | Eredine Water Supply and Network - Upgrading -Adoption of Private Supply | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-21 | 2013-08-30 | 2013-11-25 | 2015-02-25 | 2015-03-26 | Argyll and Bute-North Argyll | 837864 | 170136 | -631.01 | 801.41 | 0 | 0 | 0 | 170306.4 | 0 | 1008170.4 | 0 |  |  |  |  | 9524.8 |  | DW10 | 100%
502881 | Eredine WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-06-27 | 2033-10-12 | 2034-05-31 | 2034-08-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21104.91 | 934.24 | -20131.81 | 0 | 1907.34 | 0 | 1907.34 | 136478.56 | [6 empty] | WG1 | 100%
502909 | Erradale Street Glasgow Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2017-11-29 | 2018-11-29 | 2018-12-11 | 2020-01-07 | 2020-05-28 | Glasgow City | 0 | 0 | 0 | 765890 | 1036515.77 | 890921.1 | 0 | 2693326.87 | 0 | 2693326.87 | 0 | [6 empty] | CM_WWI | 100%
502820 | Errol WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-09-30 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Perth and Kinross | 0 | 0 | 0 | 62548.68 | 8775.8 | 168610.82 | -80493.43 | 159441.87 | 1733000.08 | 1892441.95 | 136478.56 | [6 empty] | SG1 | 100%
500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-06-26 | 2020-10-09 | Renfrewshire | 0 | 24529 | 88292.38 | 235047.62 | 153697 | 94051.97 | 89679.03 | 685297 | -31925 | 653372 | 522902.82 | [6 empty] | EC01G | 0.8999% | EC10E | 4.03% | EC01D | 19.66% | CS11 | 21.86% | CS16D | 53.55%
503255 | Erskine Road SPS Rising Main Diversion | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-06-21 | 2028-01-14 | 2028-04-17 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 19821.43 | 19821.43 | 355178.58 | 375000.01 | 0 | [6 empty] | CM_WWI | 100%
400066 | Erskine STW Refurb STW000281 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-09-04 | 2011-10-18 | 2011-11-28 | 2015-07-15 |  | Renfrewshire | 4225236.58 | 60049.65 | -571.88 | 541.42 | 0 | 0 | 0 | 60019.19 | 0 | 4285255.77 | 0 |  |  |  |  | 32057 |  | CM_WWNI | 100%
501684 | Erskine trunk mains ITS Phase 1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-02 | 2027-12-06 | 2028-03-02 | 2028-07-17 | 2028-10-13 | Renfrewshire | 0 | 0 | 15537.96 | 6213.07 | 1437.52 | 16739.15 | 0 | 39927.7 | 1496772.32 | 1536700.02 | 0 | [6 empty] | CM_WSI | 100%
503271 | Erskine WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-05-24 | 2022-10-12 | 2023-02-14 | 2024-02-12 | 2024-05-14 | Renfrewshire | 0 | 0 | 0 | 0 | 77147.74 | 61024.32 | 20794.71 | 158966.77 | 841033.31 | 1000000.08 | 136478.56 | [6 empty] | SG1 | 100%
502780 | Erskine WwTW Coarse Screens Replacement CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-06-16 | 2019-08-30 | 2019-09-12 | 2020-11-12 | 2021-02-18 | Renfrewshire | 0 | 0 | 0 | 2911.39 | 82254.07 | 814371.74 | 139792.15 | 1039329.35 | -341.68 | 1038987.67 | 0 | [6 empty] | CM_WWNI | 100%
503102 | ESD Incentivisation Actual | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS2 | 2018-07-09 | 2018-07-09 | 2020-02-07 |  | 2022-09-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 327102.8 | 0 | -0.8 | 327102 | 0 | 327102 | 414328768.69 | [6 empty] | SR15_RSK_EHR | 1.071e-10% | SR15_ENV_HABD | 0.1049% | SR15_ENV_ODO | 0.1052% | SR21_SS | 0.1196% | SR15_CMA_MAG | 0.3211% | SR15_CMA_WSI | 0.6027% | SR15_DWA_SOSI | 0.6116% | SR15_SED_INFC | 0.8638% | SR15_DWA_SRE | 1.283% | SR15_CMP_PLAN | 1.742%
502277 | Establishing Business Alarms within Situational Awareness | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-12-18 | 2018-12-18 | 2019-01-03 | 2019-07-29 | 2019-07-29 | Scottish Water Wide | 0 | 0 | 126533.47 | 15374.53 | 25967 | -151.71 | 0 | 167723.29 | 0 | 167723.29 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
502950 | European Games 2018 South Calder | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2018-05-15 | 2018-05-15 | 2018-05-17 | 2019-02-27 | 2019-02-27 | North Lanarkshire | 0 | 0 | 0 | 0 | 473670.51 | 1520.69 | 690.2 | 475881.4 | 394.15 | 476275.55 | 0 | [6 empty] | CM_WWI | 100%
504261 | E-WE-NI-09122019-Perth RWI - Backwash Pump Replacement(5264) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 2086.6 | -472.6 | 1614 | 0 | 1614 | 0 | [6 empty] | CM_WSI | 100%
505206 | E-W-I-140220-Slainspark DSR-Catterline Pipe renewal(5281) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 7107.76 | -3248.1 | 3859.66 | 0 | 3859.66 | 0 | [6 empty] | CM_WSI | 100%
503906 | E-W-I-21112019-Spynie to Forres Trunk Main-Chlorination (5571) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5972.94 | 66.76 | 6039.7 | 0 | 6039.7 | 0 | [6 empty] | CM_WSI | 100%
504281 | E-W-N-29122019-INVERCANNIE WTW - Refurbishment of Generator Key Components identified as an Issue (6237) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-23 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 9471.93 | 243.95 | 9715.88 | 0 | 9715.88 | 0 | [6 empty] | CM_WSNI | 100%
505485 | E-W-NI-020320-Mannofield WTW - RGF 6 Repair (5914) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 306.6 | 3255.21 | 3561.81 | 0 | 3561.81 | 0 | [6 empty] | CM_WSNI | 100%
504101 | E-W-NI-02122019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 27778.95 | -7758.98 | 20019.97 | 0 | 20019.97 | 0 | [6 empty] | CM_WSNI | 100%
504099 | E-W-NI02122019-CONICAVEL DSR 1994 NH992526-Replace Dupline Analog Transmitter(5580) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1248.78 | 32.16 | 1280.94 | 0 | 1280.94 | 0 | [6 empty] | CM_WSNI | 100%
504090 | E-W-NI-02122019-HERRICKS WTW 1970 NJ458494-005000214085 DAF TANK B Replacement Rotork(5579) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2236.18 | 57.59 | 2293.77 | 0 | 2293.77 | 0 | [6 empty] | CM_WSNI | 100%
504107 | E-W-NI-02122019-HERRICKS WTW-Replace Pac Dosing Pump A(5581) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1082.26 | 27.87 | 1110.13 | 0 | 1110.13 | 0 | [6 empty] | CM_WSNI | 100%
504088 | E-W-NI-02122019-KIRBISTER RWI 1962 HY369073-land purchase(5034) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 16115.06 | -624.61 | 15490.45 | 0 | 15490.45 | 0 | [6 empty] | CM_WSI | 100%
504114 | E-W-NI-03022019-TOMNAVOULIN WTW-Raised Platform for ULTRA MEMBRANE(5583) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1712 | -643.73 | 1068.27 | 0 | 1068.27 | 0 | [6 empty] | CM_WSNI | 100%
504983 | E-W-NI-030220-Boardhouse WTW-Alum Auger replacement (5051) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 8159.17 | 3017.78 | 11176.95 | 0 | 11176.95 | 0 | [6 empty] | CM_WSNI | 100%
504990 | E-W-NI-030220-Glenlatterach WTW - Treated / Filter HMI (5605) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5630.88 | 0 | 5630.88 | 0 | 5630.88 | 0 | [6 empty] | CM_WSNI | 100%
504988 | E-W-NI-030220-Skerries WTW - Code changes for auto shutdown improvement (5048) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 1132.21 | 418.76 | 1550.97 | 0 | 1550.97 | 0 | [6 empty] | CM_WSNI | 100%
504984 | E-W-NI-030220-Westray WTW - Storm Damage - Intake flood light replacement (5050) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1477.49 | -396.21 | 1081.28 | 0 | 1081.28 | 0 | [6 empty] | CM_WSNI | 100%
504120 | E-W-NI-03122019-BADENTINAN WTW-replacement valve for cell D(5585) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2049.04 | 52.77 | 2101.81 | 0 | 2101.81 | 0 | [6 empty] | CM_WSNI | 100%
504128 | E-W-NI-03122019-GLENLATTERACH WTW-installation of extraction fan in room(5586) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 744.33 | 19.17 | 763.5 | 0 | 763.5 | 0 | [6 empty] | CM_WSNI | 100%
504131 | E-W-NI-03122019-LINTRATHEN WTW-Refurb Sludge Press(5259) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 7101.87 | -4041.37 | 3060.5 | 0 | 3060.5 | 0 | [6 empty] | CM_WSNI | 100%
504116 | E-W-NI-03122019-SPYNIE DSR 1976-Replace Corroded Covers(5584) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3696.85 | -1390.06 | 2306.79 | 0 | 2306.79 | 0 | [6 empty] | CM_WSNI | 100%
505004 | E-W-NI-040220-Glenfarg WTW-DAFT Tank 2 Scraper Replace Gearbox(5275) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4159.51 | -1114.96 | 3044.55 | 0 | 3044.55 | 0 | [6 empty] | CM_WSNI | 100%
505012 | E-W-NI-040220-WESTHILLS SERVICE RES-Replace Chloinator Pumps(5276) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1391.5 | 0 | 1391.5 | 0 | 1391.5 | 0 | [6 empty] | CM_WSNI | 100%
504140 | E-W-NI-04122019-Boardhouse WTW Alum pump flow switch enhancement (5035) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1222.91 | -10.55 | 1212.36 | 0 | 1212.36 | 0 | [6 empty] | CM_WSNI | 100%
504143 | E-W-NI-04122019-GLENDEVON WTW-GLENDEVON MODIFICATION TO 3-STREAM AZTEC(5260) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2486.44 | 64.04 | 2550.48 | 0 | 2550.48 | 0 | [6 empty] | CM_WSNI | 100%
504152 | E-W-NI-04122019-GLENLATTERACH WTW-replacement power screw feeders(5587) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2471.7 | -929.4 | 1542.3 | 0 | 1542.3 | 0 | [6 empty] | CM_WSNI | 100%
504148 | E-W-NI-04122019-KEMBACK TWP-Replace Pump(5261) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2961.55 | -1113.58 | 1847.97 | 0 | 1847.97 | 0 | [6 empty] | CM_WSNI | 100%
504160 | E-W-NI-04122019-Whitehillocks WTW-replacement alum aztec monitor required(5588) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 13812.54 | -4040.54 | 9772 | 0 | 9772 | 0 | [6 empty] | CM_WSNI | 100%
505559 | E-W-NI-050320-GLENFARG WTW - Emergency Lighting (5291) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-13 |  | 2020-06-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 349.65 | 4995 | 5344.65 | 0 | 5344.65 | 0 | [6 empty] | CM_WSNI | 100%
504174 | E-W-NI-05122019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2208.94 | -780.67 | 1428.27 | 0 | 1428.27 | 0 | [6 empty] | CM_WSNI | 100%
504181 | E-W-NI-05122019-Denfind TWP-Monikie TWS level control system(5262) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2797.41 | -1076.67 | 1720.74 | 0 | 1720.74 | 0 | [6 empty] | CM_WSNI | 100%
504180 | E-W-NI-05122019-KEMBACK TWP-Replace Pump(5261) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1801.57 | 46.4 | 1847.97 | 0 | 1847.97 | 0 | [6 empty] | CM_WSNI | 100%
505589 | E-W-NI-060320-Glenlatterach WTW - Polymer Dosing Pumps (5611) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-06-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 600.68 | 8581.2 | 9181.88 | 0 | 9181.88 | 0 | [6 empty] | CM_WSNI | 100%
505583 | E-W-NI-060320-Papa Stour WTW-GAC vessel replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 2239.53 | 0 | 2239.53 | 0 | 2239.53 | 0 | [6 empty] | CM_WSNI | 100%
505575 | E-W-NI-060320-Skerries WTW-Provision of CO2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 2239.53 | 0 | 2239.53 | 0 | 2239.53 | 0 | [6 empty] | CM_WSNI | 100%
504223 | E-W-NI-06122019-NEWTYLE DSR-Renew inlet meter(5263) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1637.02 | 42.16 | 1679.18 | 0 | 1679.18 | 0 | [6 empty] | CM_WSNI | 100%
504573 | E-W-NI-08012020-FOREHILL WTW - Replacement UPS Batteries (6238) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5414.41 | -133.86 | 5280.55 | 0 | 5280.55 | 0 | [6 empty] | CM_WSNI | 100%
504568 | E-W-NI-08012020-MANNOFIELD TWP 2 1986 NJ916041-Replace 005000203807 MOTOR CONTROL CENTRE (6238) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 30182.97 | -15309.99 | 14872.98 | 0 | 14872.98 | 0 | [6 empty] | CM_WSNI | 100%
504586 | E-W-NI-09012020-GLENDEVON WTW-Glendevon source inlet valve actuator (6242) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 4034.7 | -1524.58 | 2510.12 | 0 | 2510.12 | 0 | [6 empty] | CM_WSNI | 100%
504583 | E-W-NI-09012020-INVERCANNIE WTW-GLENFARG WTW-ALUM DOSING PUMP A (6241) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 3053.71 | -1212.56 | 1841.15 | 0 | 1841.15 | 0 | [6 empty] | CM_WSNI | 100%
504579 | E-W-NI-09012020-INVERCANNIE WTW-Investigation Hermetically sealed Transformers refurbishment (6240) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2802.94 | 92.58 | 2895.52 | 0 | 2895.52 | 0 | [6 empty] | CM_WSNI | 100%
504244 | E-W-NI-09122019-Glenlatterach WTW-Relocation of Settled Water Sample Point (5590) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  |  |  | Moray | 0 | 0 | 0 | 0 | 0 | 821.44 | 21.16 | 842.6 | 0 | 842.6 | 0 | [6 empty] | CM_WSNI | 100%
504240 | E-W-NI-09122019-Tomnavoulin WTW-Roof Repairs (4022) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 2754.41 | 70.94 | 2825.35 | 0 | 2825.35 | 0 | [6 empty] | CM_WSNI | 100%
504603 | E-W-NI-10012020-Boardhouse WTW - interstage pump motor replacement (5039) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1006.69 | -246.74 | 759.95 | 0 | 759.95 | 0 | [6 empty] | CM_WSNI | 100%
504594 | E-W-NI-10012020-FOREHILL WTW-Replace 005000333076 FINAL LIME DOSE PUMP (6243) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 8855.8 | -3346.7 | 5509.1 | 0 | 5509.1 | 0 | [6 empty] | CM_WSNI | 100%
505124 | E-W-NI-100220-Glenlatterach WTW - Coagulation pH Trial (SPG012) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4779.79 | 1767.87 | 6547.66 | 0 | 6547.66 | 0 | [6 empty] | CM_WSNI | 100%
505108 | E-W-NI-100220-Invercannie WTW - Replace Coag pH Monitors (SPG003) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 31426.78 | 11623.6 | 43050.38 | 0 | 43050.38 | 0 | [6 empty] | CM_WSNI | 100%
505119 | E-W-NI-100220-Turriff WTW - Install Acid Flush to Improve Coag pH Dosing (SPG007) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 4692.53 | 416.73 | 5109.26 | 0 | 5109.26 | 0 | [6 empty] | CM_WSNI | 100%
505117 | E-W-NI-100220-Turriff WTW - Install Alum Pump Pulsation Dampers (SPG006) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5350.54 | 1978.96 | 7329.5 | 0 | 7329.5 | 0 | [6 empty] | CM_WSNI | 100%
505112 | E-W-NI-100220-Turriff WTW - Install Secondary pH Monitor (SPG004) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 11950.83 | 4420.17 | 16371 | 0 | 16371 | 0 | [6 empty] | CM_WSNI | 100%
505115 | E-W-NI-100220-Turriff WTW - Press Repairs (SPG005) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 14915.89 | 5516.83 | 20432.72 | 0 | 20432.72 | 0 | [6 empty] | CM_WSNI | 100%
505123 | E-W-NI-100220-Turriff WTW - Replace 3Nr. Sludge Air Compressors (SPG008) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 14059.8 | 5200.2 | 19260 | 0 | 19260 | 0 | [6 empty] | CM_WSNI | 100%
504285 | E-W-NI-10122019-MONIKIE TWP-Renew PUMP 2(5265) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 13333.83 | -4849.46 | 8484.37 | 0 | 8484.37 | 0 | [6 empty] | CM_WSNI | 100%
505105 | E-W-NI-102020-Inchgarth RWP - Automatic Shutdown of RWI on Various Pollution Monitoring Parameters (SPG002) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5872.31 | 2171.95 | 8044.26 | 0 | 8044.26 | 0 | [6 empty] | CM_WSNI | 100%
505153 | E-W-NI-120220-Balbeuchley TWS- Pump 2 replacement(5279) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1670.81 | 0 | 1670.81 | 0 | 1670.81 | 0 | [6 empty] | CM_WSNI | 100%
505156 | E-W-NI-120220-Eela Water WTW - Survey for Clarifier flow control upgrade (5055) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 1002.66 | 390.64 | 1393.3 | 0 | 1393.3 | 0 | [6 empty] | CM_WSNI | 100%
504336 | E-W-NI-12122019-Boardhouse WTW - Guttering repair and clean (5038) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-23 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 4194.35 | 60.91 | 4255.26 | 0 | 4255.26 | 0 | [6 empty] | CM_WSNI | 100%
504626 | E-W-NI-13012020-Herricks WTW - Installation of DOC Panels and Debubblers (5527) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 7914.27 | -2990.88 | 4923.39 | 0 | 4923.39 | 0 | [6 empty] | CM_WSNI | 100%
504351 | E-W-NI-15122019-Glenfarg WTW - PLC1 modifications (5266) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-23 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 4237.2 | -1083.41 | 3153.79 | 0 | 3153.79 | 0 | [6 empty] | CM_WSNI | 100%
504349 | E-W-NI-15122019-Kirbister WTW- uttering repair and clean (5037) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 289.68 | 4448.28 | 4737.96 | 0 | 4737.96 | 0 | [6 empty] | CM_WSNI | 100%
504350 | E-W-Ni-15122019-Turriff WTW - Contact Steps Repair (5898) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6305.62 | 91.57 | 6397.19 | 0 | 6397.19 | 0 | [6 empty] | CM_WSNI | 100%
504689 | E-W-NI-16012020-BALCARRES TWP - RADIO OUTSTATION RENEWAL (5250) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3794.5 | -1578.88 | 2215.62 | 0 | 2215.62 | 0 | [6 empty] | CM_WSNI | 100%
504681 | E-W-NI-16012020-Peterhead Newfield TWP Replacement Power Module (5900) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 7718.87 | -2917.03 | 4801.84 | 0 | 4801.84 | 0 | [6 empty] | CM_WSNI | 100%
505759 | E-W-NI-170320-Turriff Muiresk RWP - Replace Contactors on MCC No1 (5920) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-06-18 |  | 2020-06-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4448.38 | -830.95 | 3617.43 | 0 | 3617.43 | 0 | [6 empty] | CM_WSNI | 100%
505259 | E-W-NI-180220-Craighead WTW - Soda Ash Vacuum Unit (5560) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1498.27 | 554.15 | 2052.42 | 0 | 2052.42 | 0 | [6 empty] | CM_WSNI | 100%
505265 | E-W-NI-180220-Forehill WTW - Replace Access Steps to Poly Dosing Unit (5911) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1025.69 | 437 | 1462.69 | 0 | 1462.69 | 0 | [6 empty] | CM_WSNI | 100%
505272 | E-W-NI-180220-Invercannie WTW - Install Auto-Desludge Sequence to Thickeners (5908) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2599.01 | 961.28 | 3560.29 | 0 | 3560.29 | 0 | [6 empty] | CM_WSNI | 100%
505251 | E-W-NI-180220-INVERCANNIE WTW-Kirbister WTW - replace both Sludge Poly dosing pumps (5058) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 2278.54 | 180 | 2458.54 | 0 | 2458.54 | 0 | [6 empty] | CM_WSNI | 100%
505252 | E-W-NI-180220-Pourie TWS - Door Repair (5280) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 1991.81 | 736.69 | 2728.5 | 0 | 2728.5 | 0 | [6 empty] | CM_WSNI | 100%
505796 | E-W-NI-180320-Invercannie WTW - Replace VSD Sludge Pump 2 (5922) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-06-19 |  | 2020-06-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2432 | 170.23 | 2602.23 | 0 | 2602.23 | 0 | [6 empty] | CM_WSNI | 100%
503856 | E-W-NI-18112019-Lomondhills WTW-Critical Spare actuator (5253) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4579.88 | -1569.4 | 3010.48 | 0 | 3010.48 | 0 | [6 empty] | CM_WSI | 100%
505335 | E-W-NI-200220-Boardhouse WTW - roof repair (5049) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  |  |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 19715.85 | 1750.92 | 21466.77 | 0 | 21466.77 | 0 | [6 empty] | CM_WSNI | 100%
505860 | E-W-NI-200320-River Earn RWP 5 - Rewind Motor (5309) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-02 |  | 2020-06-21 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 18778.49 | 18778.49 | 0 | 18778.49 | 0 | [6 empty] | CM_WSNI | 100%
505332 | E-W-NI-202020-Turriff WTW - Modify Hypo Dosing Control (5903) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2522.31 | 224 | 2746.31 | 0 | 2746.31 | 0 | [6 empty] | CM_WSNI | 100%
503915 | E-W-NI-21112019-Badentinan WTW-Temporary Fuel Storage (5575) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1710.72 | 26.19 | 1736.91 | 0 | 1736.91 | 0 | [6 empty] | CM_WSNI | 100%
503910 | E-W-NI-21112019-Craighead WTW-Air Saturator Flow Meter (5574) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 702.52 | -246.8 | 455.72 | 0 | 455.72 | 0 | [6 empty] | CM_WSNI | 100%
503922 | E-W-NI-21112019-Muiresk RWI-Pump No1 bearing replacement (5883) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 11520.8 | -5982.16 | 5538.64 | 0 | 5538.64 | 0 | [6 empty] | CM_WSNI | 100%
503920 | E-W-NI-21112019-Ordiequish RWP-Pump Connections (5576) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2545.65 | -774.54 | 1771.11 | 0 | 1771.11 | 0 | [6 empty] | CM_WSNI | 100%
503934 | E-W-NI-22112019-Cairnton RWI-River Intake Actuator replacement (5889) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 11663.25 | 178.57 | 11841.82 | 0 | 11841.82 | 0 | [6 empty] | CM_WSI | 100%
503938 | E-W-NI-22112019-Forehill WTW-GAC interstage pump VSD replacement (5890) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3220.7 | -979.94 | 2240.76 | 0 | 2240.76 | 0 | [6 empty] | CM_WSNI | 100%
503928 | E-W-NI-22112019-Turriff WTW-Lime pump spares (5888) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3930.7 | -1195.96 | 2734.74 | 0 | 2734.74 | 0 | [6 empty] | CM_WSNI | 100%
505916 | E-W-NI-240320-Invercannie WTW - Sludge Feed Pump 3 (5927) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-06-25 |  | 2020-06-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1770.09 | 2314.06 | 4084.15 | 0 | 4084.15 | 0 | [6 empty] | CM_WSNI | 100%
505913 | E-W-NI-240320-Lettar of Ballied Bladder Replacement (5293) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-06-25 |  | 2020-06-25 |  | Angus | 0 | 0 | 0 | 0 | 0 | 3660 | 256.2 | 3916.2 | 0 | 3916.2 | 0 | [6 empty] | CM_WSNI | 100%
505401 | E-W-NI-250220-Eela water WTW - FRA action (5060) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 1275.47 | 471.75 | 1747.22 | 0 | 1747.22 | 0 | [6 empty] | CM_WSNI | 100%
505403 | E-W-NI-250220-Turriff WTW - Replace Filter Press Cloths (5912) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 7525.66 | 2783.47 | 10309.13 | 0 | 10309.13 | 0 | [6 empty] | CM_WSNI | 100%
503957 | E-W-NI-25112019-LINTRATHEN WTW-Replace SUPERNATENT RETURN PUMP (5254) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 4378.53 | -284.86 | 4093.67 | 0 | 4093.67 | 0 | [6 empty] | CM_WSNI | 100%
503967 | E-W-NI-25112019-Mannofield TWP-Refurbish Pump 3 (6235) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 27666.22 | -8417.73 | 19248.49 | 0 | 19248.49 | 0 | [6 empty] | CM_WSNI | 100%
503994 | E-W-NI-26112019-MANNOFIELD WTW-Change Fixed Speed Poly Mixers to Variable (5892) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 8115.57 | 124.26 | 8239.83 | 0 | 8239.83 | 0 | [6 empty] | CM_WSNI | 100%
503987 | E-W-NI-26112019-TURRIFF TWP-Highlift Pump Repair Motor (5891) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 13685.3 | -4163.91 | 9521.39 | 0 | 9521.39 | 0 | [6 empty] | CM_WSNI | 100%
504016 | E-W-NI-27112019-DALACHY TWP-Replace BOOSTER PUMP NO1 (5255) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2789.88 | 57.93 | 2847.81 | 0 | 2847.81 | 0 | [6 empty] | CM_WSNI | 100%
504886 | E-W-NI-28012020-GLENDEVON WTW- SODIUM HYPOCHLORITE STORAGE TANK A (5270) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 33060.49 | -6371.88 | 26688.61 | 0 | 26688.61 | 0 | [6 empty] | CM_WSNI | 100%
505461 | E-W-NI-280220-Auchtermuchty DSR - Contribution to access track upgrade (5283) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 11407.78 | 173.01 | 11580.79 | 0 | 11580.79 | 0 | [6 empty] | CM_WSNI | 100%
504038 | E-W-NI-28112019-INVERCANNIE WTW-Add Missing Telem Signals (5893) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2648 | -982.54 | 1665.46 | 0 | 1665.46 | 0 | [6 empty] | CM_WSNI | 100%
504062 | E-W-NI-28112019-INVERCANNIE WTW-SLUDGE PRESSING LATE PRESS REfURB(5894) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5092.83 | -1873.83 | 3219 | 0 | 3219 | 0 | [6 empty] | CM_WSNI | 100%
504054 | E-W-NI-28112019-KIRRIEMUIR HIGH DSR NO393547-Replace Telem Kiosk(5257) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 5216.25 | -1935.48 | 3280.77 | 0 | 3280.77 | 0 | [6 empty] | CM_WSNI | 100%
504913 | E-W-NI-290120-Badentinan CWT - Replacement UPS (5601) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1165.43 | 0 | 1165.43 | 0 | 1165.43 | 0 | [6 empty] | CM_WSNI | 100%
504910 | E-W-NI-290120-Clatto WTW - Raw water main Inspection (5268) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 2464.12 | 0 | 2464.12 | 0 | 2464.12 | 0 | [6 empty] | CM_WSNI | 100%
504909 | E-W-NI-290120-Herricks WTW-DAF Outlet Valves (5603) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5347.35 | 1020.06 | 6367.41 | 0 | 6367.41 | 0 | [6 empty] | CM_WSNI | 100%
504918 | E-W-NI-290120-Loch of Boardhouse RWI - Inlet screen winch replacement (5042) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 6897 | 1315.67 | 8212.67 | 0 | 8212.67 | 0 | [6 empty] | CM_WSI | 100%
504926 | E-W-NI-290120-Sandy Loch WTW - Inlet Valve replacement (5045) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 4846.64 | 924.54 | 5771.18 | 0 | 5771.18 | 0 | [6 empty] | CM_WSNI | 100%
504043 | E-W-NI-29112019-Caddam BM Kiosk-Replace Kiosk (5894) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4875 | -1594.23 | 3280.77 | 0 | 3280.77 | 0 | [6 empty] | CM_WSNI | 100%
504071 | E-W-NI-29112019-CULTS PITFODELS TWP-Refurb Pump as Critical Spare(5896) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 8824.29 | -431.67 | 8392.62 | 0 | 8392.62 | 0 | [6 empty] | CM_WSNI | 100%
504080 | E-W-NI-29112019-GLENLATTERACH WTW-Replace Lime Dosing Pump 1(5578) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3249.83 | -828.74 | 2421.09 | 0 | 2421.09 | 0 | [6 empty] | CM_WSNI | 100%
504079 | E-W-Ni29112019-MANNOFIELD TWP 2- Repair Pump No3 5897 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 922.21 | 922.21 | 0 | 922.21 | 0 | [6 empty] | CM_WSNI | 100%
504076 | E-W-NI-29112019-TURRIFF WTW-Generator control unit (5895) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1865.35 | 38.74 | 1904.09 | 0 | 1904.09 | 0 | [6 empty] | CM_WSNI | 100%
505211 | E-W-NI-31012019-Loch Lee-Wash Day with silt trap (5272) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1432.59 | 127.22 | 1559.81 | 0 | 1559.81 | 0 | [6 empty] | CM_WSNI | 100%
504969 | E-W-NI-31012020-PANMURE TWP-Replace Flow Meter(5273) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1494.72 | 0 | 1494.72 | 0 | 1494.72 | 0 | [6 empty] | CM_WSNI | 100%
504958 | E-W-NI-Badentinan WTW - Sodium Hypochlorite Dosing Control (5602) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 7905.72 | 1508.09 | 9413.81 | 0 | 9413.81 | 0 | [6 empty] | CM_WSNI | 100%
503851 | E-W-NI-Balreavie TWS - 18112019 - Balreavie TWS - Replace Telemetry kiosk (5252) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 6088.3 | -1852.43 | 4235.87 | 0 | 4235.87 | 0 | [6 empty] | CM_WSNI | 100%
504889 | E-W-NI-BANKFOOT DSR-280120-Contribution for Access Track Repairs(5271) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 426.46 | 5.43 | 431.89 | 0 | 431.89 | 0 | [6 empty] | CM_WSNI | 100%
505185 | E-W-NI-Cullen TWP - RTU Replacement (5907) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4733.87 | 1750.89 | 6484.76 | 0 | 6484.76 | 0 | [6 empty] | CM_WSNI | 100%
505179 | E-W-NI-Forehill WTW - Replace Poly Dosing Pump 2 (5905) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1476.67 | 546.17 | 2022.84 | 0 | 2022.84 | 0 | [6 empty] | CM_WSNI | 100%
504734 | E-W-NI-GLENDEVON WTW-Backwash pump No4 inverter replacement(6247) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4813.81 | -1819.11 | 2994.7 | 0 | 2994.7 | 0 | [6 empty] | CM_WSNI | 100%
505022 | E-W-NI-GLENFARG WTW-PRESS CLOTH WASH PUMP Refurbishment(5277) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6948.38 | 0.2 | 6948.58 | 0 | 6948.58 | 0 | [6 empty] | CM_WSNI | 100%
504771 | E-W-NI-Herricks WTW - Control System Modifications (5599) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1862.01 | -703.67 | 1158.34 | 0 | 1158.34 | 0 | [6 empty] | CM_WSNI | 100%
505178 | E-W-NI-Herricks WTW - Radon Mitigation (5560) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5091.21 | 1883.05 | 6974.26 | 0 | 6974.26 | 0 | [6 empty] | CM_WSNI | 100%
505172 | E-W-NI-Inchgarth RWP - Repair Cavity Wall Ties (5909) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3983.61 | 1473.39 | 5457 | 0 | 5457 | 0 | [6 empty] | CM_WSNI | 100%
504730 | E-W-NI-INCHGARTH RWP-LOW LIFT PUMP 3 Refurbishment (6245) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 9911.03 | 327.35 | 10238.38 | 0 | 10238.38 | 0 | [6 empty] | CM_WSNI | 100%
503924 | E-W-NI-Invercannie WTW-CIP pump refurbishment to become a spare (5885) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5741.52 | 87.91 | 5829.43 | 0 | 5829.43 | 0 | [6 empty] | CM_WSNI | 100%
504802 | E-W-NI-Killiecrankie WTW Turbidity monitors(5269) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 9989.02 | 329.93 | 10318.95 | 0 | 10318.95 | 0 | [6 empty] | CM_WSNI | 100%
504738 | E-W-NI-Lagahorie SR - Safety Improvement (5593) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 9653.01 | -3647.97 | 6005.04 | 0 | 6005.04 | 0 | [6 empty] | CM_WSNI | 100%
504692 | E-W-NI-Mannofield WTW - Laboratory Coagulation Analyser (5866) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 | 2020-04-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 13461.07 | -5178 | 8283.07 | 0 | 8283.07 | 0 | [6 empty] | CM_WSNI | 100%
505183 | E-W-NI-Mannofield WTW Final Water Instrumentation (4269) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW1 |  | 2020-06-08 | 2020-08-07 | 2021-03-25 | 2021-03-26 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 65.42 | 0 | 65.42 | 0 | 65.42 | 0 | [6 empty] | CM_WSNI | 100%
504731 | E-W-NI-Ordiequish RWP-TRANSFER PUMP A Refurbish(6246) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6336.73 | 209.3 | 6546.03 | 0 | 6546.03 | 0 | [6 empty] | CM_WSNI | 100%
505018 | E-W-NI-PERTH WTW TWP-BURGHMUIR PUMP 3 Strip and Repair(5277) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 9279.8 | 500 | 9779.8 | 0 | 9779.8 | 0 | [6 empty] | CM_WSNI | 100%
504765 | E-W-NI-Spey Wellfield - Replacement Borehole Pump (5595) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6637.83 | 219.24 | 6857.07 | 0 | 6857.07 | 0 | [6 empty] | CM_WSNI | 100%
504642 | E-W-NI-Staney Hill TWP - Pump 2 replacement (5043) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 8104.5 | -3062.97 | 5041.53 | 0 | 5041.53 | 0 | [6 empty] | CM_WSNI | 100%
504684 | E-W-NI-Stromness DSR - perimeter fence repair (5044) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-04-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1326.8 | 43.82 | 1370.62 | 0 | 1370.62 | 0 | [6 empty] | CM_WSNI | 100%
505176 | E-W-NI-Turriff WTW - Replace RGF 6 Actuator (5901) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2122.25 | 784.94 | 2907.19 | 0 | 2907.19 | 0 | [6 empty] | CM_WSNI | 100%
505550 | E-WW-04032020-DUNKELD WEST BIRNAM WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-06-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 131.76 | 1882.27 | 2014.03 | 0 | 2014.03 | 0 | [6 empty] | CM_WWNI | 100%
504963 | E-WW-31012020-DRUM WWTW-SUPPLY 12 VALVES (CRITICAL SPARES FOR NETWORK VACCUM SYSTEM) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 16048.02 | 0 | 16048.02 | 0 | 16048.02 | 0 | [6 empty] | CM_WWNI | 100%
504279 | E-WW-I-031219-7 ST GILES TCEDUNDEE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 | 2020-03-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 1331.27 | 0 | 1331.27 | 0 | 1331.27 | 0 | [6 empty] | CM_WWI | 100%
504365 | E-WW-I-041219-6 TRAQUIAR GARDENSPERTH-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 | 2020-03-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 31030 | 0 | 31030 | 0 | 31030 | 0 | [6 empty] | CM_WWI | 100%
504719 | E-WW-I-06012020-ASHBYGARVOCK RDLAURENCEKIRK-SEWER REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2449.61 | 0 | 2449.61 | 0 | 2449.61 | 0 | [6 empty] | CM_WWI | 100%
505159 | E-WW-I-06022020-213 BROAD STCOWDENBEATH-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-14 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | 4280 | 0 | 4280 | 0 | [6 empty] | CM_WWI | 100%
505168 | E-WW-I-06022020-51 SHAFTSBURY RDDUNDEE-SEWER RELAY 3M. | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-13 |  | 2020-03-31 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 1819 | 0 | 1819 | 0 | 1819 | 0 | [6 empty] | CM_WWI | 100%
505164 | E-WW-I-07022020-10 ABERDEEN AVEKINGHORN-INSTALL MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-13 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3210 | 0 | 3210 | 0 | 3210 | 0 | [6 empty] | CM_WWI | 100%
504823 | E-WW-I-09012020-36 GRANGE PLACEARBROATH-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 6588.54 | -3190.36 | 3398.18 | 0 | 3398.18 | 0 | [6 empty] | CM_WWI | 100%
505297 | E-WW-I-11022020-1 DENBURN PLACEKIRKCALDY-SEWER REHAB 5M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 5004.83 | 0 | 5004.83 | 0 | 5004.83 | 0 | [6 empty] | CM_WWI | 100%
505290 | E-WW-I-11022020-19 LANGHOUSE GREENCRAIL-SEWER REHAB 3M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2758.43 | 0 | 2758.43 | 0 | 2758.43 | 0 | [6 empty] | CM_WWI | 100%
505231 | E-WW-I-11-02-2020-DUNCHOPPIN-NEW BYTH-TURRIFF-SEWER REHAB 7M- | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1945.44 | 0 | 1945.44 | 0 | 1945.44 | 0 | [6 empty] | CM_WWI | 100%
504055 | E-WW-I-111119-25 ROSEANGLEDUNDEE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 | 2020-03-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 8145.76 | -3231.4 | 4914.36 | 0 | 4914.36 | 0 | [6 empty] | CM_WWI | 100%
504102 | E-WW-I-111119-BULLION COTTAGESINVERGOWRIE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-31 | 2020-03-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1810.62 | -146.52 | 1664.1 | 0 | 1664.1 | 0 | [6 empty] | CM_WWI | 100%
505304 | E-WW-I-12022020-108 THE HAZELSDUNDEE-SEWER REHAB 7M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2020-03-31 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 6903.57 | 0 | 6903.57 | 0 | 6903.57 | 0 | [6 empty] | CM_WWI | 100%
505213 | E-WW-I-12022020-62 FRITHSIDE STFRASERBURGH-RECURRING CHOKES | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-17 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 9991.63 | 0 | 9991.63 | 0 | 9991.63 | 0 | [6 empty] | CM_WWI | 100%
505201 | E-WW-I-12022020-72 MAIN STLEUCHARS-INSTALL MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-14 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1804.77 | 0 | 1804.77 | 0 | 1804.77 | 0 | [6 empty] | CM_WWI | 100%
505197 | E-WW-I-12022020-78 LUMPHINANS RDLOCHGELLY-REPLACE MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-17 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1408.12 | 0 | 1408.12 | 0 | 1408.12 | 0 | [6 empty] | CM_WWI | 100%
504453 | E-WW-I-121219-2 EAST GLEBE STONEHAVEN-REBUILD MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 | 2020-03-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2263.79 | 0 | 2263.79 | 0 | 2263.79 | 0 | [6 empty] | CM_WWI | 100%
504643 | E-WW-I-13012020-WOODSIDE COTTAGELUTHERMUIR-SEWER REHAB-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1294.03 | 0 | 1294.03 | 0 | 1294.03 | 0 | [6 empty] | CM_WWI | 100%
504829 | E-WW-I-14012020-50 ANNAND RDELLON-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4028.48 | -904.3 | 3124.18 | 0 | 3124.18 | 0 | [6 empty] | CM_WWI | 100%
504837 | E-WW-I-16012020-4 ELRICK CIRCLEBRIDGE OF DON-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 5663.7 | 27.84 | 5691.54 | 0 | 5691.54 | 0 | [6 empty] | CM_WWI | 100%
504834 | E-WW-I-16012020-75 LYNINGHILLSFOFAR-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 5567.5 | -173.74 | 5393.76 | 0 | 5393.76 | 0 | [6 empty] | CM_WWI | 100%
505306 | E-WW-I-17022020- 1 LICKLEY STREETPERTH-SEWER REHAB 3M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1719.24 | 0 | 1719.24 | 0 | 1719.24 | 0 | [6 empty] | CM_WWI | 100%
504501 | E-WW-I-171219-56 JUSTICE MILL LANEABERDEEN-SEWER REHAB 3.5M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 | 2020-03-31 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 3772.98 | 0 | 3772.98 | 0 | 3772.98 | 0 | [6 empty] | CM_WWI | 100%
504503 | E-WW-I-191219-47 HAUGH ROADELGIN-SEWER REHAB 5.5M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 | 2020-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 9647.84 | 0 | 9647.84 | 0 | 9647.84 | 0 | [6 empty] | CM_WWI | 100%
504463 | E-WW-I-191219-ROSELEA COTTAGEGUILDTOWN-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 | 2020-03-31 | Fife | 0 | 0 | 0 | 0 | 0 | 860.68 | 0 | 860.68 | 0 | 860.68 | 0 | [6 empty] | CM_WWI | 100%
504956 | E-WW-I-22012020-49 DUNNICHEN RDKINGSMUIR-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 8297.58 | 0 | 8297.58 | 0 | 8297.58 | 0 | [6 empty] | CM_WWI | 100%
504861 | E-WW-I-24012020-27 JAMES MITCHELL PLACEMINTLAW-MANHOLE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2421.5 | -543.57 | 1877.93 | 0 | 1877.93 | 0 | [6 empty] | CM_WWI | 100%
505035 | E-WW-I-27012020-11 DORWOOD PLACEMONTROSE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | 4280 | 0 | 4280 | 0 | [6 empty] | CM_WWI | 100%
504185 | E-WW-I-271119-15 METHVEN ROADKIRKCALDY-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 | 2020-03-31 | Fife | 0 | 0 | 0 | 0 | 0 | 5511.52 | -2082.87 | 3428.65 | 0 | 3428.65 | 0 | [6 empty] | CM_WWI | 100%
505019 | E-WW-I-28012020-CLAYPOPTTS FC-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 18190 | 0 | 18190 | 0 | 18190 | 0 | [6 empty] | CM_WWI | 100%
505556 | E-WW-I-28022020-PITMEDDEN OUTFALL-CONSTRUCT NEW ACCESS STEPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-06 |  | 2020-06-04 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 308.84 | 4412.01 | 4720.85 | 0 | 4720.85 | 0 | [6 empty] | CM_WWI | 100%
504273 | E-WW-I291119-COLLEGE MILL RDALMONDBANK-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 | 2020-03-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 4269.93 | -1607.38 | 2662.55 | 0 | 2662.55 | 0 | [6 empty] | CM_WWI | 100%
503908 | E-WW-I-301019-HAUGHS OF COSSANS FORFAR-REPAIR MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 | 2020-03-31 | Angus | 0 | 0 | 0 | 0 | 0 | 2544.41 | -137.55 | 2406.86 | 0 | 2406.86 | 0 | [6 empty] | CM_WWI | 100%
506016 | E-WW-I-31032020-37 HOLYROOD ST CARNOUSTIE-SEWER REHAB 35M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-04-01 |  | 2020-06-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 14400.06 | 14400.06 | 0 | 14400.06 | 0 | [6 empty] | CM_WWI | 100%
503882 | E-WW-I-41119-3 ASHGROVE ROAD-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 | 2020-03-31 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 13652.75 | -2302.23 | 11350.52 | 0 | 11350.52 | 0 | [6 empty] | CM_WWI | 100%
503887 | E-WW-I-51119-197 WESTBURN RD-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 | 2020-03-31 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 4955.3 | 0 | 4955.3 | 0 | 4955.3 | 0 | [6 empty] | CM_WWI | 100%
503901 | E-WW-I-51119-75 MAIN STNEWMILLS-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 | 2020-03-31 | Fife | 0 | 0 | 0 | 0 | 0 | 16281.69 | 0 | 16281.69 | 0 | 16281.69 | 0 | [6 empty] | CM_WWI | 100%
506041 | E-WW-NI-01042020-DRUMLITHIE WWTW-REPLACE ROTORK VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2020-07-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1761.76 | 1761.76 | 0 | 1761.76 | 0 | [6 empty] | CM_WWNI | 100%
505491 | E-WW-NI-02032020-BURNTISLAND STW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1952.87 | 0 | 1952.87 | 0 | 1952.87 | 0 | [6 empty] | CM_WWNI | 100%
505647 | E-WW-NI-02032020-CHARLOTTE ST WWPS-SUPPLY 20FT STORAGE CONTAINER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 185.5 | 2649.99 | 2835.49 | 0 | 2835.49 | 0 | [6 empty] | CM_WWNI | 100%
505659 | E-WW-NI-03032020-MONTROSE COBDEN ST WWPS-REPLACE GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 3225.66 | 0 | 3225.66 | 0 | 3225.66 | 0 | [6 empty] | CM_WWNI | 100%
505030 | E-WW-NI-04022020-BRECHIN WWTW-REPLACE NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1534.79 | 0 | 1534.79 | 0 | 1534.79 | 0 | [6 empty] | CM_WWNI | 100%
505134 | E-WW-NI-04022020-NEWPORT & TAYPORT WWTW-REPLACE SLUDGE MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 6672.97 | 2468.09 | 9141.06 | 0 | 9141.06 | 0 | [6 empty] | CM_WWNI | 100%
505672 | E-WW-NI-04032020-FORGANDENNY WWTW-REPLACE BLOWER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 3699.93 | 0 | 3699.93 | 0 | 3699.93 | 0 | [6 empty] | CM_WWNI | 100%
505552 | E-WW-NI-04032020-LAURENCEKIRK WWTW-REPLACE PS DESLUDGE PUMP A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 89.48 | 1278.34 | 1367.82 | 0 | 1367.82 | 0 | [6 empty] | CM_WWNI | 100%
505663 | E-WW-NI-04032020-MILNATHORT WWTW-INSTALL WALKWAY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 800.38 | 11433.99 | 12234.37 | 0 | 12234.37 | 0 | [6 empty] | CM_WWNI | 100%
505667 | E-WW-NI-04032020-NEWBIGGING WWTW-FILTER BED DECOMMISIONING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 462 | 6600 | 7062 | 0 | 7062 | 0 | [6 empty] | CM_WWNI | 100%
504313 | E-WW-NI-041219-ST FILLANS HOTEL SPS-INSTALL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 16344.08 | 0 | 16344.08 | 0 | 16344.08 | 0 | [6 empty] | CM_WWNI | 100%
505136 | E-WW-NI-05022020-PETER HOWLING SPS-INSTALL FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2491.71 | 921.59 | 3413.3 | 0 | 3413.3 | 0 | [6 empty] | CM_WWNI | 100%
505568 | E-WW-NI-05032020-PITLOCHRY FERRY CRESCENT WWPS-LOGGER INSTALLATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-05 |  | 2020-06-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 144.14 | 2059.15 | 2203.29 | 0 | 2203.29 | 0 | [6 empty] | CM_WWNI | 100%
505676 | E-WW-NI-05032020-ST FILLANS MAIN SPS-REPLACE MACERATOR PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 201.04 | 2871.99 | 3073.03 | 0 | 3073.03 | 0 | [6 empty] | CM_WWNI | 100%
504321 | E-WW-NI-051219-AUCHLEVEN WWTW-REPLACE MISSING HANDRAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5423 | -2480.08 | 2942.92 | 0 | 2942.92 | 0 | [6 empty] | CM_WWNI | 100%
504324 | E-WW-NI-051219-FOCHABERS WWTW-REPLACE HUMUS SLUDGE PUMP NO 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 2712.45 | -799.55 | 1912.9 | 0 | 1912.9 | 0 | [6 empty] | CM_WWNI | 100%
504231 | E-WW-NI-051219-UDNY GREEN WWTW-H&S CONCERNS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 832.05 | 0 | 832.05 | 0 | 832.05 | 0 | [6 empty] | CM_WWNI | 100%
504316 | E-WW-NI-051219-VALLEYFIELD WWTW-INSTALL NEW FLORRING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4104.52 | -1209.89 | 2894.63 | 0 | 2894.63 | 0 | [6 empty] | CM_WWNI | 100%
504201 | E-WW-NI-0512-2019-NEWMACHAR WWTW-H&S ISSUES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1397.83 | 0 | 1397.83 | 0 | 1397.83 | 0 | [6 empty] | CM_WWNI | 100%
504209 | E-WW-NI-05122019-TARVES WWTW-H&S ISSUES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1337.5 | -505.45 | 832.05 | 0 | 832.05 | 0 | [6 empty] | CM_WWNI | 100%
504534 | E-WW-NI-06012020-BOWHOUSE STW-REPLACE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1468.82 | -589.49 | 879.33 | 0 | 879.33 | 0 | [6 empty] | CM_WWNI | 100%
504691 | E-WW-NI-06012020-BRUCE EMBANKMENT WWPS-REPLACE FORWARDING PUMP (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 7839.78 | -3543.32 | 4296.46 | 0 | 4296.46 | 0 | [6 empty] | CM_WWNI | 100%
504711 | E-WW-NI-06012020-IRONMILL BAY WWTW-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 12161.26 | 0 | 12161.26 | 0 | 12161.26 | 0 | [6 empty] | CM_WWNI | 100%
504529 | E-WW-NI-06012020-TAYPORT WWTW-REPLACE ROTORK (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1095.68 | -495.21 | 600.47 | 0 | 600.47 | 0 | [6 empty] | CM_WWNI | 100%
505137 | E-WW-NI-06022020-COWDENBEATH GRAY PARK SPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1169.39 | 432.52 | 1601.91 | 0 | 1601.91 | 0 | [6 empty] | CM_WWNI | 100%
505141 | E-WW-NI-06022020-KIRRIEMUIR WWTW-REFURB AERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 5187.58 | 1918.7 | 7106.28 | 0 | 7106.28 | 0 | [6 empty] | CM_WWNI | 100%
505679 | E-WW-NI-06032020=MODLEY PARK ELLON WWPS-REFURBISH SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 220.2 | 3145.72 | 3365.92 | 0 | 3365.92 | 0 | [6 empty] | CM_WWNI | 100%
505587 | E-WW-NI-06032020-ABERDEEN YORK PL WWPS-REFURB FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-06-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 159.6 | 2280.02 | 2439.62 | 0 | 2439.62 | 0 | [6 empty] | CM_WWNI | 100%
505696 | E-WW-NI-06032020-KIRKCALDY WWTW-INSTALL NEW MAIN INLET CHANNEL ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2020-06-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 416.57 | 5951 | 6367.57 | 0 | 6367.57 | 0 | [6 empty] | CM_WWNI | 100%
505690 | E-WW-NI-06032020-KITTYBREWSTER WWPS-PUMP REPLACEMENT & INSTALL CONCERTOR CONTROL SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2020-06-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1103.41 | 15763.05 | 16866.46 | 0 | 16866.46 | 0 | [6 empty] | CM_WWNI | 100%
505590 | E-WW-NI-06032020-MEIGLE STW-CSO OUTFALL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-06-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 2653.6 | 0 | 2653.6 | 0 | 2653.6 | 0 | [6 empty] | CM_WWNI | 100%
505684 | E-WW-NI-06032020-WESTHILL WWPS-REPLACE ISOLATION VALVES/PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 880.13 | 12573.34 | 13453.47 | 0 | 13453.47 | 0 | [6 empty] | CM_WWNI | 100%
504337 | E-WW-NI-061219-ABERLOUR WWTW-ROOF REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 2474.59 | 0 | 2474.59 | 0 | 2474.59 | 0 | [6 empty] | CM_WWNI | 100%
504330 | E-WW-NI-061219-CELLARDYKE THE HAVEN SPS-REPLACE PUMP NO 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 13162.61 | 0 | 13162.61 | 0 | 13162.61 | 0 | [6 empty] | CM_WWNI | 100%
504259 | E-WW-NI-061219-ECHT WWTW-REPLACE INLET PUMP B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1552.41 | 0 | 1552.41 | 0 | 1552.41 | 0 | [6 empty] | CM_WWNI | 100%
504257 | E-WW-NI-061219-ELLON WWTW-REPLACE PST PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1853.77 | -700.56 | 1153.21 | 0 | 1153.21 | 0 | [6 empty] | CM_WWNI | 100%
504220 | E-WW-NI-061219-HUNTLY MEADOWS WWPS-REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2043.91 | -772.41 | 1271.5 | 0 | 1271.5 | 0 | [6 empty] | CM_WWNI | 100%
504363 | E-WW-NI-061219-MINTLAW WWTW-REPLACE WASHWATER PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3676.09 | -1083.6 | 2592.49 | 0 | 2592.49 | 0 | [6 empty] | CM_WWNI | 100%
504262 | E-WW-NI-061219-TARVES WWTW-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1669.2 | -630.81 | 1038.39 | 0 | 1038.39 | 0 | [6 empty] | CM_WWNI | 100%
504570 | E-WW-NI-07012020-BLACKFORD WWTW-REPLACE HUMUS FEED PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1288.24 | -582.25 | 705.99 | 0 | 705.99 | 0 | [6 empty] | CM_WWNI | 100%
504566 | E-WW-NI-07012020-COMRIE PORTERFIELD WWPS-REPLACE FOUL PUMP NO 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2201.2 | -994.87 | 1206.33 | 0 | 1206.33 | 0 | [6 empty] | CM_WWNI | 100%
504563 | E-WW-NI-07012020-MONTROSE WWTW-REPLACE FAULTY PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1288.74 | -582.46 | 706.28 | 0 | 706.28 | 0 | [6 empty] | CM_WWNI | 100%
505147 | E-WW-NI-07022020-AUCHTERARDER WWTW-REPLACE HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 2797.12 | 1034.55 | 3831.67 | 0 | 3831.67 | 0 | [6 empty] | CM_WWNI | 100%
504662 | E-WW-NI-09012020-ABERFELDY WWTW-REFURB SLUDGE FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2974.96 | -1277.35 | 1697.61 | 0 | 1697.61 | 0 | [6 empty] | CM_WWNI | 100%
504683 | E-WW-NI-09012020-CULROSS BLACKADDRER HAVEN WWPS-REFURB WET WELL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 5641.9 | 0 | 5641.9 | 0 | 5641.9 | 0 | [6 empty] | CM_WWNI | 100%
504676 | E-WW-NI-09012020-DUNFERMLINE STC-REFURB SLUDGE CAKE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3656.74 | -1652.72 | 2004.02 | 0 | 2004.02 | 0 | [6 empty] | CM_WWNI | 100%
504656 | E-WW-NI-09012020-IRONMILL BAY STW-REFURB SLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3030.44 | -1369.66 | 1660.78 | 0 | 1660.78 | 0 | [6 empty] | CM_WWNI | 100%
505635 | E-WW-NI-09032020-NEWMACHAR WWTW-FIT NEW DOORS ON MCC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-10 |  | 2020-06-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 129.5 | 1850 | 1979.5 | 0 | 1979.5 | 0 | [6 empty] | CM_WWNI | 100%
505598 | E-WW-NI-090320-BLACKFORD WWTW-OUTFALL PROTECTION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-03-17 | 2020-03-17 | 2020-10-12 | 2020-08-05 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 4000 | 56000 | 60000 | 0 | 60000 | 0 | [6 empty] | CM_WWNI | 100%
504423 | E-WW-NI-091219-SCONE MURRAYSHALL WWPS-INSTALL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  |  |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 11067.37 | 0 | 11067.37 | 0 | 11067.37 | 0 | [6 empty] | CM_WWNI | 100%
504754 | E-WW-NI-10012020-ABERFELDY WWTW-OPTIONEERING EXERCISE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 5863.96 | 0 | 5863.96 | 0 | 5863.96 | 0 | [6 empty] | CM_WWNI | 100%
504652 | E-WW-NI-10012020-BODDAM HARBOUR ST WWPS-REPAIR CONCRETE PLINTH & PAVING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1246.09 | 0 | 1246.09 | 0 | 1246.09 | 0 | [6 empty] | CM_WWNI | 100%
504640 | E-WW-NI-10012020-COWDENBEATH SPS-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 713.67 | 0 | 713.67 | 0 | 713.67 | 0 | [6 empty] | CM_WWNI | 100%
504735 | E-WW-NI-10012020-KEITH WWTW-REPLACE STORM RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 5404.2 | -2442.52 | 2961.68 | 0 | 2961.68 | 0 | [6 empty] | CM_WWNI | 100%
504638 | E-WW-NI-10012020-PITLOCHRY WWTW-REPLACE FE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1231.98 | -509.56 | 722.42 | 0 | 722.42 | 0 | [6 empty] | CM_WWNI | 100%
505737 | E-WW-NI-10032020-BURGHEAD STATION RD SPS-INSTALL NEW FLAP VALVE/PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 305.45 | 4363.63 | 4669.08 | 0 | 4669.08 | 0 | [6 empty] | CM_WWNI | 100%
505750 | E-WW-NI-10032020-NEW ABERDOUR WWTW-REFURB RBC1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 516.15 | 7373.51 | 7889.66 | 0 | 7889.66 | 0 | [6 empty] | CM_WWNI | 100%
505746 | E-WW-NI-10032020-STAR OF MARKINCH SPS-BUILDING REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 315.7 | 4510 | 4825.7 | 0 | 4825.7 | 0 | [6 empty] | CM_WWNI | 100%
504284 | E-WW-NI-101219-DALGETY BAY MAIN WWPS-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2192.43 | -828.54 | 1363.89 | 0 | 1363.89 | 0 | [6 empty] | CM_WWNI | 100%
504308 | E-WW-NI-101219-KILRENNY MILL WWPS-REPLACE PUMP NO 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2429.43 | -918.11 | 1511.32 | 0 | 1511.32 | 0 | [6 empty] | CM_WWNI | 100%
504426 | E-WW-NI-101219-MONTROSE WWTW-REFURB WETWELL CHAMBER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 9385.9 | 0 | 9385.9 | 0 | 9385.9 | 0 | [6 empty] | CM_WWNI | 100%
505237 | E-WW-NI-11022020-DUNDEE CENTRAL TESCO WWPS-REPLACE STORM PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-30 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 2613.93 | 966.8 | 3580.73 | 0 | 3580.73 | 0 | [6 empty] | CM_WWNI | 100%
505762 | E-WW-NI-11032020-AUCHTERARDER CASTLETON RD SPS-REPLACE FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-18 |  | 2020-06-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 324.63 | 4637.64 | 4962.27 | 0 | 4962.27 | 0 | [6 empty] | CM_WWNI | 100%
505755 | E-WW-NI-11032020-PERTH CITY WWTW-TOILET FACILITIES UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 605.5 | 8649.99 | 9255.49 | 0 | 9255.49 | 0 | [6 empty] | CM_WWNI | 100%
505173 | E-WW-NI-12022020-MEIGLE WWTW-REPLACE FILTER COLUMN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-13 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1000.52 | 370.06 | 1370.58 | 0 | 1370.58 | 0 | [6 empty] | CM_WWNI | 100%
503951 | E-WW-NI-121119-PITLESSIE CONCERTO SPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 17530.52 | -5932.52 | 11598 | 0 | 11598 | 0 | [6 empty] | CM_WWNI | 100%
503939 | E-WW-NI-121119-ST ANDREWS WWTW-REFURB PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4463.69 | -1510.58 | 2953.11 | 0 | 2953.11 | 0 | [6 empty] | CM_WWNI | 100%
504339 | E-WW-NI-121219-KITTYBREWSTER WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1332.58 | -392.82 | 939.76 | 0 | 939.76 | 0 | [6 empty] | CM_WWNI | 100%
504338 | E-WW-NI-121219-NEWMACHAR WWTW-REPLACE WASHWATER PUMP B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1662.35 | -490.01 | 1172.34 | 0 | 1172.34 | 0 | [6 empty] | CM_WWNI | 100%
505245 | E-WW-NI-13022020-BRECHIN WWTW-REPLACE PRIMARY PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2310.63 | 854.62 | 3165.25 | 0 | 3165.25 | 0 | [6 empty] | CM_WWNI | 100%
505241 | E-WW-NI-13022020-ELGIN TRINITY RD WWPS-INSTALL EMERGENCY LIGHTING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 2967.32 | 1097.5 | 4064.82 | 0 | 4064.82 | 0 | [6 empty] | CM_WWNI | 100%
505180 | E-WW-NI-13022020-KENNETHMONT WWTW-INSTALL GATES/HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-14 |  | 2020-03-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 75.67 | 0 | 75.67 | 0 | 75.67 | 0 | [6 empty] | CM_WWNI | 100%
505187 | E-WW-NI-13022020-NEW BYTH WWTW-INSTALL LADDER/HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-14 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1070.11 | 395.79 | 1465.9 | 0 | 1465.9 | 0 | [6 empty] | CM_WWNI | 100%
505193 | E-WW-NI-13022020-NEWBIGGING WWTW-REPLACE GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-17 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1814.5 | 671.11 | 2485.61 | 0 | 2485.61 | 0 | [6 empty] | CM_WWNI | 100%
505184 | E-WW-NI-13022020-STUARTFIELD WWTW-INSTALL HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-13 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1077.92 | 398.68 | 1476.6 | 0 | 1476.6 | 0 | [6 empty] | CM_WWNI | 100%
505254 | E-WW-NI-13022020-TARVES STW-REPLACE INLET PENSTOCK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2490.61 | 921.19 | 3411.8 | 0 | 3411.8 | 0 | [6 empty] | CM_WWNI | 100%
505722 | E-WW-NI-13032020-BANCHORY WWTW-REPLACE FILTER 1 FEED PUMP A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2020-06-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 139.68 | 1995.41 | 2135.09 | 0 | 2135.09 | 0 | [6 empty] | CM_WWNI | 100%
505776 | E-WW-NI-13032020-KINGSWELLS WWPS-FIT NEW PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-18 |  | 2020-06-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 179.2 | 2560 | 2739.2 | 0 | 2739.2 | 0 | [6 empty] | CM_WWNI | 100%
505714 | E-WW-NI-13032020-UDNY STATION WWTW-REPLACE INLET PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2020-06-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 93.85 | 1340.73 | 1434.58 | 0 | 1434.58 | 0 | [6 empty] | CM_WWNI | 100%
505203 | E-WW-NI-14022020-DUNSHALT WWPS-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-14 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1124.57 | 0 | 1124.57 | 0 | 1124.57 | 0 | [6 empty] | CM_WWNI | 100%
505209 | E-WW-NI-14022020-NEWMACHAR STW-REPLACE FLOW METER/TRANSMITTERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-17 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1598.48 | 591.22 | 2189.7 | 0 | 2189.7 | 0 | [6 empty] | CM_WWNI | 100%
505258 | E-WW-NI-14022020-PENNAN ST-REPLACE ST COVER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3510.26 | 1298.32 | 4808.58 | 0 | 4808.58 | 0 | [6 empty] | CM_WWNI | 100%
505260 | E-WW-NI-14022020-PETERHEAD KIRKTOWN WWPS-INVESTIGATE STORM PENSTOCK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-30 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 369.05 | 0 | 369.05 | 0 | 369.05 | 0 | [6 empty] | CM_WWNI | 100%
503933 | E-WW-NI-141119-CUPAR WWTW-REPLACE AERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 8345.79 | -2824.31 | 5521.48 | 0 | 5521.48 | 0 | [6 empty] | CM_WWNI | 100%
504764 | E-WW-NI-15012020-BRECHIN WWTW-REPLACE DOSING PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 3908.3 | 0 | 3908.3 | 0 | 3908.3 | 0 | [6 empty] | CM_WWNI | 100%
504664 | E-WW-NI-15012020-COWDENBEATH SPS-REPLACE SCREEN & MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1362.01 | -615.58 | 746.43 | 0 | 746.43 | 0 | [6 empty] | CM_WWNI | 100%
503937 | E-WW-NI-151119-CUPAR WWTW-REPLACE ROTOR & STATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3302.05 | -1117.45 | 2184.6 | 0 | 2184.6 | 0 | [6 empty] | CM_WWNI | 100%
503964 | E-WW-NI-151119-FETTERCAIRN STW-REPLACE ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2957.39 | -1000.81 | 1956.58 | 0 | 1956.58 | 0 | [6 empty] | CM_WWNI | 100%
503926 | E-WW-NI-151119-KEITH WWTW-REPLACE GATE VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2975.74 | -1007.03 | 1968.71 | 0 | 1968.71 | 0 | [6 empty] | CM_WWNI | 100%
503954 | E-WW-NI-151119-KIRRIEMUIR STW-REPLACE GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 5798.33 | -1962.22 | 3836.11 | 0 | 3836.11 | 0 | [6 empty] | CM_WWNI | 100%
503971 | E-WW-NI-151119-LETHAM WWTW-REPLACE ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 3610.65 | -1221.89 | 2388.76 | 0 | 2388.76 | 0 | [6 empty] | CM_WWNI | 100%
504001 | E-WW-NI-151119-MEIGLE WWTW-REPLACE FEED PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 21150.97 | -7157.73 | 13993.24 | 0 | 13993.24 | 0 | [6 empty] | CM_WWNI | 100%
503959 | E-WW-NI-151119-PITSCOTTIE WWTW-REPLACE DISC AIR DIFFUSERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3656.19 | -1237.29 | 2418.9 | 0 | 2418.9 | 0 | [6 empty] | CM_WWNI | 100%
503872 | E-WW-NI-15112019-ELLON WWTW-BLOWER NO1 REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2353.57 | -796.47 | 1557.1 | 0 | 1557.1 | 0 | [6 empty] | CM_WWNI | 100%
504784 | E-WW-NI-16012020-CUPAR WWTW-INSTALL MACERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 11294.19 | -4775.23 | 6518.96 | 0 | 6518.96 | 0 | [6 empty] | CM_WWNI | 100%
504789 | E-WW-NI-16012020-CUPAR WWTW-NEW SKIP BUILDING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 21186 | -9575.37 | 11610.63 | 0 | 11610.63 | 0 | [6 empty] | CM_WWNI | 100%
504787 | E-WW-NI-16012020-CUPAR WWTW-PERSPEX BUILDING REMOVAL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 5992 | -2708.19 | 3283.81 | 0 | 3283.81 | 0 | [6 empty] | CM_WWNI | 100%
504687 | E-WW-NI-16012020-STRICHEN WWTW-INSTALL HANDRAILING & GRATING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 616.89 | 0 | 616.89 | 0 | 616.89 | 0 | [6 empty] | CM_WWNI | 100%
504368 | E-WW-NI-161219-DAIRSIE WWTW-REPLACE FLOW MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1686.52 | 0 | 1686.52 | 0 | 1686.52 | 0 | [6 empty] | CM_WWNI | 100%
504373 | E-WW-NI-161219-KIRKCALDY CHARLOTTE ST WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 26141.22 | -7705.64 | 18435.58 | 0 | 18435.58 | 0 | [6 empty] | CM_WWNI | 100%
504480 | E-WW-NI-161219-KIRKCALDY STW-REPLACE MOTOR FAN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2086.46 | 0 | 2086.46 | 0 | 2086.46 | 0 | [6 empty] | CM_WWNI | 100%
504379 | E-WW-NI-161219-STRATHKINNESS SST-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1280.79 | -377.54 | 903.25 | 0 | 903.25 | 0 | [6 empty] | CM_WWI | 100%
504816 | E-WW-NI-17012020-BALMEDIE WWTW-REFURB INLET SCREEN 1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 11508.85 | 0 | 11508.85 | 0 | 11508.85 | 0 | [6 empty] | CM_WWNI | 100%
504812 | E-WW-NI-17012020-BRIDGE OF EARN DURLEY DENE SPS-INSTALL CONCERTOR PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 9198.95 | 0 | 9198.95 | 0 | 9198.95 | 0 | [6 empty] | CM_WWNI | 100%
504748 | E-WW-NI-17012020-DUNFERMLINE WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4977.68 | 0 | 4977.68 | 0 | 4977.68 | 0 | [6 empty] | CM_WWNI | 100%
504752 | E-WW-NI-17012020-DUNFERMLINE WWTW-REPLACE SAS ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2887.2 | -1372.54 | 1514.66 | 0 | 1514.66 | 0 | [6 empty] | CM_WWNI | 100%
504815 | E-WW-NI-17012020-ELGIN EDGAR ROAD SPS-REFURB ACCESS PATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 4961.6 | 56.7 | 5018.3 | 0 | 5018.3 | 0 | [6 empty] | CM_WWNI | 100%
504805 | E-WW-NI-17012020-ESSLEMONT CIRCLE WWPS-ROOF REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3166.54 | 0 | 3166.54 | 0 | 3166.54 | 0 | [6 empty] | CM_WWNI | 100%
504713 | E-WW-NI-17012020-IRONMILL BAY WWTW-REPLACE POLYMER FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1717.35 | -776.18 | 941.17 | 0 | 941.17 | 0 | [6 empty] | CM_WWNI | 100%
504828 | E-WW-NI-17012020-KIRRIEMUIR WWTW-REPLACE PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 10737.21 | -2410.25 | 8326.96 | 0 | 8326.96 | 0 | [6 empty] | CM_WWNI | 100%
504810 | E-WW-NI-17012020-MEIKLEMILL ELLON WWPS-ROOF REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 5966.33 | 0 | 5966.33 | 0 | 5966.33 | 0 | [6 empty] | CM_WWNI | 100%
504808 | E-WW-NI-17012020-PETERHEAD KIRKTOWN WWPS-REMOVE REDUNDANT ASSETS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6606.95 | 0 | 6606.95 | 0 | 6606.95 | 0 | [6 empty] | CM_WWNI | 100%
504715 | E-WW-NI-17012020-TOMNAVOULIN ST-INSTALL NEW FENCE & GATE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 2612.38 | -1180.71 | 1431.67 | 0 | 1431.67 | 0 | [6 empty] | CM_WWNI | 100%
505281 | E-WW-NI-17022020-BALMEDIE ELGIE RD WWPS-REPLACE FAULTY FLOW METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1285.18 | 0 | 1285.18 | 0 | 1285.18 | 0 | [6 empty] | CM_WWNI | 100%
505397 | E-WW-NI-17022020-CULROSS CENTRAL WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3755.06 | 0 | 3755.06 | 0 | 3755.06 | 0 | [6 empty] | CM_WWNI | 100%
505278 | E-WW-NI-17022020-DUNDEE BRIDGEFOOT WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2053.63 | 0 | 2053.63 | 0 | 2053.63 | 0 | [6 empty] | CM_WWNI | 100%
505350 | E-WW-NI-17022020-FOWLIS SMIDDY BRAE WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-21 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1702.95 | 629.86 | 2332.81 | 0 | 2332.81 | 0 | [6 empty] | CM_WWNI | 100%
505269 | E-WW-NI-17022020-INVERURIE WWTW-SUPPLY MOTOOR (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1044.92 | 31.05 | 1075.97 | 0 | 1075.97 | 0 | [6 empty] | CM_WWNI | 100%
505273 | E-WW-NI-17022020-MUTHILL WWTW-REPLACE SLUDGE TANK INLET VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1979.5 | 0 | 1979.5 | 0 | 1979.5 | 0 | [6 empty] | CM_WWNI | 100%
505398 | E-WW-NI-17022020-OAKLEY SST-FENCE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4518.66 | 1671.29 | 6189.95 | 0 | 6189.95 | 0 | [6 empty] | CM_WWNI | 100%
505899 | E-WW-NI-17032020-KIRKCALDY WWTW-REFURB LAMELLA DESLUDGE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3501.75 | -215.02 | 3286.73 | 0 | 3286.73 | 0 | [6 empty] | CM_WWNI | 100%
504483 | E-WW-NI-171219-CULROSS CENTRAL WWPS-REPLACE FOUMP PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3139.81 | -925.52 | 2214.29 | 0 | 2214.29 | 0 | [6 empty] | CM_WWNI | 100%
504445 | E-WW-NI-171219-ECHT WWTW-REPLACE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1856.79 | 0 | 1856.79 | 0 | 1856.79 | 0 | [6 empty] | CM_WWNI | 100%
504432 | E-WW-NI-171219-LIMEKILNS RED ROW WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1290.96 | -380.53 | 910.43 | 0 | 910.43 | 0 | [6 empty] | CM_WWNI | 100%
505399 | E-WW-NI-18022020-BLAIR ATHOLL MEMORIAL PARK WWPS-INSTALL CONCERTOR PUMP SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 12863.53 | 7712.07 | 20575.6 | 0 | 20575.6 | 0 | [6 empty] | CM_WWNI | 100%
505400 | E-WW-NI-18022020-PERTH CITY WWTW-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 3128.31 | 1157.04 | 4285.35 | 0 | 4285.35 | 0 | [6 empty] | CM_WWNI | 100%
505906 | E-WW-NI-18032020-ABERDOUR SHORE RD WWPS-REPLACE FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 274.43 | 3920.4 | 4194.83 | 0 | 4194.83 | 0 | [6 empty] | CM_WWNI | 100%
505813 | E-WW-NI-18032020-LOSSIE INCHBROOM SPS-REPLACE MILLTRONICS HEAD/JUNCTION BOX & CABLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-19 |  | Moray | 0 | 0 | 0 | 0 | 0 | 1352.9 | 0 | 1352.9 | 0 | 1352.9 | 0 | [6 empty] | CM_WWNI | 100%
505911 | E-WW-NI-18032020-PITLESSIE WWPS-REPLACE PUMP STOOLS & GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 270.13 | 3859.06 | 4129.19 | 0 | 4129.19 | 0 | [6 empty] | CM_WWNI | 100%
504073 | E-WW-NI-181119-BLAIR ATHOLL WWTW-INSTALL TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 40508.06 | -15231.55 | 25276.51 | 0 | 25276.51 | 0 | [6 empty] | CM_WWNI | 100%
504069 | E-WW-NI-181119-BRACO WWTW-INSTALL TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 16055.73 | 0 | 16055.73 | 0 | 16055.73 | 0 | [6 empty] | CM_WWNI | 100%
504078 | E-WW-NI-181119-PERTH CITY WWTW-CONSTRUCT FOOTPATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 2991.15 | 0 | 2991.15 | 0 | 2991.15 | 0 | [6 empty] | CM_WWNI | 100%
504487 | E-WW-NI-181219-PETERHEAD BUCHANHAVEN WWPS-REPLACE 6 ROTORKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 15030.48 | -4430.52 | 10599.96 | 0 | 10599.96 | 0 | [6 empty] | CM_WWNI | 100%
505327 | E-WW-NI-19022020-AUCHLEVEN NORTH STW-REPAIR OUTLET PIPE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1196.24 | 442.44 | 1638.68 | 0 | 1638.68 | 0 | [6 empty] | CM_WWNI | 100%
505417 | E-WW-NI-19022020-DUNFERMLINE STW-REFURB PRIMARY SLUDGE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 6396.2 | 0 | 6396.2 | 0 | 6396.2 | 0 | [6 empty] | CM_WWNI | 100%
505410 | E-WW-NI-19022020-DUNSHALT WWPS-ACCESS ROAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 6561.24 | 2426.76 | 8988 | 0 | 8988 | 0 | [6 empty] | CM_WWNI | 100%
505420 | E-WW-NI-19022020-KINROSS WWTW-REPLACE SCREW PUMP GEARBOXES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 7054.27 | 2609.11 | 9663.38 | 0 | 9663.38 | 0 | [6 empty] | CM_WWNI | 100%
505316 | E-WW-NI-19022020-NEWMACHAR WWTW-INSTALL NEW DUCT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1923.74 | 711.52 | 2635.26 | 0 | 2635.26 | 0 | [6 empty] | CM_WWNI | 100%
504266 | E-WW-NI-1903-19-VALLEYFIELD WWTW-SCOPING & INVESTIGATION WORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 6656.36 | 0 | 6656.36 | 0 | 6656.36 | 0 | [6 empty] | CM_WWNI | 100%
505829 | E-WW-NI-19032020-KIRKCALDY CHAPEL NTH WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-20 |  | 2020-06-19 |  | Fife | 0 | 0 | 0 | 0 | 0 | 171.8 | 2454.28 | 2626.08 | 0 | 2626.08 | 0 | [6 empty] | CM_WWNI | 100%
505922 | E-WW-NI-19032020-LIMEKILNS RED ROW WWPS-CONVERT STATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1091.73 | 15596.08 | 16687.81 | 0 | 16687.81 | 0 | [6 empty] | CM_WWNI | 100%
503877 | E-WW-NI-191119-CERES WWTW-REPLACE DRY WELL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2182.37 | -738.54 | 1443.83 | 0 | 1443.83 | 0 | [6 empty] | CM_WWNI | 100%
504485 | E-WW-NI-191219-NEWMACHAR WWTW-INSTALL NEW POWER CABLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4429.15 | -1305.58 | 3123.57 | 0 | 3123.57 | 0 | [6 empty] | CM_WWNI | 100%
505422 | E-WW-NI-20022020-BLACKFORD WWTW-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 15322.84 | 5667.35 | 20990.19 | 0 | 20990.19 | 0 | [6 empty] | CM_WWNI | 100%
505333 | E-WW-NI-20022020-CRIMOND LOGIE AVE WWPS - REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-21 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1295.76 | 479.25 | 1775.01 | 0 | 1775.01 | 0 | [6 empty] | CM_WWNI | 100%
505425 | E-WW-NI-20022020-KINROSS WWTW-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 12690.53 | 4693.76 | 17384.29 | 0 | 17384.29 | 0 | [6 empty] | CM_WWNI | 100%
505926 | E-WW-NI-20032020-BLACKBURN WWPS-INSTALL NEW MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 545.81 | 7797.29 | 8343.1 | 0 | 8343.1 | 0 | [6 empty] | CM_WWNI | 100%
505930 | E-WW-NI-20032020-LONGSIDE WWTW- REPLACE FILTER FEED PUMP & CONTROL PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1137.23 | 16246.17 | 17383.4 | 0 | 17383.4 | 0 | [6 empty] | CM_WWNI | 100%
505834 | E-WW-NI-20032020-NEWMACHAR WWTW-REPLACE MIXER MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-20 |  | 2020-06-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 106.47 | 1520.95 | 1627.42 | 0 | 1627.42 | 0 | [6 empty] | CM_WWNI | 100%
504268 | E-WW-NI-200819-GLENFARG WWTW-REPLACE KIOSKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 8833.06 | -1291.78 | 7541.28 | 0 | 7541.28 | 0 | [6 empty] | CM_WWNI | 100%
503894 | E-WW-NI-201119-PITMEDDEN WWTW-REPLACE SAS PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1612.06 | -545.54 | 1066.52 | 0 | 1066.52 | 0 | [6 empty] | CM_WWNI | 100%
504493 | E-WW-NI-201219-BURRELTON WWTW-REPLACE FAULTY COMPONENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 8562.25 | -2523.89 | 6038.36 | 0 | 6038.36 | 0 | [6 empty] | CM_WWNI | 100%
504477 | E-WW-NI-201219-COWDENBEATH SELKIRK AV SST-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1335.15 | -393.57 | 941.58 | 0 | 941.58 | 0 | [6 empty] | CM_WWNI | 100%
504457 | E-WW-NI-201219-DRUMLITHIE WWTW-REPLACE MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2548.33 | -751.17 | 1797.16 | 0 | 1797.16 | 0 | [6 empty] | CM_WWNI | 100%
504486 | E-WW-NI-201219-FORRES WWTW-REFURB INLET BAND SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 26590.06 | -6556.98 | 20033.08 | 0 | 20033.08 | 0 | [6 empty] | CM_WWNI | 100%
504489 | E-WW-NI-201219-NETHER KNOX WWTW-REPLACE GRIT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4469.91 | -1317.59 | 3152.32 | 0 | 3152.32 | 0 | [6 empty] | CM_WWNI | 100%
504887 | E-WW-NI-21012020-IRONMILL BAY WWTW-REFURB SLUDGE FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 3030.44 | -680.26 | 2350.18 | 0 | 2350.18 | 0 | [6 empty] | CM_WWNI | 100%
505428 | E-WW-NI-21022020-ABOYNE WWTW-INSTALL CHEMICAL DOSING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 17848 | 1249.36 | 19097.36 | 0 | 19097.36 | 0 | [6 empty] | CM_WWNI | 100%
505431 | E-WW-NI-21022020-BALMEDIE WWTW-INSTALL CHEMICAL DOSING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 16728 | 1170.96 | 17898.96 | 0 | 17898.96 | 0 | [6 empty] | CM_WWNI | 100%
505436 | E-WW-NI-21022020-CRIEFF WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1396.95 | 97.79 | 1494.74 | 0 | 1494.74 | 0 | [6 empty] | CM_WWNI | 100%
505426 | E-WW-NI-21022020-KEITH WWTW-SUPPLY NEW ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-26 |  | 2020-04-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 2196.07 | 812.24 | 3008.31 | 0 | 3008.31 | 0 | [6 empty] | CM_WWNI | 100%
505353 | E-WW-NI-21022020-MONFIETH A92 SERVICES WWPS-REFURB ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1926 | 0 | 1926 | 0 | 1926 | 0 | [6 empty] | CM_WWNI | 100%
505430 | E-WW-NI-21022020-PITMEDDEN WWTW -INSTALL CHEMICAL DOSING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 15938 | 1960.96 | 17898.96 | 0 | 17898.96 | 0 | [6 empty] | CM_WWNI | 100%
505355 | E-WW-NI-210220-DUNFERMLINE STC-REPLACE SLUDGE HOLDING TANK NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 | 2020-10-19 | 2021-04-15 | 2021-01-11 | Fife | 0 | 0 | 0 | 0 | 0 | 2000 | 226446.16 | 228446.16 | 11553.85 | 240000.01 | 56717112.68 | [6 empty] | WWNI | 100%
503918 | E-WW-NI-211119-KINCARDINE ONEIL WWTW-REPLACE FILTER GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1731.9 | -586.1 | 1145.8 | 0 | 1145.8 | 0 | [6 empty] | CM_WWNI | 100%
504081 | E-WW-NI-211119-KINROSS WWTW-REPLACE AERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 20130.98 | -7569.5 | 12561.48 | 0 | 12561.48 | 0 | [6 empty] | CM_WWNI | 100%
504126 | E-WW-NI-21219-FORFAR WWTW-REPLACE FE FILER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1884.54 | -712.2 | 1172.34 | 0 | 1172.34 | 0 | [6 empty] | CM_WWNI | 100%
504912 | E-WW-NI-22012020-DUNFERMLINE WWTW-REPLACE PRIMARY SLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 7060.87 | 0 | 7060.87 | 0 | 7060.87 | 0 | [6 empty] | CM_WWNI | 100%
504935 | E-WW-NI-22012020-MONIFIETH GRANGE RD WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 3008.2 | 0 | 3008.2 | 0 | 3008.2 | 0 | [6 empty] | CM_WWNI | 100%
504019 | E-WW-NI-221119-BUCKIE RATHVEN SPS-REPLACE PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 1313.09 | -493.74 | 819.35 | 0 | 819.35 | 0 | [6 empty] | CM_WWNI | 100%
504007 | E-WW-NI-221119-HATTON OF CRUDEN WWTW-REPLACE AIR END OF COMPRESSOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1478.74 | -500.42 | 978.32 | 0 | 978.32 | 0 | [6 empty] | CM_WWNI | 100%
504153 | E-WW-NI-221119-LHANBRYDE PARKVIEW SPS-REPLACE LEVEL CONROLLER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 1431.25 | -540.88 | 890.37 | 0 | 890.37 | 0 | [6 empty] | CM_WWNI | 100%
504263 | E-WW-NI-221119-PITSCOTTIE SPS CSO-FIT ANPRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 12214.8 | -592.14 | 11622.66 | 0 | 11622.66 | 0 | [6 empty] | CM_WWNI | 100%
504083 | E-WW-NI-221119-TURRIFF WWTW-REPAIR LIQUOR RETURN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 5354.28 | -2013.27 | 3341.01 | 0 | 3341.01 | 0 | [6 empty] | CM_WWNI | 100%
506005 | E-WW-NI-23032020-PERTH CITY WWTW-MODIFY CONTROL PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2020-06-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 9211.25 | 9211.25 | 0 | 9211.25 | 0 | [6 empty] | CM_WWNI | 100%
504138 | E-WW-NI-230919-AUCHTERARDER WWTW-INSTALL NEW FLOORING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 14910.45 | -5634.81 | 9275.64 | 0 | 9275.64 | 0 | [6 empty] | CM_WWNI | 100%
504142 | E-WW-NI-230919-BANKFOOT WWTW-INSTALL NEW FLOORING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 3147.79 | 0 | 3147.79 | 0 | 3147.79 | 0 | [6 empty] | CM_WWNI | 100%
504495 | E-WW-NI-230919-STANLEY WWTW-H&S HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 3646.21 | 0 | 3646.21 | 0 | 3646.21 | 0 | [6 empty] | CM_WWNI | 100%
505016 | E-WW-NI-24012020-HATTON WWPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 28149.68 | 0 | 28149.68 | 0 | 28149.68 | 0 | [6 empty] | CM_WWNI | 100%
504925 | E-WW-NI-24012020-KINLOSS GLEBE RD WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 3196.95 | 0 | 3196.95 | 0 | 3196.95 | 0 | [6 empty] | CM_WWNI | 100%
504937 | E-WW-NI-24012020-KINROSS WWTW-INSTALL WALKWAY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 14319.81 | 0 | 14319.81 | 0 | 14319.81 | 0 | [6 empty] | CM_WWNI | 100%
505529 | E-WW-NI-24022020-AUCHTERMUCHTY SPS-SUPPLY NEW KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2020-06-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 5628.2 | 0 | 5628.2 | 0 | 5628.2 | 0 | [6 empty] | CM_WWNI | 100%
505441 | E-WW-NI-24022020-FORFAR WWTW-SUPPLY MOTOR (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1394.48 | 1394.48 | 0 | 1394.48 | 0 | [6 empty] | CM_WWNI | 100%
505444 | E-WW-NI-24022020-GUARDBRIDGE WWTW-REPLACE ROTOR & STATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1041.69 | 72.92 | 1114.61 | 0 | 1114.61 | 0 | [6 empty] | CM_WWNI | 100%
505526 | E-WW-NI-24022020-LOWER LARGO THE TEMPLE WWPS-REPLACE SOFTSTART PANELS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-04 |  | 2020-06-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1125.45 | 16077.86 | 17203.31 | 0 | 17203.31 | 0 | [6 empty] | CM_WWNI | 100%
505456 | E-WW-NI-24022020-MARYWELL WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2084.66 | 2084.66 | 0 | 2084.66 | 0 | [6 empty] | CM_WWNI | 100%
505532 | E-WW-NI-25022020-PADANARAM WWPS-REPLACE SHAFT DRIVEN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2020-06-04 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1287.8 | 18397.15 | 19684.95 | 0 | 19684.95 | 0 | [6 empty] | CM_WWNI | 100%
505946 | E-WW-NI-25032020-BLAIRGOWRIE WWTW-REPLACE ANOXIC ZONE MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-26 |  | 2020-06-25 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 133.24 | 1903.36 | 2036.6 | 0 | 2036.6 | 0 | [6 empty] | CM_WWNI | 100%
504122 | E-WW-NI-251119-FRIOCKHEIM STW-CRITICAL SPARES (SURFACE AERATOR) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2418.12 | -913.83 | 1504.29 | 0 | 1504.29 | 0 | [6 empty] | CM_WWNI | 100%
504130 | E-WW-NI-251119-PERTH CITY WWTW-REFURB WASHPRESS UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 14425.19 | -5451.42 | 8973.77 | 0 | 8973.77 | 0 | [6 empty] | CM_WWNI | 100%
504112 | E-WW-NI-251119-ST MONANS EASTSHORE SPS-REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2934.31 | -1108.91 | 1825.4 | 0 | 1825.4 | 0 | [6 empty] | CM_WWNI | 100%
506009 | E-WW-NI-26032020-BURNTISLAND HAUGH RD WWPS-REPLACE NO3 STORM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2020-06-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 18117.08 | 18117.08 | 0 | 18117.08 | 0 | [6 empty] | CM_WWNI | 100%
503995 | E-WW-NI-261119-ELLON WWTW-REPLACE POLYMER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2126.09 | -719.49 | 1406.6 | 0 | 1406.6 | 0 | [6 empty] | CM_WWNI | 100%
504994 | E-WW-NI-27012020-KIRKCALDY WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 4116.29 | 0 | 4116.29 | 0 | 4116.29 | 0 | [6 empty] | CM_WWNI | 100%
504939 | E-WW-NI-27012020-NORTH QUEENSFERRY BATTERY RD SPS-REPLACE WET WELL & VALVE CHAMBER COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 2487.75 | 0 | 2487.75 | 0 | 2487.75 | 0 | [6 empty] | CM_WWNI | 100%
505457 | E-WW-NI-27022020-ABERDOUR SILVER SANDS WWTW-REPLACE TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1153.59 | 426.67 | 1580.26 | 0 | 1580.26 | 0 | [6 empty] | CM_WWNI | 100%
505538 | E-WW-NI-27022020-ABERFELDY WWTW-WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2020-06-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 339.5 | 4850 | 5189.5 | 0 | 5189.5 | 0 | [6 empty] | CM_WWNI | 100%
505536 | E-WW-NI-27022020-BLACKFORD WWTW-WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2020-06-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 616 | 8800 | 9416 | 0 | 9416 | 0 | [6 empty] | CM_WWNI | 100%
505533 | E-WW-NI-27022020-DUNSHALT WWPS-REPLACE STORM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2020-06-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 175.65 | 2509.3 | 2684.95 | 0 | 2684.95 | 0 | [6 empty] | CM_WWNI | 100%
505459 | E-WW-NI-27022020-LADYBANK WWPS-INSTALL HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1468.47 | 543.13 | 2011.6 | 0 | 2011.6 | 0 | [6 empty] | CM_WWNI | 100%
506014 | E-WW-NI-27032020-HATTON OF CRUDEN WWTW-INSTALL NEW SIPHON | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2020-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6931.45 | 6931.45 | 0 | 6931.45 | 0 | [6 empty] | CM_WWNI | 100%
506011 | E-WW-NI-27032020-MINTLAW WWTW-REPLACE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2020-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5901.05 | 5901.05 | 0 | 5901.05 | 0 | [6 empty] | CM_WWNI | 100%
504037 | E-WW-NI-271119-NEWMACHAR STW-REPLACE INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 48920.4 | -2765.15 | 46155.25 | 0 | 46155.25 | 0 | [6 empty] | CM_WWNI | 100%
505006 | E-WW-NI-28012020-BRECHIN WWTW-REPLACE PRIMARY PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 2873.59 | 0 | 2873.59 | 0 | 2873.59 | 0 | [6 empty] | CM_WWNI | 100%
504950 | E-WW-NI-28012020-DUNDEE CITY QUAY WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 1476.47 | 0 | 1476.47 | 0 | 1476.47 | 0 | [6 empty] | CM_WWNI | 100%
505125 | E-WW-NI-28012020-MEIGLE WWTW-PIPE MODIFICATIONS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 54677 | 20223 | 74900 | 0 | 74900 | 0 | [6 empty] | CM_WWNI | 100%
504942 | E-WW-NI-28012020-SPRINGFIELD WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1510.41 | 0 | 1510.41 | 0 | 1510.41 | 0 | [6 empty] | CM_WWNI | 100%
504997 | E-WW-NI-28012020-STRATHMIGLO WWTW-REPLACE RAS PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 8481.89 | 0 | 8481.89 | 0 | 8481.89 | 0 | [6 empty] | CM_WWNI | 100%
505501 | E-WW-NI-28022020-AUCHTERARDER WWTW-REPLACE GRIT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-03 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 144.13 | 2059 | 2203.13 | 0 | 2203.13 | 0 | [6 empty] | CM_WWNI | 100%
505509 | E-WW-NI-28022020-COMRIE WWTW-REPLACE BOTTOM BEARING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-04 |  | 2020-06-03 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 1562.2 | 0 | 1562.2 | 0 | 1562.2 | 0 | [6 empty] | CM_WWNI | 100%
505496 | E-WW-NI-28022020-DRUMOAK WWTW-REFURB ACTUATING PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 113.47 | 1621.02 | 1734.49 | 0 | 1734.49 | 0 | [6 empty] | CM_WWNI | 100%
505488 | E-WW-NI-28022020-MIDMAR HOUSING ST-FIT PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-05-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 109.2 | 1560 | 1669.2 | 0 | 1669.2 | 0 | [6 empty] | CM_WWNI | 100%
505494 | E-WW-NI-28022020-MONTROSE GREY HARLINGS WWPS-REPLACE GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1339.96 | 0.01 | 1339.97 | 0 | 1339.97 | 0 | [6 empty] | CM_WWNI | 100%
505545 | E-WW-NI-28022020-TURRIFF WWTW-REPAIR LIQUOR RETURN PUMPING MAIN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-04 |  | 2020-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 205.38 | 2934.09 | 3139.47 | 0 | 3139.47 | 0 | [6 empty] | CM_WWNI | 100%
505546 | E-WW-NI-28022020-UDNY GREEN WWPS-INSTALL CONTROL KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-04 |  | 2020-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 510.18 | 10142.04 | 10652.22 | 0 | 10652.22 | 0 | [6 empty] | CM_WWNI | 100%
504063 | E-WW-NI-281119-BANKTON PARK WWPS-CONTROL PANEL REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1870.33 | -703.27 | 1167.06 | 0 | 1167.06 | 0 | [6 empty] | CM_WWNI | 100%
504159 | E-WW-NI-291119-DRUMLITHIE WWTW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6136.45 | -2319.03 | 3817.42 | 0 | 3817.42 | 0 | [6 empty] | CM_WWNI | 100%
504094 | E-WW-NI-291119-GOURDIEBURN WWPS-REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2204.41 | -833.06 | 1371.35 | 0 | 1371.35 | 0 | [6 empty] | CM_WWNI | 100%
504173 | E-WW-NI-291119-KEMNAY PRELIM STW INLET SPS-REPLACE PENSTOCK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3443.26 | -1301.24 | 2142.02 | 0 | 2142.02 | 0 | [6 empty] | CM_WWNI | 100%
504169 | E-WW-NI-291119-KENNETHMONT WWTW-REPLACE SCREEEN BASKET | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3585.41 | 0 | 3585.41 | 0 | 3585.41 | 0 | [6 empty] | CM_WWNI | 100%
505132 | E-WW-NI-31012020-FRASERBURGH LACKIEHEAD SPS-REPLACE ULTRASONIC LEVEL METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1373.51 | 0 | 1373.51 | 0 | 1373.51 | 0 | [6 empty] | CM_WWNI | 100%
504986 | E-WW-NI-31012020-GRAHAM PLACE WWPS=REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 1386.08 | 0 | 1386.08 | 0 | 1386.08 | 0 | [6 empty] | CM_WWNI | 100%
505009 | E-WW-NI-31012020-HUNTLY WWTW-SHT REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 4630.64 | 0 | 4630.64 | 0 | 4630.64 | 0 | [6 empty] | CM_WWNI | 100%
504957 | E-WW-NI-31012020-TOMINTOUL WWTW-REPLACE ACCESS STAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Moray | 0 | 0 | 0 | 0 | 0 | 1722.7 | 0 | 1722.7 | 0 | 1722.7 | 0 | [6 empty] | CM_WWNI | 100%
506020 | E-WW-NI-31032020-ABERFELDY WWTW-ABORTIVE AERATOR REFURB COSTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2020-06-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 9095 | 9095 | 0 | 9095 | 0 | [6 empty] | CM_WWNI | 100%
503797 | E-WW-NI-51119-MONTROSEWWTW-LAGOON REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 | 2020-03-31 | Angus | 0 | 0 | 0 | 0 | 0 | 1802.7 | 0 | 1802.7 | 0 | 1802.7 | 0 | [6 empty] | CM_WWNI | 100%
504179 | E-WW-NI-51219-EAST WEMYSS MACDUFF SPS-REPLACE PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 1288.79 | -487.05 | 801.74 | 0 | 801.74 | 0 | [6 empty] | CM_WWNI | 100%
504246 | E-WW-NI-61219-CRIMOND NEW HADDO WWPS-REPLACE SCREEN MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1612.69 | -609.45 | 1003.24 | 0 | 1003.24 | 0 | [6 empty] | CM_WWNI | 100%
505454 | E-WW-NI-MONTROSE TAYOCK WWPS-REPLACE 3M PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1954.74 | 1954.74 | 0 | 1954.74 | 0 | [6 empty] | CM_WWNI | 100%
505154 | E-WW-NI-SCONE MURRAYSHALL WWPS-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-14 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 2788.53 | 1031.37 | 3819.9 | 0 | 3819.9 | 0 | [6 empty] | CM_WWNI | 100%
403175 | Existing Flooding Register Solution Development Study | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-02-05 | 2015-02-25 | 2015-04-20 | 2015-08-28 | 2014-12-11 | Scottish Water Wide | 239428.98 | 19915.61 | -253489.92 | -5854.67 | 0 | 0 | 0.01 | -239428.97 | 0 | 0.01 | 204193.13 | [6 empty] | CS11A | 100%
402426 | External Flooding Carntyne Road Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-08-31 | 2012-08-31 | 2012-08-31 | 2012-08-31 | Glasgow City | 5859.09 | 563.01 | 0 | 0 | 0 | 0 | 0 | 563.01 | 0 | 6422.1 | 0 | [6 empty] | CS15 | 100%
502272 | External Flooding Mitigations Policy Pilot Trials | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-11-21 | 2016-11-21 | 2017-02-27 | 2018-01-25 | 2018-01-25 | Scottish Water Wide | 0 | 0 | 11602.65 | 17155.41 | 0 | 0 | 0 | 28758.06 | 0 | 28758.06 | 0 | [6 empty] | CM_WWI | 100%
401674 | External Flooding Register - PHASE 1 of 2 - Build and Investigations | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2011-01-28 | 2011-12-07 | 2011-12-07 | 2015-10-30 |  | Scottish Water Wide | 1255309 | 6121 | -34.28 | 0 | 0 | 0 | 0 | 6086.72 | 0 | 1261395.72 | 0 | [6 empty] | CM_M&G | 100%
502610 | Eyemouth (North Burn Surface Water) Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-03-13 | 2017-08-31 | 2017-09-15 | 2018-02-28 | 2018-03-31 | Scottish Borders | 0 | 0 | 314.02 | 27710.98 | -5003.31 | 0 | 2266.18 | 25287.87 | 0 | 25287.87 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
500135 | Eyemouth DOA (DOA000070) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-02-20 | 2019-03-18 | Scottish Borders | 0 | 12083 | 41790 | 91336 | 58664.11 | 4760.81 | 0 | 208633.92 | 0 | 208633.92 | 10344.04 | [6 empty] | CS16D | 28.51% | EC01G | 71.49%
46214 | Eyemouth STW Refurb - STW002274 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2010-09-20 | 2010-10-04 | 2011-05-31 |  | Scottish Borders | 621165.62 | -1.27 | 0 | 0 | 0 | 0 | 0 | -1.27 | 0 | 621164.35 | 0 | [6 empty] | CM_WWNI | 100%
400617 | Facilities HS Minor Works | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-31 | 2010-03-31 | 2010-06-21 | 2016-01-01 |  | Scottish Water Wide | 793438 | -878.94 | 0 | 0 | 0 | 0 | 0 | -878.94 | 0 | 792559.06 | 0 | [6 empty] | CM_M&G | 100%
500521 | Facilities- North Office Inverness | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-05-18 | 2016-10-21 | 2016-10-21 | 2017-08-30 | 2017-08-30 | Highland | 0 | 76292 | 712181.39 | 354242.84 | 0 | 0 | 0 | 1142716.23 | 0 | 1142716.23 | 0 | [6 empty] | CM_M&G | 100%
400623 | Facilities Security Measures | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-29 | 2010-03-29 | 2010-06-21 | 2015-08-21 |  | Scottish Water Wide | 397039.06 | 32225.34 | 0 | 0 | 0 | 0 | 0 | 32225.34 | 0 | 429264.4 | 0 | [6 empty] | CM_M&G | 100%
502941 | Failing SRs Prioritisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2020-07-10 | 2020-07-15 | 2019-09-04 | 2019-09-04 | 2019-09-04 | Scottish Water Wide | 0 | 0 | 0 | 93362.48 | 21585.48 | 511.85 | 114436.11 | 229895.92 | 0 | 229895.92 | 0 | [6 empty] | CM_WSNI | 100%
502940 | Fair Isle WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2014-01-13 | 2019-03-28 | 2019-05-27 | 2021-01-31 | 2022-04-30 | Shetland Islands | 0 | 0 | 0 | 119542.36 | 661527.35 | 1568123.65 | 1639228.77 | 3988422.13 | 442613.27 | 4431035.4 | 2749114.73 |  |  |  |  | 23070 |  | DW23 | 50% | DW25P | 50% | bar: Regulatory Outputs OMG-01
503377 | Fairlie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2027-09-30 | 2028-08-08 | 2028-12-11 | 2029-06-01 | 2029-09-03 | North Ayrshire | 0 | 0 | 0 | 0 | 74385.29 | 11181.68 | 0 | 85566.97 | 56433.03 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
500240 | Fairmilehead B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | City of Edinburgh | 0 | 36243 | 37713 | 84227.13 | 0 | 0 | 17885.7 | 176068.83 | 0 | 176068.83 | 200243.19 | [6 empty] | DW5 | 100%
500823 | Fairmilehead B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-01 | 2019-07-03 | City of Edinburgh | 0 | 39048 | -14111.63 | 130646.3 | 60561.4 | 21390.58 | -0.01 | 237534.64 | 0 | 237534.64 | 1930302.81 | [6 empty] | DW5FS | 100%
503165 | Fairmilehead B RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-03-31 | 2020-10-12 | 2020-11-13 | 2020-03-25 | 2021-06-21 | City of Edinburgh | 0 | 0 | 0 | 0 | 14465.46 | 1999.79 | 0 | 16465.25 | 0 | 16465.25 | 1556352.2 | [6 empty] | DW5FS | 100%
500241 | Fairmilehead C - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2018-09-28 | 2018-09-28 | 2021-02-23 | 2021-11-16 | City of Edinburgh | 0 | 38636.29 | 67025.71 | 79606 | 782355.59 | 908719.35 | 346953.08 | 2223296.02 | 0 | 2223296.02 | 2128406.55 | [6 empty] | DW5FS | 1.349% | DW5MR | 98.65%
500824 | Fairmilehead C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-01 | 2019-08-30 | City of Edinburgh | 0 | 8629.94 | 2508.99 | 70995.16 | 169784.48 | 12716.62 | 0 | 264635.19 | 0 | 264635.19 | 349675.99 | [6 empty] | DW5FS | 100%
503166 | Fairmilehead C RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2015-03-31 | 2020-09-14 | 2020-10-16 | 2021-02-19 | 2021-05-24 | City of Edinburgh | 0 | 0 | 0 | 0 | 12610.96 | 2000 | 0 | 14610.96 | 0 | 14610.96 | 1064203.28 | [6 empty] | DW5FS | 100%
500818 | Falkirk Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-11-03 | 2017-03-13 | 2017-03-13 | 2016-09-12 | 2017-03-13 | Falkirk | 0 | 7066.63 | 7825.43 | 258.8 | 0 | 0 | 0 | 15150.86 | 0 | 15150.86 | 120964.87 | [6 empty] | CS15A | 100%
401378 | Fauldhouse STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-03-03 | 2012-09-26 | 2013-02-07 | 2014-03-14 |  | West Lothian | 1289380.3 | 5624.5 | 90 | 0 | 0 | 0 | 0 | 5714.5 | 0 | 1295094.8 | 0 | [6 empty] | CM_WWNI | 100%
503284 | Fauldhouse WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-24 | 2023-08-07 | 2023-12-08 | 2024-12-05 | 2025-03-07 | West Lothian | 0 | 0 | 0 | 0 | 81021.2 | 96.89 | 44423.48 | 125541.57 | 1874458.43 | 2000000 | 136478.56 | [6 empty] | SG1 | 100%
504490 | Faulhouse WWTW (South) Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-04 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWNI | 100%
504546 | Featurenet Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2020-04-01 | 2021-03-01 | 2021-06-30 | 2023-02-22 | 2023-05-25 | - | 0 | 0 | 0 | 0 | 0 | 465043.75 | 359585.98 | 824629.73 | 0 | 824629.73 | 0 | [6 empty] | CM_M&G | 100%
503225 | Ferniegair WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-03 | 2023-01-16 | 2023-05-17 | 2024-05-13 | 2024-08-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 115199.52 | 81800.88 | 2148.96 | 199149.36 | 4400850.66 | 4600000.02 | 136478.56 | [6 empty] | SG1 | 100%
500801 | Ferry Road Renfrew Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-08-13 | 2015-12-01 | 2015-12-01 | 2016-11-25 | 2016-11-25 | Renfrewshire | 0 | 96757 | 823743.13 | 750 | 1891.91 | -5511.44 | 0 | 917630.6 | 0 | 917630.6 | 0 | [6 empty] | CM_WWI | 100%
401349 | Ferryhills WSZ Low Pressure Enhancement WSZ000609 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-09-20 | 2012-12-07 | 2014-11-21 | 2014-03-31 | Fife | 362720.13 | 1396.51 | 914.68 | 0 | 0 | 0 | 0 | 2311.19 | 0 | 365031.32 | 1577 | [6 empty] | CS1 | 100%
501083 | Fetlar WOA Fetlar WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-05-26 | 2028-02-14 | 2028-04-13 | 2029-06-22 | 2029-09-24 | Shetland Islands | 0 | 13227.91 | 9695.09 | 0 | -274 | 430.33 | -397.7 | 22681.63 | 241.37 | 22923 | 0 | [6 empty] | CM_WSI | 100%
46859 | Fetlar WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-07-31 | 2013-03-11 | 2015-07-06 | 2016-03-30 | Shetland Islands | 2851122.27 | 4707.48 | -3233.87 | 0 | 0 | 0 | 0 | 1473.61 | 0 | 2852595.88 | 17352 | [6 empty] | DW23 | 100%
503323 | Fetterangus WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-24 | 2023-08-23 | 2023-12-20 | 2024-12-17 | 2025-03-19 | Aberdeenshire | 0 | 0 | 0 | 0 | 39582.14 | 11886.18 | 68449.83 | 119918.15 | 230081.8 | 349999.95 | 136478.56 | [6 empty] | SG1 | 100%
45548 | Fettercairn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-12-14 | 2012-02-27 | 2013-02-28 | 2013-03-29 | Aberdeenshire | 905991.77 | -66.49 | 0 | 0 | 0 | 0 | 0 | -66.49 | 0 | 905925.28 | 0 | [6 empty] | CM_WWNI | 20% | WQ01 | 80%
500922 | Fife Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-04-27 | 2017-04-27 | 2017-04-12 | 2017-04-27 | Fife | 0 | 5000 | 11724.57 | 161.72 | 0 | 0 | 0 | 16886.29 | 0 | 16886.29 | 120964.87 | [6 empty] | CS15A | 100%
501097 | Fife Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-08-31 | 2016-08-31 | 2018-10-31 | 2019-03-31 | Fife | 0 | 4329 | 24171.43 | 6214.46 | 4784.92 | -2444.62 | 0 | 37055.19 | 0 | 37055.19 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
504498 | Final Turbidity Meter Tobermory WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-09-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 334.65 | 4780.74 | 5115.39 | 0 | 5115.39 | 0 | [6 empty] | WSNI | 100%
500074 | Final Water Sampling Programme Extension | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS7 | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-09-01 | 2016-06-20 | Scottish Water Wide | 671 | 19409 | 89284.35 | 0 | 0 | 0 | 0 | 108693.35 | 0 | 109364.35 | 243025.97 | [6 empty] | CC4W | 100%
500955 | Finance Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-14 | 2017-03-30 | 2017-03-30 | 2018-09-14 |  | Scottish Water Wide | 0 | 304983 | 2895477.97 | 3969557.82 | 352790.78 | -2728.23 | 0.01 | 7520081.35 | 0 | 7520081.35 | 0 | [6 empty] | CM_M&G | 100%
500631 | Financial Control SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 273864.48 | 462835.17 | 534409.54 | 538377.44 | 571844.29 | 523694.69 | 2905025.61 | 85252.61 | 2990278.22 | 0 | [6 empty] | CM_OVH | 100%
505144 | Finlay Rise - repair of burst rising main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2021-02-11 |  | 2021-02-11 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 42043.06 | -2043.06 | 40000 | 0 | 40000 | 0 | [6 empty] | CM_WWNI | 100%
500688 | Finnieston Tunnel | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-06-11 | 2015-11-04 | 2015-11-27 | 2016-09-01 | 2016-09-01 | Glasgow City | 0 | 135984 | 136053 | 155 | 32430.47 | 350.93 | -350.91 | 304622.49 | 0 | 304622.49 | 0 | [6 empty] | CM_WWI | 100%
502926 | Finnieston Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-06-29 | 2018-08-07 | 2018-08-10 | 2020-08-27 | 2020-09-24 | Glasgow City | 0 | 0 | 0 | 6027.91 | 311004.43 | 115255.28 | 55187.5 | 487475.12 | 1812.5 | 489287.62 | 0 | [6 empty] | CM_WSI | 100%
503929 | Finnieston Tunnel sewer relining DALMUIR DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-22 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 1808.41 | 98392.88 | 100201.29 | -201.29 | 100000 | 0 | [6 empty] | CM_WWI | 100%
503574 | FIRE SAFETY FOLLOW ON WORK | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2021-01-29 | 2021-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 79464.59 | 220535.41 | 300000 | 0 | 300000 | 0 | [6 empty] | CM_M&G | 100%
36019 | Fire Safety Remedial Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWMD | Wastewater non infrastructure | MS7 | 2007-06-13 | 2007-06-13 | 2009-05-25 | 2017-03-28 |  | Scottish Water Wide | 962430 | -121.11 | 0 | 0 | 0 | 0 | 0 | -121.11 | 0 | 962308.89 | 0 | [6 empty] | WSNI | 50% | WWNI | 50%
50028 | First Time Provision | Q&S4 | Supporting economic development | First Time Provision |  |  | General |  | SWD | First Time Provision | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1700836.83 | 1700836.83 | -3310354.63 | -1609517.8 | 1084027.07 | [6 empty] | WG3 | 100%
503670 | First Time Provision - Ayr Bathing Waters improvement study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2019-08-23 | 2019-11-20 | 2019-11-21 | 2020-03-24 | 2020-09-14 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 109386.27 | 13095.74 | 122482.01 | 0 | 122482.01 | 0 | [6 empty] | EC16 | 100%
503669 | First Time Provision - Dhoon Bay Bathing Water improvement study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2019-08-23 | 2019-11-20 | 2019-11-21 | 2020-03-24 | 2020-09-07 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 36918 | 9092 | 46010 | 0 | 46010 | 0 | [6 empty] | EC16 | 100%
402956 | Fisher Avenue Kilsyth Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2015-08-25 | 2015-08-31 | 2015-09-14 | 2015-09-14 | East Dunbartonshire | 183243.64 | -183243.64 | -782.71 | 80.86 | 0 | 0.34 | 0 | -183945.15 | 0 | -701.51 | 204193.13 | [6 empty] | CS11 | 50% | CS15 | 50%
400764 | Fixed Life Asset - System Meters DI Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-10-02 |  | Scottish Water Wide | 1980000 | 5564.1 | 0 | 0 | 0 | 0 | 2852.07 | 8416.17 | 0 | 1988416.17 | 0 | [6 empty] | CM_WSI | 100%
402214 | Fixed Life Asset - System Meters TM and SR Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-08-02 | 2011-08-02 | 2011-08-01 | 2015-07-02 |  | Scottish Water Wide | 914154 | -880.78 | 3720.12 | 0 | 0 | 0 | 0 | 2839.34 | 0 | 916993.34 | 0 | [6 empty] | CM_WSI | 100%
500959 | Fixed Wire Testing - Pilot Scheme | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2015-09-17 | 2016-03-15 | 2016-03-15 | 2017-04-03 | 2017-04-04 | Scottish Water Wide | 0 | 521826.19 | 1971873.09 | -290.21 | 0 | 0 | 0 | 2493409.07 | 0 | 2493409.07 | 0 | [6 empty] | CM_M&G | 100%
502440 | Fixed Wire Testing - Wastewater East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 447850.38 | 1432334.56 | 1294290.06 | 1491543.97 | 1681478 | 6347496.97 | 0 | 6347496.97 | 0 | [6 empty] | CM_M&G | 100%
502442 | Fixed Wire Testing - Wastewater North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 278955.53 | 660222.47 | 1458950 | 932267.94 | 1200165 | 4530560.94 | 0 | 4530560.94 | 0 | [6 empty] | CM_M&G | 100%
502436 | Fixed Wire Testing - Wastewater South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 390610.3 | 1246277.51 | 611041.19 | 975142 | 1161489.03 | 4384560.03 | 0 | 4384560.03 | 0 | [6 empty] | CM_M&G | 100%
502438 | Fixed Wire Testing - Wastewater West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 465388.44 | 481743.4 | 693211.16 | 740158 | 857854.43 | 3238355.43 | 0 | 3238355.43 | 0 | [6 empty] | CM_M&G | 100%
502441 | Fixed Wire Testing - Water East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 354165.6 | 583928.4 | 540293 | 1636702.87 | 901234.46 | 4016324.33 | 0 | 4016324.33 | 0 | [6 empty] | CM_M&G | 100%
502435 | Fixed Wire Testing - Water North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 300991.69 | 1313771.87 | 674439.44 | 1025879 | 1195625.79 | 4510707.79 | 0 | 4510707.79 | 0 | [6 empty] | CM_M&G | 100%
502437 | Fixed Wire Testing - Water South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 390780.16 | 207725.84 | 326381 | 581253 | 542763 | 2048903 | 0 | 2048903 | 0 | [6 empty] | CM_M&G | 100%
502439 | Fixed Wire Testing - Water West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 468265.76 | 531870.24 | 472456.61 | 786171.12 | 813984 | 3072747.73 | 0 | 3072747.73 | 0 | [6 empty] | CM_M&G | 100%
501552 | Fixed Wire Testing Holding Line - SWD | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 130841.12 | -130841.05 | 0 | 0 | 0 | 0 | 0.07 | 0 | 0.07 | 0 | [6 empty] | CM_WWI | 100%
502934 | Flemington Road Glenrothes Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2019-01-21 | 2020-05-18 | 2020-07-27 | 2021-02-05 | 2021-05-13 | Fife | 0 | 0 | 0 | 16215.4 | 18762.43 | 185558.01 | 1226202.19 | 1446738.03 | 42635.52 | 1489373.55 | 0 | [6 empty] | CM_WWI | 100%
500432 | Flood Management Action Plan - FMAP | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-11 | 2016-09-19 | 2016-09-19 | Scottish Water Wide | 0 | 1021661 | 95378.34 | 2105.92 | 0 | 0 | 1806.9 | 1120952.16 | 0 | 1120952.16 | 1830849.77 | [6 empty] | SG5 | 100%
503481 | Flood Risk Alleviation - Larchwood Road - Galashiels Selkirk Supply DMA | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-03-31 | 2022-01-17 | 2022-03-24 | 2022-08-10 | 2022-11-10 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 549.3 | 6929.5 | 7478.8 | 194756.21 | 202235.01 | 0 | [6 empty] | CM_WSI | 100%
500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-09-11 | 2020-12-14 | Scottish Water Wide | 0 | 314167 | 270363.44 | 649727.46 | 1157101.2 | 931022.51 | 56372.39 | 3378754 | 0 | 3378754 | 7517904.3 | [6 empty] | CS16D | 100%
402021 | Flood Risk Mitigation at Balmoor RWI - PS Forehill WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-18 | 2012-07-06 | 2012-08-27 | 2013-03-28 | 2013-03-29 | Aberdeenshire | 33020 | -991.96 | 0 | 0 | 0 | 0 | 0 | -991.96 | 0 | 32028.04 | 0 | [6 empty] | CS16W | 100%
401684 | Flood risk mitigation at Kirbister WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-01 | 2014-07-24 | 2014-08-18 | 2015-03-19 | 2015-03-27 | Orkney Islands | 1243064 | 458533.6 | 10005.11 | -4595.23 | 0 | 0 | 0 | 463943.48 | 0 | 1707007.48 | 12479 | [6 empty] | CS16W | 100%
401683 | Flood Risk Mitigation at River Tay Raw Water PS Perth | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-03 | 2013-10-17 | 2013-11-11 | 2014-03-07 | 2014-03-24 | Perth and Kinross | 368016 | -589.55 | -2645.27 | 0 | 0 | 0 | 0 | -3234.82 | 0 | 364781.18 | 5192 | [6 empty] | CS16W | 100%
402020 | Flood Risk Mitigation at Ross Priory RWPS | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-16 | 2012-12-19 | 2013-02-04 | 2014-03-13 | 2014-03-31 | West Dunbartonshire | 756766.86 | 12358.9 | 5811.77 | 0 | 0 | 0 | 0 | 18170.67 | 0 | 774937.53 | 0 | [6 empty] | CS16W | 100%
502647 | Flooding Programme Support | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-03-31 | 2022-03-01 | 2022-05-20 | 2022-12-21 | 2023-03-23 | Scottish Water Wide | 0 | 0 | 10171.6 | 634301.92 | 190526.48 | 25239.48 | 14760.53 | 875000.01 | 0 | 875000.01 | 196097.17 | [6 empty] | CS11A | 100%
501003 | Flow Return and Top End Compliance Utility | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2016-02-29 | 2016-02-29 | 2019-05-13 | 2019-05-13 | Scottish Water Wide | 0 | 32769.87 | 55709.13 | 12690 | 37597 | -2865.12 | 0 | 135900.88 | 0 | 135900.88 | 0 | [6 empty] | CM_WSNI | 100%
500773 | Flures Avenue (Garnieland) Erskine Partial Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-24 | 2017-06-27 | 2017-07-31 | 2017-12-19 | 2017-12-19 | Glasgow City | 0 | 27000 | 35014.12 | 464774.93 | 1482.07 | -1354.45 | 65.34 | 526982.01 | 0 | 526982.01 | 0 | [6 empty] | CM_WWI | 100%
502320 | FMAP - Flooding Management Action Plan - Year 2 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2016-08-23 | 2016-08-23 | 2016-10-26 | 2017-09-25 | 2017-09-25 | Scottish Water Wide | 0 | 0 | 1020877.33 | 195948.15 | -74690.4 | 0 | 0 | 1142135.08 | 0 | 1142135.08 | 1830849.77 | [6 empty] | SG5 | 100%
502716 | FMAP - Flooding Management Action Plan - Year 3 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2017-05-04 | 2017-05-04 | 2017-06-01 | 2018-10-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 831214.95 | 424000 | -28841.11 | -570.15 | 1225803.69 | 0 | 1225803.69 | 1830849.77 | [6 empty] | SG5 | 100%
503559 | FMAP - Flooding Management Action Plan - Year 5 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS3 | 2019-03-26 | 2019-03-26 | 2019-06-03 |  | 2020-06-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 900000 | 60000 | 960000 | 0 | 960000 | 1830849.77 | [6 empty] | SG5 | 100%
505610 | FMAP - Flooding Management Action Plan - Year 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2020-04-01 | 2020-03-31 | 2021-04-13 | 2021-10-12 | 2022-01-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 1000000 | 0 | [6 empty] | CM_WWI | 100%
503131 | FMAP - Flooding Management Action Plan - Yr 4 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS5 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2019-07-15 | 2019-07-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 657266.95 | -11050.78 | 95.9 | 646312.07 | 0 | 646312.07 | 1830849.77 | [6 empty] | SG5 | 100%
501295 | FMAP Holding Line - SR15 Yr2-6 -Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 80.87 | 0 | 0 | 0 | 80.87 | 0 | 80.87 | 1830849.77 | [6 empty] | SG5 | 100%
500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-28 | 2018-03-29 | Moray | 0 | 8629 | 13732.56 | 37136.07 | 5231.94 | 0 | 0 | 64729.57 | 0 | 64729.57 | 45394.19 | [6 empty] | EC01G | 3.399% | EC01D | 38.39% | CS16D | 58.21%
500938 | Fochabers Main SPS Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2018-01-31 | 2018-03-12 | 2019-03-22 | 2019-03-22 | Moray | 0 | 8755 | 97090 | 274388 | 913105 | 24536 | 0 | 1317874 | 0 | 1317874 | 0 | [6 empty] | CM_WWI | 100%
503216 | Fochabers WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-03-17 | 2022-08-30 | 2022-12-27 | 2023-12-22 | 2024-03-25 | Moray | 0 | 0 | 0 | 0 | 65856.09 | 26606.5 | 50008.14 | 142470.73 | 1359529.27 | 1502000 | 136478.56 | [6 empty] | SG1 | 100%
500968 | FOCHABERS WWTW 1966 NJ341599 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2015-10-05 | 2018-01-31 | 2018-02-26 | 2020-02-13 | 2020-07-13 | Moray | 0 | 31252 | 205759.18 | 462381.3 | 1276842.4 | 437820.12 | 15408.4 | 2429463.4 | 6559.6 | 2436023 | 0 | [6 empty] | CM_WWNI | 100%
500909 | Fochabers WwTW Discharge Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-09-02 | 2027-10-15 | 2028-02-10 | 2028-10-18 | 2029-01-18 | Moray | 0 | 10688 | 109660 | 9722 | 0 | -6468.88 | 9840.75 | 133441.87 | 83287.15 | 216729.02 | 0 | [6 empty] | CM_WWNI | 100%
502758 | Foodieash ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-11-04 | 2022-09-21 | 2023-01-16 | 2023-05-23 | 2023-08-23 | Fife | 0 | 0 | 0 | 31143.1 | 1716.52 | 2461.71 | 3647823.92 | 3683145.25 | 4353831.79 | 8036977.04 | 136478.56 | [6 empty] | SG1 | 100%
403486 | Foodieash ST - Growth - 4034860000 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-17 | 2016-12-14 | 2016-12-14 | 2016-12-15 | 2016-12-15 | Fife | 46190 | 8043 | -1340.27 | 121.29 | 0 | 0 | 0 | 6824.02 | 0 | 53014.02 | 0 | [6 empty] | SG1 | 100%
503488 | FOP Funded Pressure Transient Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-03-05 | 2019-03-05 | 2020-03-23 | 2021-02-22 | 2021-05-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 217451.72 | 146687.37 | 184551.28 | 548690.37 | 13309.61 | 561999.98 | 0 | [6 empty] | CM_WSNI | 100%
504527 | Fordyce WWTW Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-09-30 | 2020-05-22 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2000 | 59528.41 | 61528.41 | 0 | 61528.41 | 0 | [6 empty] | CM_WWNI | 100%
501268 | Fordyce WwTW Final Effluent Discharge Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-02-12 | 2027-05-13 | 2027-07-20 | 2027-09-23 | 2027-12-24 | Aberdeenshire | 0 | 541.27 | 36618.73 | -8056.16 | 17000 | -4049.4 | 4049.4 | 46103.84 | 28896.16 | 75000 | 0 | [6 empty] | CM_WWNI | 100%
502360 | Forehill WTW CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-05-14 | 2028-12-28 | 2029-05-02 | 2030-07-23 | 2030-10-23 | Aberdeenshire | 0 | 0 | 44037.75 | 8138.56 | 6234.58 | 4422.83 | -4331.13 | 58502.59 | 37497.4 | 95999.99 | 0 | [6 empty] | CM_WSNI | 100%
500728 | Forest Road WWPS 1994 NJ786165 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-07-07 | 2016-02-19 | 2016-05-31 | 2017-02-07 | 2017-02-07 | Aberdeenshire | 0 | 38679.43 | 103300.57 | 12987 | -7239.14 | 0 | 7709.14 | 155437 | 0 | 155437 | 0 | [6 empty] | CM_WWNI | 100%
403969 | Forestmill ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS2 | 2016-08-19 | 2019-12-23 | 2022-05-20 | 2023-01-09 | 2023-04-11 | Clackmannanshire | 967.25 | 26789.19 | 16366.37 | 40698.19 | 96175 | 2392.02 | 0 | 182420.77 | 5108.65 | 188496.67 | 0 | [6 empty] | SG1 | 100%
30282 | Forfar New STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2012-03-27 | 2012-10-15 | 2013-09-30 | 2013-10-16 | Angus | 1817236.61 | -1399.68 | 0 | 0 | 0 | 0 | 0 | -1399.68 | 0 | 1815836.93 | 2051.56 | [6 empty] | CM_WWNI | 45% | EC04A | 55%
404115 | Former Ballerup High School East Kilbride Off Site Storage Solution | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-06-01 | 2020-03-19 | 2020-03-23 | 2019-09-19 | 2019-09-19 | South Lanarkshire | 0 | 64458.99 | 0 | 0 | 0 | 61.99 | 64397 | 128917.98 | 0 | 128917.98 | 0 | [6 empty] | CM_WWI | 100%
500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-12-12 | 2020-01-07 | Moray | 0 | 24530.29 | 37738.71 | 25403 | 101905 | 77873 | 12550 | 280000 | 0 | 280000 | 320760.51 | [6 empty] | EC01G | 3.18% | EC01D | 20.41% | CS16D | 76.41%
502811 | Forres WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-16 | 2028-07-12 | 2028-11-02 | 2029-10-23 | 2030-01-23 | Moray | 0 | 0 | 0 | 64690.06 | 7241.07 | 2141.44 | 0 | 74072.57 | 67927.43 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
500580 | Forres WWTW 1973 NJ038595 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-06-02 | 2019-10-03 | 2019-11-05 | 2021-04-28 | 2021-07-30 | Moray | 0 | 554787 | -170134.47 | 202978.36 | 574817.42 | 841409.69 | 3499569 | 5503427 | 49695 | 5553122 | 0 | [6 empty] | CM_WWNI | 100%
502251 | Forres WwTW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2018-05-30 | 2020-06-15 | 2020-08-26 | 2021-05-05 | 2021-08-09 | Moray | 0 | 0 | 8334.97 | 3419.24 | 890.38 | 8548.97 | 72514.78 | 93708.34 | 7772.88 | 101481.22 | 0 | [6 empty] | CM_WWI | 100%
45577 | Fort Augustus New WTW Upgrade Disinfection Control DW13 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-07-25 | 2012-03-26 | 2012-04-16 | Highland | 54368.07 | 156.3 | 0 | 0 | 0 | 0 | 0 | 156.3 | 0 | 54524.37 | 0 | [6 empty] | DW13 | 100%
500825 | Fort Augustus RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-03-31 | 2017-11-30 | Highland | 0 | 7753 | 16822.39 | 6578.93 | 2798.68 | -1588.1 | 0.01 | 32364.91 | 0 | 32364.91 | 35596.83 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 10.7
502878 | Fort Augustus WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-26 | 2019-04-26 | Highland | 0 | 0 | 0 | 21360.69 | 1536.1 | -20947.96 | 0 | 1948.83 | 0 | 1948.83 | 136478.56 | [6 empty] | WG1 | 100%
505106 | Fort Augustus WwTW - Inlet Screen Access | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_M&G | 100%
505116 | Fort Augustus WwTW - Scum Removal System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWNI | 100%
45796 | Fort Hill SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-03-21 | 2011-08-23 | 2012-03-22 | 2012-03-29 | Scottish Borders | 416246.08 | 266.75 | 0 | 0 | 0 | 0 | 0 | 266.75 | 0 | 416512.83 | 0 | [6 empty] | CM_WWNI | 10.06% | WQ01C | 89.94%
503388 | Forteviot ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-10-27 | 2029-03-01 | 2030-04-08 | 2030-07-09 | Perth and Kinross | 0 | 0 | 0 | 0 | 70898.48 | 5567.17 | 0 | 76465.65 | 65534.35 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
500004 | Forth Area Submarine PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-05-06 | 2017-05-31 | 2017-09-07 | 2018-08-27 | 2018-08-27 | Scottish Water Wide | 0 | 129500 | 265188 | 1266094 | 639603 | 9563.55 | -82.55 | 2309866 | 0 | 2309866 | 0 | [6 empty] | CM_WWNI | 100%
400120 | Forth Cluster 1 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-24 | 2012-10-22 | 2014-06-16 |  | Clackmannanshire | 646814 | 427 | -132.04 | 0 | 0 | 0 | 8.07 | 303.03 | 0 | 647117.03 | 0 | [6 empty] | CM_WSI | 100%
400121 | Forth Cluster 2 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-28 | 2012-10-22 | 2014-06-25 |  | East Dunbartonshire | 808054 | 1465.32 | 0 | 311.93 | 0 | 0 | 0 | 1777.25 | 0 | 809831.25 | 0 | [6 empty] | CM_WSI | 100%
501282 | Forth Estuary Sewage Related Debris Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-12-01 | 2017-03-28 | 2017-05-22 | 2018-06-20 | 2018-06-20 | All East Unitary Authorities | 0 | 3722.95 | 142768.05 | 419241.86 | 53653.2 | 86.12 | 112.13 | 619584.31 | 0 | 619584.31 | 0 | [6 empty] | EC01G | 100%
401501 | Forth Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-20 | 2011-12-20 | 2012-01-30 | 2015-03-10 |  | All West Unitary Authorities | 2336312 | 161930 | 37790.51 | 10986.62 | 0 | 0 | 0 | 210707.13 | 0 | 2547019.13 | 0 | [6 empty] | CM_WSI | 100%
403571 | Forth WwTW - Capital Maintenance Interventions CMC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2017-02-16 |  | North Lanarkshire | 694483 | 227890 | 9808.41 | 1351.53 | 0 | 0 | 0 | 239049.94 | 0 | 933532.94 | 0 | [6 empty] | CM_WWNI | 100%
500139 | Fortrose DOA (DOA000907) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-12-19 | 2017-01-11 | 2019-02-28 | 2019-06-30 | Highland | 0 | 11621 | 15843 | 14703 | 43795 | -4338.45 | 0 | 81623.55 | 0 | 81623.55 | 10344.04 | [6 empty] | EC01G | 100% | bar: Regulatory Outputs OMG-23
300029 | Fortrose WwTW - Completion Project (CID) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-11-16 | 2012-03-20 | 2012-06-06 | 2013-11-27 | 2013-09-30 | Highland | 2894000 | -2876.39 | 0 | 0 | 0 | 0 | 0 | -2876.39 | 0 | 2891123.61 | 0 | [6 empty] | EC01 | 100%
501740 | Fossil Grove Kirkintilloch - Repair sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2027-06-10 | 2028-02-14 | 2028-04-27 | 2028-09-08 | 2028-12-11 | East Dunbartonshire | 0 | 0 | 3348.84 | 9389.18 | 1967.45 | 9.24 | -714.71 | 14000 | 410184.99 | 424184.99 | 0 | [6 empty] | CM_WWI | 100%
501229 | Foula WTW (Reduction of risks identified in Drinking Water Safety Plan - Distribution) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-17 | 2015-11-17 | 2015-12-16 | 2015-12-31 | 2016-03-31 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
46857 | Foula WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-07-31 | 2013-06-28 | 2015-11-24 | 2015-12-22 | Shetland Islands | 3757923.44 | 20964.08 | -11369.61 | -782 | 0 | 0 | 0 | 8812.47 | 0 | 3766735.91 | 42872.46 | [6 empty] | CM_WSI | 30.28% | DW23 | 69.72%
403687 | Frandy Cottages PWS Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2014-03-18 | 2014-11-20 | 2014-11-20 | 2015-04-07 | 2015-05-28 | Perth and Kinross | 99049.85 | 787.97 | 0 | 0 | 0 | 0 | 0 | 787.97 | 0 | 99837.82 | 0 | [6 empty] | DW10 | 100%
500978 | Fraser Street Inverness Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-06-24 | 2017-03-30 | 2017-09-18 | 2017-11-24 | 2017-11-24 | Highland | 0 | 0 | 25442.08 | 117519.5 | 1282.86 | 1348.77 | 902.81 | 146496.02 | 0 | 146496.02 | 0 | [6 empty] | CM_WWI | 100%
500141 | Fraserburgh Phingask DOA (DOA000360) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-28 | 2019-02-05 | Aberdeenshire | 0 | 82416 | 129492 | 80151 | 23194.48 | 0 | 0 | 315253.48 | 0 | 315253.48 | 10344.04 | [6 empty] | EC01G | 19.97% | CS16D | 80.03%
403253 | Freuchie WwTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-11 | 2014-01-07 | 2014-05-19 | 2014-11-07 |  | Fife | 216779 | 0 | -242.01 | 0 | 0 | 0 | 0 | -242.01 | 0 | 216536.99 | 0 | [6 empty] | CM_WWNI | 100%
500788 | Friockheim Old & New WwTWs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-08-31 | 2027-07-07 | 2027-08-19 | 2028-06-30 | 2028-10-02 | Angus | 0 | 40099 | 152180.95 | 12029.5 | -5772.9 | 0 | 0 | 198536.55 | 1549979.91 | 1748516.46 | 0 | [6 empty] | CM_WWNI | 100%
502615 | Friockheim Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-04 | 2017-09-28 | Angus | 0 | 0 | 2359.94 | 5926.05 | 0 | 0 | -30.99 | 8255 | 0 | 8255 | 0 | [6 empty] | CM_WWI | 100%
501280 | Friockheim WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-07-27 | 2016-07-27 | Angus | 0 | 9054.59 | 747.63 | 0 | 0 | 0 | 0 | 9802.22 | 0 | 9802.22 | 136478.56 | [6 empty] | SG1 | 100%
500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS3 | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2021-05-12 | 2021-08-04 | Scottish Water Wide | 0 | 195637 | 533343.97 | 670435.94 | 747653.69 | 242584.97 | 26886.38 | 2416541.95 | 0 | 2416541.95 | 980126.37 | [6 empty] | WR6 | 100%
501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-23 | 2018-09-03 | Scottish Water Wide | 0 | 73764 | 126964.27 | 22205.77 | -15707.88 | 0 | 0 | 207226.16 | 0 | 207226.16 | 0 | [6 empty] | CS16D | 100%
502534 | FRMA Section 33-34 -Optioneering - Aberdeen catchment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-28 | 2017-02-28 | 2017-04-21 | 2018-02-26 | 2018-02-26 | Aberdeen City | 0 | 0 | 144000 | 123789.84 | 85023.16 | 11092.02 | 0 | 363905.02 | 0 | 363905.02 | 9297166.67 | [6 empty] | CS11A | 45.04% | EC10B | 54.96%
502535 | FRMA Section 33-34 -Optioneering - Ayrshire catchment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-21 | 2017-09-15 | 2017-09-15 | North Ayrshire | 0 | 0 | 7365.72 | 29472.3 | 579.37 | 0 | 0 | 37417.39 | 0 | 37417.39 | 9297166.67 | [6 empty] | CS11A | 46.55% | EC10B | 53.45%
502536 | FRMA Section 33-34 -Optioneering - Edinburgh catchment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-20 | 2017-09-15 | 2017-09-15 | City of Edinburgh | 0 | 0 | 10521.03 | 24906.82 | 0 | 0 | 0 | 35427.85 | 0 | 35427.85 | 9297166.67 | [6 empty] | CS11A | 28.23% | EC10B | 71.77%
502537 | FRMA Section 33-34 -Optioneering - Falkirk catchment | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-20 | 2017-09-15 | 2017-09-15 | Falkirk | 0 | 0 | 7365.72 | 15240.13 | 0 | 0 | 0 | 22605.85 | 0 | 22605.85 | 9297166.67 | [6 empty] | EC10B | 46.55% | CS11A | 53.45%
502538 | FRMA Section 33-34 -Optioneering - Tayside catchment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-09-15 | 2017-09-15 | Dundee City | 0 | 0 | 7365.72 | 10423.78 | 0 | 0 | 0 | 17789.5 | 0 | 17789.5 | 9297166.67 | [6 empty] | CS11A | 43.79% | EC10B | 56.21%
403642 | Frontier BM Org Implementation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-18 | 2013-12-18 | 2013-12-30 | 2015-09-24 |  | Scottish Water Wide | 266683 | -25510.2 | 0 | 0 | 0 | 0 | 0 | -25510.2 | 0 | 241172.8 | 0 | [6 empty] | CM_M&G | 100%
402680 | Frontier Futures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2012-05-18 | 2016-05-12 | 2015-11-05 | 2015-11-06 |  | Scottish Water Wide | 1414685.71 | -464.72 | 0 | 0 | 0 | 0 | 0 | -464.72 | 0 | 1414220.99 | 0 | [6 empty] | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
403644 | Frontier Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-20 | 2014-05-20 | 2014-05-20 | 2015-07-28 |  | Scottish Water Wide | 496725 | -7024.38 | 0 | 0 | 0 | 0 | 0 | -7024.38 | 0 | 489700.62 | 0 | [6 empty] | CM_M&G | 100%
403287 | Frontier North Reservoir CM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2013-07-12 | 2013-08-05 | 2014-12-17 |  | Scottish Water Wide | 538174.78 | -476.62 | 0 | 0 | 0 | 0 | 0 | -476.62 | 0 | 537698.16 | 0 | [6 empty] | CM_WSI | 100%
403288 | Frontier South Reservoir CM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2014-03-19 | 2014-03-03 | 2014-03-03 |  | Scottish Water Wide | 91330.89 | 1105 | 0 | 0 | 0 | 0 | 0 | 1105 | 0 | 92435.89 | 0 | [6 empty] | CM_WSI | 100%
403286 | Frontier West Reservoir CM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2014-03-19 | 2014-03-03 | 2014-03-03 |  | Scottish Water Wide | 281927.69 | 299 | 0 | 0 | 0 | 0 | 0 | 299 | 0 | 282226.69 | 0 | [6 empty] | CM_WSI | 100%
503541 | Fudstone WwPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2020-02-05 | 2021-01-25 | 2021-04-19 | 2021-11-15 | 2022-02-15 | North Ayrshire | 0 | 0 | 0 | 0 | 18083.72 | 37253.28 | 108920.35 | 164257.35 | 164903.65 | 329161 | 0 | [6 empty] | CM_WWI | 100%
46360 | Fyvie WWTP Refurb - STW001483 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-28 | 2010-09-29 | 2011-02-21 | 2012-02-16 |  | Aberdeenshire | 1367791.79 | 622.5 | 0 | 0 | 0 | 0 | 0 | 622.5 | 0 | 1368414.29 | 0 | [6 empty] | CM_WWNI | 100%
401923 | G SR10 Growth Guillotine (waste) from SR6 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 17229131.57 | 0.43 | 0 | 0 | 0 | 0 | 0 | 0.43 | 0 | 17229132 | 0 | [6 empty] | SG1 | 100%
401922 | G SR10 Growth Guillotine (water) from SR6 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 4508509.77 | 0.23 | 0 | 0 | 0 | 0 | 0 | 0.23 | 0 | 4508510 | 0 | [6 empty] | WG1 | 100%
46159 | Gailes SPS Refurb - SPS000198 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-03-31 | 2011-07-18 | 2014-10-30 | 2014-10-30 | North Ayrshire | 10217887.65 | 335374.86 | -14136.85 | 0 | 0 | 0 | 0 | 321238.01 | 0 | 10539125.66 | 0 | [6 empty] | CM_WWNI | 100%
403894 | Gairloch WWTW - Low Carbon Treatment - SR15 Capital Maintenance | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2017-04-30 | 2017-08-01 | 2019-01-28 | 2020-02-29 | 2020-02-29 | Highland | 9120 | 142318 | 64871.92 | 345611.25 | 655481.17 | 2408265 | 125192.66 | 3741740 | 1586.84 | 3752446.84 | 173482.21 |  |  |  |  | -50114.77 |  | EC02A | 42.6% | CM_WWNI | 57.4% | bar: Regulatory Outputs OMG-21
403213 | Gala WWTW - Design Supply and Install Combined Heat and Power (CHP) System | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-01-21 | 2015-02-26 | 2015-02-26 | 2015-03-25 | 2015-03-25 | Scottish Borders | 849238 | 228720 | 68561 | 3495 | 2367.28 | -8482.33 | 0 | 294660.95 | 0 | 1143898.95 | 106097 | [6 empty] | CC1W | 100%
500133 | Galashiels DOA (DOA000032) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-07-12 | 2018-08-08 | Scottish Borders | 0 | 19895 | 33649 | 57826 | -57.4 | 0 | -109.31 | 111203.29 | 0 | 111203.29 | 336967.95 | [6 empty] | EC01D | 26.93% | CS16D | 73.07%
501405 | Galashiels Langshaw TWP NT516363 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-05-31 | 2027-10-18 | 2028-02-21 | 2028-06-30 | 2028-10-02 | Scottish Borders | 0 | 0 | 6324.78 | 595.82 | 2207.44 | 52.79 | -52.79 | 9128.04 | 218191.01 | 227319.05 | 0 | [6 empty] | CM_WSNI | 100%
503235 | Galashiels Manse Street Infra | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS3 | 2018-05-31 | 2019-03-29 | 2019-04-29 | 2021-12-23 | 2022-03-25 | Scottish Borders | 0 | 0 | 0 | 0 | 1023930.42 | 6108422.09 | 958689.82 | 8091042.33 | 663514 | 8754556.33 | 2119700.51 | [6 empty] | DW25P | 10.73% | WR1 | 18.27% | CM_WSI | 71%
500245 | Galashiels Manse Street WTW | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | NONINF | SOSI | MS3 | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2021-07-19 | 2021-10-18 | Scottish Borders | 0 | 67704.37 | 390007.15 | 625335.21 | 1161161.07 | 848233.19 | 4754134.02 | 7846575.01 | 2979162.3 | 10825737.31 | 2119700.51 |  |  |  |  | 1000 |  | CM_WSI | 13.3% | DW25P | 14% | WR1 | 23.9% | CM_WSNI | 48.8%
400063 | Galashiels STC Refurb STC000089 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-14 | 2011-05-03 | 2011-08-01 | 2015-08-27 |  | Scottish Borders | 2913508.47 | -179181.13 | 270 | 589.78 | 0 | 0 | 0 | -178321.35 | 0 | 2735187.12 | 0 |  |  |  |  | 27876 |  | CM_WWNI | 100%
30290 | Galashiels STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-29 | 2011-05-05 | 2011-08-01 | 2015-12-11 | 2016-02-25 | Scottish Borders | 4138179.87 | 143137.41 | 11113.17 | -2910.39 | 0 | 0 | 0 | 151340.19 | 0 | 4289520.06 | 36213.36 |  |  |  |  | 27879.5 |  | CM_WWNI | 40.36% | EC01A | 59.64%
503259 | Galashiels WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-20 | 2023-10-10 | 2024-02-02 | 2025-01-28 | 2025-04-30 | Scottish Borders | 0 | 0 | 0 | 0 | 68097.92 | 1467.32 | 50234.78 | 119800.02 | 1880200.07 | 2000000.09 | 136478.56 | [6 empty] | SG1 | 100%
503290 | Galashiels WWTW - Lagoon Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-04-06 | 2028-11-08 | 2029-03-09 | 2030-06-07 | 2030-09-09 | Scottish Borders | 0 | 0 | 0 | 0 | 21883.55 | 96.89 | 19422.49 | 41402.93 | 1958597.05 | 1999999.98 | 0 | [6 empty] | CM_WWNI | 100%
401374 | Gap Sites and Vacant Properties Incentive Process | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2010-09-07 | 2011-02-21 | 2011-04-29 | 2015-07-31 | 2011-03-14 | Scottish Water Wide | 960799 | -8957.13 | 0 | 0 | 0 | 0 | 0 | -8957.13 | 0 | 951841.87 | 0 | [6 empty] | CS20 | 100%
501576 | Gaps3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-01-18 | 2016-01-18 | 2016-02-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 2228941.22 | 1162511.88 | -685647.93 | 0 | 0 | 0 | 2705805.17 | 0 | 2705805.17 | 0 | [6 empty] | CM_WSI | 100%
502787 | Garbethill 30inch Trunk mains (local network reinforcement) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2017-06-30 | 2017-10-30 | 2017-10-31 | 2018-02-28 | 2018-02-28 | North Lanarkshire | 0 | 0 | 0 | 2329220.04 | -427932.15 | -132776.02 | 199119.04 | 1967630.91 | 0 | 1967630.91 | 0 | [6 empty] | CM_WSI | 100%
402213 | Garbethill inlet main - Mitigating Risk of Failure | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-18 | 2015-03-24 | 2015-04-29 | 2015-04-02 |  | North Lanarkshire | 70000 | -1861.64 | 0 | 0 | 0 | 0 | 0 | -1861.64 | 0 | 68138.36 | 0 | [6 empty] | CM_WSI | 100%
502396 | Garbethill Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2017-06-21 | 2023-07-18 | 2023-08-18 | 2024-03-06 | 2024-03-07 | East Dunbartonshire | 0 | 0 | 7129.27 | 20076.73 | 82222.39 | 8604.18 | 0 | 118032.57 | 563573.1 | 681605.67 | 0 | [6 empty] | CM_WSI | 100%
503413 | Garbethill WSZ Trunk Main Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2020-03-26 | 2020-10-26 | 2020-10-30 | 2021-06-30 | 2021-09-30 | Moray | 0 | 0 | 0 | 0 | 91514.56 | 202276.46 | 696486.04 | 990277.06 | 722700.17 | 1712977.23 | 539345.26 | [6 empty] | DW5 | 100% | [18 empty] | Regulatory Outputs OMG-06: 83.9
503381 | Gardenstown WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 | 2029-04-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 76307.53 | 5609 | 0 | 81916.53 | 60083.47 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
403611 | Garlieston Harbour WWTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-11-07 | 2015-02-10 | 2015-07-27 | 2016-06-06 | 2016-06-06 | Dumfries and Galloway | 155449 | 383756 | 5623.52 | 0 | -828.22 | 0 | 0 | 388551.3 | 0 | 544000.3 | 0 | [6 empty] | SG1 | 100%
403254 | Garmouth SPS000832 & Storm SPS000833 Screens Pumps and Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2013-01-22 | 2016-03-29 | 2016-06-13 | 2016-11-03 | 2016-11-03 | Moray | 19920.46 | 43801.33 | 204957.16 | -976.95 | -100.61 | 0 | 0.61 | 247681.54 | 0 | 267602 | 0 | [6 empty] | CM_WWNI | 100%
503316 | Garmouth ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-06 | 2023-10-26 | 2024-02-23 | 2025-02-20 | 2025-05-23 | Moray | 0 | 0 | 0 | 0 | 31602.89 | 16193.97 | 62246.51 | 110043.37 | 639956.63 | 750000 | 136478.56 | [6 empty] | SG1 | 100%
502407 | Garmouth WwTW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2017-07-25 | 2021-07-23 | 2021-10-18 | 2022-05-03 | 2022-05-03 | Moray | 0 | 0 | 7070.44 | 2052.89 | 0 | 8768.36 | 7873.28 | 25764.97 | 30234.99 | 55999.96 | 0 | [6 empty] | CM_WWI | 100%
501085 | Gartcarron WOA Drymen WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2016-04-18 | 2018-03-30 | 2018-03-30 | 2018-11-26 | 2018-11-26 | Stirling | 0 | 26352 | 4206 | 167697.57 | 720960.35 | 28028.17 | 1066.17 | 948310.26 | 0 | 948310.26 | 0 | [6 empty] | CM_WSI | 100%
501084 | Gartcarron WOA Gartcarron WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | Stirling | 0 | 529.62 | -529.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501086 | Gartcarron WOA Low Lettre WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-13 | 2016-12-28 | 2017-03-06 | 2018-02-15 | 2018-02-15 | Stirling | 0 | 23904 | 102270 | 568645.8 | -21728.08 | -3970.02 | 1.3 | 669123 | 0 | 669123 | 0 | [6 empty] | CM_WSI | 100%
401412 | Gartcarron WTW Closure | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-10-13 | 2011-06-01 | 2011-06-15 | 2012-03-30 |  | Stirling | 4664274.29 | 495 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 4664769.29 | 0 | [6 empty] | CM_WSNI | 100%
45642 | Gartcarron WTW Refurb - WTW000633 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-24 | 2011-06-30 | 2011-06-30 | 2011-03-31 |  | Stirling | 138193.93 | -378.73 | 0 | 0 | 0 | 0 | 0 | -378.73 | 0 | 137815.2 | 0 | [6 empty] | CM_WSNI | 100%
402599 | Garthdee Syphon Flow Control and Screen | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2012-03-27 | 2027-12-27 | 2028-04-06 | 2029-07-03 |  | All East Unitary Authorities | 55600 | -476.57 | 19442.96 | 59472.45 | 45159.2 | 1045.41 | -1041.84 | 123601.61 | 2372241.88 | 2551443.49 | 0 | [6 empty] | CM_WWI | 100%
403004 | Gartly SPS pump - sewer replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-04 | 2013-03-22 | 2013-05-20 | 2013-08-01 |  | Aberdeenshire | 66053.36 | -2120.07 | 0 | 0 | 0 | 0 | 2120.07 | 0 | 0 | 66053.36 | 0 | [6 empty] | CM_WWI | 100%
502618 | Gartmore WSZ - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-27 | 2028-03-23 | 2028-06-13 | 2029-01-08 | 2029-04-10 | Stirling | 0 | 0 | 7600 | 0 | -93.43 | 5068.83 | 0 | 12575.4 | 349424.6 | 362000 | 0 | [6 empty] | CM_WSI | 100%
402347 | Gartmorn Reservoir - Improving scour capacity | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-20 | 2012-11-22 | 2013-01-14 | 2013-08-07 | 2013-08-07 | Clackmannanshire | 662764 | -833.9 | 0 | 0 | 0 | 0 | 0 | -833.9 | 0 | 661930.1 | 0 | [6 empty] | CM_WSI | 100%
30293 | Gartocharn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-08-22 | 2011-09-30 | 2013-03-20 | 2013-03-25 | West Dunbartonshire | 458320.82 | -4747.76 | 0 | 0 | 0 | 0 | 0 | -4747.76 | 0 | 453573.06 | 0 | [6 empty] | EC04A | 20% | CM_WWNI | 80%
501531 | Gartshore TWS Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-21 | 2030-01-25 | 2030-09-11 | 2030-12-12 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904142.04 | 904142.04 | 0 | [6 empty] | CM_WSNI | 100%
500808 | Garve RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-05-19 | 2017-12-31 | 2018-06-30 | Highland | 0 | 2010 | 174.7 | 6379.57 | 4227.63 | 0 | 0 | 12791.9 | 0 | 12791.9 | 19711.21 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 5.52
46852 | Garve WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-06-27 | 2014-01-06 | 2014-02-17 | Highland | 1488201.42 | -42102.16 | 774.7 | 0 | 0 | 0 | 0 | -41327.46 | 0 | 1446873.96 | 5489 | [6 empty] | DW23 | 100%
403144 | Gatehead - Irvine Valley Sewer River Bank Stabilisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2013-12-04 | 2014-02-28 | 2014-12-01 |  | East Ayrshire | 144925 | 0 | -1861.47 | 0 | 0 | 0 | 0 | -1861.47 | 0 | 143063.53 | 0 | [6 empty] | CM_WWI | 100%
500143 | Gatehouse Of Fleet DOA (DOA000098) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-27 | 2015-10-19 | 2016-10-31 | 2016-12-31 | Dumfries and Galloway | 0 | 47971 | 33479.98 | 0 | 0 | 0 | 0 | 81450.98 | 0 | 81450.98 | 72047.27 | [6 empty] | CS11 | 40.64% | CS16D | 59.36% | bar: Regulatory Outputs OMG-22
45631 | Gatehouse STW Refurb - STW000312 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-18 | 2011-02-14 | 2011-03-31 | 2013-03-26 |  | Dumfries and Galloway | 1560675.11 | 17638.04 | -114.55 | 0 | 0 | 0 | 0 | 17523.49 | 0 | 1578198.6 | 0 | [6 empty] | CM_WWNI | 100%
49030 | General Programme Risk | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS3 |  |  | 2010-04-01 | 2021-03-31 |  | Scottish Water Wide | 0 | -4000000 | 0 | 0 | 0 | 0 | 0 | -4000000 | 0 | -4000000 | 10008873.2 | [6 empty] | RISK | 100%
505570 | Generator Battery Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 13084.11 | 186129.72 | 199213.83 | 0 | 199213.83 | 0 | [6 empty] | CM_WSNI | 100%
500134 | Gifford DOA (DOA000514) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-01 | 2019-03-31 | 2019-07-31 | East Lothian | 0 | 12005 | 15136 | 17083 | 37454 | 10661.06 | 0.07 | 92339.13 | 0 | 92339.13 | 82952.13 | [6 empty] | EC01G | 13.52% | EC01D | 86.48% | bar: Regulatory Outputs OMG-23
503311 | Gifford WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-01 | 2028-09-20 | 2029-01-18 | 2030-01-21 | 2030-04-23 | East Lothian | 0 | 0 | 0 | 0 | 69110.49 | 7154.05 | 0 | 76264.54 | 65735.46 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
505537 | Gigha WTW - pH Correction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1923.72 | 8653.37 | 10577.09 | 439422.89 | 449999.98 | 0 | [6 empty] | CM_WSNI | 100%
500146 | Girvan DOA (DOA002467) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-26 | 2019-01-31 | South Ayrshire | 0 | 23967.68 | 109655.41 | 66195.91 | 63377.69 | 0 | -21.32 | 263175.37 | 0 | 263175.37 | 10344.04 | [6 empty] | CS16D | 45.51% | EC01G | 54.49%
501309 | Girvan Private Wire Project | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS3 | 2015-11-25 | 2015-11-25 | 2016-07-19 | 2020-05-01 | 2020-05-01 | South Ayrshire | 0 | 7602 | 36398 | -30.12 | 35.49 | 0 | 0 | 44005.37 | 0 | 44005.37 | 2561825.24 | [6 empty] | I2S_WWNI | 100%
500590 | GIS and Assets Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-01 | 2016-08-18 | 2016-08-18 | 2017-10-16 | 2018-01-22 | Scottish Water Wide | 0 | 281487.9 | 262956.1 | 142592.59 | 0.15 | 0 | 0 | 687036.74 | 0 | 687036.74 | 0 | [6 empty] | CM_M&G | 100%
500904 | GIS and Modelling Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-17 | 2016-09-23 | 2016-09-23 | 2018-07-12 |  | Scottish Water Wide | 0 | 2900124 | 2616598.85 | 1826234.73 | 152793.95 | 0 | 0 | 7495751.53 | 0 | 7495751.53 | 0 | [6 empty] | CM_M&G | 100%
500192 | Gladhouse Birds and Habitats Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2015-03-20 | 2016-09-27 | 2016-09-27 | 2017-12-31 | 2017-12-31 | Midlothian | 0 | 1928 | 8901 | 3079.57 | 41.28 | -1664.05 | 0 | 12285.8 | 0 | 12285.8 | 18948.39 | [6 empty] | EC08C | 100% | bar: Regulatory Outputs OMG-23
503487 | Gladhouse MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-10-04 | 2022-11-10 | 2023-03-15 | 2024-10-17 | 2025-01-17 | Midlothian | 0 | 0 | 0 | 0 | 0 | 158589.9 | 230346.81 | 388936.71 | 4688637.56 | 5077574.27 | 0 | [6 empty] | CM_WSI | 100%
501401 | Gladhouse WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-04-13 | 2028-04-24 | 2028-08-28 | 2029-04-12 | 2029-07-13 | Midlothian | 0 | 0 | 1687.85 | 0 | 995.51 | 412.82 | 451.24 | 3547.42 | 246452.68 | 250000.1 | 0 | [6 empty] | CM_WSNI | 100%
500234 | Glamis WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2017-08-15 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Angus | 0 | 49905.57 | 27672.17 | 7625.37 | 0 | 85203.11 | 0 | 170406.22 | 0 | 170406.22 | 136478.56 | [6 empty] | SG1 | 100%
500701 | Glascoego Trunk Main Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-06-17 | 2027-07-06 | 2027-09-01 | 2028-04-21 | 2029-04-16 | Aberdeenshire | 0 | 8759 | 111388 | 28101 | -5690 | -4395.11 | 22597.54 | 160760.43 | 299183.55 | 459943.98 | 0 | [6 empty] | CM_WSI | 100%
502086 | Glasgow Airport 18inch Spun Iron Main Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2016-04-08 | 2018-08-14 | 2018-09-11 | 2019-04-30 | 2019-04-30 | Renfrewshire | 0 | 0 | 92360 | 251602 | 3061857.49 | -2410.28 | 6583 | 3409992.21 | 0 | 3409992.21 | 0 | [6 empty] | CM_WSI | 100%
400526 | Glasgow Byres Road (Oxfam)- Internal Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-03-31 | 2012-05-22 | 2012-06-18 | 2013-01-30 | 2013-01-30 | Glasgow City | 26440.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26440.96 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
401880 | Glasgow City Centre Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-02 | 2012-08-30 | 2012-08-29 | 2015-03-26 |  | Glasgow City | 4527120 | -173603.53 | 182.95 | 0 | 0 | 0 | 0 | -173420.58 | 0 | 4353699.42 | 0 | [6 empty] | CM_WSI | 100%
401478 | Glasgow Sludge Contingency Plan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-11-18 | 2012-05-29 | 2012-09-18 | 2013-11-18 |  | Glasgow City | 3148288 | -7297.14 | 0 | 0 | 0 | 0 | 0 | -7297.14 | 0 | 3140990.86 | 0 |  |  |  |  | 68697 |  | CM_WWNI | 100%
403738 | Glasgow Sludge Main Rehabiliation Project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-04-03 | 2014-04-14 | 2014-04-14 | 2019-08-06 |  | Glasgow City | 259090.26 | 49249.74 | 18500.26 | -65514.41 | 0 | 0 | 0 | 2235.59 | 0 | 261325.85 | 0 | [6 empty] | CM_WWNI | 100%
501189 | Glasgow Sludge Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-29 | 2017-08-30 | 2017-08-31 | 2018-03-23 | 2018-03-23 | Glasgow City | 0 | 507137.65 | 268501.88 | 1429607.7 | -254722.91 | 1773.88 | 2572.85 | 1954871.05 | 0 | 1954871.05 | 0 | [6 empty] | CM_WWNI | 100%
502601 | Glasgow Sludge Main Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-02-02 | 2018-09-17 | 2018-09-17 | 2019-08-06 | 2019-08-06 | Renfrewshire | 0 | 0 | 23505 | 225098 | 850357.2 | 0 | 0 | 1098960.2 | 0 | 1098960.2 | 0 | [6 empty] | CM_WWI | 100%
46388 | Glasgow Strategic Study - Daldowie Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-28 | 2009-10-28 | 2019-03-04 | 2011-03-14 | Glasgow City | 2746876.29 | 2224.16 | 275.68 | 364.08 | 531.78 | 0 | 0 | 3395.7 | 0 | 2750271.99 | 2784 | [6 empty] | EC04C | 32.82% | EC10E | 32.82% | EC01D | 34.37%
46389 | Glasgow Strategic Study - Dalmarnock Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-08-28 | 2009-08-28 | 2018-08-23 | 2011-03-14 | Glasgow City | 695000 | 27 | 0 | 0 | -201.83 | 36.94 | -36.94 | -174.83 | 0 | 694825.17 | 1300 | [6 empty] | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.33%
46387 | Glasgow Strategic Study - Dalmuir Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-14 | 2009-10-14 | 2015-08-10 | 2011-03-14 | Glasgow City | 1923834.76 | 34045.46 | 0 | 0 | 0 | 0 | 0 | 34045.46 | 0 | 1957880.22 | 0 | [6 empty] | EC04C | 33% | EC10E | 33% | EC01D | 34%
46385 | Glasgow Strategic Study - Shieldhall Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-14 | 2009-10-14 | 2015-08-10 | 2011-03-14 | Glasgow City | 2130095 | 61629.08 | 0 | 0 | 0 | 0 | 1.17 | 61630.25 | 0 | 2191725.25 | 0 | [6 empty] | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.33%
401502 | Glasgow Trunk Mains Meter and PRV Installations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-20 | 2011-06-22 | 2011-10-31 | 2014-12-12 |  | Glasgow City | 2155205 | 2004 | 35456.61 | 52176.37 | 8054.96 | 0 | 0 | 97691.94 | 0 | 2252896.94 | 0 | [6 empty] | CM_WSI | 100%
402244 | Glasgow Trunk Mains Rehab - C4 and M2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-05 | 2012-04-24 | 2012-05-21 | 2015-05-25 |  | Glasgow City | 1577382 | -41130 | -8956.61 | 5461.71 | -124.78 | 0 | 0 | -44749.68 | 0 | 1532632.32 | 0 | [6 empty] | CM_WSI | 100%
46868 | Glassford WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-07 | 2011-09-28 | 2011-10-24 | 2012-04-04 | 2012-12-24 | South Lanarkshire | 1886130 | 120870 | -3999.51 | 42193.9 | 0 | 0 | 0.2 | 159064.59 | 0 | 2045194.59 | 0 | [6 empty] | DW3C | 100%
503474 | Glebe Tunnel - Structural Survey | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | GW1 | 2021-04-23 | 2022-04-01 | 2022-06-09 | 2023-01-11 | 2023-04-13 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 23582.04 | 23582.04 | 698326.95 | 721908.99 | 0 | [6 empty] | CM_WSI | 4.762% | CM_M&G | 95.24%
402965 | Glen Road Shotts | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2014-04-23 | 2014-04-23 | 2014-04-23 | 2015-06-16 | North Lanarkshire | 24435.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24435.1 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503605 | Glenbervie Place - Sewer Replacement & Lining | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2019-07-26 | 2021-02-22 | 2021-05-03 | 2022-01-07 | 2022-03-02 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 30279.53 | 44688.8 | 74968.33 | 385031.67 | 460000 | 0 | [6 empty] | CM_WWI | 100%
502551 | Glencaple ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-12-18 | 2021-04-01 | 2021-08-03 | 2022-02-28 | 2022-05-31 | Dumfries and Galloway | 0 | 0 | 31033.94 | 50651.09 | 17753.07 | 68924.08 | 90053.83 | 258416.01 | 901583.97 | 1159999.98 | 136478.56 | [6 empty] | SG1 | 100%
503989 | Glenconvinth Sample tap DSR 1993 NH505376-WN | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-11-27 | 2020-08-03 | 2020-10-14 | 2020-11-11 | Highland | 0 | 0 | 0 | 0 | 0 | 3000 | 22553.51 | 25553.51 | 0 | 25553.51 | 0 | [6 empty] | CM_WSNI | 100%
501230 | Glenconvinth WOA CM SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2017-01-31 | 2017-01-31 | Highland | 0 | 0 | 17.75 | 0 | 0 | 0 | 0 | 17.75 | 0 | 17.75 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
501547 | Glenconvinth WOA- Kirtarlity 6 inch Main Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-01-26 | 2016-09-26 | 2016-11-28 | 2017-08-17 | 2017-08-17 | Highland | 0 | 13716 | 65778.53 | 122665.06 | 9805.03 | -287.96 | 0 | 211676.66 | 0 | 211676.66 | 0 | [6 empty] | CM_WSI | 100%
502571 | Glenconvinth WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 20930.23 | 671.68 | 1536.09 | -20633.2 | 0 | 2504.8 | 0 | 2504.8 | 136478.56 | [6 empty] | WG1 | 100%
401312 | Glencorse - Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-11-29 | 2014-01-24 | 2015-03-31 | 2015-03-30 | Midlothian | 948556 | 0 | -7600.43 | 0 | 0 | 0 | 0 | -7600.43 | 0 | 940955.57 | 0 | [6 empty] | CM_WSI | 100%
31851 | Glencorse New WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2005-10-03 | 2008-07-31 | 2008-08-12 | 2012-02-10 | 2012-02-17 | Midlothian | 103900000 | 397722.57 | 1076650.43 | 1301070.77 | 952174.72 | 622570.95 | -49999.44 | 4300190 | 0 | 108200190 | 0 | [6 empty] | WSNI | 1.754% | WG1 | 4.618% | DW3G | 8.071% | DW4A | 8.071% | DW3J | 13.32% | DW13 | 21.39% | DW3A | 21.39% | DW3B | 21.39%
403324 | Glencorse WOA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-01 | 2014-08-20 | 2014-08-13 | 2014-08-14 |  | Midlothian | 79943.79 | 116 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 80059.79 | 0 | [6 empty] | CM_WSI | 100%
501236 | Glencorse WOA East Craigs-N. Corstorphine WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | City of Edinburgh | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 41.59 | 0 | 41.59 | 0 | [6 empty] | CM_WSI | 100%
500025 | Glencorse WOA Hillend Low WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-13 | 2016-09-23 | 2017-10-30 | 2018-09-18 | 2018-09-18 | City of Edinburgh | 0 | 59791 | 145842 | 590442 | 134757.78 | 4825.04 | 0 | 935657.82 | 0 | 935657.82 | 0 | [6 empty] | CM_WSI | 100%
501139 | Glencorse WOA Hutchison WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501235 | Glencorse WOA Marchbank Torduff WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | City of Edinburgh | 0 | 14734.88 | -14734.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500024 | Glencorse WOA Morningside-Grange WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-03-05 | 2016-10-21 | 2017-08-28 | 2019-02-28 | 2019-02-28 | City of Edinburgh | 0 | 31419 | 126405 | 848301.55 | 341694.64 | 4469.17 | 0 | 1352289.36 | 0 | 1352289.36 | 0 | [6 empty] | CM_WSI | 100%
501126 | Glencorse WOA Murrayfield-Ravelston WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2028-03-31 | 2028-05-10 | 2029-02-08 | 2029-05-11 | City of Edinburgh | 0 | 22032 | 2800 | 1000 | 6524.5 | 493.17 | 1288.49 | 34138.16 | 400610.59 | 434748.75 | 0 | [6 empty] | CM_WSI | 100%
501127 | Glencorse WOA North East Edinburgh WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501128 | Glencorse WOA Old Town-Canongate WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-11 | 2021-08-02 | 2021-08-24 | 2022-10-28 | 2023-02-13 | City of Edinburgh | 0 | 0 | 31526 | 102465 | 13145.02 | 138.05 | 489.26 | 147763.33 | 961821.17 | 1109584.5 | 0 | [6 empty] | CM_WSI | 100%
505008 | Glencorse WTW Air Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-03-27 |  | 2020-08-28 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 8280 | 37720 | 46000 | 0 | 46000 | 0 | [6 empty] | CM_WSNI | 100%
502776 | Glencraig Rising Main Lochgelly | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2018-05-30 | 2019-03-13 | 2019-06-17 | 2019-09-18 | 2019-09-18 | Fife | 0 | 0 | 0 | 27998.66 | 62276.34 | 39800.46 | -0.28 | 130075.18 | 1009.82 | 131085 | 0 | [6 empty] | CM_WWI | 100%
502621 | Glendale WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2024-05-01 | 2025-11-28 | 2026-01-29 | 2027-01-28 | 2027-04-30 | Highland | 0 | 0 | 20930.23 | 499.08 | 2351.08 | 4324.28 | -22086.07 | 6018.6 | 0 | 6018.6 | 136478.56 | [6 empty] | WG1 | 100%
45328 | Glendale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-23 | 2011-06-06 | 2011-12-12 | 2012-02-06 | Highland | 43143.52 | 27.72 | 0 | 0 | 0 | 0 | 0 | 27.72 | 0 | 43171.24 | 0 | [6 empty] | DW13 | 100%
502730 | Glendessary Street Caol Sewer Cross Connections | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2018-05-30 | 2019-01-31 | 2019-02-18 | 2019-07-08 | 2019-07-08 | Highland | 0 | 0 | 0 | 12917.31 | 32651.53 | 71580.67 | 207.1 | 117356.61 | 0 | 117356.61 | 0 | [6 empty] | CM_WWI | 100%
403018 | Glendevon & Glenfarg WTW Sludge Presses Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-10-26 | 2013-03-28 | 2013-08-26 | 2014-04-28 |  | Fife | 784363 | -3490.66 | 288.24 | 0 | 0 | 0 | 0 | -3202.42 | 0 | 781160.58 | 0 | [6 empty] | CM_WSNI | 100%
500861 | Glendevon _ Glenfarg RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-11-04 | 2018-09-05 | 2018-11-29 | 2019-06-30 | 2020-06-30 | Fife | 0 | 15428 | -3169.22 | 19000 | 146248.24 | 85072.28 | -4936.98 | 257642.32 | 0 | 257642.32 | 508161.63 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 94.58
46345 | Glendevon Raw Water System - Cap Maint | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-05-07 | 2012-09-28 | 2012-11-21 | 2014-03-28 |  | Fife | 620245 | 2526 | -2959.85 | 0 | 0 | 0 | -2526 | -2959.85 | 0 | 617285.15 | 0 | [6 empty] | CM_WSI | 100%
501035 | Glendevon WOA Craigbeath WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-04 | 2022-03-14 | 2022-04-11 | 2023-03-13 | 2023-05-22 | Perth and Kinross | 0 | 16995.35 | 9411.71 | 174592.94 | 9084.79 | 6624.91 | -1236.55 | 215473.15 | 1646243.86 | 1861717.01 | 0 | [6 empty] | CM_WSI | 100%
501036 | Glendevon WOA Ferryhills WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501034 | Glendevon WOA Fordell WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501031 | Glendevon WOA Glassiebarns WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 59.3 | -59.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501032 | Glendevon WOA Gowerfield WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501033 | Glendevon WOA Hoodshill WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501030 | Glendevon WOA Limekilns WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501024 | Glendevon WOA Lochgelly South Street WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501025 | Glendevon WOA Lochgelly Spion Kop WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501026 | Glendevon WOA Redcraigs WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501065 | Glendevon WOA Torbain WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501023 | Glendevon WOA Townhill WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
503503 | Glendevon WOA-WI-Longannet 15inch Inlet Main - Burst frequency | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | GW2 | 2021-05-03 | 2022-03-28 | 2022-06-27 | 2023-01-27 | 2023-05-01 | Fife | 0 | 0 | 0 | 0 | 0 | 1040.23 | 18353.01 | 19393.24 | 1312012.69 | 1331405.93 | 0 | [6 empty] | CM_M&G | 100%
501298 | Glendevon WTW - Alterations to Lime Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-03-28 | 2018-06-28 | 2018-10-23 | 2020-01-31 | 2020-04-01 | Fife | 0 | 3827.64 | 16582.25 | 5034.09 | 189797.26 | 387025.24 | 5590.2 | 607856.68 | 2305.75 | 610162.43 | 0 | [6 empty] | CM_WSNI | 100%
501600 | Glendevon WTW - Quality (Reduce high Production risks in DWSP) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2017-03-21 | 2020-08-31 | 2021-01-18 | 2021-06-17 | 2021-09-20 | Fife | 0 | 0 | 72050.45 | 5656.77 | 535.47 | 40755.53 | 127658.2 | 246656.42 | 163081.58 | 409738 | 1221777.68 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501226 | Glendevon WTW - Quality (Reduce Transmission risks in DWSP) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS5 | 2017-03-15 | 2018-03-30 | 2018-07-19 | 2019-09-30 | 2020-03-31 | Fife | 0 | 2511.63 | 16007.42 | 182563.29 | 684566.82 | 402429.04 | 7000 | 1295078.2 | 20932.8 | 1316011 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
402211 | Glendevon WTW Filter No6 Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-20 | 2013-04-12 | 2013-09-12 | 2014-03-10 |  | Fife | 423456.31 | 6.69 | -2112.11 | 0 | 0 | 0 | 2105.42 | 0 | 0 | 423456.31 | 0 | [6 empty] | CM_WSNI | 100%
500242 | Glendevon-Glenfarg-Kinnesswood- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-20 | 2017-03-30 | 2017-06-27 | 2019-02-28 | 2019-09-30 | Fife | 0 | 4244 | 21380 | 151683.37 | 255944.63 | 61494.55 | -1612.75 | 493133.8 | 0 | 493133.8 | 340094.05 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-02
500918 | Glendye - Belts of Collonach & Woodlands TM Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-09-07 | 2017-09-29 | 2017-10-02 | 2021-01-27 | 2021-04-29 | Aberdeenshire | 0 | 11620 | 94891 | 438137 | 59266.65 | 75597.96 | 1044309.14 | 1723821.75 | 174218 | 1898039.75 | 0 | [6 empty] | CM_WSI | 100%
500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-31 | Aberdeenshire | 0 | 4285 | -1476.16 | 79399.59 | 713762.33 | 175793.45 | -160.05 | 971604.16 | 0 | 971604.16 | 1616482.73 | [6 empty] | DW5 | 100%
500886 | Glendye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-06-01 | 2017-12-20 | 2018-03-20 | 2019-03-31 | 2020-02-29 | Aberdeenshire | 0 | 2426.79 | 2573.21 | 14086.92 | 17056.43 | 27062.19 | 0 | 63205.54 | 0 | 63205.54 | 113115.57 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 20.21
500037 | Glendye to Sunnyside Trunk Main Network Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-01 | 2028-02-07 | 2028-05-03 | 2029-01-24 | 2029-01-24 | Aberdeenshire | 0 | 10650 | 0 | 267.79 | 435.03 | 10971 | 0 | 22323.82 | 2417096.18 | 2439420 | 0 | [6 empty] | CM_WSI | 100%
46255 | Glenfarg Reservoir - Spillway and valve repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-22 | 2010-06-28 | 2010-10-25 | 2011-07-28 | 2011-07-28 | Fife | 132219.21 | -1.8 | 0 | 0 | 0 | 0 | 1 | -0.8 | 0 | 132218.41 | 0 | [6 empty] | CM_WSI | 100%
501063 | Glenfarg WOA Kinghorn WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2027-11-02 | 2027-12-27 | 2028-06-13 | 2028-09-13 | Fife | 0 | 22464 | 16972 | 0 | -4495 | -629.17 | 35786.94 | 70098.77 | 527439.28 | 597538.05 | 0 | [6 empty] | CM_WSI | 100%
500974 | Glenfarg WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-09-17 | 2015-09-17 | 2015-11-26 | 2018-02-19 | 2018-02-19 | Fife | 0 | 53357 | 851167.44 | 361386.6 | 35853.14 | 953.88 | 485.79 | 1303203.85 | 14.28 | 1303218.13 | 0 | [6 empty] | CM_WSNI | 100%
501221 | Glenfarg WTW - Quality (Reduction of risks identified in Drinking Water Safety Plan - Distribution) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-11-17 | 2015-11-17 | 2016-02-01 | 2018-11-30 | 2019-06-30 | Fife | 0 | 615.71 | 2360.05 | 8116.15 | 13935.94 | 1972.15 | 0 | 27000 | 0 | 27000 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
503570 | Glenfarg WTW - RGF Media Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2020-12-23 | 2020-12-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 329177.54 | 137985.26 | 467162.8 | 43837.12 | 510999.92 | 0 | [6 empty] | CM_WSNI | 100%
502128 | Glenfarg WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS4 | 2020-04-01 | 2020-04-08 | 2020-04-08 | 2020-03-10 | 2020-04-08 | Perth and Kinross | 0 | 0 | 23851.73 | 7666.01 | 7527.14 | 1616.08 | 0 | 40660.96 | 0 | 40660.96 | 136478.56 | [6 empty] | SG1 | 100%
30308 | Glenfinnan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-31 | 2011-08-29 | 2013-02-07 | 2013-02-21 | Highland | 1276327.51 | -1350.11 | 0 | 0 | 0 | 0 | 0 | -1350.11 | 0 | 1274977.4 | 0 | [6 empty] | DW23 | 100%
503427 | Glengap Lochinvar and Boreholes WRZ - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-06-11 | 2021-04-26 | 2021-07-26 | 2022-02-18 | 2022-05-23 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 196683.75 | 196683.75 | 328316.28 | 525000.03 | 0 | [6 empty] | SG1 | 100%
300034 | Glengap WFD Compliance - Loch Whinyeon Compensation Structure | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-04-23 | 2012-12-17 | 2013-02-18 | 2014-06-25 | 2011-03-14 | Dumfries and Galloway | 157181.84 | 121.45 | 213 | 0 | 0 | 0 | 54.8 | 389.25 | 0 | 157571.09 | 200 | [6 empty] | DW7 | 100%
501213 | Glengap WTW - Improving WQ in Network (OMG5) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-28 | 2016-03-04 | 2016-03-07 | 2016-03-31 | 2016-08-31 | Dumfries and Galloway | 0 | 3079 | -2656.86 | 0 | 0 | 0 | 0 | 422.14 | 0 | 422.14 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
500897 | Glenhead - Braeface Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-10-30 | 2023-08-25 | 2023-09-25 | 2024-02-29 | 2025-02-10 | Falkirk | 0 | 10709 | 77549.04 | 113553.01 | 77712.74 | 0 | 0 | 279523.79 | 1358939.17 | 1638462.96 | 0 | [6 empty] | CM_WSI | 100%
46254 | Glenlatterach Reservoir - Spillway Channel | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-22 | 2010-06-28 | 2010-11-09 | 2011-05-23 | 2011-05-23 | Moray | 118092.06 | 51 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 118143.06 | 0 | [6 empty] | CM_WSI | 100%
401080 | Glenlatterach WSZ Low Pressure Enhancement WSZ000718 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-06-21 | 2012-06-13 | 2012-07-19 | 2014-01-16 | 2014-01-31 | Moray | 106158.78 | 1579.22 | -1361.79 | 0 | 0 | 0 | 0 | 217.43 | 0 | 106376.21 | 1512 | [6 empty] | CS1 | 100%
500917 | Glenlatterach WTW - SCADA-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-10-30 | 2016-09-23 | 2016-11-28 | 2018-04-06 | 2018-04-06 | Aberdeenshire | 0 | 59148 | 746516.61 | 657914.09 | -4990.56 | 21.53 | -0.01 | 1458609.66 | 0 | 1458609.66 | 0 | [6 empty] | CM_WSNI | 100%
503589 | Glenlatterach WTW - Sewer Connection Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2020-05-19 | 2020-06-22 | 2020-08-24 | 2020-10-29 | 2020-10-29 | Moray | 0 | 0 | 0 | 0 | 0 | 28410.06 | 537486.31 | 565896.37 | 0 | 565896.37 | 0 | [6 empty] | CM_WWI | 100%
504767 | GLENLATTERACH WTW Commissioning of Sodium Hypochlorite Dosing Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-04-17 | 2020-05-11 | 2020-10-16 | 2022-05-05 | 2022-08-05 | - | 0 | 0 | 0 | 0 | 0 | 1525.11 | 372121.31 | 373646.42 | 0 | 373646.42 | 0 | [6 empty] | CM_WSNI | 100%
501217 | Glenlatterach WTW Manganese Removal | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-03-29 | 2018-03-01 | 2018-03-27 | 2021-02-28 | 2022-04-30 | Aberdeenshire | 0 | 97779.24 | 503715.93 | 1031731.15 | 789985.27 | 3800709.41 | 2619081.66 | 8843002.66 | 620793.34 | 9463796 | 4812692.83 |  |  |  |  | 79349 |  | DW25P | 1.275% | DW3G | 6.225% | CM_WSNI | 25% | DW3C | 67.5% | bar: Regulatory Outputs OMG-01
45598 | Glenlatterach WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-10-03 | 2014-03-21 | 2014-03-21 | Moray | 926687.37 | 3870.13 | -1265.25 | 0 | 0 | 0 | 60.53 | 2665.41 | 0 | 929352.78 | 7469.87 |  |  |  |  | 30204 |  | CM_WSNI | 30% | DW1A | 70%
403831 | Glenloin Crescent (Succoth) ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-02-28 | 2021-05-28 | 2021-09-24 | 2022-01-27 | 2022-04-29 | Argyll and Bute-Cowal & Bute | 4283.7 | 5779.93 | 2685.27 | 247.81 | 11924.41 | 15652.16 | 81052.98 | 117342.56 | 548553.75 | 670180.01 | 136478.56 | [6 empty] | SG1 | 100%
501668 | Glenochar to Gair trunk main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-11-01 | 2017-11-01 | 2017-11-01 | 2017-11-01 | 2017-11-01 | South Lanarkshire | 0 | 0 | 4899.67 | 1915.04 | 0 | 0 | 0 | 6814.71 | 0 | 6814.71 | 0 | [6 empty] | CM_WSI | 100%
500935 | Glensburgh Submarine PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-09-07 | 2018-03-29 | 2018-05-31 | 2018-11-30 | 2018-11-30 | All West Unitary Authorities | 0 | 45520 | 55883 | 140910 | 441142 | 2912 | 2400 | 688767 | 0 | 688767 | 0 | [6 empty] | CM_WWNI | 100%
501502 | GLENTROOL WWTW NX357781 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-10-03 | 2028-05-12 | 2028-09-08 | 2029-05-02 | 2029-08-02 | Dumfries and Galloway | 0 | 0 | 6130.29 | 41.59 | 0 | 0 | 5016.68 | 11188.56 | 353753.48 | 364942.04 | 0 | [6 empty] | CM_WWNI | 100%
502352 | Golspie WTW Sludge Removal & Lagoon modifications | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS6 | 2016-11-07 | 2018-01-29 | 2018-03-23 | 2018-12-31 | 2019-01-31 | Highland | 0 | 0 | 6342.76 | 54845.1 | 173810.65 | 0 | 0 | 234998.51 | 0 | 234998.51 | 1024271.42 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
503134 | Gorbals High Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-07-21 | 2021-11-08 | 2022-03-07 | 2022-10-17 | 2023-01-17 | East Renfrewshire | 0 | 0 | 0 | 0 | 42082.73 | 32233.74 | 15075.86 | 89392.33 | 219788.2 | 309180.53 | 0 | [6 empty] | CM_WSNI | 100%
45517 | Gorbals Pollocktown TWP Refurb - TWP000109 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-19 | 2011-12-23 | 2011-12-19 |  | East Renfrewshire | 167067.99 | 688.99 | 0 | 0 | 0 | 0 | 0 | 688.99 | 0 | 167756.98 | 0 | [6 empty] | CM_WSNI | 100%
502712 | Gorbals Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-01-21 | 2019-01-21 | East Renfrewshire | 0 | 0 | 0 | 17241.43 | 979.38 | 0 | 0 | 18220.81 | 0 | 18220.81 | 0 | [6 empty] | CM_WSI | 100%
500251 | Gorbals SR & Thornliebank WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | WWINF | Water Non infrastructure | MS3 | 2015-06-08 | 2017-03-31 | 2017-03-31 | 2020-09-28 | 2020-11-27 | East Renfrewshire | 0 | 22000 | 456411 | 740557.02 | 2687.98 | 0 | 0 | 1221656 | 0 | 1221656 | 0 | [6 empty] | CM_WSNI | 100%
502825 | Gorebridge WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-18 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Midlothian | 0 | 0 | 0 | 61544.66 | 9720.66 | 80401.09 | -3906.96 | 147759.45 | 1852240.55 | 2000000 | 136478.56 | [6 empty] | SG1 | 100%
504492 | Gorebridge WWTW (South) Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-04 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWNI | 100%
504606 | Gorthlec Mains rehab | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-14 | 2020-08-07 | 2020-09-17 | 2020-10-15 | Highland | 0 | 0 | 0 | 0 | 0 | 5623.47 | 24376.52 | 29999.99 | 0 | 29999.99 | 0 | [6 empty] | CM_WSNI | 100%
403576 | Gourdie WSZ000731 Low Pressure Enhancement | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-09-25 | 2014-02-04 | 2014-02-10 | 2014-07-17 | 2014-03-26 | Angus | 86889 | 0 | -5939.27 | 0 | 0 | 0 | 0 | -5939.27 | 0 | 80949.73 | 3814 | [6 empty] | CS1 | 100%
45332 | Govig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 71484.17 | 1517.95 | 0 | 0 | 0 | 0 | 0 | 1517.95 | 0 | 73002.12 | 0 | [6 empty] | DW13 | 100%
402480 | Grangemouth Integrated Catchment Study (Dalderse Kinneil Kerse and BoNess Sewer Catchment Areas) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-01-30 | 2013-01-30 | 2015-03-26 | 2015-04-01 | Scottish Water Wide | 1350922 | 396328.45 | 32046.68 | 0 | 0 | 0 | 879 | 429254.13 | 0 | 1780176.13 | 100062 | [6 empty] | CS16S | 100%
506044 | Grangemouth Rising Main to Kinneil Kerse Burst | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-04-03 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WWI | 100%
504175 | Grangepans WWPS - Major Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-12-05 |  | 2020-08-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5771.03 | 44228.97 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WWNI | 100%
501265 | Greengairs STW Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-10 | 2017-10-24 | 2018-01-08 | 2018-05-24 | 2018-05-24 | South Lanarkshire | 0 | 3595 | 76405 | 221039 | 36680 | 781 | 0 | 338500 | 0 | 338500 | 0 | [6 empty] | CM_WWI | 100%
30316 | Greengairs STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-09-20 | 2011-02-01 | 2012-03-16 | 2012-03-26 | North Lanarkshire | 1400389.36 | 150.28 | 0 | 0 | 0 | 0 | 0 | 150.28 | 0 | 1400539.64 | 0 | [6 empty] | EC10A | 46.21% | CM_WWNI | 53.79%
501113 | Greenholm Street Cumnock Stabilise River Bank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-10-21 | 2018-07-31 | 2018-08-28 | 2018-11-29 | 2018-11-29 | East Ayrshire | 0 | 11290 | 8843 | 142631 | 430250 | 3231.07 | -0.07 | 596245 | 0 | 596245 | 0 | [6 empty] | CM_WWI | 100%
503226 | Greenlaw WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-11 | 2030-06-06 | 2030-09-06 | Scottish Borders | 0 | 0 | 0 | 0 | 83505.79 | 3715.09 | 0 | 87220.88 | 54779.13 | 142000.01 | 136478.56 | [6 empty] | SG1 | 100%
501671 | Greenock No.8-Oveton Basin (FRMA (EN)) | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS4 | 2018-07-12 | 2019-06-17 | 2019-08-12 | 2020-02-27 | 2020-04-01 | Inverclyde | 0 | 0 | 0 | 6782.14 | 24976.65 | 278922.6 | 0 | 310681.39 | 0 | 310681.39 | 980126.37 | [6 empty] | WR6 | 100%
502903 | Greenock RSZ - DW5 Intervention - Phase1 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2017-09-27 | 2018-04-30 | 2018-04-30 | 2019-09-30 | 2020-07-31 | Inverclyde | 0 | 0 | 0 | 82141 | 461826.18 | 36275.6 | -1655.85 | 578586.93 | 0 | 578586.93 | 1099483.85 | [6 empty] | DW5FS | 18.88% | DW5MR | 81.12% | bar: Regulatory Outputs OMG-02
502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-02-05 | 2020-06-30 | Inverclyde | 0 | 0 | 46297 | 236920.4 | 63744.91 | 446772.57 | 31312.16 | 825047.04 | 0 | 825047.04 | 3810169.77 | [6 empty] | DW5MR | 100%
501574 | Greenock WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2017-03-31 | 2019-06-27 | 2019-06-27 | 2020-07-07 | 2020-10-07 | Inverclyde | 0 | 5847 | 10278.37 | 728.35 | 907.45 | -692.08 | -48.72 | 17020.37 | 0 | 17020.37 | 249310.15 | [6 empty] | DW25T | 100%
500660 | Greenock WTW Ortho | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-10-30 | 2017-05-16 | 2017-07-12 | 2018-12-11 | 2018-12-12 | Renfrewshire | 0 | 29246 | 125279.79 | 791345.19 | 611519.92 | 9322.28 | 0 | 1566713.18 | 27667.73 | 1594380.91 | 0 | [6 empty] | CM_WSNI | 100%
503533 | Greenock WTW Sludge Press & Conveyor Refurbishment-Replacement H&S Escalation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-06-30 | 2021-10-25 | 2022-01-27 | 2022-09-07 | 2022-12-08 | Inverclyde | 0 | 0 | 0 | 0 | 10567.03 | 12324.3 | 38908.67 | 61800 | 438199.95 | 499999.95 | 0 | [6 empty] | CM_WSNI | 100%
502972 | Greenock WTW Sludge Presses & Conveyor Refurbishment-Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-06-30 | 2021-10-11 | 2022-02-08 | 2022-09-20 | 2022-12-21 | Inverclyde | 0 | 0 | 0 | 16358.8 | 5717.55 | 14320.12 | 62371.54 | 98768.01 | 201232.05 | 300000.06 | 0 | [6 empty] | CM_WSNI | 100%
401346 | Greentoft WSZ Low Pressure Enhancement WSZ000751 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-12-12 | 2013-01-21 | 2013-03-01 | 2013-03-15 | Orkney Islands | 15500 | -561.65 | 0 | 0 | 0 | 0 | 0 | -561.65 | 0 | 14938.35 | 0 | [6 empty] | CS1 | 100%
45798 | Gregory Place Lossie SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2013-01-23 | 2013-01-23 | 2013-01-23 | 2013-01-23 | Scottish Water Wide | 17007.91 | 3891.32 | 0 | 0 | 0 | 0 | 0 | 3891.32 | 0 | 20899.23 | 0 | [6 empty] | WQ01C | 100%
500203 | Gremista WWPS 1995 HU463429 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-03-24 | 2017-03-30 | 2017-06-07 | 2018-10-18 | 2018-10-18 | Shetland Islands | 0 | 88503 | 114368 | 774720 | 97892 | 791 | 0 | 1076274 | 0 | 1076274 | 0 | [6 empty] | CM_WWNI | 100%
500136 | Gretna DOA (DOA000114) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-12-11 | 2019-03-29 | Dumfries and Galloway | 0 | 24619 | 15708.33 | 67359 | 28500 | -8870.29 | 0.01 | 127316.05 | 0 | 127316.05 | 92592.63 | [6 empty] | EC01G | 3.011% | CS16D | 30.24% | EC01D | 33.38% | EC10E | 33.38%
400674 | Gretna Water Supply - Phase 1 Intervention | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-01-21 | 2009-10-30 | 2009-10-30 | 2011-06-29 | 2013-06-26 | Dumfries and Galloway | 830627.5 | -1223.88 | 0 | 0 | 0 | 0 | 2.74 | -1221.14 | 0 | 829406.36 | 470181.23 | [6 empty] | CS1 | 15.35% | WG5 | 84.65%
503455 | Gretna WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-05-06 | 2023-01-11 | 2023-05-16 | 2024-08-19 | 2024-11-19 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 59441.86 | 17391.48 | 66369.68 | 143203.02 | 1856796.97 | 1999999.99 | 136478.56 | [6 empty] | SG1 | 100%
502548 | Ground Mics and Correlators - FOP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-10-06 | 2017-10-06 | Scottish Water Wide | 0 | 0 | 93660 | 3752.29 | 0 | 0 | 0 | 97412.29 | 0 | 97412.29 | 0 | [6 empty] | CM_M&G | 100%
402625 | Growth costs for Legacy CC projects | Q&S4 | Supporting economic development | RCC |  |  | General |  | SWD | RCC | MS7 | 2012-03-14 | 2013-02-06 | 2013-02-06 | 2015-10-19 | 2016-07-11 | Scottish Water Wide | 3793615.62 | 0 | 411.54 | 0 | 0 | 0 | -459.49 | -47.95 | 0 | 3793567.67 | 0 | [6 empty] | SG2 | 50% | WG2 | 50%
402180 | Gryfe No1 Drainage - Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-21 | 2012-06-18 | 2014-02-24 | 2014-02-24 | North Ayrshire | 124832.25 | 145.32 | 0 | 0 | 0 | 0 | 0 | 145.32 | 0 | 124977.57 | 0 | [6 empty] | CM_WSI | 100%
402181 | Gryfe No2 Remedial Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-12-03 | 2013-07-15 | 2014-10-27 | 2014-10-28 | North Ayrshire | 446170.39 | -1908.8 | 796.86 | 0 | 0 | 0 | 0 | -1111.94 | 0 | 445058.45 | 0 | [6 empty] | CM_WSI | 100%
501651 | GSMS Dalmarnock to Daldowie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2018-02-23 | 2018-03-19 | 2018-11-23 | 2018-11-23 | Glasgow City | 0 | 327.1 | 12345.8 | 23355.34 | 246058.52 | -30051.56 | 0.01 | 252035.21 | 0 | 252035.21 | 0 | [6 empty] | CM_WWI | 100%
501705 | GSMS Dalmuir to Shieldhall Valve Chamber Inspections | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-19 | 2020-07-13 | 2020-09-08 | 2020-12-08 | 2021-01-26 | Glasgow City | 0 | 0 | 2366.16 | 30.82 | 147.87 | 6759.69 | 43022.46 | 52327 | 0 | 52327 | 0 | [6 empty] | CM_WWI | 100%
501706 | GSMS Laighpark to Shieldhall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-11-07 | 2020-08-24 | 2020-09-21 | 2020-11-20 | 2020-11-23 | Renfrewshire | 0 | 0 | 2913.38 | 442.76 | 340.64 | 4248.42 | 44508.07 | 52453.27 | 456.74 | 52910.01 | 0 | [6 empty] | CM_WWI | 100%
403428 | GSS Implementation Support (UIDs & Flooding) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS3 | 2013-03-26 | 2013-03-26 | 2013-04-03 | 2020-08-07 | 2020-08-07 | Glasgow City | 228490.56 | 95158.44 | 95378.7 | 29822 | 51150.31 | 0 | 0 | 271509.45 | 0 | 500000.01 | 156558 | [6 empty] | EC01B | 100%
46416 | GSS Small Miscellaneous Projects Purchases | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2009-07-21 | 2012-12-07 | 2012-12-24 | 2018-06-22 | 2011-03-14 | Glasgow City | 110271.89 | 16340.24 | 0 | 0 | 0 | 0 | 0 | 16340.24 | 0 | 126612.13 | 0 | [6 empty] | EC04C | 0.976% | EC01D | 33.13% | EC10E | 65.89%
503283 | Guardbridge STW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-19 | 2023-10-02 | 2024-02-02 | 2025-01-30 | 2025-05-02 | Fife | 0 | 0 | 0 | 0 | 71970.39 | 67103.55 | 39889.28 | 178963.22 | 1900478.67 | 2079441.89 | 136478.56 | [6 empty] | SG1 | 100%
404091 | Guardbridge Water Mains Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-12-15 | 2016-12-15 | Fife | 0 | 0 | 171778.98 | 0 | 0 | 0 | 0 | 171778.98 | 0 | 171778.98 | 0 | [6 empty] | WG5 | 100%
502711 | Guershader Stornoway Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2017-10-20 | 2018-11-29 | 2019-03-11 | 2019-09-06 | 2019-09-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 19272 | 176055 | 61273 | 0 | 256600 | 400 | 257000 | 0 | [6 empty] | CM_WWI | 100%
402143 | Guildtown WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-27 | 2015-03-23 | 2015-07-13 | 2016-09-27 | 2016-09-27 | Perth and Kinross | 335118 | 1555475 | 249137.56 | 100000 | 8872.35 | 0 | 0.01 | 1913484.92 | 0 | 2248602.92 | 0 | [6 empty] | SG1 | 100%
503064 | Gulberwick SPS - Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-05-13 | 2028-05-31 | 2028-09-25 | 2029-05-14 | 2029-08-14 | Shetland Islands | 0 | 0 | 0 | 31039.13 | 3657.63 | 36197.95 | 3016.58 | 73911.29 | 1783932.4 | 1857843.69 | 0 | [6 empty] | CM_WWNI | 100%
502290 | Gullane WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | East Lothian | 0 | 0 | 36444.74 | 874.75 | 0 | 0 | 0 | 37319.49 | 0 | 37319.49 | 136478.56 | [6 empty] | SG1 | 100%
400920 | GWS000367 - Ancum Loch GWS (North Ronaldsay) - Construct New Borehole | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-19 | 2013-02-26 | 2013-06-24 | 2017-02-16 |  | Orkney Islands | 388207 | 2624 | 40096.64 | 11000 | 0 | -6018.84 | -91.86 | 47609.94 | 0 | 435816.94 | 0 | [6 empty] | CM_WSNI | 100%
502790 | Haddington 15 Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-05-03 | 2028-03-03 | 2028-05-08 | 2028-12-01 | 2029-03-05 | Scottish Borders | 0 | 0 | 0 | 31363.42 | 30636.58 | 110.82 | -110.82 | 62000 | 2997523.02 | 3059523.02 | 0 | [6 empty] | CM_WSI | 100%
500149 | Haddington DOA (DOA000513) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2017-08-31 | 2017-09-30 | East Lothian | 0 | 56880 | 118965 | 36303 | -20580.98 | 0 | 0 | 191567.02 | 0 | 191567.02 | 72047.27 | [6 empty] | CS11 | 50% | CS16D | 50% | bar: Regulatory Outputs OMG-22
502418 | Haddington Strategic Drainage Study | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2017-03-30 | 2017-03-30 | 2018-09-11 | 2018-11-26 | 2018-11-26 | East Lothian | 0 | 0 | 0 | 31532.71 | 0 | 0 | 445881.03 | 477413.74 | 4586.24 | 481999.98 | 136478.56 | [6 empty] | SG1 | 100%
501152 | Haddington STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-03-02 | 2018-09-27 | 2018-11-26 | 2020-04-28 | 2020-07-09 | East Lothian | 0 | 3848.36 | 202439.78 | 172677.93 | 625447.04 | 745191.17 | 112876.37 | 1862480.65 | 883.63 | 1863364.28 | 0 |  |  |  |  | 9690 |  | CM_WWNI | 100%
30321 | Haddington STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-08-08 | 2010-06-28 | 2011-03-03 | 2012-09-27 | 2012-11-23 | East Lothian | 1501900.87 | 1265.43 | 0 | 0 | 0 | 0 | 0 | 1265.43 | 0 | 1503166.3 | 0 | [6 empty] | CM_WWNI | 20% | EC01A | 80%
502956 | Haddington WWTW - Demolish inlet building | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-11-20 | 2017-11-20 | 2017-12-11 | 2018-05-28 | 2018-05-28 | East Lothian | 0 | 0 | 0 | 350476.64 | 95710.36 | -8000 | 0 | 438187 | 0 | 438187 | 0 | [6 empty] | CM_WWI | 100%
403968 | Haddington WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-07-19 | 2018-09-26 | 2018-11-26 | 2020-06-15 | 2020-09-10 | East Lothian | 14875.16 | 14622.85 | 230898.42 | 165329.94 | 669050.65 | 1262901.32 | 122755.23 | 2465558.41 | 30086.26 | 2510519.83 | 0 | [6 empty] | SG1 | 100%
501798 | Haddington WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS2 | 2017-06-29 | 2020-03-31 | 2020-05-25 | 2020-08-04 | 2020-08-05 | East Lothian | 0 | 0 | 1607.44 | 5297.36 | 0 | 15942.2 | 134003.51 | 156850.51 | 236.01 | 157086.52 | 0 | [6 empty] | SR21_WW | 100%
501591 | Halkirk - surface water removal and grade 5 sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2016-05-10 | 2027-07-13 | 2027-09-15 | 2028-02-07 | 2028-05-09 | Highland | 0 | 0 | 27076 | 17694 | 0 | -17334.21 | 17334.21 | 44770 | 40312 | 85082 | 0 | [6 empty] | SR21_WW | 100%
500137 | Halkirk DOA (DOA000726) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-02-26 | 2019-06-27 | Highland | 0 | 10823 | 14030 | 16982 | 52826.84 | 8646.08 | 0.01 | 103307.93 | 0 | 103307.93 | 31970.67 | [6 empty] | EC01G | 15.73% | CS16D | 37.26% | EC01D | 47.01%
32104 | Hamilton STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-10-01 | 2010-08-23 | 2010-09-27 | 2012-02-06 | 2012-03-16 | South Lanarkshire | 3975719.73 | 5339.68 | -5339.68 | 0 | 0 | 0 | 0 | 0 | 0 | 3975719.73 | 0 | [6 empty] | EC01A | 22.39% | CM_WWNI | 77.61%
501164 | Hamilton Upper Muir SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-22 | 2017-09-04 | 2017-12-04 | 2018-09-27 | 2018-09-27 | South Lanarkshire | 0 | 602.52 | 89528.48 | 540862 | 29559.65 | 0.35 | 0 | 660553 | 0 | 660553 | 0 | [6 empty] | CM_WWNI | 100%
502232 | Hamilton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2018-10-31 | 2018-10-31 | 2018-12-17 | 2019-08-28 | 2019-08-28 | South Lanarkshire | 0 | 0 | 21336.24 | 14880.39 | 73042.18 | 245316 | 0 | 354574.81 | 0 | 354574.81 | 136478.56 |  |  |  |  | 54752.69 |  | SG1 | 100%
501635 | Happendon - Camps TM Douglas Water Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-30 | 2017-08-22 | 2017-08-24 | 2021-02-19 | 2021-02-22 | South Lanarkshire | 0 | 3925 | 777237.72 | 430095.63 | 3122667.37 | 3675553.13 | 864329.94 | 8873808.79 | 25766.45 | 8899575.24 | 0 | [6 empty] | CM_WSI | 100%
502275 | Harperleas Reservoir IOS and Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-06-29 | 2019-04-30 | 2019-05-27 | 2019-09-27 | 2019-09-27 | Fife | 0 | 0 | 8571.33 | 2496.77 | 10046.78 | 113713.24 | -0.01 | 134828.11 | 0 | 134828.11 | 0 | [6 empty] | CM_WSI | 100%
46156 | Harthill STW Refurb - STW000361 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2010-11-15 | 2011-01-19 | 2012-03-14 |  | North Lanarkshire | 914721.47 | 3633.3 | -3633.3 | 0 | 0 | 0 | 0 | 0 | 0 | 914721.47 | 0 | [6 empty] | CM_WWNI | 100%
500820 | Hatton - Tay Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-21 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | Dundee City | 0 | 5211.19 | 533.7 | -92.87 | 0 | 0 | 0 | 5652.02 | 0 | 5652.02 | 120964.87 | [6 empty] | CS15A | 100%
403005 | Hatton of Cruden Bridgend Septic Tank - Soakaway | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-29 | 2013-03-28 | 2013-04-24 | 2013-06-13 |  | Aberdeenshire | 40227.43 | -927.36 | 0 | 0 | 0 | 0 | 927.36 | 0 | 0 | 40227.43 | 0 | [6 empty] | CM_WWNI | 100%
500235 | Hatton of Cruden WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS0 | 2019-03-25 | 2020-07-27 | 2020-09-21 | 2021-08-19 | 2021-11-19 | Aberdeenshire | 0 | 63480.51 | 41516.5 | 23116.55 | 23988.71 | 285667.39 | 957927.88 | 1395697.54 | 357862.47 | 1753560.01 | 136478.56 | [6 empty] | SG1 | 100%
502821 | Hatton of Fintray WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | Aberdeenshire | 0 | 0 | 0 | 63695.07 | 120.3 | 0 | -120.3 | 63695.07 | 0 | 63695.07 | 136478.56 | [6 empty] | SG1 | 100%
34798 | Hawick - Alemoor WRZ-WFD Compliance | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-19 | 2011-03-21 | 2011-03-21 | 2011-03-31 | 2011-03-31 | Scottish Borders | 192450 | 7550 | -1747.69 | 0 | 0 | 0 | 1747.69 | 7550 | 0 | 200000 | 0 | [6 empty] | DW7 | 100%
501945 | Hawick Duke Street Syphon | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-06-03 | 2016-08-10 | 2016-08-10 | 2017-02-09 | 2017-05-02 | Scottish Borders | 0 | 0 | 1405606.4 | 419775.19 | -16432.47 | 100.23 | -100.23 | 1808949.12 | 0 | 1808949.12 | 0 | [6 empty] | CM_WWI | 100%
400065 | Hawick STC Refurb000090 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-14 | 2011-05-03 | 2011-08-01 | 2016-12-15 |  | Scottish Borders | 1878109.62 | 101674.99 | -9730.27 | -31.19 | 98.34 | 0 | 0 | 92011.87 | 0 | 1970121.49 | 0 | [6 empty] | CM_WWNI | 100%
30322 | Hawick STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-29 | 2011-05-05 | 2011-08-01 | 2015-11-03 | 2015-05-29 | Scottish Borders | 2352426.24 | 77936.54 | -2507.44 | -431.83 | 0 | 0 | 0 | 74997.27 | 0 | 2427423.51 | 53147.89 | [6 empty] | CM_WWNI | 50% | EC01A | 50%
500950 | Health & Safety - Fitting of Machine Guards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-09-10 | 2015-09-10 | 2015-09-10 | 2018-10-04 | 2018-10-04 | Scottish Water Wide | 0 | 73616.97 | 6781.74 | 62.39 | 0 | 0 | 0 | 80461.1 | 0 | 80461.1 | 0 | [6 empty] | CM_M&G | 100%
403718 | Health and Safety at Reservoirs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-27 | 2014-05-29 | 2014-06-03 | 2016-03-23 | 2016-06-21 | Scottish Water Wide | 2127956 | 82000 | -8500.44 | 1484.97 | 0 | 0 | -249.86 | 74734.67 | 0 | 2202690.67 | 0 | [6 empty] | CM_WSI | 100%
400999 | Heldale Loch RWP Replace Raw Water Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-04-21 | 2012-06-07 | 2013-01-08 | 2013-12-10 |  | Orkney Islands | 331691 | -373.11 | -88.68 | 0 | 0 | 0 | 0 | -461.79 | 0 | 331229.21 | 0 | [6 empty] | CM_WSNI | 100%
403787 | Helensburgh No.1 & 2 IoS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-05-19 | 2015-06-12 | 2015-06-15 | 2015-06-15 | 2015-06-15 | Argyll and Bute-Cowal & Bute | 6220 | -1593.3 | 0 | 0 | 0 | 0 | 601.33 | -991.97 | 0 | 5228.03 | 0 | [6 empty] | CM_WSI | 100%
501167 | Helensburgh WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS1 | 2016-07-20 | 2027-04-15 | 2027-04-15 | 2028-09-14 | 2028-09-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 53942.64 | 312644.74 | -19067.38 | 0 | 0 | 347520 | 2582027.96 | 2929547.96 | 0 | [6 empty] | CM_WWNI | 100%
503932 | Helensburgh WwTW - Replace 2 Washpactor Units | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-12-01 |  | 2020-12-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 100000.02 | 100000.02 | 0 | 100000.02 | 0 | [6 empty] | CM_WWNI | 100%
504972 | Helenton Farm Symington - Scour Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MSU |  | 2020-03-18 |  | 2020-09-17 | 2020-07-31 | - | 0 | 0 | 0 | 0 | 0 | 102946.87 | 116487.22 | 219434.09 | 0 | 219434.09 | 0 | [6 empty] | CM_WSI | 100%
45039 | Heriot WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-28 | 2012-07-09 | 2013-03-28 | 2013-11-21 | Scottish Borders | 933948.27 | -496.53 | 0 | 0 | 0 | 0 | 0 | -496.53 | 0 | 933451.74 | 0 | [6 empty] | DW23 | 100%
504633 | Hermitage Street iron main replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-15 | 2020-08-06 | 2021-04-21 | 2021-04-21 | - | 0 | 0 | 0 | 0 | 0 | 9431.67 | 138853.51 | 148285.18 | 56714.82 | 205000 | 0 | [6 empty] | WSNI | 100%
502361 | Herrick WTW - RGF Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2016-12-20 | 2027-04-01 | Aberdeenshire | 0 | 0 | 40186.05 | 0 | 0 | 0 | 0 | 40186.05 | 0 | 40186.05 | 0 | [6 empty] | CM_WSI | 12.5% | CM_WSNI | 87.5%
501110 | Herricks WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-11-23 | 2029-03-28 | 2030-06-19 | 2030-09-11 | Aberdeenshire | 0 | 23339.61 | 120920.78 | 11583.01 | 41175.22 | 1981.38 | 0 | 199000 | 2999982.09 | 3198982.09 | 0 | [6 empty] | CM_WSNI | 100%
503422 | Herricks WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-10-31 | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Moray | 0 | 0 | 0 | 0 | 39230.01 | 65485.76 | 0.01 | 104715.78 | 0 | 104715.78 | 0 | [6 empty] | CM_WSNI | 100%
501233 | Herricks WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-03-22 | 2020-02-28 | 2020-02-28 | 2020-08-17 | 2020-11-09 | Aberdeenshire | 0 | 2424.81 | 31934.21 | 66689.69 | 71488.29 | 303121 | 942740.09 | 1418398.09 | 5102.91 | 1423501 | 3547.71 | [6 empty] | DW25D | 33% | DW25P | 67%
503590 | High Boxton Pipe and Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-09-30 | 2019-09-30 | 2019-12-11 | 2020-10-29 | 2020-12-22 | Falkirk | 0 | 0 | 0 | 0 | 0 | 217700.82 | 236011.59 | 453712.41 | 2320.99 | 456033.4 | 0 | [6 empty] | CM_WSI | 100%
402993 | High Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-02 | 2013-03-15 | 2013-06-03 | 2013-10-25 | 2013-10-25 | Glasgow City | 52853 | -957.31 | 0 | 0 | 0 | 0 | 0 | -957.31 | 0 | 51895.69 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403436 | High Street Strichen Fraserburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-04-16 | 2014-08-21 | 2014-08-28 | 2014-10-28 | 2014-10-28 | Aberdeenshire | 74956 | -1393.93 | 599.83 | -276.31 | 0 | 0 | 0 | -1070.41 | 0 | 73885.59 | 1863 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402529 | High Voltage Switchgear Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-05-14 | 2012-12-20 | 2013-04-25 | 2014-07-31 |  | All South Unitary Authorities | 549729 | 0 | -25780.55 | 0 | 0 | 0 | 0 | -25780.55 | 0 | 523948.45 | 0 | [6 empty] | CM_WWNI | 100%
500920 | Highland Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2018-02-23 | 2018-02-01 | 2018-02-01 | 2018-02-01 | Highland | 0 | 4904.29 | 1471.49 | -4483.58 | 0 | 0 | 0 | 1892.2 | 0 | 1892.2 | 120964.87 | [6 empty] | CS15A | 100%
503292 | Highland PFI Transition Plan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2018-08-23 | 2021-02-22 | 2021-03-02 | 2022-03-22 | 2022-06-22 | Highland | 0 | 0 | 0 | 0 | 10713.01 | 28011.36 | 37764.53 | 76488.9 | 73511.11 | 150000.01 | 0 | [6 empty] | CM_WWI | 20% | CM_WWNI | 80%
500865 | Hillend RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-09-06 | 2018-09-04 | 2018-11-29 | 2019-09-30 | 2020-01-17 | City of Edinburgh | 0 | 5818.45 | 8144.52 | 36650.36 | 95442.32 | 44550.87 | 4303.82 | 194910.34 | 0 | 194910.34 | 396328.86 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 54.3
501733 | Hillfarm DSR Mainout | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2028-07-31 | 2029-05-16 | 2029-09-19 | 2030-01-29 | 2030-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.97 | 99999.97 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
500937 | Hillfoot SPS RM Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-09-02 | 2017-01-19 | 2017-02-27 | 2017-05-31 | 2017-05-31 | East Dunbartonshire | 0 | 12500 | 104277.85 | 38168.15 | 0 | -2285.74 | 39.74 | 152700 | 0 | 152700 | 0 | [6 empty] | CM_WWI | 100%
45797 | Hillfoot SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-06-13 | 2011-09-19 | 2014-06-09 | 2014-08-06 | East Dunbartonshire | 645407.49 | 248.91 | 0 | 0 | 0 | 0 | 0 | 248.91 | 0 | 645656.4 | 0 | [6 empty] | WQ01C | 100%
503149 | HL - Charley Horse Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-03-31 | 2021-04-26 | 2021-04-28 | 2021-04-29 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0.42 | 208.72 | -72.86 | 0 | 136.28 | 0 | 136.28 | 0 | [6 empty] | CM_WSI | 100%
503145 | HL - Pipebridge Remedial Work Holding Line | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU | 2021-04-02 | 2021-04-05 | 2021-06-25 | 2021-06-25 | 2021-06-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000000.04 | 2000000.04 | 0 | 2000000.04 | 0 | [6 empty] | CM_M&G | 100%
503086 | HL - Property Facilities Statutory Compliance Holding Line | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW1 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | Scottish Water Wide | 0 | 0 | 0 | 2255.01 | -2255.01 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_M&G | 100%
503151 | HL -Development to CX2 Wastewater Holding Line | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2027-04-01 | 2027-04-01 | 2027-04-01 |  | 2027-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 3.64 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | [6 empty] | CM_WWNI | 100%
503152 | HL -Development to CX2 Water Holding Line | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-03-31 | 2021-05-24 | 2021-05-31 |  | 2021-07-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 0 | [6 empty] | CM_WSNI | 100%
403505 | HL SVCW - CMC Reservoir Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-07-18 | 2019-09-03 | 2019-09-03 | Scottish Water Wide | 674967 | 510718 | -21985.32 | 19900.3 | 0 | 0 | 0 | 508632.98 | 0 | 1183599.98 | 0 | [6 empty] | CM_WSI | 100%
403535 | HL SVCW CMC East Inf | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-08-30 | 2016-02-05 |  | All East Unitary Authorities | 133628 | 10515.11 | 0 | 0 | 0 | 0 | 0 | 10515.11 | 0 | 144143.11 | 0 | [6 empty] | CM_WSI | 100%
403536 | HL SVCW CMC East Non Inf | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-07-16 | 2018-11-05 |  | All East Unitary Authorities | 292688 | 196191 | 0.06 | 79.86 | 111.5 | 0 | 0 | 196382.42 | 0 | 489070.42 | 0 | [6 empty] | CM_WSNI | 100%
502304 | Holl Reservoir IOS and Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-04-25 | 2018-04-30 | 2018-06-25 | 2020-11-20 | 2020-11-20 | Fife | 0 | 0 | 15537.25 | 29859.75 | 369319.45 | 48510.81 | 260858 | 724085.26 | 29290 | 753375.26 | 0 | [6 empty] | CM_WSI | 100%
402501 | Home Farm Denny Gravity Sewer Remedial Work | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-01-27 | 2012-12-21 | 2013-03-22 | 2014-04-02 |  | Falkirk | 208639.33 | 171.3 | 0 | 0 | 0 | 0 | 0 | 171.3 | 0 | 208810.63 | 0 | [6 empty] | CM_WWI | 100%
402897 | Hopes Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-20 | 2013-10-30 | 2014-02-11 | 2015-04-14 | 2015-04-14 | Scottish Borders | 188319.19 | 77887.28 | 0 | 0 | 0 | 0 | 0 | 77887.28 | 0 | 266206.47 | 0 | [6 empty] | CM_WSI | 100%
500476 | Hopes WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-24 | 2017-04-24 | 2017-06-07 | 2017-06-30 | 2017-08-31 | East Lothian | 0 | 9164.03 | 14348.14 | 2249.87 | 0 | 0 | 0 | 25762.04 | 0 | 25762.04 | 298015.2 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403485 | Horizons Hydros | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2013-05-07 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 52616 | 59901 | -112517 | 2507.14 | 15448.51 | 0 | -17948.38 | -52608.73 | 0 | 7.27 | 0 | [6 empty] | CC1W | 100%
502970 | Howden GWS - Borehole Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-11-23 | 2029-03-09 | 2030-06-07 | 2030-09-09 | Scottish Borders | 0 | 0 | 0 | 60911.02 | 11046.71 | 71946.9 | 3278.73 | 147183.36 | 1452816.74 | 1600000.1 | 0 | [6 empty] | CM_WSNI | 100%
503266 | Howden WTW Chloramination | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2017-08-29 | 2018-12-20 | 2019-03-20 | 2020-06-01 | 2020-06-01 | Scottish Borders | 0 | 0 | 0 | 0 | 441754.02 | 1084824.98 | 120484 | 1647063 | 15527 | 1662590 | 947737.62 | [6 empty] | DW2 | 100% | bar: Regulatory Outputs OMG-01
400832 | Howden WTW New CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-05-18 | 2012-04-24 | 2012-06-11 | 2016-03-03 |  | Scottish Borders | 1461421.17 | 98345.59 | 6305.52 | 5432.16 | 0 | 0 | 0.01 | 110083.28 | 0 | 1571504.45 | 0 | [6 empty] | CM_WSNI | 100%
500815 | Howes Way Carstairs | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS3 | 2015-08-24 | 2015-09-22 | 2015-09-23 | 2021-01-05 | 2021-02-09 | South Lanarkshire | 0 | 34000 | 37000.44 | 4083.71 | 7147.61 | 12768.24 | 0 | 95000 | 0 | 95000 | 904764.02 | [6 empty] | CS15 | 100%
500217 | Hoy Calder - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | Highland | 0 | 12402 | -8517.05 | 47460.76 | 3651.45 | 0 | -0.16 | 54997 | 0 | 54997 | 1805010.12 | [6 empty] | DW5 | 100%
500862 | Hoy Calder RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-07-21 | 2018-06-27 | 2018-10-03 | 2019-01-31 | 2019-09-30 | Highland | 0 | 39033.81 | 12866.89 | 6598.03 | 126457.75 | 15323.24 | 0 | 200279.72 | 0 | 200279.72 | 2663808.28 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 116.04
501830 | HR - Human Capital Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-02-17 | 2019-03-04 | 2019-03-04 | 2020-05-26 | 2020-05-26 | Scottish Water Wide | 0 | 0 | 69831.63 | 286057.4 | 3303572.17 | 2134347.33 | 1823024.85 | 7616833.38 | 0 | 7616833.38 | 0 |  |  |  |  | 731000 |  | CM_M&G | 100%
402594 | HS Focused Delivery CID WWNI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2017-07-03 |  | All East Unitary Authorities | 1112873 | -52496 | 2089.17 | 7109.53 | 0 | 0 | -12.12 | -43309.42 | 0 | 1069563.58 | 0 | [6 empty] | CM_M&G | 100%
401233 | Human Resources Information System (HRIS) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-10-07 | 2011-08-09 | 2011-08-16 | 2015-07-24 |  | Scottish Water Wide | 4919789 | -14799.73 | 0 | 0 | 0 | 0 | 0 | -14799.73 | 0 | 4904989.27 | 0 | [6 empty] | CM_M&G | 100%
501356 | Humbie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2028-07-12 | 2028-11-15 | 2029-11-08 | 2030-02-08 | West Lothian | 0 | 0 | 0 | 22846.86 | 3012.81 | 1750.44 | 0 | 27610.11 | 572389.89 | 600000 | 0 | [6 empty] | CM_WSNI | 100%
501666 | Hungry Snout | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-04-25 | 2018-09-06 | 2018-09-28 | 2020-04-01 | 2020-04-01 | Scottish Borders | 0 | 0 | 145156.39 | 297675.17 | 1095145.57 | 1196978.87 | 118932 | 2853888 | 9620 | 2863508 | 0 | [6 empty] | CM_WSNI | 100%
500138 | Huntly DOA (DOA000367) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-03-25 | 2019-06-18 | Aberdeenshire | 0 | 28827 | 5635 | 38771.25 | 44456 | 10729.57 | 0 | 128418.82 | 0 | 128418.82 | 148460.38 | [6 empty] | EC01G | 0.298% | CS16D | 31.84% | EC01D | 67.86%
46581 | Huntly STW Refurb - STW001398 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2009-04-28 | 2012-07-10 | 2012-11-26 | 2014-05-06 | 2014-05-06 | Aberdeenshire | 3593953.37 | 105577.13 | -7565.74 | 0 | 0 | 0 | 0 | 98011.39 | 0 | 3691964.76 | 136478.56 | [6 empty] | CM_WWNI | 40% | SG1 | 60%
402777 | Hurlford Irvine Valley Sewer Renewal | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-08-06 | 2013-07-24 | 2013-09-02 | 2014-12-01 |  | East Ayrshire | 1507080 | 0 | -24812.7 | 0 | 0 | 0 | 0 | -24812.7 | 0 | 1482267.3 | 0 | [6 empty] | CM_WWI | 100%
45334 | Hushinish WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 81297.87 | 1482.91 | 0 | 0 | 0 | 0 | 0 | 1482.91 | 0 | 82780.78 | 0 | [6 empty] | DW13 | 100%
502262 | HV Asset Replacement Phase 1 - Albert Rd PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2017-04-28 | 2018-09-13 | 2018-09-14 | 2019-06-12 | 2019-06-12 | City of Edinburgh | 0 | 0 | 2141.96 | 72841.04 | 369885 | 23087.61 | 44.39 | 468000 | 0 | 468000 | 0 | [6 empty] | CM_WWNI | 100%
502263 | HV Asset Replacement Phase 1 - Dalgrain PS | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2021-04-01 | 2022-01-21 | 2022-05-30 | 2023-05-18 | 2023-08-18 | Falkirk | 0 | 0 | 20465 | 50987.75 | 28420.45 | 31706.43 | -1134.02 | 130445.61 | 1369554.37 | 1499999.98 | 0 | [6 empty] | SR21_WW | 100%
502265 | HV Asset Replacement Phase 1 - Gailes PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2017-04-28 | 2019-03-07 | 2019-03-08 | 2020-03-03 | 2020-04-01 | North Ayrshire | 0 | 0 | 6300 | 102632 | 196031 | 754858 | 10243 | 1070064 | 2500 | 1072564 | 0 | [6 empty] | CM_WWNI | 100%
502266 | HV Asset Replacement Phase 1 - Hamilton STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-28 | 2017-06-19 | 2017-06-19 | 2017-06-19 | 2017-06-19 | South Lanarkshire | 0 | 0 | 243.09 | 8.9 | 0 | 0 | 0 | 251.99 | 0 | 251.99 | 0 | [6 empty] | CM_WWNI | 100%
502267 | HV Asset Replacement Phase 1 - Laighpark WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-04-06 | 2019-04-16 | 2019-05-13 | 2020-07-14 | 2020-07-14 | Renfrewshire | 0 | 0 | 28500 | 115138 | 259816 | 1585211.42 | 468424.59 | 2457090.01 | 2400 | 2459490.01 | 0 | [6 empty] | CM_WWNI | 100%
502268 | HV Asset Replacement Phase 1 - Shieldhall WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2017-04-24 | 2019-03-07 | 2019-03-15 | 2020-10-09 | 2021-01-15 | Glasgow City | 0 | 0 | 38873.16 | 227005.74 | 495632.21 | 1121519.57 | 505238.14 | 2388268.82 | 14409.88 | 2402678.7 | 0 | [6 empty] | CM_WWNI | 100%
502269 | HV Asset Replacement Phase 1 - Stevenston Point WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-04-05 | 2019-03-26 | 2019-03-28 | 2020-06-30 | 2020-06-30 | North Ayrshire | 0 | 0 | 11816 | 87054 | 403331 | 1707641.95 | 39484.05 | 2249327 | 2400 | 2251727 | 0 | [6 empty] | CM_WWNI | 100%
501147 | HV Policy Development | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-10-08 | 2015-10-08 | 2016-02-01 | 2020-06-30 | 2020-06-30 | Scottish Water Wide | 0 | 25784 | 16033.35 | 94000 | 0 | 7538.92 | 6643.73 | 150000 | 0 | 150000 | 0 | [6 empty] | CM_WSNI | 38.67% | CM_WWNI | 61.33%
503044 | Hydraulic Modelling Enabling Works | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Wastewater |  | SWMD | DWQ - Preparing for Future Investment | MS3 | 2018-05-17 | 2018-11-27 | 2018-12-10 | 2021-01-14 | 2021-04-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 168393.29 | 149224.34 | 349272.04 | 666889.67 | 83110.33 | 750000 | 1570056.27 | [6 empty] | CS16S | 100%
402453 | Hydro Generation Cluster 1 of 3 - Lomond Schemes | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS5 | 2011-08-30 | 2012-09-28 | 2013-01-29 | 2015-03-24 | 2015-03-24 | Scottish Water Wide | 9067418 | 172663.15 | 61754.85 | 160835 | 155859 | 313836.75 | -468.92 | 864479.83 | 15530.18 | 9947428.01 | 16826 | [6 empty] | CC1W | 100%
402999 | Hydro Generation Cluster 1A (Glendevon & Glencorse) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-28 | 2012-10-31 | 2012-11-30 | 2015-03-30 | 2015-03-30 | Scottish Water Wide | 4434154 | -17058.99 | 15064.99 | 88578 | 7499.13 | 0 | 0 | 94083.13 | 0 | 4528237.13 | 43467 | [6 empty] | CC1W | 100%
402454 | Hydro Generation Cluster 2 of 3 Katrine Catchment | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-30 | 2012-09-28 | 2012-10-25 | 2015-10-08 | 2015-10-08 | Scottish Water Wide | 1280300 | -83872.78 | 1763.15 | 0 | 0 | 0 | -0.37 | -82110 | 0 | 1198190 | 0 | [6 empty] | CC1W | 100%
402455 | Hydro Generation Cluster 3 of 3 South and West Sites | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-30 | 2012-09-28 | 2012-10-25 | 2014-12-18 | 2015-01-30 | Scottish Water Wide | 6749999 | 2493.21 | 81281.79 | 44226 | 25394.11 | 0 | 0 | 153395.11 | 0 | 6903394.11 | 54089 | [6 empty] | CC1W | 100%
402893 | ICAT Improvement Project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MS7 | 2012-08-31 | 2013-01-09 | 2013-02-05 | 2015-02-09 |  | Scottish Water Wide | 375097.32 | -11258.8 | 0 | 0 | 0 | 0 | 11258.8 | 0 | 0 | 375097.32 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
504779 | ICF - Avoch Memorial Field - Strategic Surface Water Removal Project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-03-04 |  |  |  | - | 0 | 0 | 0 | 0 | 0 | 69758.74 | -56663.74 | 13095 | 0 | 13095 | 1830849.77 | [6 empty] | SG5 | 100%
503614 | ICF - Bathgate Alternative Feed - Section bisecting Garden District - Redheughs Village. W | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-07-28 | 2021-08-02 | 2021-09-13 | 2023-04-07 | 2023-05-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 10583.12 | 103257.72 | 113840.84 | 386159.16 | 500000 | 470181.23 | [6 empty] | WG5 | 100%
503704 | ICF - Coatbridge to Daldowie Waste | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-07-01 | 2020-07-13 | 2020-09-22 | 2021-02-11 | 2021-04-06 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 98471.47 | 98471.47 | 5528.51 | 103999.98 | 1830849.77 | [6 empty] | SG5 | 100%
503450 | ICF - Dunbeg Development - Strategic Wastewater Solution | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 | 2019-09-18 | 2019-09-18 | 2020-08-10 | 2021-10-11 | 2022-01-11 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 32710.28 | 455889.25 | 488599.53 | 111400.49 | 600000.02 | 1830849.77 | [6 empty] | SG5 | 100%
503705 | ICF - East Calder - Pumpherston Road NIA0179.D01 - WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-09-02 | 2020-09-07 | 2020-11-18 | 2021-06-25 | 2021-08-18 | West Lothian | 0 | 0 | 0 | 0 | 0 | 27.55 | 412588.3 | 412615.85 | 137384.18 | 550000.03 | 1830849.77 | [6 empty] | SG5 | 100%
503706 | ICF - Ellon - Bridge of Don (Aberdeen) Development Corridor - Balmedie to Blackdog Section. W | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-07-01 | 2020-07-06 | 2020-09-08 | 2021-10-11 | 2021-12-02 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2493672.35 | 2493672.35 | 1006327.68 | 3500000.03 | 470181.23 | [6 empty] | WG5 | 100%
503707 | ICF - Falkirk Strategic NIA Waste Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-09-02 | 2021-07-26 | 2021-07-26 | 2022-07-11 | 2022-10-07 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 688319.33 | 688319.33 | 4211680.69 | 4900000.02 | 1830849.77 | [6 empty] | SG5 | 100%
505032 | ICF - Grandholm Aberdeen - Water Main Installation. | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS0 | 2020-03-23 | 2020-05-25 | 2020-06-01 | 2021-02-09 | 2026-03-03 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140000.01 | 2140000.01 | 470181.23 | [6 empty] | WG5 | 100%
503439 | ICF - Greenlaw - Newton Mearns | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-03-26 | 2019-03-26 | 2019-07-10 | 2020-09-10 | 2020-09-10 | Glasgow City | 0 | 0 | 0 | 0 | 1253928.81 | 81830.8 | 47938.06 | 1383697.67 | 29990.73 | 1413688.4 | 1830849.77 | [6 empty] | SG5 | 100%
503449 | ICF - maidenhill Newton Mearns WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-02-25 | 2019-02-25 | 2019-04-01 | 2020-10-27 | 2020-10-27 | East Renfrewshire | 0 | 0 | 0 | 0 | 1225233.64 | 4921.83 | -2530.78 | 1227624.69 | -2391.02 | 1225233.67 | 1830849.77 | [6 empty] | SG5 | 100%
503522 | ICF - Perth Drainage - 2018 - 2028 development enablement WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-11-19 | 2021-08-23 | 2021-12-06 | 2023-06-30 | 2023-10-02 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 60511.32 | 154845.8 | 215357.12 | 2784642.82 | 2999999.94 | 1830849.77 | [6 empty] | SG5 | 100%
503703 | ICF - Spean Bridge Developments - Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-07-01 | 2020-07-06 | 2020-09-08 | 2021-01-28 | 2021-03-23 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 118174.38 | 118174.38 | 4825.64 | 123000.02 | 470181.23 | [6 empty] | WG5 | 100%
503448 | ICF - St Leonard s Place Dundee - Surface Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-10-29 | 2020-11-16 | 2020-12-30 | 2021-04-05 | 2021-07-06 | Dundee City | 0 | 0 | 0 | 0 | 0 | 27489.52 | 649702.93 | 677192.45 | 141966.57 | 819159.02 | 1830849.77 | [6 empty] | SG5 | 100%
503708 | ICF - Stratton Farm Inverness. Strategic Water Main Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-07-01 | 2020-07-06 | 2020-09-08 | 2021-04-16 | 2021-06-09 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 450538.37 | 450538.37 | 49461.62 | 499999.99 | 470181.23 | [6 empty] | WG5 | 100%
503709 | ICF - West Edinburgh Strategic Approach - WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-07-01 | 2021-09-06 | 2021-11-16 | 2023-01-23 | 2023-03-16 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 43.06 | 230956.94 | 231000 | 6769000.04 | 7000000.04 | 1830849.77 | [6 empty] | SG5 | 100%
503710 | ICF - Winchburgh Village Development - Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-01-03 | 2020-01-06 | 2020-03-11 | 2020-12-15 | 2021-02-11 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1318514.8 | 1318514.8 | 37038.2 | 1355553 | 470181.23 | [6 empty] | WG5 | 100%
503456 | ICF- Aberdeen - Nigg Harbour Development -Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS0 | 2019-08-01 | 2020-12-07 | 2021-01-22 | 2021-08-19 | 2021-11-04 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3271.03 | 286985.65 | 290256.68 | 209743.35 | 500000.03 | 470181.23 | [6 empty] | WG5 | 100%
503549 | ICF-Armadale 12inch Trunk Main Replacement - Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2019-04-11 | 2019-04-11 | 2019-09-23 | 2021-09-03 | 2021-09-03 | West Lothian | 0 | 0 | 0 | 0 | 0 | 857047.3 | -33337.59 | 823709.71 | -73709.72 | 749999.99 | 470181.23 | [6 empty] | WG5 | 100%
503451 | ICF-NGIWMS Glasgow -WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-07-06 | 2020-07-13 | 2020-09-28 | 2023-09-21 | 2023-12-22 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500000 | 5500000 | 1830849.77 | [6 empty] | SG5 | 100%
504271 | ICF-Winchburgh Village Development | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-02-11 |  |  |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 781418.02 | 918581.98 | 1700000 | 0 | 1700000 | 0 | [6 empty] | SG5 | 100%
500675 | Identity and Access Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-05 | 2017-01-31 | 2017-01-31 | 2018-04-15 |  | Scottish Water Wide | 0 | 237418 | 1113994.05 | 145800.67 | 11566.97 | 0 | -4645.5 | 1504134.19 | 0 | 1504134.19 | 0 | [6 empty] | CM_M&G | 100%
500262 | IDP - Wastewater Infra Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2017-05-26 | 2017-05-26 | All East Unitary Authorities | 0 | 6404.59 | -6404.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
500293 | IDP - Economic Level of Leakage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-01-31 | 2016-02-01 | Scottish Water Wide | 0 | 37812.79 | -37812.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500295 | IDP - Leakage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 197423 | 10906.72 | 0 | 0 | 0 | 0 | 208329.72 | 0 | 208329.72 | 0 | [6 empty] | CM_WSI | 100%
403845 | IDP - Leakage - 4038450000 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2015-11-13 |  | Scottish Water Wide | 135796.78 | 41182.86 | 0 | 0 | 0 | 0 | 0 | 41182.86 | 0 | 176979.64 | 0 | [6 empty] | CM_WSI | 100%
500294 | IDP - Leakage - Research and Innovation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 90122 | 5062.93 | 32003.15 | 0 | 0 | 0 | 127188.08 | 0 | 127188.08 | 0 | [6 empty] | CM_WSI | 100%
404120 | IDP - Property Emergency Remedial Work - 14-15 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-08-04 | 2015-09-04 | Scottish Water Wide | 320000 | -7745.71 | 0 | 0 | 0 | 0 | 0 | -7745.71 | 0 | 312254.29 | 0 | [6 empty] | CM_M&G | 100%
500296 | IDP - Reservoirs - FRMA | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWD | Flood Risk Management Act | MS7 | 2015-04-16 | 2015-04-16 | 2016-01-06 | 2016-01-06 | 2016-01-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WR6 | 100%
500297 | IDP - Reservoirs - Interest of Safety | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-01-05 | 2016-01-05 | 2016-01-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403861 | IDP - Reservoirs FRMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2017-01-31 |  | Scottish Water Wide | 50000 | 78348.08 | 51311.29 | 98.34 | 0 | 0 | 0 | 129757.71 | 0 | 179757.71 | 0 | [6 empty] | CM_WSI | 100%
403846 | IDP - Reservoirs interest of safety | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2017-01-31 |  | Scottish Water Wide | 60000 | 178885.68 | 85973.17 | 0 | 0 | 0 | 0 | 264858.85 | 0 | 324858.85 | 0 | [6 empty] | CM_WSI | 100%
500292 | IDP - UID Storage Assets - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-15 | 2016-11-15 | Scottish Water Wide | 0 | 182491 | 21721.4 | 0 | 0 | 0 | 0 | 204212.4 | 0 | 204212.4 | 0 | [6 empty] | CM_WWI | 100%
502176 | IDP - Wastewater Central - Infra Assets - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 0 | 703722.47 | 11871.62 | 23.76 | 0 | 2493.66 | 718111.51 | 0 | 718111.51 | 0 | [6 empty] | CM_WWI | 100%
502177 | IDP - Wastewater Central - Non-Infra Assets - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 2017-07-21 | 2017-07-21 | Scottish Water Wide | 0 | 0 | 675131.21 | 3758.1 | 0 | 0 | 0 | 678889.31 | 0 | 678889.31 | 0 | [6 empty] | CM_WWNI | 100%
502677 | IDP - Wastewater Central Infra Assets - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-03-03 | 2021-03-12 | 2021-03-17 |  | 2021-03-19 | Scottish Water Wide | 0 | 0 | 0 | 96515.68 | 32885.42 | 15893.97 | -7695.08 | 137599.99 | 0 | 137599.99 | 0 | [6 empty] | CM_WWNI | 100%
502678 | IDP - Wastewater Central Non Infra Assets - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-07-10 | 2019-07-10 | Scottish Water Wide | 0 | 0 | 0 | 123080.32 | 12519.14 | -14669.48 | -221.63 | 120708.35 | 0 | 120708.35 | 0 | [6 empty] | CM_WWNI | 100%
502178 | IDP - Wastewater East - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-06 | 2020-01-06 | 2020-01-06 |  | 2020-01-06 | All East Unitary Authorities | 0 | 0 | 485612.9 | 23701.33 | 13396.42 | 46107.59 | 0 | 568818.24 | 0 | 568818.24 | 0 | [6 empty] | CM_WWNI | 100%
502679 | IDP - Wastewater East - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-01-15 | 2020-01-15 |  | 2020-01-15 | All East Unitary Authorities | 0 | 0 | 0 | 103428.15 | 21824.17 | 6706.12 | 0 | 131958.44 | 0 | 131958.44 | 0 | [6 empty] | CM_WWNI | 100%
500268 | IDP - Wastewater Infra Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-03-01 | All West Unitary Authorities | 0 | 41770 | -40282.65 | 813.24 | 0 | 0 | -449.37 | 1851.22 | 0 | 1851.22 | 0 | [6 empty] | CM_WWI | 100%
502180 | IDP - Wastewater South - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-07 | 2020-01-15 | 2020-01-15 |  | 2020-01-15 | All South Unitary Authorities | 0 | 0 | 174480.13 | 10821.61 | 95.93 | 0.01 | 0 | 185397.68 | 0 | 185397.68 | 0 | [6 empty] | CM_WWNI | 100%
502680 | IDP - Wastewater South - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-01-15 | 2020-01-15 |  | 2020-01-15 | All South Unitary Authorities | 0 | 0 | 0 | 107697.83 | 0 | 0 | 0 | 107697.83 | 0 | 107697.83 | 0 | [6 empty] | CM_WWNI | 100%
502181 | IDP - Wastewater West - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-01-15 | 2020-01-15 |  | 2020-01-15 | All West Unitary Authorities | 0 | 0 | 234149.86 | 7726.48 | 967.86 | 73.88 | 0 | 242918.08 | 0 | 242918.08 | 0 | [6 empty] | CM_WWNI | 100%
502681 | IDP - Wastewater West - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-01-15 | 2020-01-15 |  | 2020-01-15 | All West Unitary Authorities | 0 | 0 | 623.08 | 76847.22 | 147.51 | 0 | 0 | 77617.81 | 0 | 77617.81 | 0 | [6 empty] | CM_WWNI | 100%
500298 | IDP - Water Balance Data Studies and Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 300976 | 39504.94 | 96617.57 | 0 | 0 | 0.01 | 437098.52 | 0 | 437098.52 | 0 | [6 empty] | CM_WSI | 100%
502170 | IDP - Water Central - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-07-20 | 2017-07-20 | 2017-07-20 | 2017-04-03 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 1094408.92 | -152099.26 | 0 | 0 | 3611.09 | 945920.75 | 0 | 945920.75 | 0 | [6 empty] | CM_WSNI | 100%
502682 | IDP - Water Central - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-05-09 | 2019-05-09 | 2019-05-09 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 108000 | 98593.79 | 17086.71 | -24710.03 | 0 | 198970.47 | 0 | 198970.47 | 0 | [6 empty] | CM_WSNI | 100%
502171 | IDP - Water East - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-09-09 | 2019-09-09 | All East Unitary Authorities | 0 | 0 | 428530.5 | 114845.23 | 0 | 43928.34 | 0 | 587304.07 | 0 | 587304.07 | 0 | [6 empty] | CM_WSNI | 100%
502683 | IDP - Water East - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-09-12 | 2019-09-12 | Scottish Water Wide | 0 | 0 | 177120 | 177433.33 | 230400 | -126966.55 | 0 | 457986.78 | 0 | 457986.78 | 0 | [6 empty] | CM_WSNI | 100%
500287 | IDP - Water Infra Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-12-08 | 2016-12-21 | Scottish Water Wide | 0 | 416621.26 | 52520.63 | 0 | 0 | 0 | 0 | 469141.89 | 0 | 469141.89 | 0 | [6 empty] | CM_WSI | 100%
500274 | IDP - Water Infra Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 | 2016-09-28 | All East Unitary Authorities | 0 | 12025.09 | 3102.25 | 94.5 | 8.26 | 0 | -102.76 | 15127.34 | 0 | 15127.34 | 0 | [6 empty] | CM_WSI | 100%
500278 | IDP - Water Infra Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-09-26 | 2017-06-29 | All North Unitary Authorities | 0 | 60060.58 | 53030.86 | -19320.57 | 0 | 0 | -1870.48 | 91900.39 | 0 | 91900.39 | 0 | [6 empty] | CM_WSI | 100%
500282 | IDP - Water Infra Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-02-01 | 2017-03-16 | All West Unitary Authorities | 0 | 63235 | 33163.69 | 1913.14 | 0 | 0 | 0 | 98311.83 | 0 | 98311.83 | 0 | [6 empty] | CM_WSI | 100%
502172 | IDP - Water North - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-07-21 | 2017-07-21 | All North Unitary Authorities | 0 | 0 | 422624.76 | 17903.78 | 0 | 0 | 98955.83 | 539484.37 | 0 | 539484.37 | 0 | [6 empty] | CM_WSNI | 100%
502684 | IDP - Water North - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-07-17 | 2019-07-17 | 2019-06-20 | 2019-06-20 | 2019-06-20 | All North Unitary Authorities | 0 | 0 | 177120 | 115277.12 | 114346.62 | 19510 | 0 | 426253.74 | 0 | 426253.74 | 0 | [6 empty] | CM_WSNI | 100%
502173 | IDP - Water South - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-06-20 | 2017-06-20 | All South Unitary Authorities | 0 | 0 | 471509.52 | 62195.87 | 0 | 0 | 0.01 | 533705.4 | 0 | 533705.4 | 0 | [6 empty] | CM_WSNI | 100%
502685 | IDP - Water South - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-07-01 | 2019-07-31 | 2019-07-31 | 2019-07-01 | 2019-07-01 | All South Unitary Authorities | 0 | 0 | 177120 | 253315.88 | 180044.27 | 27586.78 | -13771.17 | 624295.76 | 0 | 624295.76 | 0 | [6 empty] | CM_WSNI | 100%
502174 | IDP - Water West - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-03-31 | 2017-03-31 | All West Unitary Authorities | 0 | 0 | 534693.1 | 108739.39 | 0 | 0 | 0 | 643432.49 | 0 | 643432.49 | 0 | [6 empty] | CM_WSNI | 100%
502676 | IDP - Water West - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-06-19 | 2019-06-19 | All West Unitary Authorities | 0 | 0 | 177120 | 275319.9 | 260981.9 | 150408.34 | -130045.61 | 733784.53 | 0 | 733784.53 | 0 | [6 empty] | CM_WSNI | 100%
500275 | IDP - WPS Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 | 2016-08-08 | All East Unitary Authorities | 0 | 157872.26 | 19120.14 | 0 | 0 | 0 | 0 | 176992.4 | 0 | 176992.4 | 0 | [6 empty] | CM_WSNI | 100%
500279 | IDP - WPS Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-08-18 | 2016-09-14 | All North Unitary Authorities | 0 | 43980 | -2389.4 | 0 | 0 | 0 | 0 | 41590.6 | 0 | 41590.6 | 0 | [6 empty] | CM_WSNI | 100%
500291 | IDP - WPS Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-09-14 | 2016-09-14 | All South Unitary Authorities | 0 | 95111.44 | 56350.95 | 0 | 0 | 0 | 0 | 151462.39 | 0 | 151462.39 | 0 | [6 empty] | CM_WSNI | 100%
500283 | IDP - WPS Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2017-02-01 | 2017-03-16 | All West Unitary Authorities | 0 | 147862 | -29745.92 | 0 | 0 | 0 | 0 | 118116.08 | 0 | 118116.08 | 0 | [6 empty] | CM_WSNI | 100%
500276 | IDP - WSR Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 | 2016-07-21 | All East Unitary Authorities | 0 | 32673 | -554.38 | 0 | 0 | 0 | 0 | 32118.62 | 0 | 32118.62 | 0 | [6 empty] | CM_WSNI | 100%
500280 | IDP - WSR Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-08-18 | 2016-09-14 | All North Unitary Authorities | 0 | 33996 | 701.08 | 0 | 0 | 0 | 0 | 34697.08 | 0 | 34697.08 | 0 | [6 empty] | CM_WSNI | 100%
500289 | IDP - WSR Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-03 | 2016-11-03 | All South Unitary Authorities | 0 | 83070.02 | 11610.56 | 0 | 0 | 0 | 0 | 94680.58 | 0 | 94680.58 | 0 | [6 empty] | CM_WSNI | 100%
500284 | IDP - WSR Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-12-13 | 2017-02-02 | All West Unitary Authorities | 0 | 239540 | 63337.64 | 268.31 | 0 | 704.26 | -704.26 | 303145.95 | 0 | 303145.95 | 0 | [6 empty] | CM_WSNI | 100%
500286 | IDP - WTW Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-01-06 | 2016-12-08 | 2017-03-30 | Scottish Water Wide | 0 | 1081651.52 | 247985.14 | -530.4 | 0 | -121.63 | 121.63 | 1329106.26 | 0 | 1329106.26 | 0 | [6 empty] | CM_WSNI | 100%
500277 | IDP - WTW Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2016-06-06 | 2016-07-21 | All East Unitary Authorities | 0 | 593688.69 | 23897.7 | 4920.54 | 7602.6 | 0 | -12442.28 | 617667.25 | 0 | 617667.25 | 0 | [6 empty] | CM_WSNI | 100%
500281 | IDP - WTW Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-09-18 | 2016-08-18 | 2016-09-16 | All North Unitary Authorities | 0 | 365517.58 | 29930.32 | 0 | 0 | 0 | 0 | 395447.9 | 0 | 395447.9 | 0 | [6 empty] | CM_WSNI | 100%
500288 | IDP - WTW Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-02-02 | 2016-11-03 | 2016-11-03 | All South Unitary Authorities | 0 | 511637.9 | 585542.53 | 106.31 | 0 | 0 | -106.31 | 1097180.43 | 0 | 1097180.43 | 0 | [6 empty] | CM_WSNI | 100%
500285 | IDP - WTW Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2016-12-19 | 2017-01-19 | All West Unitary Authorities | 0 | 453258 | -200263.09 | 0 | 0 | 0 | 0 | 252994.91 | 0 | 252994.91 | 0 | [6 empty] | CM_WSNI | 100%
500271 | IDP - WW Infra Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2017-05-12 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 1033259.2 | -24561.78 | 6945.26 | 385.75 | 0 | -4938.27 | 1011090.16 | 0 | 1011090.16 | 0 | [6 empty] | CM_WWI | 100%
500265 | IDP - WW Infra Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-06-29 | All South Unitary Authorities | 0 | 8909.96 | 2720.06 | 0 | 0 | 0 | 0 | 11630.02 | 0 | 11630.02 | 0 | [6 empty] | CM_WWI | 100%
500272 | IDP - WWPS Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-11-01 | 2016-11-01 | 2017-05-18 | Scottish Water Wide | 0 | 268531.28 | 114268.44 | 6398.26 | 0 | 0 | 0.02 | 389198 | 0 | 389198 | 0 | [6 empty] | CM_WWNI | 100%
500263 | IDP - WWPS Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2017-01-30 | 2017-01-30 | 2017-01-30 | All East Unitary Authorities | 0 | 100985 | -62109.66 | 0 | 0 | 0 | 0 | 38875.34 | 0 | 38875.34 | 0 | [6 empty] | CM_WWNI | 100%
500266 | IDP - WWPS Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-01-06 | All South Unitary Authorities | 0 | 158609.82 | 69747.56 | 228.75 | 0 | 172.24 | -172.24 | 228586.13 | 0 | 228586.13 | 0 | [6 empty] | CM_WWNI | 100%
500269 | IDP - WWPS Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-01-06 | All West Unitary Authorities | 0 | 255942.21 | 60646.06 | 234.58 | 637.53 | 0 | 0.01 | 317460.39 | 0 | 317460.39 | 0 | [6 empty] | CM_WWNI | 100%
500273 | IDP - WWTW Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-07-20 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 399834.33 | 53662.25 | -106283.44 | 0 | 838.16 | -16879.3 | 331172 | 0 | 331172 | 0 | [6 empty] | CM_WWNI | 100%
500264 | IDP - WWTW Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-02-02 | 2017-01-31 | 2017-01-31 | All East Unitary Authorities | 0 | 330052 | -203269.31 | -2930.31 | 0 | 0 | 0 | 123852.38 | 0 | 123852.38 | 0 | [6 empty] | CM_WWNI | 100%
500267 | IDP - WWTW Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-01-06 | 2017-04-26 | All South Unitary Authorities | 0 | 456568.9 | 279224.69 | 722.23 | 5699.56 | 0 | -6188.24 | 736027.14 | 0 | 736027.14 | 0 | [6 empty] | CM_WWNI | 100%
500270 | IDP - WWTW Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-01 | 2015-07-13 | 2015-07-13 | 2017-01-06 | 2017-03-06 | All West Unitary Authorities | 0 | 289496.83 | 35341.45 | 1778.92 | 0 | 0 | 0 | 326617.2 | 0 | 326617.2 | 0 | [6 empty] | CM_WWNI | 100%
403836 | IDP Infra Assets Central 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-17 | 2014-06-17 | 2014-06-17 | 2016-12-07 |  | Scottish Water Wide | 403503 | 30983 | -2011.25 | 0 | 0 | 0 | 0 | 28971.75 | 0 | 432474.75 | 0 | [6 empty] | CM_WSI | 100%
403837 | IDP Infra Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-23 |  | All East Unitary Authorities | 12629 | 12371 | -15475.14 | 0 | 0 | 0 | 0 | -3104.14 | 0 | 9524.86 | 0 | [6 empty] | CM_WSI | 100%
403838 | IDP Infra Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-08 |  | All North Unitary Authorities | 24128.76 | 81354.24 | -64981.05 | 0 | 0 | 0 | 0 | 16373.19 | 0 | 40501.95 | 0 | [6 empty] | CM_WSI | 100%
403840 | IDP Infra Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-09 |  | All West Unitary Authorities | 20521.67 | 3716.03 | 116.15 | 0 | 0 | 0 | 0 | 3832.18 | 0 | 24353.85 | 0 | [6 empty] | CM_WSI | 100%
501783 | IDP Leakage Yr2 to IDP Leakage Yrs 2-4 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2020-04-03 | 2020-02-26 | 2020-05-29 | 2021-03-31 | 2020-05-29 | Scottish Water Wide | 0 | 0 | 499613 | 172485 | 113926 | 439621 | 173245.02 | 1398890.02 | 0 | 1398890.02 | 0 | [6 empty] | CM_WSI | 100%
403841 | IDP UID Storage Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 54389.62 | 78615.37 | 12334.62 | 0 | 0 | 0 | 0 | 90949.99 | 0 | 145339.61 | 0 | [6 empty] | CM_WWNI | 100%
403842 | IDP UID Storage Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2015-11-05 |  | All North Unitary Authorities | 34982.7 | -1120.29 | 0 | 0 | 0 | 0 | 0 | -1120.29 | 0 | 33862.41 | 0 | [6 empty] | CM_WSNI | 43.87% | CM_WWNI | 56.13%
500290 | IDP -Water Infra Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-03 | 2016-11-03 | All South Unitary Authorities | 0 | 41385.94 | 129720.26 | 0 | 0 | 0 | 0 | 171106.2 | 0 | 171106.2 | 0 | [6 empty] | CM_WSI | 100%
403833 | IDP WPS Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-07 |  | All East Unitary Authorities | 36435.57 | -2408.57 | -1012.73 | 0 | 0 | 0 | 0 | -3421.3 | 0 | 33014.27 | 0 | [6 empty] | CM_WSNI | 100%
403834 | IDP WPS Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-08 |  | All North Unitary Authorities | 29931.93 | 56849.28 | 604.44 | 0 | 0 | 0 | 0 | 57453.72 | 0 | 87385.65 | 0 | [6 empty] | CM_WSNI | 100%
403835 | IDP WPS Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 21760.52 | 36663.48 | -5894.4 | 226.51 | 0 | 0 | 0 | 30995.59 | 0 | 52756.11 | 0 | [6 empty] | CM_WSNI | 100%
403832 | IDP WPS Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-10 |  | All West Unitary Authorities | 45329.9 | 5112.04 | 1250.85 | 0 | 0 | 0 | 0 | 6362.89 | 0 | 51692.79 | 0 | [6 empty] | CM_WSNI | 100%
403847 | IDP WSR Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-07 |  | All East Unitary Authorities | 21309.06 | 50111.4 | 10.09 | 0 | 0 | 0 | 0 | 50121.49 | 0 | 71430.55 | 0 | [6 empty] | CM_WSNI | 100%
403848 | IDP WSR Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-08-15 |  | All North Unitary Authorities | 47409.54 | 35152.46 | 2359.99 | 0 | 0 | 0 | 0 | 37512.45 | 0 | 84921.99 | 0 | [6 empty] | CM_WSNI | 100%
403849 | IDP WSR Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 46766.9 | 22472.46 | 342.38 | 264.7 | 0 | 0 | 0 | 23079.54 | 0 | 69846.44 | 0 | [6 empty] | CM_WSNI | 100%
403850 | IDP WSR Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-09 |  | All West Unitary Authorities | 58090.12 | 6425.27 | 0 | 0 | 0 | 0 | 0 | 6425.27 | 0 | 64515.39 | 0 | [6 empty] | CM_WSNI | 100%
403851 | IDP WW Infra Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 9479.95 | 10795.12 | 7173.08 | 0 | 0 | 0 | 0 | 17968.2 | 0 | 27448.15 | 0 | [6 empty] | CM_WWNI | 100%
403852 | IDP WW Infra Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-01-13 |  | All North Unitary Authorities | 624 | 423.12 | 0 | 0 | 0 | 0 | 0 | 423.12 | 0 | 1047.12 | 0 | [6 empty] | CM_WWNI | 100%
403853 | IDP WW Infra Assets Scotland Wide 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-09-01 |  | Scottish Water Wide | 371310.51 | 415764.61 | 15702.21 | 0 | 0 | 0 | 0 | 431466.82 | 0 | 802777.33 | 0 | [6 empty] | CM_WWI | 100%
403854 | IDP WW Infra Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All South Unitary Authorities | 341.73 | 415.07 | -106.07 | 0 | 0 | 0 | 0 | 309 | 0 | 650.73 | 0 | [6 empty] | CM_WWNI | 100%
403839 | IDP WW Infra Assets South 14-15 - 4038390000 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 8847.03 | 626.04 | -388.18 | 0 | 0 | 0 | 0 | 237.86 | 0 | 9084.89 | 0 | [6 empty] | CM_WWNI | 100%
403855 | IDP WW Infra Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All West Unitary Authorities | 10539.69 | 7391.5 | 422.22 | 0 | 0 | 0 | 0 | 7813.72 | 0 | 18353.41 | 0 | [6 empty] | CM_WWNI | 100%
403856 | IDP WWPS Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 135598.35 | 125725.88 | 15559.85 | 202.15 | 0 | 0 | 0 | 141487.88 | 0 | 277086.23 | 0 | [6 empty] | CM_WWNI | 100%
403858 | IDP WWPS Assets Scotland Wide 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-09-15 |  | Scottish Water Wide | 4544.36 | 1070.55 | 0 | 0 | 0 | 0 | 0.09 | 1070.64 | 0 | 5615 | 0 | [6 empty] | CM_WWNI | 100%
403859 | IDP WWPS Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All South Unitary Authorities | 41151.62 | 80070.25 | 1621.81 | 0 | 0 | 0 | 0 | 81692.06 | 0 | 122843.68 | 0 | [6 empty] | CM_WWNI | 100%
403860 | IDP WWPS Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All West Unitary Authorities | 57501.5 | 91866.5 | 416.42 | 315 | 0 | 0 | -315 | 92282.92 | 0 | 149784.42 | 0 | [6 empty] | CM_WWNI | 100%
402080 | IFOC Flooding Management Action Plan (FMAP) Process Phase 2 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-04-20 | 2011-06-14 | 2011-06-14 | 2012-05-25 |  | Scottish Water Wide | 1683555.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683555.13 | 0 | [6 empty] | CM_WWI | 100%
402522 | IFOC Flooding Management Action Plan (FMAP) Process Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-26 | 2012-04-24 | 2012-04-24 | 2013-08-14 |  | Scottish Water Wide | 1737334 | 23.63 | 0 | 0 | 0 | 0 | 0 | 23.63 | 0 | 1737357.63 | 0 | [6 empty] | CM_WWI | 100%
403354 | IFOC Flooding Management Action Plan (FMAP) Process Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-05-29 | 2013-05-29 | 2014-05-08 |  | Scottish Water Wide | 1686883 | 0 | -1126.16 | 0 | 0 | 0 | 0 | -1126.16 | 0 | 1685756.84 | 0 | [6 empty] | CM_WWI | 100%
403355 | IFOC Flooding Management Action Plan (FMAP) Process Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-09-09 | 2014-03-25 | 2014-03-26 | 2015-09-21 |  | Scottish Water Wide | 1683000 | 53393.07 | 2197.4 | 102.59 | 0 | 0 | 100 | 55793.06 | 0 | 1738793.06 | 0 | [6 empty] | CM_WWI | 100%
503540 | IFOS - Carnegies Brae Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-03-26 | 2022-08-11 | 2022-10-19 | 2023-05-30 | 2023-08-30 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 44167.39 | 25850.3 | 70017.69 | 829982.28 | 899999.97 | 196097.17 | [6 empty] | CS11A | 100%
505458 | IFOS - Sandsherd Fowlis Road - NE539 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-01-24 | 2023-12-11 | 2024-05-20 | 2025-12-01 | 2026-03-03 | Angus | 0 | 0 | 0 | 0 | 0 | 86.12 | 0 | 86.12 | 0 | 86.12 | 204193.13 | [6 empty] | CS11 | 100%
503743 | IFOS (1769-1) - Muir Street Forfar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-05 | 2021-07-08 | 2021-09-27 | 2022-02-09 | 2022-04-04 | Angus | 0 | 0 | 0 | 0 | 0 | 20700 | 69750.01 | 90450.01 | 34550.03 | 125000.04 | 196097.17 | [6 empty] | CS11A | 100%
503596 | IFOS (225-2) - Dumbarton Road Glasgow (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2020-03-03 | 2020-03-20 | 2021-01-08 | 2021-05-21 | 2021-08-23 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 25924.67 | 21122.39 | 47047.06 | 27952.94 | 75000 | 196097.17 | [6 empty] | CS11A | 100%
503616 | IFOS (506-1) - Academy Road Irvine (Meadowhead) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-04-09 | 2021-01-25 | 2021-02-01 | 2021-03-12 | 2021-03-15 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 23765.53 | 51234.47 | 75000 | 0 | 75000 | 196097.17 | [6 empty] | CS11A | 100%
503599 | IFOS (642-3) - Arthurlie Avenue Barrhead (Shieldhall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2020-03-03 | 2020-03-20 | 2021-02-02 | 2021-06-11 | 2021-09-03 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 25924.67 | 24892.46 | 50817.13 | 23796.87 | 74614 | 196097.17 | [6 empty] | CS11A | 100%
503698 | IFOS W628 - Muirpark Terrace Bishopbriggs (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-03-24 | 2022-11-01 | 2023-03-06 | 2024-09-27 | 2024-11-20 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 24738.02 | 77856.29 | 102594.31 | 497405.69 | 600000 | 196097.17 | [6 empty] | CS11A | 100%
501148 | Implementation of temporary solutions to internally affected properties | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2016-02-17 | 2016-02-17 | 2016-04-21 | 2016-11-29 | 2016-11-29 | Scottish Water Wide | 0 | 0 | 166282.93 | 370 | -5493.28 | 0 | 0 | 161159.65 | 0 | 161159.65 | 196097.17 | [6 empty] | CS11A | 100%
502936 | Implementation of temporary solutions to internally flooding affected properties Year 3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS5 | 2017-10-18 | 2017-10-18 | 2017-11-30 | 2019-04-29 | 2019-04-29 | Scottish Water Wide | 0 | 0 | 0 | 17155.14 | 195610.95 | -12178.59 | 0 | 200587.5 | 0 | 200587.5 | 196097.17 | [6 empty] | CS11A | 100%
503577 | Implementation of temporary solutions to internally flooding affected properties Year 5 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2019-05-22 | 2019-05-22 | 2019-07-24 |  | 2020-09-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 226355.14 | 14805.58 | 241160.72 | 31579.42 | 272740.14 | 196097.17 | [6 empty] | CS11A | 100%
505614 | Implementation of temporary solutions to internally flooding affected properties Year 6 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2020-04-01 | 2020-03-26 | 2021-04-13 | 2021-10-12 | 2022-01-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 250000 | 196097.17 | [6 empty] | CS11A | 100%
502423 | Implementation of temporary solutions to internally flooding affected properties Yr 2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-01-25 | 2017-01-25 | 2017-03-20 | 2018-03-02 | 2018-03-02 | Scottish Water Wide | 0 | 0 | 34559.14 | 178775 | -20286.73 | 0 | 3497.1 | 196544.51 | 0 | 196544.51 | 196097.17 | [6 empty] | CS11A | 100%
403352 | Implementation of Temporary Solutions to Properties Affected by Internal Flooding Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-15 | 2013-04-15 | 2013-04-15 | 2014-09-01 |  | Scottish Water Wide | 250000 | 0 | -3483.66 | 0 | 0 | 0 | 0 | -3483.66 | 0 | 246516.34 | 0 | [6 empty] | CM_WWI | 100%
403353 | Implementation of Temporary Solutions to Properties Affected by Internal Flooding Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-22 | 2014-03-25 | 2014-03-26 | 2015-12-04 |  | Scottish Water Wide | 244939 | 23210 | 0 | 0 | 0 | 0 | 0 | 23210 | 0 | 268149 | 0 | [6 empty] | CM_WWI | 100%
403618 | Implementation of Temporary Solutions to Properties Affected by Internal Flooding Phase 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-11-11 | 2013-11-22 | 2013-11-22 | 2015-12-15 |  | Scottish Water Wide | 250039.62 | 5034.26 | 3015.57 | -214 | 0 | 0 | 0 | 7835.83 | 0 | 257875.45 | 0 | [6 empty] | CM_WWI | 100%
400107 | Improvement To S-D Balance - Ardrishaig WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-28 | 2013-07-29 | 2014-03-19 | 2014-03-26 | Argyll and Bute-North Argyll | 927418 | 171.28 | 45 | 9237.5 | 0 | 0 | 0 | 9453.78 | 0 | 936871.78 | 799 | [6 empty] | WG4 | 100%
45389 | Improvement To S-D Balance - Auchneel Barclyle Palnure Penwhirn WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-07-20 | 2012-08-20 | 2014-08-29 | 2014-09-29 | Dumfries and Galloway | 8257963 | 5322 | -3611.08 | 286 | 0 | 0 | 0.01 | 1996.93 | 0 | 8259959.93 | 47035 | [6 empty] | WG4 | 100%
45390 | Improvement To S-D Balance - Black Esk Kettleton Moffat Winterhope and Langholm WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-26 | 2013-01-16 | 2014-06-20 | 2014-06-30 | Dumfries and Galloway | 8875802 | 95146.27 | 10288.93 | 3.71 | 0 | 0 | 0 | 105438.91 | 0 | 8981240.91 | 88153 |  |  |  |  | 42445.63 |  | WG4 | 100%
45395 | Improvement To S-D Balance - Bonar Bridge WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2015-03-11 | 2015-03-23 | 2017-03-31 | 2017-03-31 | Highland | 1433616.26 | 127784.74 | 766588.79 | 183701.49 | 41076.06 | -6087.41 | 0.01 | 1113063.68 | 0 | 2546679.94 | 94074 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-03
45385 | Improvement To S-D Balance - Broadford WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-06-20 | 2013-09-02 | 2014-12-05 | 2015-02-09 | Highland | 2636329 | 131721 | 15956.57 | 0 | 0 | 0 | 0.36 | 147677.93 | 0 | 2784006.93 | 29723 | [6 empty] | WG4 | 100%
400103 | Improvement To S-D Balance - Carbost WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-06-18 | 2012-10-29 | 2013-03-25 | 2013-03-28 | Highland | 654891.77 | -2720.25 | 0 | 0 | 0 | 0 | 0 | -2720.25 | 0 | 652171.52 | 0 | [6 empty] | CM_WSNI | 21.83% | WG4 | 78.17%
45388 | Improvement To S-D Balance - Fife WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2011-08-08 | 2011-08-16 | 2014-02-06 | 2014-03-19 | Fife | 3913359 | 19324.46 | 0 | 0 | 0 | 0 | 0 | 19324.46 | 0 | 3932683.46 | 6115 | [6 empty] | WG4 | 100%
45384 | Improvement To S-D Balance - Gorthleck WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-03-27 | 2012-06-04 | 2014-02-03 | 2014-03-19 | Highland | 4463646 | -9351.44 | 0 | 0 | 0 | 0 | 0 | -9351.44 | 0 | 4454294.56 | 0 | [6 empty] | WG4 | 100%
400106 | Improvement To S-D Balance - Inveraray WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-11 | 2013-07-29 | 2014-03-28 | 2014-03-31 | Argyll and Bute-North Argyll | 3027762 | -9896 | -18000.01 | 16146.89 | 2026.11 | 55.41 | -55.4 | -9723 | 0 | 3018039 | 32034 | [6 empty] | WG4 | 100%
45383 | Improvement To S-D Balance - Inverness and Nairn WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2017-09-27 | 2017-07-03 | 2017-06-01 | 2017-07-03 | Highland | 1207584 | 443800 | 1204130.21 | 129429.82 | 0 | 0 | 0 | 1777360.03 | 0 | 2984944.03 | 11719825 | [6 empty] | WG4 | 100%
45392 | Improvement To S-D Balance - Killin WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-08-31 | 2012-12-03 | 2014-03-28 | 2014-03-31 | Stirling | 1613978 | -7128 | 790.7 | 0 | 0 | 0 | 0 | -6337.3 | 0 | 1607640.7 | 4041 | [6 empty] | WG4 | 100%
400105 | Improvement To S-D Balance - Tarbert (Western Isles) | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-03-13 | 2012-07-23 | 2012-12-14 | 2013-03-28 | Na H-Eileanan an Iar | 891281.46 | 11422.65 | 0 | 0 | 0 | 0 | 0 | 11422.65 | 0 | 902704.11 | 0 | [6 empty] | WG4 | 100%
500042 | Improvement to Supply/Demand Balance - South Uist WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-25 | 2016-08-26 | Na H-Eileanan an Iar | 0 | 27596 | -27596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG4 | 100%
500043 | Improvement to Supply-Demand Balance - Benbecula WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | NONINF | SOSI | MS5 | 2016-03-29 | 2017-12-22 | 2017-12-22 | 2019-06-30 | 2019-06-30 | Na H-Eileanan an Iar | 302.76 | 43756.68 | 237292.44 | 526588.9 | 513198.19 | 77842.77 | 1116.16 | 1399795.14 | 10401.1 | 1410499 | 761457.15 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500041 | Improvement to Supply-Demand Balance - Lochinver WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS6 | 2016-10-10 | 2017-09-29 | 2018-02-26 | 2018-09-30 | 2019-01-31 | Highland | 127.3 | 15472.7 | 19109.32 | 214411.51 | 490774.52 | -3616.55 | 2139.27 | 738290.77 | 277.29 | 738695.36 | 1062422.7 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500048 | Improvement to Supply-Demand Balance - Mallaig WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2015-02-23 | 2015-03-18 | 2015-03-18 | 2015-04-30 | 2015-12-31 | Highland | 0 | 1150 | -895.75 | 0 | 0 | 0 | 745.75 | 1000 | 0 | 1000 | 375898.29 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500032 | Improvement to Supply-Demand Balance - North Hoy WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS6 | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-19 | 2019-03-27 | Orkney Islands | 24.93 | 47754.46 | 131072.47 | 1567095.98 | 206236.33 | 92321.01 | -4010.92 | 2040469.33 | 11940.74 | 2052435 | 4557528.27 | [6 empty] | WG4 | 100%
500033 | Improvement to Supply-Demand Balance - Sandy Loch WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2019-09-25 | 2019-09-16 | 2019-09-16 | 2019-08-16 | 2019-08-16 | Shetland Islands | 686.11 | 42999.07 | -43685.18 | 394.84 | 0 | 160 | 0 | -131.27 | 0 | 554.84 | 3250279.58 | [6 empty] | WG4 | 100%
500046 | Improvement to Supply-Demand Balance - Stornoway WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS0 | 2018-09-28 | 2021-03-15 | 2021-04-08 | 2022-01-31 | 2022-04-30 | Na H-Eileanan an Iar | 0 | 53505.94 | 61798.03 | 40362.52 | 72120.81 | 162207.05 | 529526.09 | 919520.44 | 2587789.66 | 3507310.1 | 969103.43 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500034 | Improvement to Supply-Demand Balance - Tullich WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS6 | 2016-10-31 | 2018-03-21 | 2018-06-26 | 2019-03-31 | 2019-09-30 | Argyll and Bute-North Argyll | 105.42 | 11237.68 | 31714.6 | 23573.82 | 201544.43 | -953.63 | 0.01 | 267116.91 | 0 | 267222.33 | 696780.05 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500044 | Improvement to Supply-Demand Balance - Waternish WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS5 | 2018-09-28 | 2018-12-17 | 2018-12-17 | 2018-12-31 | 2019-03-31 | Highland | 148.01 | 10265.99 | 0 | 963.75 | 7934.54 | 36383.22 | 0 | 55547.5 | 0 | 55695.51 | 555910.14 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500045 | Improvement to Supply-Demand Balance - West Lewis WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS5 | 2016-03-29 | 2020-07-01 | 2020-07-01 | 2019-05-20 | 2019-05-20 | Na H-Eileanan an Iar | 471.4 | 54181.41 | 395305.6 | 226128.06 | 11180.7 | 0 | 0 | 686795.77 | 0 | 687267.17 | 258568.71 | [6 empty] | WG4 | 100%
402842 | Improvement work to various WwTWs to improve CAS compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-09-14 | 2015-05-11 | 2015-01-12 | 2015-09-18 |  | Scottish Water Wide | 370193.69 | 317710.15 | 91.88 | 529.69 | 0 | 0 | 0 | 318331.72 | 0 | 688525.41 | 0 | [6 empty] | CM_WWNI | 100%
500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS5 | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-23 | 2020-03-31 | Scottish Water Wide | 0 | 3426.41 | 258352.68 | 1699284.75 | 803926.7 | 103314.09 | 3953.51 | 2872258.14 | 11685.97 | 2883944.11 | 769021.85 |  |  |  |  | 54611.67 |  | CM_WSNI | 37.71% | DW25T | 62.29%
501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-08-30 | Scottish Water Wide | 0 | 0 | 0 | 24418 | 4917 | -20331.05 | 0 | 9003.95 | 0 | 9003.95 | 769021.85 | [6 empty] | DW25T | 100%
501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2021-09-13 | 2021-12-13 | Scottish Water Wide | 0 | 15069.77 | 24435.68 | 345517.01 | 1121617.78 | 885260.58 | 312538.5 | 2704439.32 | 19796.45 | 2724235.77 | 769021.85 | [6 empty] | CM_WSNI | 35% | DW25T | 65%
501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-27 | 2018-12-14 | Scottish Water Wide | 0 | 15069.77 | 23441.86 | -2511.63 | 0 | -5895.75 | 0 | 30104.25 | 0 | 30104.25 | 769021.85 | [6 empty] | DW25T | 100%
501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 32167.33 | 43960.24 | 0 | 0 | 0 | 76127.57 | 0 | 76127.57 | 769021.85 | [6 empty] | DW25T | 100%
50012 | Improving Reliability of WQ in Network - Holding Line | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2396025.48 | 2396025.48 | 0 | 2396025.48 | 769021.85 | [6 empty] | DW25T | 100%
501116 | Improving resilience of supplies - Backies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-31 | 2016-05-31 | Highland | 0 | 7116.28 | 0 | 0 | 0 | 0 | 0 | 7116.28 | 0 | 7116.28 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
501115 | Improving resilience of supplies - Howden | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS6 | 2016-09-20 | 2018-03-29 | 2018-03-29 | 2019-06-30 | 2019-09-30 | Scottish Borders | 0 | 21600 | 133675 | 569454 | 2709796.42 | 184181.6 | 0 | 3618707.02 | 0 | 3618707.02 | 2294081.61 | [6 empty] | CS16WR | 50% | WG5 | 50% | bar: Regulatory Outputs OMG-07
501041 | Improving Resilience of Supplies - Kirbister | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-02-29 | 2016-03-11 | 2016-03-11 | 2016-03-31 | 2016-05-31 | Orkney Islands | 0 | 7027.31 | 0 | 0 | 0 | 0 | 0 | 7027.31 | 0 | 7027.31 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
500973 | Improving Resilience of Supplies - Westray | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | NONINF | Supply Resilience | MS5 | 2016-03-17 | 2017-03-31 | 2017-06-30 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 13249.92 | 595494.23 | 314930.7 | 699443.05 | 12952.1 | 10806.35 | 1646876.35 | 4409.79 | 1651286.14 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
500733 | Improving resilience of supplies at Invercannie | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2015-08-25 | 2016-03-22 | 2016-03-22 | 2016-12-31 | 2017-03-31 | All North Unitary Authorities | 0 | 35000 | -8280.32 | -3471.55 | 0 | 10.74 | 5723.57 | 28982.44 | 0 | 28982.44 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
401262 | Incentivising Developers to Adopt Water Efficiency Measures | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-09-15 | 2015-03-11 | 2015-03-11 | 2015-07-13 | 2015-07-13 | Scottish Water Wide | 958741 | 7703.71 | 0 | 0 | 0 | 0 | 0 | 7703.71 | 0 | 966444.71 | 469149 | [6 empty] | CS18W | 100%
501257 | Inchgarth RWI High-Lift Pumps - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-08-15 | 2018-05-31 | 2018-06-05 | 2020-07-13 | 2020-10-12 | Aberdeenshire | 0 | 22853.75 | 23497.75 | 601684.13 | 923785.01 | 642794.6 | 297228.85 | 2511844.09 | 17133.9 | 2528977.99 | 0 |  |  |  |  | 11830 |  | CM_WSNI | 100%
46198 | Inchgarth RWI Refurb - RWI000723 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2010-09-27 | 2011-05-30 | 2011-12-23 |  | Aberdeenshire | 1059999.17 | 72.76 | 0 | 0 | 0 | 0 | 0 | 72.76 | 0 | 1060071.93 | 0 | [6 empty] | CM_WSI | 100%
502630 | Inchgarth RWP - Replace Permanent Standby Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-03-14 | 2017-07-28 | 2017-09-11 | 2018-05-03 | 2018-05-03 | Aberdeen City | 0 | 0 | 5981.31 | 1792983.87 | 48637.64 | 636.94 | 2203.2 | 1850442.96 | 159.85 | 1850602.81 | 0 | [6 empty] | CM_WSNI | 100%
503370 | Inchinnan WwPS - Replacement Access Road | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | GW1 | 2021-04-22 | 2022-06-22 | 2022-10-25 | 2023-07-21 | 2023-10-23 | Renfrewshire | 0 | 0 | 0 | 0 | 12383.48 | 19956.56 | -2304.05 | 30035.99 | 535193.95 | 565229.94 | 0 | [6 empty] | CM_M&G | 100%
45335 | Inchlaggan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-11-18 | 2012-03-09 | 2012-03-30 | Highland | 41220.72 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 41241.72 | 0 | [6 empty] | DW13 | 100%
503275 | Inchmarlo WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-01-07 | 2022-05-27 | 2022-09-29 | 2023-09-27 | 2023-12-28 | Aberdeenshire | 0 | 0 | 0 | 0 | 83449.24 | 33509.88 | 50946.62 | 167905.74 | 1978654.23 | 2146559.97 | 136478.56 | [6 empty] | SG1 | 100%
505534 | Industrial Emissions Directive (IED) - Study | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS1 | 2020-03-13 | 2020-11-09 | 2021-03-16 | 2021-09-14 | 2021-12-15 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 9813.08 | 0 | 9813.08 | 0 | 9813.08 | 0 | [6 empty] | Ww3 | 100%
500591 | Industry Applications Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-11-18 | 2016-06-30 | 2016-06-30 | 2021-02-23 | 2021-02-23 | Scottish Water Wide | 0 | 185131 | 339196.8 | 194102.15 | 166354.73 | -5651.79 | 10010 | 889142.89 | 0 | 889142.89 | 0 | [6 empty] | CM_M&G | 100%
504066 | Information Compliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-01-06 | 2020-03-20 | 2020-03-20 | 2020-05-20 | 2020-05-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 435922.5 | 117454.2 | 553376.7 | 0 | 553376.7 | 0 | [6 empty] | CM_M&G | 100%
500593 | Information Management Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-17 | 2016-12-22 | 2016-12-22 | 2020-05-14 | 2020-05-15 | Scottish Water Wide | 0 | 496728 | 121999.92 | 330491.88 | 105818.78 | 58853.73 | 0.01 | 1113892.32 | 0 | 1113892.32 | 0 | [6 empty] | CM_M&G | 100%
500676 | Information Management SharePoint Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2015-06-05 | 2017-09-01 | 2017-09-01 | 2020-03-03 |  | Scottish Water Wide | 0 | 382234.46 | 1059259.67 | 1270328.94 | 730971.26 | 432055.35 | 0 | 3874849.68 | 0 | 3874849.68 | 0 |  |  |  |  | -206215.05 |  | CM_M&G | 100%
503357 | INFRA - Banchory Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 | 2019-03-11 | 2019-03-11 | 2022-05-09 | 2023-12-01 | 2023-12-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 29439.25 | 362000 | 184433.75 | 575873 | 0 | 575873 | 470181.23 | [6 empty] | WG5 | 100%
503435 | INFRA - Banknock | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-04-08 | 2019-04-08 | 2020-02-13 | 2022-01-26 | 2022-01-26 | Falkirk | 0 | 0 | 0 | 0 | 0 | 47223.32 | 255740.41 | 302963.73 | 444466.3 | 747430.03 | 1830849.77 | [6 empty] | SG5 | 100%
503436 | INFRA - Elgin - Waste | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS0 | 2019-07-31 | 2021-02-22 | 2021-04-27 | 2022-05-23 | 2022-05-24 | Moray | 0 | 0 | 0 | 0 | 0 | 13084.11 | 647425.89 | 660510 | 1339489.98 | 1999999.98 | 1830849.77 | [6 empty] | SG5 | 100%
503360 | INFRA - Johnshaven & St Cyrus Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-08-06 | 2021-02-15 | 2021-04-12 | 2021-10-05 | 2022-01-05 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 40204.52 | 52522.75 | 92727.27 | 1907272.69 | 1999999.96 | 470181.23 | [6 empty] | WG5 | 100%
503359 | INFRA - Ravelrigg - Edinburgh | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2020-07-08 | 2020-10-26 | 2020-11-19 | 2021-12-13 | 2022-03-15 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 1936.86 | 1936.86 | -1936.86 | 0 | 0 | [6 empty] | WG5 | 100%
503518 | INFRA -SR15 Development - Programme Overhead | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MS3 | 2019-05-14 | 2019-05-14 | 2019-06-28 |  | 2021-03-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 6757778.67 | 2911569.11 | 9669347.78 | 0 | 9669347.78 | 2301031 | [6 empty] | SG5 | 50% | WG5 | 50%
503362 | Infra-Kingdom Park | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-03-28 | 2019-03-28 | 2020-02-13 | 2021-07-02 | 2021-07-02 | Fife | 0 | 0 | 0 | 0 | 60797 | 134768.47 | 772022.98 | 967588.45 | 1032411.5 | 1999999.95 | 0 | [6 empty] | SG5 | 100%
503358 | INFRA-Newmills - Edinburgh | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2019-05-28 | 2019-05-28 | 2019-05-28 | 2022-11-23 | 2022-12-05 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 455541.4 | -135462.36 | 320079.04 | -78.96 | 320000.08 | 470181.23 | [6 empty] | WG5 | 100%
500954 | Infrastructure Monitoring Tools Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-23 | 2015-12-14 | 2015-12-14 | 2017-06-23 |  | Scottish Water Wide | 0 | 286124 | 52979.45 | 0 | 0 | 0 | 0 | 339103.45 | 0 | 339103.45 | 0 | [6 empty] | CM_M&G | 100%
403909 | Infrastructure Prog Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-09-05 | 2014-09-05 | 2014-09-05 | 2015-06-30 |  | Scottish Water Wide | 261711 | 4072.61 | 0 | 0 | 0 | 0 | 0 | 4072.61 | 0 | 265783.61 | 0 | [6 empty] | CM_M&G | 100%
501532 | Innellan Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-06-07 | 2029-10-11 | 2030-02-20 | 2030-05-23 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237339.99 | 237339.99 | 0 | [6 empty] | CM_WSNI | 100%
502572 | Innerleithen WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2020-09-18 | 2021-06-07 | 2021-08-06 | 2022-07-14 | 2022-10-14 | Scottish Borders | 0 | 0 | 20930.23 | 2091.45 | 45128.41 | 3442.97 | -3855.17 | 67737.89 | 12262.12 | 80000.01 | 136478.56 | [6 empty] | WG1 | 100%
45409 | Innerleithen WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-03-16 | 2011-10-03 | 2015-03-27 | 2015-12-17 | Scottish Borders | 4230414.8 | 217150.56 | 33919.75 | -32156.47 | -9436.03 | 0 | 0.01 | 209477.82 | 0 | 4439892.62 | 45802 |  |  |  |  | 21395 |  | CS16W | 1.577% | DW23 | 98.42%
501512 | INSH WWTW 1996 NH809016 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-03-24 | 2027-09-17 | 2027-12-06 | 2028-04-18 | 2028-07-19 | Highland | 0 | 0 | 0 | 25324.23 | 28245.63 | 14776.7 | -8346.57 | 59999.99 | 615000 | 674999.99 | 0 | [6 empty] | CM_WWNI | 100%
403960 | Installation of Auto-samplers | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-11-10 | 2015-04-20 | 2015-05-11 | 2017-03-08 | 2017-04-13 | Scottish Water Wide | 85123 | 2573932 | 291248 | 38056 | -4671.37 | 0 | 1933.38 | 2900498.01 | 0 | 2985621.01 | 1888493 | [6 empty] | EC01A | 100%
500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWD | Renewable power | MS7 | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2018-05-11 | 2018-05-11 | Scottish Water Wide | 0 | 791122.51 | 793.12 | 0 | 0 | 0 | 0 | 791915.63 | 0 | 791915.63 | 832227.31 | [6 empty] | I2S_WI | 100%
401676 | Intelligent Control Centre - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-02-04 | 2012-09-05 | 2012-09-18 | 2016-08-08 |  | Scottish Water Wide | 15017167 | 207275 | -1133.9 | 35.59 | 0 | 0 | 1083.16 | 207259.85 | 0 | 15224426.85 | 0 | [6 empty] | CM_M&G | 100%
503395 | Interim THM and Cryptosporidium measures - MD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-09-06 | 2019-06-20 | 2019-05-21 | 2019-05-21 | 2019-05-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | 0.01 | 0 | [6 empty] | CM_WSNI | 100%
503394 | Interim THM and Cryptosporidium Measures - SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-08-24 | 2018-09-04 | 2018-09-04 | 2020-08-21 | 2020-10-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 233115.61 | 503240.61 | 93643.78 | 830000 | 0 | 830000 | 0 | [6 empty] | CM_WSNI | 100%
402351 | Internal Flooding Aberdeen Harbour Area | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-09-20 | 2012-06-27 | 2012-08-27 | 2013-02-27 | 2013-02-27 | Aberdeen City | 92563.76 | 85.66 | 0 | 0 | 0 | 0 | 0 | 85.66 | 0 | 92649.42 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402390 | Internal Flooding Ardgay Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2014-07-22 | 2014-07-30 | 2014-09-22 | 2014-09-22 | Glasgow City | 322018 | 0 | 0 | 0 | -921.74 | 0 | 0 | -921.74 | 0 | 321096.26 | 573.6 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402448 | Internal Flooding at Burns Statue Square Ayr | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2012-09-14 | 2012-11-21 | 2013-12-10 | 2013-12-10 | South Ayrshire | 20111 | -215.05 | 0 | 0 | 0 | 0 | 0 | -215.05 | 0 | 19895.95 | 280.8 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402449 | Internal Flooding at City Road Dundee | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2012-06-27 | 2012-08-27 | 2012-12-20 | 2012-12-20 | Dundee City | 27349.74 | 46.35 | 0 | 0 | 0 | 0 | -0.35 | 46 | 0 | 27395.74 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402442 | Internal Flooding at Don Street Forfar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2011-12-07 | 2015-01-09 | 2015-01-26 | 2015-03-13 | 2015-03-13 | Angus | 191645 | -16175.5 | 0 | 48.04 | 0 | 0 | 0 | -16127.46 | 0 | 175517.54 | 204193.13 | [6 empty] | CS11A | 100%
402445 | Internal Flooding at Rattray Gardens Bathgate | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-02 | 2013-07-22 | 2013-10-14 | 2014-06-30 | 2014-06-30 | West Lothian | 522906.49 | 1516.7 | 0 | 0 | 0 | 0 | 0 | 1516.7 | 0 | 524423.19 | 1154.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402657 | Internal Flooding at Roseangle Dundee | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-05-18 | 2013-07-12 | 2013-07-29 | 2016-11-25 | 2016-11-25 | Dundee City | 106546 | 5170 | -1282.98 | -16369.3 | 0 | 0 | 0 | -12482.28 | 0 | 94063.72 | 405511.2 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402655 | Internal Flooding at Russel Drive Bearsden | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS4 | 2012-04-23 | 2019-06-12 | 2020-07-27 | 2019-06-12 | 2020-07-27 | Glasgow City | 57171 | 0 | 3829 | 2000 | 2000 | 22730.69 | 496.69 | 31056.38 | 0 | 88227.38 | 204193.13 | [6 empty] | CS11A | 100%
402447 | Internal Flooding at Townhead Catrine Mauchline | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2013-06-20 | 2014-01-27 | 2014-03-28 | 2014-03-28 | East Ayrshire | 207982 | -2322.39 | 0 | 53.04 | 0 | 0 | -53.04 | -2322.39 | 0 | 205659.61 | 768.6 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403292 | Internal Sewer Flooding APRNV Programme Phase1 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-02-20 | 2013-03-20 | 2013-04-25 | 2015-11-02 | 2016-01-05 | Scottish Water Wide | 1956539 | 29488 | 45029.29 | -625.1 | 0 | 0 | 0 | 73892.19 | 0 | 2030431.19 | 21267 | [6 empty] | CM_WWI | 40% | CS11A | 60%
500715 | Interruptions to Supply Proactive Management | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-30 | 2015-06-30 | 2016-02-01 | 2018-10-31 | 2018-10-31 | Scottish Water Wide | 0 | 365730 | 194009.85 | 138748.36 | 0 | 0 | 0 | 698488.21 | 0 | 698488.21 | 753145.45 | [6 empty] | CS12 | 100%
403515 | Inveraray STW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-26 | 2015-02-16 | 2015-06-02 | 2015-10-07 | 2015-10-07 | Argyll and Bute-North Argyll | 40890 | 150152 | 812.93 | -346 | 0 | 0 | 0 | 150618.93 | 0 | 191508.93 | 0 | [6 empty] | SG1 | 100%
502882 | Inveraray WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-06-27 | 2033-10-12 | 2034-05-31 | 2034-08-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21238 | 1824.51 | -19016.59 | 0 | 4045.92 | 0 | 4045.92 | 136478.56 | [6 empty] | WG1 | 100%
500826 | Inverasdale RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-11-17 | 2016-03-25 | 2016-10-03 | 2017-06-30 | 2018-03-31 | Highland | 0 | 5471.98 | 15794.66 | 25561.64 | 4438.09 | 12564.52 | -11564.51 | 52266.38 | 0 | 52266.38 | 56543 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 26.72
34831 | Invercannie - Mannofield WRZ-WFD Compliance | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-15 | 2010-11-05 | 2011-01-06 | 2012-03-23 | 2012-03-23 | Aberdeenshire | 4773284 | 448.31 | 0 | 0 | 0 | 0 | 2051.69 | 2500 | 0 | 4775784 | 29376.53 | [6 empty] | WSNI | 20.96% | WR1 | 79.04%
501619 | Invercannie 1866 - Uppermill of Crathes Culvert Crossing Repairs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-31 |  | Aberdeenshire | 0 | 2323.88 | 63676.12 | 0 | 2520 | 1712.21 | -1306.59 | 68925.62 | -83.33 | 68842.29 | 334512.73 | [6 empty] | DW25P | 100%
503479 | Invercannie 1866 Aqueduct - Vegetation Intrusion | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-05-03 | 2022-02-14 | 2022-04-21 | 2022-09-07 | 2022-12-08 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2364.63 | 2364.63 | 47635.41 | 50000.04 | 0 | [6 empty] | CM_WSI | 100%
403952 | Invercannie East DIR Cleaning Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-10-06 | 2014-10-06 | 2014-11-03 | 2015-02-05 |  | Aberdeenshire | 145523 | 9620 | 0.04 | -599.35 | 0 | 0 | 0 | 9020.69 | 0 | 154543.69 | 0 | [6 empty] | CM_WSI | 100%
503123 | Invercannie WTW - Augmentation 5mld | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW1 | 2020-08-31 | 2020-09-14 | 2020-09-14 | 2020-09-14 | 2020-09-14 | Aberdeenshire | 0 | 0 | 0 | 2989.2 | 58205.73 | 69295.85 | -25973.87 | 104516.91 | 0 | 104516.91 | 0 | [6 empty] | WG5 | 100%
502330 | Invercannie WTW - Catchment Survey and Monitoring | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2016-09-29 | 2016-09-29 | 2017-08-01 | 2020-07-31 | 2020-08-19 | Aberdeen City | 0 | 0 | 0 | 0 | 74.17 | 300.01 | 0 | 374.18 | 0 | 374.18 | 128372.27 | [6 empty] | DW25P | 100%
502166 | Invercannie WTW - Cleaning of Invercannie West DIR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-31 | 2020-04-07 | Aberdeenshire | 0 | 0 | 40126.31 | 1077618.96 | 149677.34 | 1590.13 | 3409.86 | 1272422.6 | 0 | 1272422.6 | 128372.27 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
502756 | Invercannie WTW - CWT | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS0 | 2019-01-22 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 2020-05-25 | Aberdeenshire | 0 | 0 | 0 | 177570.91 | 489468.18 | -667039.08 | 0.01 | 0.02 | 0 | 0.02 | 8695235.16 | [6 empty] | DW25P | 100%
502480 | Invercannie WTW - PLC Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-23 | 2017-02-23 | 2017-04-12 | 2019-02-19 | 2019-02-19 | Aberdeenshire | 0 | 0 | 300779.3 | 1217634.86 | 565517.41 | 2836.14 | 1115.77 | 2087883.48 | 306.42 | 2088189.9 | 0 | [6 empty] | CM_WSNI | 100%
401872 | Invercannie WTW and 1924 Aqueduct Investigation - Intervention Development | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-23 | 2012-09-27 | 2012-10-17 | 2014-08-29 |  | Aberdeenshire | 77235 | 3848 | -214.01 | 0 | 0 | 0 | 214.01 | 3848 | 0 | 81083 | 0 | [6 empty] | CM_WSI | 100%
501243 | Invercannie WTW Pre-Treatment CWT and CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2019-02-08 | 2020-02-28 | 2020-03-16 | 2022-09-02 | 2023-11-10 | Aberdeenshire | 0 | 158593.32 | 27727.57 | 268382.76 | 444017.61 | 7997042.98 | 17143558.36 | 26039322.6 | 26318415.34 | 52357737.94 | 6784612.62 | [6 empty] | DW23 | 100%
503838 | Inverclyde DOA - SIlverwells Culvert Flows Diversion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | GW1 |  | 2020-06-22 | 2020-07-10 | 2021-02-11 | 2021-03-11 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 5435.18 | -3435.18 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWI | 100%
500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-06-22 | 2021-01-08 | Inverclyde | 0 | 49028 | 451618 | 215673.38 | 215043.9 | 150626.62 | 57146.5 | 1139136.4 | 0 | 1139136.4 | 481381.62 | [6 empty] | EC01G | 2.1% | EC01D | 19.34% | CS11 | 21.15% | CS16D | 57.41%
500827 | Invergarry RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-10-28 | 2017-03-23 | 2017-06-02 | 2017-12-31 | 2018-06-30 | Highland | 0 | 3000 | -689.01 | 10352.03 | 11494.28 | 0 | 0 | 24157.3 | 0 | 24157.3 | 21335.14 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.36
502314 | Invergowrie Burnside Road SPS and Tayport WWTW River Modelling | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-10-31 | 2017-05-31 | 2017-07-27 | 2018-06-29 | 2018-06-29 | All East Unitary Authorities | 0 | 0 | 4602.93 | 96498 | 36524.58 | 0 | 0 | 137625.51 | 0 | 137625.51 | 0 | [6 empty] | CM_WWI | 100%
45811 | Invergowrie SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-12-05 | 2012-02-13 | 2012-08-01 | 2012-08-21 | Perth and Kinross | 171036.3 | 14.5 | 0 | 0 | 0 | 0 | 0 | 14.5 | 0 | 171050.8 | 0 | [6 empty] | WQ01C | 100%
400720 | Inverkeilor WWTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2012-01-23 | 2012-06-04 | 2014-12-04 | 2014-12-04 | Angus | 734267 | -15237.57 | 5654.79 | 8071.21 | 1342.72 | 0 | 157.28 | -11.57 | 0 | 734255.43 | 136478.56 | [6 empty] | SG1 | 100%
402607 | Inverkeilor WwTW Access Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2013-01-22 | 2013-04-08 | 2013-09-05 |  | All East Unitary Authorities | 110195.31 | -1083.36 | 0 | 0 | 0 | 0 | 0 | -1083.36 | 0 | 109111.95 | 0 | [6 empty] | CM_M&G | 100%
400060 | Inverkeithing Preston Crescent SPS Refurb SPS001587 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2012-02-06 | 2012-04-24 | 2013-03-28 |  | Fife | 651072.18 | 46529.52 | -3.81 | 0 | 0 | 0 | 0 | 46525.71 | 0 | 697597.89 | 0 | [6 empty] | CM_WWNI | 100%
502879 | Invermoriston WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-05-09 | 2019-05-09 | 2019-05-09 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 21341.97 | 1526.48 | -20968.36 | -0.01 | 1900.08 | 0 | 1900.08 | 136478.56 | [6 empty] | WG1 | 100%
500218 | Inverness - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS2 | 2015-03-23 | 2019-10-02 | 2020-07-06 | 2021-03-31 | 2022-05-13 | Highland | 0 | 10902 | -2352.37 | 47394.09 | 53357.84 | 167041.12 | 1317687.89 | 1594030.57 | 230954.97 | 1824985.54 | 1519613.06 | [6 empty] | DW5FS | 8.988% | DW5 | 91.01% | bar: Regulatory Outputs OMG-02
402060 | Inverness Campus Link Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2011-06-07 | 2011-12-23 | 2011-12-23 | 2013-10-01 |  | Highland | 86314 | -20403.72 | 0 | 0 | 0 | 0 | 0 | -20403.72 | 0 | 65910.28 | 0 | [6 empty] | WG5 | 100%
500150 | Inverness DOA (DOA002372) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS7 | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-11-13 | 2020-01-31 | Highland | 0 | 36582 | 113398 | 350757.87 | 185040.98 | 44805.26 | 0.01 | 730584.12 | 0 | 730584.12 | 277404.61 | [6 empty] | CS16D | 100%
501623 | Inverness Opa Area- Rail Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-08-23 | 2027-06-23 | 2027-09-16 | 2028-03-10 | 2028-06-12 | Highland | 0 | 0 | 5868.58 | 7634.71 | 8.84 | 0 | 0 | 13512.13 | 0 | 13512.13 | 0 | [6 empty] | CM_WSI | 100%
500828 | Inverness RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-07-25 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 5225.07 | 2774.93 | 0 | -147.16 | 0 | 0 | 7852.84 | 0 | 7852.84 | 240041.94 | [6 empty] | DW5FS | 100%
503167 | Inverness RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2015-03-31 | 2020-09-14 | 2020-10-16 | 2021-05-20 | 2021-08-20 | Highland | 0 | 0 | 0 | 0 | 20031.71 | 0 | 0 | 20031.71 | 0 | 20031.71 | 759806.53 | [6 empty] | DW5FS | 100%
403559 | Inverness Slackbuie Link Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-08-27 | 2014-09-18 | 2014-10-07 | 2015-09-09 | 2015-09-09 | Highland | 216238 | 18838.91 | 0 | 0 | 0 | 0 | 0 | 18838.91 | 0 | 235076.91 | 0 | [6 empty] | WG5 | 100%
503247 | Inverness WOA - Inverness Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-05 | 2027-06-25 | 2027-08-09 | 2027-11-29 | 2027-12-03 | Highland | 0 | 0 | 0 | 0 | 54669.37 | 15286.57 | 0.02 | 69955.96 | 959444.05 | 1029400.01 | 0 | [6 empty] | CM_WSI | 100%
500735 | Inverness WOA - Urchany & Raitloan SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS4 | 2015-08-26 | 2018-03-01 | 2018-03-19 | 2020-03-12 | 2020-06-26 | Highland | 0 | 125135 | 127146.1 | 852359.46 | 2195642.07 | 555395.4 | 12930.02 | 3868608.05 | 22164.95 | 3890773 | 466277.79 |  |  |  |  | 35340.64 |  | DW25T | 100% | bar: Regulatory Outputs OMG-05
502784 | Inverness WOA- Scorguie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-28 | 2028-10-19 | 2029-02-06 | 2030-01-28 | 2030-04-30 | Highland | 0 | 0 | 0 | 30753.52 | 18434.53 | 341.1 | 0 | 49529.15 | 1150470.86 | 1200000.01 | 0 | [6 empty] | CM_WSNI | 100%
502632 | Inverness WTW- PLC s replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-10-30 | 2020-12-21 | 2021-03-31 | 2022-03-30 | 2022-06-30 | Highland | 0 | 0 | 0 | 19096.2 | 46860.77 | 91584.61 | 731658.41 | 889199.99 | 1200800.02 | 2090000.01 | 0 | [6 empty] | CM_WSNI | 100%
504018 | Inverness WTW Regulatory sample tap replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-05 | 2020-08-03 | 2020-11-11 | 2020-12-09 | Highland | 0 | 0 | 0 | 0 | 0 | 2500 | 20133.12 | 22633.12 | 0 | 22633.12 | 0 | [6 empty] | CM_WSNI | 100%
401919 | Inversnaid WwTW SAF Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-05-11 | 2013-06-26 | 2013-06-26 | 2014-06-24 |  | Stirling | 259474.94 | 97.06 | 0 | 0 | 0 | 0 | -97.06 | 0 | 0 | 259474.94 | 0 | [6 empty] | CM_WWNI | 100%
45010 | Inverurie New STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-11-24 | 2015-08-21 | 2015-02-06 | 2015-02-06 | 2015-02-06 | Aberdeenshire | 841736.06 | 472.83 | 0 | 0 | 0 | 0 | -0.01 | 472.82 | 0 | 842208.88 | 0 | [6 empty] | EC01A | 100%
545010 | Inverurie New STW Upgrade TR From 045010 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS1 | 2008-11-24 | 2016-09-28 | 2016-11-04 | 2017-11-20 | 2018-02-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310409.7 | [6 empty] | EC01A | 5% | CM_WWNI | 95%
501174 | Inverurie STC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-06-23 | 2018-03-20 | 2018-03-20 | 2017-05-25 | 2017-05-25 | Aberdeenshire | 0 | 0 | 29755.88 | -7554.89 | 0 | 0 | 0 | 22200.99 | 0 | 22200.99 | 0 | [6 empty] | CM_WWNI | 100%
30394 | Inverurie STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2015-08-21 | 2015-02-06 | 2015-02-06 | 2015-02-06 | Aberdeenshire | 2014773.91 | -8704.1 | 0 | 0 | 0 | 0 | 0 | -8704.1 | 0 | 2006069.81 | 0 | [6 empty] | EC01A | 100%
403935 | Inverurie STW Upgrade (Transfer from 30394 and 45010) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2009-06-05 | 2017-02-23 | 2017-04-03 | 2020-03-31 | 2020-03-31 | Aberdeenshire | 147386 | 746158 | 1651782.48 | 8299679.17 | 9718823.12 | 2470102.27 | 600991.89 | 23487536.93 | 52484.8 | 23687407.73 | 2191117.25 | [6 empty] | SG1 | 19% | CM_WWNI | 35% | EC01A | 46%
530394 | Inverurie STW Upgrade TR From 030394 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS1 | 2009-06-05 | 2016-09-28 | 2016-11-04 | 2017-11-20 | 2018-02-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5663.96 | [6 empty] | EC01A | 3% | EC04A | 34% | CM_WWNI | 63%
502424 | Inverurie Uryside Phase 2 SR | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW0 | 2020-10-19 | 2021-09-13 | 2022-01-17 | 2023-04-05 | 2023-07-05 | Aberdeenshire | 0 | 0 | 39204.71 | 6913.69 | 11423.74 | 18103.09 | 6361.11 | 82006.34 | 4003993.68 | 4086000.02 | 470181.23 | [6 empty] | WG5 | 100%
502323 | Inverurie Uryside Phase 2 SR - Developer design | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2021-04-07 | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-04-21 | Aberdeenshire | 0 | 0 | 85448.37 | -31.5 | 2314.58 | -1989.88 | 0 | 85741.57 | 0 | 85741.57 | 470181.23 | [6 empty] | WG5 | 100%
503504 | Investigation into Helensburgh trunk main | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-05-03 | 2022-02-14 | 2022-04-22 | 2022-09-06 | 2022-12-07 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 9460.12 | 9460.12 | 190539.88 | 200000 | 0 | [6 empty] | CM_M&G | 100%
402648 | IPM Commercial Support | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2012-03-29 | 2012-03-29 | 2012-04-02 | 2016-10-26 |  | Scottish Water Wide | 230600.53 | 100000.47 | -46213.31 | 0 | 0 | 0 | 0 | 53787.16 | 0 | 284387.69 | 0 | [6 empty] | WSI | 4.826% | WWNI | 4.826% | WWI | 45.17% | WSNI | 45.17%
503084 | IR18 - 59032 - Dry Weather Flow Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-07-09 | 2020-11-02 | 2020-11-02 | 2021-12-20 | 2022-03-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 27388 | 545600 | 572988 | 701012 | 1274000 | 649102.99 | [6 empty] | EC10E | 100%
503094 | IR18 - 59034 - Legacy sludge requirement at Operational Sites | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWD | Sludge | MS3 | 2018-10-30 | 2020-03-12 | 2020-03-31 | 2020-12-31 | 2021-01-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 8431.2 | 26528.5 | 125040.27 | 159999.97 | 0 | 159999.97 | 429303.62 | [6 empty] | LA01_S | 100% | bar: Regulatory Outputs OMG-23
503136 | IR18 - 59044 - WFD - Priority Substances Intervention Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-10-20 | 2023-02-28 | 2023-06-22 | 2024-02-07 | 2024-05-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 53568.55 | 47300.93 | 100869.48 | 257130.61 | 358000.09 | 101413.84 | [6 empty] | EC23B_ID | 100%
503137 | IR18 - 59048 - WFD - WwTW Intervention Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-06-17 | 2022-11-23 | 2023-03-21 | 2023-11-06 | 2024-02-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 20233.34 | 15781.12 | 36014.46 | 727985.53 | 763999.99 | 216349.53 | [6 empty] | EC10A_ID | 100%
503140 | IR18 - 59061 - Event and Duration Monitoring Intervention Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | GW1 | 2022-08-25 | 2022-09-23 | 2022-09-23 | 2023-09-28 | 2023-09-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 86500 | 11065.07 | -2023.82 | 95541.25 | 0 | 95541.25 | 226231.33 | [6 empty] | CS29_ID | 100%
503124 | IR18 - 59066 - Glasgow Sludge Main Resilience Study | Q&S4 | Improving the customer experience | Customer Experience Studies |  |  | Wastewater |  | SWMD | Customer Experience Studies | MS7 | 2018-09-28 | 2019-03-25 | 2019-03-27 | 2019-05-31 | 2019-08-31 | Glasgow City | 0 | 0 | 0 | 0 | 134124.04 | 41678.26 | 0 | 175802.3 | 0 | 175802.3 | 221290.52 | [6 empty] | CS16SR | 100% | bar: Regulatory Outputs OMG-23
503077 | IR18 - 59076 - CAS Compliance Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2018-10-31 | 2020-05-11 | 2020-05-18 | 2024-09-16 | 2024-09-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 15583 | 214781.04 | 700102.02 | 930466.06 | 3269534.01 | 4200000.07 | 1181691.4 | [6 empty] | WQ01_S | 100%
503083 | IR18 - 59077 - Inner Clyde Estuary Modelling | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2018-07-13 | 2019-06-26 | 2019-07-08 | 2021-02-10 | 2021-05-13 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 72831.78 | 1239340.12 | 244928.94 | 1557100.84 | 88781 | 1645881.84 | 1272420.52 | [6 empty] | EC01D | 50% | EC10E | 50% | bar: Regulatory Outputs OMG-23
503400 | IR18 - Barra - Distribution Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2019-03-27 | 2019-09-30 | 2020-01-06 | 2020-03-31 | 2021-10-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 9600 | 119492.35 | 68589.65 | 197682 | 0 | 197682 | 231573.17 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 60
503126 | IR18 - Boardhouse WTW Inlet Screen | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-12-20 | 2021-10-11 | 2022-01-07 | 2022-07-07 | 2022-10-05 | Orkney Islands | 0 | 0 | 0 | 0 | 55998.21 | 36414.16 | -22128.65 | 70283.72 | 424360.26 | 494643.98 | 693889.29 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
503139 | IR18 - Event and Duration Monitoring Phase 1 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2018-11-21 | 2020-04-22 | 2020-04-22 | 2020-04-22 | 2020-04-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 5050.47 | 215.3 | 0 | 5265.77 | 0 | 5265.77 | 284605.17 | [6 empty] | CS29 | 100%
503178 | IR18 - External Flooding Carstairs | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-06-30 | 2021-04-08 | 2021-07-05 | 2022-01-31 | 2022-05-03 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 53393.33 | 53393.33 | 354606.69 | 408000.02 | 472726.74 | [6 empty] | CS15 | 100%
503177 | IR18 - External Flooding Clarkston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2019-03-05 | 2020-03-30 | 2020-06-19 | 2020-12-09 | 2021-03-25 | Glasgow City | 0 | 0 | 0 | 0 | 12571.94 | 189244.06 | 979243.51 | 1181059.51 | 10623.32 | 1191682.83 | 724670.43 | [6 empty] | CS15 | 100%
503334 | IR18 - Intelligent Water Networks - Improvements to Interruptions to Supply and Low Pressure Managem | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWD | Pressure | GW0 | 2021-05-31 | 2022-01-17 | 2022-03-14 | 2023-11-27 | 2024-02-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 97394.8 | -1244.8 | 96150 | 3349850 | 3446000 | 130947.15 | [6 empty] | CS1 | 100%
503176 | IR18 - Internal Sewer Flooding - SR21 cost surety (holding line) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-05-07 | 2021-06-28 | 2021-07-07 | 2021-08-18 | 2021-08-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 793.87 | -793.87 | 0 | 4368000 | 4368000 | 4391785.23 | [6 empty] | CS11A | 100%
503179 | IR18 - Interventions from Aberdeen ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-05-07 | 2022-11-03 | 2022-12-30 | 2023-03-23 | 2024-03-21 | Aberdeen City | 0 | 0 | 0 | 0 | 7000 | 26175.21 | 214824.79 | 248000 | 307000 | 555000 | 995091.55 | [6 empty] | CS16D_ID | 100%
503184 | IR18 - Interventions from Edinburgh ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-05-07 | 2022-11-03 | 2022-12-30 | 2023-03-23 | 2024-03-21 | City of Edinburgh | 0 | 0 | 0 | 0 | 7000 | 32651.32 | 200698.68 | 240350 | 314650 | 555000 | 559320.1 | [6 empty] | CS16D_ID | 100%
503182 | IR18 - Interventions from Falkirk ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-07-07 | 2023-01-03 | 2023-03-02 | 2023-05-24 | 2024-05-22 | Falkirk | 0 | 0 | 0 | 0 | 7000 | 9733.45 | 38253.23 | 54986.68 | 500013.3 | 554999.98 | 559320.1 | [6 empty] | CS16D_ID | 100%
503181 | IR18 - Interventions from Meadowhead ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-07-01 | 2021-12-22 | 2022-02-17 | 2022-05-17 | 2022-08-17 | North Ayrshire | 0 | 0 | 0 | 0 | 7076.05 | 10797.67 | 11641.23 | 29514.95 | 525485.04 | 554999.99 | 559320.1 | [6 empty] | CS16D_ID | 100%
503183 | IR18 - Interventions from SR15 ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-11-04 | 2023-05-03 | 2023-06-29 | 2023-09-20 | 2024-09-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 26168.22 | 21310.19 | 0 | 47478.41 | 1814521.59 | 1862000 | 423578.06 | [6 empty] | CS16D_ID | 100%
503180 | IR18 - Interventions from Tayside ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-03-11 | 2022-09-07 | 2022-11-03 | 2023-01-25 | 2024-01-24 | Dundee City | 0 | 0 | 0 | 0 | 7076.05 | 25856.48 | 9156.48 | 42089.01 | 512910.99 | 555000 | 559320.1 | [6 empty] | CS16D_ID | 100%
503249 | IR18 Investigate Future Changes in the Occurrance of Algal Blooms | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-06-05 | 2019-09-18 | 2019-09-18 | 2020-12-21 | 2021-03-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 4396.71 | 31713.32 | 97497.57 | 133607.6 | 3392.4 | 137000 | 158480.25 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503332 | IR18 - Mannofield WTW - Raw Water Blending & Inlet Improvements | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW1 | 2020-06-25 | 2021-11-08 | 2022-04-07 | 2023-03-22 | 2023-06-22 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 60310.05 | 44537.71 | 104847.76 | 349633.25 | 454481.01 | 1295905.08 | [6 empty] | DW23 | 100%
503185 | IR18 - Masterplanning for Aberdeen ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2020-09-02 | 2020-11-20 | Aberdeen City | 0 | 0 | 0 | 0 | 1478.77 | 11614.69 | 20532.55 | 33626.01 | 0 | 33626.01 | 110645.26 | [6 empty] | CS27 | 100%
503187 | IR18 - Masterplanning for Edinburgh ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2020-10-06 | 2020-12-24 | City of Edinburgh | 0 | 0 | 0 | 0 | 1478.77 | 72381.75 | 30139.46 | 103999.98 | 0 | 103999.98 | 110645.26 | [6 empty] | CS27 | 100%
503188 | IR18 - Masterplanning for Falkirk ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2020-09-02 | 2020-11-20 | Falkirk | 0 | 0 | 0 | 0 | 1478.77 | 40208.33 | 21312.9 | 63000 | 0 | 63000 | 110645.26 | [6 empty] | CS27 | 100%
503189 | IR18 - Masterplanning for Meadowhead ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2020-09-02 | 2020-11-20 | North Ayrshire | 0 | 0 | 0 | 0 | 1478.77 | 44029 | 21492.26 | 67000.03 | 0 | 67000.03 | 110645.26 | [6 empty] | CS27 | 100%
503190 | IR18 - Masterplanning for SR15 ICS Catchments | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2020-09-02 | 2020-11-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2721.5 | 22629.35 | 2649.15 | 28000 | 0 | 28000 | 87023.55 | [6 empty] | CS27 | 100%
503186 | IR18 - Masterplanning for Tayside ICS | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2020-09-02 | 2020-11-20 | Dundee City | 0 | 0 | 0 | 0 | 2744.29 | 38546.61 | 30708.81 | 71999.71 | 0 | 71999.71 | 110645.26 | [6 empty] | CS27 | 100%
503191 | IR18 - Options for Flood Risk Reduction (Stormwater Strategy) | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2019-07-11 | 2019-07-11 | 2019-08-28 | 2021-07-09 | 2021-08-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 230991.04 | 265921.11 | 496912.15 | 1644087.84 | 2140999.99 | 2212905.25 | [6 empty] | CS16D_ID | 100%
503246 | IR18 - Sewer Monitoring Demonstrator (Intelligent Networks) | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS1 | 2018-07-30 | 2020-06-15 | 2020-08-31 | 2021-11-24 | 2022-02-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 58372.9 | 297644.08 | 110529.63 | 466546.61 | 53453.46 | 520000.07 | 827161.57 | [6 empty] | EC01M | 100%
503237 | IR18 THM- TOC Catchment Manangement - Forehill | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-06-21 | 2019-06-28 | 2019-06-28 | 2021-02-28 | 2021-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 16302.93 | 240871.55 | 519825.53 | 777000.01 | 0 | 777000.01 | 250727.71 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
503248 | IR18 THM- TOC Catchment Manangement Study -Pateshill | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-05 | 2019-01-08 | 2019-04-26 | 2020-11-24 | 2021-02-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 24347.35 | 49255.68 | 102025.6 | 175628.63 | 4371.38 | 180000.01 | 208031.69 | [6 empty] | DW25PS | 100%
503129 | IR18 - WFD - Priority Substances Study (59059) | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-09-26 | 2021-04-01 | 2021-07-22 | 2022-03-10 | 2022-06-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 14212.01 | 32987.97 | 47199.98 | 310800.01 | 357999.99 | 188256.53 | [6 empty] | EC23A | 100%
502648 | IR18 Allowance - Ardrishaig WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2018-03-30 | 2020-01-31 | 2020-03-16 | 2021-11-30 | 2023-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 45494.62 | 116467.18 | 1290176.2 | 5092449.79 | 6544587.79 | 255734.21 | 6800322 | 3246734.22 | [6 empty] | DW2 | 100% | bar: Regulatory Outputs OMG-01
502652 | IR18 Allowance - Barra WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2018-06-30 | 2020-09-21 | 2020-12-15 | 2021-02-28 | 2021-09-20 | Na H-Eileanan an Iar | 0 | 0 | 0 | 7268.99 | 4177.09 | 2759.57 | 304567.33 | 318772.98 | 91636.42 | 410409.4 | 483284.82 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
502386 | IR18 Allowance - Black Esk - Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-05-17 | 2019-05-17 | Dumfries and Galloway | 0 | 0 | 17700 | 20300 | -8718.2 | 51.97 | -51.97 | 29281.8 | 0 | 29281.8 | 26377.73 | [6 empty] | WR2A | 100%
502411 | IR18 Allowance - Caddon Water Intake - Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWMD | WFD | MS0 | 2018-07-25 | 2022-04-20 | 2022-06-21 | 2022-09-19 | 2022-12-16 | Scottish Borders | 0 | 0 | 20900 | 24841.9 | 27530.2 | 28131.08 | 112147.61 | 213550.79 | 233227.75 | 446778.54 | 457430.11 | [6 empty] | WR2A_ID | 100%
502381 | IR18 Allowance - Corsehouse - Abstraction Improvement | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-05-09 | 2019-05-09 | South Ayrshire | 0 | 0 | 7900 | 3721.81 | 0 | 0 | 0 | 11621.81 | 0 | 11621.81 | 131990.95 | [6 empty] | WR1 | 100%
502563 | IR18 Allowance - Dye Water Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWMD | WFD | MS2 | 2018-10-26 | 2020-03-24 | 2021-07-15 | 2022-01-13 | 2022-04-14 | East Lothian | 0 | 0 | 15550 | 5069.87 | 8271.7 | 48290.73 | 87591.95 | 164774.25 | 65594.75 | 230369 | 26377.73 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
502382 | IR18 Allowance - East Berwickshire - Abstraction Improvement | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWMD | WFD | MS2 | 2019-01-31 | 2020-03-27 | 2021-02-12 | 2021-06-30 | 2021-09-30 | Scottish Borders | 0 | 0 | 7900 | 1888.82 | 7025.81 | 36284.61 | 222973.01 | 276072.25 | 167404.19 | 443476.44 | 385236.73 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
502220 | IR18 Allowance - Edgehead Septic Tank | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | WWINF | WFD | MS1 | 2017-11-30 | 2020-11-02 | 2021-04-12 | 2021-12-08 | 2022-03-24 | Midlothian | 0 | 0 | 82593.19 | 46293.4 | 222374.46 | 295294.95 | 118718.59 | 765274.59 | 1737437.72 | 2502712.31 | 596457.04 |  |  |  |  | 10000 |  | EC10A | 100% | bar: Regulatory Outputs OMG-20
502383 | IR18 Allowance - Fife - Abstraction Improvement | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWMD | WFD | MS0 | 2019-03-11 | 2020-12-07 | 2021-04-14 | 2021-08-31 | 2021-11-30 | Fife | 0 | 0 | 10779 | 2862.6 | 11358.4 | 6117.07 | 40293.77 | 71410.84 | 135589.24 | 207000.08 | 725893.39 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
502380 | IR18 Allowance - Forth Valley - Abstraction Improvement | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS3 | 2019-02-26 | 2019-03-25 | 2019-03-25 | 2020-08-31 | 2020-11-30 | Perth and Kinross | 0 | 0 | 4000 | 2450.25 | 4436.13 | 24196.68 | 24916.94 | 60000 | 0 | 60000 | 213269.29 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
502384 | IR18 Allowance - Glenleith - Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-05-09 | 2019-05-09 | Dumfries and Galloway | 0 | 0 | 2274 | 17726 | 0 | -15498.05 | 0 | 4501.95 | 0 | 4501.95 | 26377.73 | [6 empty] | WR2A | 100%
502385 | IR18 Allowance - Loch Venachar - Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWMD | WFD | MS2 | 2018-09-28 | 2020-03-27 | 2020-11-06 | 2020-11-30 | 2020-12-31 | Stirling | 0 | 0 | 7950 | 1143.4 | 5673.59 | 39992.73 | 30885.24 | 85644.96 | 1355.04 | 87000 | 158341.74 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
502213 | IR18 Allowance - Longriggend WWTW | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS7 | 2017-11-14 | 2019-06-21 | 2019-06-21 | 2019-04-03 | 2019-04-03 | North Lanarkshire | 0 | 0 | 128544.83 | 56371.51 | 14822.43 | 525.04 | -0.35 | 200263.46 | 0 | 200263.46 | 213455.65 | [6 empty] | EC10A | 100%
503491 | IR18 Allowance - Longriggend WWTW (recycled) | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS0 | 2017-11-14 | 2022-09-22 | 2023-01-25 | 2024-04-30 | 2024-07-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 45048.56 | 25609.33 | 65737.93 | 136395.82 | 2106604.14 | 2242999.96 | 213455.65 | [6 empty] | EC10A | 100% | bar: Regulatory Outputs OMG-20
502212 | IR18 Allowance - Newton Septic Tank | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS0 | 2017-11-30 | 2021-02-22 | 2021-08-03 | 2022-03-10 | 2022-06-16 | City of Edinburgh | 0 | 0 | 65632.35 | 33482.65 | 78708.52 | 62650.95 | 154527.79 | 395002.26 | 3391087.64 | 3786089.9 | 1046890.41 | [6 empty] | EC10A | 100% | bar: Regulatory Outputs OMG-20
502650 | IR18 Allowance - Tarbert WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2017-09-15 | 2019-09-30 | 2019-10-29 | 2021-11-30 | 2023-02-28 | Argyll and Bute-North Argyll | 0 | 0 | 27062.79 | 136518.6 | 507784.07 | 1947896.54 | 2705890 | 5325152 | 133548 | 5458700 | 3453376.49 | [6 empty] | DW2 | 100% | bar: Regulatory Outputs OMG-01
502731 | IR18 Allowance - Turriff WRZ Abstraction Impact Monitoring | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS5 | 2018-07-02 | 2020-05-25 | 2020-05-25 | 2019-08-31 | 2019-08-31 | Aberdeenshire | 0 | 0 | 0 | 9566.31 | 5123.95 | 59489.74 | 153820 | 228000 | 0 | 228000 | 131990.95 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
503113 | IR18 Blairlinnans & Milngavie Connectivity | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2020-09-29 | 2022-08-12 | 2022-10-31 | 2023-06-02 | 2023-09-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 206449.82 | 75688.2 | 20222.19 | 302360.21 | 389639.86 | 692000.07 | 801392.57 | [6 empty] | CS16WRID | 100%
502326 | IR18 CAS Compliance at WWTW and Network Assets | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWD | Compliance Assessment Scheme | MS7 | 2019-05-29 | 2019-05-29 | 2019-05-29 | 2019-05-09 | 2019-05-09 | Scottish Water Wide | 0 | 0 | 140980.02 | 63551.84 | -56151.84 | 715.14 | -715.14 | 148380.02 | 0 | 148380.02 | 717445.56 | [6 empty] | WQ01D | 30.43% | WQ01E | 69.57%
502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-08 | 2021-10-11 | Scottish Water Wide | 0 | 0 | 0 | 2604.35 | 72751.05 | 159070.81 | 405806 | 640232.21 | 47794.3 | 688026.51 | 406153.51 | [6 empty] | WQ01E | 100%
502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2022-04-28 | 2022-08-01 | Scottish Water Wide | 0 | 0 | 0 | 3596.88 | 76342.3 | 318056.23 | 375988.34 | 773983.75 | 256999.73 | 1030983.48 | 406153.51 | [6 empty] | WQ01E | 100%
502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2022-01-27 | 2022-05-02 | Scottish Water Wide | 0 | 0 | 0 | 3781.74 | 75752.48 | 245258.29 | 523106.85 | 847899.36 | 258876.68 | 1106776.04 | 311292.06 | [6 empty] | WQ01D | 100%
502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS3 | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2022-01-12 | 2022-04-19 | Scottish Water Wide | 0 | 0 | 0 | 764.42 | 71108.7 | 200796.79 | 295258.23 | 567928.14 | 144791.76 | 712719.9 | 717445.56 | [6 empty] | WQ01D | 14.04% | WQ01E | 85.96%
502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-05-26 | 2021-08-27 | Scottish Water Wide | 0 | 0 | 0 | 1330.51 | 37838.4 | 93934.69 | 216461.41 | 349565.01 | 11289 | 360854.01 | 311292.06 | [6 empty] | WQ01D | 100%
503118 | IR18 Cyber Security Governance Line | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-08-23 | 2019-02-27 | 2019-02-27 | 2021-01-21 | 2021-01-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 154907.52 | 192760.91 | 224860.76 | 572529.19 | 0 | 572529.19 | 2117982 | [6 empty] | CS24S | 50% | CS24W | 50%
503434 | IR18 Daer CWT | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS2 | 2015-10-30 | 2019-10-01 | 2020-05-04 | 2021-08-31 | 2021-11-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 17126 | 221999 | 0 | 239125 | 2440864.01 | 2679989.01 | 645915.7 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503243 | IR18 Daer WTW Bacti Risk Reduction Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-05 | 2019-03-12 | 2019-03-18 | 2020-06-01 | 2020-08-03 | South Lanarkshire | 0 | 0 | 0 | 0 | 25836.58 | 67171.8 | 66642.63 | 159651.01 | 0 | 159651.01 | 214795.96 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503430 | IR18 Disinfection Improvements - Minor Upgrades | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW0 | 2020-07-06 | 2020-07-20 | 2020-09-30 | 2021-09-30 | 2021-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 21286.05 | 35356.56 | 1208166.88 | 1264809.49 | 769190.56 | 2034000.05 | 1149921.61 | [6 empty] | DW25P | 100%
503437 | IR18 Drinking Water Quality Provision of Sampling Points | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW0 | 2020-05-12 | 2022-07-29 | 2022-12-01 | 2023-09-01 | 2023-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 22596.28 | 23957.89 | 109253.65 | 155807.82 | 2003192.21 | 2159000.03 | 38383.47 | [6 empty] | DW25PS | 47% | DW25TS | 53%
503175 | IR18- External sewer Flooding SR21 Cost surety | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-05-07 | 2021-06-28 | 2021-07-07 | 2021-08-18 | 2021-08-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 460465.12 | 628875.95 | 1089341.07 | 10658.91 | 1099999.98 | 1157865.87 | [6 empty] | CS15E | 100%
503252 | IR18 Impact of Future Drinking Water Directive Changes - Sampling Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-15 | 2019-06-27 | 2019-07-01 | 2023-08-04 | 2023-11-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 15709.22 | 112563.61 | 177797.66 | 306070.49 | 446929.47 | 752999.96 | 176850.45 | [6 empty] | DW25PS | 100%
503103 | IR18 Inverness and Nairn - Growth and Resilience | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS0 | 2018-06-26 | 2020-07-13 | 2020-07-13 | 2021-08-10 | 2021-11-11 | Highland | 0 | 0 | 0 | 0 | 470529.39 | 1253970.91 | 12629896.13 | 14354396.43 | 10170296.72 | 24524693.15 | 5380159.47 | [6 empty] | CS16WR | 20% | WG4 | 20% | WG1 | 60%
503236 | IR18- Investigation of Long Term DOC increases in Drinking Water Catchments | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-14 | 2018-10-24 | 2019-04-26 | 2020-11-30 | 2021-03-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 126203.84 | 79437.79 | 30375.14 | 236016.77 | 2431.27 | 238448.04 | 315166.55 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
502905 | IR18 Kirk Yetholm STW Quality Enhancement | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | GW0 | 2022-02-28 | 2023-07-17 | 2023-11-08 | 2024-10-28 | 2025-01-28 | Scottish Borders | 0 | 0 | 0 | 29815.23 | 12454.62 | 38945.91 | 77882.07 | 159097.83 | 2035902.12 | 2194999.95 | 46501.53 | [6 empty] | EC01A | 100%
503505 | IR18 Larchfield WOA lead reduction | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW1 | 2020-05-05 | 2021-05-24 | 2021-08-26 | 2022-03-09 | 2022-06-09 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 11252.09 | 85693.57 | 294163.53 | 391109.19 | 2192486.65 | 2583595.84 | 361769.97 | [6 empty] | DW1A | 100%
503121 | IR18 Legacy Infrastructure | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-11-21 | 2020-01-31 | 2020-01-31 | 2021-01-29 | 2021-03-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 551169.33 | 2726448.8 | 2214617.44 | 5492235.57 | 0 | 5492235.57 | 2117982 | [6 empty] | CS24S | 50% | CS24W | 50%
503128 | IR18 Legacy Sludge - Intervention Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS5 | 2019-07-17 | 2019-05-31 | 2019-05-20 | 2019-07-11 | 2019-07-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 387264.11 | 61818.07 | 917.82 | 450000 | 0 | 450000 | 1936292.09 | [6 empty] | LA01_ID | 100%
503120 | IR18 Network Segregation Datacentre | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS1 | 2018-11-12 | 2020-07-13 | 2020-07-13 | 2021-01-29 | 2021-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 50434.58 | 139024.48 | 334558.5 | 524017.56 | 0 | 524017.56 | 2117982 | [6 empty] | CS24S | 50% | CS24W | 50%
503119 | IR18 Network Segregation Treatment | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS1 | 2018-11-12 | 2020-07-13 | 2020-07-13 | 2021-01-29 | 2021-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 42897.58 | 305055.41 | 3412046.95 | 3759999.94 | 0 | 3759999.94 | 2117982 | [6 empty] | CS24S | 50% | CS24W | 50%
503204 | IR18 Operational Technology | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-12-12 | 2018-12-12 | 2018-12-12 | 2021-01-21 | 2021-01-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 263401.77 | 229477.19 | 507099.86 | 999978.82 | 0 | 999978.82 | 2117982 | [6 empty] | CS24S | 50% | CS24W | 50%
503052 | IR18 Pateshill WTW Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2020-02-28 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 1643.29 | 20667.1 | 70334.92 | 53354.69 | 146000 | 0 | 146000 | 168058.32 | [6 empty] | DW25PS | 100%
503109 | IR18- Rawburn WTW Nitrite Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS4 | 2018-03-26 | 2018-06-26 | 2018-08-09 | 2020-02-26 | 2020-06-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 29227.36 | 63730.78 | 52041.86 | 145000 | 0 | 145000 | 167890.55 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503114 | IR18 Resilience - Glencorse and East Lothian Connectivity | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2020-11-24 | 2021-12-06 | 2022-02-22 | 2022-11-29 | 2023-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 214376.96 | 175905.38 | 176951.6 | 567233.94 | 674766.08 | 1242000.02 | 90216.65 | [6 empty] | CS16WRID | 100%
503115 | IR18 Resilience - Glenlaterrach to Badentinnan Connectivity | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2021-02-23 | 2022-05-06 | 2022-07-27 | 2023-08-25 | 2023-11-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 375169.32 | 138764.68 | 388533.17 | 902467.17 | 1332532.82 | 2234999.99 | 91156.46 | [6 empty] | CS16WRID | 100%
503117 | IR18 Resilience- Pan Scotland Resilience - Interim Risk Reduction Development | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MSU | 2021-02-23 | 2021-06-21 | 2021-09-09 | 2022-04-06 | 2022-07-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 85195.93 | 59493.06 | 82177.45 | 226866.44 | 251133.57 | 478000.01 | 553226.31 | [6 empty] | CS16WRID | 100%
503116 | IR18 Resilience - Perth and Turrett Connectivity | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-01-24 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 215768.99 | 0 | 0.01 | 215769 | 0 | 215769 | 90216.65 | [6 empty] | CS16WRID | 100%
503051 | IR18 Roberton WTW Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2018-02-27 | 2018-06-05 | 2018-08-06 | 2020-02-26 | 2020-06-29 | Scottish Water Wide | 0 | 0 | 0 | 1476.93 | 64523.08 | 26042.44 | 53957.57 | 146000.02 | 0 | 146000.02 | 168058.32 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503291 | IR18 Security Operations Tools | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2019-02-06 | 2020-02-12 | 2020-02-12 | 2020-08-10 | 2020-08-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 67237.33 | 733703.66 | 894299.63 | 1695240.62 | 0 | 1695240.62 | 2117982 |  |  |  |  | 316881 |  | CS24S | 50% | CS24W | 50%
503241 | IR18 Single Supplies (Non Regulatory Zones) Improvement Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-21 | 2018-10-31 | 2019-04-01 | 2021-02-11 | 2021-04-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 134215.51 | 53519.96 | 1441530.19 | 1629265.66 | 25734.32 | 1654999.98 | 1916603.36 | [6 empty] | DW25PS | 100%
503048 | IR18 Study into Lead Concentrations at Schools and Nurseries | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-02-20 | 2018-09-03 | 2019-02-20 | 2021-02-15 | 2021-04-16 | Scottish Water Wide | 0 | 0 | 0 | 5926.68 | 78568.95 | 239038.41 | 248806.14 | 572340.18 | 7317.82 | 579658 | 231573.17 | [6 empty] | DW25PS | 100%
503110 | IR18 Tighnabruaich Lead Comms Investigation and Replacement | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-03-26 | 2018-10-16 | 2018-10-25 | 2020-12-24 | 2021-02-26 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 30000 | 122336.38 | 86663.63 | 239000.01 | 0 | 239000.01 | 276201.26 | [6 empty] | DW25DS | 100% | bar: Regulatory Outputs OMG-47
503195 | IR18 Water Quality Improvement - Camps RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2018-12-20 | 2019-10-01 | 2019-09-30 | 2021-05-31 | 2022-02-28 | South Lanarkshire | 0 | 0 | 0 | 0 | 267807 | 602957.58 | 1289273.27 | 2160037.85 | 25167 | 2185204.85 | 0 | [6 empty] | DW5FS | 46.79% | DW5MR | 53.21% | [16 empty] | Regulatory Outputs OMG-06: 278.1064
503196 | IR18 Water Quality Improvement - Corsehouse RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2018-09-17 | 2018-12-20 | 2019-03-28 | 2019-12-03 | 2020-12-31 | East Ayrshire | 0 | 0 | 0 | 0 | 223050.53 | 305780.54 | -8392.2 | 520438.87 | -131.13 | 520307.74 | 0 | [6 empty] | DW5MR | 6.825% | DW5FS | 93.18% | [16 empty] | Regulatory Outputs OMG-06: 128.982
503197 | IR18 Water Quality Improvement - Pateshill RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-12-10 | 2019-12-31 | 2020-01-27 | 2021-06-30 | 2022-06-30 | West Lothian | 0 | 0 | 0 | 0 | 194699.64 | 450548.39 | 934292.94 | 1579540.97 | 21666.03 | 1601207 | 0 | [6 empty] | DW5MR | 48.96% | DW5FS | 51.04% | [16 empty] | Regulatory Outputs OMG-06: 210.021
503198 | IR18 Water Quality Improvement - Rawburn RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-11-30 | 2019-10-01 | 2020-01-24 | 2021-06-30 | 2022-07-31 | Scottish Borders | 0 | 0 | 0 | 0 | 247014.19 | 591559.37 | 576885.93 | 1415459.49 | 270077.48 | 1685536.97 | 0 | [6 empty] | DW5MR | 15.44% | DW5FS | 84.56% | [16 empty] | Regulatory Outputs OMG-06: 313.829
503199 | IR18 Water Quality Improvement - Roberton RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-10-26 | 2019-12-20 | 2020-02-13 | 2021-07-31 | 2022-07-31 | Scottish Borders | 0 | 0 | 0 | 0 | 275000 | 411014.49 | 1375967.39 | 2061981.88 | 4333 | 2066314.88 | 0 | [6 empty] | DW5MR | 15% | DW5FS | 85% | [16 empty] | Regulatory Outputs OMG-06: 343.5619
503200 | IR18 Water Quality Improvement - Spynie RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-12-20 | 2019-09-30 | 2019-09-30 | 2020-11-30 | 2021-08-31 | Moray | 0 | 0 | 0 | 0 | 181983.16 | 388906.96 | 208208.39 | 779098.51 | 14671.37 | 793769.88 | 0 | [6 empty] | DW5MR | 30.15% | DW5FS | 69.85% | [16 empty] | Regulatory Outputs OMG-06: 149.5785
500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-31 | 2020-09-22 | Fife | 0 | 59488.58 | 471786.42 | 188739 | 179929 | 175766.94 | 34975.06 | 1110685 | 0 | 1110685 | 634368.34 | [6 empty] | EC01G | 0.89% | CS11 | 17.02% | CS16D | 39.26% | EC01D | 42.83%
503215 | Iron Mill Bay WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-10-27 | 2023-04-11 | 2023-08-10 | 2024-08-06 | 2024-11-06 | Fife | 0 | 0 | 0 | 0 | 72338.92 | 28466.11 | 32011.95 | 132816.98 | 14867183.01 | 14999999.99 | 136478.56 | [6 empty] | SG1 | 100%
402601 | Ironmill Bay WWTP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-29 | 2012-12-13 | 2013-01-30 | 2015-03-20 |  | All East Unitary Authorities | 841219 | 6572 | -94.89 | 1203.64 | 0 | 0 | 0 | 7680.75 | 0 | 848899.75 | 0 | [6 empty] | CM_WWNI | 100%
501010 | Ironmill Bay WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-10-07 | 2027-09-30 | 2027-11-30 | 2028-01-31 | 2028-03-29 | Fife | 0 | 28951 | 81470.98 | 616.8 | -5504.25 | 122704.69 | 0 | 228239.22 | 0 | 228239.22 | 0 | [6 empty] | CM_WWNI | 100%
500485 | Ironworks | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2016-09-27 | 2016-10-31 | Scottish Water Wide | 0 | 9894141.74 | -73613.6 | 0 | 0 | 0 | 0 | 9820528.14 | 0 | 9820528.14 | 0 | [6 empty] | CM_WSI | 100%
502197 | Ironworks - Capital maintenance - 2016-17 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2017-07-29 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 8700000 | 187192.13 | 12509.91 | -12509.91 | 0 | 8887192.13 | 0 | 8887192.13 | 0 | [6 empty] | CM_WSI | 100%
502637 | Ironworks - Capital maintenance - 2017-18 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-03-23 | 2017-03-23 | 2017-04-03 | 2018-04-30 | 2018-04-30 | Scottish Water Wide | 0 | 0 | 653551.4 | 8246524.6 | 125925.58 | 0 | 0 | 9026001.58 | 0 | 9026001.58 | 0 | [6 empty] | CM_WSI | 100%
503085 | Ironworks - Capital maintenance - 2018-19 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS6 | 2018-03-26 | 2018-03-26 | 2018-04-02 | 2019-04-29 | 2019-04-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 9200000 | -309847.06 | 0 | 8890152.94 | 0 | 8890152.94 | 0 | [6 empty] | CM_WSI | 100%
503557 | Ironworks - Capital maintenance - 2019-20 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2019-03-27 | 2019-03-27 | 2019-04-26 | 2020-09-30 | 2021-05-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 8642930.5 | 1193069.5 | 9836000 | 0 | 9836000 | 0 | [6 empty] | CM_WSI | 100%
505557 | Ironworks - Capital maintenance - 2020 - 21 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2020-03-19 | 2020-04-13 | 2020-07-01 | 2021-08-03 | 2021-08-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9350623.78 | 9350623.78 | 599501.22 | 9950125 | 0 | [6 empty] | CM_WSI | 100%
402101 | Ironworks Backlog Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2011-12-06 | 2012-07-20 | 2012-07-30 | 2014-05-27 |  | Scottish Water Wide | 2136640 | 26732 | 6332.38 | 0 | 0 | 0 | 0 | 33064.38 | 0 | 2169704.38 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
402574 | Ironworks Replacement Programme - 2014-15 investment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-03-12 | 2014-03-11 | 2014-03-11 | 2016-05-19 |  | Scottish Water Wide | 9933487 | 178688 | -228000.92 | 0 | 0 | 0 | 0 | -49312.92 | 0 | 9884174.08 | 0 | [6 empty] | CM_WSI | 100%
502390 | Ironworks SR15 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-15 | 2022-03-01 | 2022-05-20 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 13.46 | -13.46 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403545 | Irvine BW scoping of capex 3 costs Gailes ps | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2013-09-23 | 2017-06-05 | 2018-01-22 | 2019-02-28 | 2019-02-28 | North Ayrshire | 13361 | -2413 | 109777 | 650766 | 78599 | 18085.03 | -0.03 | 854814 | 0 | 868175 | 80660 | [6 empty] | EC16A | 100%
400071 | Irvine Harbour SPS Refurb SPS000257 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-09-29 | 2011-10-27 | 2011-10-31 | 2011-12-14 |  | North Ayrshire | 123162.48 | 98.96 | 0 | 0 | 0 | 0 | 0 | 98.96 | 0 | 123261.44 | 0 | [6 empty] | CM_WWNI | 100%
402476 | Irvine to Ayr Integrated Catchment Study (Meadowhead Sewer Catchment Area) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-02-06 | 2013-02-06 | 2015-03-26 | 2015-03-31 | Scottish Water Wide | 1630748 | 629 | 2694.83 | 1272.35 | 0 | 0 | 0 | 4596.18 | 0 | 1635344.18 | 139001 | [6 empty] | CS16S | 100%
501012 | Irvine Valley Galston to Gateshead Sewer Inspections | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-09-30 | 2016-06-29 | 2016-06-29 | 2017-04-24 | 2017-04-24 | East Ayrshire | 0 | 2000 | 43000 | 1477.4 | 0 | 0 | 0 | 46477.4 | 0 | 46477.4 | 0 | [6 empty] | CM_WWI | 100%
403752 | IT Assets Capex Allowance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-03-17 | 2014-03-17 | 2014-04-04 | 2016-02-08 |  | Scottish Water Wide | 464158 | 114216.75 | 0 | 0 | 0 | 0 | 0 | 114216.75 | 0 | 578374.75 | 0 | [6 empty] | CM_M&G | 100%
500644 | IT Assets Capex Allowance in SR15 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 371744 | 662846.94 | 681827.3 | 710142.67 | 582430.56 | 222052.47 | 3231043.94 | 0 | 3231043.94 | 0 | [6 empty] | CM_M&G | 100%
401603 | ITS Contingency Plans-Water Area Studies | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2011-01-18 | 2011-04-29 | 2015-07-07 |  | Scottish Water Wide | 1503807 | -148.84 | 0 | 0 | 0 | 0 | 0 | -148.84 | 0 | 1503658.16 | 0 | [6 empty] | CM_WSI | 100%
401604 | ITS Emergency Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2011-03-16 | 2011-04-07 | 2016-05-05 |  | Scottish Water Wide | 1843779 | -39957.47 | 0 | 0 | 0 | 0 | 0 | -39957.47 | 0 | 1803821.53 | 0 | [6 empty] | CM_WSI | 100%
500713 | ITS Emergency Equipment - 5007130000 | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS3 | 2015-06-29 | 2015-06-29 | 2016-02-26 | 2020-07-08 | 2020-09-16 | Scottish Water Wide | 0 | 535584.07 | 138920.93 | 78824.77 | 124333.41 | 23497.14 | -337.49 | 900822.83 | 0 | 900822.83 | 753145.45 | [6 empty] | CS12 | 100%
401605 | ITS End to End Process Development | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2013-03-20 | 2013-04-23 | 2016-05-05 |  | Scottish Water Wide | 1740486.5 | 781163.5 | -524533.68 | 0 | 0 | 0 | 0 | 256629.82 | 0 | 1997116.32 | 0 | [6 empty] | CM_WSI | 100%
500714 | ITS Network Contingency Plan Development | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-30 | 2015-06-30 | 2016-02-04 | 2019-01-25 | 2019-01-25 | Scottish Water Wide | 0 | 489674 | 467544.3 | 141668.28 | 0 | 0 | 0 | 1098886.58 | 0 | 1098886.58 | 753145.45 | [6 empty] | CS12 | 100%
401602 | ITS Root Cause Analysis | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-02 | 2011-01-17 | 2011-04-29 | 2015-08-12 |  | Scottish Water Wide | 300470.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300470.18 | 0 | [6 empty] | CM_WSI | 100%
501267 | IVS Drybridge Sinkholes | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS5 | 2015-12-03 | 2020-04-08 | 2020-04-08 | 2019-09-23 | 2019-09-23 | South Ayrshire | 0 | 8024.88 | 59471.12 | 104498 | 143 | -42423.82 | -21.53 | 129691.65 | 0 | 129691.65 | 0 | [6 empty] | CM_WWI | 100%
501562 | James St - Taymouth Terr - Burnside St Carnoustie Sewer Replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2016-08-29 | 2028-02-09 | 2028-04-05 | 2028-09-07 | 2028-12-08 | Angus | 0 | 0 | 12650 | -8861.81 | 0 | -550.66 | 7374.24 | 10611.77 | 747646.21 | 758257.98 | 0 | [6 empty] | SR21_WW | 100%
502638 | Jamestown Auchincarroch Rd - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-03 | 2028-02-24 | 2028-05-02 | 2028-12-04 | 2029-03-06 | West Dunbartonshire | 0 | 0 | 17120.93 | 279.07 | 2060.01 | 6202.98 | 0 | 25662.99 | 826337.05 | 852000.04 | 0 | [6 empty] | CM_WSI | 100%
502718 | Jedburgh WWTW - Replace Screw pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-04-10 | 2017-04-10 | 2017-04-24 | 2018-04-29 | 2018-04-29 | Scottish Borders | 0 | 0 | 0 | 277200 | -1400 | 0 | 0 | 275800 | 0 | 275800 | 0 | [6 empty] | CM_WWNI | 100%
502578 | Johnstone Black Cart Aerial Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-08-28 | 2020-02-21 | 2020-03-16 | 2021-05-20 | 2021-05-20 | Renfrewshire | 0 | 0 | 4601.65 | 11604.19 | 65346.16 | 402777.18 | 944221.35 | 1428550.53 | 65670.47 | 1494221 | 0 | [6 empty] | CM_WWI | 100%
504202 | Joppa SPS - mine water dispersion modelling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-24 | 2020-07-22 | 2021-04-12 | 2021-01-07 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 1000 | 7483.07 | 8483.07 | 116.92 | 8599.99 | 0 | [6 empty] | CM_WWNI | 100%
402674 | Joppa SPS Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-05-16 | 2013-02-27 | 2013-03-25 | 2014-03-31 |  | City of Edinburgh | 315892 | 1369 | -2335.97 | 0 | 0 | 0 | 0 | -966.97 | 0 | 314925.03 | 0 | [6 empty] | CM_WWI | 100%
45606 | Kaim (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-08-29 | 2015-03-25 | 2015-06-02 | Renfrewshire | 574766.94 | 26978.6 | 16.55 | 0 | 0 | 0 | 0 | 26995.15 | 0 | 601762.09 | 7198 | [6 empty] | DW1A | 100%
504170 | Kaim Spillway Channel Proactive Works | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-01-07 | 2020-06-01 | 2020-09-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 950 | 14468.22 | 15418.22 | 0 | 15418.22 | 821666.8 | [6 empty] | CS22 | 100%
502365 | Katrine Aqueduct- Balfron Station Pipe Bridge Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-10-18 | 2016-10-18 | 2017-03-10 | 2018-08-29 | 2018-08-29 | Stirling | 0 | 0 | 348411.21 | 1587519.12 | 1074872.11 | 21036.19 | -1080.12 | 3030758.51 | 0 | 3030758.51 | 0 | [6 empty] | CM_WSI | 100%
45652 | Katrine Aqueduct Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-06-20 | 2012-09-03 | 2014-03-24 |  | East Dunbartonshire | 6852331.91 | 1214.09 | -266.95 | 0 | 0 | 0 | 0 | 947.14 | 0 | 6853279.05 | 0 | [6 empty] | CM_WSNI | 100%
500775 | Keith Balloch Rd WWPS 1978 NJ434506 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-07-24 | 2017-01-30 | 2017-04-28 | 2017-08-17 | 2017-08-17 | Aberdeenshire | 0 | 8332.08 | 235336.92 | 66148 | 0 | -20673.91 | 1.47 | 289144.56 | 0 | 289144.56 | 0 | [6 empty] | CM_WWNI | 100%
403006 | Keith Regent St Sewer Replace-reroute | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-30 | 2015-12-15 | 2015-12-16 | 2015-12-18 |  | Moray | 864.49 | 15341.72 | 521.21 | 0 | 0 | 0.15 | 150.43 | 16013.51 | 0 | 16878 | 0 | [6 empty] | CM_WWI | 100%
501561 | Keith River Isla Sewer Crossing | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2017-05-30 | 2019-01-17 | 2019-06-26 | 2020-01-29 | 2020-05-05 | Moray | 0 | 0 | 9769.62 | 11224.38 | 93353 | 86210 | 1478.88 | 202035.88 | 771.12 | 202807 | 0 | [6 empty] | CM_WWI | 100%
503217 | Keith WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-07-15 | 2023-12-28 | 2024-04-23 | 2025-04-18 | 2025-07-21 | Moray | 0 | 0 | 0 | 0 | 43006.42 | 20449.07 | 46902.28 | 110357.77 | 3389642.26 | 3500000.03 | 136478.56 | [6 empty] | SG1 | 100%
36072 | Keithhill Tank - Abandonment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2007-07-02 | 2007-07-02 | 2008-02-07 | 2015-04-21 |  | East Lothian | 86265 | -16375 | -2391.79 | 0 | 0 | 0 | 0 | -18766.79 | 0 | 67498.21 | 0 | [6 empty] | WSNI | 100%
500198 | Kelso WWTW Odour Upgrade | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS6 | 2015-08-26 | 2017-03-23 | 2017-03-27 | 2018-03-31 | 2018-12-31 | Scottish Borders | 0 | 18160 | 85902.15 | 483157.03 | 82853.1 | 23742 | 0 | 693814.28 | 0 | 693814.28 | 348349.33 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
500498 | Kelty SST - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-06-02 | 2018-03-29 | 2018-06-29 | 2020-04-14 | 2020-04-14 | Fife | 0 | 77186 | 17914 | 223857 | 940527 | 230835.48 | 686.52 | 1491006 | 2776 | 1493782 | 0 |  |  |  |  | 14900 |  | CM_WWI | 100%
45410 | Kenmore Borehole WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2013-02-18 | 2013-02-26 | 2013-11-28 | 2015-12-22 | Perth and Kinross | 657833.69 | 20733.15 | 0 | 0 | 0 | 0 | 0 | 20733.15 | 0 | 678566.84 | 29100 | [6 empty] | DW23 | 100%
503312 | Kennedy WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-03-05 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 30670.13 | 0 | 0 | 30670.13 | 0 | 30670.13 | 136478.56 | [6 empty] | SG1 | 100%
403782 | Kennethmont WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2017-02-17 | 2020-11-02 | 2021-04-23 | 2022-03-23 | 2022-06-15 | Aberdeenshire | 9738 | 4161.52 | 7031.98 | 12806.56 | 7265.99 | 135240.06 | 431170 | 597676.11 | 1169134.07 | 1776548.18 | 0 | [6 empty] | SG1 | 100%
501731 | Kerse TWS Refurb | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-09-27 | 2020-04-01 | 2020-03-30 | 2021-09-30 | 2021-12-31 | East Ayrshire | 0 | 0 | 0 | 0 | 29674.86 | 399984.14 | 2865152.38 | 3294811.38 | 1505188.62 | 4800000 | 1781526.09 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502305 | Kettleton CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-09-12 | 2029-01-10 | 2029-12-31 | 2030-04-02 | Dumfries and Galloway | 0 | 0 | 36995.83 | 79190.13 | 52002.04 | 116812 | 0 | 285000 | 6915000.04 | 7200000.04 | 0 | [6 empty] | CM_WSNI | 100%
503480 | Kettleton Impounding Reservoir | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-03 | 2022-02-28 | 2022-05-30 | 2023-01-06 | 2023-04-10 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 774.2 | 17571.25 | 18345.45 | 595745.67 | 614091.12 | 0 | [6 empty] | CM_WSI | 100%
400730 | Kilbirnie Mill Court - Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-04-16 | 2011-11-15 | 2011-11-15 | 2016-12-19 | 2016-12-19 | North Ayrshire | 146717 | 1272922 | 202361 | 0 | -11617.57 | 0 | 0.01 | 1463665.44 | 0 | 1610382.44 | 204193.13 | [6 empty] | CS11 | 100%
45338 | Kilchoan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-03-29 | 2011-11-02 | 2013-07-12 | 2013-08-16 | Highland | 3068040.71 | -16125.02 | 0 | 1308 | 0 | 0 | -0.01 | -14817.03 | 0 | 3053223.68 | 0 | [6 empty] | DW3F | 3.277% | DW13 | 9.83% | DW23 | 86.89%
501735 | Kildoon Low DSR Mainout | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2028-07-24 | 2029-05-09 | 2029-09-12 | 2030-01-22 | 2030-04-24 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.97 | 99999.97 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
30406 | Killearn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-14 | 2011-08-22 | 2011-09-30 | 2012-03-22 | 2013-03-25 | Stirling | 605665.56 | -5248.87 | 0 | 0 | 0 | 0 | 0 | -5248.87 | 0 | 600416.69 | 0 | [6 empty] | EC10A | 8% | EC04A | 8.001% | CM_WWNI | 84%
503712 | Killearn WWTW - new access bridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2020-03-02 | 2020-04-06 | 2020-06-25 | 2021-02-09 | 2021-04-02 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 304128 | 304128 | 15872.02 | 320000.02 | 0 | [6 empty] | CM_WWNI | 100%
505083 | Killearn WwTW - New Access Bridge Replacement - 320k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-02-28 | 2020-11-09 | 2020-12-18 | 2021-06-24 | 2021-09-24 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 184.7 | 0 | 184.7 | 0 | 184.7 | 0 | [6 empty] | CM_WWNI | 100%
500219 | Killiecrankie - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-31 | 2016-03-31 | 2017-02-28 | 2017-10-31 | Perth and Kinross | 0 | 5176 | 4657.15 | 4146.38 | 1208.12 | 0 | 0 | 15187.65 | 0 | 15187.65 | 164281.32 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
504608 | KILLIECRANKIE WTW-DIRTY WASHWATER TANK NO1 - MIXER (5267) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-04-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 3320.6 | -1254.89 | 2065.71 | 0 | 2065.71 | 0 | [6 empty] | CM_WSNI | 100%
500829 | Killin RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-03-24 | 2017-04-13 | 2017-05-31 | 2017-09-30 | 2018-06-30 | Stirling | 0 | 1730 | 852 | 20034.12 | 3339.88 | 29304.4 | 673.69 | 55934.09 | 0 | 55934.09 | 53108.65 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 6.67
502577 | Killin WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-09 | 2019-04-24 | 2019-04-24 | 2019-01-23 | 2019-01-23 | Stirling | 0 | 0 | 20930.23 | 238.73 | 118.3 | 0 | 0 | 21287.26 | 0 | 21287.26 | 136478.56 | [6 empty] | WG1 | 100%
401043 | Killylour WTW Strategic Solution | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2010-09-13 | 2012-09-27 | 2012-09-27 | 2016-05-27 | 2016-06-21 | Dumfries and Galloway | 11920420 | 785534 | 469991 | 99306 | 10015 | 9845.8 | 0.02 | 1374691.82 | 0 | 13295111.82 | 349590.07 |  |  |  |  | 272088.51 |  | DW1A | 1.7% | WG1 | 11.9% | DW3B | 12.9% | DW13 | 13% | DW3G | 13% | DW4 | 13% | CM_WSNI | 34.5%
500750 | Kilmaluag WTW CWT Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-08-26 | 2017-05-15 | 2017-09-11 | 2018-08-30 | 2018-08-30 | Highland | 0 | 111237 | 219645.37 | 793610.73 | 215877.68 | 328.22 | 0 | 1340699 | 0 | 1340699 | 0 | [6 empty] | CM_WSNI | 100%
46841 | Kilmaluag WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-03-27 | 2012-04-30 | 2012-11-14 | 2012-11-14 | Highland | 232517.46 | -736.3 | -5361.73 | 0 | 0 | 0 | 0 | -6098.03 | 0 | 226419.43 | 0 | [6 empty] | DW23 | 100%
500220 | Kilmelford - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-05-25 | 2016-06-25 | 2017-01-31 | 2017-07-31 | Highland | 0 | 269.54 | 3190.9 | 0 | 1243.34 | 0 | 0 | 4703.78 | 0 | 4703.78 | 5104.06 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500689 | Kilmory STW - Welfare Facilities Block | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS4 | 2015-07-28 | 2017-03-15 | 2018-09-03 | 2020-03-24 | 2020-05-08 | Scottish Water Wide | 0 | 3554 | 28491.06 | 19007.58 | 228201.94 | -939.3 | -11223.01 | 267092.27 | 407.72 | 267499.99 | 0 |  |  |  |  | 4415.32 |  | CM_M&G | 100%
502366 | Kilmuir WOA AC Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2017-01-20 | 2028-02-09 | 2028-06-13 | 2030-01-07 | 2030-04-09 | Highland | 0 | 0 | 0 | 3087.85 | 0 | 459.5 | 0 | 3547.35 | 459452.64 | 462999.99 | 0 | [6 empty] | CM_WSI | 100%
45341 | Kilmuir WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-28 | 2011-11-14 | 2016-09-26 | 2016-09-30 | Highland | 4167788.17 | 1636969.05 | 1492748.69 | 75875.6 | -16663.6 | 0 | 6771.33 | 3195701.07 | 0 | 7363489.24 | 713823 |  |  |  |  | 70000 |  | DW23 | 100%
403974 | Kilmun Alderburn Place UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2019-08-31 | 2019-12-31 | Argyll and Bute-Cowal & Bute | 4700.32 | 23949.68 | 185284 | 281842 | 14004 | -157871 | 0 | 347208.68 | 1091 | 353000 | 433363.43 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403975 | Kilmun Hillrig UNS SO - Kilmun Inveroch CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-07-06 | 2018-03-29 | Argyll and Bute-Cowal & Bute | 294.85 | 73301.15 | 378245 | 719971 | -365685 | 267.76 | 1605.24 | 807705.15 | 0 | 808000 | 433363.43 | [6 empty] | EC01A | 100%
402958 | Kilpatrick Avenue Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-10-02 | 2014-09-30 | 2014-11-17 | 2015-04-01 | 2015-04-01 | Renfrewshire | 324721 | 15279 | 245.36 | 0 | 4009.02 | 0 | 0.62 | 19534 | 0 | 344255 | 204193.13 | [6 empty] | CS11 | 100%
502402 | Kiltarlity WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-12-18 | 2021-01-25 | 2021-05-18 | 2021-12-28 | 2022-03-30 | Highland | 0 | 0 | 21430.58 | 5013.34 | 18811.55 | 94291.63 | 345079.48 | 484626.58 | 1245675.53 | 1730302.11 | 136478.56 | [6 empty] | SG1 | 100%
403976 | Kimun 1 Duncans Cottage Cottage UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-03-28 | 2018-03-29 | Argyll and Bute-Cowal & Bute | 4729.75 | 1061.04 | 2209.21 | -2000 | -3298.44 | 0 | 0.44 | -2027.75 | 0 | 2702 | 433363.43 | [6 empty] | EC01A | 100%
400524 | Kincardine Kirk Street - Sewer Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-03-31 | 2014-11-28 | 2015-01-05 | 2015-12-23 | 2015-12-23 | Fife | 350297 | 982705 | 56000.34 | 13679.71 | 0 | 0 | 0 | 1052385.05 | 0 | 1402682.05 | 204193.13 | [6 empty] | CS11A | 100%
502260 | Kincardine O Neil WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-15 | 2019-04-15 | Aberdeenshire | 0 | 0 | 35402.3 | 3385.67 | 138.98 | 0 | 0 | 38926.95 | 0 | 38926.95 | 136478.56 | [6 empty] | SG1 | 100%
501312 | Kincardine WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Fife | 0 | 13086.25 | 60700.75 | 1458.44 | 3365.37 | 0 | 0 | 78610.81 | 0 | 78610.81 | 136478.56 | [6 empty] | SG1 | 100%
500497 | Kincardine WwTW - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-06-02 | 2018-09-27 | 2019-01-28 | 2020-07-20 | 2020-10-16 | Fife | 0 | 181182 | 192042.71 | 75555.29 | 383995.19 | 1215272.13 | 223580.87 | 2271628.19 | 2441.81 | 2274070 | 0 | [6 empty] | CM_WWNI | 100%
505675 | Kinfauns Drive Drumchapel Subsidence - Sewer and Water Main Replacement Value 500K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MSU | 2020-04-01 | 2020-04-13 | 2020-04-20 | 2020-07-24 | 2020-10-26 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 2342.46 | 0 | 2342.46 | 0 | 2342.46 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
503500 | King George V Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | GW1 | 2021-05-03 | 2022-02-14 | 2022-04-22 | 2022-09-06 | 2022-12-07 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 8276.17 | 8276.17 | 680027.88 | 688304.05 | 0 | [6 empty] | CM_M&G | 100%
502338 | Kinghorn Bathing Water - Catchment Network Improvements | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2016-11-15 | 2018-03-20 | 2018-03-20 | 2018-09-30 | 2018-11-30 | Fife | 0 | 0 | 34171 | 186306 | 759431 | 44825 | 267 | 1025000 | 0 | 1025000 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
403506 | Kingsbarns WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-26 | 2015-04-20 | 2015-05-18 | 2016-03-15 | 2016-03-15 | Fife | 108648 | 463086 | 1080.82 | 0 | -12432.8 | 0 | 0 | 451734.02 | 0 | 560382.02 | 0 | [6 empty] | SG1 | 100%
400724 | Kingussie WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-01 | 2012-02-07 | 2012-07-09 | 2014-07-10 | 2014-07-10 | Highland | 4770864.63 | 38309.75 | -24810.42 | 0 | 0 | 0 | 0 | 13499.33 | 0 | 4784363.96 | 0 | [6 empty] | SG1 | 100%
502841 | Kinlochbervie WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-10-20 | 2034-02-17 | 2035-02-14 | 2035-05-17 | Highland | 0 | 0 | 0 | 20930.23 | 1500.85 | -18698.9 | 0 | 3732.18 | 0 | 3732.18 | 136478.56 | [6 empty] | WG1 | 100%
45033 | Kinlochewe WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-29 | 2011-06-24 | 2013-02-28 | 2013-03-27 | Highland | 3134690.02 | -3396 | 0 | 0 | 0 | 0 | 0 | -3396 | 0 | 3131294.02 | 0 | [6 empty] | DW23 | 100%
46835 | Kinlochleven (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-18 | 2011-05-02 | 2011-09-13 | 2011-12-07 | Highland | 38613.63 | 89.47 | 0 | 0 | 0 | 0 | 0 | 89.47 | 0 | 38703.1 | 0 | [6 empty] | DW13 | 100%
504245 | Kinlochleven CWT drainage improvements and capital maintainance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-31 | 2020-03-31 | - | 0 | 0 | 0 | 0 | 0 | 60410.36 | 59589.64 | 120000 | 0 | 120000 | 0 | [6 empty] | CM_WSNI | 100%
502880 | Kinlochleven WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-09-06 | 2033-12-29 | 2034-12-20 | 2035-03-22 | Highland | 0 | 0 | 0 | 21034.21 | 1135.29 | -20037.96 | 0 | 2131.54 | 0 | 2131.54 | 136478.56 | [6 empty] | WG1 | 100%
45549 | Kinneff STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2010-12-21 | 2011-09-19 | 2013-02-26 | 2013-03-25 | Aberdeenshire | 807699.15 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 807701.15 | 0 | [6 empty] | WQ01 | 40% | CM_WWNI | 60%
501106 | Kinneil Kerse Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-08-31 | 2017-01-27 | 2018-06-30 | 2018-11-30 | Falkirk | 0 | 579 | 7903.25 | 10878.75 | 3321.59 | 0 | 0 | 22682.59 | 0 | 22682.59 | 55156.49 | [6 empty] | EC10E | 46.28% | EC01G | 53.72% | bar: Regulatory Outputs OMG-23
502886 | Kinneil Kerse STrC Sludge Import Screen | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2027-04-01 | 2028-06-14 | 2028-10-04 | 2029-05-23 | 2029-08-23 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2681 | 2681 | 372318.95 | 374999.95 | 0 | [6 empty] | SR21_WA | 100%
500579 | Kinneil Kerse WwTW - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-08-25 | 2018-11-30 | 2018-12-18 | 2021-05-27 | 2021-08-18 | Falkirk | 0 | 45317 | 217943.27 | 124637.36 | 1440188.87 | 2523527.02 | 1566327.66 | 5917941.18 | 467027.82 | 6384969 | 0 |  |  |  |  | 36840 |  | CM_WWNI | 100%
501207 | Kinnesswood WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-12-20 | 2019-12-31 | 2019-12-31 | 2019-07-31 | 2020-02-14 | Fife | 0 | 18500.42 | 118321.96 | 35276.82 | 9497.95 | 59235.6 | 4167.24 | 244999.99 | 0 | 244999.99 | 1272850.32 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501269 | Kinning Park SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-09-29 | 2016-09-29 | Glasgow City | 0 | 41860 | 2867.69 | 147.51 | 0 | 0 | -147.51 | 44727.69 | 0 | 44727.69 | 0 | [6 empty] | CM_WWNI | 100%
502902 | Kinning Park WWPS-Capital Maintenance(SR15) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-07-19 | 2028-10-25 | 2029-02-12 | 2030-08-06 | 2030-11-06 | Glasgow City | 0 | 0 | 0 | 144835.69 | 3605.9 | 20624.94 | 2124.22 | 171190.75 | 6828809.3 | 7000000.05 | 0 | [6 empty] | CM_WWNI | 100%
500151 | Kinross DOA (DOA000260) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2016-10-31 | 2016-12-31 | Perth and Kinross | 0 | 27843 | 61747.18 | 0 | 20.64 | 0 | 0.36 | 89611.18 | 0 | 89611.18 | 72047.27 | [6 empty] | CS16D | 44.91% | CS11 | 55.09% | bar: Regulatory Outputs OMG-22
45795 | Kinross South SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-09-01 | 2012-01-20 | 2013-03-28 | 2013-09-12 | Perth and Kinross | 1805160.73 | 21863.32 | 51855.71 | 0 | 0 | 0 | 0.55 | 73719.58 | 0 | 1878880.31 | 7322 | [6 empty] | WQ01C | 100%
46363 | Kinross WWTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2009-07-29 | 2012-01-24 | 2012-05-28 | 2015-01-06 | 2015-01-06 | Perth and Kinross | 3112638 | 8077.19 | 29299.51 | 30.81 | 0 | 0 | 0 | 37407.51 | 0 | 3150045.51 | 136478.56 | [6 empty] | SG1 | 100%
500794 | Kintore Strategic Wastewater Solution | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-02-22 | 2021-03-22 | 2021-03-24 | 2021-03-26 | 2021-03-26 | Aberdeenshire | 0 | 3271.03 | 1566.9 | 0 | 0 | 39452.54 | 5709.53 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WWNI | 100%
501157 | Kippen STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-04-25 | 2027-06-09 | 2027-10-21 | 2028-05-15 | 2028-08-15 | Stirling | 0 | 0 | 42868.62 | -5664.12 | 0 | -4543.69 | 26697.2 | 59358.01 | 495641.87 | 554999.88 | 0 | [6 empty] | CM_WWNI | 100%
45560 | Kippen STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-06-01 | 2011-07-28 | 2012-03-28 | 2012-03-31 | Stirling | 1049400.59 | 401.94 | 0 | 0 | 0 | 0 | 0 | 401.94 | 0 | 1049802.53 | 0 | [6 empty] | CM_WWNI | 8.612% | WQ01 | 91.39%
503285 | Kippen WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-15 | 2019-04-15 | Stirling | 0 | 0 | 0 | 0 | 78314.46 | 0 | 0 | 78314.46 | 0 | 78314.46 | 136478.56 | [6 empty] | SG1 | 100%
503310 | Kippford ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 30495.35 | 531.58 | -64.6 | 30962.33 | 0 | 30962.33 | 136478.56 | [6 empty] | SG1 | 100%
504188 | Kippford Temporary Dosing Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-08-04 | 2021-03-22 | 2021-03-23 | - | 0 | 0 | 0 | 0 | 0 | 10582.15 | 0 | 10582.15 | 0 | 10582.15 | 0 | [6 empty] | CM_WWNI | 100%
501252 | Kirbister WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-07-27 | 2028-06-08 | 2028-10-11 | 2029-02-23 | 2029-05-28 | Orkney Islands | 0 | 3837.43 | 3043.46 | 778.19 | 2071.33 | 2614.75 | -0.16 | 12345 | 159655.01 | 172000.01 | 0 | [6 empty] | CM_WSNI | 100%
503244 | Kirbister WTW - Poly dosing unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2020-06-29 | 2021-02-15 | 2021-06-24 | 2022-02-03 | 2022-05-06 | Orkney Islands | 0 | 0 | 0 | 0 | 24246.42 | 4115.49 | 163091.79 | 191453.7 | 899991.38 | 1091445.08 | 0 | [6 empty] | CM_WSNI | 100%
501228 | Kirbister WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2017-03-21 | 2019-06-28 | 2019-06-28 | 2019-06-30 | 2019-06-30 | Orkney Islands | 0 | 6117.97 | 58678.96 | -1342.57 | 1244.37 | 1822.69 | -0.01 | 66521.41 | 0 | 66521.41 | 185655.66 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
502566 | Kirbister WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2020-08-03 | 2020-08-17 | 2020-08-26 | 2020-08-27 | 2020-08-28 | Orkney Islands | 0 | 0 | 20930.23 | 5186.78 | 117888.2 | 20797.9 | 2494.9 | 167298.01 | 0 | 167298.01 | 136478.56 | [6 empty] | WG1 | 100%
402579 | Kirbister WTW Provision of Pre-Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-05-10 | 2014-07-29 | 2014-09-01 | 2015-05-25 |  | Orkney Islands | 164189 | 40176 | 82.08 | -490.17 | 0 | 0 | 0 | 39767.91 | 0 | 203956.91 | 0 | [6 empty] | CM_WSNI | 100%
500767 | Kirk Street Peterhead Reline Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2016-04-29 | 2016-05-25 | 2017-05-24 | 2017-05-24 | Aberdeenshire | 0 | 12000 | 81006 | 24295 | 5388.15 | -3275.25 | 386.1 | 119800 | 0 | 119800 | 0 | [6 empty] | CM_WWI | 100%
500196 | Kirk Yetholm WWTW Relocation | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2015-09-18 | 2018-03-22 | 2018-03-22 | 2018-02-05 | 2018-03-22 | Scottish Borders | 0 | 18094 | -3623.38 | 4166.19 | 0 | 0 | -915.72 | 17721.09 | 0 | 17721.09 | 46501.53 | [6 empty] | EC01A | 100%
46158 | Kirkcaldy Buchanan Court SPS Refurb - SPS001615 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2010-11-29 | 2011-06-27 | 2012-01-26 |  | Fife | 533572.99 | 43.68 | 0 | 0 | 0 | 0 | 0 | 43.68 | 0 | 533616.67 | 0 | [6 empty] | CM_WWNI | 100%
403749 | Kirkcaldy BW Investigation of Options | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-03-27 | 2014-10-29 | 2014-11-03 | 2016-03-31 | 2016-03-31 | Fife | 232937 | 119503 | 11180.6 | 0 | 0 | 0 | 0 | 130683.6 | 0 | 363620.6 | 173896 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
501102 | Kirkcaldy Catchment (DAS) & Aesthetic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2013-09-09 | 2014-05-30 | 2014-06-23 | 2017-01-31 | 2017-03-31 | Fife | 0 | 3144 | 27070 | 2019.86 | 0 | 0 | 0 | 32233.86 | 0 | 32233.86 | 90738 | [6 empty] | EC01G | 15% | EC01D | 85% | bar: Regulatory Outputs OMG-23
46155 | Kirkcaldy Charlotte Street SPS Refurb - SPS001812 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-09-09 | 2011-03-30 | 2011-03-31 |  | Fife | 132499.81 | -52.52 | 0 | 0 | 0 | 0 | 0 | -52.52 | 0 | 132447.29 | 0 | [6 empty] | CM_WWNI | 100%
46219 | Kirkcaldy STC Refurb - STC000097 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-03-30 | 2011-09-23 | 2012-08-14 |  | Fife | 322993.93 | 18.19 | 0 | 0 | 0 | 0 | 0 | 18.19 | 0 | 323012.12 | 0 | [6 empty] | CM_WWNI | 100%
45635 | Kirkcaldy STW Refurb - STW001982 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-03-31 | 2011-09-20 | 2013-10-31 |  | Fife | 2149017.14 | 32458.08 | -652.43 | 0 | 0 | 0 | 0 | 31805.65 | 0 | 2180822.79 | 0 | [6 empty] | CM_WWNI | 100%
501746 | KIRKCALDY WWTW 1987 NT287923 Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-07-13 | 2020-09-14 | 2021-03-17 | 2021-03-18 | Fife | 0 | 0 | 3632.58 | 0 | 0 | 16342.25 | 118130.76 | 138105.59 | 9550.38 | 147655.97 | 0 | [6 empty] | SR21_WW | 100%
501153 | Kirkconnel STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-12-10 | 2018-12-12 | 2019-01-07 | 2020-09-14 | 2020-12-15 | Dumfries and Galloway | 0 | 20632 | 211214.27 | 110259.44 | 480178.54 | 1514666.25 | 326843.88 | 2663794.38 | 24110.62 | 2687905 | 0 | [6 empty] | CM_WWNI | 100%
46335 | Kirkconnel STW - STW000435 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-25 | 2010-12-23 | 2011-02-28 | 2015-06-23 | 2015-06-23 | Dumfries and Galloway | 1409351.23 | 67676.99 | 3305.3 | 1372.06 | 0 | 0 | 0.01 | 72354.36 | 0 | 1481705.59 | 0 | [6 empty] | CM_WWNI | 100%
503809 | Kirkcudbright - Harbour Sq CSO and Beaconsfield Pl Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2021-06-14 | 2022-11-14 | 2023-03-16 | 2023-11-09 | 2024-02-09 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 27480.9 | 0 | 27480.9 | 0 | 27480.9 | 0 | [6 empty] | CM_WWI | 100%
503218 | Kirkinner WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-13 | 2030-06-10 | 2030-09-10 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 67002.51 | 1364.05 | 0 | 68366.56 | 73633.44 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
501287 | Kirkland Methil Pipebridge Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-07-07 | 2018-02-26 | 2018-02-27 | 2019-04-15 | 2019-04-15 | Fife | 0 | 0 | 104370 | 833616 | 3189428 | 109094.68 | 0.32 | 4236509 | 0 | 4236509 | 0 | [6 empty] | CM_WWI | 100%
501070 | Kirkmichael WTW - CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW2 | 2020-05-15 | 2021-03-01 | 2021-04-28 | 2022-11-22 | 2023-02-22 | Perth and Kinross | 0 | 13344.84 | 122988.01 | 13783.99 | 21959.5 | 102279.6 | 130560.51 | 404916.45 | 3306504.51 | 3711420.96 | 451950.83 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501353 | KIRKMICHAEL WWTW NS336086 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-11 | 2020-05-11 | 2020-08-03 | 2021-06-24 | 2021-09-24 | South Ayrshire | 0 | 0 | 42579.77 | 81481.19 | -12008.25 | 5353.55 | 1165416.19 | 1282822.45 | 276325.65 | 1559148.1 | 0 | [6 empty] | CM_WWNI | 100%
46177 | Kirkoswald Sewage Pumping Station | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-06-27 | 2011-09-19 | 2012-06-27 | 2012-09-07 | South Ayrshire | 692270.12 | 1127.98 | 0 | 0 | 0 | 0 | 0 | 1127.98 | 0 | 693398.1 | 0 | [6 empty] | WQ01C | 100%
45538 | Kirkpatrick Fleming STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-21 | 2011-10-12 | 2012-08-30 | 2013-01-21 | Dumfries and Galloway | 821788.19 | 2090.06 | 0 | 0 | 0 | 0 | 0 | 2090.06 | 0 | 823878.25 | 136478.56 | [6 empty] | SG1 | 16.45% | WQ01 | 83.55%
500144 | Kirkwall DOA (DOA000561) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2019-01-01 | 2019-03-28 | Orkney Islands | 0 | 36113 | 4093 | 40463 | 15400 | -12894.42 | 0 | 83174.58 | 0 | 83174.58 | 9550.69 | [6 empty] | EC01D | 25.5% | CS16D | 74.5%
504760 | Kirkwall Head of Work STC - Lime Plant Modifications | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | - | 0 | 0 | 0 | 0 | 0 | 817.76 | 0 | 817.76 | 0 | 817.76 | 0 | [6 empty] | CM_WWNI | 100%
500777 | Kirkwall WWTW 2003 HY475137 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-08-20 | 2027-04-22 | 2027-06-22 | 2027-11-26 | 2028-02-28 | Orkney Islands | 0 | 22822 | 70421.98 | -4847.98 | 0 | -5191.88 | 6136.26 | 89340.38 | 10698.63 | 100039.01 | 0 | [6 empty] | CM_WWNI | 100%
30425 | Kirriemuir STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-07-24 | 2011-09-21 | 2011-11-08 | 2014-07-31 | 2014-08-26 | Angus | 3697297.02 | 21146.29 | -31175.6 | 7050.58 | 0 | 0 | 0 | -2978.73 | 0 | 3694318.29 | 61201.88 | [6 empty] | CM_WWNI | 10% | EC04A | 90%
45800 | Kirtlebridge Marquiss SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-07-28 | 2011-09-05 | 2013-03-01 | 2013-03-26 | Dumfries and Galloway | 3294058.06 | -1356.44 | 0 | 0 | 0 | 0 | 0 | -1356.44 | 0 | 3292701.62 | 4611.92 | [6 empty] | CM_WWNI | 5% | WQ01C | 95%
501728 | Knockdon SR to Bellshill SR - Loch Doon Trunk Main Rehabilitation | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-01 | 2027-12-10 | 2028-03-03 | 2028-07-18 | 2028-10-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4428.78 | 4428.78 | 194441.39 | 198870.17 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
402182 | Knockendon Reservoir Spillway Repair- Drainage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-27 | 2012-06-11 | 2013-03-08 | 2013-03-08 | North Ayrshire | 404614.81 | 118.17 | 0 | 0 | 0 | 0 | 0 | 118.17 | 0 | 404732.98 | 0 | [6 empty] | CM_WSI | 100%
503432 | Knockendon VT Bridge | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | GW2 | 2020-06-22 | 2021-11-22 | 2022-03-18 | 2023-03-31 | 2023-06-23 | North Ayrshire | 0 | 0 | 0 | 0 | 10046.51 | 7500.83 | 10888.89 | 28436.23 | 1098863.77 | 1127300 | 821666.8 | [6 empty] | CS22 | 100%
501237 | Knockfell SR - Outlet Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS1 | 2016-04-06 | 2020-05-11 | 2020-07-06 | 2021-02-09 | 2021-01-11 | Dumfries and Galloway | 0 | 0 | 33190.8 | 49740.83 | 109998.33 | 139596.75 | 1824462.8 | 2156989.51 | 40168 | 2197157.51 | 0 | [6 empty] | CM_WSI | 100%
401013 | Knockjarder Service Reservoir Outlet Mains Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-05-31 | 2010-12-20 | 2011-02-07 | 2015-07-20 |  | South Ayrshire | 1318123 | 32000 | 11797.93 | -52550.98 | 0 | 0 | 0 | -8753.05 | 0 | 1309369.95 | 0 | [6 empty] | CM_WSI | 100%
402183 | Knocknairshill Reservoir Spillway - Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2011-11-10 | 2011-11-14 | 2012-03-01 | 2012-03-21 | Inverclyde | 335439.09 | 43.68 | 0 | 0 | 0 | 0 | 0 | 43.68 | 0 | 335482.77 | 0 | [6 empty] | CM_WSI | 100%
402896 | Knowesdean Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-23 | 2013-12-17 | 2014-02-11 | 2014-10-21 | 2015-02-02 | Scottish Borders | 154029.62 | 205.43 | 0 | 0 | 0 | 0 | 0 | 205.43 | 0 | 154235.05 | 0 | [6 empty] | CM_WSI | 100%
500831 | Kyle of Lochalsh RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-01-20 | 2016-03-30 | 2016-06-22 | 2017-01-31 | 2017-11-30 | Highland | 0 | 4445.71 | 8896.29 | 3042.01 | 1205.05 | 8923.59 | -8923.59 | 17589.06 | 0 | 17589.06 | 56616.84 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 19.22
503364 | Kyle of Lochalsh WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2022-01-17 | 2028-06-06 | 2028-10-03 | 2029-09-28 | 2029-12-31 | Highland | 0 | 0 | 0 | 0 | 20093.02 | -20093.02 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG1 | 100%
502908 | Kyle of Lochalsh WTW pH Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-04-23 | 2019-04-23 | Highland | 0 | 0 | 0 | 21935.36 | 123.03 | -20117.96 | 0 | 1940.43 | 0 | 1940.43 | 0 | [6 empty] | CM_WSNI | 100%
504482 | Kyle WTW - pH Correction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Highland | 0 | 0 | 0 | 0 | 0 | 446.12 | 0 | 446.12 | 0 | 446.12 | 0 | [6 empty] | CM_WSNI | 100%
500830 | Kylesku RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-04-18 | 2017-06-30 | 2018-03-31 | Highland | 0 | 3140 | 6229.9 | 7656.63 | 500.65 | 0 | 0 | 17527.18 | 0 | 17527.18 | 11817.97 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.34
502840 | Kylesku WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2027-04-02 | 2033-10-20 | 2034-02-17 | 2035-02-14 | 2035-05-17 | Highland | 0 | 0 | 0 | 20930.23 | 1545.39 | -19817.55 | 0 | 2658.07 | 0 | 2658.07 | 136478.56 | [6 empty] | WG1 | 100%
503837 | Labsense Coagulation Chemistry Analysers 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-17 |  | 2020-06-19 | 2020-07-23 | - | 0 | 0 | 0 | 0 | 0 | 59920.23 | -3034.52 | 56885.71 | 0 | 56885.71 | 0 | [6 empty] | CM_WSNI | 100%
501533 | Ladykirk Raith TWS Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-08-23 | 2029-12-27 | 2030-08-13 | 2030-11-13 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488915.04 | 488915.04 | 0 | [6 empty] | CM_WSNI | 100%
503075 | Ladysneuk SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2027-05-07 | 2028-02-29 | 2028-05-24 | 2028-12-20 | 2029-03-22 | Stirling | 0 | 0 | 0 | 12898.17 | 11257.12 | 1646.75 | 42.79 | 25844.83 | 642721.16 | 668565.99 | 0 | [6 empty] | CM_WWI | 100%
404133 | Laggan Bridge WTW - Cartridge Filter and UV | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS4 | 2017-04-28 | 2018-08-28 | 2018-10-11 | 2020-02-24 | 2020-04-01 | Highland | 0 | 0 | 0 | 48029.2 | 481961.44 | 146820.93 | 611.92 | 677423.49 | 1353.52 | 678777.01 | 0 |  |  |  |  | 23180.06 |  | DW23 | 100%
502573 | Laggan Bridge WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2026-07-29 | 2028-09-21 | 2028-11-29 | 2029-11-08 | 2030-02-08 | Argyll and Bute-North Argyll | 0 | 0 | 20930.23 | 671.68 | 1194.7 | -18475.49 | 0 | 4321.12 | 0 | 4321.12 | 136478.56 | [6 empty] | WG1 | 100%
502839 | Laid WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 21346.13 | 1290.63 | -19701.53 | 0 | 2935.23 | 0 | 2935.23 | 136478.56 | [6 empty] | WG1 | 100%
46193 | Laighpark (Paisley) STW Refurb - STW000455 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-09-23 | 2011-09-23 | 2013-12-20 |  | Renfrewshire | 5855436.22 | -68728.56 | 0 | 0 | 0 | 0 | 0 | -68728.56 | 0 | 5786707.66 | 0 |  |  |  |  | 20230 |  | CM_WWNI | 100%
501719 | Laighpark Paisley WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-10-31 | 2018-08-14 | 2018-11-05 | 2020-05-06 | 2020-08-06 | Renfrewshire | 0 | 0 | 15850.44 | 195135.33 | 1076591.23 | 241161 | 0 | 1528738 | 3457 | 1532195 | 0 | [6 empty] | CM_WWI | 100%
502733 | Laighpark WWTW - Intermediate Lift Screw Pump Failure | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-04-25 | 2017-07-12 | 2017-08-07 | 2018-02-07 | 2018-02-07 | Glasgow City | 0 | 0 | 0 | 2250180.95 | -43342.27 | -20586.74 | 24768.06 | 2211020 | 0 | 2211020 | 0 | [6 empty] | CM_WWNI | 100%
402641 | Laighpark WwTW Aeration Lane cleaning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-18 | 2012-06-18 | 2012-07-30 | 2016-06-30 |  | East Renfrewshire | 38932.3 | -0.3 | -6367.51 | 0 | 0 | 0 | 0.3 | -6367.51 | 0 | 32564.79 | 0 | [6 empty] | CM_WWNI | 100%
501399 | LAIRDS CAST TWP 2001 NO678963 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-06-30 | 2016-07-28 | Aberdeenshire | 0 | 2121.87 | 79.8 | 0 | 0 | 0 | 0 | 2201.67 | 0 | 2201.67 | 0 | [6 empty] | CM_WSNI | 100%
402946 | Lambert Drive Dunfermline | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-09-28 | 2012-12-04 | 2013-02-18 | 2013-03-25 | 2013-03-25 | Fife | 30195 | -472.46 | 0 | 0 | 0 | 0 | 0 | -472.46 | 0 | 29722.54 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503501 | Lambhill Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | GW1 | 2021-05-03 | 2022-03-28 | 2022-06-27 | 2023-03-28 | 2023-06-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 48059.36 | 48059.36 | 1187196.68 | 1235256.04 | 0 | [6 empty] | CM_M&G | 100%
504301 | Lamington Park mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-30 | 2020-08-14 | 2020-11-16 | 2020-11-17 | Highland | 0 | 0 | 0 | 0 | 0 | 645.24 | 4354.76 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WSI | 100%
503378 | Lamlash WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-04-09 | 2022-02-16 | 2022-06-21 | 2022-12-12 | 2023-03-14 | Renfrewshire | 0 | 0 | 0 | 0 | 65637.27 | 10654.75 | 64697.09 | 140989.11 | 1010.89 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
501693 | Lanark Rd Kirkmuirhill Pipe Bridge Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-07-05 | 2018-12-05 | 2019-02-25 | 2019-07-08 | 2019-07-08 | South Lanarkshire | 0 | 0 | 18862.98 | 90485.02 | 314047 | 8805.75 | 0.25 | 432201 | 1799 | 434000 | 0 | [6 empty] | CM_WWI | 100%
30434 | Lanark STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-12-30 | 2011-01-18 | 2012-01-01 | 2012-03-21 | South Lanarkshire | 2177233.5 | 1197.87 | 0 | 0 | 0 | 0 | 0 | 1197.87 | 0 | 2178431.37 | 0 | [6 empty] | EC01A | 30.82% | CM_WWNI | 69.18%
503070 | Lanark WWTW - RAS Screw Pumps Replacement | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-07-21 | 2028-03-02 | 2028-06-02 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 14858 | 14858 | 301142.02 | 316000.02 | 0 | [6 empty] | CM_WWNI | 100%
501194 | Land Acquisition Run off and Compensation Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-11-27 | 2015-11-27 | 2016-02-12 | 2021-11-12 | 2022-02-07 | Scottish Water Wide | 0 | 298491.68 | 894180.67 | 603924.65 | 1122274.71 | 633526.5 | 452465.01 | 4004863.22 | 130137.17 | 4135000.39 | 0 | [6 empty] | CM_M&G | 100%
500145 | Langholm DOA (DOA000075) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2018-12-01 | 2019-07-04 | Dumfries and Galloway | 0 | 12754 | 15157.18 | 97773.82 | 8161 | 8232.76 | 0.2 | 142078.96 | 0 | 142078.96 | 69142.69 | [6 empty] | EC01G | 8.062% | EC01D | 42.68% | CS16D | 49.26%
503700 | Larchfield Borehole WTW - UV Plant Replacement | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2020-07-08 | 2020-08-31 | 2020-12-14 | 2021-08-04 | 2021-09-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 197342.5 | 197342.5 | 62657.5 | 260000 | 0 | [6 empty] | CM_WSI | 100%
500147 | Largoward DOA (DOA000249) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-19 | 2019-05-31 | 2019-07-31 | Fife | 0 | 13245 | 11894 | 11838 | 40966.84 | 6545.43 | 0.01 | 84489.28 | 0 | 84489.28 | 107558.32 | [6 empty] | EC01G | 25.04% | EC01D | 74.96% | bar: Regulatory Outputs OMG-23
402837 | Largs Bathing Water Compliance | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-08-31 | 2019-07-31 | 2019-07-17 | 2019-07-24 | 2019-07-24 | Argyll and Bute-Cowal & Bute | 32664.39 | 4584.61 | 0.25 | -4302 | 334.77 | 0 | 0 | 617.63 | 0 | 33282.02 | 23244 | [6 empty] | EC02B | 100%
500152 | Largs DOA (DOA002517) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2018-03-29 | 2018-06-25 | North Ayrshire | 0 | 36102 | 130135 | 61859.29 | -16.85 | 0 | -0.03 | 228079.41 | 0 | 228079.41 | 10344.04 | [6 empty] | CS16D | 32.24% | EC01G | 67.76%
403548 | Largs Pencil BW Scoping of Cx 3 Costs for Fairlie WWTW and Anthony Road CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2013-11-29 | 2018-09-25 | 2018-12-19 | 2020-04-01 | 2020-07-07 | North Ayrshire | 88297.88 | 73202.12 | 137298 | 102940.3 | 1414236.7 | 743644 | 0 | 2471321.12 | 2500 | 2562119 | 1391238 |  |  |  |  | 7950 |  | EC16 | 100%
503272 | Largs WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-01-15 | 2029-05-18 | 2030-05-16 | 2030-08-16 | North Ayrshire | 0 | 0 | 0 | 0 | 77263.27 | 5527.39 | 0 | 82790.66 | 59209.35 | 142000.01 | 136478.56 | [6 empty] | SG1 | 100%
502091 | Larrchfield | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2028-03-23 | 2028-07-12 | 2029-02-27 | 2029-05-30 | Dumfries and Galloway | 0 | 0 | 20306.83 | 14658.54 | 0 | 11078.55 | 0 | 46043.92 | 218046.08 | 264090 | 0 | [6 empty] | CM_WSNI | 100%
500248 | Latch Inlet Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-06-02 | 2027-06-08 | 2027-07-07 | 2028-01-10 | 2028-10-03 | West Lothian | 0 | 1109 | 50133 | 4862 | -332 | -10073.59 | 15924.01 | 61622.42 | 203410.56 | 265032.98 | 0 | [6 empty] | CM_WSI | 100%
503107 | Laurencekirk SR - Growth & CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2020-11-30 | 2022-07-22 | 2022-11-18 | 2024-02-12 | 2024-05-14 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 26657.92 | 68419.01 | 95076.93 | 3904923.09 | 4000000.02 | 470181.23 | [6 empty] | CM_WSNI | 50% | WG5 | 50%
402428 | Laurencekirk WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-10-17 | 2013-07-24 | 2013-11-04 | 2014-08-07 | 2014-08-07 | Angus | 951313 | 98025.22 | 0 | 0 | 0 | 0 | 0 | 98025.22 | 0 | 1049338.22 | 0 | [6 empty] | SG1 | 100%
403412 | LCMS/MS and GCMS/MS System | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2013-12-24 | 2013-12-24 | 2016-02-02 | 2016-04-04 | 2016-04-28 | Scottish Water Wide | 358873.93 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0 | 358874 | 0 | [6 empty] | CS20 | 100%
503486 | Lead Pipe Removal Pilot | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-02-21 | 2019-04-30 | 2019-05-15 | 2021-08-09 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2851.61 | 101442.99 | 303215.09 | 407509.69 | 201242.78 | 608752.47 | 19191.74 | [6 empty] | DW25TS | 100%
400562 | Lead Water East Other | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-24 | All East Unitary Authorities | 79483.85 | -1122.37 | 0 | 0 | 0 | 0 | 0 | -1122.37 | 0 | 78361.48 | 0 | [6 empty] | DW1B | 100%
400564 | Lead Water North Other | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-17 | All North Unitary Authorities | 200377 | -8680.28 | 0 | 0 | 0 | 0 | 5253.72 | -3426.56 | 0 | 196950.44 | 0 | [6 empty] | DW1B | 100%
400569 | Lead Water West Other | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-11 | All West Unitary Authorities | 15057.35 | -1228.24 | 0 | 0 | 0 | 0 | 1131.78 | -96.46 | 0 | 14960.89 | 0 | [6 empty] | DW1B | 100%
30439 | Leadhills STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2012-01-23 | 2013-05-14 | 2013-05-22 | 2013-05-22 | South Lanarkshire | 262701.69 | 366.87 | 0 | 0 | 0 | 0 | 0 | 366.87 | 0 | 263068.56 | 0 | [6 empty] | EC04A | 23.19% | EC10A | 76.81%
500148 | Leadhills W DOA (DOA002386) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-05-30 | 2016-07-29 | 2019-03-31 | 2019-06-30 | South Lanarkshire | 0 | 4037 | 12977 | 20750 | 41962.83 | -236.82 | 0 | 79490.01 | 0 | 79490.01 | 24464.77 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
402500 | Leakage Assets Representation in GIS and Ellipse | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-01-16 | 2012-12-07 | 2012-12-07 | 2015-08-07 |  | Scottish Water Wide | 337450 | -378.42 | 526.68 | 0 | 0 | 0 | 0 | 148.26 | 0 | 337598.26 | 0 | [6 empty] | CM_WSI | 100%
400800 | Leakage East FLA Distribution Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-01 | 2010-05-04 | 2016-10-20 |  | City of Edinburgh | 1760000 | 54388.64 | -36079.88 | 0 | 0 | 0 | 0 | 18308.76 | 0 | 1778308.76 | 0 | [6 empty] | CM_WSI | 100%
400759 | Leakage East FLA DMA Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | City of Edinburgh | 1405375.69 | 2955.12 | 0 | 0 | 0 | 0 | 0 | 2955.12 | 0 | 1408330.81 | 0 | [6 empty] | CM_WSI | 100%
400757 | Leakage East FLA Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-12-14 |  | City of Edinburgh | 1310000 | 3898.13 | 0 | 0 | 0 | 0 | 0 | 3898.13 | 0 | 1313898.13 | 0 | [6 empty] | CM_WSI | 100%
402046 | Leakage Planning DI Telemetry Improvements Water Balance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-05-27 | 2014-10-20 | 2014-10-20 | 2015-09-18 |  | Scottish Water Wide | 26380 | -3221.85 | 0 | 0 | 0 | 0 | 0 | -3221.85 | 0 | 23158.15 | 0 | [6 empty] | CM_WSI | 100%
502720 | Leakage SR15 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-15 |  | 2021-04-15 |  | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 432288 | 432288 | 0 | 432288 | 0 | [6 empty] | CM_WSI | 100%
400572 | Leakage Water Mains Replacement | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-10-19 |  | Scottish Water Wide | 1733264.37 | -204424 | 0 | 0 | 0 | 0 | 0 | -204424 | 0 | 1528840.37 | 0 | [6 empty] | DW1B | 100%
400760 | Leakage West FLA Distribution Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 1400000 | 68044.17 | 0 | 0 | 0 | 0 | 0 | 68044.17 | 0 | 1468044.17 | 0 | [6 empty] | CM_WSI | 100%
400758 | Leakage West FLA DMA Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 530000 | -16882.91 | 0 | 0 | 0 | 0 | 0 | -16882.91 | 0 | 513117.09 | 0 | [6 empty] | CM_WSI | 100%
400756 | Leakage West FLA Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 817000 | -78770.04 | 0 | 0 | 0 | 0 | 0 | -78770.04 | 0 | 738229.96 | 0 | [6 empty] | CM_WSI | 100%
502792 | Lease line telecoms OFCOM deregulation | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-01-31 | 2019-07-11 | 2019-07-11 | 2020-08-03 | 2020-09-28 | Scottish Water Wide | 0 | 0 | 0 | 173511.81 | 418509.05 | 2684981.12 | 1202652.02 | 4479654 | 0 | 4479654 | 4288576.06 | [6 empty] | CS28S | 50% | CS28W | 50%
503208 | LED Lighting Programme (FOP Funded) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS3 | 2018-07-26 | 2018-07-26 | 2018-11-01 | 2020-12-04 | 2021-03-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 304417.39 | 124575.71 | 57486.6 | 486479.7 | 4874.7 | 491354.4 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
402864 | Ledard Road Battlefield Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2013-05-21 | 2013-09-10 | 2014-02-10 | 2014-02-10 | Glasgow City | 49175 | -188.54 | 0 | 0 | 0 | 0 | 0 | -188.54 | 0 | 48986.46 | 130.8 | [6 empty] | CM_WWI | 40% | CS11A | 60%
501272 | Legacy Comms fails improvement programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-16 | 2015-11-16 | 2016-03-01 | 2016-12-15 | 2017-02-15 | Scottish Water Wide | 0 | 135992.95 | 76990.95 | 0 | 0 | 0 | -11.47 | 212972.43 | 0 | 212972.43 | 0 | [6 empty] | CM_WWNI | 20% | CM_WSNI | 80%
500946 | Legacy Hydro refurbishments (3 sites) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-10-21 | 2016-11-18 | 2017-07-24 | 2019-12-19 | 2020-02-03 | Scottish Water Wide | 0 | 7736.3 | 165355.7 | 315479.48 | 82069.52 | 83845.19 | 300.82 | 654787.01 | 212.99 | 655000 | 0 | [6 empty] | CM_WSNI | 100%
38008 | Legacy Pumping Station Adoption - Phase 2 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWMD | RCC | MS7 | 2009-06-01 | 2009-06-16 | 2009-06-15 | 2013-11-19 | 2011-03-14 | Scottish Water Wide | 467667.65 | -305746.56 | 0 | 0 | 0 | 0 | 0 | -305746.56 | 0 | 161921.09 | 591600.75 | [6 empty] | SG2 | 100%
400743 | Legacy Pumping Station Adoption - Phase 3 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2007-03-08 | 2010-03-31 | 2010-04-06 | 2018-08-16 | 2015-09-24 | Scottish Water Wide | 5438129 | 663990.98 | 359368.9 | 303888.05 | 65684.47 | 39.9 | -39.9 | 1392932.4 | 0 | 6831061.4 | 0 | [6 empty] | SG5 | 100%
403162 | Legacy Road Defects | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-26 | 2013-12-19 | 2014-01-31 | 2015-03-04 |  | Scottish Water Wide | 700142 | 19858 | 0 | 107545.76 | 0 | 0 | 0 | 127403.76 | 0 | 827545.76 | 0 | [6 empty] | WSI | 0.3021% | WSNI | 0.3021% | WWNI | 0.3021% | WWI | 99.09%
503092 | Legbrannock DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-05-05 | 2021-08-16 | 2021-12-08 | 2022-07-20 | 2022-10-20 | North Lanarkshire | 0 | 0 | 0 | 15869.3 | 11599.43 | 17137.65 | 101597.12 | 146203.5 | 958796.49 | 1104999.99 | 0 | [6 empty] | CM_WSNI | 100%
500155 | Lesmahagow DOA (DOA000597) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-10-29 | 2015-12-14 | 2017-03-31 | 2017-05-31 | South Lanarkshire | 0 | 59345 | 52490.81 | -539.46 | 123.84 | 0 | 0.16 | 111420.35 | 0 | 111420.35 | 558366.35 | [6 empty] | CS15 | 27.34% | CS11 | 27.88% | CS16D | 44.78% | bar: Regulatory Outputs OMG-22
502812 | Lesmahagow WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-05-11 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | South Lanarkshire | 0 | 0 | 0 | 77870.1 | 19160.03 | 10271.36 | 33707.14 | 141008.63 | 1858991.38 | 2000000.01 | 136478.56 | [6 empty] | SG1 | 100%
45554 | Letham STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2010-09-20 | 2011-03-14 | 2012-03-23 | 2012-03-26 | Fife | 528482.63 | 187.98 | 0 | 0 | 0 | 0 | 0 | 187.98 | 0 | 528670.61 | 0 | [6 empty] | CM_WWNI | 10.08% | WQ01 | 89.92%
502883 | LETHAM TERRACE SPS CSO OUTFALL | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2020-10-23 | 2021-08-18 | 2021-11-10 | 2022-06-13 | 2022-09-13 | Falkirk | 0 | 0 | 0 | 0 | 0 | 14874.24 | 23515.76 | 38390 | 311609.96 | 349999.96 | 0 | [6 empty] | CM_WWI | 100%
503329 | Letham WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-04-01 | 2021-04-01 | 2019-09-03 | 2019-09-03 | 2019-09-03 | Angus | 0 | 0 | 0 | 0 | 75284.35 | -47335.48 | 0 | 27948.87 | 0 | 27948.87 | 136478.56 | [6 empty] | SG1 | 100%
501181 | LETHAM WWTW 1940 NO537489 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-02-17 | 2027-04-01 | 2027-07-19 | 2028-07-13 | 2028-10-13 | Angus | 0 | 5311.04 | 107085.66 | 47777.96 | 4932.51 | 4017.97 | 0 | 169125.14 | 875489.83 | 1044614.97 | 0 | [6 empty] | CM_WWNI | 100%
401338 | Lettoch WSZ Low Pressure Enhancement WSZ000980 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-02-29 | 2012-08-27 | 2013-04-18 | 2013-04-18 | Highland | 123010 | -664.47 | 0 | 0 | 0 | 0 | 0 | -664.47 | 0 | 122345.53 | 0 | [6 empty] | CS1A | 30% | CS1 | 70%
500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-11-20 | 2021-03-18 | Fife | 0 | 13243 | 108441.15 | 371383.85 | 395785 | 290598.93 | 101013.07 | 1280465 | 0 | 1280465 | 327207.23 | [6 empty] | EC01G | 0.65% | EC01D | 2.43% | EC10E | 9.73% | CS16D | 87.19%
505878 | Levenmouth DOA - Remove blockage from sewer and rehabilitate as necessary | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-31 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Fife | 0 | 0 | 0 | 0 | 0 | 53.41 | 0 | 53.41 | 0 | 53.41 | 0 | [6 empty] | WWI | 100%
501745 | LEVENMOUTH PFI - LEVENMOUTH WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-07-13 | 2020-09-14 | 2021-03-17 | 2021-03-18 | Fife | 0 | 0 | 5499.61 | 0 | 0 | 40695.39 | 179976.65 | 226171.65 | 15721.39 | 241893.04 | 0 | [6 empty] | SR21_WW | 100%
505978 | Liberton TMs NDT investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MSU | 2020-04-01 | 2020-12-07 | 2021-04-13 | 2021-10-12 | 2022-01-12 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 300 | 0 | [6 empty] | CM_WSI | 100%
503127 | Liberton Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-05-04 | 2028-03-06 | 2028-05-22 | 2030-01-31 | 2030-05-03 | City of Edinburgh | 0 | 0 | 0 | 278048.32 | 150745.61 | 25360.23 | -2536.18 | 451617.98 | -20618.02 | 430999.96 | 0 | [6 empty] | CM_WSI | 100%
502224 | Limekilns Main St SPS Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2017-03-29 | 2019-04-29 | 2019-06-17 | 2020-01-29 | 2020-05-05 | Fife | 0 | 0 | 4983.09 | 9369.91 | 65944 | 347563 | 0 | 427860 | 2250 | 430110 | 0 | [6 empty] | CM_WWI | 100%
402492 | LIMS Enhancements - Tranche 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-19 | 2013-04-22 | 2013-04-22 | 2015-05-13 |  | Scottish Water Wide | 2341014 | 853.12 | 0 | 0 | 0 | 0 | 0 | 853.12 | 0 | 2341867.12 | 0 | [6 empty] | CM_M&G | 100%
501818 | LIMS Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-08-21 | 2018-03-27 | 2018-03-27 | 2020-05-25 | 2020-05-25 | Scottish Water Wide | 0 | 0 | 0 | 332879.82 | 558676.08 | 171151.26 | 16874 | 1079581.16 | 0 | 1079581.16 | 0 |  |  |  |  | 14000 |  | CM_M&G | 100%
500156 | Lincluden DOA (DOA000122) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-11-28 | 2018-03-29 | Dumfries and Galloway | 0 | 27658 | 67082.92 | 19917.08 | -1518.12 | 0 | 0 | 113139.88 | 0 | 113139.88 | 57309.56 | [6 empty] | CS16D | 5.303% | EC01D | 94.7%
500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS7 | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-01-28 | 2019-06-11 | West Lothian | 0 | 21427 | 174286 | 88043 | 67069 | 28805.2 | -17437.12 | 362193.08 | 0 | 362193.08 | 350862.86 | [6 empty] | EC01D | 26.88% | CS16D | 73.12%
30446 | Linlithgow STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2010-09-20 | 2011-03-28 | 2016-02-04 | 2016-02-04 | West Lothian | 2701382.5 | 30316.5 | -50865.97 | 0 | 0 | 0 | 0 | -20549.47 | 0 | 2680833.03 | 23388.31 | [6 empty] | EC01A | 15% | CM_WWNI | 30% | EC04A | 55%
403066 | Lintrathen - Kirkmichael Water Pumping scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-20 | 2014-04-22 | 2014-04-22 | 2014-04-22 |  | Perth and Kinross | 3308.04 | -46.5 | 0 | 0 | 0 | 0 | 0 | -46.5 | 0 | 3261.54 | 0 | [6 empty] | CM_WSI | 100%
500479 | Lintrathen Network Hydro Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-18 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | Angus | 0 | 32623 | -6612.25 | 0 | 0 | 0 | 0 | 26010.75 | 0 | 26010.75 | 832227.31 | [6 empty] | I2S_WI | 100%
503263 | Lintrathen Raw Water Tunnel Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-05-05 | 2028-02-24 | 2028-05-04 | 2028-12-01 | 2029-03-05 | Angus | 0 | 0 | 0 | 0 | 17859.81 | 925.3 | 0 | 18785.11 | 581214.86 | 599999.97 | 0 | [6 empty] | CM_WSI | 100%
501055 | Lintrathen WOA Alyth Loyal WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-05-31 | 2021-08-02 | 2021-09-23 | 2022-10-17 | 2023-01-17 | Perth and Kinross | 0 | 6823.26 | 37854.91 | 93871.83 | 57517.17 | 0 | 0 | 196067.17 | 1767457.91 | 1963525.08 | 0 | [6 empty] | CM_WSI | 100%
501056 | Lintrathen WOA Baggerton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501057 | Lintrathen WOA Balkiellie New WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501054 | Lintrathen WOA Balmashanner WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501051 | Lintrathen WOA Blairgowrie Burnhead WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501052 | Lintrathen WOA Cairnhall Pump Station WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501053 | Lintrathen WOA Coupar Angus WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501050 | Lintrathen WOA Kingoldrum WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500020 | Lintrathen WOA Maisondieu WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-10 | 2015-11-27 | 2015-11-30 | 2016-04-01 | 2016-11-23 | Perth and Kinross | 4636 | 96788.19 | 14215.15 | 8043.41 | 7093.44 | -8292.53 | 0 | 117847.66 | 0 | 122483.66 | 0 | [6 empty] | CM_WSI | 100%
500021 | Lintrathen WOA Meikle Tullo WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-09 | 2016-01-29 | 2016-03-02 | 2017-03-23 | 2017-03-27 | Aberdeenshire | 1455 | 178066 | 304091.41 | 41387.59 | 3833.46 | 4884.01 | 0 | 532262.47 | 0 | 533717.47 | 0 | [6 empty] | CM_WSI | 100%
501044 | Lintrathen WOA Rattray WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501045 | Lintrathen WOA Stanley WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501046 | Lintrathen WOA West Ballochy WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501043 | Lintrathen WOA Wuddylaw WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501216 | Lintrathen WTW - QUALITY (Disinfection) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2018-11-23 | 2020-08-31 | 2020-12-21 | 2021-06-02 | 2021-09-03 | Angus | 0 | 5023.26 | 1774.08 | 3840.39 | 8019.19 | 39593.95 | 175402.8 | 233653.67 | 164346.31 | 397999.98 | 449492.43 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501227 | Lintrathen WTW - QUALITY (Reduction of risks identified in Drinking Water Safety Plan - Transmission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2015-11-18 | 2016-01-07 | 2016-04-01 | 2020-11-30 | 2021-02-26 | Angus | 0 | 0 | 71 | 1905.95 | 4565.25 | 1513.5 | -710.97 | 7344.73 | -76.57 | 7268.16 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
45619 | Lintrathen WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-04-01 | 2012-12-06 | 2013-01-18 | Angus | 470857.25 | -288 | 0 | 0 | 0 | 0 | 0 | -288 | 0 | 470569.25 | 0 | [6 empty] | DW1A | 100%
503424 | Linwood WwPS - Emergency Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2018-12-20 | 2019-06-28 | 2019-07-01 | 2020-09-17 | 2020-12-18 | Renfrewshire | 0 | 0 | 0 | 0 | 280465 | 1410530.83 | 131754.17 | 1822750 | 0 | 1822750 | 0 | [6 empty] | CM_WWNI | 100%
505573 | Linwood WWPS Burst 900 DIA Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-06 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 39115 | 60885 | 100000 | 0 | 100000 | 0 | [6 empty] | WWI | 100%
503383 | Livingston WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 | 2029-04-16 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 83748.31 | 2943.83 | 0 | 86692.14 | 55307.86 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
402885 | Loch Arklet - Remedial works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-11-12 | 2014-06-20 | 2014-06-30 | 2015-08-05 | 2015-08-05 | Stirling | 4921681.17 | 635551.3 | 18088.46 | 18407.5 | -44348.8 | 0 | 0 | 627698.46 | 0 | 5549379.63 | 0 | [6 empty] | CM_WSI | 100%
401352 | Loch Ascog Remedial Work To Low Level Outlet Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-26 | 2013-05-20 | 2013-06-28 | 2014-12-01 | 2014-05-26 | Argyll and Bute-North Argyll | 844436.38 | 1424 | 33.75 | 0 | 0 | 0 | 0 | 1457.75 | 0 | 845894.13 | 0 | [6 empty] | CM_WSI | 100%
501572 | Loch Ascog WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-03-15 | 2019-03-08 | 2019-03-25 | 2020-09-30 | 2020-07-08 | Argyll and Bute-Cowal & Bute | 0 | 2930.23 | 2694.42 | 4567.63 | 141103.23 | 867221.49 | 53315.21 | 1071832.21 | 2321.79 | 1074154 | 146343.21 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403276 | Loch Ascog WTW - SR06 defects remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-31 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | Argyll and Bute-Cowal & Bute | 67921.36 | 614.97 | 0 | 0 | 0 | 0 | 0 | 614.97 | 0 | 68536.33 | 0 | [6 empty] | CM_WSNI | 100%
402059 | Loch Calder Hoy sludge building Asbestos Electrical and Building HS Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-06 | 2014-04-30 | 2014-06-30 | 2015-03-09 |  | Highland | 538209 | 7936.47 | 82.19 | 0 | 0 | 0 | 0 | 8018.66 | 0 | 546227.66 | 0 |  |  |  |  | 20056 |  | CM_M&G | 100%
501061 | Loch Calder WOA Apigill (Loch Leacach) WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2028-03-08 | 2028-06-16 | 2029-02-02 | 2029-05-07 | Highland | 0 | 15488.37 | 22693.63 | 250 | 4487.22 | 1584.41 | 471.8 | 44975.43 | 684765.5 | 729740.93 | 0 | [6 empty] | CM_WSI | 100%
501062 | Loch Calder WOA Bettyhill (Swordly) WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Highland | 0 | 669.77 | -669.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500019 | Loch Calder WOA Heathfield WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2027-05-06 | 2028-06-01 | 2029-02-28 | 2029-05-31 | Highland | 1377 | 46260 | 3557 | 16501 | 20429.47 | -2530.52 | 3506.99 | 87723.94 | 1577479.02 | 1666579.96 | 0 | [6 empty] | CM_WSI | 100%
501060 | Loch Calder WOA Melvich/Strathy WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500756 | Loch Calder WOA Oust WZS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-08-10 | 2027-05-05 | 2027-06-24 | 2027-12-01 | 2028-02-15 | Highland | 0 | 12336 | 4650 | 3359.56 | 832.44 | 7392.52 | 0 | 28570.52 | 507052.68 | 535623.2 | 0 | [6 empty] | CM_WSI | 100%
501260 | Loch Calder WOA Skaill SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2015-11-09 | 2028-01-05 | 2028-02-18 | 2028-06-22 | 2028-09-22 | Highland | 0 | 19624 | 77616.49 | -0.49 | -5743.46 | -3994.77 | 0 | 87501.77 | 0 | 87501.77 | 0 | [6 empty] | CM_WSNI | 100%
501261 | Loch Calder WOA Thusater & Ramscraig SRs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2015-11-09 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 2020-10-21 | Highland | 0 | 20908 | 120422.68 | 6352.32 | -6152.14 | 7252.03 | 0 | 148782.89 | 0 | 148782.89 | 0 | [6 empty] | CM_WSNI | 100%
500785 | Loch Calder WOA Wick Airport Iron Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-07-30 | 2016-12-15 | 2019-08-26 | 2019-08-26 | 2019-08-20 | Highland | 0 | 29700 | 11971 | 15859 | 1267.37 | -24741.74 | 0.77 | 34056.4 | 0 | 34056.4 | 0 | [6 empty] | CM_WSI | 100%
504995 | Loch Calder WTW - Treated Water Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Highland | 0 | 0 | 0 | 0 | 0 | 21976.74 | 1559.16 | 23535.9 | 726464.1 | 750000 | 79911852.97 | [6 empty] | WSNI | 100%
500742 | Loch Calder WTW Disinfection Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-08-25 | 2018-11-29 | 2018-12-10 | 2020-04-01 | 2020-07-01 | Highland | 0 | 33184 | 90616.72 | 165287.6 | 683823.37 | 458358.9 | 13202.41 | 1444473 | 0 | 1444473 | 0 | [6 empty] | CM_WSNI | 100%
500754 | Loch Calder WTW Power Quality Filters and Power Correction Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-08-24 | 2016-09-08 | 2016-11-22 | 2017-07-31 | 2017-08-18 | Highland | 0 | 29132 | 242773.04 | 12877.36 | 13192.1 | 3371.35 | 0 | 301345.85 | 0 | 301345.85 | 0 | [6 empty] | CM_WSNI | 100%
502588 | Loch Calder WTW Relocation of Sludge Blowers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2027-05-03 | 2028-06-30 | 2028-10-13 | 2019-06-28 | 2019-06-28 | Highland | 0 | 0 | 12682.18 | 35274.87 | 574.41 | 17115.35 | -120 | 65526.81 | 0 | 65526.81 | 0 | [6 empty] | CM_WSNI | 100%
500894 | Loch Coulter Additional Scour Capacity | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS7 | 2016-08-30 | 2017-03-27 | 2017-06-12 | 2017-09-30 | 2020-06-01 | Stirling | 0 | 12882.16 | 11217.33 | 129321.2 | 9.11 | 18.47 | 0 | 153448.27 | 0 | 153448.27 | 165739.68 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-13
402174 | Loch Coulter Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-08-29 | 2012-11-16 | 2014-10-28 | 2014-10-28 | Scottish Water Wide | 354500.37 | -4497.15 | -483.48 | 0 | 0 | 0 | 0 | -4980.63 | 0 | 349519.74 | 0 | [6 empty] | CM_WSI | 100%
403795 | Loch Drunkie IoS Measures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-05-19 | 2016-03-18 | 2016-03-28 | 2016-04-08 | 2016-04-08 | Stirling | 26116.12 | 44802.16 | 0 | 0 | 0 | 0 | 0 | 44802.16 | 0 | 70918.28 | 0 | [6 empty] | CM_WSI | 100%
503528 | Loch Drunkie Pipe Lining | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-06-12 | 2019-06-12 | 2019-07-15 | 2020-10-29 | 2020-10-30 | Stirling | 0 | 0 | 0 | 0 | 0 | 561648.05 | 4567.93 | 566215.98 | 151884.62 | 718100.6 | 0 | [6 empty] | CM_WSI | 100%
501642 | Loch Eck | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2017-03-29 | 2018-12-21 | 2019-08-23 | 2020-11-04 | 2021-01-19 | Argyll and Bute-Cowal & Bute | 0 | 2511.63 | 10076.66 | 14013.35 | 5020.97 | 389.76 | -389.76 | 31622.61 | 0 | 31622.61 | 133039.29 | [6 empty] | DW25P | 100%
404082 | Loch Eck Caustic and Hypo Dosing Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-01-27 | 2019-01-28 | 2019-02-28 | 2021-08-26 | 2021-11-26 | Argyll and Bute-Cowal & Bute | 6104 | 213592 | 272674.27 | 239157.51 | 980714.14 | 1352149.93 | 622211.53 | 3680499.38 | 422997.41 | 4109600.79 | 0 |  |  |  |  | 28400 |  | CM_WSNI | 100%
501305 | Loch Eck incident - filter refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2016-06-13 | 2016-06-13 | Argyll and Bute-Cowal & Bute | 0 | 814140.26 | 62332.93 | 124.77 | 0 | 0 | 0 | 876597.96 | 0 | 876597.96 | 0 | [6 empty] | CM_WSNI | 100%
501306 | Loch Eck incident - operational interventions | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-04-28 | 2019-07-29 | 2019-07-29 | Argyll and Bute-Cowal & Bute | 0 | 257453.52 | 75521.46 | 0 | 5428.27 | 0 | 0 | 338403.25 | 0 | 338403.25 | 0 | [6 empty] | CM_WSNI | 100%
501307 | Loch Eck Incident - Temporary treatment | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2016-03-31 | 2016-03-31 | Argyll and Bute-Cowal & Bute | 0 | 275834 | -22546.83 | 0 | 0 | 0 | 0 | 253287.17 | 0 | 253287.17 | 638845.62 | [6 empty] | CM_WSNI | 30% | CS16WR | 70% | bar: Regulatory Outputs OMG-07
500039 | Loch Eck WOA Strachur New WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-04-09 | 2015-11-17 | 2015-11-17 | 2015-11-17 | 2016-10-03 | Argyll and Bute-Cowal & Bute | 0 | 627.97 | 0 | 0 | 0 | 0 | 0.03 | 628 | 0 | 628 | 0 | [6 empty] | CM_WSI | 100%
46312 | Loch Eck WTW - Mn Removal | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-11-07 | 2010-08-16 | 2010-09-14 | 2013-01-14 | 2013-03-28 | Argyll and Bute-Cowal & Bute | 6902178.02 | 58596.47 | 26155.33 | 0 | 0 | 0 | -0.12 | 84751.68 | 0 | 6986929.7 | 74877 | [6 empty] | DW3C | 100%
403679 | Loch Goin Reservoir - Draw Down | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-03 | 2015-06-22 | 2015-07-20 | 2015-11-10 | 2015-11-10 | East Ayrshire | 39781 | 268451 | 39844.62 | -282.78 | 0 | 0 | 0 | 308012.84 | 0 | 347793.84 | 0 | [6 empty] | CM_WSI | 100%
505337 | Loch Horn - Repairs to Access Track | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-02-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 10166.67 | 14833.33 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WSI | 100%
403717 | Loch Katrine Concrete Buttress | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-27 | 2015-01-29 | 2015-04-20 | 2016-03-11 | 2016-03-11 | Argyll and Bute-North Argyll | 93778 | 774209 | 0 | 0 | -4605.68 | 0 | 0 | 769603.32 | 0 | 863381.32 | 0 | [6 empty] | CM_WSI | 100%
503780 | Loch Katrine Landslips Incident | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS3 | 2019-10-31 | 2019-11-01 | 2020-02-06 | 2020-08-06 | 2020-12-24 | Stirling | 0 | 0 | 0 | 0 | 0 | 972207.84 | 825639 | 1797846.84 | 0 | 1797846.84 | 0 | [6 empty] | CM_M&G | 100%
1286 | Loch Katrine Water Supply Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2001-12-14 | 2004-04-28 | 2004-03-22 | 2007-10-12 | 2008-04-22 | East Dunbartonshire | 120381045.78 | 4873.68 | 266.25 | 0 | 0 | 0 | 0 | 5139.93 | 0 | 120386185.71 | 0 | [6 empty] | DW1 | 33.33% | DW4 | 33.33% | DW3 | 33.34%
403164 | Loch Lee Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2014-06-25 | 2014-06-25 | 2014-11-17 | 2014-11-17 | Angus | 766237.65 | 71820.14 | -892.53 | 0 | 0 | 0 | 0 | 70927.61 | 0 | 837165.26 | 0 | [6 empty] | CM_WSI | 100%
500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-19 | 2019-08-28 | Scottish Water Wide | 0 | 8923 | 84596.82 | 252787.18 | 172653 | 10153.93 | 0 | 529113.93 | 0 | 529113.93 | 117082.76 | [6 empty] | CS16D | 25.46% | EC10H | 74.54%
404131 | Loch Maree | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2016-06-23 | 2016-10-10 | 2016-10-31 | 2018-03-01 | 2018-03-30 | Highland | 0 | 0 | 3283025.81 | 2547613.51 | 109665.25 | 9929.44 | 9549.01 | 5959783.02 | 0 | 5959783.02 | 0 |  |  |  |  | 43200 |  | DW23 | 50% | DW3A | 50%
45396 | Loch Maree Strategic Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-07-16 | 2009-11-02 | 2011-03-28 | 2016-07-07 | 2016-07-07 | Highland | 8254375.06 | 2493608.96 | 475527.38 | 184077.34 | 21.29 | 0 | 0.01 | 3153234.98 | 0 | 11407610.04 | 1972445.76 |  |  |  |  | 40008 |  | WG1 | 50% | WG4 | 50%
505055 | Loch Nell Abstraction Meter Installation (2) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-17 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2679.85 | 17320.14 | 19999.99 | 0 | 19999.99 | 0 | [6 empty] | WSNI | 100%
45505 | Loch Ryan Shellfish Waters improvement Scheme Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS6 | 2008-11-20 | 2010-06-14 | 2011-01-18 | 2015-03-31 | 2016-03-31 | Dumfries and Galloway | 47476169 | 669547.98 | 589133.02 | 152614 | 297435.41 | 122061.74 | -2121.74 | 1828670.41 | 0 | 49304839.41 | -1670236.18 |  |  |  |  | 374726 |  | CM_WSI | 0.184% | EC01A | 49.91% | EC03A | 49.91% | bar: Regulatory Outputs OMG-07
503251 | Loch Tay Strategic Scheme | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-04-01 | 2020-10-12 | 2021-01-12 | 2022-10-05 | 2023-01-05 | Perth and Kinross | 0 | 0 | 0 | 0 | 32629.24 | 368.29 | -331.35 | 32666.18 | 0 | 32666.18 | 0 | [6 empty] | CM_WSNI | 100%
502329 | Loch Thom MIOS Drawdown & Freebaoard Enhancement | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-07-31 | 2019-07-23 | 2019-09-12 | 2021-09-30 | 2021-12-31 | Inverclyde | 0 | 0 | 38455.43 | 5660.8 | 230589.15 | 2334209.19 | 3445039.06 | 6053953.63 | 888363.7 | 6942317.33 | 880386.96 |  |  |  |  | 1180 |  | WR6 | 100% | bar: Regulatory Outputs OMG-13
501568 | Loch Turret Drawdown Enhancement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-05-20 | 2018-01-23 | 2018-02-08 | 2018-08-10 | 2018-08-10 | Perth and Kinross | 0 | 10754.35 | 14061.07 | 102799 | 59719.46 | 0 | 0 | 187333.88 | 0 | 187333.88 | 0 | [6 empty] | CM_WSI | 100%
502558 | Loch Turret IOS Works - Actuators | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-01-26 | 2018-01-26 | 2018-03-07 | 2018-04-04 | 2018-04-04 | Perth and Kinross | 0 | 0 | 0 | 39626.17 | 319000.96 | 1840 | 0 | 360467.13 | 0 | 360467.13 | 0 | [6 empty] | CM_WSI | 100%
500191 | Loch Venachar Improvements to Compensation Releases | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS5 | 2015-03-20 | 2018-09-26 | 2018-10-01 | 2019-03-31 | 2019-03-31 | Stirling | 0 | 2325 | 458 | 4286 | 141 | 10024.34 | -24.34 | 17210 | 0 | 17210 | 99661.84 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
501634 | Lochaline WTW - WQ Upgrade - Early Delivery Elements | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2016-03-31 | 2016-09-29 | 2016-09-30 | 2017-10-31 | 2019-03-31 | Highland | 0 | 20607 | 3751345.93 | 823117.05 | 538228.25 | 7469.42 | 0 | 5140767.65 | 0 | 5140767.65 | 1855121.96 | [6 empty] | DW23 | 100% | bar: Regulatory Outputs OMG-01
46176 | Lochans STW Refurb - STW000471 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-29 | 2014-05-28 | 2014-08-01 | 2014-09-12 |  | Dumfries and Galloway | 610873.75 | 473.75 | 0 | 0 | 0 | 0 | 0 | 473.75 | 0 | 611347.5 | 0 | [6 empty] | CM_WWNI | 100%
503309 | Lochans WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-04-09 | 2022-09-29 | 2023-01-27 | 2024-01-25 | 2024-04-26 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 30748.66 | 15744.61 | 94037.4 | 140530.67 | 1469.34 | 142000.01 | 136478.56 | [6 empty] | SG1 | 100%
46850 | Lochcarron WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-16 | 2011-07-12 | 2013-05-20 | 2013-09-30 | Highland | 3736788.25 | 6078.23 | 0 | 0 | 0 | 0 | 0 | 6078.23 | 0 | 3742866.48 | 7727 | [6 empty] | DW23 | 100%
46869 | Lochenkit WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-07 | 2013-07-17 | 2013-07-17 | 2016-03-17 | 2016-05-27 | Dumfries and Galloway | 3757654 | 8135 | 21576 | 18827.62 | 21276.11 | 0 | 3724.76 | 73539.49 | 0 | 3831193.49 | 21665 | [6 empty] | DW9A | 0.265% | DW3G | 33.23% | DW3A | 33.25% | DW3F | 33.25%
402838 | Lochgair WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-08-21 | 2016-05-30 | 2016-09-08 | 2017-02-24 | 2017-02-24 | Argyll and Bute-North Argyll | 48500 | 27048.37 | 382722.89 | 33529.82 | -14659.04 | 55.41 | 0.01 | 428697.46 | 0 | 477197.46 | 0 | [6 empty] | SG1 | 100%
500813 | Lochgelly Spion Kop WSZ Low Pressure Enhancement | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWMD | Pressure | MS6 | 2015-08-07 | 2017-08-18 | 2017-10-02 | 2017-11-07 | 2017-11-07 | Fife | 0 | 4525.56 | 22464.67 | 33779.77 | -2158.18 | 1446.17 | 2341.37 | 62399.36 | 0 | 62399.36 | 364502.97 | [6 empty] | CS1B | 14.49% | CS1 | 85.51%
503099 | Lochgelly Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS4 | 2018-12-21 | 2019-08-06 | 2019-08-19 | 2020-03-18 | 2020-12-04 | Fife | 0 | 0 | 0 | 0 | 20324.39 | 354898.17 | 33321.57 | 408544.13 | 9790.42 | 418334.55 | 470181.23 | [6 empty] | WG5 | 100%
501662 | Lochgilphead- Remove Dual MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-09-20 | 2018-02-27 | 2018-03-21 | 2020-05-14 | 2020-08-18 | Argyll and Bute-North Argyll | 0 | 0 | 7020.53 | 191786.47 | 456186 | 28948 | 3141 | 687082 | 2400 | 689482 | 0 | [6 empty] | CM_WWI | 100%
501571 | Lochgoilhead WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2016-03-29 | 2016-10-24 | 2017-02-03 | 2018-01-31 | 2020-04-30 | Argyll and Bute-Cowal & Bute | 0 | 2511.63 | 17.09 | 454.02 | 833.51 | -309.14 | -389.76 | 3117.35 | 0 | 3117.35 | 72374.96 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501360 | Lochgoilhead WTW - 500766 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS7 | 2016-03-29 | 2016-10-24 | 2017-02-03 | 2018-01-30 | 2019-08-01 | Argyll and Bute-Cowal & Bute | 0 | 142 | 39477.05 | 139961.96 | 5028.46 | 342.07 | -385.77 | 184565.77 | 0 | 184565.77 | 72374.96 | [6 empty] | DW25P | 100%
502574 | Lochgoilhead WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-06-04 | 2022-01-17 | 2022-03-28 | 2023-03-09 | 2023-06-09 | Argyll and Bute-Cowal & Bute | 0 | 0 | 20930.23 | 0 | 5171.84 | 9954.82 | 13385.4 | 49442.29 | 950557.73 | 1000000.02 | 136478.56 | [6 empty] | WG1 | 100%
503132 | Lochgoilhead WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-12-22 | 2028-08-16 | 2028-12-11 | 2029-12-06 | 2030-03-08 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 28088.63 | 6409.82 | 753007.26 | 787505.71 | 1212494.27 | 1999999.98 | 0 | [6 empty] | CM_WWNI | 100%
402184 | Lochgoin Outlet Pipe Lining | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-09-07 | 2013-03-04 | 2014-02-27 | 2014-02-27 | North Ayrshire | 395929.97 | 167.23 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 396097.2 | 0 | [6 empty] | CM_WSI | 100%
502395 | Lochgreen Rd - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-03 | 2028-02-23 | 2028-05-01 | 2028-12-01 | 2028-12-01 | Falkirk | 0 | 0 | 7000 | 13292.48 | 5801.86 | 181.34 | 0 | 26275.68 | 595724.32 | 622000 | 0 | [6 empty] | CM_WSI | 100%
403046 | Lochieport AC Mains Replacement and Iron Specials Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-22 | 2013-01-14 | 2013-09-02 |  | Na H-Eileanan an Iar | 303015 | 11921.76 | 0 | 0 | 0 | 0 | 0 | 11921.76 | 0 | 314936.76 | 0 | [6 empty] | CM_WSI | 100%
500832 | Lochinvar RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-10-28 | 2017-12-21 | 2018-02-13 | 2019-03-31 | 2020-02-29 | Dumfries and Galloway | 0 | 145996 | -4380.77 | 38810.28 | 155408.67 | 20331.07 | 0 | 356165.25 | 0 | 356165.25 | 599034.52 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 97.72
502837 | Lochinver WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2027-04-02 | 2033-10-20 | 2034-02-17 | 2020-03-31 | 2035-05-17 | Highland | 0 | 0 | 0 | 21346.13 | 1340.34 | -19665.74 | 0 | 3020.73 | 0 | 3020.73 | 136478.56 | [6 empty] | WG1 | 100%
402627 | Lochmaben WwTW Electrical Distribution Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-04-16 | 2013-01-08 | 2013-06-03 | 2014-02-04 |  | Dumfries and Galloway | 329482 | 435.53 | 0 | 0 | 0 | 0 | 0 | 435.53 | 0 | 329917.53 | 0 | [6 empty] | CM_WWNI | 100%
403903 | Lochmaddy WTW - WQ - DW3 DW13 DW23 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2011-03-29 | 2016-02-29 | 2017-07-21 | 2019-06-30 | 2019-08-31 | Na H-Eileanan an Iar | 124155 | 789610 | 533484.34 | 6194438.82 | 4250210.23 | 463192.66 | 15779.76 | 12246715.81 | 21285.51 | 12392156.32 | 5043339 |  |  |  |  | 65927 |  | DW25 | 8.1% | DW13 | 14% | DW23 | 14% | DW3G | 14% | CM_WSNI | 49.9% | bar: Regulatory Outputs OMG-03
46870 | Lochmaddy WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-28 | 2015-03-27 | 2014-11-28 | 2014-11-28 | 2014-11-28 | Na H-Eileanan an Iar | 877949.16 | 3032.46 | -1594.22 | 0 | 0 | 0 | 0 | 1438.24 | 0 | 879387.4 | 0 | [6 empty] | DW3G | 100%
501248 | Lockenkit Trunk Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-12-07 | 2016-07-19 | 2016-08-22 | 2017-05-23 | 2017-05-23 | Dumfries and Galloway | 0 | 7799 | 315643.03 | 74820.3 | 385 | 62 | 0 | 398709.33 | 0 | 398709.33 | 0 | [6 empty] | CM_WSI | 100%
500161 | Lockerbie DOA (DOA000076) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2019-06-01 | 2019-07-04 | Dumfries and Galloway | 0 | 11300 | 21721 | 19810.63 | 76500 | -7141.45 | 0 | 122190.18 | 0 | 122190.18 | 71629.44 | [6 empty] | EC01G | 2.269% | CS16D | 22.99% | EC10E | 27.05% | EC01D | 47.7%
500496 | Lockerbie WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-07-21 | 2018-10-30 | 2018-10-30 | 2020-04-03 | 2020-06-30 | Dumfries and Galloway | 0 | 44415 | 307872.31 | 162492.04 | 858332.62 | 1213889.99 | 12250.25 | 2599252.21 | 54364.58 | 2653616.79 | 0 | [6 empty] | CM_WWNI | 100%
503387 | Lockerbie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-06-15 | 2023-04-24 | 2023-08-25 | 2024-02-15 | 2024-05-17 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 76108.55 | 8095.04 | 29506.76 | 113710.35 | 1886289.66 | 2000000.01 | 136478.56 | [6 empty] | SG1 | 100%
503665 | Lockerbie WwTW CSOs Intervention Developments | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-03-29 | 2022-11-28 | 2023-03-31 | 2024-10-24 | 2024-12-17 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 14341.8 | 180819.74 | 195161.54 | 8804838.45 | 8999999.99 | 354277.77 | [6 empty] | EC01F_ID | 50% | EC10B_ID | 50%
502127 | Logistics - Emergency Equipment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2017-03-30 | 2017-03-30 | Scottish Water Wide | 0 | 0 | 1046258 | -15856 | 0 | 0 | 0 | 1030402 | 0 | 1030402 | 0 | [6 empty] | CM_M&G | 100%
401016 | Logistics - Plant Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2010-06-14 | 2010-06-21 | 2016-06-23 |  | Scottish Water Wide | 1153954.54 | -23570 | -11683.9 | 0 | 0 | 0 | 0 | -35253.9 | 0 | 1118700.64 | 0 | [6 empty] | CM_M&G | 100%
402042 | Logistics - Vehicle Replacement LCV - Tranche 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-10 | 2011-03-31 | 2011-05-03 | 2016-06-23 |  | Scottish Water Wide | 8844315.74 | -53785.54 | 0 | 0 | 0 | 0 | 0 | -53785.54 | 0 | 8790530.2 | 0 | [6 empty] | CM_M&G | 100%
403467 | Logistics - Vehicle Replacement LCV - Tranche 3 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-04-30 | 2013-04-30 | 2013-05-07 | 2016-06-23 |  | Scottish Water Wide | 5935188 | -785393.05 | -23064.31 | 0 | 0 | 0 | 0.01 | -808457.35 | 0 | 5126730.65 | 0 | [6 empty] | CM_M&G | 100%
401017 | Logistics - Vehicle Replacement LGV | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2010-06-14 | 2010-06-21 | 2016-06-23 |  | Scottish Water Wide | 5615967.07 | 666546.32 | -26464.71 | 0 | 0 | 0 | 0 | 640081.61 | 0 | 6256048.68 | 0 | [6 empty] | CM_M&G | 100%
401069 | Logistics - Vehicle Telematics | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-06-28 | 2015-03-17 | 2015-03-17 | 2016-06-23 |  | Scottish Water Wide | 96405 | -49689.01 | 373.95 | 0 | 0 | 0 | 0 | -49315.06 | 0 | 47089.94 | 0 | [6 empty] | CM_M&G | 100%
501203 | Lomond Hills WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-08-26 | 2018-08-01 | 2018-08-31 | 2020-07-20 | 2020-10-21 | Fife | 0 | 5978.09 | 84186.42 | 292354.42 | 555670.51 | 1242617.69 | 416331.5 | 2597138.63 | 34209.37 | 2631348 | 0 | [6 empty] | CM_WSNI | 100%
503105 | Lomond Hills WTW - Local water supply imrovements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-05-28 | 2018-05-29 | 2018-06-18 | 2018-06-18 | 2018-06-18 | Fife | 0 | 0 | 0 | 0 | 339627.81 | 0 | 0 | 339627.81 | 0 | 339627.81 | 0 | [6 empty] | CM_WSNI | 100%
500972 | Lomond Hills WTW - Mn | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-03 | 2015-11-06 | 2015-12-14 | 2016-06-30 | 2016-09-30 | Fife | 0 | 32100.94 | 41913.47 | 63 | 321.9 | -12099.47 | -32.58 | 62267.26 | 0 | 62267.26 | 790368.92 | [6 empty] | DW3C | 100% | bar: Regulatory Outputs OMG-01
500494 | Lomond Scheme Flowmeter Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-05-28 | 2018-03-30 | 2018-06-28 | 2020-11-27 | 2021-02-24 | All West Unitary Authorities | 0 | 90181 | 102346.02 | 167120.91 | 922759.62 | 504940.45 | 613705 | 2401053 | 151720 | 2552773 | 0 | [6 empty] | CM_WSNI | 100%
502324 | London Road Glasgow Sewer Rehabilitation - Lift and relay section of sewer and water main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-09-02 | 2016-09-14 | 2016-09-28 | 2017-05-05 | 2017-05-05 | Glasgow City | 0 | 0 | 1392865.62 | -19722.01 | 680.42 | 4127.46 | 0.01 | 1377951.5 | 0 | 1377951.5 | 0 | [6 empty] | CM_WWI | 100%
403941 | London Road Legal Costs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2020-08-06 |  | Glasgow City | 11754.35 | 829.65 | 6199.85 | 22874.84 | 2226.9 | 0 | 0 | 32131.24 | 0 | 43885.59 | 0 | [6 empty] | CM_WWNI | 100%
403122 | London Road Sewer Repair (near to junction with Kerrydale Street) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-22 | 2013-02-20 | 2013-02-20 | 2014-03-14 |  | Glasgow City | 2031916.02 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 2032066.02 | 0 | [6 empty] | CM_WWI | 100%
503718 | London Road Water Mains replacement & investigations | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2020-04-01 | 2020-07-20 | 2020-08-03 | 2021-03-04 | 2021-04-27 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 51471.67 | 306981.79 | 358453.46 | 137201.54 | 495655 | 0 | [6 empty] | CM_WSI | 100%
503702 | Londornoch WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-07-07 | 2022-01-17 | 2022-05-19 | 2023-05-15 | 2023-08-11 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 123460 | 123460 | 876539.96 | 999999.96 | 136478.56 | [6 empty] | SG1 | 100%
502280 | Londornoch WTW Sludge Lagoon Upgrade | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS2 | 2017-08-18 | 2020-03-31 | 2020-09-11 | 2021-09-14 | 2021-12-01 | Highland | 0 | 0 | 23204.84 | 97916.77 | 112919.88 | 145721.09 | 1652550.58 | 2032313.16 | 1012268.85 | 3044582.01 | 312056.86 |  |  |  |  | 44570 |  | LA01 | 100% | bar: Regulatory Outputs OMG-24
502669 | Lone Worker | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-04-27 | 2017-04-27 | 2017-04-27 | 2019-05-14 | 2019-05-14 | Scottish Water Wide | 0 | 0 | 0 | 145865.69 | 40634.55 | 9290.1 | 0 | 195790.34 | 0 | 195790.34 | 0 | [6 empty] | CM_M&G | 100%
404105 | Long Loch Outlet Pipe Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-03-06 | 2015-05-19 | 2015-05-27 | 2015-05-28 | 2015-06-24 | East Renfrewshire | 19.98 | 338622.1 | 0 | 0 | 0 | 0 | 0.32 | 338622.42 | 0 | 338642.4 | 0 | [6 empty] | CM_WSI | 100%
402606 | Longforgan Station Rd SPS Access Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2012-11-20 | 2013-01-07 | 2015-04-01 |  | All East Unitary Authorities | 125354 | 2143.35 | 299.59 | 14.84 | 0 | 0 | 0 | 2457.78 | 0 | 127811.78 | 0 | [6 empty] | CM_M&G | 100%
501749 | Longforgan trunk sewer - Reline sewer | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2020-06-24 | 2021-04-01 | 2021-06-17 | 2021-10-29 | 2022-01-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 4798.67 | 57680.74 | 62479.41 | 187438.26 | 249917.67 | 0 | [6 empty] | CM_WWI | 100%
500236 | Longside WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Aberdeenshire | 0 | 43391.93 | 0 | 0 | 0 | 0 | 0 | 43391.93 | 0 | 43391.93 | 136478.56 | [6 empty] | SG1 | 100%
503443 | Loon Burn Pipe Bridge Penicuik | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2020-06-24 | 2021-04-29 | 2021-07-20 | 2022-02-07 | 2022-05-10 | Midlothian | 0 | 0 | 0 | 0 | 12365.91 | 15801.99 | 158000.1 | 186168 | 413832 | 600000 | 0 | [6 empty] | CM_WWI | 100%
503173 | Lossie Wynd - Mains Refurbishment | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-01 | 2028-02-02 | 2028-04-25 | 2028-11-20 | 2029-02-20 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791139.79 | 1791139.79 | 0 | [6 empty] | CM_WSI | 100%
502205 | Lossie Wynd Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-09-22 | 2019-09-30 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Aberdeenshire | 0 | 0 | 16896.43 | 5114.75 | 6398.49 | 1302.38 | -507.17 | 29204.88 | 0 | 29204.88 | 0 | [6 empty] | CM_WSI | 100%
505292 | Lossiemouth Coulardbank Storm No. 1 Pump No. 2 investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-05-22 |  | 2020-05-22 | 2020-05-22 | Moray | 0 | 0 | 0 | 0 | 0 | 4351.33 | 6348.67 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_WWNI | 100%
503032 | Lossiemouth DSRs CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2020-08-31 | 2021-12-20 | 2022-04-21 | 2023-07-14 | 2023-10-16 | Moray | 0 | 0 | 0 | 0 | 66861.77 | 18276.24 | 118112.95 | 203250.96 | 2046749.02 | 2249999.98 | 0 | [6 empty] | CM_WSNI | 100%
402802 | Lossiemouth WSZ Low Pressure Enhancement | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-23 | 2013-01-24 | 2013-02-11 | 2013-03-31 | 2013-03-31 | Moray | 333936.25 | 585.56 | 0 | 0 | 0 | 0 | 0 | 585.56 | 0 | 334521.81 | 0 | [6 empty] | CS1 | 100%
403409 | Lothianburn PRV Hydro | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2015-06-10 | 2015-06-10 | 2015-06-10 | 2015-06-10 | City of Edinburgh | 560826.99 | -380973.56 | 0 | 0 | 0 | 0 | -0.43 | -380973.99 | 0 | 179853 | 0 | [6 empty] | CC1W | 100%
502616 | Low Askomil Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-23 | 2027-12-16 | 2028-03-02 | 2028-07-14 | 2028-10-16 | Argyll and Bute-North Argyll | 0 | 0 | 5144 | 0 | -4.69 | 80 | 0 | 5219.31 | 0 | 5219.31 | 0 | [6 empty] | CM_WSI | 100%
500480 | Lower Glendevon Reservoir Hydro Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | Fife | 0 | 40100.85 | 54.86 | 0 | 0 | 0 | 0 | 40155.71 | 0 | 40155.71 | 832227.31 | [6 empty] | I2S_WI | 100%
502190 | Lower Largo Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-08-29 | 2018-01-29 | 2018-03-26 | 2018-07-27 | 2018-07-27 | Fife | 0 | 0 | 12095 | 222361 | 419062.93 | 1441.82 | 0 | 654960.75 | 0 | 654960.75 | 0 | [6 empty] | CM_WWI | 100%
501313 | Lower Largo WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-08-30 | Fife | 0 | 10465.12 | 3234.3 | 0 | 0 | 0 | 0 | 13699.42 | 0 | 13699.42 | 136478.56 | [6 empty] | SG1 | 100%
502800 | LRC3 Permament Chemical Dosing | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-07-27 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | Glasgow City | 0 | 0 | 0 | 447693.52 | -447248.4 | 0 | 0 | 445.12 | 0 | 445.12 | 11105602.59 | [6 empty] | EC01A | 100%
502963 | LTRAP MD Long Term Redundant Assets - East Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2020-08-17 | 2020-10-19 | 2021-10-06 | 2021-10-07 | Scottish Water Wide | 0 | 0 | 0 | 4754.03 | 36211.75 | 13559.34 | 84323.02 | 138848.14 | 65751.09 | 204599.23 | 0 | [6 empty] | CM_M&G | 100%
502964 | LTRAP MD Long Term Redundant Assets - North Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS2 | 2017-11-09 | 2019-12-09 | 2020-08-24 | 2021-05-11 | 2021-08-11 | Scottish Water Wide | 0 | 0 | 0 | 8432.5 | 55304.82 | 6802.63 | 129095.21 | 199635.16 | 6955.77 | 206590.93 | 0 | [6 empty] | CM_M&G | 100%
502965 | LTRAP MD Long Term Redundant Assets - South Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2021-05-24 | 2021-08-09 | 2021-11-29 | 2021-11-29 | Scottish Water Wide | 0 | 0 | 0 | 17056.54 | 11932.59 | 2799.52 | 1796.94 | 33585.59 | 300690.47 | 334276.06 | 0 | [6 empty] | CM_M&G | 100%
502966 | LTRAP MD Long Term Redundant Assets - West Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2017-11-10 | 2020-01-21 | 2020-02-03 | 2020-12-17 | 2021-03-25 | Scottish Water Wide | 0 | 0 | 0 | 16124.79 | 23852.91 | 23410.65 | 361736.65 | 425125 | 0 | 425125 | 0 | [6 empty] | CM_M&G | 100%
502897 | LTRAP SWD Long Term Redundant Assets | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-10-09 | 2017-10-09 | 2018-04-02 |  | 2021-07-07 | Scottish Water Wide | 0 | 0 | 0 | 17970 | 12530 | 24261.44 | 170238.56 | 225000 | 0 | 225000 | 0 | [6 empty] | CM_M&G | 100%
501593 | LUGAR WWPS NS585207 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2018-12-05 | 2019-02-11 | 2020-05-15 | 2020-05-15 | East Ayrshire | 0 | 0 | 88307 | 125426 | 729553 | 727500 | 9957 | 1680743 | 2400 | 1683143 | 0 |  |  |  |  | 16060 |  | CM_WWNI | 100%
401331 | Lybster - Young Crescent - Sewer Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-24 | 2014-01-29 | 2014-04-25 | 2015-01-26 | 2015-01-26 | Highland | 463211 | 25154 | -1054.84 | 0 | 0 | 0 | 0 | 24099.16 | 0 | 487310.16 | 1367.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
500157 | Lybster DOA (DOA001064) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-01 | 2017-04-24 | 2017-04-24 | Highland | 0 | 13260 | 743.08 | -4250.7 | 0 | 0 | 0 | 9752.38 | 0 | 9752.38 | 72047.27 | [6 empty] | CS11 | 100%
45545 | Lyne of Skene STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-08-22 | 2011-11-28 | 2012-09-30 | 2013-01-24 | Aberdeenshire | 571660.02 | 1298.08 | 0 | 0 | 0 | 0 | 0 | 1298.08 | 0 | 572958.1 | 0 | [6 empty] | WQ01 | 100%
500221 | Maaruig - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-06-23 | 2017-01-31 | 2018-02-28 | Highland | 0 | 193.5 | 2448.07 | 302.75 | 1272.85 | 0 | 0 | 4217.17 | 0 | 4217.17 | 5495.73 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
45353 | Maaruig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-14 | 2011-10-03 | 2013-01-07 | 2013-01-31 | Na H-Eileanan an Iar | 945001.43 | 2556.53 | 0 | 0 | 0 | 0 | 0 | 2556.53 | 0 | 947557.96 | 0 | [6 empty] | DW23 | 100%
501277 | Macritch Hill Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS7 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2018-09-03 | 2018-09-03 | Angus | 0 | 14278.04 | -12614.89 | 2538.92 | 0 | 0 | 0 | 4202.07 | 0 | 4202.07 | 0 | [6 empty] | I2S_WI | 100%
501225 | Mahon Court Bridgeburn Drive Moodiesburn Replace Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-22 | 2018-04-30 | 2018-06-11 | 2018-12-21 | 2018-12-21 | North Lanarkshire | 0 | 5630.61 | 134369.39 | 169757 | 781213.97 | 11029.03 | 0 | 1102000 | 0 | 1102000 | 0 | [6 empty] | CM_WWI | 100%
503230 | Main Street Kirkconnel Pipe Bridge | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-02-21 | 2021-01-11 | 2021-03-29 | 2021-11-01 | 2022-02-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 11847.83 | 29027.8 | 385882.23 | 426757.86 | 609620.76 | 1036378.62 | 0 | [6 empty] | SR21_WW | 100%
503630 | Mains Cleaning in 5 RSZs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-09-30 | 2020-03-31 | 2020-03-31 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 311335.99 | 1852802.85 | 2164138.84 | 625610.19 | 2789749.03 | 649651.11 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 558.41
46225 | Mains Investigations - Raw Water Mains Investigations | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-01 | 2012-06-30 | 2012-06-30 | 2014-03-05 |  | Scottish Water Wide | 523461.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523461.15 | 0 | [6 empty] | CM_WSI | 100%
46226 | Mains Investigations - Trunk Mains Investigations Programme Build Up | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-01 | 2012-07-18 | 2012-07-23 | 2015-06-30 | 2015-10-28 | Scottish Water Wide | 2052507 | 126185.54 | -112266.66 | 0 | 0 | 0 | 0 | 13918.88 | 0 | 2066425.88 | 0 | [6 empty] | CM_WSI | 100%
46677 | Mains Rehab - WOA000011 Alnwickhill Schemes within 2 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-03-26 | 2012-05-28 | 2013-09-13 |  | City of Edinburgh | 300370 | -509.56 | 0 | 0 | 0 | 0 | 0 | -509.56 | 0 | 299860.44 | 0 | [6 empty] | CM_WSI | 100%
46076 | Mains Rehab - WOA000029 Back and Tolsta Schemes within WSZ000100 Back | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-10 | 2013-03-25 | 2013-04-25 | 2014-11-03 |  | Na H-Eileanan an Iar | 384000 | 0 | -492.87 | 0 | 0 | 0 | 0 | -492.87 | 0 | 383507.13 | 0 | [6 empty] | CM_WSI | 100%
46141 | Mains Rehab - WOA000033 Badentinan 2 Schemes within 2 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-28 | 2011-11-21 | 2013-01-28 |  | Aberdeenshire | 455036 | -1144.49 | 0 | 0 | 0 | 0 | 0 | -1144.49 | 0 | 453891.51 | 0 | [6 empty] | CM_WSI | 100%
46679 | Mains Rehab - WOA000054 Black Esk 14 Schemes within 12 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-12 | 2012-09-26 | 2012-11-19 | 2014-02-26 |  | Dumfries and Galloway | 2386023.73 | 1542.16 | 0 | 0 | 0 | 0 | 0 | 1542.16 | 0 | 2387565.89 | 0 | [6 empty] | CM_WSI | 100%
46655 | Mains Rehab - WOA000093 Clatto Schemes within 6 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-10-26 | 2012-11-12 | 2013-07-11 |  | Angus | 355920 | 34.33 | 0 | 0 | 0 | 0 | 4.2 | 38.53 | 0 | 355958.53 | 0 | [6 empty] | CM_WSI | 100%
46171 | Mains Rehab - WOA000137 Eela Water 7 Schemes within 6 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-08-08 | 2012-08-29 | 2012-09-24 | 2013-05-17 |  | Shetland Islands | 420000 | -11611.7 | 0 | 0 | 0 | 0 | 0.57 | -11611.13 | 0 | 408388.87 | 0 | [6 empty] | CM_WSI | 100%
46136 | Mains Rehab - WOA000166 Glengap - Ringford 3 Schemes within 1 WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-09-21 | 2012-11-19 | 2013-07-15 |  | Dumfries and Galloway | 563338 | -921.46 | 0 | 0 | 0 | 0 | 0 | -921.46 | 0 | 562416.54 | 0 | [6 empty] | CM_WSI | 100%
46072 | Mains Rehab - WOA000177 Glengap 3 Schemes within 2 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-10 | 2012-09-26 | 2013-02-25 | 2014-01-21 | 2014-02-03 | Dumfries and Galloway | 1013817 | 4420.37 | 0 | 0 | 0 | 0 | 0 | 4420.37 | 0 | 1018237.37 | 0 | [6 empty] | CM_WSI | 100%
46145 | Mains Rehab - WOA000179 Glenlatterach and Badentinan 6 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2008-07-31 | 2013-06-19 | 2013-06-28 | 2017-09-28 |  | Moray | 1407177 | 0 | 128759.04 | 204063.96 | 5237 | 35158.65 | 0 | 373218.65 | 0 | 1780395.65 | 0 | [6 empty] | CM_WSI | 100%
46071 | Mains Rehab - WOA000199 Invercannie and Mannofield 18 Schemes within 11 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2008-06-26 | 2010-11-15 | 2011-03-07 | 2022-06-27 |  | Aberdeen City | 874096 | -71791 | 5545 | 69038.02 | 198616.78 | 48274.76 | 185815.64 | 435499.2 | 90404.77 | 1399999.97 | 0 | [6 empty] | CM_WSI | 100%
46135 | Mains Rehab - WOA000200 Invercannie 2 Schemes within 2 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-28 | 2011-03-07 | 2013-04-25 |  | Aberdeenshire | 425106 | -1635.83 | 0 | 0 | 0 | 0 | 0 | -1635.83 | 0 | 423470.17 | 0 | [6 empty] | CM_WSI | 100%
45657 | Mains Rehab - WOA000209 Kettleton 12 Schemes within 7 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2009-03-12 | 2012-09-26 | 2013-01-28 | 2019-03-12 | 2019-03-12 | Dumfries and Galloway | 3230378 | 42743.65 | 1567.53 | 30689 | 7615.96 | 33829.97 | 8093.11 | 124539.22 | 337.2 | 3355254.42 | 0 | [6 empty] | CM_WSI | 100%
46139 | Mains Rehab - WOA000213 Killiecrankie 4 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-25 | 2011-03-21 | 2012-11-20 |  | Perth and Kinross | 206000 | -3660.02 | 0 | 0 | 0 | 0 | 0 | -3660.02 | 0 | 202339.98 | 0 | [6 empty] | CM_WSI | 100%
46689 | Mains Rehab - WOA000215 Killylours - Terregles 8 Schemes within 5 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-09-26 | 2013-01-25 | 2014-07-07 | 2014-10-01 | Dumfries and Galloway | 662664 | -2926.11 | 71 | 0 | 0 | 0 | 0 | -2855.11 | 0 | 659808.89 | 0 | [6 empty] | CM_WSI | 100%
46690 | Mains Rehab - WOA000215 Killylours - Terregles Scheme within DMA002096 Terregles Road | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2013-03-06 | 2013-06-18 | 2014-05-23 | 2014-08-14 | Dumfries and Galloway | 453109 | -570.16 | 71 | 0 | 0 | 0 | 0 | -499.16 | 0 | 452609.84 | 0 | [6 empty] | CM_WSI | 100%
46672 | Mains Rehab - WOA000224 Kirbister and Boardhouse 5 Schemes within 4 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-08-08 | 2012-10-17 | 2012-11-05 | 2015-08-24 |  | Orkney Islands | 1098985 | -12669 | 2474.6 | 12012.89 | 0 | 0 | -0.01 | 1818.48 | 0 | 1100803.48 | 0 | [6 empty] | CM_WSI | 100%
46070 | Mains Rehab - WOA000246 Lochinvar 7 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-26 | 2012-09-26 | 2012-11-19 | 2017-03-03 |  | Dumfries and Galloway | 4168789 | 10234 | 157961.7 | 24486.04 | 124757.63 | 27869.92 | -10955.79 | 334353.5 | 0 | 4503142.5 | 0 | [6 empty] | CM_WSI | 100%
46169 | Mains Rehab - WOA000275 Ness 2 Schemes within 2 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-10-24 | 2012-10-30 | 2013-09-16 |  | Na H-Eileanan an Iar | 319626.61 | 65.62 | 0 | 0 | 0 | 0 | 0 | 65.62 | 0 | 319692.23 | 0 | [6 empty] | CM_WSI | 100%
46146 | Mains Rehab - WOA000295 Perth (Gowans Terrace) 8 Schemes within 4 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-11-05 | 2011-03-21 | 2012-08-23 |  | Perth and Kinross | 947796 | -3555.72 | 0 | 0 | 0 | 0 | 0 | -3555.72 | 0 | 944240.28 | 0 | [6 empty] | CM_WSI | 100%
46147 | Mains Rehab - WOA000318 Sandy Loch 5 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-02-29 | 2012-04-16 | 2013-02-28 |  | Shetland Islands | 382746 | -2634.13 | 0 | 0 | 0 | 0 | 0 | -2634.13 | 0 | 380111.87 | 0 | [6 empty] | CM_WSI | 100%
46663 | Mains Rehab - WOA000374 Turret (Tayside) 4 Schemes within 4 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-27 | 2012-08-29 | 2012-09-24 | 2013-10-22 |  | Perth and Kinross | 1239159 | 2415.68 | 0 | 0 | 0 | 0 | 334.32 | 2750 | 0 | 1241909 | 0 | [6 empty] | CM_WSI | 100%
45654 | Mains Rehab - WOA000375 Turriff 9 Schemes within 6 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-12 | 2012-08-29 | 2012-09-03 | 2013-06-24 |  | Aberdeenshire | 803271 | -1755.22 | 0 | 0 | 0 | 0 | -128.31 | -1883.53 | 0 | 801387.47 | 0 | [6 empty] | CM_WSI | 100%
46702 | Mains Rehab - WSZ000318 Camps Happendon to Carluke SR (Trunk Main) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2013-07-31 | 2013-09-16 | 2014-07-15 |  | South Lanarkshire | 2047099 | 4617 | 1560.21 | 0 | 0 | 0 | 0 | 6177.21 | 0 | 2053276.21 | 0 | [6 empty] | CM_WSI | 100%
502672 | Mains Rehab Farquhar Terrace South Queensferry | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2017-06-28 | 2017-06-28 | 2017-09-29 | 2018-08-24 | 2018-08-24 | West Lothian | 0 | 0 | 0 | 361334.47 | 14574.08 | 243.88 | 652.44 | 376804.87 | 103.68 | 376908.55 | 0 | [6 empty] | CM_WSI | 100%
503035 | Mains Rehab Hardhill Drive Bathgate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-02-20 | 2018-07-11 | 2018-07-12 | 2018-10-01 | 2018-10-01 | West Lothian | 0 | 0 | 0 | 2204.74 | 343195.65 | 1537.87 | 0 | 346938.26 | 5462.13 | 352400.39 | 0 | [6 empty] | CM_M&G | 100%
500163 | Mallaig DOA (DOA000323) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-19 | 2019-02-28 | 2019-06-30 | Highland | 0 | 11027 | 19421 | 42019 | 77480 | -228.73 | 0.02 | 149718.29 | 0 | 149718.29 | 84126.66 | [6 empty] | EC01G | 14.83% | EC01D | 85.17% | bar: Regulatory Outputs OMG-23
504176 | Mallaig WOA - Intake Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-05-24 | 2022-10-24 | 2023-02-23 | 2023-10-19 | 2024-01-19 | Highland | 0 | 0 | 0 | 0 | 0 | 1270.38 | 0 | 1270.38 | 0 | 1270.38 | 0 | [6 empty] | CM_WSI | 100%
504998 | Mallaig WTW - Filtomats | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Highland | 0 | 0 | 0 | 0 | 0 | 2178.38 | 16155.22 | 18333.6 | 761666.44 | 780000.04 | 0 | [6 empty] | WSNI | 100%
502674 | Mallaig WTW Prefiltration | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | Highland | 0 | 0 | 0 | 61811.81 | 0 | 0 | 0 | 61811.81 | 0 | 61811.81 | 0 | [6 empty] | CM_WSNI | 100%
500075 | Mannofield Coagulant Change Trial and Monitoring | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-09 | 2015-03-20 | 2015-03-20 | 2016-02-26 | 2016-02-26 | Aberdeen City | 11002 | 2561.5 | 0 | 0 | 0 | 0 | 0 | 2561.5 | 0 | 13563.5 | 56021.66 | [6 empty] | DW3C_S | 100%
500209 | Mannofield East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2017-12-22 | 2017-12-27 | 2018-03-23 | 2018-03-28 | Aberdeen City | 0 | 1490 | 1413 | 68175.68 | 0 | 0 | 3749.18 | 74827.86 | 0 | 74827.86 | 491407.97 | [6 empty] | DW5FS | 34% | DW5 | 66%
500833 | Mannofield East RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-03-07 | 2017-12-21 | 2018-03-23 | 2019-12-31 | 2020-09-30 | Aberdeen City | 0 | 26277.48 | 28355.52 | 230298.72 | 212543.66 | 280522.96 | 23761.73 | 801760.07 | 0 | 801760.07 | 1119988.24 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 174.54
500834 | Mannofield North RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-09-20 | 2018-09-18 | 2018-11-30 | 2019-09-30 | 2020-10-30 | Aberdeen City | 0 | 25559.07 | 15355.22 | 39111.93 | 105280.83 | 70204.38 | 5330.7 | 260842.13 | 97.21 | 260939.34 | 1187753.42 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 72.17
500205 | Mannofield West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS6 | 2015-03-27 | 2018-03-30 | 2018-03-30 | 2018-10-31 | 2019-06-30 | Aberdeen City | 0 | 3854 | 2406 | 149054 | 77028.66 | -46740.9 | 0 | 185601.76 | 0 | 185601.76 | 1880301.15 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500835 | Mannofield West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-03-10 | 2021-04-05 | Aberdeen City | 0 | 24086.41 | 15578.59 | 267817.87 | 163863.62 | 277651.45 | 15498.89 | 764496.83 | -778.58 | 763718.25 | 1122593.17 | [6 empty] | DW5FS | 100%
502555 | Mannofield WTW - Commissioning of Sodium Hypochlorite Dosing Kiosk | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2016-03-31 | 2017-12-12 | 2017-12-12 | 2018-09-30 | 2019-03-31 | Aberdeen City | 0 | 0 | 6740.69 | 69935.22 | 225792.53 | 225 | 1292.35 | 303985.79 | 354.94 | 304340.73 | 334512.73 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-01
502211 | Mannofield WTW - Hydrocarbon Monitor | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-06-21 | 2017-08-15 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 334512.73 | [6 empty] | DW25P | 100%
502373 | Mannofield WTW - Inchgarth Reservoir Investigations | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS2 | 2019-03-06 | 2020-03-25 | 2020-11-03 | 2021-08-02 | 2021-10-29 | Aberdeen City | 0 | 0 | 51929.3 | 62957.19 | 6238.51 | 6009.5 | 49966.69 | 177101.19 | 17950.08 | 195051.27 | 334512.73 | [6 empty] | DW25P | 100%
501297 | Mannofield WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2016-03-31 | 2020-08-17 | 2020-11-16 | 2021-05-21 | 2021-05-24 | Aberdeen City | 0 | 8707.77 | 2807.07 | 3217.71 | 5366.37 | 10658.77 | 66641.51 | 97399.2 | 5587.81 | 102987.01 | 334512.73 | [6 empty] | DW25P | 100%
502653 | Mannofield WTW - RGF Controls Software Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-04-10 | 2017-08-24 | 2017-10-03 | 2018-03-16 | 2018-03-16 | Aberdeen City | 0 | 0 | 0 | 320759.47 | 2956.94 | -248.29 | 0 | 323468.12 | 0 | 323468.12 | 0 | [6 empty] | CM_WSNI | 100%
502312 | Mannofield WTW -Improvements to Network Assets (SR Isolation Valves) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2017-03-23 | 2021-12-20 | 2022-03-10 | 2023-02-06 | 2023-05-08 | Aberdeen City | 0 | 0 | 4850.33 | 5970.72 | 30182.8 | 130350.65 | -70078.78 | 101275.72 | 765243.2 | 866518.92 | 0 | [6 empty] | DW25T | 100%
502236 | Mannofield WTW -Improvements to SR s | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2016-05-30 | 2016-05-30 | 2016-09-05 | 2020-07-17 | 2020-07-20 | Aberdeen City | 0 | 0 | 35209.46 | 3323.55 | 438.78 | 9070.15 | 1958.07 | 50000.01 | 0 | 50000.01 | 334512.73 | [6 empty] | DW25P | 100%
502243 | Mannofield WTW -Improvements to Treatment Process | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2017-03-31 | 2020-10-12 | 2020-11-09 |  | 2020-04-30 | Aberdeen City | 0 | 0 | 115578.93 | 137340.58 | 14528.35 | 321711.45 | 1730571.25 | 2319730.56 | 443299.97 | 2763030.53 | 0 | [6 empty] | CM_WSNI | 100% | bar: Regulatory Outputs OMG-05
501250 | Mannofield WTW SCADA-PLC Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-23 | 2015-11-23 | 2015-12-01 | 2017-06-01 | 2017-06-01 | Aberdeen City | 0 | 731045 | 762009.44 | 25517.02 | 2334.22 | -798.23 | 0 | 1520107.45 | 0 | 1520107.45 | 0 | [6 empty] | CM_WSNI | 100%
500836 | Mannofield-Turiff-Invercannie RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-31 | 2018-11-21 | 2018-11-21 | 2018-11-30 | 2018-11-30 | Aberdeen City | 0 | 12297.55 | 9157.79 | 9640.3 | 2336.14 | 0 | 0 | 33431.78 | 0 | 33431.78 | 469821.8 | [6 empty] | DW5FS | 100%
402964 | Manse Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2012-10-01 | 2020-03-03 | 2020-04-08 | 2020-03-12 | 2020-04-08 | City of Edinburgh | 41239 | 11000 | 49253.12 | 24707.88 | 29074 | 18719.43 | -961.2 | 131793.23 | 0 | 173032.23 | 204193.13 | [6 empty] | CS11 | 100%
30509 | Manse Street Galashiels Water WTW - Upgrade | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2005-12-01 | 2007-09-26 | 2008-01-25 | 2008-01-25 | 2008-06-12 | Scottish Borders | 185895.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185895.93 | 0 | [6 empty] | DW13 | 33.33% | DW3B | 33.33% | DW4A | 33.33%
45643 | Manse Street Galashiels WTW Refurb - WTW000681 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-01-30 | 2012-02-07 | 2012-01-31 |  | Scottish Borders | 281569.05 | 639.79 | 0 | 0 | 0 | 0 | 0 | 639.79 | 0 | 282208.84 | 0 | [6 empty] | CM_WSNI | 100%
500837 | Manse Street RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-01-12 | 2017-03-23 | 2017-05-01 | 2018-10-31 | 2019-05-31 | Scottish Borders | 0 | 7616.67 | 33053.22 | 49167.6 | 59880.69 | -6975.2 | 0.01 | 142742.99 | 0 | 142742.99 | 238122.94 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 34.53
500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-12-23 | 2020-11-27 | City of Edinburgh | 0 | 50989 | 124821.68 | 313228.22 | 666744.54 | 69011.58 | 18017.13 | 1242812.15 | 449.87 | 1243262.02 | 3028853.1 | [6 empty] | DW5 | 100%
500838 | Marchbank B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-08-03 | 2017-09-29 | 2017-10-02 | 2018-08-31 | 2019-03-31 | Midlothian | 0 | 1739.39 | 851.34 | 51301.9 | 108361.95 | -9625.08 | 0.01 | 152629.51 | 0 | 152629.51 | 40226.72 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 6.28
501080 | Marchbank WOA Marchbank Hermiston WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-28 | 2027-12-08 | 2028-01-31 | 2028-06-28 | 2028-09-28 | West Lothian | 0 | 24192 | -7710 | 0 | 481 | 391.17 | -391.17 | 16963 | 0 | 16963 | 0 | [6 empty] | CM_WSI | 100%
501079 | Marchbank WOA Marchbank Torduff WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-01 | 2023-07-18 | 2023-08-16 | 2024-03-21 | 2024-03-22 | City of Edinburgh | 0 | 23832 | 57340 | 47222 | -27721.18 | 0 | 0 | 100672.82 | 485412.16 | 586084.98 | 0 | [6 empty] | CM_WSI | 100%
402851 | Marchmont Crescent Edinburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2012-11-27 | 2012-12-17 | 2013-03-28 | 2013-03-28 | City of Edinburgh | 89562.86 | 274.14 | 0 | 0 | 0 | 0 | 0 | 274.14 | 0 | 89837 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403527 | Marchmont Road Warrender Park Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS5 | 2013-07-18 | 2019-07-31 | 2019-08-05 | 2019-08-15 | 2019-08-15 | City of Edinburgh | 318833 | 39461 | 200122.78 | -76968.78 | 47293 | 8275 | 0 | 218183 | 0 | 537016 | 204193.13 | [6 empty] | CS11 | 100%
400814 | Marybank WWTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-05-07 | 2011-10-11 | 2013-10-23 | 2014-09-26 | 2014-09-26 | Highland | 468782 | 43218 | -3838.46 | 0 | 0 | 0 | 0 | 39379.54 | 0 | 508161.54 | 0 | [6 empty] | SG1 | 100%
502828 | Marykirk WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-03-04 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Aberdeenshire | 0 | 0 | 0 | 62575.95 | 7446.41 | 53204.8 | 18772.85 | 142000.01 | 2258000.02 | 2400000.03 | 136478.56 | [6 empty] | SG1 | 100%
500158 | Mauchline DOA (DOA000137) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-29 | 2016-06-29 | 2018-02-28 | 2018-03-31 | East Ayrshire | 0 | 1669 | 15230 | 13078.58 | 0 | 0 | 0 | 29977.58 | 0 | 29977.58 | 10344.04 | [6 empty] | EC01G | 100% | bar: Regulatory Outputs OMG-23
45539 | Mauchline STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2012-09-18 | 2014-01-09 | 2015-03-23 | 2015-03-31 | East Ayrshire | 3452973.92 | 147377.27 | 2954.47 | -650.8 | 0 | 0 | 0 | 149680.94 | 0 | 3602654.86 | 50762.99 | [6 empty] | CM_WWNI | 40.02% | WQ01 | 59.98%
503545 | Mauchline WwTW Bathing Water Improvement | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | WWINF | Revised Bathing Waters Directive | MS1 | 2019-07-09 | 2020-05-18 | 2020-07-27 | 2021-03-31 | 2021-07-07 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 225763 | 1885753.5 | 2111516.5 | 71833.5 | 2183350 | 2277461.36 | [6 empty] | EC16B | 100%
30512 | Mauldslie (Carluke) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-08-23 | 2010-09-27 | 2012-02-01 | 2012-03-05 | South Lanarkshire | 2322396.25 | 36488.35 | 0 | 0 | 0 | 0 | 0 | 36488.35 | 0 | 2358884.6 | 0 | [6 empty] | EC01A | 40% | CM_WWNI | 60%
503418 | Mauldslie Access Road & Bridge Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2020-04-01 | 2020-03-30 | 2020-03-30 | 2021-12-09 | 2021-12-09 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 891082.96 | 167855.09 | 1058938.05 | 41061.95 | 1100000 | 0 | [6 empty] | CM_WWI | 100%
502317 | Mauldslie WwTW - Secondary Treatment Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | South Lanarkshire | 0 | 0 | 0 | 52325.58 | 0 | 0 | 0 | 52325.58 | 0 | 52325.58 | 0 | [6 empty] | CM_WWNI | 100%
402603 | MCC Controls Aberdeenshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2013-07-03 | 2013-09-17 | 2016-11-25 |  | All East Unitary Authorities | 180124 | 53914.8 | 5943.55 | 341.85 | 0 | 0 | 0 | 60200.2 | 0 | 240324.2 | 0 | [6 empty] | CM_M&G | 100%
502350 | MCC SR15- East SPS MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-20 | 2020-03-06 | 2020-03-20 | 2020-05-01 | All East Unitary Authorities | 0 | 0 | 34200 | 184.6 | 89.25 | 38181.11 | 0 | 72654.96 | 0 | 72654.96 | 0 | [6 empty] | CM_WWNI | 100%
502339 | MCC SR15 East WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-03-12 | 2020-05-13 | All East Unitary Authorities | 0 | 0 | 38620.47 | 190.89 | 43.72 | 4192.3 | 0 | 43047.38 | 0 | 43047.38 | 0 | [6 empty] | CM_WWNI | 100%
502342 | MCC SR15- Hamilton WWTW MCC Replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-05-29 | 2021-05-31 | 2021-03-30 | 2022-02-16 | 2022-05-19 | South Lanarkshire | 0 | 0 | 24773.02 | 50153.65 | -3348.29 | 18482.75 | 145693.14 | 235754.27 | 848342.79 | 1084097.06 | 0 | [6 empty] | SR21_WW | 100%
502355 | MCC SR15- Shieldhall WWTW MCC Replacement Phase 2 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-05-29 | 2021-11-29 | 2022-03-31 | 2023-03-15 | 2023-06-15 | Glasgow City | 0 | 0 | 29521.37 | 157120.27 | 13813.51 | 12776.8 | 256130.75 | 469362.7 | 4298721.29 | 4768083.99 | 0 | [6 empty] | SR21_WW | 100%
502356 | MCC SR15- Shieldhall WWTW MCC Replacement Phase 3 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-05-29 | 2021-12-27 | 2022-04-28 | 2023-04-26 | 2023-07-27 | Glasgow City | 0 | 0 | 38700 | 1858 | 242409.45 | 50510.61 | 359289.07 | 692767.13 | 6295832.93 | 6988600.06 | 0 | [6 empty] | SR21_WW | 100%
502343 | MCC SR15- South SPS MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2020-04-01 | 2020-04-15 | 2020-04-16 | 2020-03-13 | 2020-07-10 | All South Unitary Authorities | 0 | 0 | 23860.47 | 190.89 | 43.72 | 26678.13 | -50532.25 | 240.96 | 0 | 240.96 | 0 | [6 empty] | CM_WWNI | 100%
502340 | MCC SR15- South WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2020-04-01 |  | 2020-03-06 | 2020-03-17 | 2020-05-13 | All South Unitary Authorities | 0 | 0 | 38620.47 | 307.87 | 1089.9 | 4438.27 | 0 | 44456.51 | 0 | 44456.51 | 0 | [6 empty] | CM_WWNI | 100%
502341 | MCC SR15- West WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2020-04-01 | 2020-04-01 | 2020-03-06 | 2020-03-13 | 2020-05-13 | All West Unitary Authorities | 0 | 0 | 38842.4 | 454.1 | 43.72 | 4154.21 | 0 | 43494.43 | 0 | 43494.43 | 0 | [6 empty] | CM_WWNI | 100%
500436 | MD SVCW SR 15 Waste East Infra | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-14 | 2015-05-14 | 2015-05-14 | 2018-06-21 | 2018-06-21 | All East Unitary Authorities | 0 | 134279 | 638692.24 | 479937.18 | -49306.66 | 0 | 3949.12 | 1207550.88 | 0 | 1207550.88 | 0 | [6 empty] | CM_WWI | 100%
500796 | Meadow Road WwPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-08-13 | 2016-04-29 | 2016-05-25 | 2016-08-01 | 2016-08-01 | Fife | 0 | 3180.17 | 24605.83 | 0 | 3600.07 | 0 | 0 | 31386.07 | 0 | 31386.07 | 0 | [6 empty] | CM_WWNI | 100%
403169 | Meadowbank Avenue Meadowbank Place Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-26 | 2015-08-31 | 2015-08-31 | 2015-09-02 | 2015-09-02 | City of Edinburgh | 168947 | -168800.88 | -0.21 | 0 | 0 | 0 | 0.21 | -168800.88 | 0 | 146.12 | 204193.13 | [6 empty] | CS11 | 100%
501103 | Meadowhead DAS Aesthetic and ICM WQ Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-03-28 | 2017-03-28 | 2018-06-30 | 2018-12-31 | East Ayrshire | 0 | 715 | 56584 | 220843.51 | 130823.36 | 3316.65 | 0.01 | 412282.53 | 0 | 412282.53 | 146510.66 | [6 empty] | EC10E | 2.979% | EC01G | 19.4% | EC01D | 77.62% | bar: Regulatory Outputs OMG-23
500822 | Meadowhead Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2015-12-16 | 2015-12-16 | 2019-03-06 | 2019-03-06 | North Ayrshire | 0 | 138784.81 | 41429.7 | 13260.1 | -87399.7 | 0 | 0 | 106074.91 | 0 | 106074.91 | 120964.87 | [6 empty] | CS15A | 100%
403755 | Meadowhead Inlet Works Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-03-05 | 2014-05-28 | 2014-05-20 | 2016-06-24 |  | North Ayrshire | 1968942 | 734102 | -16083.83 | -3177.12 | 0 | 0 | 0 | 714841.05 | 0 | 2683783.05 | 0 |  |  |  |  | 10865 |  | CM_WWNI | 100%
503353 | Meadowhead IW - Refurbishment of 4 No. Grit rakes (M&E) | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-07-16 | 2028-03-03 | 2028-06-05 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 23512.5 | 23512.5 | 476487.49 | 499999.99 | 0 | [6 empty] | CM_WWI | 100%
501169 | Meadowhead STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2018-08-31 | 2019-01-29 | 2020-05-14 | 2020-10-07 | North Ayrshire | 0 | 0 | 75934.72 | 264799.96 | 644526.29 | 1510771.03 | 303673 | 2799705 | 21531.17 | 2821236.17 | 0 |  |  |  |  | 520 |  | CM_WWNI | 100%
501739 | Meadowhead WwTW HCS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-11-22 | 2018-03-23 | 2018-03-26 | 2020-05-11 | 2020-08-11 | North Ayrshire | 0 | 0 | 8150.38 | 281060.11 | 779583.51 | 177482.29 | 4508.71 | 1250785 | 0 | 1250785 | 0 | [6 empty] | CM_WWI | 100%
502873 | Meavaig WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2027-04-02 | 2033-10-13 | 2034-02-03 | 2035-01-26 | 2035-04-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 21238 | 1387.35 | -18849.74 | 0 | 3775.61 | 0 | 3775.61 | 136478.56 | [6 empty] | WG1 | 100%
46836 | Meavaig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 62811.62 | 1099.5 | 0 | 0 | 0 | 0 | 0 | 1099.5 | 0 | 63911.12 | 0 | [6 empty] | DW13 | 100%
400104 | Medowhead STW Inlet Works Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-03-26 | 2014-10-27 | 2014-10-21 | 2014-10-21 | 2014-10-21 | North Ayrshire | 740196.96 | 12589.77 | -12667.92 | 0 | 0 | 0 | 0 | -78.15 | 0 | 740118.81 | 0 | [6 empty] | CM_WWNI | 100%
501869 | Megget E - Replacement of 300m of 900mm dia plus option to reline existing | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW1 | 2020-04-27 | 2021-04-12 | 2021-07-07 | 2022-12-08 | 2023-03-10 | Midlothian | 0 | 0 | 0 | 14403.05 | 1121.71 | 0 | 0 | 15524.76 | 0 | 15524.76 | 5935596.51 | [6 empty] | CS16WR | 100%
502789 | Megget Aqueduct to Bonnycraig RWM - Manor Water Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-04-02 | 2027-11-18 | 2028-01-21 | 2028-06-15 | 2028-09-15 | Scottish Borders | 0 | 0 | 0 | 12252.49 | 12747.51 | 0 | 0 | 25000 | 190340.02 | 215340.02 | 0 | [6 empty] | CM_WSI | 100%
403141 | Megget Reservoir - Interests of Safety work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2013-09-27 | 2013-10-03 | 2014-02-18 | 2014-02-18 | Scottish Borders | 263670.43 | 879.93 | 0 | 0 | 0 | 0 | 0 | 879.93 | 0 | 264550.36 | 0 | [6 empty] | CM_WSI | 100%
403678 | Megget Reservoir - Rip Rap Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-03 | 2014-08-22 | 2014-09-30 | 2014-12-12 | 2014-12-19 | Scottish Borders | 218316 | -16806.22 | 0 | 0 | 0 | 0 | 0 | -16806.22 | 0 | 201509.78 | 0 | [6 empty] | CM_WSI | 100%
500684 | Megray Inlet Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS2 | 2015-06-08 | 2018-11-30 | 2021-05-17 | 2021-06-25 | 2021-06-28 | Aberdeenshire | 0 | 40054 | 143098 | 77582.72 | 105972.42 | 0 | 0 | 366707.14 | 625721.99 | 992429.13 | 0 | [6 empty] | CM_WSI | 100%
503317 | Meigle WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-18 | 2023-09-07 | 2024-01-05 | 2025-01-02 | 2025-04-04 | Angus | 0 | 0 | 0 | 0 | 36358.8 | 38928.12 | 48700.55 | 123987.47 | 2876012.48 | 2999999.95 | 136478.56 | [6 empty] | SG1 | 100%
500790 | Meigle WwTW & SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-09-07 | 2027-07-14 | 2027-09-23 | 2028-08-09 | 2028-11-01 | Perth and Kinross | 0 | 38927 | 290174.81 | 1405.99 | 0 | -18908.49 | 19838.95 | 331438.26 | 2325219.09 | 2656657.35 | 0 | [6 empty] | CM_WWNI | 100%
502969 | Meikle Tullo WSZ - Memus Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-06-29 | 2028-04-24 | 2028-07-24 | 2029-02-26 | 2029-05-29 | Angus | 0 | 0 | 0 | 7178.94 | 7221.06 | -2763.56 | 0.02 | 11636.46 | 0 | 11636.46 | 0 | [6 empty] | CM_WSI | 100%
401600 | Meikle Wartle WWTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-12 | 2013-12-11 | 2014-02-24 | 2018-04-11 | 2018-04-11 | Aberdeenshire | 1047156.05 | 30092.95 | 11999.63 | 36768.6 | 0 | 0 | 0 | 78861.18 | 0 | 1126017.23 | 0 | [6 empty] | SG1 | 100%
500165 | Melrose DOA (DOA000072) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-12-11 | 2019-03-22 | Scottish Borders | 0 | 13273 | 41433 | 69908 | 39500 | -6043.1 | -0.02 | 158070.88 | 0 | 158070.88 | 56120.4 | [6 empty] | EC01G | 8.713% | CS16D | 42.78% | EC01D | 48.5%
503308 | Melrose WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-21 | 2030-06-18 | 2030-09-18 | Scottish Borders | 0 | 0 | 0 | 0 | 27021.53 | 6606.13 | 0 | 33627.66 | 1466372.38 | 1500000.04 | 136478.56 | [6 empty] | SG1 | 100%
502539 | Membrane Cleaning - Dunbar WWTW - MBR Tank 2 & 4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-27 | 2017-06-27 | 2017-06-28 | 2017-08-15 | 2017-08-15 | East Lothian | 0 | 0 | 36636 | 1220212.63 | 0 | 0 | 0 | 1256848.63 | 0 | 1256848.63 | 0 | [6 empty] | CM_WWNI | 100%
401029 | Membrane Replacement SR10 - Phase1 High Priority | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-06-21 | 2010-06-21 | 2010-07-19 | 2012-01-31 |  | Scottish Water Wide | 1180786.8 | -351.8 | 0 | 0 | 0 | 0 | 0 | -351.8 | 0 | 1180435 | 0 | [6 empty] | CM_WSNI | 100%
400551 | Meter Maintenance and Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-06-07 | 2010-06-14 | 2015-09-01 |  | Scottish Water Wide | 10235403.83 | -141732.59 | -79630.81 | -31414.75 | 6000 | 0 | 0 | -246778.15 | 0 | 9988625.68 | 0 | [6 empty] | CM_WSI | 100%
402257 | Metering Commission Market Changes | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-08-01 | 2013-05-29 | 2013-05-30 | 2016-08-08 | 2016-10-03 | Scottish Water Wide | 4125000 | 0 | -52307.22 | 0 | 0 | 0 | 0 | -52307.22 | 0 | 4072692.78 | 0 | [6 empty] | CS20 | 100%
503220 | Methlick WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-15 | 2030-06-12 | 2030-09-12 | Aberdeenshire | 0 | 0 | 0 | 0 | 86256.55 | 11597.62 | 0 | 97854.17 | 1402145.84 | 1500000.01 | 136478.56 | [6 empty] | SG1 | 100%
403680 | Methven - Lyndoch Road additional capacity | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2014-02-18 | 2014-02-18 | 2014-02-18 | 2015-10-12 | 2017-03-29 | Scottish Water Wide | 456837 | -333227.7 | -70000 | 62.39 | 0 | 0 | -62.39 | -403227.7 | 0 | 53609.3 | 0 | [6 empty] | WG5 | 100%
400090 | Mid Tolsta STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-11-16 | 2013-01-07 | 2013-05-28 | 2014-03-31 | 2014-03-31 | Na H-Eileanan an Iar | 773340.05 | 10677.32 | 0 | 0 | 0 | 0 | 0 | 10677.32 | 0 | 784017.37 | 8882 | [6 empty] | EC10A | 50% | WQ01 | 50%
402701 | Midfield Unst WSZ Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2012-10-09 | 2014-06-27 | 2014-08-29 | 2021-01-19 |  | Shetland Islands | 240764 | 141575 | 15760.72 | 10112.57 | 0 | 0 | 0 | 167448.29 | 0 | 408212.29 | 0 | [6 empty] | CM_WSI | 100%
45561 | Milesmark STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-09-06 | 2013-01-14 | 2013-10-31 | 2013-11-08 | Fife | 1584207.38 | 12081.18 | 20272.95 | 29614.25 | -25750 | 0 | 0 | 36218.38 | 0 | 1620425.76 | 34909.92 | [6 empty] | CM_WWNI | 12.22% | WQ01 | 87.78%
501556 | Mill Street Dingwall Relay Sewe | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2016-05-04 | 2027-07-08 | 2027-08-27 | 2027-12-24 | 2028-03-27 | Highland | 0 | 0 | 73700 | 26272.09 | 9177.39 | 0 | -119.79 | 109029.69 | 158142.33 | 267172.02 | 0 | [6 empty] | SR21_WW | 100%
500971 | Millburn Avenue Coaltown of Balgonie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-10-12 | 2016-08-30 | 2016-09-26 | 2016-11-21 | 2016-11-21 | Fife | 0 | 4172.5 | 73266.5 | 1799 | -1865.77 | 0 | 0.77 | 77373 | 0 | 77373 | 0 | [6 empty] | CM_WWI | 100%
503112 | Millglen Reservoir | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS7 | 2020-05-01 | 2020-05-11 | 2020-02-03 | 2020-05-11 | 2020-05-11 | North Ayrshire | 0 | 0 | 0 | 6697.67 | 278.85 | 87.99 | 0 | 7064.51 | 0 | 7064.51 | 821666.8 | [6 empty] | CS22 | 100%
500160 | Millport DOA (DOA000937) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-02-26 | 2016-07-01 | 2017-09-30 | 2018-01-31 | North Ayrshire | 0 | 14828 | 88779 | 27851 | -3555.34 | 0 | 0.01 | 127902.67 | 0 | 127902.67 | 10344.04 | [6 empty] | EC01G | 100% | bar: Regulatory Outputs OMG-23
503826 | Millport WwTW - FE Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2021-01-15 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 3640.19 | 44159.81 | 47800 | 0 | 47800 | 0 | [6 empty] | WWNI | 100%
503280 | Millport WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-01-15 | 2029-05-18 | 2030-05-16 | 2030-08-16 | North Ayrshire | 0 | 0 | 0 | 0 | 77728.06 | 3854.89 | 0 | 81582.95 | 1418417.04 | 1499999.99 | 136478.56 | [6 empty] | SG1 | 100%
500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS6 | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-29 | 2019-03-01 | Glasgow City | 332.03 | 128254.97 | 7761 | 199420 | 336716.28 | 3347.57 | 0 | 675499.82 | 0 | 675831.85 | 738217.43 | [6 empty] | CM_WSI | 29% | DW5 | 71%
500839 | Milngavie C2 RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-10-28 | 2017-03-23 | 2017-03-31 | 2018-03-31 | 2020-02-29 | Glasgow City | 0 | 18193 | 40657.62 | 152632.69 | 44644.09 | 4283.07 | 716.93 | 261127.4 | 0 | 261127.4 | 189290.41 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 28.28
500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS6 | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2018-05-09 | 2020-04-01 | Glasgow City | 332.03 | 136786.97 | 234253 | 574625 | 360420.76 | 8624.9 | 27.35 | 1314737.98 | 0 | 1315070.01 | 1747057.34 | [6 empty] | DW5 | 46.08% | DW5FS | 53.92%
503168 | Milngavie C3 RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-02-28 | 2016-03-31 | 2016-08-22 | 2022-01-25 | 2022-04-27 | East Dunbartonshire | 0 | 0 | 0 | 0 | 54152.01 | 2000.01 | 0 | 56152.02 | 0 | 56152.02 | 873528.67 | [6 empty] | DW5FS | 100%
500009 | Milngavie C4 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-09-25 | 2018-12-19 | Glasgow City | 332.03 | 60038.97 | 214299 | 172131 | 320158.41 | -86611.22 | 592.87 | 680609.03 | 0 | 680941.06 | 539345.26 | [6 empty] | DW5 | 100%
500840 | Milngavie C4 RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-12-10 | 2017-03-23 | 2017-03-24 | 2019-01-31 | 2019-08-31 | Glasgow City | 0 | 5268 | 29890.62 | 80702.37 | 53231.09 | 4061.72 | 1064.41 | 174218.21 | 0 | 174218.21 | 33798.86 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 6.91
503169 | Milngavie C4 RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-02-28 | 2016-03-30 | 2016-03-30 | 2022-01-25 | 2022-04-27 | East Dunbartonshire | 0 | 0 | 0 | 0 | 62977 | 2000 | 0 | 64977 | 0 | 64977 | 539345.26 | [6 empty] | DW5FS | 100%
500010 | Milngavie M1 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS6 | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2019-03-22 | 2020-04-01 | Glasgow City | 332.03 | 187144.97 | 591927.09 | 275470.71 | 96295.7 | 6731.94 | 0 | 1157570.41 | 0 | 1157902.44 | 1606002.05 | [6 empty] | CM_WSI | 34.57% | DW5 | 65.43%
503170 | Milngavie M1 RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-02-28 | 2016-03-31 | 2016-03-31 | 2020-03-31 | 2020-04-30 | East Dunbartonshire | 0 | 0 | 0 | 0 | 49085.77 | 2471.03 | 32175.08 | 83731.88 | 28065.19 | 111797.07 | 1414613.63 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 42.03
500863 | Milngavie M4C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-09-20 | 2018-06-27 | 2018-09-12 | 2019-03-31 | 2019-08-31 | Glasgow City | 0 | 18259.61 | 28121.72 | 58974.12 | 134780.58 | 13009.48 | 0 | 253145.51 | 0 | 253145.51 | 1058349.63 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 45.63
500887 | Milngavie South Moorhouse RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-10-13 | 2018-09-21 | 2018-10-25 | 2019-06-30 | 2020-02-29 | East Renfrewshire | 0 | 6404.84 | 2646.27 | 6920.97 | 93249.68 | 14297.66 | 645.58 | 124165 | 0 | 124165 | 503405.31 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 42.45
503475 | Milngavie WOA - Keppochhill Road DMA - Borron Tunnel Condition | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | GW1 | 2021-04-01 | 2022-02-14 | 2022-05-13 | 2023-12-08 | 2024-03-11 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 13730.02 | 13730.02 | 253270.01 | 267000.03 | 0 | [6 empty] | CM_WSI | 4.762% | CM_M&G | 95.24%
504919 | Milngavie WOA - M1 PRV Design & Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-01-31 |  | 2020-08-01 | 2020-08-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 27500 | 22500 | 50000 | 0 | 50000 | 0 | [6 empty] | WSNI | 100%
501074 | Milngavie WOA C2 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-27 | 2028-04-03 | 2028-05-16 | 2029-07-24 | 2030-04-24 | Glasgow City | 0 | 61056 | 14211.95 | 4143 | 12425.59 | -17153.66 | 22075.52 | 96758.4 | 2041284.9 | 2138043.3 | 0 | [6 empty] | CM_WSI | 100%
501073 | Milngavie WOA C3 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501072 | Milngavie WOA C5 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-13 | 2031-09-16 | 2031-10-29 | 2032-04-05 | 2032-06-14 | Glasgow City | 0 | 9720 | 17227.58 | 26577.42 | 54627.77 | 0 | 0 | 108152.77 | 271575.53 | 379728.3 | 0 | [6 empty] | CM_WSI | 100%
501071 | Milngavie WOA M2 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-27 | 2028-03-09 | 2028-04-26 | 2029-03-06 | 2029-12-13 | Glasgow City | 0 | 37440 | 42780 | 6000 | 106606 | -114553.77 | 134245.47 | 212517.7 | 1319311.3 | 1531829 | 0 | [6 empty] | CM_WSI | 100%
501075 | Milngavie WOA M4 Mugdock C WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
505390 | Milngavie WTW - Drainage Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2020-08-04 | 2020-09-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 2090.51 | 27909.5 | 30000.01 | 0 | 30000.01 | 0 | [6 empty] | CM_WSNI | 100%
403966 | Milngavie WTW Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2014-10-16 | 2015-06-25 | 2015-06-25 | 2016-07-21 |  | East Renfrewshire | 594719 | 1276918 | 223864.73 | 79588 | -2685.72 | 2333.45 | -1720.64 | 1578297.82 | 0 | 2173016.82 | 0 | [6 empty] | CM_WSNI | 100%
502793 | Milroy Gardens Pipe Bridge Bellshill | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS1 | 2018-02-26 | 2020-07-27 | 2020-10-28 | 2021-05-17 | 2021-08-19 | North Lanarkshire | 0 | 0 | 0 | 16244.04 | 25656.96 | 69302.42 | 331156.94 | 442360.36 | 51226.64 | 493587 | 0 | [6 empty] | CM_WWI | 100%
502974 | Milton of Panholes WwTW - Growth - Interim Solution | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2020-07-22 | 2021-09-03 | 2022-01-03 | 2022-08-15 | 2022-11-15 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 46467.14 | 46467.14 | 508492 | 554959.14 | 136478.56 | [6 empty] | SG1 | 100%
501109 | Mini Excavators trailers and breakers | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 2016-06-30 | 2017-05-15 | Scottish Water Wide | 0 | 987186.22 | 506 | 0 | 0 | 0 | 0 | 987692.22 | 0 | 987692.22 | 0 | [6 empty] | CM_M&G | 100%
500230 | Mintlaw WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2018-04-27 | 2021-03-08 | 2021-07-19 | 2022-07-29 | 2022-10-31 | Aberdeenshire | 0 | 64339.51 | 20868.31 | 39931.07 | 27352.65 | 136090.94 | 271554.45 | 560136.93 | 2253501.07 | 2813638 | 136478.56 | [6 empty] | CM_WWNI | 14% | SG1 | 86%
500501 | Mobile Turbo Actiflo Water Treatment Unit | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2015-06-08 | 2015-06-08 | 2015-06-08 | 2016-09-08 | 2016-09-08 | Scottish Water Wide | 0 | 329499 | 249835.18 | 0 | 196.08 | 0 | 0 | 579530.26 | 0 | 579530.26 | 638845.62 | [6 empty] | CS16WR | 100%
403898 | Mobilisation of Amey Black & Veatch (aBV) Wastewater Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | WWINF | Management and General | MS3 | 2014-07-25 | 2014-10-08 | 2014-10-08 |  |  | Scottish Water Wide | 1544206.72 | 1101002.28 | -1476785.52 | -1018423.48 | 0 | 0 | 0 | -1394206.72 | 0 | 150000 | 0 | [6 empty] | CM_M&G | 100%
403884 | Mobilisation of Caledonia Water Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | WINF | Management and General | MS3 | 2014-07-25 | 2014-10-08 | 2014-10-08 | 2021-06-30 | 2021-06-30 | Scottish Water Wide | 2200000 | 0 | 2526911.48 | 376948.12 | -3341838.6 | 204796.84 | -2406.25 | -235588.41 | -1093.75 | 1963317.84 | 0 | [6 empty] | CM_M&G | 100%
500942 | Mobilisation of ESD Non Infra Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | NONINF | Management and General | MS3 | 2015-09-30 | 2015-10-21 | 2015-12-01 |  | 2021-04-30 | Scottish Water Wide | 0 | 0 | 1538913.88 | 2184600.95 | -2174084.69 | 383813.11 | 0 | 1933243.25 | 0 | 1933243.25 | 0 | [6 empty] | QS4EQS | 50% | QS4EQW | 50%
501800 | Modelling - 1 in 30 Review Sewer Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-03-20 | 2021-08-02 | 2021-12-03 | 2022-11-28 | 2023-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 57443.5 | 57443.5 | 1125985.18 | 1183428.68 | 9297166.67 | [6 empty] | CS11A | 100%
502609 | Monifeith Bathing Water Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-03-15 | 2017-06-16 | 2017-06-16 | 2017-11-30 | 2018-03-31 | Angus | 0 | 0 | 314.02 | 30565.42 | -1456.41 | 0 | 0 | 29423.03 | 0 | 29423.03 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
502646 | Monitoring and Reporting of Scottish Water Assets impacting bathing waters part 2 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS6 | 2017-04-11 | 2017-04-11 | 2017-06-26 | 2018-08-17 | 2018-08-17 | Scottish Water Wide | 0 | 0 | 0 | 357386.81 | 7656.34 | 0 | 0 | 365043.15 | 0 | 365043.15 | 0 | [6 empty] | EC16 | 100%
403546 | Monitoring and Reporting of Scottish Water Assets Impacting BW Quality | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-30 | 2016-01-18 | 2016-02-29 | 2016-12-01 | 2017-02-01 | Scottish Water Wide | 69955 | 80379 | 142500.64 | 12766 | 66.95 | 0 | 0 | 235712.59 | 0 | 305667.59 | 540220 | [6 empty] | EC16 | 100%
503691 | Monitoring Disinfection By-products in Chloraminated Supplies | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2019-09-16 | 2019-09-16 | 2019-09-17 |  | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 220000 | 0 | 220000 | 0 | [6 empty] | CM_M&G | 100%
502221 | Montgarrie ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS2 | 2017-11-27 | 2020-03-31 | 2020-10-20 | 2021-10-22 | 2021-10-22 | Aberdeenshire | 0 | 0 | 36096.34 | 27842.56 | 76651.28 | 122057.14 | 342601.24 | 605248.56 | 233678.7 | 838927.26 | 136478.56 | [6 empty] | SG1 | 100%
502954 | Montrose WwTW - Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-11-27 | 2018-03-14 | 2018-03-26 | 2018-06-29 | 2018-06-29 | Angus | 0 | 0 | 0 | 179401.67 | 820806.03 | 1053.46 | 1446.54 | 1002707.7 | 0 | 1002707.7 | 0 | [6 empty] | CM_WWNI | 100%
500499 | Montrose WwTW - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-05-21 | 2019-10-02 | 2019-10-28 | 2021-10-29 | 2022-01-25 | Angus | 0 | 143901 | 122582.39 | 88815.87 | 243720.59 | 400407.15 | 757082.29 | 1756509.29 | 120399.69 | 1876908.98 | 0 | [6 empty] | CM_WWNI | 100%
502334 | Monymusk WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-24 | 2019-04-15 | Aberdeenshire | 0 | 0 | 38549.52 | 2466.9 | 0 | 0 | 0 | 41016.42 | 0 | 41016.42 | 136478.56 | [6 empty] | SG1 | 100%
500926 | Moray Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2018-11-30 | 2018-11-30 | 2018-11-30 | 2018-11-30 | Moray | 0 | 6000 | 4712.79 | -2979.67 | -701.67 | 0 | -0.05 | 7031.4 | 0 | 7031.4 | 120964.87 | [6 empty] | CS15A | 100%
501022 | Morebattle STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2015-12-14 | 2020-09-07 | 2020-11-02 | 2022-07-04 | 2022-11-25 | Scottish Borders | 0 | 20575 | 269789.31 | 96827.67 | 59950.61 | 309005.15 | 946531.28 | 1702679.02 | 1211333.94 | 2914012.96 | 0 | [6 empty] | CM_WWNI | 100%
402712 | Morphie WSZ Low Pressure Enhancement WSZ001115 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-03 | 2014-12-05 | 2014-12-16 | 2015-06-25 | 2015-03-23 | Aberdeenshire | 61387 | 2983 | -0.11 | -342.47 | 0 | 0 | 0 | 2640.42 | 0 | 64027.42 | 4258 | [6 empty] | CS1 | 100%
403434 | Moss Street Keith | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-16 | 2014-09-03 | 2014-10-10 | 2015-05-22 | 2015-05-22 | Moray | 804635 | 139977.66 | 29.67 | 658.56 | 0 | 0 | 0 | 140665.89 | 0 | 945300.89 | 204193.13 | [6 empty] | CS11A | 100%
45806 | Motehill SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-05-27 | 2011-02-21 | 2012-01-11 | 2012-03-23 | Scottish Water Wide | 3983.13 | 365.87 | 0 | 0 | 0 | 0 | 0 | 365.87 | 0 | 4349 | 0 | [6 empty] | WQ01C | 100%
403602 | Mowbray Gardens Crossgates Cowdenbeath | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-10-23 | 2015-02-27 | 2015-03-31 | 2015-07-23 | 2015-07-23 | Fife | 98510 | 264270.66 | 5919.34 | 0 | 69265.89 | 0 | 0.12 | 339456.01 | 0 | 437966.01 | 204193.13 | [6 empty] | CS11 | 100%
501714 | MSI PFI Inverclyde WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2016-07-29 | 2020-06-01 | 2020-08-03 | 2021-02-15 | 2028-03-27 | Inverclyde | 0 | 0 | 33248 | -8828 | 0 | 11741 | 412831.56 | 448992.56 | 0 | 448992.56 | 0 | [6 empty] | SR21_WW | 100%
403047 | Muchalls Marine Terrace rising main and BPT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-06 | 2013-06-27 | 2013-07-29 | 2014-04-08 |  | Aberdeenshire | 83300.92 | 0.08 | -718.3 | 0 | 0 | 0 | -0.08 | -718.3 | 0 | 82582.62 | 0 | [6 empty] | CM_WWI | 100%
45555 | Muckhart STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-06-01 | 2011-07-28 | 2012-04-07 | 2013-02-06 | Clackmannanshire | 786725.35 | 2001.54 | 0 | 0 | 0 | 0 | 0 | 2001.54 | 0 | 788726.89 | 0 | [6 empty] | CM_WWNI | 6.398% | WQ01 | 93.6%
503603 | Muckhart WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-03-02 | 2023-10-10 | 2024-02-12 | 2025-09-05 | 2025-10-29 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 83163.11 | 42950.92 | 126114.03 | 1873885.96 | 1999999.99 | 136478.56 | [6 empty] | SG1 | 100%
504655 | Mugdock Reservoir Vegetation Clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 107.65 | 0 | 107.65 | 0 | 107.65 | 0 | [6 empty] | CM_WSI | 100%
505109 | Muir of Ord WwTW - Install MLSS Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WWNI | 100%
502421 | Muirdrum WwTW Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2020-06-12 | 2020-08-05 | 2020-08-06 | 2020-08-06 | 2020-08-06 | Angus | 0 | 0 | 15069.77 | 628.53 | 4087.27 | 0 | 19785.57 | 39571.14 | 0 | 39571.14 | 0 | [6 empty] | CM_WWNI | 100%
500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-01 | 2019-03-01 | Renfrewshire | 0 | 44645 | 187355 | 305651.58 | 559147.36 | 339665.02 | 1179637.08 | 2616101.04 | 28999.99 | 2645101.03 | 3607589.06 | [6 empty] | DW5FS | 100%
501535 | Muirdykes No2 Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-17 | 2029-09-24 | 2030-01-28 | 2030-09-12 | 2030-12-13 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860519.06 | 860519.06 | 0 | [6 empty] | CM_WSNI | 100%
501536 | Muirdykes No3 Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-21 | 2030-01-25 | 2030-09-11 | 2030-12-12 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417966.04 | 417966.04 | 0 | [6 empty] | CM_WSNI | 100%
501069 | Muirdykes WOA Foxbar Hollowhouse WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-06-01 | 2028-04-27 | 2028-06-20 | 2029-07-17 | 2029-10-17 | East Renfrewshire | 0 | 88272 | 12853 | 7283 | 1719.56 | 14585.1 | 0 | 124712.66 | 2277149.35 | 2401862.01 | 0 | [6 empty] | CM_WSI | 100%
501068 | Muirdykes WOA Stanely WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-12 | 2016-04-12 | 2016-04-12 | 2016-04-12 | 2016-04-12 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403955 | Muirdykes WTW | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS5 | 2015-01-28 | 2015-07-31 | 2015-08-24 | 2017-12-31 | 2018-12-31 | Renfrewshire | 13000 | 4236033.98 | 10772967 | 1092460.44 | 109.29 | 830331.23 | 555098.1 | 17487000.04 | 0 | 17500000.04 | 12121303 |  |  |  |  | 179670 |  | DW3C | 0.14% | DW3H | 0.31% | DW23 | 99.55% | bar: Regulatory Outputs OMG-03
500575 | Muirdykes WTW CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2016-06-01 | 2020-06-08 | 2020-07-30 | 2021-11-26 | 2022-02-14 | Renfrewshire | 0 | 22338.8 | 119869.52 | 111428.68 | -127103.62 | 217242 | 2078801.64 | 2422577.02 | 77422.98 | 2500000 | 0 | [6 empty] | CM_WSNI | 100%
500914 | Muiresk (Turriff WTW) RWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-11-06 | 2028-02-01 | 2028-05-16 | 2028-09-27 | 2028-12-26 | Aberdeenshire | 0 | 5904.44 | 44390.19 | -4838.16 | 9042.77 | 24956.49 | 0 | 79455.73 | 21901.7 | 101357.43 | 0 | [6 empty] | CM_WSNI | 100%
45793 | Muirhead SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2010-12-21 | 2011-03-25 | 2011-12-19 | 2012-01-31 | Angus | 565017.8 | 175.52 | 0 | 0 | 0 | 0 | 0 | 175.52 | 0 | 565193.32 | 0 | [6 empty] | CM_WWNI | 5.014% | WQ01B | 5.015% | WQ01C | 89.97%
503207 | Mulben Craighead ST ecological treatment system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2018-09-05 | 2021-03-08 | 2021-12-01 | 2022-08-31 | 2022-12-21 | Moray | 0 | 0 | 0 | 0 | 26314.1 | 42708.1 | 2129.15 | 71151.35 | 115848.64 | 186999.99 | 0 | [6 empty] | CM_WWNI | 100%
501120 | MULTIPLE - CHEMICAL DOSING PROGRAMME Phase 1 Year 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWMD | Water Non infrastructure | MS7 | 2015-11-05 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-12 | Scottish Water Wide | 0 | 30896 | 62243.94 | 75423.23 | 11889.09 | 0 | -69.22 | 180383.04 | 0 | 180383.04 | 0 | [6 empty] | CM_M&G | 49.14% | CM_WSNI | 50.86%
500028 | Multiple - GAC Replacement Programme - Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-27 | 2015-04-28 | 2015-06-23 | 2017-10-09 | 2017-12-01 | Scottish Water Wide | 0 | 1550664 | 1276315.48 | 312182.12 | -1158.51 | 0 | 0 | 3138003.09 | 0 | 3138003.09 | 0 | [6 empty] | CM_WSNI | 100%
501772 | Multiple - GAC Replacement Programme Phase 2 Years 3 - 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-12-08 | 2017-03-22 | 2017-07-27 | 2019-09-03 | 2020-01-20 | Scottish Water Wide | 0 | 0 | 254977.55 | 1114203.37 | 1380331.58 | 193301.98 | 0 | 2942814.48 | 0 | 2942814.48 | 0 | [6 empty] | CM_WSNI | 100%
502245 | MULTIPLE - GAC REPLACEMENT PROGRAMME Phase 3 Years 5 & 6 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-04-15 | 2019-04-15 | 2019-05-02 | 2021-06-16 | 2021-09-16 | Scottish Water Wide | 0 | 0 | 3284.15 | -17.83 | 4114.81 | 1129363.44 | 1175299.06 | 2312043.63 | 381548.01 | 2693591.64 | 0 | [6 empty] | CM_WSNI | 100%
502175 | Multiple - High Voltage Programme Phase 1 (Lomond Scheme) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-04-25 | 2027-08-06 | 2027-08-06 | 2028-09-29 | 2028-09-29 | Scottish Water Wide | 0 | 0 | 159385.81 | 313796.99 | 14013.06 | 0 | 0 | 487195.86 | 7512804.11 | 7999999.97 | 0 | [6 empty] | CM_WSNI | 100%
501675 | MULTIPLE - HIGH VOLTAGE PROGRAMME Phase 2 (Mannofield) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2016-10-14 | 2016-10-14 | 2017-05-29 | 2022-11-22 | 2023-02-22 | Aberdeen City | 0 | 0 | 0 | 3582.97 | 3192.16 | 2742.3 | 19097.16 | 28614.59 | 21385.44 | 50000.03 | 0 |  |  |  |  | 50000 |  | CM_WSNI | 100%
500029 | Multiple - Membrane Programme Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-02-27 | 2015-04-28 | 2015-07-07 | 2018-06-18 | 2018-06-18 | Scottish Water Wide | 135.86 | 4177771.14 | 1928293.73 | 1073446.9 | 7997.69 | 298114.1 | 197.12 | 7485820.68 | 0 | 7485956.54 | 0 | [6 empty] | CM_WSNI | 100%
501771 | Multiple - Membrane Programme Phase 2 Years 3 & 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2016-12-28 | 2017-05-31 | 2017-06-26 | 2019-07-05 | 2019-07-05 | Scottish Water Wide | 0 | 0 | 67764.79 | 4358385.76 | 4387706.85 | 1044707.65 | 0.04 | 9858565.09 | 0 | 9858565.09 | 0 | [6 empty] | CM_WSNI | 100%
502244 | Multiple - Membrane Programme Phase 3 Years 5 & 6 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-04-17 | 2019-04-17 | 2019-05-08 | 2021-06-22 | 2021-11-16 | Scottish Water Wide | 0 | 0 | 8992.45 | 972.02 | 5090.89 | 3922739.53 | 7530549.07 | 11468343.96 | 1335027.37 | 12803371.33 | 0 | [6 empty] | CM_WSNI | 100%
503713 | Multiple sites Chemical Dosing H&S Programme Programme Costs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-03-19 | 2021-04-12 | 2021-07-26 | 2021-12-10 | 2022-02-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2003.12 | 2361.88 | 4365 | 1120634.99 | 1124999.99 | 0 | [6 empty] | CM_M&G | 14.3% | CM_WSNI | 85.7%
501752 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-03-21 | 2020-11-09 | 2020-12-04 | 2022-05-09 | 2022-06-13 | Scottish Water Wide | 0 | 15426.5 | 6578.3 | 3226 | 146024.06 | 292494.79 | 1045019.24 | 1508768.89 | 1491230.48 | 2999999.37 | 0 | [6 empty] | CM_M&G | 16.67% | CM_WSNI | 83.33%
501753 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-01 | 2020-02-03 | 2020-03-13 | 2024-03-29 | 2024-06-28 | Scottish Water Wide | 0 | 0 | 28856.57 | 4496.19 | 161677.07 | 276097.6 | 4707205.57 | 5178333 | 0 | 5178333 | 0 | [6 empty] | CM_M&G | 9.677% | CM_WSNI | 90.32%
501754 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2025-03-31 | 2026-01-30 | 2026-04-23 | 2028-01-14 | 2028-04-13 | Scottish Water Wide | 0 | 0 | 62288.37 | 349.36 | 2895.31 | 80862.58 | 432.78 | 146828.4 | 4597526.57 | 4744354.97 | 0 | [6 empty] | CM_M&G | 6.452% | CM_WSNI | 93.55%
501755 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2025-03-31 | 2025-06-24 | 2025-07-23 | 2026-06-10 | 2026-07-14 | Scottish Water Wide | 0 | 0 | 50857.53 | 438.51 | 1523.26 | 69160.42 | 0 | 121979.72 | 2017236.3 | 2139216.02 | 0 | [6 empty] | CM_WWI | 32.99% | CM_WSNI | 67.01%
503091 | Murray TWP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-07-19 | 2028-09-20 | 2029-01-15 | 2029-08-27 | 2029-11-27 | North Lanarkshire | 0 | 0 | 0 | 16137.21 | 897.38 | 4743.25 | 15933.55 | 37711.39 | 765288.57 | 802999.96 | 0 | [6 empty] | CM_WSNI | 100%
502614 | Murrayshall Scone Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | Perth and Kinross | 0 | 0 | 3696.28 | 27494.71 | 10969.45 | 0 | -0.04 | 42160.4 | 0 | 42160.4 | 0 | [6 empty] | CM_WWI | 100%
500249 | Myreside to Morham Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-06-09 | 2019-03-20 | 2019-04-29 | 2020-12-15 | 2020-12-16 | East Lothian | 0 | 65357 | 55269.08 | 97403.45 | 258941.77 | 1504642.54 | 37005.01 | 2018618.85 | 0 | 2018618.85 | 0 | [6 empty] | CM_WSI | 100%
504588 | N TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-02-07 | 2022-01-31 | 2022-07-08 | 2024-01-19 | 2024-04-22 | - | 0 | 0 | 0 | 0 | 0 | 3962.59 | 777432.76 | 781395.35 | 0 | 781395.35 | 0 | [6 empty] | CM_WSNI | 100%
501665 | N Uist - Ashdail Cottages Sewer Rehab - Replace PF sewers | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS2 | 2016-08-31 | 2017-03-27 | 2027-07-08 | 2027-04-01 | 2027-04-01 | Na H-Eileanan an Iar | 0 | 0 | 17170.11 | 3623.98 | 0 | 3977.24 | 0 | 24771.33 | 115234.53 | 140005.86 | 0 | [6 empty] | SR21_WW | 100%
505110 | N/W/NI/100220-Aultbea WTW- Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 | 2020-08-13 | 2021-04-02 | 2021-07-16 | Highland | 0 | 0 | 0 | 0 | 0 | 1174.04 | 0 | 1174.04 | 0 | 1174.04 | 0 | [6 empty] | CM_WSNI | 100%
505148 | N/W/NI-100220-Multiple North Sites- Outstation Replacements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS2 |  | 2020-02-17 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Highland | 0 | 0 | 0 | 0 | 0 | 3207.22 | 0 | 3207.22 | 0 | 3207.22 | 0 | [6 empty] | CM_WWNI | 100%
504277 | N_W_NI_101219_Colonsay WTW_Audit risks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-16 |  |  |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2526.71 | 17473.29 | 20000 | 0 | 20000 | 0 | [6 empty] | WSNI | 100%
501175 | N179 Merchant Quarter Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2016-10-17 | 2018-08-13 | 2018-08-20 | 2018-08-22 | 2018-08-22 | Aberdeen City | 0 | 26930 | 454433.2 | -118577.2 | -354921.46 | 1388.61 | -1334.28 | 7918.87 | 0 | 7918.87 | 196097.17 | [6 empty] | CS11A | 100%
500162 | Nairn DOA (DOA000470) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-12-21 | 2018-03-29 | Highland | 0 | 45798 | 145814 | 67183 | -2328.05 | 0 | 0 | 256466.95 | 0 | 256466.95 | 10344.04 | [6 empty] | EC01G | 41.75% | CS16D | 58.25%
503264 | Nairn Moss Side Road Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2018-06-26 | 2018-08-27 | 2018-09-24 | 2019-09-10 | 2019-09-10 | Highland | 0 | 0 | 0 | 0 | 475300.84 | 50485.05 | -323.2 | 525462.69 | 0 | 525462.69 | 0 | [6 empty] | CM_WSI | 100%
500188 | Nairn odour (STW003728) | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWD | Odour | MS7 | 2015-03-16 | 2015-06-26 | 2015-06-29 | 2015-06-30 | 2015-06-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
46359 | Nairn WWTP Refurb - STW001283 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-28 | 2012-01-17 | 2011-10-10 | 2013-05-08 |  | Highland | 1214920.55 | -364.04 | 0 | 0 | 0 | 0 | 0 | -364.04 | 0 | 1214556.51 | 0 | [6 empty] | CM_WWNI | 100%
500586 | Nairn WWTW - Ventilation Project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-19 | 2015-07-24 | 2015-08-31 | 2015-12-10 | 2015-12-11 | Highland | 0 | 254887.96 | 0 | 0 | 0 | 0 | 0 | 254887.96 | 0 | 254887.96 | 0 | [6 empty] | CM_WWNI | 100%
504628 | Nam Bat DSR Power Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-15 | 2020-08-06 | 2021-01-13 | 2021-02-10 | Highland | 0 | 0 | 0 | 0 | 0 | 3504.76 | 0 | 3504.76 | 0 | 3504.76 | 0 | [6 empty] | CM_WSNI | 100%
403425 | National Operations Centre - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-04-30 | 2013-04-30 | 2013-05-02 | 2015-07-27 |  | Scottish Water Wide | 5296295.2 | -2547.01 | 0 | 5433 | 0 | 0 | -5433 | -2547.01 | 0 | 5293748.19 | 0 | [6 empty] | CM_M&G | 100%
501015 | NE176 - Kings Gate Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS5 | 2018-01-29 | 2019-02-12 | 2019-04-08 | 2019-07-30 | 2019-07-30 | Aberdeen City | 0 | 38030 | 24065.42 | 33343.78 | 138118.8 | 276543.16 | -1564.16 | 508537 | 1813.9 | 510350.9 | 204193.13 | [6 empty] | CS11 | 100%
503289 | NE179 Merchant Quarter Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2020-02-18 | 2021-01-11 | 2021-03-02 | 2022-02-14 | 2022-05-17 | Aberdeen City | 0 | 0 | 0 | 0 | 543000 | 914286.92 | 375107.97 | 1832394.89 | 3505509.11 | 5337904 | 196097.17 | [6 empty] | CS11A | 100%
501636 | NE18 - Marshall Place Scott Street Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2021-12-24 | 2022-03-22 | 2022-10-28 | 2023-01-13 | Perth and Kinross | 0 | 21530 | 794.22 | 1675.78 | 9000 | 20227.27 | 49974.09 | 103201.36 | 496798.64 | 600000 | 196097.17 | [6 empty] | CS11A | 100%
500747 | NE188 - Fiskens Kia Queenswell Road Forfar - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-03-27 | 2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-04-06 | Angus | 0 | 22000 | 37647.26 | 16790.45 | 26562.29 | -102999 | 0.01 | 1.01 | 0 | 1.01 | 204193.13 | [6 empty] | CS11 | 100%
502348 | NE205 Brunswick Place Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-18 | 2021-07-26 | 2021-09-27 | 2022-03-07 | 2022-06-06 | Aberdeen City | 0 | 0 | 0 | 0 | 105000 | 152919.69 | 25851.76 | 283771.45 | 734367.56 | 1018139.01 | 196097.17 | [6 empty] | CS11A | 100%
500746 | NE21 - Church Street-Feus Road Perth - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2021-12-27 | 2022-03-22 | 2022-10-21 | 2023-01-13 | Perth and Kinross | 0 | 23000 | 31382.88 | 16580.8 | 48606.61 | 20033.1 | 49723.46 | 189326.85 | 460673.15 | 650000 | 204193.13 | [6 empty] | CS11 | 100%
502347 | NE210 5-7 Main Road Cardenden Lochgelly | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-01-16 | 2019-01-16 | Fife | 0 | 0 | 0 | 22000 | -16737.42 | 6243.19 | -11504.77 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
502889 | NE223 South Street Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2021-12-27 | 2022-03-22 | 2022-10-27 | 2023-01-13 | Perth and Kinross | 0 | 0 | 0 | 0 | 52000 | 17923.05 | 33220.13 | 103143.18 | 196856.82 | 300000 | 196097.17 | [6 empty] | CS11A | 100%
500500 | NE235 - Mercat Centre and Esplanade Kirkcaldy | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-08-12 | 2019-08-12 | 2019-07-18 | 2019-07-18 | 2019-07-18 | Fife | 0 | 20500 | 4681.78 | 29818.22 | 11000 | -46402.2 | -19596.8 | 1 | 0 | 1 | 279997.17 | [6 empty] | CS11 | 100%
501018 | NE244 - Bayview Court Seatown Cullen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-11-27 | 2019-04-11 | 2019-04-11 | 2019-01-16 | 2018-01-16 | Moray | 0 | 26893 | 39072.99 | 38223.01 | -104188 | 0 | 0 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500677 | NE261 - Albert Street Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-23 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Dundee City | 0 | 42930 | 12119.4 | -55049.4 | 0 | 0 | 1 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
503602 | NE297 - Lochside Road Forfar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-05 | 2022-05-19 | 2022-09-21 | 2024-04-16 | 2024-06-07 | Angus | 0 | 0 | 0 | 0 | 0 | 16840.55 | 103378.99 | 120219.54 | 179780.45 | 299999.99 | 196097.17 | [6 empty] | CS11A | 100%
500089 | NE347 - Links Street Kirkcaldy | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-01-21 | 2019-01-21 | Fife | 0 | 10025 | 13092.19 | 17132.81 | -40249 | 5818.25 | -5818.25 | 1 | 0 | 1 | 1834034.34 | [6 empty] | CS11 | 100%
502890 | NE531 Dundonald Street Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-06-17 | 2021-06-11 | 2021-08-25 | 2022-03-29 | 2022-06-29 | Dundee City | 0 | 0 | 0 | 0 | 81000 | 19000 | 2920 | 102920 | 17080.08 | 120000.08 | 196097.17 | [6 empty] | CS11A | 100%
500998 | NE538 - Peel Cottage Station Road Longforgan Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2019-07-11 | 2020-03-31 | 2020-06-22 | 2020-11-13 | 2020-11-13 | Perth and Kinross | 0 | 22430 | 32002.89 | 45567.11 | 43000 | 153282 | 335136.87 | 631418.87 | 0 | 631418.87 | 204193.13 | [6 empty] | CS11 | 100%
503697 | NE60 Cavendish Avenue area Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2022-10-26 | 2023-02-28 | 2024-09-23 | 2024-11-14 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 12067.27 | 33360.73 | 45428 | 1154572 | 1200000 | 120964.87 | [6 empty] | CS15A | 100%
501254 | NE707 - Loch Leven Fisheries Pier Road Kinross | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2017-08-07 | 2018-01-29 | 2018-01-30 | 2018-02-08 | 2018-02-08 | Perth and Kinross | 0 | 29930 | 24915.34 | 10650.49 | -65375.98 | 0 | -118.85 | 1 | 0 | 1 | 42315.92 | [6 empty] | CS11 | 100%
500656 | NE8 - Dundee Loan Forfar | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2016-11-21 | 2016-11-21 | 2016-11-18 | 2016-06-28 | 2016-11-18 | - | 0 | 60770 | -60770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11 | 100%
502888 | NE85 Lynedoch Road | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2019-09-24 | 2019-09-24 | 2019-08-14 | 2019-08-14 | 2019-08-14 | - | 0 | 0 | 0 | 0 | 61000 | -60999 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CS11A | 100%
502971 | Neilston Main Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-02 | 2028-01-27 | 2028-04-28 | 2029-05-24 | 2029-08-24 | Glasgow City | 0 | 0 | 0 | 24867.85 | 7699.07 | 22497.67 | -64.59 | 55000 | 2145000.06 | 2200000.06 | 0 | [6 empty] | CM_WSI | 100%
30535 | Neilston STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 2015-03-12 | East Renfrewshire | 962475.53 | 1008 | 0 | 0 | 0 | 0 | 0 | 1008 | 0 | 963483.53 | 0 | [6 empty] | EC04A | 100%
500026 | Neilston WOA Neilston Low CWT WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-23 | 2016-08-01 | 2016-09-12 | 2017-05-17 | 2017-05-31 | Glasgow City | 332.03 | 75903.97 | 470076 | 51298 | 19882.82 | 1159.38 | 0 | 618320.17 | 0 | 618652.2 | 0 | [6 empty] | CM_WSI | 100%
502137 | Neilston WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2016-07-06 | 2016-07-07 | 2016-09-30 | 2016-09-30 | East Renfrewshire | 0 | 0 | 3069.53 | 245.28 | 0 | 0 | 0 | 3314.81 | 0 | 3314.81 | 4434.64 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503135 | Neilston WTW - New Service Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-06-08 | 2028-10-10 | 2029-05-22 | 2029-08-22 | East Renfrewshire | 0 | 0 | 0 | 0 | 8447.47 | 39986.78 | -5434.24 | 43000.01 | 238000.05 | 281000.06 | 0 | [6 empty] | CM_WSNI | 100%
401917 | Neilston WTW Closure Strategic Solution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-02-04 | 2011-12-20 | 2012-02-20 | 2014-11-05 | 2014-11-05 | East Renfrewshire | 4082651.78 | 130122.58 | 122432.28 | -111378.87 | -68996.14 | 144.23 | 68906.16 | 141230.24 | 0 | 4223882.02 | 0 | [6 empty] | CM_WSNI | 100%
45641 | Neilston WTW Refurb - WTW000188 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-24 | 2011-06-30 | 2011-06-30 | 2011-03-31 |  | East Renfrewshire | 232473.21 | 6341.81 | 0 | 0 | 0 | 0 | 0 | 6341.81 | 0 | 238815.02 | 0 | [6 empty] | CM_WSNI | 100%
403937 | Neilston WwTW | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2009-05-15 | 2016-08-31 | 2017-02-27 | 2018-11-29 | 2019-03-13 | East Renfrewshire | 144852 | 312945 | 836831.9 | 3770911.19 | 1156812.64 | -45641.81 | 40373.88 | 6072232.8 | 0 | 6217084.8 | 2782022.84 | [6 empty] | EC04A | 24.92% | EC10A | 24.92% | CM_WWNI | 50.16%
503315 | Neilston WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-21 | 2030-06-19 | 2030-09-19 | East Renfrewshire | 0 | 0 | 0 | 0 | 18173.47 | 5892.6 | 0 | 24066.07 | 117933.93 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
503968 | Neilston WwTW - RAS & Interstage Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2019-12-19 | 2020-12-21 | 2021-04-27 | 2021-12-13 | 2022-05-02 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 4531.54 | 5468.46 | 10000 | 0 | 10000 | 0 | [6 empty] | Ww3 | 100%
502603 | Ness Castle and Ness Side - Strategic Water Supply Infrastructure (Inverness) | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS5 | 2017-10-19 | 2017-10-19 | 2018-04-02 | 2018-10-25 | 2018-10-25 | Highland | 0 | 0 | 0 | 284154.57 | -13639.18 | 0 | 13639.45 | 284154.84 | 0 | 284154.84 | 470181.23 | [6 empty] | WG5 | 100%
400115 | Ness Cluster 2 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2012-09-21 | 2012-10-22 | 2013-06-10 |  | Na H-Eileanan an Iar | 465006 | -1896.05 | 0 | 0 | 0 | 0 | 0 | -1896.05 | 0 | 463109.95 | 0 | [6 empty] | CM_WSI | 100%
400117 | Ness Cluster 4 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2012-09-14 | 2012-10-31 | 2013-08-05 |  | Na H-Eileanan an Iar | 928392 | -1214.42 | 0 | 0 | 0 | 0 | 0 | -1214.42 | 0 | 927177.58 | 0 | [6 empty] | CM_WSI | 100%
400118 | Ness Cluster 5 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2011-12-23 | 2012-01-18 | 2017-02-01 |  | Na H-Eileanan an Iar | 213643 | -8751 | 52905.9 | 6642.99 | -778.4 | 0 | 0 | 50019.49 | 0 | 263662.49 | 0 | [6 empty] | CM_WSI | 100%
403649 | Ness Side Developments Inverness Strategic Wastewater Solution | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2014-01-13 | 2014-02-06 | 2014-02-06 | 2017-11-16 | 2017-11-16 | Highland | 495024 | 0 | -456353.52 | -11251.95 | -281.28 | 0 | 0 | -467886.75 | 0 | 27137.25 | 0 | [6 empty] | SG5 | 100%
502134 | Ness WTW WQ SRs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2016-03-29 | 2016-03-29 | 2016-07-31 | 2016-09-30 | Na H-Eileanan an Iar | 0 | 65.42 | 104.82 | 196.68 | 0 | 0 | 0 | 366.92 | 0 | 366.92 | 1020606.26 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-05
502040 | NETCOM Foundations Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2018-03-28 |  | Scottish Water Wide | 0 | 508698 | 511912.53 | 353424.25 | -1809.01 | 0 | -853.44 | 1371372.33 | 0 | 1371372.33 | 0 | [6 empty] | CM_M&G | 100%
504966 | Nethan Bridge Camps TM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2500.92 | 0 | 2500.92 | 0 | 2500.92 | 0 | [6 empty] | WSI | 100%
502540 | Nether Knox Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-02-02 | 2017-11-17 | 2018-05-29 | 2019-05-09 | 2019-05-09 | Angus | 0 | 0 | 440.51 | 5525.79 | 16314.4 | 3766.64 | 0 | 26047.34 | 0 | 26047.34 | 0 | [6 empty] | CM_WWI | 100%
500050 | Nether Knox WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Aberdeenshire | 0 | 32482.18 | 24117.86 | 7.41 | 0 | 0 | 0 | 56607.45 | 0 | 56607.45 | 136478.56 | [6 empty] | SG1 | 100%
30537 | Netherburn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS6 | 2008-07-15 | 2012-09-05 | 2012-10-29 | 2018-04-30 | 2016-02-24 | South Lanarkshire | 2223247.7 | 90421.38 | 127647.15 | 1368310.28 | -277272.29 | 347102.89 | 126672.3 | 1782881.71 | 0 | 4006129.41 | 650779 | [6 empty] | EC04A | 100%
503923 | Nethermains WwPS - Abandonment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2021-03-22 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 35643.93 | 9356.17 | 45000.1 | 0 | 45000.1 | 0 | [6 empty] | Ww3 | 100%
500811 | Network Model Building Developer Support (Waste) | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS3 | 2015-09-28 | 2015-12-21 | 2015-12-21 | 2021-10-25 | 2022-01-19 | Scottish Water Wide | 0 | 193828 | 338947.83 | 197548.17 | 201000 | 334241 | 249000 | 1514565 | 990435 | 2505000 | 1830849.77 | [6 empty] | SG5 | 100%
500895 | Network Model Building Developer Support (Water) | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS3 | 2015-09-24 | 2015-12-23 | 2015-12-24 | 2021-07-28 | 2021-07-28 | Scottish Water Wide | 0 | 32570 | 18868 | 220224.54 | 506228.26 | 1003809.3 | 1014929 | 2796629.1 | 401370.9 | 3198000 | 470181.23 | [6 empty] | WG5 | 100%
401391 | Network Model Building Developer Support Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2010-09-15 | 2011-03-18 | 2011-03-18 | 2015-08-20 | 2015-10-28 | Scottish Water Wide | 287479 | 12986 | 1412.92 | 0 | 0 | 0 | 0 | 14398.92 | 0 | 301877.92 | 0 | [6 empty] | SG5 | 100%
401392 | Network Model Building Developer Support Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2010-09-24 | 2011-03-17 | 2011-03-17 | 2015-08-24 | 2015-10-28 | Scottish Water Wide | 178070 | 11940.06 | 713.91 | 0 | 0 | 0 | 0 | 12653.97 | 0 | 190723.97 | 0 | [6 empty] | WG5 | 100%
401951 | Network Model Data Management - FTP Setup | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-03-21 | 2018-01-29 | 2018-01-29 | 2018-01-29 |  | Scottish Water Wide | 36.59 | 3463.41 | 0 | -100.31 | 0 | 0 | 0 | 3363.1 | 0 | 3399.69 | 0 | [6 empty] | CM_WWI | 100%
402000 | Network Model Data Management - HYRAD Development | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-03-21 | 2020-05-15 | 2020-05-15 | 2020-01-28 |  | Scottish Water Wide | 42269.05 | 17730.95 | 0 | -17730.95 | 0 | 0 | 0 | 0 | 0 | 42269.05 | 0 | [6 empty] | CM_WWI | 100%
45564 | Network Non-Sanitary License (Essential) Requirements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2011-09-21 | 2011-09-23 | 2015-03-31 | 2015-05-29 | Scottish Water Wide | 4569041.04 | 7238.54 | -6011.41 | 372.15 | 0 | 0 | 0 | 1599.28 | 0 | 4570640.32 | 206942 | [6 empty] | WQ01B | 100%
500592 | Networks and Communications Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-14 | 2016-06-30 | 2016-06-30 | 2018-03-28 | 2018-03-28 | Scottish Water Wide | 0 | 213349 | 380145.06 | 290162.9 | 0 | 0 | 0 | 883656.96 | 0 | 883656.96 | 0 | [6 empty] | CM_M&G | 100%
500993 | New Aberdour WWTW - screen replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-07 | 2016-10-27 | 2017-03-17 | 2017-11-24 | 2017-11-24 | Aberdeenshire | 0 | 2127 | 14132 | 56241 | 0 | 0 | 0 | 72500 | 0 | 72500 | 0 | [6 empty] | CM_WWNI | 100%
500164 | New Cumnock DOA (DOA000138) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-09 | 2018-03-12 | 2018-03-12 | East Ayrshire | 0 | 41549 | 82887 | 17760 | 12584.16 | 0 | -0.02 | 154780.14 | 0 | 154780.14 | 72047.27 | [6 empty] | CS11 | 100%
500167 | New Galloway DOA (DOA001211) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-06-21 | 2016-09-07 | 2019-06-30 | 2019-09-30 | Dumfries and Galloway | 0 | 10409 | 12925 | 12502 | 52000 | -1105.04 | 0 | 86730.96 | 0 | 86730.96 | 78042.2 | [6 empty] | EC01G | 7.63% | EC01D | 92.37% | bar: Regulatory Outputs OMG-23
502816 | New Galloway ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2020-07-01 | 2020-08-26 | 2020-08-26 | 2020-09-02 | 2020-09-03 | Dumfries and Galloway | 0 | 0 | 0 | 77047.47 | 27924.53 | 2236.26 | -42.18 | 107166.08 | 0 | 107166.08 | 136478.56 | [6 empty] | SG1 | 100%
403330 | New Road - Stirling Road Milnathort | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-02-18 | 2016-02-15 | 2016-02-16 | 2016-07-18 | 2016-07-18 | Perth and Kinross | 196881 | 1267417 | 58388.33 | -1686.33 | -15926.94 | 0 | 0.94 | 1308193 | 0 | 1505074 | 474995.67 | [6 empty] | CS15 | 28% | CS11 | 72%
501664 | New Valley Stornoway Phase 1 Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2017-03-22 | 2017-06-12 | 2017-09-11 | 2017-09-11 | Na H-Eileanan an Iar | 0 | 1267 | 20969.46 | 69556.02 | 0 | 0 | 0 | 91792.48 | 0 | 91792.48 | 0 | [6 empty] | CM_WWI | 100%
500166 | Newbie DOA (DOA002071) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2015-09-27 | 2017-03-01 | 2017-04-14 | 2017-04-14 | Dumfries and Galloway | 0 | 15244 | -4313.77 | -2077.22 | 0 | 0 | 0 | 8853.01 | 0 | 8853.01 | 558366.35 | [6 empty] | CS15 | 49.17% | CS11 | 50.83%
502408 | Newburgh WwTW - CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-06-30 | 2028-05-24 | 2028-09-15 | 2029-05-04 | 2029-07-30 | Fife | 0 | 0 | 13934.19 | 13400.57 | 28252.3 | 9641.82 | 27140.29 | 92369.17 | 803740.94 | 896110.11 | 0 | [6 empty] | CM_WWNI | 100%
503372 | Newburgh WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-04-18 | 2028-08-21 | 2029-02-09 | 2029-05-14 | Fife | 0 | 0 | 0 | 0 | 76428.31 | 5134.2 | 0 | 81562.51 | 60437.48 | 141999.99 | 136478.56 | [6 empty] | SG1 | 100%
45718 | Newcastleton WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2011-07-28 | 2011-10-17 | 2016-03-17 | 2016-03-30 | Scottish Borders | 3066864.75 | 435815.96 | 108168.08 | -9281.89 | -6038.32 | 0 | 5569.46 | 534233.29 | 0 | 3601098.04 | 508166 |  |  |  |  | 29173.63 |  | DW23 | 100%
503106 | Newfield Trunk Main Reinforcement | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS3 | 2018-05-17 | 2019-08-27 | 2019-11-11 | 2020-11-02 | 2021-02-08 | Aberdeenshire | 0 | 0 | 0 | 0 | 95443.07 | 925071.09 | 293086.54 | 1313600.7 | 14767.31 | 1328368.01 | 470181.23 | [6 empty] | WG5 | 100%
500731 | Newmachar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2017-08-18 | 2020-09-14 | 2020-10-26 | 2022-07-28 | 2022-10-27 | Aberdeenshire | 0 | 21155.09 | 89337.45 | 211089.81 | 389838.85 | 298899.05 | 1257781.7 | 2268101.95 | 3217060.09 | 5485162.04 | 136478.56 |  |  |  |  | 9430 |  | CM_WWNI | 3% | SG1 | 97%
501694 | Newmains River Crossings | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2017-03-29 | 2020-02-11 | 2020-04-01 | 2021-07-20 | 2021-10-22 | North Lanarkshire | 0 | 0 | 46991.03 | 65450.97 | 195173 | 849291.26 | 3120609.39 | 4277515.65 | 289975.35 | 4567491 | 0 | [6 empty] | CM_WWI | 100%
500208 | Newmore - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-27 | 2018-06-27 | 2018-06-29 | 2019-02-28 | 2020-01-31 | Highland | 0 | 6891 | -5257.45 | 36980.45 | 116586.55 | -14384.8 | 0 | 140815.75 | 0 | 140815.75 | 960709.78 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-02
500705 | Newmore Raw Main Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2015-07-10 | 2015-07-30 | 2015-08-11 | 2016-01-01 | 2016-01-04 | Highland | 0 | 705064.64 | 0 | 0 | 0 | 0 | 0 | 705064.64 | 0 | 705064.64 | 0 | [6 empty] | CM_M&G | 100%
505287 | Newmore Raw water losses investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-23 | 2020-08-06 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 456.28 | 0 | 456.28 | 0 | 456.28 | 0 | [6 empty] | CM_WSI | 100%
500866 | Newmore RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-08 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 6715.98 | 4512.65 | 934.8 | -805.05 | 0 | 0 | 11358.38 | 0 | 11358.38 | 514358.04 | [6 empty] | DW5FS | 100%
501370 | Newmore WOA Lamington PS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-05-11 | 2027-09-22 | 2028-02-04 | 2029-09-21 | 2029-12-24 | Highland | 0 | 0 | 81345.57 | 3191.68 | 0 | -14290.59 | -2986.32 | 67260.34 | 0 | 67260.34 | 0 | [6 empty] | CM_WSNI | 100%
502757 | Newmore WTW- Caustic and Alum Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-05-23 | 2017-08-29 | 2017-09-18 | 2020-01-07 | 2020-04-01 | Highland | 0 | 0 | 0 | 1045148.6 | 476227.71 | 144739.44 | 2589.29 | 1668705.04 | 6001.46 | 1674706.5 | 0 | [6 empty] | CM_WSNI | 100%
503206 | Newmore WTW Filtralite Media Change | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-03 | 2022-07-01 | 2022-10-31 | 2023-06-15 | 2023-09-15 | Highland | 0 | 0 | 0 | 0 | 21094.27 | 7468.05 | 21107.87 | 49670.19 | 900329.83 | 950000.02 | 0 | [6 empty] | CM_WSNI | 100%
402067 | Newmore WTW Long Blue Pipe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-05-04 | 2011-12-21 | 2012-01-30 | 2013-12-03 |  | Highland | 142274 | -185.6 | 0 | 0 | 0 | 0 | 0 | -185.6 | 0 | 142088.4 | 0 | [6 empty] | CM_WSNI | 100%
401343 | Newport WSZ Low Pressure Enhancement WSZ001168 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-02-22 | 2012-08-27 | 2013-11-19 | 2013-03-31 | Fife | 138307.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138307.6 | 530 | [6 empty] | CS1 | 100%
401234 | Newstead WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-09-01 | 2015-10-26 | 2016-01-11 | 2018-04-24 | 2018-04-24 | Scottish Borders | 256722 | 175202 | 623854.82 | 107979.67 | 1600.12 | 161.2 | -161.2 | 908636.61 | 0 | 1165358.61 | 0 | [6 empty] | SG1 | 100%
502796 | Newton Avenue (Pipe bridge) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-07-26 | 2017-07-26 | 2018-01-30 | 2018-10-25 | 2018-10-25 | South Lanarkshire | 0 | 0 | 0 | 236825.81 | 531527.26 | 4898.74 | 0.02 | 773251.83 | 0 | 773251.83 | 0 | [6 empty] | CM_WWI | 100%
300032 | Newton Stewart WwTW - Sludge and HS | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-05-11 | 2014-04-25 | 2014-11-24 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 499376 | 767727 | 47798.05 | 374.24 | -113.78 | 0 | 113.78 | 815899.29 | 0 | 1315275.29 | 698453 | [6 empty] | WQ01 | 100%
501727 | Newtonloan to Dalhousie Castle Trunk Main Rehabilitation | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-23 | 2028-06-01 | 2028-08-29 | 2029-03-29 | 2029-06-29 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435821.98 | 435821.98 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
500068 | Newtown St Boswells WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-11-09 | 2020-03-18 | 2020-03-18 | 2021-10-28 | 2022-01-26 | Scottish Borders | 0 | 46006.3 | 20969.55 | 52573.93 | 14567.8 | 212699.22 | 728643.79 | 1075460.59 | -17925.59 | 1057535 | 136478.56 | [6 empty] | SG1 | 100%
501779 | Nigg and Persley WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-06-29 | 2020-09-07 | 2021-03-10 | 2021-03-11 | Aberdeenshire | 0 | 0 | 4186.05 | 80.86 | 0 | 28521.09 | 270001.47 | 302789.47 | 17291.44 | 320080.91 | 0 | [6 empty] | SR21_WW | 100%
400284 | Nith Cluster 1 Capital maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2012-02-28 | 2012-04-02 | 2013-03-06 |  | South Lanarkshire | 640273 | 1722 | -1163.97 | 0 | 0 | 0 | 0.07 | 558.1 | 0 | 640831.1 | 0 | [6 empty] | CM_WSI | 100%
400285 | Nith Cluster 2 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2012-09-21 | 2013-05-28 | 2014-07-07 |  | South Lanarkshire | 428665 | 13428 | -5899.02 | 0 | 0 | 0 | 0 | 7528.98 | 0 | 436193.98 | 0 | [6 empty] | CM_WSI | 100%
401499 | Nith Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2010-10-20 | 2012-06-14 | 2012-08-27 | 2020-08-14 | 2020-03-27 | All South Unitary Authorities | 138815 | 13098 | 12003.59 | 40027.41 | 131792.51 | 25933.85 | 3209.4 | 226064.76 | 951.29 | 365831.05 | 0 | [6 empty] | CM_WSI | 100%
401459 | NM CID Cap Maint Completion transfer to SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-10-06 | 2011-01-11 | 2011-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 909744.8 | 0.2 | -118931.62 | 0 | 0 | 0 | -0.2 | -118931.62 | 0 | 790813.18 | 0 | [6 empty] | CM_WSI | 100%
300011 | NM CID Enviro Completion costs on non migrated projects | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-10-28 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 347516.84 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0 | 347517 | 11 | [6 empty] | EC01 | 100%
401461 | NM CID Growth Completion transfer into Sr10 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2010-10-06 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 37133 | 0 | -3556.16 | 0 | 0 | 0 | 0 | -3556.16 | 0 | 33576.84 | 0 | [6 empty] | SG1 | 100%
401460 | NM SWD Cap Maint Completion transfer into Sr10 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-10-01 | 2019-03-28 | 2019-03-28 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 308210.28 | -0.28 | 0 | 0 | 0 | 0 | 0 | -0.28 | 0 | 308210 | 0 | [6 empty] | CM_WSI | 100%
401462 | NM SWD Growth Completion transfer into Sr10 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2010-10-01 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 130463 | 0 | 38949.5 | 0 | 0 | 0 | 0 | 38949.5 | 0 | 169412.5 | 0 | [6 empty] | SG1 | 100%
49717 | NONINF - DWQ Compliance - Profile Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -10000000 | -10000000 | 10000000 | 0 | 0 | [6 empty] | SR15_DWQ_COM | 100%
49723 | NONINF - DWQ Reliability - Profile Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | General |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -7000000 | -7000000 | 7000000 | 0 | 0 | [6 empty] | SR15_DWQ_REL | 100%
49602 | NONINF - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | NONINF | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | RISK | 100%
50038 | NONINF - SR21 Early Start - Profile Adjustment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -3115581.63 | -3115581.63 | 3115581.63 | 0 | 0 | [6 empty] | SR21_SS | 100%
49885 | NONINF - Strategic Capacity - Profile Adjustment | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -10000000 | -10000000 | 10000000 | 0 | 0 | [6 empty] | SG1 | 50% | WG1 | 50%
402638 | North Area Future Projects Block Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-04-16 | 2012-04-16 | 2012-05-01 | 2015-11-10 |  | All North Unitary Authorities | 42000 | -41999 | 0 | 0 | 0 | 0 | 0 | -41999 | 0 | 1 | 0 | [6 empty] | CM_WWI | 100%
501108 | North Berwick Catchment Study (DAS) | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-02-27 | 2017-06-22 | 2018-07-31 | 2019-01-31 | East Lothian | 0 | 600 | 9728.23 | 31652.77 | 19464 | -169.67 | 0 | 61275.33 | 0 | 61275.33 | 9787.75 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
500963 | North Berwick WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | East Lothian | 0 | 87789.66 | 141648.39 | 16435.89 | 1608.74 | 3355.94 | -3710.83 | 247127.79 | 0 | 247127.79 | 136478.56 | [6 empty] | SG1 | 100%
403531 | North Berwick WwTW - Growth - 4035310000 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-04 | 2015-03-04 | East Lothian | 75343.95 | 0 | 124.25 | 0 | 82.56 | 0 | 0 | 206.81 | 0 | 75550.76 | 0 | [6 empty] | SG1 | 100%
503060 | North Berwick WWTW Intervention Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2020-08-20 | 2022-03-04 | 2022-06-28 | 2023-06-22 | 2023-09-22 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 1010526.97 | 201604.48 | 337130.31 | 1549261.76 | -196771.4 | 1352490.36 | 2205512.72 | [6 empty] | EC01A_ID | 100%
403598 | North CMC Inf SV Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-25 | 2013-09-25 | 2014-01-15 | 2015-01-23 |  | Highland | 14404.92 | 0 | 0 | 8.84 | 0 | 0 | 0 | 8.84 | 0 | 14413.76 | 0 | [6 empty] | CM_WSI | 100%
500755 | North Coast SCADA Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2016-06-28 | 2020-05-25 | 2020-11-02 | 2022-02-16 | 2022-05-17 | Highland | 0 | 0 | 22086.21 | 67342.95 | 26493.68 | 124446.53 | 509880.37 | 750249.74 | 1478040.26 | 2228290 | 0 | [6 empty] | CM_WSNI | 100%
504791 | North Court Lane Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MSU |  | 2020-02-04 |  | 2020-09-18 | 2020-12-11 | - | 0 | 0 | 0 | 0 | 0 | 64523.81 | 21049.21 | 85573.02 | 0 | 85573.02 | 0 | [6 empty] | CM_WWI | 100%
404137 | North Harris improvement scheme | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS3 | 2015-02-06 | 2019-03-20 | 2019-03-20 | 2020-09-11 | 2020-12-07 | Na H-Eileanan an Iar | 0 | 0 | 0 | 83414.63 | 2567597.37 | 1584714.83 | 635994.09 | 4871720.92 | 48823.57 | 4920544.49 | 0 |  |  |  |  | 22230 |  | DW13 | 100% | bar: Regulatory Outputs OMG-03
404097 | North Harris Regional Scheme | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2015-02-06 | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-01-30 | Na H-Eileanan an Iar | 12804.88 | 155131.12 | -213593.29 | 45755.63 | 27369.83 | 1511.25 | -630.68 | 15543.86 | 0 | 28348.74 | 0 | [6 empty] | DW13 | 100%
500927 | North Lanarkshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-03-13 | 2017-03-13 | 2016-12-08 | 2017-03-13 | All West Unitary Authorities | 0 | 6000 | -452.9 | 0 | 0 | 0 | 0 | 5547.1 | 0 | 5547.1 | 120964.87 | [6 empty] | CS15A | 100%
501098 | North Lanarkshire Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2015-09-30 | 2016-09-27 | 2016-09-29 | 2019-08-31 | 2019-08-31 | North Lanarkshire | 0 | 3934 | 43642.05 | 7223.95 | 26700 | 8500 | 2000 | 92000 | 0 | 92000 | 0 | [6 empty] | EC10D | 100% | [18 empty] | Regulatory Outputs OMG-23: 2
500867 | North Lochs RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-09-06 | 2018-09-20 | 2018-12-10 | 2019-09-30 | 2021-01-19 | Na H-Eileanan an Iar | 0 | 4388.67 | 16878.57 | 16737.51 | 166645.22 | 128931.03 | 0 | 333581 | 0 | 333581 | 251515.97 | [6 empty] | DW5FS | 100%
502552 | North Middleton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-01 | 2018-08-01 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Midlothian | 0 | 0 | 38756.46 | 20101.52 | -10884.64 | 0 | 0.01 | 47973.35 | 0 | 47973.35 | 136478.56 | [6 empty] | SG1 | 100%
501409 | North Pentland Springs | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-04-06 | 2028-01-20 | 2028-05-25 | 2028-10-04 | 2029-01-04 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 290.09 | 290.09 | 1499709.89 | 1499999.98 | 0 | [6 empty] | CM_WSI | 100%
505616 | North Res CM Loch Lunndaidh Access Track Repair | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS2 |  | 2020-03-10 |  | 2020-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1079.44 | 15420.56 | 16500 | 0 | 16500 | 821666.8 | [6 empty] | CS22 | 100%
501040 | North Ronaldsay WTW Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2018-03-30 | 2019-06-28 | 2019-09-30 | 2021-01-29 | 2021-04-30 | Orkney Islands | 0 | 4293.78 | 11.86 | 8280.65 | 51690.12 | 354656.7 | 369528.46 | 788461.57 | 73766.07 | 862227.64 | 292002.14 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
45035 | North Ronaldsay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2012-09-11 | 2013-01-21 | 2013-07-11 | 2015-12-15 | Orkney Islands | 229994.37 | -1068.33 | 0 | 0 | 0 | 0 | 0 | -1068.33 | 0 | 228926.04 | 604 | [6 empty] | DW23 | 100%
402166 | North Taing WWPS Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-09-12 | 2013-06-26 | 2013-08-29 | 2014-06-25 |  | Shetland Islands | 315974 | 0 | -1845.69 | 0 | 0 | 0 | 0 | -1845.69 | 0 | 314128.31 | 0 | [6 empty] | CM_WWNI | 100%
402175 | North Third Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-08-29 | 2012-11-16 | 2014-09-16 | 2014-09-16 | Scottish Water Wide | 520747.18 | 6611.33 | -11908.06 | 0 | 0 | 0 | 0 | -5296.73 | 0 | 515450.45 | 0 | [6 empty] | CM_WSI | 100%
500482 | North Third Reservoir Hydro Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-18 | 2015-06-30 | 2015-08-24 | 2017-03-31 | 2017-03-31 | Stirling | 0 | 1711983.15 | 165771.85 | 79808.11 | 8120.83 | -27704.27 | 22086.41 | 1960066.08 | 0 | 1960066.08 | 832227.31 | [6 empty] | I2S_WI | 100% | [18 empty] | Regulatory Outputs OMG-43: 0.59
505048 | Northmavine CWT Inspection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1982.75 | 17.25 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WSNI | 100%
402698 | Northmavine WSZ Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2013-07-29 | 2013-09-09 | 2014-04-03 |  | Shetland Islands | 311693 | 11988.21 | -101.07 | 0 | 0 | 0 | 0 | 11887.14 | 0 | 323580.14 | 0 | [6 empty] | CM_WSI | 100%
33155 | NRSWA - Service Relocate - Edinburgh Tram Lines - Mains Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWMD | NRSWA | MS7 | 2006-01-20 | 2008-07-08 | 2010-04-27 | 2010-05-03 |  | City of Edinburgh | 7867844 | -250000 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 7617844 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
401081 | NRSWA C3 Non Rechargeable Sewer Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2010-06-24 | 2010-06-24 | 2005-02-21 | 2015-08-28 |  | Scottish Water Wide | 78400 | -12074.6 | 0 | 0 | 0 | 0 | 0 | -12074.6 | 0 | 66325.4 | 0 | [6 empty] | CM_WWI | 100%
401082 | NRSWA C3 Non Rechargeable Water Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-06-24 | 2010-06-24 | 2005-02-21 | 2015-08-28 |  | Scottish Water Wide | 316229 | 26947.1 | 0 | 0 | 0 | 0 | 0 | 26947.1 | 0 | 343176.1 | 0 | [6 empty] | CM_WSI | 100%
400324 | NRSWA C3 Service Relocate Edinburgh Tram Lines Mains Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWMD | NRSWA | MS3 | 2006-01-20 | 2008-06-18 | 2010-12-01 | 2023-04-14 |  | City of Edinburgh | 3635779 | -73716.56 | 102647.56 | 21628.23 | 45367.77 | 334148.9 | 143354.1 | 573430 | 401240 | 4610449 | 0 | [6 empty] | SR15_SED_NRSW | 100%
402232 | NRSWA C4 - A92 Courthill to Hawkhill Bends Improvement Angus | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-06-23 |  |  | 2011-12-07 |  | Angus | 2527.26 | 0 | 0 | 0 | 35.22 | 0 | -35.22 | 0 | 0 | 2527.26 | 0 | [6 empty] | CM_WSI | 100%
402102 | NRSWA C4 - Elgin Flood Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-04-26 |  |  | 2013-07-10 |  | Moray | 249611.31 | 83637.89 | 18136.03 | 271.03 | 183.66 | 0 | 0 | 102228.61 | 0 | 351839.92 | 0 | [6 empty] | CM_WWI | 100%
502832 | NRSWA C4 Estimate for C4 Design Only Hawick Flood Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2017-07-25 | 2018-03-29 | 2018-08-23 | 2022-12-15 | 2022-12-15 | Scottish Borders | 0 | 0 | 0 | 45177.25 | 36436.75 | 314.53 | 2284.39 | 84212.92 | 15787.08 | 100000 | 43684.09 | [6 empty] | CS23W | 100%
403062 | NRSWA C4 Sewer Detailed Estimates - Scottish Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-10-23 |  |  | 2015-08-28 |  | Scottish Water Wide | 64356 | -11793.29 | 0 | 0 | 0 | 0 | 0 | -11793.29 | 0 | 52562.71 | 0 | [6 empty] | CM_WWI | 100%
500783 | NRSWA C4 Sewer Detailed Estimates - Scottish Water Wide - 5007830000 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS7 | 2015-08-24 | 2019-09-25 | 2019-09-13 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 57103 | 46133.64 | 36345.5 | 4505.71 | -42366.93 | -2183.03 | 99537.89 | 0 | 99537.89 | 2614273.27 | [6 empty] | CS23S | 100%
503299 | NRSWA C4 Sewer Detailed Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-06-01 | 2021-06-02 | 2021-06-02 | 2021-08-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 57992.84 | 25891.02 | 15471.5 | 99355.36 | 644.64 | 100000 | 2614273.27 | [6 empty] | CS23S | 100%
400744 | NRSWA C4 Sewers M8 Baillieston Newhouse | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2009-04-21 | 2012-08-15 | 2012-12-17 | 2014-10-23 |  | North Lanarkshire | 149438.69 | 0 | 0 | 0 | 85.16 | 0 | -85.16 | 0 | 0 | 149438.69 | 0 | [6 empty] | CM_WWI | 100%
402917 | NRSWA C4 Water - Muir of Ord Railway Bridge | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-08-27 |  |  | 2013-04-10 |  | Highland | 1182.25 | 0 | 0 | 0 | 26.42 | 0 | -26.42 | 0 | 0 | 1182.25 | 0 | [6 empty] | CM_WSI | 100%
503453 | NRSWA C4 Water (Design Only) - Grandholme Link Trunk Main Haudagain Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-02-22 | 2019-03-25 | 2019-06-10 | 2020-03-13 | 2020-04-01 | Aberdeen City | 0 | 0 | 0 | 0 | 11876.7 | 98382.13 | -0.01 | 110258.82 | 0 | 110258.82 | 43684.09 | [6 empty] | CS23W | 100%
500782 | NRSWA C4 Water Detailed Estimates - Scottish Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-25 | 2019-09-13 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 73930 | 328156.79 | 216767.27 | 446.46 | -275804.4 | -21464.71 | 322031.41 | 0 | 322031.41 | 43684.09 | [6 empty] | CS23W | 100%
403063 | NRSWA C4 Water Detailed Estimates - Scottish Water Wide - 4030630000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-10-23 | 2012-11-05 | 2013-01-11 | 2015-08-28 |  | Scottish Water Wide | 264292.42 | 106363.72 | 272.19 | 361.83 | 1984.14 | 0 | 0 | 108981.88 | 0 | 373274.3 | 0 | [6 empty] | CM_WSI | 100%
503298 | NRSWA C4 Water Detailed Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 152703.09 | 119915.67 | 123843.71 | 396462.47 | 3537.52 | 399999.99 | 43684.09 | [6 empty] | CS23W | 100%
402196 | NRSWA C5 - Construction Sewers - M80 Post-Construction CCTV | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-06-15 | 2011-10-31 | 2012-01-09 | 2015-06-30 |  | North Lanarkshire | 131668 | 44945.24 | 0 | 0 | 0 | 0 | 0 | 44945.24 | 0 | 176613.24 | 0 | [6 empty] | CM_WWI | 100%
402608 | NRSWA C5 - EGIP B9124 Galamuir Rd Alloa Bridge 31 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-03-30 | 2012-08-29 | 2012-12-03 | 2014-10-20 |  | Stirling | 61810.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61810.68 | 0 | [6 empty] | CM_WSI | 100%
403557 | NRSWA C5 - EGIP Langmuir Road Bargeddie Bridge 021 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-08-20 | 2014-04-17 | 2014-04-25 | 2014-12-09 |  | North Lanarkshire | 50870 | -336.17 | 0 | 0 | 0 | 0 | 0 | -336.17 | 0 | 50533.83 | 0 | [6 empty] | CM_WSI | 100%
403584 | NRSWA C5 - EGIP Main Street Larbert - Bridge 132-041 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-09-03 | 2014-04-02 | 2014-04-04 | 2015-01-27 |  | Falkirk | 196421 | 959.14 | 0 | 0 | 0 | 0 | 0 | 959.14 | 0 | 197380.14 | 0 | [6 empty] | CM_WSI | 100%
402702 | NRSWA C5 Const Sewer - Edinburgh Gateway | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-06-05 | 2014-01-21 | 2014-06-16 | 2015-08-03 |  | City of Edinburgh | 2514139 | 39063 | -0.04 | -43418.63 | 0 | 0 | 0 | -4355.67 | 0 | 2509783.33 | 0 | [6 empty] | CM_WWI | 100%
402651 | NRSWA C5 Const Sewer - Forth Crossing SW-D10 Ferrytoll Road Rosyth | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-04-30 | 2012-11-30 | 2012-12-10 | 2014-04-01 |  | City of Edinburgh | 248616.33 | 6862.93 | 0 | 0 | 0 | 0 | 0.51 | 6863.44 | 0 | 255479.77 | 0 | [6 empty] | CM_WWI | 100%
402267 | NRSWA C5 Construction - Forth Street Culvert Dunfermline | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-07-21 | 2012-11-16 | 2012-11-30 | 2015-02-02 |  | Fife | 181333 | -3078.09 | 0 | 0 | 0 | 0 | 0 | -3078.09 | 0 | 178254.91 | 0 | [6 empty] | CM_WSI | 100%
402494 | NRSWA C5 Construction - The Helix Canal Project Falkirk | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-01-26 | 2012-02-19 | 2012-03-12 | 2014-12-01 |  | Falkirk | 62272 | 881.95 | 4.45 | 0 | 0 | 0 | 0 | 886.4 | 0 | 63158.4 | 0 | [6 empty] | CM_WSI | 100%
403203 | NRSWA C5 Construction Sewer - Borders Rail Link SW-S2 & S3 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-12-17 | 2013-08-20 | 2013-08-28 | 2016-01-20 |  | Scottish Borders | 1620673 | 156998.7 | -52485.44 | 0 | 0 | 0 | 0 | 104513.26 | 0 | 1725186.26 | 0 | [6 empty] | CM_WWI | 100%
403574 | NRSWA C5 Construction Sewer - Borders Rail Link SW-S30 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-08-21 | 2014-02-28 | 2014-03-06 | 2014-10-07 |  | Scottish Borders | 4994.24 | 1143 | 0 | 0 | 0 | 0 | 0 | 1143 | 0 | 6137.24 | 0 | [6 empty] | CM_WWI | 100%
403421 | NRSWA C5 Construction Sewer - Borders Rail Link SW-S69 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-03-15 | 2013-12-16 | 2014-02-20 | 2015-03-19 |  | Scottish Borders | 632218.27 | 226594.31 | 0 | 0 | 0 | 0 | 0.75 | 226595.06 | 0 | 858813.33 | 0 | [6 empty] | CM_WWI | 100%
403612 | NRSWA C5 Construction Sewer - Forth Crossing SWD12 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-10-22 | 2014-10-08 | 2014-10-13 | 2016-02-01 |  | City of Edinburgh | 133491 | 534515 | 134264.43 | 22481.88 | -28405.8 | 207.6 | -207.6 | 662855.51 | 0 | 796346.51 | 0 | [6 empty] | CM_WWI | 100%
402820 | NRSWA C5 Construction Sewer - M8 Improvements SWS 03 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-05-13 | 2013-05-20 | 2014-12-10 |  | North Lanarkshire | 818395 | -508.38 | 0 | 0 | 0 | 0 | 0 | -508.38 | 0 | 817886.62 | 0 | [6 empty] | CM_WWI | 100%
403711 | NRSWA C5 Construction Sewer - M8 Improvements SWS 03 Phase 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2014-03-07 | 2014-04-25 | 2014-06-03 | 2014-12-10 |  | North Lanarkshire | 1243427.56 | 0 | -37131.72 | 0 | 0 | 0 | 37131.92 | 0.2 | 0 | 1243427.76 | 0 | [6 empty] | CM_WWI | 100%
402819 | NRSWA C5 Construction Sewer - M8 Improvements SWS 05 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2013-09-25 | 2013-10-07 | 2016-08-22 |  | North Lanarkshire | 395352 | 1011323 | -81952.5 | 0 | 0 | 0 | 0.25 | 929370.75 | 0 | 1324722.75 | 0 | [6 empty] | CM_WWI | 100%
402818 | NRSWA C5 Construction Sewer - M8 Improvements SWS 06 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-01-21 | 2014-08-18 | 2015-02-16 |  | North Lanarkshire | 450526 | -78961.1 | 0 | 0 | 0 | 0 | 0 | -78961.1 | 0 | 371564.9 | 0 | [6 empty] | CM_WWI | 100%
402817 | NRSWA C5 Construction Sewer - M8 Improvements SWS 07 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-03-27 | 2013-04-29 | 2015-02-16 |  | North Lanarkshire | 848731.31 | 1488.73 | 0 | 0 | 0 | 0 | 0 | 1488.73 | 0 | 850220.04 | 0 | [6 empty] | CM_WWI | 100%
402805 | NRSWA C5 Construction Sewer - M8 Improvements SWS 15 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-09-15 | 2015-01-26 | 2015-10-07 |  | North Lanarkshire | 696853 | 707751.96 | 166.08 | 0 | 0 | 0 | -0.09 | 707917.95 | 0 | 1404770.95 | 0 | [6 empty] | CM_WWI | 100%
402804 | NRSWA C5 Construction Sewer - M8 Improvements SWS 16 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2015-09-30 | 2015-09-30 | 2017-12-08 |  | North Lanarkshire | 279209 | 50217 | 203062 | 1435178.3 | 1717.28 | 0 | 0.01 | 1690174.59 | 0 | 1969383.59 | 0 | [6 empty] | CM_WWI | 100%
402803 | NRSWA C5 Construction Sewer - M8 Improvements SWS 17 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-09-18 | 2015-01-23 | 2015-09-08 |  | North Lanarkshire | 482544 | 549610.81 | 0 | 0 | 0 | 0 | 0 | 549610.81 | 0 | 1032154.81 | 0 | [6 empty] | CM_WWI | 100%
402812 | NRSWA C5 Construction Sewer - M8 Improvements SWS 20A | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-08-07 | 2014-09-15 | 2014-11-20 |  | North Lanarkshire | 52660 | -13887.54 | 0 | 0 | 0 | 0 | 3001.08 | -10886.46 | 0 | 41773.54 | 0 | [6 empty] | CM_WWI | 100%
402809 | NRSWA C5 Construction Sewer - M8 Improvements SWS 23 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-11-06 | 2015-05-18 | 2015-07-01 |  | North Lanarkshire | 51923 | 4461.95 | 0 | 0 | 0 | 0 | 0 | 4461.95 | 0 | 56384.95 | 0 | [6 empty] | CM_WWI | 100%
402808 | NRSWA C5 Construction Sewer - M8 Improvements SWS 29 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2015-03-17 | 2015-07-31 | 2017-03-01 |  | North Lanarkshire | 86749.38 | 308022.62 | 1393267 | -53896.84 | 1043.8 | 0 | 0 | 1648436.58 | 0 | 1735185.96 | 0 | [6 empty] | CM_WWI | 100%
402806 | NRSWA C5 Construction Sewer - M8 Improvements SWS 30A | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-24 | 2014-09-22 | 2016-08-22 |  | North Lanarkshire | 342.94 | 74.98 | 291.2 | 0 | 0 | 0 | -0.05 | 366.13 | 0 | 709.07 | 0 | [6 empty] | CM_WWI | 100%
403489 | NRSWA C5 Construction Sewer - Maitland Street Culvert Leven Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-05-08 | 2014-05-20 | 2014-06-18 | 2015-03-13 |  | Fife | 19159 | 911.46 | 0 | 0 | 0 | 0 | 0 | 911.46 | 0 | 20070.46 | 0 | [6 empty] | CM_WWI | 100%
403518 | NRSWA C5 Construction Sewer - Third Don Crossing Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-07-11 | 2014-09-08 | 2014-11-24 | 2016-06-24 |  | Aberdeen City | 171725 | 31045 | -275.95 | 0 | 0 | 0 | 0 | 30769.05 | 0 | 202494.05 | 0 | [6 empty] | CM_WWI | 100%
403620 | NRSWA C5 Construction Sewer Borders Rail Link SW-S8a | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-07-22 | 2014-08-05 | 2014-08-08 |  | Scottish Borders | 308.66 | 0 | 0 | 0 | -278.85 | 0 | 278.85 | 0 | 0 | 308.66 | 0 | [6 empty] | CM_WWI | 100%
403621 | NRSWA C5 Construction Sewer Borders Rail Link SW-S8b and c | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-05-30 | 2014-06-09 | 2014-12-03 |  | Scottish Borders | 210336 | -26756.92 | 0 | 0 | 0 | 0 | 1346.14 | -25410.78 | 0 | 184925.22 | 0 | [6 empty] | CM_WWI | 100%
500691 | NRSWA C5 Construction Sewers - Borders Rail Link Remedial Works | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-06-09 | 2015-08-26 | 2015-09-22 | 2016-06-29 | 2016-07-22 | Scottish Borders | 0 | 115651.89 | 3136.1 | 0 | 0 | 0 | 0.02 | 118788.01 | 0 | 118788.01 | 0 | [6 empty] | CM_WWI | 100%
403651 | NRSWA C5 Construction Sewers-Aberdeen Western Peripheral Route Holding Line | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS4 | 2014-01-20 | 2015-04-30 | 2015-08-31 | 2019-09-26 |  | Aberdeen City | 236758.42 | 598351.58 | 67232.39 | 293124.16 | 750540.64 | 312537.17 | -667.08 | 2021118.86 | 0 | 2257877.28 | 0 | [6 empty] | CM_WWI | 100%
402534 | NRSWA C5 Construction Water - A92 Hawkhill Bends Angus | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-02-07 | 2012-04-18 | 2012-04-23 | 2013-06-28 |  | Angus | 64087.6 | 575.88 | 0 | 0 | 0 | 0 | 0.4 | 576.28 | 0 | 64663.88 | 0 | [6 empty] | CM_WSI | 100%
403521 | NRSWA C5 Construction Water - A96 Park & Choose Dyce Drive Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-17 | 2014-06-16 | 2016-04-07 |  | Aberdeen City | 53008 | 276818 | -15058.63 | 0 | 0 | 0 | 0 | 261759.37 | 0 | 314767.37 | 0 | [6 empty] | CM_WSI | 100%
403319 | NRSWA C5 Construction Water - Aimer Street Lochee Dundee | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-02-04 | 2013-05-15 | 2013-05-28 | 2016-09-28 |  | Dundee City | 12008 | 461 | 727.74 | 9880.16 | 0 | 0 | 0 | 11068.9 | 0 | 23076.9 | 0 | [6 empty] | CM_WSI | 100%
401714 | NRSWA C5 Construction Water - Borders Rail Link - SW-W11-W13 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-12-14 | 2011-08-01 | 2012-05-25 | 2014-11-18 |  | Scottish Borders | 1012352 | -16339.3 | 0 | 0 | 0 | 0 | 0 | -16339.3 | 0 | 996012.7 | 0 | [6 empty] | CM_WSI | 100%
403708 | NRSWA C5 Construction Water - Borders Rail Link - SW-W11-W13 (Ph.2) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-02-04 | 2014-03-25 | 2014-03-31 | 2014-11-18 |  | Scottish Borders | 582388.63 | -12482.62 | 0 | 0 | 0 | 0 | 0 | -12482.62 | 0 | 569906.01 | 0 | [6 empty] | CM_WSI | 100%
403211 | NRSWA C5 Construction Water - Borders Rail Link SW-W14 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-12-17 | 2013-11-12 | 2013-12-12 | 2015-08-05 |  | Scottish Borders | 388894 | 4819.8 | 128 | 0 | 0 | 0 | 0 | 4947.8 | 0 | 393841.8 | 0 | [6 empty] | CM_WSI | 100%
403818 | NRSWA C5 Construction Water - Bute Drive Perth Junction Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-27 | 2014-10-09 | 2014-10-20 | 2015-06-01 |  | Perth and Kinross | 35380 | 759.77 | 0 | 0 | 0 | 0 | 0 | 759.77 | 0 | 36139.77 | 0 | [6 empty] | CM_WSI | 100%
403524 | NRSWA C5 Construction Water - Duddingston Road Rail Bridge Edinburgh | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-27 | 2014-04-28 | 2015-03-13 |  | City of Edinburgh | 43470.95 | 20.44 | 0 | 0 | 0 | 0 | 2.74 | 23.18 | 0 | 43494.13 | 0 | [6 empty] | CM_WSI | 100%
403381 | NRSWA C5 Construction Water - Hatton Mill Bridge Hatton Aberdeenshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-02-21 | 2013-04-25 | 2013-04-29 | 2013-09-25 |  | Aberdeenshire | 24064 | 0 | 0 | 0 | 10.33 | 0 | -0.33 | 10 | 0 | 24074 | 0 | [6 empty] | CM_WSI | 100%
403871 | NRSWA C5 Construction Water - High Park Culvert Turnberry South Ayrshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2014-08-29 | 2014-09-26 | 2015-04-24 |  | South Ayrshire | 27667 | -127.92 | 0 | 0 | 0 | 0 | 126.55 | -1.37 | 0 | 27665.63 | 0 | [6 empty] | CM_WSI | 100%
403872 | NRSWA C5 Construction Water - Locharbriggs Retaining Wall Dumfries | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2014-08-29 | 2015-01-23 | 2015-03-17 |  | Dumfries and Galloway | 23689 | 13945.83 | 0 | 0 | 0 | 0 | 0 | 13945.83 | 0 | 37634.83 | 0 | [6 empty] | CM_WSI | 100%
403484 | NRSWA C5 Construction Water - M8 Improvements SWW 05 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-10 | 2014-06-27 | 2014-08-13 | 2015-09-10 |  | North Lanarkshire | 70808 | 103213 | 0 | 0 | 0 | 0 | 114.52 | 103327.52 | 0 | 174135.52 | 0 | [6 empty] | CM_WSI | 100%
402790 | NRSWA C5 Construction Water - M8 Improvements SWW 11 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-19 | 2014-05-12 | 2015-12-01 |  | North Lanarkshire | 66555 | 80910.56 | 0 | 0 | 0 | 0 | 0 | 80910.56 | 0 | 147465.56 | 0 | [6 empty] | CM_WSI | 100%
402794 | NRSWA C5 Construction Water - M8 Improvements SWW 12 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-04-11 | 2014-07-07 | 2015-12-21 |  | North Lanarkshire | 117997 | 69638.01 | 468.13 | 0 | 0 | 0 | 0 | 70106.14 | 0 | 188103.14 | 0 | [6 empty] | CM_WSI | 100%
403483 | NRSWA C5 Construction Water - M8 Improvements SWW 13 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-10 | 2014-07-17 | 2014-07-18 | 2016-07-28 |  | North Lanarkshire | 307941 | 252602.73 | 561747.93 | 0 | 0 | 0 | 0 | 814350.66 | 0 | 1122291.66 | 0 | [6 empty] | CM_WSI | 100%
402795 | NRSWA C5 Construction Water - M8 Improvements SWW 14 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-12 | 2015-12-01 |  | North Lanarkshire | 378919 | 402354.96 | -128.87 | 0 | 0 | 0 | 0 | 402226.09 | 0 | 781145.09 | 0 | [6 empty] | CM_WSI | 100%
402793 | NRSWA C5 Construction Water - M8 Improvements SWW 15 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-05 | 2015-12-14 |  | North Lanarkshire | 168811 | -7932 | 5898.38 | 0 | 0 | 0 | -0.39 | -2034.01 | 0 | 166776.99 | 0 | [6 empty] | CM_WSI | 100%
402797 | NRSWA C5 Construction Water - M8 Improvements SWW 16 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-06-02 | 2015-04-21 |  | North Lanarkshire | 109102 | 9916.27 | 0 | 0 | 0 | 0 | 0 | 9916.27 | 0 | 119018.27 | 0 | [6 empty] | CM_WSI | 100%
402798 | NRSWA C5 Construction Water - M8 Improvements SWW 17 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-07-01 | 2015-06-22 | 2016-09-19 |  | North Lanarkshire | 203092.27 | 1234625.92 | 158723.06 | 0 | 0 | 0 | 0 | 1393348.98 | 0 | 1596441.25 | 0 | [6 empty] | CM_WSI | 100%
402786 | NRSWA C5 Construction Water - M8 Improvements SWW 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-10 | 2014-11-25 | 2015-01-12 | 2016-09-19 |  | North Lanarkshire | 61016.23 | 105306.77 | 175746.35 | 0 | 0 | 0 | 0 | 281053.12 | 0 | 342069.35 | 0 | [6 empty] | CM_WSI | 100%
402800 | NRSWA C5 Construction Water - M8 Improvements SWW 20 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-10-28 | 2014-10-30 | 2015-09-16 |  | North Lanarkshire | 146485 | 139068.3 | 36380.86 | 45.17 | 0 | 0 | -0.41 | 175493.92 | 0 | 321978.92 | 0 | [6 empty] | CM_WSI | 100%
402801 | NRSWA C5 Construction Water - M8 Improvements SWW 21 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-06-30 | 2014-07-21 | 2015-02-23 |  | North Lanarkshire | 13798.59 | 5709.83 | 0 | 0 | 0 | 0 | 0 | 5709.83 | 0 | 19508.42 | 0 | [6 empty] | CM_WSI | 100%
402799 | NRSWA C5 Construction Water - M8 Improvements SWW 22 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2015-03-16 | 2015-08-12 | 2016-02-10 |  | North Lanarkshire | 31079.34 | 93575.66 | 1977.86 | 0 | 0 | 0 | 0.33 | 95553.85 | 0 | 126633.19 | 0 | [6 empty] | CM_WSI | 100%
403634 | NRSWA C5 Construction Water - M8 Improvements SWW 23 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2015-02-23 | 2016-02-22 | 2016-11-11 |  | North Lanarkshire | 35529 | 2893 | 35457.24 | 20515.6 | 0 | 0 | 0 | 58865.84 | 0 | 94394.84 | 0 | [6 empty] | CM_WSI | 100%
403635 | NRSWA C5 Construction Water - M8 Improvements SWW 24 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2014-12-05 | 2015-02-27 | 2015-10-10 |  | North Lanarkshire | 40821 | 170535.88 | 0 | 0 | 0 | 0 | 0 | 170535.88 | 0 | 211356.88 | 0 | [6 empty] | CM_WSI | 100%
402787 | NRSWA C5 Construction Water - M8 Improvements SWW 3 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-19 | 2013-08-21 | 2013-09-19 | 2015-04-21 |  | North Lanarkshire | 149199.15 | -7119.32 | 0 | 0 | 0 | 0 | 6.82 | -7112.5 | 0 | 142086.65 | 0 | [6 empty] | CM_WSI | 100%
403784 | NRSWA C5 Construction Water - M8 Improvements SWW 3 (Perm) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-13 | 2015-01-27 | 2015-07-30 | 2016-05-31 |  | North Lanarkshire | 10919 | 137193 | 162253.08 | 0 | 0 | 0 | 0 | 299446.08 | 0 | 310365.08 | 0 | [6 empty] | CM_WSI | 100%
403633 | NRSWA C5 Construction Water - M8 Improvements SWW 34 35 & 36 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2015-01-29 | 2015-01-28 | 2015-12-21 |  | North Lanarkshire | 493356 | 834996.97 | 0 | 0 | 0 | 0 | -0.09 | 834996.88 | 0 | 1328352.88 | 0 | [6 empty] | CM_WSI | 100%
403869 | NRSWA C5 Construction Water - M8 Improvements SWW 38 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2015-02-27 | 2015-03-16 | 2015-09-16 |  | North Lanarkshire | 155535.02 | 195444.44 | 0 | 422.45 | 0 | 0 | 0.25 | 195867.14 | 0 | 351402.16 | 0 | [6 empty] | CM_WSI | 100%
402785 | NRSWA C5 Construction Water - M8 Improvements SWW 4 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-06-29 | 2014-08-05 | 2014-11-03 | 2015-10-10 |  | North Lanarkshire | 87941 | 8281.46 | 0 | 0 | 0 | 0 | 0 | 8281.46 | 0 | 96222.46 | 0 | [6 empty] | CM_WSI | 100%
402788 | NRSWA C5 Construction Water - M8 Improvements SWW 6 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-13 | 2014-06-23 | 2015-07-08 |  | North Lanarkshire | 353562 | 199010.19 | 0 | 0 | 0 | 0 | 0 | 199010.19 | 0 | 552572.19 | 0 | [6 empty] | CM_WSI | 100%
402789 | NRSWA C5 Construction Water - M8 Improvements SWW 7 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-27 | 2014-06-30 | 2016-02-18 |  | North Lanarkshire | 266427 | 345968.31 | 24522.29 | 0 | 0 | 0 | 0.09 | 370490.69 | 0 | 636917.69 | 0 | [6 empty] | CM_WSI | 100%
402791 | NRSWA C5 Construction Water - M8 Improvements SWW 8 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-09-24 | 2013-10-07 | 2015-01-15 |  | North Lanarkshire | 1293564 | -242038.84 | 0 | 0 | 0 | 0 | 0 | -242038.84 | 0 | 1051525.16 | 0 | [6 empty] | CM_WSI | 100%
403742 | NRSWA C5 Construction Water - M8 Improvements SWW 8 Phase 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-03-07 | 2014-04-29 | 2014-05-22 | 2015-01-26 |  | North Lanarkshire | 660774 | 595.74 | 0 | 0 | 0 | 0 | 0 | 595.74 | 0 | 661369.74 | 0 | [6 empty] | CM_WSI | 100%
402792 | NRSWA C5 Construction Water - M8 Improvements SWW 9 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-12 | 2017-03-08 |  | North Lanarkshire | 275547 | 57936 | -18696 | 62051.85 | 0 | 0 | 0 | 101291.85 | 0 | 376838.85 | 0 | [6 empty] | CM_WSI | 100%
403488 | NRSWA C5 Construction Water - Maitland Street Culvert Leven Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-08 | 2014-05-20 | 2014-06-09 | 2015-07-06 |  | Fife | 36261 | 673.01 | 0 | 0 | 0 | 0 | 0 | 673.01 | 0 | 36934.01 | 0 | [6 empty] | CM_WSI | 100%
403525 | NRSWA C5 Construction Water - Peffermill Road Rail Bridge Edinburgh | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-27 | 2014-06-09 | 2015-11-02 |  | City of Edinburgh | 130465 | 61267.1 | 0 | 0 | 0 | 0 | 0 | 61267.1 | 0 | 191732.1 | 0 | [6 empty] | CM_WSI | 100%
403534 | NRSWA C5 Construction Water - Port-na-Craig Footbridge Pitlochry | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-07-11 | 2014-03-03 | 2014-03-13 | 2015-02-02 |  | Perth and Kinross | 23185.95 | 445.95 | 0 | 0 | 0 | 0 | 0 | 445.95 | 0 | 23631.9 | 0 | [6 empty] | CM_WSI | 100%
403519 | NRSWA C5 Construction Water - Third Don Crossing Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-09-11 | 2014-11-24 | 2016-06-29 |  | Aberdeen City | 246797 | 87388 | 48234.58 | 273.45 | 0 | 0 | 290.81 | 136186.84 | 0 | 382983.84 | 0 | [6 empty] | CM_WSI | 100%
403905 | NRSWA C5 Construction Water - Townhead St-Low Patrick St Hamilton | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-08-20 | 2014-09-19 | 2014-12-05 | 2015-03-12 |  | South Lanarkshire | 8327 | -1396.18 | 0 | 0 | 0 | 0 | 2.74 | -1393.44 | 0 | 6933.56 | 0 | [6 empty] | CM_WSI | 100%
403652 | NRSWA C5 Construction Water Aberdeen Western Peripheral Route Holding Line | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS4 | 2014-01-16 | 2015-04-28 | 2015-06-29 | 2020-03-16 |  | Aberdeen City | 800753 | 3456914.85 | 2568606.87 | 2709028.28 | 1572245.43 | 167314.06 | 0 | 10474109.49 | 0 | 11274862.49 | 0 | [6 empty] | CM_WSI | 100%
403622 | NRSWA C5 Construction Water Borders Rail Link SW-W16a | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-07-22 | 2014-08-15 | 2015-06-25 |  | Scottish Borders | 18526 | -7844.14 | 0 | 0 | 0 | 0 | 0 | -7844.14 | 0 | 10681.86 | 0 | [6 empty] | CM_WSI | 100%
403260 | NRSWA C5 Construction Water Dura Den Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-01-15 | 2014-02-13 | 2014-02-26 | 2015-09-01 |  | Fife | 89591 | -3016.5 | 0 | 0 | 0 | 0 | 0 | -3016.5 | 0 | 86574.5 | 0 | [6 empty] | CM_WSI | 100%
402739 | NRSWA C5 Construction Water Matthews Burn Culvert Darvel | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-09-04 | 2012-12-12 | 2013-01-07 | 2013-09-24 |  | East Ayrshire | 68672 | -2327.66 | 0 | 0 | 0 | 0 | -0.02 | -2327.68 | 0 | 66344.32 | 0 | [6 empty] | CM_WSI | 100%
403932 | NRSWA C5 Construction Water-A749 Western Rd-East Kilbride Rd Cambuslang | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-10-10 | 2015-01-22 | 2015-02-12 | 2016-02-01 |  | South Lanarkshire | 47986.53 | 217.45 | 0 | 0 | 0 | 0 | 0 | 217.45 | 0 | 48203.98 | 0 | [6 empty] | CM_WSI | 100%
500692 | NRSWA C5 Construction Water-A917 Kilrenny Burn Bridge Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-09 | 2015-09-30 | 2016-08-18 | 2017-05-04 | 2017-05-04 | Fife | 0 | 21180 | -11838.08 | -4107.04 | 0 | 0 | 3224.7 | 8459.58 | 0 | 8459.58 | 0 | [6 empty] | CM_WSI | 100%
403806 | NRSWA C5 Construction Water-A96 Inveramsay Bridge Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-19 | 2014-11-20 | 2014-12-24 | 2015-10-22 |  | Aberdeenshire | 17336 | 13787.42 | 0 | 0 | 0 | 0 | 27.42 | 13814.84 | 0 | 31150.84 | 0 | [6 empty] | CM_WSI | 100%
404011 | NRSWA C5 Construction Water-EGIP 2015 Bridges | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-12-08 | 2015-05-11 | 2015-05-19 | 2016-12-23 |  | Falkirk | 23973 | 117540 | 26725.8 | 17444.39 | 0 | 0 | 0 | 161710.19 | 0 | 185683.19 | 0 | [6 empty] | CM_WSI | 100%
403933 | NRSWA C5 Construction Water-Nairn Cemetery | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-10-29 | 2015-03-31 | 2015-06-01 | 2015-10-27 |  | Highland | 15150 | 21737.34 | 0 | 0 | 0 | 0 | 0 | 21737.34 | 0 | 36887.34 | 0 | [6 empty] | CM_WSI | 100%
404012 | NRSWA C5 Construction Water-Shotts Line 2015 Bridges | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-12-10 | 2015-05-11 | 2015-05-12 | 2017-10-11 |  | North Lanarkshire | 1850 | 244422 | 438877 | 205311.01 | 52.47 | 0 | 0 | 888662.48 | 0 | 890512.48 | 0 | [6 empty] | CM_WSI | 100%
501176 | NRSWA C5 Water - Culvert Replacement at Ballygrant Islay | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-10-28 | 2016-09-26 | 2016-09-27 | 2017-03-27 | 2017-03-27 | Argyll and Bute-North Argyll | 0 | 14000 | 31250.88 | -359.6 | 0 | 0 | 0 | 44891.28 | 0 | 44891.28 | 43684.09 | [6 empty] | CS23W | 100%
403438 | NRSWA C5 Water A75 Hardgrove to Kinmount Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-03-29 | 2013-11-21 | 2013-11-21 | 2016-03-24 |  | Dumfries and Galloway | 255314 | 174943 | 752.25 | 0 | 0 | 0 | 0 | 175695.25 | 0 | 431009.25 | 0 | [6 empty] | CM_WSI | 100%
403326 | NRSWA C5 Water A77 Symington to Bogend Toll Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-01-28 | 2013-09-18 | 2013-10-28 | 2015-04-22 |  | South Ayrshire | 317957 | -22017.24 | 0 | 0 | 0 | 0 | 0.61 | -22016.63 | 0 | 295940.37 | 0 | [6 empty] | CM_WSI | 100%
403075 | NRSWA C5 Water EGIP Beancross Rd Grangemouth (GMH-OB078-005-SWW7) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-10-25 | 2014-02-27 | 2014-06-17 | 2014-12-17 |  | Falkirk | 44926 | 220.1 | 0 | 0 | 0 | 0 | 0 | 220.1 | 0 | 45146.1 | 0 | [6 empty] | CM_WSI | 100%
401453 | NRSWA C5 Water Wilsonville - Caw Bridges West Lothian | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-09-24 | 2011-11-01 | 2011-10-31 | 2012-06-19 |  | West Lothian | 21041.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21041.64 | 0 | [6 empty] | CM_WSI | 100%
404113 | NRSWA C7 Construction Sewer - Dunlappie Road Culvert Edzell | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-09-14 | 2015-09-14 | 2015-09-09 |  | Angus | 47.16 | 326.18 | 0 | 0 | 0 | 0 | 0 | 326.18 | 0 | 373.34 | 0 | [6 empty] | CM_WWI | 100%
404016 | NRSWA C7 Construction Sewer AWPR SWD03 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS6 | 2014-12-05 | 2015-05-29 | 2016-08-22 | 2017-08-31 |  | Aberdeen City | 29431 | 31033 | 357429.52 | 141873.83 | -54910.91 | -14120.93 | -1206.58 | 460097.93 | 0 | 489528.93 | 0 | [6 empty] | CM_WWI | 100%
500693 | NRSWA C7 Construction Water - A702 Mauricewood Roundabout Penicuick | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-05 | 2015-09-24 | 2015-11-30 | 2017-11-15 | 2017-11-15 | Midlothian | 0 | 618815 | 1448319.37 | 1894699.53 | 29375.28 | 0 | 0 | 3991209.18 | 0 | 3991209.18 | 43684.09 | [6 empty] | CS23W | 100%
404129 | NRSWA C7 Construction Water - A905 Lower Polmaise Junction Stirling | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-07-07 | 2015-07-27 | 2015-11-23 |  | Stirling | 0 | 92121.18 | 0 | 0 | 0 | 0 | -0.18 | 92121 | 0 | 92121 | 0 | [6 empty] | CM_WSI | 100%
404128 | NRSWA C7 Construction Water - A96 Keith Rail Bridge Moray | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-09-28 | 2015-10-26 | 2019-02-28 |  | Moray | 0 | 68865 | -46982 | 0 | 77868.88 | 18.47 | 0 | 99770.35 | 0 | 99770.35 | 0 | [6 empty] | CM_WSI | 100%
404111 | NRSWA C7 Construction Water - Arrochar Street Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-07-23 | 2015-08-17 | 2015-08-14 |  | Glasgow City | 86.46 | 584.73 | 0 | 0 | 0 | 0 | 328.81 | 913.54 | 0 | 1000 | 0 | [6 empty] | CM_WSI | 100%
404014 | NRSWA C7 Construction Water - AWPR 1866 Aqueduct | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS6 | 2014-12-09 | 2015-12-16 | 2016-01-05 | 2018-11-16 |  | Aberdeen City | 215249 | 1053507.57 | 171917.24 | 479055.19 | -137767.34 | -142558.06 | -3041.39 | 1421113.21 | 0 | 1636362.21 | 0 | [6 empty] | CM_WSI | 100%
404015 | NRSWA C7 Construction Water - AWPR SWW19 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS6 | 2014-12-08 | 2015-05-19 | 2016-01-15 | 2018-01-10 |  | Aberdeen City | 29699 | 31102 | 851577.02 | 118239.32 | 53489.16 | -1859.39 | -942.88 | 1051605.23 | 0 | 1081304.23 | 0 | [6 empty] | CM_WSI | 100%
404114 | NRSWA C7 Construction Water - Dunlappie Road Culvert Edzell | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-05-18 | 2015-08-18 | 2015-10-12 | 2016-04-25 |  | Angus | 0 | 37204 | -2482.88 | 546.9 | 0 | 0 | 0 | 35268.02 | 0 | 35268.02 | 0 | [6 empty] | CM_WSI | 100%
404127 | NRSWA C7 Construction Water - Gogar Pedestrian Underpass | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-09-30 | 2015-09-30 | 2016-11-22 |  | City of Edinburgh | 0 | 182820 | 82020.58 | 621.28 | 0 | 0 | 0.01 | 265461.87 | 0 | 265461.87 | 0 | [6 empty] | CM_WSI | 100%
404126 | NRSWA C7 Construction Water - Inverness Western Link Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-07-30 | 2015-07-31 | 2015-10-06 |  | Highland | 0 | 57508.66 | 0 | 0 | 0 | 0 | 0 | 57508.66 | 0 | 57508.66 | 0 | [6 empty] | CM_WSI | 100%
404119 | NRSWA C7 Construction Water - Inverness Western Link Road - 4041190000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-30 | 2015-09-30 | 2015-10-01 | 2016-08-09 | 2016-09-21 | Highland | 0 | 785867.13 | 29265.61 | 282.88 | 0 | 0 | 0.32 | 815415.94 | 0 | 815415.94 | 0 | [6 empty] | CM_WSI | 100%
404088 | NRSWA C7 Construction Water-A9 Dualling Kincraig to Dalraddy | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-01-27 | 2015-08-31 | 2015-09-01 | 2016-07-07 |  | Highland | 5000 | 793732.11 | 123403.86 | -6719.05 | 27949.95 | 499.28 | -499.28 | 938366.87 | 0 | 943366.87 | 0 | [6 empty] | CM_WSI | 100%
404013 | NRSWA C7 Construction Water-AWPR 1924 Aqueduct | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS6 | 2014-12-02 | 2015-08-10 | 2015-08-10 | 2018-02-23 |  | Aberdeen City | 404227 | 870325.07 | 2315805.62 | -538575.69 | -317925.23 | -91773.29 | -3672.94 | 2234183.54 | 0 | 2638410.54 | 0 | [6 empty] | CM_WSI | 100%
404107 | NRSWA C7 Construction Water-Forth Replacement Crossing SWW25 Remedial Works | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-06-24 | 2015-06-24 | 2016-10-10 |  | City of Edinburgh | 70.74 | 43872.26 | 10654.21 | 273.45 | 0 | 0 | 0.11 | 54800.03 | 0 | 54870.77 | 0 | [6 empty] | CM_WSI | 100%
404087 | NRSWA C7 Construction Water-Station Road Polmont | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-01-27 | 2015-04-29 | 2015-05-15 | 2015-10-14 |  | Falkirk | 1503.56 | 42243.79 | 0 | 0 | 0 | 0 | 0 | 42243.79 | 0 | 43747.35 | 0 | [6 empty] | CM_WSI | 100%
502413 | NRSWA Construction PIF Water Freuchie Bridge Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | Fife | 0 | 0 | 1693 | -275.79 | 0 | 0 | 0.25 | 1417.46 | 0 | 1417.46 | 43684.09 | [6 empty] | CS23W | 100%
501320 | NRSWA Construction Sewer - A9-A85 Crieff Road Junctions | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-12-16 | 2016-11-30 | 2017-01-06 | 2018-03-23 | 2018-03-23 | Perth and Kinross | 0 | 974.97 | 413509.03 | 788194 | -470860.68 | 0 | 0 | 731817.32 | 0 | 731817.32 | 2614273.27 | [6 empty] | CS23S | 100%
501319 | NRSWA Construction Sewer - Aberdeen Bypass - SWD09 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS6 | 2016-02-26 | 2016-08-15 | 2016-08-29 | 2019-05-29 | 2019-08-07 | Aberdeen City | 0 | 20998.05 | 597152.6 | 84515.41 | 170034.61 | -290106.42 | -1728.49 | 580865.76 | 0 | 580865.76 | 2614273.27 | [6 empty] | CS23S | 100%
501631 | NRSWA Construction Sewer - Aberdeen Inverness Rail Enhancement - Elgin | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-07-29 | 2016-08-31 | 2017-03-15 | 2017-03-15 | Moray | 0 | 13506 | -5898.77 | -922.7 | 0 | 0 | 0 | 6684.53 | 0 | 6684.53 | 2614273.27 | [6 empty] | CS23S | 100%
501630 | NRSWA Construction Sewer - Aberdeen Inverness Rail Enhancement - Forres | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-08 | 2016-07-29 | 2016-09-05 | 2017-03-15 | 2017-03-15 | Moray | 0 | 2879 | 22357.96 | 66951.81 | 0 | 0 | 2747.31 | 94936.08 | 0 | 94936.08 | 2614273.27 | [6 empty] | CS23S | 100%
502126 | NRSWA Construction Sewer - Almondbank Flood Prevention Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-03-02 | 2016-11-30 | 2017-02-20 | 2017-12-08 | 2017-12-08 | Perth and Kinross | 0 | 1000 | 56512.89 | 226563.59 | 27419.85 | 0 | -0.02 | 311496.31 | 0 | 311496.31 | 2614273.27 | [6 empty] | CS23S | 100%
502253 | NRSWA Construction Sewer - Littlemill Bridge Replacement Rankinston East Ayrshire | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2016-06-29 | 2017-12-18 | 2018-06-25 | 2021-01-13 | 2021-01-13 | East Ayrshire | 0 | 0 | 723.75 | 50110.25 | -17834 | 4029.61 | 61370.39 | 98400 | 31250 | 129650 | 2614273.27 | [6 empty] | CS23S | 100%
501624 | NRSWA Construction Sewer - M8 Motorway - SWS20B | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-07-27 | 2016-07-27 | 2017-03-01 | 2017-03-01 | South Lanarkshire | 0 | 6655 | 982933.2 | 17098.7 | 169.33 | 0 | 0 | 1006856.23 | 0 | 1006856.23 | 2614273.27 | [6 empty] | CS23S | 100%
500988 | NRSWA Construction Sewer - M8 Motorway Ancillary Works | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-11-29 | 2016-11-30 | 2018-12-18 | 2018-12-18 | North Lanarkshire | 0 | 2763.28 | 307308.52 | 92176.62 | 68797.73 | 79.94 | -79.94 | 471046.15 | 0 | 471046.15 | 2614273.27 | [6 empty] | CS23S | 100%
502561 | NRSWA Construction Sewer - M9 Junction 5 Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-02-06 | 2017-09-14 | 2017-09-21 | 2018-03-16 | 2018-03-16 | Falkirk | 0 | 0 | 686.51 | 12376.39 | -1505.38 | 0 | 1402.48 | 12960 | 0 | 12960 | 2614273.27 | [6 empty] | CS23S | 100%
502547 | NRSWA Construction Sewer - Sauchiehall St Glasgow - Streetscape Works | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-01-31 | 2017-09-26 | 2017-09-29 | 2018-05-04 | 2018-05-04 | Glasgow City | 0 | 0 | 397.56 | 54893.44 | -44441.82 | 0 | 0 | 10849.18 | 0 | 10849.18 | 2614273.27 | [6 empty] | CS23S | 100%
502807 | NRSWA Construction Sewer A9 Dualling Luncarty to Birnam | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2017-07-25 | 2018-03-29 | 2018-03-30 | 2020-12-01 | 2020-12-01 | Perth and Kinross | 0 | 0 | 0 | 68338 | 85958.23 | 235820.98 | 89291.83 | 479409.04 | 0 | 479409.04 | 2614273.27 | [6 empty] | CS23S | 100%
503147 | NRSWA Construction Sewer A90-A96 Haudagain Improvement Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2018-03-29 | 2018-07-23 | 2018-08-17 | 2021-02-19 | 2021-05-21 | Aberdeen City | 0 | 0 | 0 | 0 | 74469.45 | 125640.44 | 197443.45 | 397553.34 | 2446.67 | 400000.01 | 2614273.27 | [6 empty] | CS23S | 100%
502863 | NRSWA Construction Sewer B9090 Realignment Clephanton | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-05-23 | 2018-06-04 | 2018-11-30 | 2018-11-30 | Highland | 0 | 0 | 0 | 0 | 5116.33 | 0 | 0 | 5116.33 | 0 | 5116.33 | 2614273.27 | [6 empty] | CS23S | 100%
503607 | NRSWA Construction Sewer Carman Road Rail Bridge West Dunbartonshire | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MSU | 2020-03-02 | 2020-04-06 | 2020-04-23 | 2020-09-01 | 2020-10-23 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 56370.29 | 56370.29 | 1683.63 | 58053.92 | 2614273.27 | [6 empty] | CS23S | 100%
502866 | NRSWA Construction Sewer Greenhills Road Widening East Kilbride | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2018-01-31 | 2018-04-11 | 2018-06-26 | 2020-12-01 | 2020-12-02 | South Lanarkshire | 0 | 0 | 0 | 37720.03 | 453779.97 | 2382122.57 | 90716.93 | 2964339.5 | 0 | 2964339.5 | 2614273.27 | [6 empty] | CS23S | 100%
502797 | NRSWA Construction Sewer Kirk Rd Widening Dunbeg Oban | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-03-29 | 2018-03-30 | 2018-10-26 | 2018-10-26 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 29862.91 | 163072 | 16365.89 | -578.58 | 208722.22 | 0 | 208722.22 | 2614273.27 | [6 empty] | CS23S | 100%
502906 | NRSWA Construction Sewer Station Hotel Guild St Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-10-25 | 2018-03-27 | 2018-03-29 | 2018-09-27 | 2018-09-27 | Aberdeen City | 0 | 0 | 0 | 26800 | 143084.11 | 0 | 0.01 | 169884.12 | 0 | 169884.12 | 2614273.27 | [6 empty] | CS23S | 100%
402335 | NRSWA Construction Sewers Forth Crossing SW-D3A | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-09-12 | 2012-05-16 | 2012-08-13 | 2015-05-04 |  | Fife | 3657684 | 7000 | 13133.6 | 0 | 0 | 0 | 0 | 20133.6 | 0 | 3677817.6 | 0 | [6 empty] | CM_WWI | 100%
402336 | NRSWA Construction Sewers Forth Crossing SW-D9A - B | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-09-12 | 2012-08-29 | 2012-11-19 | 2013-11-14 |  | City of Edinburgh | 409918 | -10778.56 | 0 | 0 | 0 | 0 | 8778.64 | -1999.92 | 0 | 407918.08 | 0 | [6 empty] | CM_WWI | 100%
501625 | NRSWA Construction Water - A70 Glenbuck Road Realignment | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-29 | 2016-06-30 | 2019-08-29 | 2019-08-29 | East Ayrshire | 0 | 23053 | 259685.44 | 99482.56 | 104298.53 | 97402.64 | -1501.49 | 582420.68 | 0 | 582420.68 | 43684.09 | [6 empty] | CS23W | 100%
501944 | NRSWA Construction Water - A71 Darvel Landslip Remedial Works | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-05-30 | 2016-06-28 | 2017-01-09 | 2017-01-09 | East Ayrshire | 0 | 2000 | 103028.74 | 0 | 0 | 0 | 3910.73 | 108939.47 | 0 | 108939.47 | 43684.09 | [6 empty] | CS23W | 100%
503346 | NRSWA Construction Water - A736 Brackenburn Bridge Kilmaurs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-09-17 | 2018-11-26 | 2018-11-29 | 2019-03-11 | 2019-03-11 | East Ayrshire | 0 | 0 | 0 | 0 | 41499.35 | 10489.08 | -64.6 | 51923.83 | 0 | 51923.83 | 43684.09 | [6 empty] | CS23W | 100%
502875 | NRSWA Construction Water - A827 West of Fearnan Culvert Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-12-13 | 2018-01-31 | 2018-02-12 | 2018-05-17 | 2018-05-17 | Perth and Kinross | 0 | 0 | 0 | 26699.06 | 7720.64 | 0 | 0 | 34419.7 | 0 | 34419.7 | 43684.09 | [6 empty] | CS23W | 100%
502634 | NRSWA Construction Water - A835 Leckmelm Culvert Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-17 | 2017-05-31 | 2017-05-31 | 2018-10-22 | 2018-10-22 | Highland | 0 | 0 | 201.9 | 78112.3 | 115467.18 | 0 | -0.49 | 193780.89 | 0 | 193780.89 | 43684.09 | [6 empty] | CS23W | 100%
503351 | NRSWA Construction Water - A887 Lagain Bhain Bridge Replacement Invermoriston | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-21 | 2018-12-21 | 2020-07-24 | 2020-07-24 | Highland | 0 | 0 | 0 | 0 | 29852.23 | 16352.89 | 165951.88 | 212157 | 0 | 212157 | 43684.09 | [6 empty] | CS23W | 100%
502289 | NRSWA Construction Water - A913 Burnside Bridge Replacement Newburgh Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-07-26 | 2017-02-28 | 2017-02-28 | 2017-08-14 | 2017-08-14 | Fife | 0 | 0 | 25576 | 25313.18 | 0 | 0 | 0 | 50889.18 | 0 | 50889.18 | 43684.09 | [6 empty] | CS23W | 100%
501263 | NRSWA Construction Water - A9-A85 Crieff Road Junctions | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-15 | 2016-11-30 | 2016-12-20 | 2018-02-07 | 2018-02-07 | Perth and Kinross | 0 | 11764 | 92967.83 | 240763.72 | 385338.82 | 1628.16 | -1411.08 | 731051.45 | 0 | 731051.45 | 43684.09 | [6 empty] | CS23W | 100%
502125 | NRSWA Construction Water - Almondbank Flood Prevention Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-02 | 2016-08-24 | 2016-09-26 | 2018-10-10 | 2018-10-10 | Perth and Kinross | 0 | 1000 | 341808 | 418205 | 32809.31 | 0 | 0.01 | 793822.32 | 0 | 793822.32 | 43684.09 | [6 empty] | CS23W | 100%
502045 | NRSWA Construction Water - B714 Girthill to Yonderhouses Road Realignment | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-10-31 | 2017-07-10 | 2017-07-26 | 2017-07-26 | North Ayrshire | 0 | 1000 | 34540.19 | 6190.18 | 0 | 0 | 0 | 41730.37 | 0 | 41730.37 | 43684.09 | [6 empty] | CS23W | 100%
502728 | NRSWA Construction Water - B792 Inchmuir Road Bathgate | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-09-04 | 2017-09-12 | 2017-09-14 | 2017-09-14 | West Lothian | 0 | 0 | 0 | 5430.52 | 0 | 0 | 0 | 5430.52 | 0 | 5430.52 | 43684.09 | [6 empty] | CS23W | 100%
503399 | NRSWA Construction Water - B936 Freuchie Bridge Deck Replacement Freuchie Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-09-18 | 2018-10-17 | 2018-11-05 | 2019-01-03 | 2019-01-03 | Fife | 0 | 0 | 0 | 0 | 14310.48 | 0 | 0 | 14310.48 | 0 | 14310.48 | 43684.09 | [6 empty] | CS23W | 100%
503348 | NRSWA Construction Water - B966 Abbeyton Bridge Fordoun Aberdeenshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2019-02-26 | 2019-03-28 | 2020-12-01 | 2020-12-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 32194.49 | 43540.7 | 130588.28 | 206323.47 | 10585.6 | 216909.07 | 43684.09 | [6 empty] | CS23W | 100%
503345 | NRSWA Construction Water - Baldovan Road Culvert Dundee | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-20 | 2018-12-21 | 2020-04-01 | 2020-04-01 | Dundee City | 0 | 0 | 0 | 0 | 24491.66 | 19899.17 | -53.83 | 44337 | 0 | 44337 | 43684.09 | [6 empty] | CS23W | 100%
502884 | NRSWA Construction Water - Balgownie Drive Retaining Wall Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-11-23 | 2018-01-08 | 2018-01-29 | 2018-09-27 | 2018-09-27 | Aberdeen City | 0 | 0 | 0 | 25685.52 | 91802.02 | 0 | -0.04 | 117487.5 | 0 | 117487.5 | 43684.09 | [6 empty] | CS23W | 100%
503566 | NRSWA Construction Water - Balgraystone Road Improvements Barrhead | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-05-30 | 2019-07-23 | 2019-08-09 | 2019-12-19 | 2020-04-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 11529.77 | 86.01 | 11615.78 | 0 | 11615.78 | 43684.09 | [6 empty] | CS23W | 100%
501627 | NRSWA Construction Water - Bishopbriggs Relief Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-06-30 | 2016-06-30 | 2017-01-30 | 2017-01-30 | East Dunbartonshire | 0 | 2438 | 182099.91 | -1240.72 | 0 | 0 | 1514.17 | 184811.36 | 0 | 184811.36 | 43684.09 | [6 empty] | CS23W | 100%
501626 | NRSWA Construction Water - Bush Bridge Replacement Craigellachie | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-05-30 | 2016-06-27 | 2017-01-26 | 2017-01-26 | Moray | 0 | 1219 | 43251.73 | -34848.99 | 0 | 0 | 0 | 9621.74 | 0 | 9621.74 | 43684.09 | [6 empty] | CS23W | 100%
501629 | NRSWA Construction Water - Cathkin Relief Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-30 | 2016-06-30 | 2017-03-29 | 2017-03-29 | South Lanarkshire | 0 | 22134 | 249939.19 | 51010.24 | 0 | 0 | 0 | 323083.43 | 0 | 323083.43 | 43684.09 | [6 empty] | CS23W | 100%
501751 | NRSWA Construction Water - Chambers Street Statues Edinburgh | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-03-30 | 2016-04-22 | 2017-02-08 | 2017-02-08 | City of Edinburgh | 0 | 355.68 | 24952.64 | 2648.27 | 0 | 0 | 0 | 27956.59 | 0 | 27956.59 | 43684.09 | [6 empty] | CS23W | 100%
503352 | NRSWA Construction Water - Chapleton Bridge Widening Port Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-11-26 | 2018-11-29 | 2019-04-26 | 2019-04-26 | Inverclyde | 0 | 0 | 0 | 0 | 40000 | -7407.54 | 243.61 | 32836.07 | 0 | 32836.07 | 43684.09 | [6 empty] | CS23W | 100%
503446 | NRSWA Construction Water - Corran Bridge Lochgilphead | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2019-02-26 | 2019-08-05 | 2019-08-12 | 2022-02-14 | 2022-02-25 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 457.94 | 14092.93 | 51910.65 | 66461.52 | 0 | 66461.52 | 43684.09 | [6 empty] | CS23W | 100%
500986 | NRSWA Construction Water - Cowlairs Rail Bridge Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-05-23 | 2016-06-22 | 2019-01-10 | 2019-01-10 | Glasgow City | 0 | 3770.87 | 273611.53 | -40396 | 33756.71 | 0 | 0 | 270743.11 | 0 | 270743.11 | 43684.09 | [6 empty] | CS23W | 100%
503396 | NRSWA Construction Water - Craigend Bridge Coulter Biggar | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-11-28 | 2019-02-26 | 2019-02-26 | 2019-09-09 | 2019-09-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 22500.08 | 5645.67 | 0 | 28145.75 | 0 | 28145.75 | 43684.09 | [6 empty] | CS23W | 100%
502544 | NRSWA Construction Water - Duck Bay (Loch Lomond) South Access Bridge Repairs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-01-19 | 2017-05-29 | 2017-06-09 | 2017-08-23 | 2017-08-23 | Argyll and Bute-North Argyll | 0 | 0 | 410 | 27284.18 | 0 | 0 | 0 | 27694.18 | 0 | 27694.18 | 43684.09 | [6 empty] | CS23W | 100%
502000 | NRSWA Construction Water - EGIP Cleland Station Bridge Cleland | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-06-30 | 2016-07-28 | 2017-01-19 | 2017-01-19 | North Lanarkshire | 0 | 1000 | 97445 | -1390.99 | 0 | 0 | 0 | 97054.01 | 0 | 97054.01 | 43684.09 | [6 empty] | CS23W | 100%
502545 | NRSWA Construction Water - EGIP Falkirk - Dunblane Bridge Replacements | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-08 | 2017-09-14 | 2017-09-21 | 2019-01-07 | 2019-01-07 | Stirling | 0 | 0 | 2274.83 | 233841.31 | 140172.9 | 0 | 0 | 376289.04 | 0 | 376289.04 | 43684.09 | [6 empty] | CS23W | 100%
502560 | NRSWA Construction Water - Feabuie Culvert Replacement Culloden Inverness | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-06 | 2017-08-28 | 2017-09-18 | 2018-04-19 | 2018-04-19 | Highland | 0 | 0 | 569.85 | 35547.15 | -14686.18 | 0 | 0.01 | 21430.83 | 0 | 21430.83 | 43684.09 | [6 empty] | CS23W | 100%
503547 | NRSWA Construction Water - Glasgow Airport Investment Area | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2019-06-25 | 2019-07-26 | 2019-09-02 | 2020-05-04 | 2020-05-04 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 37000 | 0 | 37000 | 0 | 37000 | 43684.09 | [6 empty] | CS23W | 100%
504548 | NRSWA Construction Water - Grandholme Pipeline | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MSU | 2020-03-02 | 2020-03-16 | 2020-04-15 | 2021-02-15 | 2021-02-15 | - | 0 | 0 | 0 | 0 | 0 | 861.2 | 0 | 861.2 | 0 | 861.2 | 0 | [6 empty] | CS23W | 100%
500961 | NRSWA Construction Water - Huntly Flood Scheme Aberdeenshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-08-29 | 2016-08-31 | 2016-11-25 | 2016-11-25 | Aberdeen City | 0 | 6312 | 109442.57 | 1196.61 | 0 | 0 | 0 | 116951.18 | 0 | 116951.18 | 43684.09 | [6 empty] | CS23W | 100%
503350 | NRSWA Construction Water - Inverness West Link Road Phase 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-12-21 | 2018-12-21 | 2020-02-28 | 2020-04-01 | Highland | 0 | 0 | 0 | 0 | 16000 | 66568.11 | 0 | 82568.11 | 0 | 82568.11 | 43684.09 | [6 empty] | CS23W | 100%
502189 | NRSWA Construction Water - Kirkill Culvert Replacement Nr Mouswald Dumfries | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-30 | 2016-08-24 | 2016-08-24 | 2016-08-25 | 2016-08-25 | Dumfries and Galloway | 0 | 0 | 338.87 | 0 | 0 | 0 | 0 | 338.87 | 0 | 338.87 | 43684.09 | [6 empty] | CS23W | 100%
500905 | NRSWA Construction Water - Kirkland Brae Tinwald Locharbriggs Dumfries. | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-12-11 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | Dumfries and Galloway | 0 | 2159 | 100771.11 | 0 | 0 | 0 | 0 | 102930.11 | 0 | 102930.11 | 43684.09 | [6 empty] | CS23W | 100%
502092 | NRSWA Construction Water - Lampits Road Bus Laybys Carstairs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-17 | 2016-08-16 | 2016-09-22 | 2017-02-10 | 2017-02-10 | South Lanarkshire | 0 | 459.38 | 3901.87 | 17490.78 | 0 | 0 | 0 | 21852.03 | 0 | 21852.03 | 43684.09 | [6 empty] | CS23W | 100%
502252 | NRSWA Construction Water - Littlemill Bridge Replacement Rankinston East Ayrshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2016-06-29 | 2017-12-18 | 2018-06-25 | 2021-01-07 | 2021-01-07 | East Ayrshire | 0 | 0 | 1126.58 | 52223.42 | -8349.71 | 3631.92 | 72068.79 | 120701 | 30000 | 150701 | 43684.09 | [6 empty] | CS23W | 100%
501628 | NRSWA Construction Water - Lochwinnoch Bridge Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-14 | 2016-06-29 | 2017-01-30 | 2017-01-30 | Renfrewshire | 0 | 3311 | 132544 | 10325.56 | 0 | 0 | 0.26 | 146180.82 | 0 | 146180.82 | 43684.09 | [6 empty] | CS23W | 100%
502559 | NRSWA Construction Water - M9 Junction 5 Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-09 | 2017-12-21 | 2017-12-22 | 2018-03-16 | 2018-03-16 | Falkirk | 0 | 0 | 509.66 | 214613.32 | -83506.39 | 0 | 0.01 | 131616.6 | 0 | 131616.6 | 43684.09 | [6 empty] | CS23W | 100%
503361 | NRSWA Construction Water - Muir Street Extension Motherwell | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MSU | 2020-07-08 | 2020-11-23 | 2021-03-25 | 2021-07-16 | 2021-10-18 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 118.42 | 54342.59 | 54461.01 | 95539 | 150000.01 | 43684.09 | [6 empty] | CS23W | 100%
500960 | NRSWA Construction Water - Park Farm Road Bridge Linlithgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-02-16 | 2016-02-25 | 2016-06-27 | 2016-07-12 | West Lothian | 0 | 33673 | 21845.08 | 546.9 | 0 | 0 | 0.09 | 56065.07 | 0 | 56065.07 | 43684.09 | [6 empty] | CS23W | 100%
502546 | NRSWA Construction Water - Sauchiehall St Glasgow - Streetscape Works | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-01-31 | 2017-07-31 | 2017-08-14 | 2018-07-09 | 2018-07-09 | Glasgow City | 0 | 0 | 574.41 | 169362.59 | -7381.66 | 0 | 0 | 162555.34 | 0 | 162555.34 | 43684.09 | [6 empty] | CS23W | 100%
501321 | NRSWA Construction Water - Seatown Footbridge Cullen Moray | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-12-15 | 2016-03-16 | 2016-04-28 | 2016-09-29 | 2016-10-14 | Moray | 0 | 3733 | 38364.63 | 334.04 | 0 | 0 | 0.27 | 42431.94 | 0 | 42431.94 | 43684.09 | [6 empty] | CS23W | 100%
503349 | NRSWA Construction Water - Skolie Burn Bridge Replacement Loganlea | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-18 | 2019-02-08 | 2020-09-03 | 2020-09-03 | West Lothian | 0 | 0 | 0 | 0 | 6500 | 36409.48 | 13479.32 | 56388.8 | 0 | 56388.8 | 43684.09 | [6 empty] | CS23W | 100%
502093 | NRSWA Construction Water - Taychreggan Retaining Wall Appin Argyll | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-11 | 2016-08-29 | 2016-10-27 | 2017-03-28 | 2017-03-28 | Argyll and Bute-North Argyll | 0 | 499.11 | 20762.39 | 12801.7 | 0 | 0 | 978.51 | 35041.71 | 0 | 35041.71 | 43684.09 | [6 empty] | CS23W | 100%
503406 | NRSWA Construction Water - Westburn Roundabout Cambuslang | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-12-21 | 2019-04-29 | 2019-05-01 | 2020-02-25 | 2020-04-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 19284.11 | 238517.58 | -0.04 | 257801.65 | 0 | 257801.65 | 43684.09 | [6 empty] | CS23W | 100%
503620 | NRSWA Construction Water A811 Lomond Rd Bridge Balloch | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-10-03 | 2019-11-25 | 2019-11-25 | 2020-03-04 | 2020-04-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 230484.45 | 0 | 230484.45 | 0 | 230484.45 | 43684.09 | [6 empty] | CS23W | 100%
502808 | NRSWA Construction Water A9 Dualling Luncarty to Birnam | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2017-07-26 | 2018-03-30 | 2018-03-30 | 2020-12-01 | 2020-12-01 | Perth and Kinross | 0 | 0 | 0 | 219766.03 | 593166.14 | 1169067.48 | 337670.93 | 2319670.58 | 0 | 2319670.58 | 43684.09 | [6 empty] | CS23W | 100%
503146 | NRSWA Construction Water A90-A96 Haudagain Improvement Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-03-29 | 2018-07-23 | 2018-08-17 | 2021-02-19 | 2021-05-21 | Aberdeen City | 0 | 0 | 0 | 0 | 84114.71 | 827288.26 | 147509.03 | 1058912 | 0 | 1058912 | 43684.09 | [6 empty] | CS23W | 100%
502862 | NRSWA Construction Water B9090 Realignment Clephanton | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-06-28 | 2018-07-03 | 2019-02-26 | 2019-02-26 | Highland | 0 | 0 | 0 | 0 | 308101.04 | 799.01 | -799 | 308101.05 | 0 | 308101.05 | 43684.09 | [6 empty] | CS23W | 100%
502831 | NRSWA Construction Water Baker Street - Drumfrochar Rd Greenock | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-01-30 | 2018-02-08 | 2019-03-11 | 2019-03-11 | Inverclyde | 0 | 0 | 0 | 34855.86 | 153944.14 | -5955.78 | -0.07 | 182844.15 | 0 | 182844.15 | 43684.09 | [6 empty] | CS23W | 100%
503606 | NRSWA Construction Water Carman Road Rail Bridge Renton West Dunbartonshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-08-30 | 2019-09-24 | 2019-09-25 | 2020-02-27 | 2020-04-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 17084.82 | 0 | 17084.82 | 0 | 17084.82 | 43684.09 | [6 empty] | CS23W | 100%
503254 | NRSWA Construction Water Clyde Waterfron Renfrew | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-05-23 | 2019-03-25 | 2019-03-25 | 2021-07-05 | 2021-07-05 | Renfrewshire | 0 | 0 | 0 | 0 | 62296.74 | 42784.68 | 33870.82 | 138952.24 | 303805.7 | 442757.94 | 43684.09 | [6 empty] | CS23W | 100%
503265 | NRSWA Construction Water Clyde Waterfron Renfrew - TRIAL HOLE | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-05-29 | 2018-06-27 | 2018-06-27 | 2018-08-01 | 2018-08-01 | Renfrewshire | 0 | 0 | 0 | 0 | 19592.06 | 0 | 0 | 19592.06 | 0 | 19592.06 | 43684.09 | [6 empty] | CS23W | 100%
402329 | NRSWA Construction Water Forth Crossing SWW11 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-08-29 | 2012-10-15 | 2015-04-01 |  | City of Edinburgh | 469402 | 30084.6 | 0 | 0 | 0 | 0 | 0.37 | 30084.97 | 0 | 499486.97 | 0 | [6 empty] | CM_WSI | 100%
402330 | NRSWA Construction Water Forth Crossing SWW14 - 15 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-07-23 | 2012-09-24 | 2016-07-21 |  | City of Edinburgh | 246338 | 2346 | 62267.85 | 0 | 0 | 0 | 0 | 64613.85 | 0 | 310951.85 | 0 | [6 empty] | CM_WSI | 100%
402331 | NRSWA Construction Water Forth Crossing SWW16 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2013-06-24 | 2013-11-18 | 2015-11-26 |  | Fife | 50172 | 28502.85 | 0 | 0 | 0 | 0 | 0 | 28502.85 | 0 | 78674.85 | 0 | [6 empty] | CM_WSI | 100%
402332 | NRSWA Construction Water Forth Crossing SWW18 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-07-26 | 2012-09-17 | 2015-12-10 |  | Fife | 223077 | 166796 | 25732.56 | 1043.79 | 6414.86 | 0 | 0 | 199987.21 | 0 | 423064.21 | 0 | [6 empty] | CM_WSI | 100%
402333 | NRSWA Construction Water Forth Crossing SWW25 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-08 | 2012-07-26 | 2013-05-13 | 2014-03-06 |  | City of Edinburgh | 45067.05 | 168.92 | 0 | 133.92 | 0 | 0 | 13859.77 | 14162.61 | 0 | 59229.66 | 0 | [6 empty] | CM_WSI | 100%
402326 | NRSWA Construction Water Forth Crossing SWW5 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-06 | 2012-07-20 | 2012-09-17 | 2015-11-26 |  | City of Edinburgh | 104893 | 42733.59 | 163.19 | 0 | 0 | 0 | 0 | 42896.78 | 0 | 147789.78 | 0 | [6 empty] | CM_WSI | 100%
402327 | NRSWA Construction Water Forth Crossing SWW7 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-06 | 2012-07-26 | 2012-09-17 | 2015-11-26 |  | City of Edinburgh | 457227 | 290048 | 6160.58 | 273.45 | 0 | 0 | 0 | 296482.03 | 0 | 753709.03 | 0 | [6 empty] | CM_WSI | 100%
503629 | NRSWA Construction Water Gibshill Rd Weir St Greenock | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-08-22 | 2019-09-24 | 2019-09-25 | 2020-02-27 | 2020-04-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 40417.59 | 0 | 40417.59 | 0 | 40417.59 | 43684.09 | [6 empty] | CS23W | 100%
502867 | NRSWA Construction Water Greenhills Road Widening East Kilbride | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-31 | 2018-04-11 | 2018-06-26 | 2020-12-01 | 2020-12-01 | South Lanarkshire | 0 | 0 | 0 | 44162.03 | 370888.04 | 1004892.94 | 20000 | 1439943.01 | 0 | 1439943.01 | 43684.09 | [6 empty] | CS23W | 100%
502798 | NRSWA Construction Water Kirk Rd Widening Dunbeg Oban | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-03-26 | 2018-03-30 | 2018-10-19 | 2018-10-19 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 89717 | 420719.43 | 1335.63 | -430.81 | 511341.25 | 0 | 511341.25 | 43684.09 | [6 empty] | CS23W | 100%
502737 | NRSWA Construction Water Muirhead Rd Overbridge Replacement Baillieston | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-11-29 | 2017-11-30 | 2019-02-04 | 2019-02-04 | Glasgow City | 0 | 0 | 0 | 172469.57 | 85750.07 | 1849.69 | -1849.68 | 258219.65 | 0 | 258219.65 | 43684.09 | [6 empty] | CS23W | 100%
502799 | NRSWA Construction Water Ravelrig Road Balerno | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-09-29 | 2017-09-29 | 2018-01-24 | 2018-03-22 | City of Edinburgh | 0 | 0 | 0 | 485000.23 | -399.96 | 0 | 0.01 | 484600.28 | 0 | 484600.28 | 43684.09 | [6 empty] | CS23W | 100%
502345 | NRSWA Construction Water-11 Finlayson Drive Airdrie | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-10-07 | 2017-03-07 | 2017-03-10 | 2017-08-07 | 2017-08-07 | Perth and Kinross | 0 | 0 | 98646 | 424520.42 | 550 | 0 | 0 | 523716.42 | 0 | 523716.42 | 43684.09 | [6 empty] | CS23W | 100%
502414 | NRSWA Construction Water-A737 Dalry Bypass | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS4 | 2016-12-12 | 2017-09-29 | 2017-09-29 | 2020-01-30 |  | North Ayrshire | 0 | 0 | 2350 | 1032257.81 | 1472653.96 | 298320.82 | 0 | 2805582.59 | 0 | 2805582.59 | 43684.09 | [6 empty] | CS23W | 100%
503038 | NRSWA Construction Water-A737 The Den Dalry | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-19 | 2018-06-29 | 2018-06-29 | 2020-03-12 | 2020-04-01 | North Ayrshire | 0 | 0 | 0 | 2927.69 | 204424.4 | 237391.45 | -8.09 | 444735.45 | 0 | 444735.45 | 43684.09 | [6 empty] | CS23W | 100%
503037 | NRSWA Construction Water-A77 Maybole Bypass | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-23 | 2018-08-20 | 2018-08-31 | 2020-10-20 | 2020-10-21 | South Ayrshire | 0 | 0 | 0 | 3469.61 | 56789.3 | 406122.27 | 426199.82 | 892581 | 0 | 892581 | 43684.09 | [6 empty] | CS23W | 100%
503138 | NRSWA Construction Water-A830 Shlatach Rail Bridge Glenfinnan | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-03-28 | 2018-11-26 | 2018-12-03 | 2021-05-13 | 2021-05-13 | Highland | 0 | 0 | 0 | 0 | 66086 | 83414 | 101000 | 250500 | 183676 | 434176 | 43684.09 | [6 empty] | CS23W | 100%
503055 | NRSWA Construction Water-A9 Berriedale Braes Re-Alignment | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-30 | 2018-06-28 | 2018-07-02 | 2019-07-29 | 2019-07-29 | Highland | 0 | 0 | 0 | 3191.41 | 38248.61 | 31226.37 | 0.01 | 72666.4 | 0 | 72666.4 | 43684.09 | [6 empty] | CS23W | 100%
503288 | NRSWA Construction Water-A9 Dualling Tay Crossing to Ballinluig | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2018-11-07 | 2020-12-21 | 2020-12-30 | 2022-03-16 | 2022-05-25 | Perth and Kinross | 0 | 0 | 0 | 0 | 15000.06 | 47999.94 | 100532.72 | 163532.72 | 1409467.29 | 1573000.01 | 43684.09 | [6 empty] | CS23W | 100%
502309 | NRSWA Construction Water-A95 Cromdale Footbridge Replacement Near Grantown-on-Spey | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-08-02 | 2017-01-06 | 2017-01-06 | 2017-01-26 | 2017-01-26 | Highland | 0 | 0 | 2071.79 | 546.9 | 0 | 0 | 0.66 | 2619.35 | 0 | 2619.35 | 43684.09 | [6 empty] | CS23W | 100%
503081 | NRSWA Construction Water-B9006 Inshes Bridge Widening Inverness | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-06-28 | 2018-06-28 | 2018-08-17 | 2018-08-17 | Highland | 0 | 0 | 0 | 0 | 75514.68 | 0 | -0.06 | 75514.62 | 0 | 75514.62 | 43684.09 | [6 empty] | CS23W | 100%
503097 | NRSWA Construction Water-Bridgend Bridges near Stenhousemuir | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-04-11 | 2018-09-17 | 2018-10-08 | 2020-12-01 | 2020-12-01 | Stirling | 0 | 0 | 0 | 0 | 100084 | -5835.34 | 38496.34 | 132745 | 0 | 132745 | 43684.09 | [6 empty] | CS23W | 100%
502321 | NRSWA Construction Water-Lornty Farmhouse Blairgowrie | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-10-07 | 2016-11-30 | 2017-02-10 | 2017-06-29 | 2017-07-03 | Perth and Kinross | 0 | 0 | 70604.97 | 111905.6 | 0 | 0 | 0.29 | 182510.86 | 0 | 182510.86 | 43684.09 | [6 empty] | CS23W | 100%
503057 | NRSWA Construction Water-Retaining Wall on Galashiels Rd Walkerburn | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-23 | 2018-02-27 | 2018-03-15 | 2018-04-03 | 2018-04-03 | Scottish Borders | 0 | 0 | 0 | 0 | 8.81 | 0 | 0.01 | 8.82 | 0 | 8.82 | 43684.09 | [6 empty] | CS23W | 100%
502415 | NRSWA Construction Water-Slaughterhouse Park Dounby Orkney | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-26 | 2017-06-30 | 2018-03-28 | 2018-03-28 | Orkney Islands | 0 | 0 | 309.57 | 58498.43 | -174.19 | 0 | 0 | 58633.81 | 0 | 58633.81 | 43684.09 | [6 empty] | CS23W | 100%
503043 | NRSWA Construction Water-Springkell Avenue Rail Bridge Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-30 | 2018-02-20 | 2018-02-21 | 2018-09-20 | 2018-09-20 | Glasgow City | 0 | 0 | 0 | 4738 | 37054.69 | 0 | 0 | 41792.69 | 0 | 41792.69 | 43684.09 | [6 empty] | CS23W | 100%
503095 | NRSWA Construction Water-White Cart Flood Scheme Glasgow Area 36 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-06-15 | 2018-06-26 | 2018-11-12 | 2018-11-12 | Glasgow City | 0 | 0 | 0 | 0 | 5273.5 | 0 | 0 | 5273.5 | 0 | 5273.5 | 43684.09 | [6 empty] | CS23W | 100%
505384 | NRSWA Edinburgh Trams York Place to Newhaven | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2020-03-11 | 2020-07-06 | 2020-07-09 | 2024-02-23 | 2024-02-23 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 487566 | 487566 | 3224376 | 3711942 | 43684.09 | [6 empty] | CS23W | 100%
500779 | NRSWA HOLDING LINE SP Third Party - Sewer Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-09 | 2019-09-09 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 340509.42 | 443609.58 | 44094.33 | 0.01 | -131708.81 | 0.01 | 696504.54 | 0 | 696504.54 | 2614273.27 | [6 empty] | CS23S | 100%
402624 | NRSWA HOLDING LINE SP Third Party - Sewer Diversions - 4026240000 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-03-22 | 2012-03-22 | 2012-07-10 | 2015-08-28 |  | Scottish Water Wide | 608000 | 103499.77 | 569.4 | 88.64 | 0 | 0 | 0.1 | 104157.91 | 0 | 712157.91 | 0 | [6 empty] | CM_WWI | 100%
500778 | NRSWA HOLDING LINE SP Third Party - Water Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-30 | 2019-09-13 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 462256 | 697623 | 25553.95 | -25181.93 | -201300.56 | 0 | 958950.46 | 0 | 958950.46 | 43684.09 | [6 empty] | CS23W | 100%
402623 | NRSWA HOLDING LINE SP Third Party - Water Diversions - 4026230000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-03-22 | 2012-03-22 | 2012-07-03 | 2015-08-28 |  | Scottish Water Wide | 917216.93 | 410399.61 | 584.4 | 0 | 5.54 | 0 | 0 | 410989.55 | 0 | 1328206.48 | 0 | [6 empty] | CM_WSI | 100%
503301 | NRSWA HOLDING LINE SP Third Party-SR18 Sewer Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-27 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-08-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 382454 | -109392.09 | 1896122.89 | 2169184.8 | 49404.34 | 2218589.14 | 2614273.27 | [6 empty] | CS23S | 100%
503300 | NRSWA HOLDING LINE SP Third Party-SR18 Water Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-27 | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2021-07-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 96715.44 | 1593605.92 | 1271458.3 | 2961779.66 | 20001.27 | 2981780.93 | 43684.09 | [6 empty] | CS23W | 100%
500781 | NRSWA Non Rechargeable C3 Sewer Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-25 | 2019-09-02 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 24229.99 | 74820.55 | 42974.83 | 0 | -77025 | 0 | 65000.37 | 0 | 65000.37 | 2614273.27 | [6 empty] | CS23S | 100%
503297 | NRSWA Non Rechargeable C3 Sewer Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-08-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 47909.01 | 49053.53 | -16284.04 | 80678.5 | 0 | 80678.5 | 3834201.03 | [6 empty] | CS23S | 100%
500780 | NRSWA Non Rechargeable C3 Water Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-09 | 2019-09-09 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 182121.86 | 13898.26 | 115590 | 2619.42 | 8284.5 | 0 | 322514.04 | 0 | 322514.04 | 43684.09 | [6 empty] | CS23W | 100%
503296 | NRSWA Non Rechargeable C3 Water Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-08-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 796620.51 | -592460.95 | 93101.51 | 297261.07 | 2738.92 | 299999.99 | 43684.09 | [6 empty] | CS23W | 100%
502416 | NRSWA PIF Construction Sewer B936 Freuchie Bridge Deck | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | Fife | 0 | 0 | 1549 | -248.76 | 0 | 0 | 0.16 | 1300.4 | 0 | 1300.4 | 2614273.27 | [6 empty] | CS23S | 100%
402997 | NRSWA Wastewater Holding Line 2013-2014 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-09-27 |  |  | 2015-09-01 |  | Scottish Water Wide | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWI | 100%
402996 | NRSWA Water Holding Line 2013-2014 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-09-27 |  |  | 2015-10-09 |  | Scottish Water Wide | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSI | 100%
501013 | NW19 - Burn Road Inverness | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2021-04-01 | 2021-04-01 | 2019-09-26 | 2019-09-26 | 2019-09-26 | Highland | 0 | 27500 | 34114.62 | 36956 | -98569.62 | 0 | 3277.28 | 3278.28 | 0 | 3278.28 | 204193.13 | [6 empty] | CS11 | 100%
504622 | N-W-20-130120 WI Co-ag Predictors St 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-26 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 14682.05 | 205317.95 | 220000 | 0 | 220000 | 0 | [6 empty] | CM_WSNI | 100%
500744 | NW2-N1 SR15 Avoch Flooding Project | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-01-29 | 2019-06-11 | 2019-06-11 | 2019-06-06 | 2019-06-06 | Highland | 0 | 88100 | 237348.61 | 73169.7 | 89227.97 | -484270.94 | -3574.34 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500088 | NW303 - Harbour Road Inverness | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS4 | 2019-07-18 | 2019-12-04 | 2019-12-04 | 2019-08-16 | 2019-12-04 | Highland | 0 | 23600 | 54205.05 | 37172.89 | 36022.06 | 84234.48 | 0.01 | 235234.49 | 0 | 235234.49 | 388163.48 | [6 empty] | CS11 | 100%
503787 | N-Water-NI-041119-Strathpeffer-Lower-DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 | 2020-03-31 | - | 0 | 0 | 0 | 0 | 0 | 0 | 1871.96 | 1871.96 | 0 | 1871.96 | 0 | [6 empty] | CM_WSNI | 100%
504182 | N-W-I_051219_Tullich WOA-Raw and Final Interface | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-12-10 |  |  |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2459.12 | 17540.88 | 20000 | 0 | 20000 | 0 | [6 empty] | WSI | 100%
504975 | N-W-I-01022020-Inverness_WOA-Modeling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 313.1 | 786.89 | 1099.99 | 0 | 1099.99 | 0 | [6 empty] | CM_M&G | 100%
505483 | N-W-I-020320-Storr Springs-Spring 11 Intake | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 6279.07 | 0 | 6279.07 | 0 | 6279.07 | 0 | [6 empty] | WSI | 100%
504096 | N-W-I-02122019-Port Ellen DMA - Imereval Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | GW1 |  | 2020-08-31 | 2020-09-18 | 2020-12-29 | 2021-01-28 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 19616.5 | 200383.49 | 219999.99 | 0 | 219999.99 | 0 | [6 empty] | WSI | 100%
504127 | N-W-I-031219-Daal_Terrace_WOA-Trial_Holes | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_M&G | 100%
505034 | N-W-I-050220-Conon_Bridge-WOA-TM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 215.89 | 3084.12 | 3300.01 | 0 | 3300.01 | 0 | [6 empty] | CM_WSI | 100%
505547 | N-W-I-05032020 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2020-04-30 |  | 2020-04-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 5326.84 | 23.16 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSI | 100%
504545 | N-W-I-070120-Loch_Calder_WOA-Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2884.52 | 15.48 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WSI | 100%
505623 | N-WI-100320 - Mallaig WTW Gate 50 Deliverables | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 8497.67 | 11802.34 | 20300.01 | 0 | 20300.01 | 0 | [6 empty] | CS16D_ID | 100%
505149 | N-W-I-110220-Tullich_WOA-TFillPoint | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-12 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4858.78 | -258.77 | 4600.01 | 0 | 4600.01 | 0 | [6 empty] | CM_WSI | 100%
504326 | N-W-I-121219-Bogbain_TM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-15 |  | 2020-01-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7117.03 | 82.97 | 7200 | 0 | 7200 | 0 | [6 empty] | CM_WSI | 100%
504637 | N-W-I-14012020- Geocrab WOA- Stockinish to Drinshader Iron /specials replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-28 |  | 2020-12-24 | 2020-12-24 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 263.99 | 75260.99 | 75524.98 | 0 | 75524.98 | 0 | [6 empty] | CM_WSNI | 100%
504648 | N-W-I-140120-Portree_Torvaig_WOA_Sconser_Colliemore_Embankment_Slip_Design | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-01-24 | 2020-08-13 | 2020-11-19 | 2020-12-17 | - | 0 | 0 | 0 | 0 | 0 | 1523.36 | 13476.63 | 14999.99 | 0 | 14999.99 | 0 | [6 empty] | CM_WSI | 100%
505730 | N-W-I-140320-Torra_WOA_Valve_Replace | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-06-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 753.15 | 9442.88 | 10196.03 | 0 | 10196.03 | 0 | [6 empty] | WSNI | 100%
503841 | N-W-I-151119- Oykel Bridge- Black Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-11-19 |  | 2020-02-13 | 2020-02-13 | - | 0 | 0 | 0 | 0 | 0 | 11533.1 | 0 | 11533.1 | 0 | 11533.1 | 0 | [6 empty] | CM_WSNI | 100%
504697 | N-W-I-16012020-UigWOA-Uig Glen MR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MSU |  | 2020-02-26 |  | 2020-11-06 | 2020-11-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1189.32 | -1158.68 | 30.64 | 0 | 30.64 | 0 | [6 empty] | CM_WSI | 100%
505731 | N-W-I-160320-Gigha_WOA-Meters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-08-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 813.06 | 10956.94 | 11770 | 0 | 11770 | 0 | [6 empty] | WSNI | 100%
504370 | N-W-I-171219-Drumbeg Intake- Refurb Rose | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 | 2020-03-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 3200 | 0 | 3200 | 0 | [6 empty] | CM_WSI | 100%
504414 | N-W-I-181219-Ullapool West DMA inlet meter- Cover | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 | 2020-03-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 2650 | 0 | 2650 | 0 | [6 empty] | CM_WSI | 100%
503868 | N-W-I-191119-Inverness_WOA-Surface Drain | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 10700 | 0 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_WSI | 100%
503881 | N-W-I-201119-Bowmore_DMA-Gartmain | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-12-16 | 2020-08-06 | 2020-11-12 | 2020-12-10 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3144.29 | 16855.72 | 20000.01 | 0 | 20000.01 | 0 | [6 empty] | CM_WSI | 100%
504749 | N-W-I-210120-Inverness_WOA-Tanker_FP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3210 | 0 | 3210 | 0 | 3210 | 0 | [6 empty] | CM_WSI | 100%
504747 | N-W-I-210120-Tiree_WOA-FindFix | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 22729.27 | -1329.27 | 21400 | 0 | 21400 | 0 | [6 empty] | CM_WSI | 100%
504772 | N-W-I-22012020-Barra WOA-Castlebay Square branch replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-03-02 |  | 2020-03-31 | 2020-05-08 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 5973.55 | -86.12 | 5887.43 | 0 | 5887.43 | 0 | [6 empty] | CM_WSI | 100%
505364 | N-W-I-220220-Inverness WOA-Trial_Holes | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 170.09 | 2429.91 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_M&G | 100%
505905 | N-W-I-240320-Barcaldine_Village_DMA-Modelling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2149.98 | 2149.98 | 0 | 2149.98 | 0 | [6 empty] | CM_M&G | 100%
504878 | N-W-I-27012020-Adabrock SR-Leaking inlet pipe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-12 |  | 2020-04-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 6228.13 | 3771.87 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WSNI | 100%
504872 | N-W-I-27012020-Stornoway County DMA- Main replacement Laxdale Lane | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-02-12 | 2020-08-26 | 2020-12-02 | 2021-01-05 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 43.06 | 0 | 43.06 | 0 | 43.06 | 0 | [6 empty] | CM_WSI | 100%
503992 | N-WI-NI-261119 - Backies WTW - Membrane Valve Transmitter & Switches Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-13 | 2020-07-20 | 2020-09-25 | 2020-09-25 | Highland | 0 | 0 | 0 | 0 | 0 | 5294.08 | 69705.92 | 75000 | 0 | 75000 | 0 | [6 empty] | CM_WSNI | 100%
505779 | N-W-I-Tobermory_WOA-Gullen_Dhu_Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-20 |  | 2020-05-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 71.7 | 1024.35 | 1096.05 | 0 | 1096.05 | 0 | [6 empty] | WSNI | 100%
506030 | N-W-N-010420-Diabeg_WTW-Cl_Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WSNI | 100%
506024 | N-W-N-010420-Lednagullin_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WSNI | 100%
506027 | N-W-N-010420-Thusater_DSR-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1610 | 1610 | 0 | 1610 | 0 | [6 empty] | CM_WSNI | 100%
506070 | N-W-N-020420-Tullich_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1720 | 1720 | 0 | 1720 | 0 | [6 empty] | CM_WSNI | 100%
504617 | N-W-NI 130120-Croft_Hill_CWT-Panels | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WSNI | 100%
503903 | N-W-NI- 211119-Kinlochbervie_WTW-Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WSNI | 100%
504976 | N-W-NI-01022020-Ardtoe_PS-Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1298.13 | 201.88 | 1500.01 | 0 | 1500.01 | 0 | [6 empty] | CM_WSNI | 100%
504978 | N-W-NI-01022020-Kilmaluag_WTW-Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1121.96 | 16028.05 | 17150.01 | 0 | 17150.01 | 0 | [6 empty] | CM_WSNI | 100%
504980 | N-W-NI-01022020-Londornoch_WTW-Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2063.67 | 4186.32 | 6249.99 | 0 | 6249.99 | 0 | [6 empty] | CM_WSNI | 100%
504979 | N-W-NI-01022020-Peddieston_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4108.57 | 91.43 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WSNI | 100%
504977 | N-W-NI-01022020-Portree_Torvaig_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 137.38 | 1962.61 | 2099.99 | 0 | 2099.99 | 0 | [6 empty] | CM_WSNI | 100%
504981 | N-W-NI-01022020-Sanna_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2250.47 | 49.54 | 2300.01 | 0 | 2300.01 | 0 | [6 empty] | CM_WSNI | 100%
505769 | N-W-NI-010320-Bunessan_WTW-Diesel_Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-20 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4278.4 | 0 | 4278.4 | 0 | 4278.4 | 0 | [6 empty] | WSNI | 100%
505473 | N-W-NI-010320-Bunessan_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2179.37 | 120.61 | 2299.98 | 0 | 2299.98 | 0 | [6 empty] | CM_WSNI | 100%
505475 | N-W-NI-010320-Dunnet_Head_Brough_TWP-Bldng_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 71.96 | 1028.02 | 1099.98 | 0 | 1099.98 | 0 | [6 empty] | CM_WSNI | 100%
505474 | N-W-NI-010320-Inverness_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.97 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WSNI | 100%
505478 | N-W-NI-020320-Applecross WTW-Membrane Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 | 2020-05-29 | 2020-09-04 | 2020-10-02 | Highland | 0 | 0 | 0 | 0 | 0 | 1960.13 | 0 | 1960.13 | 0 | 1960.13 | 0 | [6 empty] | CM_WSNI | 100%
505484 | N-W-NI-020320-Bracadale_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 91.59 | 2608.41 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
505477 | N-W-NI-020320-Campbeltown_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-02 |  | 2020-06-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 157.59 | 2251.33 | 2408.92 | 0 | 2408.92 | 0 | [6 empty] | WSNI | 100%
505487 | N-W-NI-020320-Kyle_of_Lochalsh_WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 117.76 | 1682.24 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WSNI | 100%
505486 | N-W-NI-020320-Raasay_CWT-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4438.83 | 271.17 | 4710 | 0 | 4710 | 0 | [6 empty] | CM_WSNI | 100%
505479 | N-W-NI-020320-Stoneybridge_WTW-Power_Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1533.14 | 76.84 | 1609.98 | 0 | 1609.98 | 0 | [6 empty] | CM_WSNI | 100%
504098 | N-W-NI-021219-Campbeltown_WTW-Pump_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
504093 | N-W-NI-021219-Carradale_WTW-Media_Maniofold | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 12900 | 0 | 12900 | 0 | 12900 | 0 | [6 empty] | CM_WSNI | 100%
504086 | N-W-NI-021219-Inveraray-Furnace Generator Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2019-12-04 |  | 2020-04-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 341.42 | -43.06 | 298.36 | 0 | 298.36 | 0 | [6 empty] | WSNI | 100%
504103 | N-W-NI-021219-Stoneybridge_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WSNI | 100%
504987 | N-W-NI-03022020-Glenconvinth_WTW-GeneratorSwitch | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5518.46 | 81.52 | 5599.98 | 0 | 5599.98 | 0 | [6 empty] | CM_WSNI | 100%
505540 | N-W-NI-03032020-Uist Dynasand WTW-chlorine control | Q&S4 | Sustaining existing high service for customers | Water non infrastructure |  |  | General |  | SWMD | Water non infrastructure | MS2 |  | 2020-03-09 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 350 | 0 | 350 | 0 | [6 empty] | SR15_CMA_WSNI | 100%
505514 | N-W-NI-030320-Port_Charlotte_WTW_Clarifier_Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-04 |  |  |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 102.55 | 1567.55 | 1670.1 | 0 | 1670.1 | 0 | [6 empty] | WSNI | 100%
504117 | N-W-NI-031219-Staffin_WTW_Valve_Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WSNI | 100%
504119 | N-W-NI-031219-Stoneybridge_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WSNI | 100%
505027 | N-W-NI-050220-Inverness_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 392.52 | 5607.47 | 5999.99 | 0 | 5999.99 | 0 | [6 empty] | CM_WSNI | 100%
505047 | N-W-NI-050220-Tobermory_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5117.66 | 32.34 | 5150 | 0 | 5150 | 0 | [6 empty] | CM_WSNI | 100%
505561 | N-W-NI-050320 - Londornoch WTW Thickened Sludge Pump No 2 Torque Limiter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2020-04-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2489.42 | 5834.58 | 8324 | 0 | 8324 | 0 | [6 empty] | CM_WSNI | 100%
505558 | N-W-NI-050320-Stoneybridge WOA-Garynamonie SR sample tap | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW1 |  | 2020-08-17 | 2020-09-04 | 2020-12-11 | 2021-01-14 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 700 | 10000 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_WSNI | 100%
504171 | N-W-NI-051219- Cladich WTW-Chemical Waste | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-10 |  |  |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2121.76 | 12878.24 | 15000 | 0 | 15000 | 0 | [6 empty] | WSNI | 100%
504533 | N-W-NI-060120-Applercross_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 3800 | 0 | 3800 | 0 | [6 empty] | CM_WSNI | 100%
505061 | N-W-NI-060220-Ardrishaig_WTW-DAFValve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1593.18 | 26.81 | 1619.99 | 0 | 1619.99 | 0 | [6 empty] | CM_WSNI | 100%
505584 | N-W-NI-060320-Campbeltown_WTW_Storm_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2020-04-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 172.14 | 2459.19 | 2631.33 | 0 | 2631.33 | 0 | [6 empty] | WSNI | 100%
505578 | N-W-NI-060320-Cladish_WTW-Storm_Damage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-06 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2800 | -2800 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 100%
505567 | N-W-NI-060320-Gigha_WTW-DOC_repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-06 |  | 2020-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 87.22 | 1246 | 1333.22 | 0 | 1333.22 | 0 | [6 empty] | WSNI | 100%
504225 | N-W-NI-061219-Broadford_WTW-LCT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WSNI | 100%
504216 | N-W-NI-061219-Ullapool County SR- Land Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-06 |  |  |  | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WSNI | 100%
504199 | N-W-NI-061219-West Coast Sites-HMI Critical Spare | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-30 | 2020-03-30 | Highland | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 7500 | 0 | [6 empty] | CM_WSNI | 100%
504556 | N-W-NI-070120-Inveraray_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3840.37 | 59.63 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WSNI | 100%
504554 | N-W-NI-070120-Portnahaven_DSR-Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 176.64 | 2523.36 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
505071 | N-W-NI-070220-Ardrishaig_WTW-WQMonitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-07 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 12601.51 | -1251.52 | 11349.99 | 0 | 11349.99 | 0 | [6 empty] | CM_WSNI | 100%
505068 | N-W-NI-070220-Ardrishaig-WTW-RunToWaste | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-17 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1929.64 | 10070.35 | 11999.99 | 0 | 11999.99 | 0 | [6 empty] | WSNI | 100%
505085 | N-W-NI-070220-Ludaig_TWP-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-10 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1379.61 | 20.39 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
505086 | N-W-NI-070220-Tiree WTW-filter change out | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-05-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1000 | 46903.06 | 47903.06 | 0 | 47903.06 | 0 | [6 empty] | CM_WSNI | 100%
504560 | N-W-NI-080120-Ullapool_Tank_DSR-Technocovers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
504590 | N-W-NI-090120-Ullapool WTW- Soda Dosing Loading Platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-15 | 2020-08-06 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 513.77 | 14486.23 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_M&G | 100%
505089 | N-W-NI-090220-Alligin_WTW-BldngCladding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-10 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 11882.05 | 117.95 | 12000 | 0 | 12000 | 0 | [6 empty] | CM_WSNI | 100%
505090 | N-W-NI-090220-Badcaul_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-10 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1661.98 | 158.01 | 1819.99 | 0 | 1819.99 | 0 | [6 empty] | CM_WSNI | 100%
505088 | N-W-NI-090220-Meavaig_WTW-FlowMeter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-10 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 865.05 | 884.95 | 1750 | 0 | 1750 | 0 | [6 empty] | CM_WSNI | 100%
505087 | N-W-NI-090220-Ness_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-10 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 877.17 | 11872.82 | 12749.99 | 0 | 12749.99 | 0 | [6 empty] | CM_WSNI | 100%
505602 | N-W-NI-090320 - Bonar Bridge WTW Replacement Raw Water Pump Motor No.1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-03-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1153.86 | 16483.7 | 17637.56 | 0 | 17637.56 | 0 | [6 empty] | CM_WSNI | 100%
505605 | N-W-NI-09032020-Ness WTW-Dynasand filter door replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-06-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 115.79 | 1654.21 | 1770 | 0 | 1770 | 0 | [6 empty] | CM_WSNI | 100%
505611 | N-W-NI-09032020-Rhenigadale WTW-Faulty turb monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-04-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 89.56 | 1279.44 | 1369 | 0 | 1369 | 0 | [6 empty] | CM_WSNI | 100%
505604 | N-W-NI-090320-Tarbert_WTW-BPT_covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-04-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4082.05 | 0 | 4082.05 | 0 | 4082.05 | 0 | [6 empty] | WSNI | 100%
505597 | N-W-NI-090320-Ullapool WTW- Soda Storage Shed Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 9200 | 0 | 9200 | 0 | [6 empty] | CM_WSNI | 100%
504241 | N-W-NI-091219-Carbost_WTW-Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
504260 | N-W-NI-091219-Ft_Augustus_WTW-Sand_Filter_1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-10 |  | 2020-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 224135.25 | 0 | 224135.25 | 0 | 224135.25 | 0 | [6 empty] | CM_WSNI | 100%
504255 | N-W-NI-091219-Loch_Calder_WTW-Motor_Gearbox | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5906.59 | 93.41 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WSI | 100%
505113 | N-W-NI-100220- Londornoch WTW - DAF Gearbox Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-02-11 |  | 2020-09-25 | 2020-09-25 | Highland | 0 | 0 | 0 | 0 | 0 | 6019.44 | 33980.56 | 40000 | 0 | 40000 | 0 | [6 empty] | CM_WSNI | 100%
505099 | N-W-NI-100220-Craighouse_WTW-Intake-repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-05-30 |  | 2020-05-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1000 | 11000 | 12000 | 0 | 12000 | 0 | [6 empty] | WSNI | 100%
505636 | N-W-NI-100320 Loch Duntelchaig RWI Cattle Grid replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 525 | 7049.35 | 7574.35 | 0 | 7574.35 | 0 | [6 empty] | CM_WSNI | 100%
505644 | n-w-ni-10032020-Tiree WTW-Turbidity ICE PIC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-04-10 | 2020-04-10 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 89.04 | 1271.96 | 1361 | 0 | 1361 | 0 | [6 empty] | CM_WSNI | 100%
505618 | N-W-NI-100320-Luing_DSR-Chlorine_Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2020-05-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 191.88 | 2741.2 | 2933.08 | 0 | 2933.08 | 0 | [6 empty] | WSNI | 100%
504270 | N-W-NI-101219-Inveraray_WTW-pH_Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1554.36 | 95.64 | 1650 | 0 | 1650 | 0 | [6 empty] | CM_WSNI | 100%
504287 | N-W-NI-101219-Ness_WTW-Monitor_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
504272 | N-W-NI-101219-Port Charlotte WTW - Colour Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-18 |  |  |  | - | 0 | 0 | 0 | 0 | 0 | 2401.27 | 12598.72 | 14999.99 | 0 | 14999.99 | 0 | [6 empty] | WSNI | 100%
505152 | N-W-NI-110220-Ardrishaig_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-12 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 6932.49 | 167.52 | 7100.01 | 0 | 7100.01 | 0 | [6 empty] | CM_WSNI | 100%
505151 | N-W-NI-110220-Gigha_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-12 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2044.35 | 315.65 | 2360 | 0 | 2360 | 0 | [6 empty] | CM_WSNI | 100%
505150 | N-W-NI-110220-Meavaig_WTW- Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-12 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2428.94 | -28.95 | 2399.99 | 0 | 2399.99 | 0 | [6 empty] | CM_WSNI | 100%
503793 | N-W-NI-111119-Allt Airdeasaidh(Badcaul WTW)-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW1 |  | 2020-08-31 | 2020-09-18 | 2020-12-29 | 2021-01-28 | - | 0 | 0 | 0 | 0 | 0 | 7155 | 142845 | 150000 | 0 | 150000 | 0 | [6 empty] | CM_WSI | 100%
504288 | N-W-NI-111219-Drumbeg Intake- Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 | 2020-03-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1928.48 | 1928.48 | 0 | 1928.48 | 0 | [6 empty] | CM_WSI | 100%
504295 | N-W-NI-111219-Inveraray_WTW-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 0 | 10500 | 0 | [6 empty] | CM_WSNI | 100%
504293 | N-W-NI-111219-Kilchoan_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 2300 | 0 | [6 empty] | CM_WSNI | 100%
504289 | N-W-NI-111219-Kilchrnnan_Taynuilt_WTW-Floor_Plates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3844.17 | 55.83 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WSNI | 100%
504299 | N-W-NI-111219-Newmore_WTW-Sludge_Thickener | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5636.49 | 63.51 | 5700 | 0 | 5700 | 0 | [6 empty] | CM_WSNI | 100%
503799 | N-W-NI-111219-Sheildaig WTW- HMI Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-13 |  | 2020-03-31 | 2020-03-31 | - | 0 | 0 | 0 | 0 | 0 | 7210.85 | -2530.95 | 4679.9 | 0 | 4679.9 | 0 | [6 empty] | CM_WSNI | 100%
504305 | N-W-NI-111219-Stornoway_WTW-Guttering | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1405.13 | 94.87 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WSNI | 100%
504304 | N-W-NI-111219-Stornoway_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
504645 | N-W-NI-120120-Melvich_Strathy_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 4300 | 0 | 4300 | 0 | [6 empty] | CM_WSNI | 100%
504614 | N-W-NI-120120-Tarbert_WTW-Sludge_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-12 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WSNI | 100%
504615 | N-W-NI-120120-Tarbert_WTW-Soda_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1723.91 | 76.09 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WSNI | 100%
505215 | N-W-NI-12022020-Tarbert (WI)WTW-CWT valve house flooring | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS2 |  | 2020-02-28 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1243.77 | 0 | 1243.77 | 0 | 1243.77 | 0 | [6 empty] | CM_M&G | 100%
505162 | N-W-NI-120220-Inveraray_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-12 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1492.25 | 7.76 | 1500.01 | 0 | 1500.01 | 0 | [6 empty] | CM_WSNI | 100%
505170 | N-W-NI-120220-Kyle_RWP-VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1628.72 | 371.29 | 2000.01 | 0 | 2000.01 | 0 | [6 empty] | CM_WSNI | 100%
505686 | N-W-NI-120320-Campbeltown_WTW-Fire_Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-12 |  | 2020-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 244.3 | 3490.01 | 3734.31 | 0 | 3734.31 | 0 | [6 empty] | WSNI | 100%
503909 | N-W-NI-121119-Tora_WTW-Sludge_Press | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-22 |  | 2020-03-31 | 2020-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 10969.89 | 0 | 10969.89 | 0 | 10969.89 | 0 | [6 empty] | CM_WSNI | 100%
503804 | N-W-NI-121119-Ullapool County DSR- Tank Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 8541.71 | -2925.83 | 5615.88 | 0 | 5615.88 | 0 | [6 empty] | CM_WSNI | 100%
504335 | N-W-NI-121219-Earlish_Uig_WTW-Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WSNI | 100%
504312 | N-W-NI-121219-Inverness_WOA-Replacement_Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 37500 | 0 | [6 empty] | CM_WSI | 100%
504319 | N-W-NI-121219-Stornoway_WTW-Office | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
504332 | N-W-NI-121219-Stornoway_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2489.81 | 10.19 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WSNI | 100%
504623 | N-W-NI-13012020-Loch_Nell_RWPS-Bursting_Disks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 7973.82 | 2026.18 | 10000 | 0 | 10000 | 0 | [6 empty] | WSNI | 100%
504618 | N-W-NI-13012020-Torra_WTW-Intake_Raw_Main_Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-05-04 |  | 2020-05-04 |  | - | 0 | 0 | 0 | 0 | 0 | 16472.35 | 10210.85 | 26683.2 | 0 | 26683.2 | 0 | [6 empty] | CM_WSNI | 100%
505175 | N-W-NI-130220-Garyvard_TWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 353.27 | 5046.74 | 5400.01 | 0 | 5400.01 | 0 | [6 empty] | CM_WSNI | 100%
505181 | N-W-NI-130220-Londornoch_WTW-SiloBin | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 228.97 | 3271.05 | 3500.02 | 0 | 3500.02 | 0 | [6 empty] | CM_WSNI | 100%
505186 | N-W-NI-130220-North_Lochs_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1933.86 | 66.15 | 2000.01 | 0 | 2000.01 | 0 | [6 empty] | CM_WSNI | 100%
505174 | N-W-NI-130220-Strollamus_DSR-AccessRoad | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 484.11 | 6915.91 | 7400.02 | 0 | 7400.02 | 0 | [6 empty] | CM_WSNI | 100%
505706 | N-W-NI-13032020-Aultbea Intake- Screen Chamber | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-30 | 2020-09-04 | 2020-12-11 | 2021-01-14 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WSI | 100%
505725 | N-W-NI-13032020-Loch HatravatRWI-RTU replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-04-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1015.81 | 14511.51 | 15527.32 | 0 | 15527.32 | 0 | [6 empty] | CM_WSI | 100%
505727 | N-W-NI-13032020-Loch Mor-A-Stairr-RTU replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-04-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1015.79 | 14511.21 | 15527 | 0 | 15527 | 0 | [6 empty] | CM_WSI | 100%
505711 | N-W-NI-130320-Torra_WTW-RGF_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3672.24 | 49827.76 | 53500 | 0 | 53500 | 0 | [6 empty] | WSNI | 100%
504341 | N-W-NI-131219-North_Lochs_WTW-Covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1366.59 | 33.41 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
504647 | N-W-NI-140120-Loch_Calder_WTW-PLC _ Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1310 | 0 | 1310 | 0 | 1310 | 0 | [6 empty] | CM_WSNI | 100%
505192 | N-W-NI-140220-Arnol_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-17 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2003.78 | 96.21 | 2099.99 | 0 | 2099.99 | 0 | [6 empty] | CM_WSNI | 100%
505195 | N-W-NI-140220-Diabeg_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-17 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 183.18 | 2616.83 | 2800.01 | 0 | 2800.01 | 0 | [6 empty] | CM_WSNI | 100%
505729 | N-W-NI-140320-Campbeltown_WTW-Sludge_Bld_Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-04-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 172.14 | 2459.19 | 2631.33 | 0 | 2631.33 | 0 | [6 empty] | WSNI | 100%
504654 | N-W-NI-15012020-Brnbecula Aird Low RWPS-Building ventilation for Generator | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS2 |  | 2020-02-03 |  | 2020-09-10 | 2020-09-11 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1182.94 | 9517.06 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_M&G | 100%
504670 | N-W-NI-15012020-Uig WTW-Leaking roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-05 |  | 2020-12-24 | 2020-12-24 | - | 0 | 0 | 0 | 0 | 0 | 415.3 | 42529.89 | 42945.19 | 0 | 42945.19 | 0 | [6 empty] | CM_WSNI | 100%
503839 | N-W-NI-151119-Ullapool WTW- Flow Switch Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-19 |  | 2019-12-15 | 2020-03-29 | - | 0 | 0 | 0 | 0 | 0 | 1520.7 | -396 | 1124.7 | 0 | 1124.7 | 0 | [6 empty] | CM_WSNI | 100%
504945 | N-W-NI-16012020-N Lochs WTW-Leaking roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-10-02 | 2020-10-02 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 731.79 | 5688.21 | 6420 | 0 | 6420 | 0 | [6 empty] | CM_WSNI | 100%
504685 | N-W-NI-160120-Ardfern_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3516.91 | 83.09 | 3600 | 0 | 3600 | 0 | [6 empty] | CM_WSNI | 100%
504679 | N-W-NI-160120-Balnain_DSR-Fuel_Cell | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 9444.71 | 5.29 | 9450 | 0 | 9450 | 0 | [6 empty] | CM_WSNI | 100%
504695 | N-W-NI-160120-Glenconvinth_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-19 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 2300 | 0 | [6 empty] | CM_WSNI | 100%
504696 | N-W-NI-160120-Tarbert_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-19 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1802.98 | -82.98 | 1720 | 0 | 1720 | 0 | [6 empty] | CM_WSNI | 100%
504694 | N-W-NI-160120-Teangue_WTW-Filtomat | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-19 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 7500 | 0 | [6 empty] | CM_WSNI | 100%
504688 | N-W-NI-160120-Tobermory_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-19 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1100.76 | 99.24 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
505742 | N-W-NI-160320-Ardrishaig_WTW-DOMS_Store | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2020-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 11848.5 | -24.99 | 11823.51 | 0 | 11823.51 | 0 | [6 empty] | WSNI | 100%
505733 | N-W-NI-160320-Dalmally_WTW-Access_rd_repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-20 |  | 2020-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 773.5 | 11050.01 | 11823.51 | 0 | 11823.51 | 0 | [6 empty] | WSNI | 100%
504353 | N-W-NI-161219-Geocrab_WTW-Filter_Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WSNI | 100%
504364 | N-W-NI-161219-Kyle and Acharacle Chemical Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-17 | 2020-08-06 | 2020-11-17 | 2020-12-15 | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 48000 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WSNI | 100%
504717 | N-W-NI-170120-Inverness_WTW-Circuit_Breaker | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-19 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5350 | 0 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
505233 | N-W-NI-170220-Ardfern_WTW-PumpNr1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-17 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1029.08 | 70.91 | 1099.99 | 0 | 1099.99 | 0 | [6 empty] | CM_WSNI | 100%
505234 | N-W-NI-170220-Campbeltown_WTW-Filter_Depth_Boards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-17 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 319.46 | 2180.54 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WSNI | 100%
505247 | N-W-NI-170220-Carbost_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1534.49 | 215.51 | 1750 | 0 | 1750 | 0 | [6 empty] | CM_WSNI | 100%
505246 | N-W-NI-170220-Inveraray_WTW-Gem80_Spares | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-17 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 176.64 | 2523.36 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
505249 | N-W-NI-170220-Port_Charlotte _WTW-RTU | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 189.72 | 2710.28 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WSNI | 100%
505774 | N-W-NI-170320-Ballygrant_WTW-Generator Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-20 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4315.32 | 0 | 4315.32 | 0 | 4315.32 | 0 | [6 empty] | WSNI | 100%
505785 | N-W-NI-170320-Herbusta TWP- Wiring Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1699.98 | 1699.98 | 0 | 1699.98 | 0 | [6 empty] | CM_WSNI | 100%
505766 | N-W-NI-170320-Taynuilt_WTW-H&S_Improv | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-20 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 8489.03 | 0 | 8489.03 | 0 | 8489.03 | 0 | [6 empty] | WSNI | 100%
504382 | N-W-NI-171219-Bonar_Bridge_WTW-Filtomats | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-17 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 9000 | 0 | [6 empty] | CM_WSNI | 100%
504384 | N-W-NI-171219-Tongue_DSR-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-17 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WSNI | 100%
504390 | N-W-NI-171219-Tongue_TWP-Flow_Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3210 | 0 | 3210 | 0 | 3210 | 0 | [6 empty] | CM_WSNI | 100%
505266 | N-W-NI-180220-Achnahillin_DSR-Access_Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 170.09 | 2429.91 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WSNI | 100%
505261 | N-W-NI-180220-Altnaharra_WTW-Lights | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 166.82 | 2383.18 | 2550 | 0 | 2550 | 0 | [6 empty] | CM_WSNI | 100%
505264 | N-W-NI-180220-Kinlochbervie_WTW-PLC-HMI_Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 157.01 | 2242.98 | 2399.99 | 0 | 2399.99 | 0 | [6 empty] | CM_WSNI | 100%
505256 | N-W-NI-180220-Lochcarron_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 150.47 | 1149.53 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WSNI | 100%
505797 | N-W-NI-180320-Campbeltown_WTW-RGF_C_Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-20 |  | 2020-04-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 523.36 | 7476.64 | 8000 | 0 | 8000 | 0 | [6 empty] | WSNI | 100%
503844 | N-W-NI-181119-Torra_WTW-Poly_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1770.46 | -170.46 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WSNI | 100%
504419 | N-W-NI-181219-Loch_Calder_WTW-Covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WSNI | 100%
504395 | N-W-NI-181219-Torra_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3933.33 | 66.67 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WSNI | 100%
503876 | N-W-NI-191119-Drumbeg WTW- Recycle Pump replacement parts | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-21 |  | 2020-03-30 | 2020-03-30 | - | 0 | 0 | 0 | 0 | 0 | 1557.5 | -432.8 | 1124.7 | 0 | 1124.7 | 0 | [6 empty] | CM_WSNI | 100%
504424 | N-W-NI-191219-Stoneybridge_WTW-AlumMonitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 13258.29 | 41.71 | 13300 | 0 | 13300 | 0 | [6 empty] | CM_WSNI | 100%
504422 | N-W-NI-191219-WI Co-ag Predictors St 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-28 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1009.16 | 218990.85 | 220000.01 | 0 | 220000.01 | 0 | [6 empty] | CM_WSNI | 100%
503879 | N-W-NI-201119-Acharacle_WTW-Level_Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1627.91 | 72.09 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WSNI | 100%
504745 | N-W-NI-210120-Dalmally_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1383.09 | 16.91 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
504750 | N-W-NI-210120-Durness Keoldale WTW - Filter water holding chamber repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-08-31 |  | 2020-10-15 | 2020-07-17 | Highland | 0 | 0 | 0 | 0 | 0 | 3000 | 68443.97 | 71443.97 | 0 | 71443.97 | 0 | [6 empty] | CM_WSNI | 100%
504759 | N-W-NI-210120-Kinlochbervie; Bonar Bridge; Scourie WTW- Media replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-28 | 2020-02-02 | 2020-09-17 | 2020-10-15 | Highland | 0 | 0 | 0 | 0 | 0 | 14000 | 26000 | 40000 | 0 | 40000 | 0 | [6 empty] | CM_WSNI | 100%
504762 | N-W-NI-210120-Stornoway _WTW-FilterSurvey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 4100 | 0 | 4100 | 0 | [6 empty] | CM_WSNI | 100%
504753 | N-W-NI-210120-Stornoway_WTW- Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1624.94 | 25.06 | 1650 | 0 | 1650 | 0 | [6 empty] | CM_WSNI | 100%
505362 | N-W-NI-210220-Londornoch_WTW-RCD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 91.59 | 1308.41 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
505343 | N-W-NI-210220-Tiree WTW borehole 1 to 3 cleaning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-03 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1000 | 95300 | 96300 | 0 | 96300 | 0 | [6 empty] | CM_WSI | 100%
505357 | N-W-NI-210220-Tobermory-Turb_Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1127.62 | 72.38 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
503905 | N-W-NI-211119-Barcaldine_DSR-Land_Inv | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5350 | 0 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
503913 | N-W-NI-211119-Broadford_WTW-Amiad_Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-22 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WSNI | 100%
503899 | N-W-NI-211119-Inveraray_WTW-Heating | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WSNI | 100%
503917 | N-W-NI-211119-Staffin_WTW-Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-22 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 16000 | 0 | 16000 | 0 | [6 empty] | CM_WSNI | 100%
505367 | N-W-NI-220220-Appin_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1556.87 | -256.87 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WSNI | 100%
505363 | N-W-NI-220220-Broadford_WTW-Transmitter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2052.16 | 347.83 | 2399.99 | 0 | 2399.99 | 0 | [6 empty] | CM_WSNI | 100%
505369 | N-W-NI-220220-Dalmally_WTW-ValveActuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 352.17 | 2647.81 | 2999.98 | 0 | 2999.98 | 0 | [6 empty] | CM_WSNI | 100%
505368 | N-W-NI-220220-Inveraray_WTW-DAF | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1292.45 | -92.45 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
505365 | N-W-NI-220220-Loch_Calder_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3341.73 | 158.29 | 3500.02 | 0 | 3500.02 | 0 | [6 empty] | CM_WSNI | 100%
505366 | N-W-NI-220220-Teangue_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.95 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WSNI | 100%
503940 | N-W-NI-221119-Bonar_Bridge_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WSNI | 100%
504809 | N-W-NI-230120 Loch Calder WTW - Total Treated Water Chlorine Monitor Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-24 |  |  |  | Highland | 0 | 0 | 0 | 0 | 0 | 6204.19 | 0 | 6204.19 | 0 | 6204.19 | 0 | [6 empty] | CM_WSNI | 100%
504472 | N-W-NI-231219- Ullapool WTW- H&S Loading Platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-07 |  |  |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 0 | 13000 | 0 | [6 empty] | CM_M&G | 100%
504831 | N-W-NI-240120- Loch Calder - Stemster TWP Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-28 | 2020-07-16 | 2020-10-22 | 2020-11-19 | Highland | 0 | 0 | 0 | 0 | 0 | 6048.69 | 143951.31 | 150000 | 0 | 150000 | 0 | [6 empty] | CM_WSNI | 100%
504827 | N-W-NI-24012020-Tarbert WTW-Membranes. Replace pipework with stainless steel. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2020-08-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 11750.03 | 9649.97 | 21400 | 0 | 21400 | 0 | [6 empty] | CM_WSNI | 100%
504833 | N-W-NI-240120-Backies_WTW-Access_Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WSNI | 100%
504822 | N-W-NI-240120-Benbecula_WOA-Marker _Posts | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 4059.02 | 40.98 | 4100 | 0 | 4100 | 0 | [6 empty] | CM_WSI | 100%
504820 | N-W-NI-240120-Stornoway _WTW-Cl_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 2700 | 4150 | 6850 | 0 | 6850 | 0 | [6 empty] | CM_WSNI | 100%
504824 | N-W-NI-240120-Tarbert_Arg_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1117.85 | 82.15 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
503944 | N-W-NI-241119-Durness_Sangomore_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7250 | 0 | 7250 | 0 | 7250 | 0 | [6 empty] | CM_WSNI | 100%
503943 | N-W-NI-241119-Londornoch_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4281.04 | -1081.04 | 3200 | 0 | 3200 | 0 | [6 empty] | CM_WSNI | 100%
503942 | N-W-NI-24119-GighaWTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5185.56 | 14.44 | 5200 | 0 | 5200 | 0 | [6 empty] | CM_WSNI | 100%
505413 | N-W-NI-250220-Assynt_CWT-Bldng_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 366.36 | 5233.62 | 5599.98 | 0 | 5599.98 | 0 | [6 empty] | CM_WSNI | 100%
505411 | N-W-NI-250220-Durness_Keodale_WTW-Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 425.89 | 6084.12 | 6510.01 | 0 | 6510.01 | 0 | [6 empty] | CM_WSNI | 100%
505925 | N-W-NI-250320-Aird_Low_RWPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 490.65 | 7009.35 | 7500 | 0 | 7500 | 0 | [6 empty] | CM_WSNI | 100%
505932 | N-W-NI-250320-Campbeltown_WTW-Chlorinator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 435.05 | 6214.93 | 6649.98 | 0 | 6649.98 | 0 | [6 empty] | CM_WSNI | 100%
505937 | N-W-NI-250320-Stoneybridge_WTW-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 6137.81 | 7962.19 | 14100 | 0 | 14100 | 0 | [6 empty] | CM_WSNI | 100%
505924 | N-W-NI-250320-Tobermory_WTW-DAF_Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 140.65 | 2009.33 | 2149.98 | 0 | 2149.98 | 0 | [6 empty] | CM_WSNI | 100%
505934 | N-W-NI-250320-Torra_WTW-Power_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 441.59 | 6308.41 | 6750 | 0 | 6750 | 0 | [6 empty] | CM_WSNI | 100%
505939 | N-W-NI-250320-Uig_WTW-Valves | Q&S4 | Protecting and enhancing the environment | WFD |  |  | General |  | SWD | WFD | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1574.2 | 425.78 | 1999.98 | 0 | 1999.98 | 0 | [6 empty] | SR15_ENV_WFD | 100%
503974 | N-W-NI-251119-Benbecula_WTW-Radio_Link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 999.82 | 0.18 | 1000 | 0 | 1000 | 0 | [6 empty] | CM_WSNI | 100%
503953 | N-W-NI-251119-Tiree_WTW-Wellfare_Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 6107.37 | 2092.63 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WSNI | 100%
505423 | N-W-NI-260220-Inveraray_WTW-pH_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 232.24 | 3317.75 | 3549.99 | 0 | 3549.99 | 0 | [6 empty] | CM_WSNI | 100%
505959 | N-W-NI-260320-Assynt_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 183.18 | 2616.84 | 2800.02 | 0 | 2800.02 | 0 | [6 empty] | CM_WSNI | 100%
505953 | N-W-NI-260320-Inverness_WTW-Microstrainer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 539.72 | 7710.28 | 8250 | 0 | 8250 | 0 | [6 empty] | CM_WSNI | 100%
505951 | N-W-NI-260320-Inverness_WTW-Security_Gate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 91.59 | 1308.39 | 1399.98 | 0 | 1399.98 | 0 | [6 empty] | CM_WSNI | 100%
504064 | N-W-NI-261119-Loch_Duntelchaig_NRPH-Flooring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 5200 | 0 | [6 empty] | CM_WSNI | 100%
504877 | N-W-NI-270120-Stornoway_WTW-Container | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-28 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 5300 | 0 | 5300 | 0 | 5300 | 0 | [6 empty] | CM_WSNI | 100%
505449 | N-W-NI-270220-Inverness_WTW-Telemetry_Spares | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 22000 | 0 | [6 empty] | CM_WSNI | 100%
504893 | N-W-NI-280120-Garyvard_TWP-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1219.47 | -19.47 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
504888 | N-W-NI-280120-Lemreway_SR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 5064.66 | 35.34 | 5100 | 0 | 5100 | 0 | [6 empty] | CM_WSNI | 100%
505462 | N-W-NI-28022020-Loch Airigh Na Lic- Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-06 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 350 | 5000 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
504077 | N-W-NI-281119-Loch_Calder-RWI-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5418.53 | 81.47 | 5500 | 0 | 5500 | 0 | [6 empty] | CM_WSNI | 100%
504903 | N-W-NI-290120-North_Lochs_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 4739.16 | -1589.16 | 3150 | 0 | 3150 | 0 | [6 empty] | CM_WSNI | 100%
504518 | N-W-NI-291219-Craggie_TWP-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1548.33 | 61.67 | 1610 | 0 | 1610 | 0 | [6 empty] | CM_WSNI | 100%
504515 | N-W-NI-291219-Glenelg_WTW-FM_Transmitter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WSNI | 100%
504513 | N-W-NI-291219-Glenuig_WTW-Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
504519 | N-W-NI-291219-Grantown_DSR-Power_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
504517 | N-W-NI-291219-Kyle_WTW-Pressure_Guages | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WSNI | 100%
504514 | N-W-NI-291219-Raasay_WTW-Turb_Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 4100 | 0 | 4100 | 0 | [6 empty] | CM_WSNI | 100%
504516 | N-W-NI-291219-Teangue_WTW-Access_Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 3550 | 0 | 3550 | 0 | [6 empty] | CM_WSNI | 100%
504520 | N-W-NI-301219-Dervaig_WTW-Relift_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1145.3 | 54.7 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
504521 | N-W-NI-301219-Mulindry_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WSNI | 100%
504974 | N-W-NI-310120-Balnain_DSR-SiteBatteries | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 75.23 | 1074.75 | 1149.98 | 0 | 1149.98 | 0 | [6 empty] | CM_WSNI | 100%
504954 | N-W-NI-310120-Glenvconvinth_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 3550 | 0 | 3550 | 0 | [6 empty] | CM_WSNI | 100%
504968 | N-W-NI-310120-Mallaig_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WSNI | 100%
504973 | N-W-NI-310120-Tiree_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 3220 | 0 | 3220 | 0 | [6 empty] | CM_WSNI | 100%
503855 | N-W-NI-Bogbain_TWP- Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 0 | 9700 | 0 | [6 empty] | CM_WSNI | 100%
504222 | N-W-NI-Bogbain_TWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2108.4 | 31.6 | 2140 | 0 | 2140 | 0 | [6 empty] | CM_WSNI | 100%
505142 | N-W-NI-Campbeltown_WTW-Soda deposits | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-20 | 2020-08-27 | 2020-12-03 | 2021-01-06 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1500 | 9500 | 11000 | 0 | 11000 | 0 | [6 empty] | WSNI | 100%
503849 | N-W-NI-Moineruadh-CWT-Cl_Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 0 | 9700 | 0 | [6 empty] | CM_WSNI | 100%
503978 | N-W-NI-Shiledaig_WTW-HMI | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-29 | 2020-03-29 | Highland | 0 | 0 | 0 | 0 | 0 | 4170 | -1192.85 | 2977.15 | 0 | 2977.15 | 0 | [6 empty] | CM_WSNI | 100%
503861 | N-W-NI-Tobermory_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1437.84 | 62.16 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WSNI | 100%
504378 | N-WW-171219-Kiltarlity_STW-MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-19 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 3220 | 0 | 3220 | 0 | [6 empty] | CM_WWNI | 100%
504109 | N-WW-I-021219-Wick_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2013.5 | -113.5 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWI | 100%
504135 | N-WW-I-041219-Muir_of_Ord-CCTV_Scoping | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1840.37 | -0.37 | 1840 | 0 | 1840 | 0 | [6 empty] | CM_WWI | 100%
504157 | N-WW-I-041219-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWI | 100%
505542 | N-WW-I-05032020-Campbeltown Kinloch Park - DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-06 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 160.38 | 1239.6 | 1399.98 | 0 | 1399.98 | 0 | [6 empty] | CM_WWI | 100%
504238 | N-WW-I-061219-Leverburgh-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1344.56 | -144.56 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWI | 100%
504537 | N-WW-I-070120-Thurso_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-09 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1757.07 | 62.93 | 1820 | 0 | 1820 | 0 | [6 empty] | CM_WWI | 100%
504611 | N-WW-I-100120-Muir_of_Ord-Pipe_Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5350 | 0 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WWI | 100%
504599 | N-WW-I-100120-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 8600 | 0 | 8600 | 0 | 8600 | 0 | [6 empty] | CM_WWI | 100%
505126 | N-WW-I-100220-Ardrishaig_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 643.57 | -33.55 | 610.02 | 0 | 610.02 | 0 | [6 empty] | CM_WWI | 100%
505118 | N-WW-I-100220-Broadstone_Av | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 562.62 | 8037.37 | 8599.99 | 0 | 8599.99 | 0 | [6 empty] | CM_WWNI | 100%
505625 | N-WW-I-100320-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-10 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 147.2 | 2102.8 | 2250 | 0 | 2250 | 0 | [6 empty] | CM_WWI | 100%
505130 | N-WW-I-110220-Oban_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1338.93 | -138.93 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWI | 100%
505221 | N-WW-I-160220-Thurso_DOA-BT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 212.62 | 3037.38 | 3250 | 0 | 3250 | 0 | [6 empty] | CM_WWI | 100%
505280 | N-WW-I-180220-Thurso_DOA-BT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 124.3 | 1775.71 | 1900.01 | 0 | 1900.01 | 0 | [6 empty] | CM_WWI | 100%
505307 | N-WW-I-190220-Stornoway_DOA-Sewer | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS2 |  | 2020-02-20 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 369.69 | 1780.31 | 2150 | 0 | 2150 | 173482.21 | [6 empty] | EC01A | 100%
503871 | N-WW-I-191119-Wick_DOA_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1353.25 | -53.25 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWI | 100%
505331 | N-WW-I-200220-Leurbost_East_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 281.31 | 4018.67 | 4299.98 | 0 | 4299.98 | 0 | [6 empty] | CM_WWI | 100%
505322 | N-WW-I-200220-Rosskeen_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4894.49 | 1605.51 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WWNI | 100%
505319 | N-WW-I-200220-Strathpeffer_DOA - Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 771.96 | 11028.04 | 11800 | 0 | 11800 | 0 | [6 empty] | CM_WWI | 100%
505859 | N-WW-I-200320-Kingussie_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 609.07 | 8700.95 | 9310.02 | 0 | 9310.02 | 0 | [6 empty] | CM_WWI | 100%
504446 | N-WW-I-201219-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1111.75 | 88.25 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWI | 100%
504443 | N-WW-I-201219-Kingussie_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7856 | 0 | 7856 | 0 | 7856 | 0 | [6 empty] | CM_WWI | 100%
505866 | N-WW-I-210320-Keiss_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 134.11 | 1915.91 | 2050.02 | 0 | 2050.02 | 0 | [6 empty] | CM_WWI | 100%
505873 | N-WW-I-220320-Eochar_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 245.33 | 3504.67 | 3750 | 0 | 3750 | 0 | [6 empty] | CM_WWI | 100%
505872 | N-WW-I-220320-Inverness_DOA-Dunabban_Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 147.2 | 2102.8 | 2250 | 0 | 2250 | 0 | [6 empty] | CM_WWI | 100%
505870 | N-WW-I-220320-Inverness_DOA-KingDuncan-BTrap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 147.2 | 2102.8 | 2250 | 0 | 2250 | 0 | [6 empty] | CM_WWI | 100%
503925 | N-WW-I-221119-Cromarty_DOA-MH_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 52345447.02 | [6 empty] | WWI | 100%
505370 | N-WW-I-230220-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 98.13 | 1401.88 | 1500.01 | 0 | 1500.01 | 0 | [6 empty] | CM_WWI | 100%
505907 | N-WW-I-240320-Aviemore_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 932.24 | 13317.76 | 14250 | 0 | 14250 | 0 | [6 empty] | CM_WWNI | 100%
505912 | N-WW-I-240320-Eriska;y_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-25 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 210 | 3000 | 3210 | 0 | 3210 | 0 | [6 empty] | CM_WWI | 100%
505918 | N-WW-I-240320-Oban_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-25 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 350 | 5000.02 | 5350.02 | 0 | 5350.02 | 0 | [6 empty] | CM_WWI | 100%
505917 | N-WW-I-240320-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-25 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 203.46 | 2906.52 | 3109.98 | 0 | 3109.98 | 0 | [6 empty] | CM_WWI | 100%
503946 | N-WW-I-241119-Helmsdale_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5536.05 | -36.05 | 5500 | 0 | 5500 | 52345447.02 | [6 empty] | WWI | 100%
504033 | N-WW-I-271119-Ft_William_Ashburn_Lane-Hatchbox | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWI | 100%
504508 | N-WW-I-271219-Bayble_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWI | 100%
504507 | N-WW-I-271219-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4482.68 | 17.32 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWI | 100%
504070 | N-WW-I-281119-Inverness-DOA-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWI | 100%
504923 | N-WW-I-290120-North_Toogs_Burra_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 7820 | 0 | 7820 | 0 | 7820 | 0 | [6 empty] | CM_WWI | 100%
505999 | N-WW-I-300320-Thurso_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWI | 100%
505998 | N-WW-I-300320-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4050 | 4050 | 0 | 4050 | 0 | [6 empty] | CM_WWI | 100%
506000 | N-WW-I-300320-Wick_DOA-Sewer-MurchisonSt | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3150 | 0 | 3150 | 0 | [6 empty] | CM_WWI | 100%
506018 | N-WW-I-310320-Lerwick_DOA-Rising_Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 9866.29 | 833.71 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_WWNI | 100%
506046 | N-WW-NI-010420-Campbeltown_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 24100 | 24100 | 0 | 24100 | 0 | [6 empty] | CM_WWNI | 100%
506045 | N-WW-NI-010420-Fortrose_STW-Biodisc_Filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5800 | 5800 | 0 | 5800 | 0 | [6 empty] | CM_WWNI | 100%
506040 | N-WW-NI-010420-Kiltarlity_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 8250 | 0 | 8250 | 0 | [6 empty] | CM_WWNI | 100%
506033 | N-WW-NI-010420-Oban_Corran_Park_SPS-ST_Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 1750 | 0 | 1750 | 0 | [6 empty] | CM_WWNI | 100%
506043 | N-WW-NI-010420-Riverbank_Tce_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 3550 | 0 | 3550 | 0 | [6 empty] | CM_WWNI | 100%
506061 | N-WW-NI-020420-Avoch_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4820 | 4820 | 0 | 4820 | 0 | [6 empty] | CM_WWNI | 100%
506067 | N-WW-NI-020420-Dornoch_STW_Tanker_point_grating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-03 |  |  |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
506053 | N-WW-NI-020420-Gairloch_STW-Site_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
506047 | N-WW-NI-020420-Kiknlochewe_Village_Sep-Access_Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 6750 | 0 | [6 empty] | CM_WWNI | 100%
504108 | N-WW-NI-021219-Carradale_Foreshore_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3670.12 | 29.88 | 3700 | 0 | 3700 | 0 | [6 empty] | CM_WWNI | 100%
505002 | N-WW-NI-030220-Dingwall_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 189.72 | 2710.28 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
505511 | N-WW-NI-030320-Alness_Invergordon_STW-SIS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-04 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 10176.56 | 123.46 | 10300.02 | 0 | 10300.02 | 0 | [6 empty] | CM_WWNI | 100%
505515 | N-WW-NI-030320-Barbaravuille_Sutor_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-04 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 124.3 | 1775.72 | 1900.02 | 0 | 1900.02 | 0 | [6 empty] | CM_WWNI | 100%
505502 | N-WW-NI-030320-Clachan_STW-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-04 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 365.06 | 3534.94 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
505513 | N-WW-NI-030320-Dornoch_STW-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-04 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 435.05 | 6214.93 | 6649.98 | 0 | 6649.98 | 0 | [6 empty] | CM_WWNI | 100%
504113 | N-WW-NI-031219-Wick_STW-CASS_Jack_Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-30 | 2020-03-30 | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505013 | N-WW-NI-040220-Gairloch_East_Strath_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2686.85 | 3113.16 | 5800.01 | 0 | 5800.01 | 0 | [6 empty] | CM_WWNI | 100%
505010 | N-WW-NI-040220-Kildary_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3236.25 | 83.77 | 3320.02 | 0 | 3320.02 | 0 | [6 empty] | CM_WWNI | 100%
505024 | N-WW-NI-040220-Kildary_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1066.36 | 15233.65 | 16300.01 | 0 | 16300.01 | 0 | [6 empty] | CM_WWNI | 100%
505023 | N-WW-NI-040220-Stornoway_Coastguard_SPS-Deragger | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 4347.71 | 52.3 | 4400.01 | 0 | 4400.01 | 0 | [6 empty] | CM_WWNI | 100%
505527 | N-WW-NI-040320-Croy_STW-Geared_Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 255.14 | 3644.86 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
505539 | N-WW-NI-040320-Stornoway_STW-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1457.93 | 42.07 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505044 | N-WW-NI-050220-Kirkwall_HoW_STC-Sludge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 3418 | 382 | 3800 | 0 | 3800 | 0 | [6 empty] | CM_WWNI | 100%
505041 | N-WW-NI-050220-Ullapool_STW-InletScreen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5756.32 | 43.69 | 5800.01 | 0 | 5800.01 | 0 | [6 empty] | CM_WWNI | 100%
505564 | N-WW-NI-050320-Kingussie_STW-RAS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 268.22 | 3831.76 | 4099.98 | 0 | 4099.98 | 0 | [6 empty] | CM_WWNI | 100%
505565 | N-WW-NI-050320-Newtonmore_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-06 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 196.26 | 2803.74 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWI | 100%
505555 | N-WW-NI-050320-Thurso_STC-Sludge_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.97 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
504530 | N-WW-NI-060120-Clachan_Seil_Brookside_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1375.98 | -25.98 | 1350 | 0 | 1350 | 0 | [6 empty] | CM_WWNI | 100%
504532 | N-WW-NI-060120-Dulnain_Bridge-Brushes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
504531 | N-WW-NI-060120-Stornoway STW-Scaffolding | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 5350 | 0 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WWNI | 100%
505065 | N-WW-NI-060220-Lairg_War_Memorial_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2150.12 | 49.9 | 2200.02 | 0 | 2200.02 | 0 | [6 empty] | CM_WWNI | 100%
505580 | N-WW-NI-060320-Campbeltown_Kinloch_Park_SPS-NRVs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-10 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2445.28 | 154.7 | 2599.98 | 0 | 2599.98 | 0 | [6 empty] | CM_WWNI | 100%
505576 | N-WW-NI-060320-Peninver_Outfall_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2783.34 | -83.34 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504232 | N-WW-NI-061219- Ballachulish_West_SPS-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2140 | 0 | 2140 | 0 | 2140 | 0 | [6 empty] | CM_WWNI | 100%
504237 | N-WW-NI-061219-Campbeltown_STW-Storm_Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2400.21 | 99.79 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504239 | N-WW-NI-061219-Ferness_STW-Odour | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1343.47 | 56.53 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
504236 | N-WW-NI-061219-Furnace_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1326.61 | 73.39 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
504235 | N-WW-NI-061219-Wick_Scalesburn_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | 4280 | 0 | 4280 | 0 | [6 empty] | CM_WWNI | 100%
504228 | N-WW-NI-061219-Wick_STW-Grit_Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
504535 | N-WW-NI-070120-Portmahomack_Main_St_SPS-Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-09 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1582.46 | 27.54 | 1610 | 0 | 1610 | 0 | [6 empty] | CM_WWNI | 100%
504565 | N-WW-NI-080120-Bu_Point_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1585.33 | 24.67 | 1610 | 0 | 1610 | 0 | [6 empty] | CM_WWNI | 100%
504595 | N-WW-NI-080120-Conon_Bridge_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | 4280 | 0 | 4280 | 0 | [6 empty] | CM_WWNI | 100%
504567 | N-WW-NI-080120-Grantown_STW-Sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-09 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1117.3 | 82.7 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
504562 | N-WW-NI-080120-Jemimaville_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-09 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1746.2 | 3.8 | 1750 | 0 | 1750 | 0 | [6 empty] | CM_WWNI | 100%
504572 | N-WW-NI-080120-Lerwick_Gremista_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 2819.38 | -19.38 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WWNI | 100%
504249 | N-WW-NI-091219-Benderloch_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4144.26 | 55.74 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
504251 | N-WW-NI-091219-Watten_STW-Site_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3135.98 | 64.02 | 3200 | 0 | 3200 | 0 | [6 empty] | CM_WWNI | 100%
504610 | N-WW-NI-100120-Alness_Invergordon_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2445.1 | 54.9 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504612 | N-WW-NI-100120-Cawdor_STW-Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2150 | 0 | 2150 | 0 | 2150 | 0 | [6 empty] | CM_WWNI | 100%
504609 | N-WW-NI-100120-Inveraray_Barn_Brae_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5522.86 | 77.14 | 5600 | 0 | 5600 | 0 | [6 empty] | CM_WWNI | 100%
504613 | N-WW-NI-100120-Inverness_Culduthel_Av_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1497.6 | 2.4 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
504602 | N-WW-NI-100120-Kyleakin_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 8600 | 0 | 8600 | 0 | 8600 | 0 | [6 empty] | CM_WWNI | 100%
504597 | N-WW-NI-100120-Lerwick_Rovahead_STC-Belt_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1249.49 | 50.51 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504601 | N-WW-NI-100120-Salen_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1367.55 | 32.45 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505129 | N-WW-NI-100220-Alness_Teaninich_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1613.4 | 106.61 | 1720.01 | 0 | 1720.01 | 0 | [6 empty] | CM_WWNI | 100%
505121 | N-WW-NI-100220-Campbeltown_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2143.94 | 106.05 | 2249.99 | 0 | 2249.99 | 0 | [6 empty] | CM_WWNI | 100%
505098 | N-WW-NI-100220-Piperhill_SPS-Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1749.31 | 70.68 | 1819.99 | 0 | 1819.99 | 0 | [6 empty] | CM_WWNI | 100%
505654 | N-WW-NI-100320-Acharacle STW - Refurbish telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 71.96 | 1028.02 | 1099.98 | 0 | 1099.98 | 0 | [6 empty] | CM_WWNI | 100%
505653 | N-WW-NI-100320-Alness & Invergordon STW - Replace FE Pump A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 837.38 | 11962.6 | 12799.98 | 0 | 12799.98 | 0 | [6 empty] | CM_WWNI | 100%
505624 | N-WW-NI-100320-Campbeltown Bengullion Road SPS - Replace Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-08 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2093.02 | 0 | 2093.02 | 0 | 2093.02 | 0 | [6 empty] | CM_WWNI | 100%
505642 | N-WW-NI-100320-Connel TPS1 - Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 523.36 | 7476.62 | 7999.98 | 0 | 7999.98 | 0 | [6 empty] | CM_WWNI | 100%
505648 | N-WW-NI-100320-Grantown STW - Electrical Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 503.74 | 7196.24 | 7699.98 | 0 | 7699.98 | 0 | [6 empty] | CM_WWNI | 100%
505657 | N-WW-NI-100320-Kilchoan Mingarry ST - Replace Cover & Refurbish Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 170.09 | 2429.89 | 2599.98 | 0 | 2599.98 | 0 | [6 empty] | CM_WWNI | 100%
505650 | N-WW-NI-100320-Nairn STW - CAS Basin Critical Spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 418.69 | 5981.33 | 6400.02 | 0 | 6400.02 | 0 | [6 empty] | CM_WWNI | 100%
505629 | N-WW-NI-100320-Nairn_STW- Skimer_Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-10 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4685.16 | 24.84 | 4710 | 0 | 4710 | 0 | [6 empty] | CM_WWNI | 100%
504267 | N-WW-NI-101219-Aviemore_STW-DO_Probes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 8200 | 0 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WWNI | 100%
504264 | N-WW-NI-101219-Oban_STW-Belt_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 16400.92 | 0 | 16400.92 | 0 | 16400.92 | 0 | [6 empty] | CM_WWNI | 100%
503802 | N-WW-NI-111219-Broadford_Ind_Est_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 | 2020-03-31 | Highland | 0 | 0 | 0 | 0 | 0 | 9841.89 | -241.89 | 9600 | 0 | 9600 | 0 | [6 empty] | CM_WWNI | 100%
503810 | N-WW-NI-121119-Alness & Invergordon STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 56717112.68 | [6 empty] | WWNI | 100%
503807 | N-WW-NI-121119-Fort_Augustus_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1241.05 | 58.95 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504635 | N-WW-NI-130120-Ft_Augustus_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
505188 | N-WW-NI-130220-Alness_Invergordon_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.95 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
505190 | N-WW-NI-130220-Thurso _STW-Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 532.17 | 2967.85 | 3500.02 | 0 | 3500.02 | 0 | [6 empty] | CM_WWNI | 100%
503817 | N-WW-NI-131119-Bonawe_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 | 2020-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 10230.63 | -8930.63 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWI | 100%
505198 | N-WW-NI-140220-Balintore_STW-RBC3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2695.33 | 38504.69 | 41200.02 | 0 | 41200.02 | 0 | [6 empty] | CM_WWNI | 100%
505200 | N-WW-NI-140220-Benderloch_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4086.72 | 113.28 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
504672 | N-WW-NI-150120-Cawdor_STW-Pump_CS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3804.03 | 95.97 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
504666 | N-WW-NI-150120-Kinlochewe_Incheril_SEP-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2670.96 | 29.04 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504674 | N-WW-NI-150120-Lerwick_Gremista_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 2014.48 | 235.52 | 2250 | 0 | 2250 | 0 | [6 empty] | CM_WWNI | 100%
503840 | N-WW-NI-151119-Thurso_STW-Auto_Sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | - | 0 | 0 | 0 | 0 | 0 | 8400 | 0 | 8400 | 0 | 8400 | 56717112.68 | [6 empty] | WWNI | 100%
504347 | N-WW-NI-151219-Muir_of_Ord-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3052.72 | 97.28 | 3150 | 0 | 3150 | 0 | [6 empty] | CM_WWNI | 100%
504348 | N-WW-NI-151219-St_Marys_Sep_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505218 | N-WW-NI-160220-Avoch_STW-RBC2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1470 | 20999.99 | 22469.99 | 0 | 22469.99 | 0 | [6 empty] | CM_WWNI | 100%
505224 | N-WW-NI-160220-Balivanich_STW-PolyTank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4139.91 | 160.07 | 4299.98 | 0 | 4299.98 | 0 | [6 empty] | CM_WWNI | 100%
505219 | N-WW-NI-160220-Boat_of_Garten_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1085.79 | 3414.22 | 4500.01 | 0 | 4500.01 | 0 | [6 empty] | CM_WWNI | 100%
505223 | N-WW-NI-160220-Dornoch_STW-PolyDosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1045.39 | 54.6 | 1099.99 | 0 | 1099.99 | 0 | [6 empty] | CM_WWNI | 100%
505220 | N-WW-NI-160220Henderson_Drive_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1577.97 | 72.05 | 1650.02 | 0 | 1650.02 | 0 | [6 empty] | CM_WWNI | 100%
505225 | N-WW-NI-160220-Lochcarron_STW-PFT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 595.33 | 8504.67 | 9100 | 0 | 9100 | 0 | [6 empty] | CM_WWNI | 100%
505743 | N-WW-NI-160320-Balivanich_STW-Isolater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1497.15 | 1202.85 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
505754 | N-WW-NI-160320-Caravan_Avie_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 91.59 | 1308.39 | 1399.98 | 0 | 1399.98 | 0 | [6 empty] | CM_WWNI | 100%
505744 | N-WW-NI-160320-Cawdor_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 336.92 | 4813.06 | 5149.98 | 0 | 5149.98 | 0 | [6 empty] | CM_WWNI | 100%
505756 | N-WW-NI-160320-Conon_Bridge_STW-Penstock | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-18 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 700 | 9999.98 | 10699.98 | 0 | 10699.98 | 0 | [6 empty] | CM_WWNI | 100%
505749 | N-WW-NI-160320-Grantown_STW-Electrical_Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 8236.21 | 13.79 | 8250 | 0 | 8250 | 0 | [6 empty] | CM_WWNI | 100%
504355 | N-WW-NI-161219-Campbeltown_STW-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WWNI | 100%
504360 | N-WW-NI-161219-Clachan_STW-Cabin | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5900 | 0 | 5900 | 0 | 5900 | 0 | [6 empty] | CM_WWNI | 100%
504358 | N-WW-NI-161219-Oban_STW-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3670.18 | -1870.18 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
504362 | N-WW-NI-161219-Wick_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-19 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504722 | N-WW-NI-170120-Cawdor_STW-RASPump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
504720 | N-WW-NI-170120-Kirkhill_STW-Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5511.54 | 88.46 | 5600 | 0 | 5600 | 0 | [6 empty] | CM_WWNI | 100%
504721 | N-WW-NI-170120-Stornoway_STC-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1202.89 | -2.89 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
504374 | N-WW-NI-171219-Invergordon_63_Saltburn_ SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-19 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3294.04 | 55.96 | 3350 | 0 | 3350 | 0 | [6 empty] | CM_WWNI | 100%
505279 | N-WW-NI-180220-Glenelg_STW-Access_Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 130.84 | 2009.15 | 2139.99 | 0 | 2139.99 | 0 | [6 empty] | CM_WWNI | 100%
505802 | N-WW-NI-180320-Balintore_STW-RBC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 143.93 | 12256.09 | 12400.02 | 0 | 12400.02 | 0 | [6 empty] | CM_WWNI | 100%
504416 | N-WW-NI-181219-Fortrose_STW-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4700 | 0 | 4700 | 0 | 4700 | 0 | [6 empty] | CM_WWNI | 100%
504411 | N-WW-NI-181219-Stornoway_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-19 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 2045.2 | 54.8 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
504727 | N-WW-NI-190120-Balintore_STW-RBC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 22700 | 0 | 22700 | 0 | 22700 | 0 | [6 empty] | CM_WWNI | 100%
504728 | N-WW-NI-190120-Duror_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WWNI | 100%
504729 | N-WW-NI-190120-FtAugustus_MarketHIll_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1339.75 | 60.25 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
504723 | N-WW-NI-190120-Kilmory_STW-ValveScrew | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1283.29 | 16.71 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504726 | N-WW-NI-190120-Kingussie_STW-ScopeReport | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WWNI | 100%
504725 | N-WW-NI-190120-Oban_George_St_CSO-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504724 | N-WW-NI-190120-Weyland_Bay_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 2250 | 0 | [6 empty] | CM_WWNI | 100%
505302 | N-WW-NI-190220-Campbeltown_STW-Flooring_Clips | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 502.71 | 5707.3 | 6210.01 | 0 | 6210.01 | 0 | [6 empty] | CM_WWNI | 100%
505298 | N-WW-NI-190220-Clachan_Seil_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 119.25 | 1280.75 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505305 | N-WW-NI-190220-Stornoway_STW-WashWater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3296.39 | -76.4 | 3219.99 | 0 | 3219.99 | 0 | [6 empty] | CM_WWNI | 100%
505830 | N-WW-NI-190320-Boat_of_Garten_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-20 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 14250 | 14250 | 0 | 14250 | 0 | [6 empty] | CM_WWNI | 100%
505818 | N-WW-NI-190320-Lochinver_Inver_Tce_SPS-Converter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 425.23 | 6074.75 | 6499.98 | 0 | 6499.98 | 0 | [6 empty] | CM_WWNI | 100%
505828 | N-WW-NI-190320-Oban_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-20 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 394.96 | 4905.02 | 5299.98 | 0 | 5299.98 | 0 | [6 empty] | CM_WWNI | 100%
503875 | N-WW-NI-191119-Dulnain_Bridge_STW- SAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 3550 | 0 | 3550 | 0 | [6 empty] | CM_WWNI | 100%
503873 | N-WW-NI-191119-Kiltarlity_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1317.34 | 82.66 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
504430 | N-WW-NI-191219-Lerwick_Gremista_SPS-Refurb_NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 3389.6 | 310.4 | 3700 | 0 | 3700 | 0 | [6 empty] | CM_WWNI | 100%
504427 | N-WW-NI-191219-Sclloway_West_Shore_SPS - Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 20418.65 | 1581.35 | 22000 | 0 | 22000 | 0 | [6 empty] | CM_WWNI | 100%
504439 | N-WW-NI-191219-Thurso_STC-Lime_Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 916.8 | 383.2 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504433 | N-WW-NI-191219-Thurso_STW-Kiosk_Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-16 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
504742 | N-WW-NI-200120-Aviemore_STW-Pump_Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2862.38 | -62.38 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WWNI | 100%
504741 | N-WW-NI-200120-Dingwall_Jubilee_Park_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6739.22 | 60.78 | 6800 | 0 | 6800 | 0 | [6 empty] | CM_WWNI | 100%
504739 | N-WW-NI-200120-Kiltarlity_STW-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1657.09 | 92.91 | 1750 | 0 | 1750 | 0 | [6 empty] | CM_WWNI | 100%
504743 | N-WW-NI-200120-Portree_STW-InletScreen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWNI | 100%
504737 | N-WW-NI-200120-Thurso_STW-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1428.64 | 71.36 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505336 | N-WW-NI-200220-Halkirk_Braal_Rd_SPS-Building_Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 346.73 | 4953.27 | 5300 | 0 | 5300 | 0 | [6 empty] | CM_WWNI | 100%
505317 | N-WW-NI-200220-Portmahomack_STW-Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1276.63 | 23.37 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
505334 | N-WW-NI-200220-Stornoway_STW-Screen_Brushes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 1737.03 | 462.99 | 2200.02 | 0 | 2200.02 | 0 | [6 empty] | CM_WWNI | 100%
505323 | N-WW-NI-200220-Tain_STW-UV_System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1694.39 | 24205.61 | 25900 | 0 | 25900 | 0 | [6 empty] | CM_WWNI | 100%
505839 | N-WW-NI-200320-Campbeltown_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-20 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 106.16 | 1093.84 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
503883 | N-WW-NI-201119-Brora_STW-Outfall_Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6800 | 19000 | 25800 | 0 | 25800 | 0 | [6 empty] | CM_WWNI | 100%
503895 | N-WW-NI-201119-Henderson_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1909.99 | -109.99 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
503890 | N-WW-NI-201119-Kingussie_STW-Air_Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 3200 | 0 | 3200 | 0 | [6 empty] | CM_WWI | 100%
503886 | N-WW-NI-201119-Ullapool_STW-Centrifuge_HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 14400 | 0 | 14400 | 0 | [6 empty] | CM_WWNI | 100%
504456 | N-WW-NI-201219-Bowmore_STW-Aerators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 21700 | 0 | 21700 | 0 | 21700 | 0 | [6 empty] | CM_WWNI | 100%
504461 | N-WW-NI-201219-Stornoway_STW-Roller_Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-24 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 3300 | 0 | 3300 | 0 | [6 empty] | CM_WWNI | 100%
504449 | N-WW-NI-201219-Tain_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504458 | N-WW-NI-201219-Thurso_STC-Sludge_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-24 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 5400 | 0 | 5400 | 0 | [6 empty] | CM_WWNI | 100%
504770 | N-WW-NI-210120-Brora_Salt_St_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3498.27 | 41.73 | 3540 | 0 | 3540 | 0 | [6 empty] | CM_WWNI | 100%
504769 | N-WW-NI-210120-Halkirk_STW-FallRestraint | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505869 | N-WW-NI-210320-Alness_Invergordon_STC-Lime_HotBox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 955.14 | 13644.84 | 14599.98 | 0 | 14599.98 | 0 | [6 empty] | CM_WWNI | 100%
505867 | N-WW-NI-210320-Teaninich_SPS-Diaphram_CS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.97 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
504800 | N-WW-NI-220120-Halkirk_STW-ControlPanel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3109.06 | -209.06 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
504780 | N-WW-NI-220120-Inveraray_Burn_Brae_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 6300 | 0 | 6300 | 0 | 6300 | 0 | [6 empty] | CM_WWI | 100%
504797 | N-WW-NI-220120-Nairn_STW-Centrifuge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 17120 | 0 | 17120 | 0 | 17120 | 0 | [6 empty] | CM_WWNI | 100%
504781 | N-WW-NI-220120-Newtonmore_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
504807 | N-WW-NI-230120-Gairloch_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2388.7 | 11.3 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WWI | 100%
504819 | N-WW-NI-230120-Gairloch_DOA-MH_Horisdale | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3280.52 | -160.52 | 3120 | 0 | 3120 | 0 | [6 empty] | CM_WWI | 100%
504804 | N-WW-NI-230120-Lochcarron_Slumbay_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504817 | N-WW-NI-230120-Nethy_Bridge-MH_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWI | 100%
504818 | N-WW-NI-230120-Voe_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 1169.86 | 130.14 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
505378 | N-WW-NI-230220-Edderton_STW-SAF_Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 157.01 | 2242.98 | 2399.99 | 0 | 2399.99 | 0 | [6 empty] | CM_WWNI | 100%
505376 | N-WW-NI-230220-Evanton_STW_FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 137.38 | 1962.61 | 2099.99 | 0 | 2099.99 | 0 | [6 empty] | CM_WWNI | 100%
505377 | N-WW-NI-230220-Halkirk_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2152.73 | 147.28 | 2300.01 | 0 | 2300.01 | 0 | [6 empty] | CM_WWNI | 100%
505373 | N-WW-NI-230220-Oban_STW-Crane | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 191.21 | 2308.79 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505371 | N-WW-NI-230220-Swainbost_SEP-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 220.4 | 879.59 | 1099.99 | 0 | 1099.99 | 0 | [6 empty] | CM_WWNI | 100%
505904 | N-WW-NI-230320-Glenachulish_ST-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 119.07 | 1700.91 | 1819.98 | 0 | 1819.98 | 0 | [6 empty] | CM_WWNI | 100%
505897 | N-WW-NI-230320-Tarbert_STW- Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 298.23 | 1311.75 | 1609.98 | 0 | 1609.98 | 0 | [6 empty] | CM_WWNI | 100%
505896 | N-WW-NI-230320-Teaninich_SPS-Transfer_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.97 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
504838 | N-WW-NI-240120-Nairn_3 Sites-Inlet_Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4400 | 0 | 4400 | 0 | 4400 | 0 | [6 empty] | CM_WWNI | 100%
504826 | N-WW-NI-240120-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 9000 | 0 | [6 empty] | CM_WWI | 100%
505393 | N-WW-NI-240220-Balivanich_STW-NRVs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 180.95 | 1969.05 | 2150 | 0 | 2150 | 0 | [6 empty] | CM_WWNI | 100%
505391 | N-WW-NI-240220-Strathpeffer_STW-Safety_Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 248.6 | 3551.4 | 3800 | 0 | 3800 | 0 | [6 empty] | CM_WWNI | 100%
505920 | N-WW-NI-240320-Oban_STW--Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 768.3 | 8861.7 | 9630 | 0 | 9630 | 0 | [6 empty] | CM_WWNI | 100%
503945 | N-WW-NI-241119-Thurso_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 | 2020-03-31 | Highland | 0 | 0 | 0 | 0 | 0 | 1778.61 | -78.61 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
504499 | N-WW-NI-241219- Fort Augustus WWTW (North)Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWNI | 100%
504500 | N-WW-NI-241219-Cromarty Sutors WWTW (North) -Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWNI | 100%
504839 | N-WW-NI-250120-Nairn_3 Sites-Inlet_Screens Pt2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 4540.37 | 59.63 | 4600 | 0 | 4600 | 0 | [6 empty] | CM_WWNI | 100%
505396 | N-WW-NI-250220-Eochar_SPS- Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 105.33 | 1504.7 | 1610.03 | 0 | 1610.03 | 0 | [6 empty] | CM_WWNI | 100%
505394 | N-WW-NI-250220-Eochar_SPS-Wetwell | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 40.3 | 2659.7 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
503963 | N-WW-NI-251119-Broadford_STW-Dewaterer_Vent | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 0 | [6 empty] | CM_WWNI | 100%
503969 | N-WW-NI-251119-Tobermory_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4991.11 | -191.11 | 4800 | 0 | 4800 | 0 | [6 empty] | CM_WWNI | 100%
503973 | N-WW-NI251119-Wick_STW-Pump_Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 | 2020-03-31 | Highland | 0 | 0 | 0 | 0 | 0 | 4310.38 | -1210.38 | 3100 | 0 | 3100 | 0 | [6 empty] | CM_WWNI | 100%
504844 | N-WW-NI-260120-Alness_Invergordon_STW-Autosampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2334.11 | 65.89 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WWNI | 100%
504841 | N-WW-NI-260120-Campbeltown_Kinloch _Park_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1149.66 | 50.34 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
504843 | N-WW-NI-260120-Cawdor_STW-MeterCabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504840 | N-WW-NI-260120-Duror_STW-Cabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2143.99 | -143.99 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504847 | N-WW-NI-260120-Evanton_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 3550 | 0 | 3550 | 0 | [6 empty] | CM_WWNI | 100%
504848 | N-WW-NI-260120-Kingussie_West_CSO-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWI | 100%
504846 | N-WW-NI-260120-Stornoway_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 3450 | 0 | 3450 | 0 | 3450 | 0 | [6 empty] | CM_WWI | 100%
505432 | N-WW-NI-260220-Wick_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1160.62 | 139.38 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504875 | N-WW-NI-270120-Appin_DOA -Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1421.76 | 78.24 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWI | 100%
504862 | N-WW-NI-270120-Aviemore_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7400 | 0 | 7400 | 0 | 7400 | 0 | [6 empty] | CM_WWNI | 100%
504863 | N-WW-NI-270120-Kingussie_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWI | 100%
504864 | N-WW-NI-270120-Portmahomack_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1470.45 | 29.55 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505435 | N-WW-NI-270220-Benderloch_STW-Gate_SafetyRepairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 270.66 | 4549.32 | 4819.98 | 0 | 4819.98 | 0 | [6 empty] | CM_WWNI | 100%
505450 | N-WW-NI-270220-Oban_STW-Alarm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 27.66 | 2122.34 | 2150 | 0 | 2150 | 0 | [6 empty] | CM_WWNI | 100%
505438 | N-WW-NI-270220-Oban_STW-Pipework_Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 7100.01 | 7100.01 | 0 | 7100.01 | 0 | [6 empty] | CM_WWNI | 100%
505451 | N-WW-NI-270220-Stornoway_Lower_Sandwick_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 241.46 | 4058.52 | 4299.98 | 0 | 4299.98 | 0 | [6 empty] | CM_WWNI | 100%
505440 | N-WW-NI-270220-Stornoway_STW-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2021-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 241.46 | 4058.52 | 4299.98 | 0 | 4299.98 | 0 | [6 empty] | CM_WWNI | 100%
506006 | N-WW-NI-270320-Alness_Teaninich_SPS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 5400 | 0 | 5400 | 0 | [6 empty] | CM_WWNI | 100%
504004 | N-WW-NI-271119-Applecross_Toilet_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
504027 | N-WW-NI-271119-Oban_Stevenson_St_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4319.26 | 80.74 | 4400 | 0 | 4400 | 0 | [6 empty] | CM_WWNI | 100%
504020 | N-WW-NI-271119-Strathpeffer_Jamestown_ SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504006 | N-WW-NI-271119-Wick_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 0 | [6 empty] | CM_WWNI | 100%
504040 | N-WW-NI-271119-Wick_STW _Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1533.83 | -33.83 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
504506 | N-WW-NI-271219-Crowlista_STW-Tipping_Tray | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WWNI | 100%
504505 | N-WW-NI-271219-Halkirk_STW-Sludge_HT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1720 | 0 | 1720 | 0 | 1720 | 0 | [6 empty] | CM_WWNI | 100%
505463 | N-WW-NI-280220-Alness_Invergordon_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 896.26 | 12803.75 | 13700.01 | 0 | 13700.01 | 0 | [6 empty] | CM_WWNI | 100%
505465 | N-WW-NI-280220-Bowmorre_STW-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 170.09 | 2429.91 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WWNI | 100%
505464 | N-WW-NI-280220-Thurso_Harbour_Transfer_SPS-Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2973.26 | 26.72 | 2999.98 | 0 | 2999.98 | 0 | [6 empty] | CM_WWNI | 100%
504046 | N-WW-NI-281119-Alness_Invergordon_STW-PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1909.92 | 90.08 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504065 | N-WW-NI-281119-Baltasound_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-30 |  | 2020-03-30 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 3686.26 | 613.74 | 4300 | 0 | 4300 | 0 | [6 empty] | CM_WWNI | 100%
504049 | N-WW-NI-281119-Campbeltown_STW-LIghtning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
504512 | N-WW-NI-281219-Campbeltown_STW-Blowers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504511 | N-WW-NI-281219-Lerwick_Rovahead_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1250.5 | 1449.5 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504510 | N-WW-NI-281219-Lochcarron_STW-DO_Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504509 | N-WW-NI-281219-Stornoway_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 5350 | 0 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WWNI | 100%
504928 | N-WW-NI-290120-Aviemore_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 8800 | 0 | 8800 | 0 | 8800 | 0 | [6 empty] | CM_WWNI | 100%
504927 | N-WW-NI-290120-Fassfern_STW-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 3220 | 0 | 3220 | 0 | [6 empty] | CM_WWNI | 100%
504930 | N-WW-NI-290120-Nairn_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2150 | 0 | 2150 | 0 | 2150 | 0 | [6 empty] | CM_WWI | 100%
504906 | N-WW-NI-290120-Stornoway _STW-Container | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 3550 | 0 | 3550 | 0 | [6 empty] | CM_WWNI | 100%
505466 | N-WW-NI-290220-Broadford_STW-Kiosk_Power | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 281.31 | 4018.67 | 4299.98 | 0 | 4299.98 | 0 | [6 empty] | CM_WWNI | 100%
505468 | N-WW-NI-290220-Dornoch_STW-Sludge_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3811.32 | 88.68 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
505472 | N-WW-NI-290220-Evanton_STW-FST_Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 137.38 | 1962.61 | 2099.99 | 0 | 2099.99 | 0 | [6 empty] | CM_WWNI | 100%
505471 | N-WW-NI-290220-Gremista_SPS-Site_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 1098.19 | 101.81 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
505467 | N-WW-NI-290220-Thurso_STW-Shower_Area | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1841.84 | 158.17 | 2000.01 | 0 | 2000.01 | 0 | [6 empty] | CM_WWNI | 100%
504075 | N-WW-NI-291119-Tore_STW-Outfall_Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 3306.27 | 93.73 | 3400 | 0 | 3400 | 0 | [6 empty] | CM_WWNI | 100%
504946 | N-WW-NI-300120-Bowmore_STW-AlgaeSapper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504949 | N-WW-NI-300120-Campbeltown_STW-InletChannel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-03 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 10999.97 | 800.03 | 11800 | 0 | 11800 | 0 | [6 empty] | CM_WWNI | 100%
504940 | N-WW-NI-300120-Campbeltown_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
504951 | N-WW-NI-300120-Tain_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1243.07 | 56.93 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
505997 | N-WW-NI-300320-Dornoch_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505989 | N-WW-NI-300320-Salen_Outlet_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
506002 | N-WW-NI-310320- Clachan_Seil_Brookside_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
506003 | N-WW-NI-310320-Campbeltowh_Kinloch_Park_SPS-VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 27.66 | 1272.34 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
506015 | N-WW-NI-310320-Conon_Bridge_STW-Aeration | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 2310 | 0 | 2310 | 0 | [6 empty] | CM_WWNI | 100%
506007 | N-WW-NI-310320-Dornoch_STW-Roller CS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 2865 | 245 | 3110 | 0 | 3110 | 0 | [6 empty] | CM_WWNI | 100%
506010 | N-WW-NI-310320-Lerwick_DOA-Gremista_Rd_MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-03-31 |  | 2021-03-31 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 4884.42 | 415.58 | 5300 | 0 | 5300 | 0 | [6 empty] | CM_WWI | 100%
506008 | N-WW-NI-310320-North_Ballachulish_STW-Lagging | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
506013 | N-WW-NI-310320-Oban_Corran_Park_SPS-Macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 1180 | 120 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
503950 | N-WW-NI-Taynuilt_STW-UV_Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 | 2020-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 10300 | 0 | 10300 | 0 | 10300 | 0 | [6 empty] | CM_WWNI | 100%
504283 | N-WW-NI-Tobermory_SPS-Var | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-09 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 3486.82 | 46513.18 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WWNI | 100%
504455 | N-WW-STW-201219-Oban_STW-Sludge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-20 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 19000 | 0 | 19000 | 0 | [6 empty] | CM_WWNI | 100%
500510 | O&D- Building Fabric Condition Surveys | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 17473 | 8371.65 | 20352.35 | 69487.24 | 30591.73 | 58724.03 | 205000 | 0 | 205000 | 0 | [6 empty] | CM_M&G | 100%
500511 | O&D- Building Fabric in Roof Renewals & Condition Surveys | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 282199 | 144609 | 228401 | 256587.9 | 92949.07 | 353468.03 | 1358214 | 0 | 1358214 | 0 | [6 empty] | CM_M&G | 100%
500947 | O&D- Dumfries Office - Marchmount & Lincluden Depots | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-17 | 2019-09-06 | 2019-12-15 | 2021-05-06 | 2021-05-06 | Dumfries and Galloway | 0 | 56607 | -5101.98 | 2200 | 97028.21 | 295279.12 | 1563986.65 | 2009999 | 0 | 2009999 | 0 | [6 empty] | CM_M&G | 100%
500513 | O&D- EU Energy Directive | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 90241 | 72836.42 | 69669.96 | 105744.31 | 94854.31 | 191654 | 625000 | 0 | 625000 | 0 | [6 empty] | CM_M&G | 100%
500520 | O&D- Facilities East Office Fairmilehead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-05-18 | 2016-10-24 | 2016-10-24 | 2019-03-07 | 2019-03-07 | Scottish Water Wide | 0 | 301700 | 849674.93 | 1783224.55 | 1715213.35 | 39545.9 | -16652 | 4672706.73 | 0 | 4672706.73 | 0 | [6 empty] | CM_M&G | 100%
500514 | O&D- Fixed Wire Testing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 108706.24 | 151257.76 | 75373 | 93638 | 63949.08 | 91076.99 | 584001.07 | 0 | 584001.07 | 0 | [6 empty] | CM_M&G | 100%
500515 | O&D- FRA inc Fire Alarms | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 88605 | 54097 | 62762.82 | 100947.52 | 102098.66 | 233489 | 642000 | 0 | 642000 | 0 | [6 empty] | CM_M&G | 100%
500516 | O&D- H&S Minor Works | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 188619 | 364067 | 412601 | 329583.49 | 366579.45 | 588179.06 | 2249629 | 0 | 2249629 | 0 | [6 empty] | CM_M&G | 100%
500517 | O&D- Heating & Ventilation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 71001.35 | 61042.65 | 143646.3 | 141375.37 | 56855.34 | 125500.77 | 599421.78 | 0 | 599421.78 | 0 | [6 empty] | CM_M&G | 100%
500518 | O&D- Refurb & Capital Maintenance inc HVAC | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 143114 | 456482 | 329441.01 | 959030.99 | 595356.15 | 548753.85 | 3032178 | 0 | 3032178 | 0 | [6 empty] | CM_M&G | 100%
500512 | O&D- Replacement Furniture (DSE) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 95097 | 49190.54 | 201343.46 | 142836.14 | 104015.8 | 187517.06 | 780000 | 0 | 780000 | 0 | [6 empty] | CM_M&G | 100%
500519 | O&D- Security Measures inc Intruder Alarms | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 106171.37 | 164061.63 | 265458.89 | 259111.2 | 51277.96 | 285918.96 | 1132000.01 | 0 | 1132000.01 | 0 | [6 empty] | CM_M&G | 100%
500169 | Oban DOA (DOA001020) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-27 | 2018-03-01 | Na H-Eileanan an Iar | 0 | 9361.17 | 31552.83 | 22638.43 | 382.39 | 0 | 0.02 | 63934.84 | 0 | 63934.84 | 9047.24 | [6 empty] | EC01D | 34.08% | CS16D | 65.92%
46195 | Oban North- South TWS Refurb - TWS000580-TWS000581 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-03-27 | 2014-10-23 | 2014-10-23 | 2014-10-21 | 2014-10-23 | Argyll and Bute-North Argyll | 728722.47 | 1689.83 | 0 | 0 | 0 | 0 | 0 | 1689.83 | 0 | 730412.3 | 0 | [6 empty] | CM_WSNI | 100%
403830 | Oban North- South TWS Refurb - TWS000580-TWS000581 TR From 046195 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-06 | 2014-08-08 | 2014-08-08 | 2015-06-15 |  | Argyll and Bute-North Argyll | 162529.62 | 30105.21 | 0 | 0 | 0 | 0 | 0 | 30105.21 | 0 | 192634.83 | 0 | [6 empty] | CM_WSNI | 100%
46222 | Oban STC Refurb - STC000032 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | Argyll and Bute-North Argyll | 185037.31 | -0.31 | 0 | 0 | 0 | 0 | 0 | -0.31 | 0 | 185037 | 0 | [6 empty] | CM_WWNI | 100%
504576 | Oban Stevenson Street SPS - Refurbish Screw Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 | 2020-07-17 | 2020-10-23 | 2020-11-20 | - | 0 | 0 | 0 | 0 | 0 | 14719.63 | 210280.35 | 224999.98 | 0 | 224999.98 | 56717112.68 | [6 empty] | WWNI | 100%
46201 | Oban STW Refurb - STW000559 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | Argyll and Bute-North Argyll | 125419.25 | -0.25 | 0 | 0 | 0 | 0 | 0 | -0.25 | 0 | 125419 | 0 | [6 empty] | CM_WWNI | 100%
501168 | Ochiltree STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-04-12 | 2020-03-12 | 2020-03-23 | 2021-05-05 | 2021-08-05 | East Ayrshire | 0 | 0 | 42142.34 | 74429.76 | -5483.99 | 248391.73 | 1010612.42 | 1370092.26 | 215891.68 | 1585983.94 | 0 | [6 empty] | CM_WWNI | 100%
403798 | Old Broughty Ferry Castle Uns SO NO464304 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2014-05-14 | 2015-12-10 | 2016-01-06 | 2016-03-31 | 2016-04-30 | Dundee City | 25562 | 429532.94 | 73005.92 | 0 | -16758.31 | 0 | 0.45 | 485781 | 0 | 511343 | 30997.67 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
501381 | Old Cambus TWP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-04-30 | 2028-06-16 | 2028-10-20 | 2029-06-06 | 2029-09-06 | Scottish Borders | 0 | 0 | 7779.77 | 245.79 | 424.6 | 284.15 | -284.15 | 8450.16 | 217255.88 | 225706.04 | 0 | [6 empty] | CM_WSNI | 100%
503417 | Old Craighall ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-13 | 2023-03-15 | 2023-07-04 | 2024-02-26 | 2024-05-28 | East Lothian | 0 | 0 | 0 | 0 | 64441.86 | 11555.55 | 59273.88 | 135271.29 | 364728.76 | 500000.05 | 136478.56 | [6 empty] | SG1 | 100%
501537 | Old Kilpatrick Large SR Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-21 | 2030-01-25 | 2030-09-11 | 2030-12-12 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729210 | 729210 | 0 | [6 empty] | CM_WSNI | 100%
500772 | Old Mains Cottage Greenock Road Inchinnan Partial Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-08-10 | 2018-04-30 | 2018-05-22 | 2018-12-24 | 2018-12-24 | Renfrewshire | 0 | 23500 | 50735 | 128377.14 | 930613.86 | 112774 | 0 | 1246000 | 0 | 1246000 | 0 | [6 empty] | CM_WWI | 100%
502736 | Oldmedrum WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2020-06-18 | 2021-11-15 | 2022-03-10 | 2023-02-28 | 2023-05-31 | Aberdeenshire | 0 | 0 | 0 | 68854.88 | 90485.37 | 65493.31 | 220553.25 | 445386.81 | 6315754.2 | 6761141.01 | 136478.56 | [6 empty] | SG1 | 100%
503441 | Oldmeldrum STW - Surface Aerator Replacement & Temp SAF Install | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-01-16 | 2021-10-29 | 2022-02-25 | 2022-12-13 | 2023-03-15 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 3655.68 | 41212.44 | 44868.12 | 537834.94 | 582703.06 | 136478.56 | [6 empty] | SG1 | 100%
50016 | OMG180 Risk Adjustment | Q&S4 | Programme Risk | OMG180 Risk |  |  | General |  | SWD | OMG180 Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4097838.39 | 4097838.39 | 30000000 | [6 empty] | SR15_RSK_OMG | 100%
502248 | On Site Productivity Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MSU | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2021-01-19 | 2021-01-19 | Scottish Water Wide | 0 | 0 | 135242.6 | -242.6 | 61663.62 | 54444.4 | 0 | 251108.02 | 0 | 251108.02 | 0 | [6 empty] | CM_M&G | 100%
500850 | Onich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-11-04 | 2016-03-25 | 2016-03-28 | 2017-01-31 | 2017-11-30 | Highland | 0 | 7050 | 22977.97 | 0 | 1000.03 | -8770.07 | 0 | 22257.93 | 0 | 22257.93 | 61811.26 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 19.15
402589 | OPA Focused Delivery CID WWI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-20 | 2012-03-20 | 2012-04-02 | 2015-02-02 |  | All East Unitary Authorities | 269263.54 | 736.46 | 83.46 | 0 | 0 | 0 | 0 | 819.92 | 0 | 270083.46 | 0 | [6 empty] | CM_WWI | 100%
402590 | OPA Focused Delivery CID WWNI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2017-02-16 |  | All East Unitary Authorities | 1360489 | 54625.98 | 844.67 | 0 | -1566.87 | 0 | 1566.87 | 55470.65 | 0 | 1415959.65 | 0 | [6 empty] | CM_WWNI | 100%
401680 | Opportunistic Lead Comms Pipe Replacement - East | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2011-06-23 | 2011-06-27 | 2014-03-31 | 2014-03-31 | All East Unitary Authorities | 106189 | 0 | -355.62 | 0 | 0 | 0 | 0 | -355.62 | 0 | 105833.38 | 2131 | [6 empty] | DW1B | 100%
401681 | Opportunistic Lead Comms Pipe Replacement - North | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2012-03-15 | 2012-03-26 | 2015-03-13 | 2015-03-31 | All North Unitary Authorities | 58575.56 | 23.18 | 0 | 0 | 0 | 0 | 0 | 23.18 | 0 | 58598.74 | 216 | [6 empty] | DW1B | 100%
401679 | Opportunistic Lead Comms Pipe Replacement - South | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2012-02-10 | 2012-02-10 | 2015-03-25 | 2015-03-31 | All South Unitary Authorities | 74082 | 848 | -0.41 | -602.15 | 0 | 0 | 0 | 245.44 | 0 | 74327.44 | 2270 | [6 empty] | DW1B | 100%
401678 | Opportunistic Lead Comms Pipe Replacement - West (Forth and Clyde) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2011-10-27 | 2011-11-14 | 2014-12-15 | 2015-03-31 | All West Unitary Authorities | 125043 | 275 | -941.04 | 0 | 0 | 0 | 0 | -666.04 | 0 | 124376.96 | 1000 | [6 empty] | DW1B | 100%
500437 | OPS SVCW SR 15 Waste East Infra | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-11-27 | 2015-11-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
400732 | OPTIMISE MAINTAIN - AUDIT PRVS - EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2010-04-22 | 2010-05-03 | 2015-07-02 |  | Scottish Water Wide | 2739142 | 39075.76 | 6442.58 | 0 | 0 | 0 | 0 | 45518.34 | 0 | 2784660.34 | 0 | [6 empty] | CM_WSI | 100%
400733 | OPTIMISE MAINTAIN - AUDIT PRVS - WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2010-04-22 | 2010-05-03 | 2015-07-02 |  | Scottish Water Wide | 3534103 | -20614 | -25906.68 | 0 | 0 | 0 | 0 | -46520.68 | 0 | 3487582.32 | 0 | [6 empty] | CM_WSI | 100%
404106 | Oran Contract- 44T Tractor Units and Trailers (HGV) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-23 | 2015-03-23 | 2015-03-23 | 2016-06-23 |  | Scottish Water Wide | 434759 | 198424.15 | -21989.66 | 0 | 0 | 0 | 0 | 176434.49 | 0 | 611193.49 | 0 | [6 empty] | CM_M&G | 100%
502241 | Orbiston WWTW Legacy Sludge Removal | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS7 | 2016-06-30 | 2017-03-28 | 2017-05-11 | 2017-08-31 | 2017-11-30 | North Lanarkshire | 0 | 0 | 10327.1 | 41039.61 | 0 | 0 | 2967 | 54333.71 | 0 | 54333.71 | 0 | [6 empty] | LA01_S | 100% | bar: Regulatory Outputs OMG-24
501544 | Orkney Sludge Strategy Sanday Westray Kirbister and Boardhouse WTWs | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2027-04-02 | 2028-10-31 | 2029-03-05 | 2030-08-28 | 2030-11-28 | Orkney Islands | 0 | 23360.73 | 16088.43 | 18965.78 | 201636.68 | 87508.33 | -11559.95 | 336000 | 6600970.02 | 6936970.02 | 0 | [6 empty] | SR21_WA | 100%
502553 | Ormiston WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | East Lothian | 0 | 0 | 31033.94 | 28867.84 | 0 | 0 | 0.01 | 59901.79 | 0 | 59901.79 | 136478.56 | [6 empty] | SG1 | 100%
500576 | Orphir Village WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-07-15 | 2022-11-16 | 2023-02-07 | 2023-08-07 | 2025-01-14 | Orkney Islands | 0 | 25559.02 | 8671.97 | 33315.61 | 32356.9 | 36664.66 | -4147.06 | 132421.1 | 1667578.88 | 1799999.98 | 136478.56 | [6 empty] | SG1 | 100%
403606 | Outcome of Failure Implementation Plans FPP Needs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-11-11 | 2013-11-21 | 2014-04-01 | 2016-12-19 |  | All East Unitary Authorities | 303821 | -54625 | -25540.49 | 256.8 | 0 | 0 | 0 | -79908.69 | 0 | 223912.31 | 0 | [6 empty] | CM_WWNI | 100%
403669 | Overton DSR Improvements to Inlet Arrangement | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2014-08-18 | 2015-06-30 | 2015-10-26 | 2017-08-28 | 2017-08-28 | Aberdeen City | 7020 | 162390 | 163864.24 | 141725.76 | -8572.72 | -4377.56 | 0 | 455029.72 | 0 | 462049.72 | 0 | [6 empty] | CM_WSNI | 7.336% | WG5 | 92.66%
502282 | Oykel Bridge - Radon | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-06-28 | 2021-02-01 | 2021-05-10 |  |  | Highland | 0 | 0 | 24636.03 | 9100.5 | 13363.47 | 0 | 54900.5 | 102000.5 | 522999.55 | 625000.05 | 525664.36 | [6 empty] | DW25P | 100%
504213 | Oykel Bridge WTW - Temporary TWS | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2019-06-28 | 2020-04-13 | 2020-07-20 | 2020-04-01 | 2020-04-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
45358 | Oykel Bridge WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-02-13 | 2012-05-14 | 2014-09-16 | 2014-11-21 | Highland | 334827.49 | -238.97 | 0 | 0 | 0 | 0 | 0 | -238.97 | 0 | 334588.52 | 2774 | [6 empty] | DW13 | 100%
403271 | PACE Phase 2 Spend to Save | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-14 | 2013-06-14 | 2013-06-14 | 2016-05-31 |  | Scottish Water Wide | 2799601.53 | 68081.42 | -112.98 | 0 | 0 | 0 | 0 | 67968.44 | 0 | 2867569.97 | 0 | [6 empty] | CM_WWNI | 100%
402687 | Package B - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-05-28 | 2012-09-26 | 2013-01-31 | 2014-12-18 | 2014-12-24 | Scottish Water Wide | 2806579.54 | -36028.04 | -15610.49 | 0 | 0 | 0 | 0 | -51638.53 | 0 | 2754941.01 | 9187 | [6 empty] | DW9A | 100%
402888 | Package C - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 2055446.39 | 1942792.55 | 292518.37 | -4886.64 | 0 | 0 | 0 | 2230424.28 | 0 | 4285870.67 | 761868.94 | [6 empty] | CM_WSNI | 48% | DW9A | 52%
402889 | Package D - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-25 | 2016-03-25 | Scottish Water Wide | 4210597.59 | 4551823.44 | 1395787.56 | 473.15 | -220 | 0 | 217 | 5948081.15 | 0 | 10158678.74 | 3314681.22 | [6 empty] | CM_WSNI | 45.1% | DW9A | 54.9%
402890 | Package E - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-16 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 3308494.47 | 3544477.05 | 1443347.04 | 1747.15 | 0 | 0 | 0 | 4989571.24 | 0 | 8298065.71 | 2227468.82 | [6 empty] | DW9E | 0.1% | CM_WSNI | 48% | DW9A | 51.9%
402891 | Package F - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-10 | 2013-02-12 | 2013-02-13 | 2013-05-29 | 2013-06-24 | Scottish Water Wide | 197486.97 | -6975 | 0 | 0 | 0 | 0 | 0 | -6975 | 0 | 190511.97 | 1282 | [6 empty] | DW9A | 100%
402892 | Package G - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-30 | 2016-03-31 | Scottish Water Wide | 1740881.26 | 1731310.81 | 1010501.84 | 77188.59 | -45975.02 | 0 | 0 | 2773026.22 | 0 | 4513907.48 | 1446743 | [6 empty] | DW9E | 2.9% | CM_WSNI | 48% | DW9A | 49.1%
501742 | Paisley Road Barrhead - Reline sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-06-19 | 2017-06-19 | 2017-06-19 | 2017-05-29 | 2017-05-29 | Renfrewshire | 0 | 0 | 2347.55 | 3213.47 | 125.79 | 0 | -2824.81 | 2862 | 0 | 2862 | 0 | [6 empty] | CM_WWI | 100%
46333 | Palnackie Septic Tank No.1 (Harbour) - STW000563 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-25 | 2010-07-26 | 2013-03-25 | 2014-09-09 | 2014-09-09 | Dumfries and Galloway | 1159027.88 | 14945.96 | -1006.43 | 4 | 0 | 0 | 0 | 13943.53 | 0 | 1172971.41 | 136478.56 | [6 empty] | SG1 | 24.98% | CM_WWNI | 75.02%
501155 | Pan Rocks SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-12-14 | 2017-03-28 | 2017-06-23 | 2019-01-31 | 2019-01-31 | South Ayrshire | 0 | 8800.42 | 221686.58 | 744670 | 374928 | 26911 | 2254 | 1379250 | 0 | 1379250 | 0 | [6 empty] | CM_WWNI | 100%
502953 | Papa Stour Water supply | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS4 | 2016-09-28 | 2019-03-27 | 2019-06-28 | 2019-12-31 | 2021-03-26 | Shetland Islands | 0 | 0 | 0 | 20542.96 | 143986.01 | 253484.33 | 1197.7 | 419211 | 1439.4 | 420650.4 | 600729.56 |  |  |  |  | 840.94 |  | DW2 | 2.22% | DW23 | 48.89% | DW25P | 48.89% | bar: Regulatory Outputs OMG-01
403567 | Park Crescent Torrance | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-08-30 | 2014-12-11 | 2015-02-04 | 2015-07-16 | 2016-03-10 | East Dunbartonshire | 323184 | 120116 | 5000 | 0 | 159424.79 | 0 | 0.21 | 284541 | 0 | 607725 | 338633.31 | [6 empty] | CS11 | 100%
504212 | Partick PS - Front Elevation remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-12-08 |  | 2020-12-08 |  | - | 0 | 0 | 0 | 0 | 0 | 249.41 | 24250.6 | 24500.01 | 0 | 24500.01 | 0 | [6 empty] | CM_WWNI | 100%
46194 | Partick SPS Refurb - SPS000366 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-17 | 2011-06-14 | 2011-08-22 | 2013-12-30 | 2014-02-25 | Glasgow City | 2957266.32 | 50697.84 | 0 | 0 | 0 | 0 | 0 | 50697.84 | 0 | 3007964.16 | 0 | [6 empty] | CM_WWNI | 100%
501545 | Pateshill Raw Water Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2016-01-27 | 2021-11-08 | 2022-03-10 | 2022-10-17 | 2023-01-17 | West Lothian | 0 | 3689 | 18453.17 | 0 | 0 | 203.84 | 0 | 22346.01 | 327653.99 | 350000 | 0 | [6 empty] | CM_WSNI | 100%
501750 | Pateshill WTW - OMG4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-29 | 2016-03-07 | 2016-03-07 | 2016-03-31 | 2016-03-31 | West Lothian | 0 | 2462 | 7684.64 | 228.75 | 0 | 0 | -228.75 | 10146.64 | 0 | 10146.64 | 1773.42 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501389 | Pateshill WTW (Westwater Reservoir) Algae | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-04-13 | 2028-08-17 | 2029-04-03 | 2029-07-04 | West Lothian | 0 | 0 | 10046.51 | 0 | 638.7 | 0 | 0 | 10685.21 | 489314.82 | 500000.03 | 0 | [6 empty] | CM_WSNI | 100%
501397 | Pateshill WTW Raw Water Mains | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-09-21 | 2028-07-17 | 2028-10-12 | 2029-11-09 | 2030-02-11 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059117.01 | 1059117.01 | 0 | [6 empty] | CM_WSI | 100%
46822 | Pateshill WTW Refurb - WTW000626 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-05-07 | 2012-02-28 | 2012-08-20 | 2014-09-29 | 2015-11-02 | West Lothian | 3031467.15 | -20087.4 | -3417.05 | 0 | 0 | 0 | 0 | -23504.45 | 0 | 3007962.7 | 0 | [6 empty] | CM_WSNI | 100%
503440 | Pathhead WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-28 | 2023-05-19 | 2023-09-21 | 2024-04-17 | 2024-07-18 | Midlothian | 0 | 0 | 0 | 0 | 59441.86 | 39733.04 | 55660.58 | 154835.48 | 595164.52 | 750000 | 136478.56 | [6 empty] | SG1 | 100%
503544 | Patna WwTW Bathing Water Improvement | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2021-04-06 | 2021-10-18 | 2022-01-17 | 2023-02-09 | 2023-05-12 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 27.55 | -27.55 | 0 | 4882689.98 | 4882689.98 | 2277461.36 | [6 empty] | EC16B | 100%
501499 | PATNA WWTW NS414124 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS1 | 2016-07-11 | 2020-06-29 | 2020-09-17 | 2021-09-03 | 2021-12-06 | East Ayrshire | 0 | 0 | 43306.86 | 205553.08 | 24944.82 | 163347.24 | 1517716.37 | 1954868.37 | 922750.63 | 2877619 | 0 | [6 empty] | CM_WWNI | 100%
502865 | Payroll Oracle Cloud Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2019-02-18 | 2019-02-18 | Scottish Water Wide | 0 | 0 | 0 | 393561.79 | 513769.58 | -2039.38 | 0 | 905291.99 | 0 | 905291.99 | 0 | [6 empty] | CM_M&G | 100%
403698 | PCCA Zone Rationalisation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-02-27 | 2016-07-29 | 2016-02-16 | 2015-10-30 |  | Scottish Water Wide | 74499 | 10759.1 | 175.36 | 0 | 0 | 0 | 0 | 10934.46 | 0 | 85433.46 | 0 | [6 empty] | CM_WSI | 100%
502434 | Peat Inn & Denhead DMA - Cameron Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-06-30 | 2028-04-18 | 2028-07-24 | 2029-02-16 | 2029-02-16 | Fife | 0 | 0 | 4764.74 | 365.02 | 21.29 | 2898.07 | 0 | 8049.12 | 366950.88 | 375000 | 0 | [6 empty] | CM_WSI | 100%
403973 | Peebles WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-07-11 | 2018-11-05 | 2018-11-27 | 2020-04-13 | 2020-07-03 | Scottish Borders | 2866.55 | 29088.45 | 75422.73 | 271147.21 | 1451750.32 | 1693906.75 | 9838.99 | 3531154.45 | 53534 | 3587555 | 0 | [6 empty] | SG1 | 100%
502613 | Pelstream Burn Crossing Stirling | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-08-28 | 2019-02-26 | 2019-06-10 | 2019-09-26 | 2019-09-26 | Stirling | 0 | 0 | 1551.36 | 34662.64 | 73751 | 81992.31 | -890.81 | 191066.5 | 933.5 | 192000 | 0 | [6 empty] | CM_WWI | 100%
502554 | Pencaitland WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-04-15 | 2022-08-17 | 2022-12-20 | 2023-12-18 | 2024-03-19 | East Lothian | 0 | 0 | 34581.06 | 9386.07 | 5741.56 | 3520.05 | 0 | 53228.74 | 81771.26 | 135000 | 136478.56 | [6 empty] | SG1 | 100%
500171 | Penicuik DOA (DOA000526) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-06-29 | 2018-01-30 | Midlothian | 0 | 5000 | 33648 | 18769 | -3380.38 | 0 | 0 | 54036.62 | 0 | 54036.62 | 88483.35 | [6 empty] | EC01D | 7.47% | CS16D | 18.51% | EC01G | 37.01% | EC10E | 37.01%
30573 | Penicuik STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-17 | 2010-09-20 | 2011-03-15 | 2012-01-27 | 2012-02-10 | Midlothian | 568855.38 | -13342.3 | 0 | 0 | 0 | 0 | 0 | -13342.3 | 0 | 555513.08 | 0 | [6 empty] | CM_WWNI | 20% | EC01A | 80%
502810 | Penicuik WWTW - Aeration Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2017-08-01 | 2017-08-01 | 2018-03-30 | 2019-11-28 | 2020-04-01 | Midlothian | 0 | 0 | 0 | 43591.23 | 236038.7 | 267627.15 | 15264.21 | 562521.29 | 3703.71 | 566225 | 0 | [6 empty] | CM_WWNI | 100%
503223 | Penicuik WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-05-13 | 2022-10-19 | 2023-02-20 | 2024-02-15 | 2024-05-17 | Midlothian | 0 | 0 | 0 | 0 | 83888.74 | 36338.47 | 21042.84 | 141270.05 | 1858729.94 | 1999999.99 | 136478.56 | [6 empty] | SG1 | 100%
45570 | Peninver WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2011-09-28 | 2012-07-18 | 2013-09-10 | 2014-01-27 | Argyll and Bute-North Argyll | 1105298.15 | -6287.87 | 0 | 0 | 0 | 0 | 0 | -6287.87 | 0 | 1099010.28 | 2725 | [6 empty] | DW23 | 100%
501501 | Pentland & Slaemuir Ave Port Glasgow - Replace sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-22 | 2017-12-18 | 2018-02-09 | 2019-08-30 | 2019-08-30 | Inverclyde | 0 | 3342.34 | 7037.66 | 181877.63 | 608155.24 | 172688.13 | 181 | 973282 | 1718 | 975000 | 0 | [6 empty] | CM_WWI | 100%
403359 | Penwhapple Reservoir - Spillway Improvement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-29 | 2014-07-31 | 2014-07-31 | 2015-03-30 | 2015-04-29 | South Ayrshire | 2427033.35 | 113007.6 | 3211.91 | 12834.76 | 0 | 0 | 0 | 129054.27 | 0 | 2556087.62 | 0 | [6 empty] | CM_WSI | 100%
501575 | Penwhapple WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-12 | 2017-03-06 | 2017-03-06 | 2017-08-31 | 2017-10-31 | South Ayrshire | 0 | 0.07 | 1073.31 | 676.04 | 0.01 | 0 | 0 | 1749.43 | 0 | 1749.43 | 105615.47 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
503742 | Penwhapple WTW - Performance Improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-10-03 | 2020-11-23 | 2021-01-29 | 2021-09-07 | 2021-10-29 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 4053.13 | 257904.07 | 261957.2 | 238042.8 | 500000 | 0 | [6 empty] | CM_WSNI | 100%
503356 | Penwhirn WTW - Additional Hypochlorite Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-03-12 | 2021-03-01 | 2021-04-26 | 2021-09-20 | 2021-12-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 1962.62 | 31784.98 | 113355.84 | 147103.44 | 237896.51 | 384999.95 | 0 | [6 empty] | CM_WSNI | 100%
502636 | Perkhill Road Lumphanan | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-17 | 2017-07-25 | 2017-07-28 | 2017-08-30 | 2017-08-30 | Aberdeenshire | 0 | 0 | 468.32 | 5753.75 | 0 | 0 | 0.24 | 6222.31 | 0 | 6222.31 | 43684.09 | [6 empty] | CS23W | 100%
501099 | Perth & Kinross Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-01-22 | 2016-03-01 | 2016-03-04 | 2016-03-04 | Perth and Kinross | 0 | 2071.38 | 306.66 | 0 | 0 | 0 | 0 | 2378.04 | 0 | 2378.04 | 0 | [6 empty] | EC10D | 100%
500168 | Perth City DOA (DOA000674) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS5 | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-30 | 2020-01-08 | Perth and Kinross | 0 | 33270 | 284033 | 473530 | 193883.24 | 78221.76 | 36062 | 1099000 | 0 | 1099000 | 349451.88 | [6 empty] | CS11 | 19.85% | CS16D | 80.15%
45633 | Perth City STW Refurb - STW001712 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-06-28 | 2011-09-30 | 2013-03-28 |  | Perth and Kinross | 1974705.5 | -6148.15 | -1044.45 | 0 | 0 | 0 | 0 | -7192.6 | 0 | 1967512.9 | 0 | [6 empty] | CM_WWNI | 100%
500635 | Perth City WwTW - Upgrade Access Road (Lower Friarton) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-20 | 2016-11-21 | 2016-11-21 | 2017-05-29 | 2017-05-29 | Perth and Kinross | 0 | 101145 | 389458.35 | 151578.6 | 29848.55 | -936.13 | 0 | 671094.37 | 0 | 671094.37 | 0 | [6 empty] | CM_WWNI | 100%
502067 | Perth City WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-06-15 | 2020-11-06 | 2021-02-24 | 2021-05-27 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 9824 | 499431.69 | 509255.69 | 29104.33 | 538360.02 | 0 | [6 empty] | SR21_WW | 100%
500210 | Perth- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2019-03-15 | 2019-09-30 | Perth and Kinross | 0 | 1000 | 29934 | 206004 | 403391.82 | 93913.44 | -2395.13 | 731848.13 | 0 | 731848.13 | 323388.43 | [6 empty] | DW5 | 100%
45801 | Perth Friarton SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-07-29 | 2011-08-09 | 2011-07-01 | 2011-07-01 | Perth and Kinross | 43397.64 | 4105.34 | 0 | 0 | 0 | 0 | 0 | 4105.34 | 0 | 47502.98 | 0 | [6 empty] | CM_WWNI | 8.488% | WQ01C | 91.51%
500868 | Perth RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-03-09 | 2018-09-18 | 2018-10-24 | 2019-09-30 | 2020-10-07 | Perth and Kinross | 0 | 19786.85 | 7325.15 | 24264.45 | 87513.77 | 81837.38 | 6575.5 | 227303.1 | 0 | 227303.1 | 582864.01 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 52.71
503690 | Perth RWI - River Anti Pollution Measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2020-10-02 | 2022-06-03 | 2022-10-06 | 2024-05-01 | 2024-06-24 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 58718.36 | 39610.95 | 98329.31 | 351670.71 | 450000.02 | 0 | [6 empty] | CM_WSI | 100%
502933 | Perth STC - Enabling Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-10-31 | 2018-07-04 | 2018-11-26 | 2020-09-25 | 2020-09-28 | Perth and Kinross | 0 | 0 | 0 | 4549.71 | 285639.79 | 278114.79 | 16866.75 | 585171.04 | 3266.38 | 588437.42 | 0 | [6 empty] | CM_WWNI | 100%
46745 | Perth STW - Enhancement of Sludge Treatment Facilities | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-16 | 2011-06-28 | 2011-09-30 | 2013-11-28 | 2014-01-27 | Perth and Kinross | 7874424.69 | -54121.36 | 20288.55 | 0 | 0 | 0 | 0 | -33832.81 | 0 | 7840591.88 | 81872 | [6 empty] | EC06 | 100%
402012 | Perth WWTW Inlet SPS | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-04-11 | 2014-07-02 | 2014-07-02 | 2015-03-18 | 2015-03-19 | Perth and Kinross | 2527497.73 | 113186.6 | 26203.18 | 0 | 0 | 0 | 0 | 139389.78 | 0 | 2666887.51 | 279674 | [6 empty] | WQ01C | 100%
504736 | Peterhead Buchanhaven WWPS Penstock service/repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-02-22 | 2020-05-22 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 20972 | 5893.56 | 26865.56 | 0 | 26865.56 | 0 | [6 empty] | CM_WWNI | 100%
500172 | Peterhead DOA (DOA000361) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-31 | 2016-08-08 | 2018-09-30 | 2018-11-30 | Aberdeenshire | 0 | 32752 | 18476.81 | 61423.19 | 56589 | 9825.37 | -42.99 | 179023.38 | 0 | 179023.38 | 10344.04 | [6 empty] | EC01G | 10.35% | CS16D | 89.65% | bar: Regulatory Outputs OMG-22
46258 | Peterhead Newfield WPS SR10 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-03-30 | 2009-02-17 | 2011-09-05 | 2012-03-29 |  | Aberdeenshire | 448551.62 | 620 | 0 | 0 | 0 | 0 | 0 | 620 | 0 | 449171.62 | 0 | [6 empty] | CM_WSNI | 100%
403277 | Ph 3 East Dunfermline WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-05-21 | 2015-03-26 | 2015-07-08 | 2015-12-04 |  | Fife | 283861.46 | 753282.18 | 2455.31 | 809.46 | 0 | 0 | 0 | 756546.95 | 0 | 1040408.41 | 0 | [6 empty] | CM_WWNI | 100%
403278 | Ph 3 East Fochabers WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-08 | 2014-08-13 | 2014-08-13 | 2014-08-14 |  | Moray | 126036.93 | -33.92 | 0 | 0 | 0 | 0 | 0 | -33.92 | 0 | 126003.01 | 0 | [6 empty] | CM_WWNI | 100%
403280 | Ph 3 East Forres WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-01-10 | 2015-09-22 | 2015-09-16 | 2015-04-21 | 2015-04-21 | Moray | 191256 | 5254.57 | 0 | 0 | 0 | 0 | 0 | 5254.57 | 0 | 196510.57 | 0 | [6 empty] | CM_WWNI | 100%
403279 | Ph 3 Head of Works STC Kirkwall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-01 | 2014-06-30 | 2014-04-16 | 2014-04-16 |  | Orkney Islands | 83247.73 | 3183.73 | 0 | 0 | 0 | 0 | 0 | 3183.73 | 0 | 86431.46 | 0 | [6 empty] | CM_WWNI | 100%
500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS5 | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-31 | 2020-01-08 | South Lanarkshire | 0 | 73937.35 | 308628.65 | 234930 | 117125 | 70300 | 10654 | 815575 | 0 | 815575 | 349451.88 | [6 empty] | CS11 | 18.97% | CS16D | 81.03%
402987 | Philipshill Storm Return Pumping Station | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-30 | 2013-03-05 | 2013-03-18 | 2015-09-21 |  | South Lanarkshire | 258787 | 5450 | 0.31 | -3186.45 | 0 | 0 | 0 | 2263.86 | 0 | 261050.86 | 0 | [6 empty] | CM_WWI | 100%
46355 | Philipshill STW Refurb - STW000576 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-06-01 | 2011-09-21 | 2011-10-31 | 2016-02-16 |  | South Lanarkshire | 2838709.32 | 13753.03 | -16535.04 | 600.6 | 0 | 0 | 0 | -2181.41 | 0 | 2836527.91 | 0 | [6 empty] | CM_WWNI | 100%
503224 | Philipshill WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-15 | 2023-08-28 | 2023-12-21 | 2024-12-17 | 2025-03-19 | South Lanarkshire | 0 | 0 | 0 | 0 | 65219.25 | 746.42 | 55490.52 | 121456.19 | 1878543.82 | 2000000.01 | 136478.56 | [6 empty] | SG1 | 100%
502691 | Philipshill WWTW - Phase B Aeration replacement - 5026910000 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2028-05-26 | 2028-09-18 | 2029-04-30 | 2029-07-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1785 | 1785 | 248465.09 | 250250.09 | 0 | [6 empty] | CM_WWNI | 100%
501807 | Philipshill WWTW Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-16 | 2020-06-15 | 2020-08-17 | 2021-02-17 | 2021-02-17 | South Lanarkshire | 0 | 0 | 6082.77 | 204.16 | 0 | 26362.07 | 195093 | 227742 | 10681.93 | 238423.93 | 0 | [6 empty] | SR21_WW | 100%
500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-06-27 | 2020-08-14 | East Renfrewshire | 0 | 38753 | 47802.42 | 79902.25 | 81330.83 | 54709.26 | 33738.25 | 336236.01 | 0 | 336236.01 | 2107629.1 | [6 empty] | DW5FS | 100%
500869 | Picketlaw RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-04-12 | 2017-03-30 | 2017-03-31 | 2018-08-31 | 2018-12-31 | East Renfrewshire | 0 | 2671.71 | 7621.29 | 98587 | 54146.78 | -9429.05 | 3911.94 | 157509.67 | 0 | 157509.67 | 242534.78 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 54.04
501214 | Picketlaw WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-21 | 2016-09-06 | 2016-09-07 | 2016-09-30 | 2016-09-30 | South Lanarkshire | 0 | 761.13 | 1179.66 | 207.95 | 0 | 0 | 0 | 2148.74 | 0 | 2148.74 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503624 | Picketlaw WTW - Drought Operations 2019 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-04-01 | 2020-07-20 | 2020-09-07 | 2021-04-29 | 2021-06-22 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 214495.89 | 214495.89 | 35504.14 | 250000.03 | 0 | [6 empty] | CM_WSNI | 100%
505248 | Picketlaw WTW - Investigation on Chemical Spill Tank Ingress | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-05-26 | 2020-08-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 87.76 | 9912.24 | 10000 | 0 | 10000 | 0 | [6 empty] | WSNI | 100%
404132 | Picketlaw WTW - Main Out | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS3 | 2013-06-30 | 2016-01-31 | 2016-02-29 | 2021-08-30 | 2021-11-28 | East Renfrewshire | 0 | 0 | 11661.8 | 76869.1 | 243010.9 | -34218.01 | 669067.76 | 966391.55 | 4533608.45 | 5500000 | 0 | [6 empty] | DW25 | 100% | bar: Regulatory Outputs OMG-03
503550 | Picketlaw WTW - Purchase Install & Commission Polymer Dosing Equipment | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-04-01 | 2021-05-10 | 2021-09-09 | 2022-10-19 | 2023-01-19 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 33628.1 | 33628.1 | 226371.9 | 260000 | 0 | [6 empty] | CM_WSNI | 100%
505250 | Picketlaw WTW S14 & S15 Chambers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-05-30 | 2020-07-31 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 1351.62 | 6157.38 | 7509 | 0 | 7509 | 0 | [6 empty] | WSNI | 100%
500671 | Pier Road Balloch Sewer Replacment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-06-11 | 2017-01-30 | 2017-02-20 | 2017-10-27 | 2017-10-27 | West Dunbartonshire | 0 | 22800 | 185033 | 51130 | -5687 | 1240.33 | -0.33 | 254516 | 0 | 254516 | 0 | [6 empty] | CM_WWI | 100%
501658 | Pier Road-Cromlech Road Dunoon - Relay sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2027-06-11 | 2028-04-03 | 2028-06-29 | 2029-01-29 | 2029-05-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 3834.94 | 526.76 | 12186.85 | 9.24 | -557.78 | 16000.01 | 121527.03 | 137527.04 | 0 | [6 empty] | SR21_WW | 100%
502209 | Pipebridge H&S Improvements East Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-05-09 | 2016-08-01 | 2016-09-30 | 2022-03-29 | 2022-03-30 | Scottish Water Wide | 0 | 0 | 439137.02 | 938796.76 | 543444.37 | 277630.25 | -7363.02 | 2191645.38 | 108354.63 | 2300000.01 | 0 | [6 empty] | CM_M&G | 100%
502201 | Pipebridge H&S Improvements North Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-04-18 | 2016-11-21 | 2017-07-04 |  | 2020-02-21 | Scottish Water Wide | 0 | 0 | 69618.94 | 74409.97 | 84999.06 | 362031.04 | 2784.46 | 593843.47 | 2025.06 | 595868.53 | 0 | [6 empty] | CM_M&G | 100%
502202 | Pipebridge H&S Improvements South Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-05-04 | 2016-08-30 | 2016-10-25 | 2021-12-28 | 2021-12-28 | Scottish Water Wide | 0 | 0 | 83884.46 | 568627.74 | 683256 | 315070.62 | 342414.21 | 1993253.03 | 144848.54 | 2138101.57 | 0 | [6 empty] | CM_M&G | 100%
502203 | Pipebridge H&S Improvements West Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-04-18 | 2016-08-30 | 2016-11-28 | 2021-12-16 | 2022-03-18 | Scottish Water Wide | 0 | 0 | 127858.7 | 544404.81 | 517974.26 | 444174.09 | 543912.14 | 2178324 | 90665.25 | 2268989.25 | 0 | [6 empty] | CM_M&G | 100%
501611 | PITENWEEM WEST SHORE WWPS NO547024 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2028-02-21 | 2028-12-20 | 2029-04-25 | 2029-09-04 | 2029-12-05 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141670.99 | 141670.99 | 0 | [6 empty] | CM_WWNI | 100%
500967 | Pitscottie WwPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2015-10-21 | 2018-03-14 | 2018-05-23 | 2020-02-14 | 2020-02-14 | Fife | 0 | 7151.89 | 17447.11 | 184000 | 514970.76 | 69299.12 | 9215.12 | 802084 | 1410 | 803494 | 0 | [6 empty] | CM_WWNI | 100%
403625 | Pittenweem Model Build | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-12-17 | 2014-04-23 | 2014-04-29 | 2015-01-23 |  | Fife | 116099 | 6614.1 | 0 | 0 | 0 | 0 | 4660.66 | 11274.76 | 0 | 127373.76 | 0 | [6 empty] | CM_WWI | 100%
30585 | Plains STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2012-05-29 | 2012-08-20 | 2014-08-14 | 2014-09-29 | North Lanarkshire | 8537337.19 | 32812.02 | 55334.5 | 0 | 0 | 0 | 0 | 88146.52 | 0 | 8625483.71 | 222231.92 | [6 empty] | CM_WWNI | 5% | SG1 | 5% | EC10A | 40% | EC04A | 50%
502543 | Plains WwTW DOA - Moffat View Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-02-23 | 2017-02-23 | 2017-03-01 | 2017-03-31 | 2017-03-31 | North Lanarkshire | 0 | 0 | 42523.36 | 820908.49 | -690.74 | 300.68 | -300.68 | 862741.11 | 0 | 862741.11 | 0 | [6 empty] | CM_WWI | 100%
404010 | Plan Attainment- Cost of Failure | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-03-29 | 2017-04-03 | 2017-04-03 | 2017-04-03 |  | Scottish Water Wide | 173465.68 | 56598.32 | -939.21 | 0 | 0 | 0 | 0 | 55659.11 | 0 | 229124.79 | 0 | [6 empty] | CM_M&G | 100%
501223 | Planned Cleaning Programme - PCP | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-22 | 2016-05-18 | 2017-06-26 | 2021-06-09 | 2021-06-09 | Scottish Water Wide | 0 | 33776.17 | 143894.46 | 18189.12 | 287613.25 | -140940.57 | 1134317.38 | 1476849.81 | 0 | 1476849.81 | 0 | [6 empty] | CM_WWI | 100%
500708 | Planned Preventative Maintenance (Flushing & Swabbing) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2017-01-11 | 2017-01-27 | Scottish Water Wide | 0 | 2662000 | 226225.11 | 17415.43 | 0 | 0 | 0 | 2905640.54 | 0 | 2905640.54 | 0 | [6 empty] | CM_WSI | 100%
502675 | Planned Preventative Maintenance (Year 3) 2017 to 2018 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-08-30 | 2017-09-26 | 2017-09-26 | 2020-07-10 | 2020-07-10 | Scottish Water Wide | 0 | 0 | 0 | 2626405.26 | 2300251.78 | -1647730.68 | -577269.32 | 2701657.04 | 0 | 2701657.04 | 0 | [6 empty] | CM_WSI | 100%
503059 | Planned Preventative Maintenance (Year 4) 2018 to 2019 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-03-12 | 2019-03-28 | 2019-03-28 | 2020-09-21 | 2021-01-28 | Scottish Water Wide | 0 | 0 | 0 | 3753.5 | 109964.69 | 1797653.63 | 1251628.18 | 3163000 | 0 | 3163000 | 0 | [6 empty] | CM_WSI | 100%
502261 | Planned Preventative Maintenance Year 2 (2016 - 2017) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-07-13 | 2016-07-13 | 2016-08-01 | 2020-08-25 | 2020-08-25 | Scottish Water Wide | 0 | 0 | 1342187.81 | 922812.19 | 0 | 55.1 | -55.1 | 2265000 | 0 | 2265000 | 0 | [6 empty] | CM_WSI | 100%
501718 | Plantation Avenue Patna - Relay sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-10-21 | 2016-11-17 | East Ayrshire | 0 | 0 | 3313.17 | 0 | 0 | 0 | -0.17 | 3313 | 0 | 3313 | 0 | [6 empty] | CM_WWI | 100%
502319 | PMAP - Pollution Management Action Plan - Year 2 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2016-08-23 | 2016-08-23 | 2016-10-26 | 2017-09-25 | 2017-09-25 | Scottish Water Wide | 0 | 0 | 886608.99 | 277965.1 | 391.69 | -307.91 | 0 | 1164657.87 | 0 | 1164657.87 | 1830849.77 | [6 empty] | SG5 | 100%
505612 | PMAP - Pollution Management Action Plan - Year 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2020-04-01 | 2020-03-30 | 2021-04-13 | 2021-10-12 | 2022-01-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 0 | 700000 | 0 | [6 empty] | CM_WWI | 100%
502715 | PMAP - Pollution Management Action Plan Yr3 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2017-05-04 | 2017-05-04 | 2017-06-01 | 2018-10-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 887640.95 | 245976.99 | -22958.36 | -177.22 | 1110482.36 | 0 | 1110482.36 | 1830849.77 | [6 empty] | SG5 | 100%
503130 | PMAP - Pollution Management Action Plan Yr4 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS5 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2019-07-15 | 2019-07-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 575695.62 | 19293.38 | 17.45 | 595006.45 | 0 | 595006.45 | 1830849.77 | [6 empty] | SG5 | 100%
503560 | PMAP - Pollution Management Action Plan Yr5 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS3 | 2019-03-26 | 2019-03-26 | 2019-06-03 |  | 2020-06-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 550000 | 120000 | 670000 | 0 | 670000 | 1830849.77 | [6 empty] | SG5 | 100%
501296 | PMAP Holding Line - SR15 Yr2-6 -Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 20.22 | 0 | 0 | 0 | 20.22 | 0 | 20.22 | 1830849.77 | [6 empty] | SG5 | 100%
46411 | Pollocktown PS Refurb - TWP000189 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-20 | 2011-12-29 | 2011-12-19 |  | East Renfrewshire | 40766.39 | 3291.78 | 0 | 0 | 0 | 0 | 0 | 3291.78 | 0 | 44058.17 | 0 | [6 empty] | CM_WSNI | 100%
500433 | Pollution Management Action Plan | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-11 | 2016-09-22 | 2016-09-22 | Scottish Water Wide | 0 | 984391 | -25695.61 | 431.52 | 0 | 0 | 3944.48 | 963071.39 | 0 | 963071.39 | 0 | [6 empty] | CM_WWI | 100%
500908 | Poolewe WOA Melvaig South SR (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-06-30 | 2016-06-30 | Argyll and Bute-North Argyll | 0 | 3010 | -149.81 | 0 | 0 | 0 | 0 | 2860.19 | 0 | 2860.19 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502838 | Poolewe WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2027-04-02 | 2028-08-24 | 2028-12-22 | 2020-03-31 | 2030-03-21 | Highland | 0 | 0 | 0 | 21346.13 | 1340.34 | 0 | -19665.74 | 3020.73 | 0 | 3020.73 | 136478.56 | [6 empty] | WG1 | 100%
403415 | Port Appin Septic Tank and Outfall Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-12-05 | 2015-01-12 |  | Argyll and Bute-North Argyll | 286000 | 0 | -2765.58 | 0 | 0 | 0 | 0 | -2765.58 | 0 | 283234.42 | 0 | [6 empty] | CM_WWI | 40.15% | CM_WWNI | 59.85%
504012 | Port Charlotte Caustic Dosing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | GW1 |  | 2020-09-14 | 2020-10-02 | 2021-01-14 | 2021-02-11 | - | 0 | 0 | 0 | 0 | 0 | 22960.36 | 147039.64 | 170000 | 0 | 170000 | 0 | [6 empty] | WSI | 100%
502368 | Port Charlotte Clear Water Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-03 | 2028-10-16 | 2029-02-16 | 2030-09-12 | 2030-12-13 | Argyll and Bute-North Argyll | 0 | 0 | 35762.48 | 33128.44 | 1957.09 | 13437.92 | 0 | 84285.93 | 1387971.09 | 1472257.02 | 0 | [6 empty] | CM_WSNI | 100%
502131 | Port Charlotte STW Outfall Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | Argyll and Bute-North Argyll | 0 | 0 | 18464.01 | 0 | 0 | 0 | 0.01 | 18464.02 | 0 | 18464.02 | 0 | [6 empty] | CM_WWI | 100%
500776 | Port Charlotte WOA Conisby SR Abandonment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-08-24 | 2020-04-22 | 2019-06-03 | 2019-06-03 | 2019-06-03 | Argyll and Bute-North Argyll | 0 | 28311 | 68658.02 | 10961.58 | -38615.8 | 30768.27 | -3818.42 | 96264.65 | 0 | 96264.65 | 0 | [6 empty] | CM_WSNI | 100%
403020 | Port Charlotte WTW Chemical Dosing Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-10-30 | 2012-10-30 | 2012-12-03 | 2013-11-22 |  | Argyll and Bute-Cowal & Bute | 414439 | 214.68 | 0 | 0 | 0 | 0 | 0 | 214.68 | 0 | 414653.68 | 0 | [6 empty] | CM_WSNI | 100%
502869 | Port Charlotte WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2027-04-02 | 2028-08-17 | 2028-12-08 | 2029-11-30 | 2030-03-04 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21238 | 3195.35 | 5533.21 | -14424.11 | 15542.45 | 0 | 15542.45 | 136478.56 | [6 empty] | WG1 | 100%
501378 | Port Ellen TPS1 Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-04-12 | 2017-06-20 | 2017-06-26 | 2018-03-07 | 2018-03-07 | Argyll and Bute-North Argyll | 0 | 0 | 93085 | 721499 | -4316.51 | -18855.03 | 0 | 791412.46 | 0 | 791412.46 | 0 | [6 empty] | CM_WWI | 100%
403431 | Port Glasgow Road Kilmacolm | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2013-04-16 | 2019-03-26 | 2019-06-24 | 2020-04-01 | 2020-07-07 | Renfrewshire | 44912.9 | 47506.97 | 43854.13 | 67779 | 441132 | 1867472.4 | 87188.38 | 2554932.88 | 0 | 2599845.78 | 204193.13 |  |  |  |  | 8180 |  | CS11 | 100%
404095 | Portfolio Acceleration Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-12-24 | 2015-02-19 | 2015-02-19 | 2016-06-14 |  | Scottish Water Wide | 199676 | 877400.01 | -20923.38 | 0 | 0 | 0 | 0 | 856476.63 | 0 | 1056152.63 | 0 | [6 empty] | CM_M&G | 100%
501577 | Portfolio Programme and Project Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2017-02-28 | 2018-04-30 | 2018-04-30 | 2020-03-13 |  | Scottish Water Wide | 0 | 92596 | 1068720.1 | 4018802.17 | 5267213.73 | 5442619.04 | -243860.54 | 15646090.5 | 0 | 15646090.5 | 0 |  |  |  |  | 311173.23 |  | CM_M&G | 100%
300033 | Portobello Water Quality Study - Further Investigations | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-03-21 | 2012-06-15 | 2012-06-15 | 2015-01-09 | 2015-01-09 | City of Edinburgh | 83839 | -5842.4 | 0 | 0 | 0 | 0 | 0 | -5842.4 | 0 | 77996.6 | 0 | [6 empty] | EC02B | 100%
300024 | Portobello Water Quality Study - Further Investigations | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2011-09-29 | 2019-01-23 | 2019-01-03 | 2019-01-16 | 2019-01-16 | City of Edinburgh | 243.9 | 46251.1 | -46251.1 | 0 | 0 | 0 | 0 | 0 | 0 | 243.9 | 142822 | [6 empty] | EC01C | 100%
403757 | Portobello West BW - Improvements to CSOs impacting Braid Burn and Bathing Water | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS3 | 2014-03-31 | 2019-03-21 | 2019-03-21 | 2020-10-31 | 2021-01-31 | City of Edinburgh | 82211 | 1921 | 90735.57 | 334550.43 | 1566752 | 476362 | 32467.51 | 2502788.51 | 15000 | 2599999.51 | 0 |  |  |  |  | 2470 |  | EC16 | 100% | bar: Regulatory Outputs OMG-21
403677 | Portree Storr Forest WTW Emergency Temporary Crypto Barrier | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-12-20 | 2013-01-30 | 2014-04-09 | 2016-12-22 | 2017-06-30 | Highland | 1137229 | 1531475 | 448847.37 | 97927.88 | -81292.32 | 2997.49 | -2302.36 | 1997653.06 | 0 | 3134882.06 | 1528439 |  |  |  |  | 91884 |  | DW23 | 100%
502622 | Portree Torvaig WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2024-05-01 | 2025-12-22 | 2026-03-31 | 2027-01-28 | 2027-04-30 | Highland | 0 | 0 | 20930.23 | 415.9 | 2390.44 | 4231.17 | -22762.43 | 5205.31 | 0 | 5205.31 | 136478.56 | [6 empty] | WG1 | 100%
402137 | Post Project Water Quality Sampling and Reporting- SWW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS3 | 2011-07-15 | 2011-09-26 | 2011-09-26 | 2021-06-23 |  | Scottish Water Wide | 580324.41 | 27902.59 | 48273 | 25000 | 0 | 9109.95 | 5890.04 | 116175.58 | 0 | 696499.99 | 84954 | [6 empty] | DW5A | 100%
400064 | Powburn PS Prestwick Refurb SPS000381 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2011-10-27 | 2011-10-31 | 2011-12-14 |  | South Ayrshire | 185587.15 | -251.23 | 0 | 0 | 0 | 0 | 0 | -251.23 | 0 | 185335.92 | 0 | [6 empty] | CM_WWNI | 100%
503324 | Powmill WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-08-05 | 2029-01-17 | 2029-05-09 | 2030-05-07 | 2030-08-07 | Perth and Kinross | 0 | 0 | 0 | 0 | 68716.44 | 4332.26 | 0 | 73048.7 | 68951.3 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
401004 | Pre - QS II Capital Projects Land Cost run-offs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2012-05-16 | 2012-06-04 | 2015-11-03 |  | Scottish Water Wide | 2795547 | -70396.2 | 142 | 0 | 0 | 0 | -142 | -70396.2 | 0 | 2725150.8 | 0 | [6 empty] | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
500080 | Pressure Management - New PMV and PMA Installs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-12-06 | 2021-12-06 | Scottish Water Wide | 0 | 804674 | 917811 | 637273 | 482630 | 448157 | 301703.98 | 3592248.98 | 0 | 3592248.98 | 0 | [6 empty] | CM_WSI | 100%
500081 | Pressure Management - PMV & PMA Optimisation Modulation Servicing and Replacement Controllers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-05-10 | 2021-05-10 | Scottish Water Wide | 293.4 | 1861412.45 | -881760.44 | 2438280.17 | 2051476.42 | 2365933 | 2132848 | 9968189.6 | 0 | 9968483 | 0 | [6 empty] | CM_WSI | 100%
500082 | Pressure Management - Replacement of Existing PMVs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2021-05-10 | 2021-05-10 | Scottish Water Wide | 0 | 288095 | 265604 | 292195 | 352649 | 478653 | 373275 | 2050471 | 0 | 2050471 | 0 | [6 empty] | CM_WSI | 100%
500057 | Prestonpans Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-02-27 | 2016-05-18 | 2016-05-18 | 2017-04-21 | 2017-04-21 | East Lothian | 102.09 | 77263.91 | 1299998 | 57077 | -20858.92 | 0 | 0.92 | 1413480.91 | 0 | 1413583 | 0 | [6 empty] | CM_WWI | 100%
403956 | Pre-Stress Concrete Pipe Proximity Risk | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | Scottish Water Wide | 40000 | 102058 | -2057.89 | 0 | 0 | 0 | -0.11 | 100000 | 0 | 140000 | 0 | [6 empty] | CM_WSI | 100%
503410 | Pre-stressed & post-tensioned concrete tanks capital maintenance (North) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2019-09-20 | 2021-01-04 | 2021-04-26 | 2021-10-21 | 2021-10-28 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 24723.07 | 214071.12 | 238794.19 | 966846.79 | 1205640.98 | 0 | [6 empty] | CM_WSNI | 20% | CM_WWNI | 80%
503409 | Pre-stressed & post-tensioned concrete tanks capital maintenance (South) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2019-09-20 | 2021-03-01 | 2021-05-24 | 2022-02-22 | 2022-05-23 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 17026.01 | 182320.46 | 199346.47 | 1277715.57 | 1477062.04 | 0 | [6 empty] | CM_WSNI | 41.59% | CM_WWNI | 58.41%
503397 | Pre-stressed & post-tensioned concrete tanks capital maintenance (West) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2019-09-20 | 2020-08-17 | 2020-12-07 | 2021-08-06 | 2021-11-04 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 36500 | 471511.48 | 508011.48 | 278228.58 | 786240.06 | 0 | [6 empty] | CM_WSNI | 16.59% | CM_WWNI | 83.41%
502713 | Pre-stressed concrete tanks capital maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-09-20 | 2021-04-12 | 2021-07-05 | 2023-09-15 | 2022-03-24 | Scottish Water Wide | 0 | 0 | 0 | 83683.21 | 38138.45 | 23533.54 | 43509.25 | 188864.45 | 2848598.57 | 3037463.02 | 0 | [6 empty] | CM_WSNI | 100%
400513 | Prestwick Airport Overflow Relief Sewer- Esplanade SPS Rising Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-04-07 | 2012-10-31 | 2012-11-26 | 2015-03-27 |  | South Ayrshire | 1450053 | 238767 | 121572.86 | -254.45 | 0 | 0 | 254.45 | 360339.86 | 0 | 1810392.86 | 0 | [6 empty] | CM_WWI | 15.08% | CM_WWNI | 84.92%
500985 | Print Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-23 | 2017-10-09 | 2017-10-09 | 2018-06-13 | 2018-06-13 | Scottish Water Wide | 0 | 72904 | 107252.98 | 229242.06 | 34261.6 | 0 | 0 | 443660.64 | 0 | 443660.64 | 0 | [6 empty] | CM_M&G | 100%
503573 | Pro-Active Maintenance for Time Based Intervention | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-04-01 | 2020-02-11 | 2020-03-15 | 2021-10-25 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 214352.65 | 570981.25 | 785333.9 | 1714666.1 | 2500000 | 0 | [6 empty] | CM_WWNI | 100%
503858 | Pro-active Maintenance for Time Based Intervention (North and East) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2020-04-01 | 2020-01-06 | 2020-07-20 | 2021-10-15 | 2023-07-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 70000 | 620654.56 | 690654.56 | 1809345.4 | 2499999.96 | 0 | [6 empty] | CM_WWNI | 100%
503062 | Proactive works to Gryfe VT Bridges | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS7 | 2020-05-01 | 2021-06-28 | 2021-10-27 | 2022-06-08 | 2022-09-08 | Inverclyde | 0 | 0 | 0 | 26399.63 | 31074.59 | 3462.83 | -155.91 | 60781.14 | 0 | 60781.14 | 821666.8 | [6 empty] | CS22 | 100%
501028 | Process Scientist Plan (IDP) Support - SR15 Yr1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-09 | 2016-06-09 | 2016-06-09 | 2016-04-25 | 2016-06-09 | Scottish Water Wide | 0 | 1182834.01 | 0 | 0 | 0 | 0 | 0 | 1182834.01 | 0 | 1182834.01 | 0 | [6 empty] | CM_WSI | 100%
502196 | Process Scientist Plan (IDP) Support (Waste) - SR15 Yr1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-14 | 2016-09-12 | 2016-09-21 | Scottish Water Wide | 0 | 0 | 233973 | 0 | 0 | 0 | 0 | 233973 | 0 | 233973 | 0 | [6 empty] | CM_WWNI | 100%
403215 | Productisation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-12-10 | 2013-04-17 | 2013-04-17 | 2015-04-15 |  | Scottish Water Wide | 385060.48 | -36294.85 | 0 | 0 | 0 | 0 | 460.99 | -35833.86 | 0 | 349226.62 | 0 | [6 empty] | CM_WSNI | 25% | CM_WWI | 25% | CM_WWNI | 50%
502734 | Project ATOM - Lubrication Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-06-28 | 2017-06-28 | 2017-11-16 | 2021-03-24 | 2021-03-24 | Scottish Water Wide | 0 | 0 | 0 | 81290.48 | 206419.52 | 48018.2 | 164271.79 | 499999.99 | 0 | 499999.99 | 0 | [6 empty] | CM_WSNI | 100%
500758 | Project ATOM HL - Waste Water East | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All East Unitary Authorities | 0 | 382061 | 951443.95 | 622113.05 | -248455.06 | 343190.53 | 761168.53 | 2811522 | 0 | 2811522 | 0 | [6 empty] | CM_WWNI | 100%
500759 | Project ATOM HL - Waste Water North | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 603435.72 | 620516.77 | 288612.51 | -340668.15 | 214687.15 | 519980 | 1906564 | 0 | 1906564 | 0 | [6 empty] | CM_WWNI | 100%
500760 | Project ATOM HL - Waste Water South | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All South Unitary Authorities | 0 | 385748 | 571222.62 | 429903.38 | -228125.82 | 217147.25 | 515970.57 | 1891866 | 0 | 1891866 | 0 | [6 empty] | CM_WWNI | 100%
500761 | Project ATOM HL - Waste Water West | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All West Unitary Authorities | 0 | 432958 | 584047 | 236119 | -255032.01 | 109277.01 | 415272 | 1522641 | 0 | 1522641 | 0 | [6 empty] | CM_WWNI | 100%
500762 | Project ATOM HL - Water East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-06-22 | 2021-05-31 | All East Unitary Authorities | 0 | 328566 | 401738 | 68496 | -107950.39 | 149264.28 | 301195.11 | 1141309 | 0 | 1141309 | 0 | [6 empty] | CM_WSNI | 100%
500763 | Project ATOM HL - Water North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 530551.94 | 493016.06 | 785582 | -298407.9 | 157576.21 | 537556.69 | 2205875 | 0 | 2205875 | 0 | [6 empty] | CM_WSNI | 100%
500764 | Project ATOM HL - Water South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All South Unitary Authorities | 0 | 313597 | 163344 | 142547 | -29560.95 | 161348.89 | 213202.06 | 964478 | 0 | 964478 | 0 | [6 empty] | CM_WSNI | 100%
500765 | Project ATOM HL - Water West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All West Unitary Authorities | 0 | 326421 | 405457 | 80643 | -104966.98 | 145188.06 | 306145.92 | 1158888 | 0 | 1158888 | 0 | [6 empty] | CM_WSNI | 100%
500712 | Project ATOM Intervention | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-05-31 | 2021-05-31 | Scottish Water Wide | 0 | 1110530.45 | 184219.51 | -104912.96 | -327113.28 | 59534.28 | 89995 | 1012253 | 0 | 1012253 | 0 | [6 empty] | CM_WSI | 50% | CM_WWNI | 50%
502393 | Property Estates - Loch Katrine Access Road Repair | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2017-01-16 | 2017-08-31 | 2017-08-31 | 2018-02-15 | 2018-02-15 | All West Unitary Authorities | 0 | 0 | 14000 | 646525.92 | -28075.92 | -875.49 | 0 | 631574.51 | 0 | 631574.51 | 0 | [6 empty] | CM_M&G | 100%
503087 | Property Facilities Statutory Building Compliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2018-07-13 | 2018-07-13 | 2018-07-16 | 2021-06-18 | 2021-06-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1127831 | 1236538 | 1032867 | 3397236 | 0 | 3397236 | 0 | [6 empty] | CM_M&G | 100%
400826 | Provision of Drought Plans Phase 2 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2011-05-13 | 2011-05-13 | 2015-03-06 |  | Scottish Water Wide | 383198.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383198.72 | 0 | [6 empty] | CM_WSI | 100%
400798 | Provision of New DI Flowmetering SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-01 | 2010-08-02 | 2015-09-16 |  | Scottish Water Wide | 1662000 | -161083.01 | 0 | 0 | 0 | 0 | 0 | -161083.01 | 0 | 1500916.99 | 0 | [6 empty] | CM_WSI | 100%
404001 | PSCD Glenhove to Dalmacoulter Rising Main - Close Proximity Diversions | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS6 | 2015-12-08 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2020-01-31 | North Lanarkshire | 586 | 3238759 | 5164682 | 2114871.63 | 278644.84 | 173513.82 | 0 | 10970471.29 | 0 | 10971057.29 | 1823900.39 | [6 empty] | SR15_EXC_EXC | 7% | CS16WR | 93% | bar: Regulatory Outputs OMG-07
505669 | Public Network Katrine & Stronachlacher | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWMD | Exceptional Capital Maintenance | MSU |  | 2020-08-01 |  | 2020-08-01 | 2020-08-01 | Stirling | 0 | 0 | 0 | 0 | 0 | 3271.03 | 46728.96 | 49999.99 | 0 | 49999.99 | 0 | [6 empty] | SR15_EXC_EXC | 100%
503582 | Pump Chain Maintenance - Phase 1 & 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-05-27 | 2019-05-27 | 2019-05-28 | 2020-10-16 | 2020-10-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 361059.05 | 40980.95 | 402040 | 0 | 402040 | 0 | [6 empty] | CM_WSNI | 38.85% | CM_WWNI | 61.15%
400991 | Pundeavon Reservoir Freeboard Related Remedial Work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2010-06-07 | 2015-05-19 | 2015-06-15 | 2017-10-03 | 2017-10-03 | North Ayrshire | 136802 | 800575.52 | 792545.33 | 138555.41 | 0 | 0 | 0 | 1731676.26 | 0 | 1868478.26 | 0 | [6 empty] | CM_WSI | 100%
503699 | Purdomstone MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-05-11 | 2022-04-01 | 2022-06-14 | 2023-01-13 | 2023-04-14 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 13687.06 | 3024.01 | 16711.07 | 333288.91 | 349999.98 | 0 | [6 empty] | CM_WSI | 100%
503499 | PV Project Vesting - Pump Stations - East | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-13 | 2021-07-27 | 2021-10-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 159546.09 | 238820.05 | 426983.16 | 825349.3 | 88050.98 | 913400.28 | 808416.23 | [6 empty] | SG7 | 100%
503496 | PV Project Vesting - Pump Stations - North | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-04-20 | 2021-07-21 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 177220.45 | 33933.47 | 2449.13 | 213603.05 | 499996.95 | 713600 | 808416.23 | [6 empty] | SG7 | 100%
503492 | PV Project Vesting - Pump Stations - South | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-06-01 | 2021-09-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 91876.25 | 116932.77 | 311398.75 | 520207.77 | 50692.84 | 570900.61 | 808416.23 | [6 empty] | SG7 | 100%
503493 | PV Project Vesting - Pump Stations - West | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-05-13 | 2021-08-13 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 338918.62 | 537688.25 | 240714.51 | 1117321.38 | 322112.59 | 1439433.97 | 808416.23 | [6 empty] | SG7 | 100%
502096 | PV Project Vesting - Spec upgrade - Barratt North | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-22 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG7 | 100%
502095 | PV Project Vesting - Spec upgrade - Springfield | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG7 | 100%
502097 | PV Project Vesting - Spec upgrade - Taylor Wimpey West | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG7 | 100%
503498 | PV Project Vesting - SUDS - East | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-06 | 2021-07-27 | 2021-10-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 92198.78 | 423773.57 | 650781.48 | 1166753.83 | 100183.9 | 1266937.73 | 808416.23 | [6 empty] | SG7 | 100%
503497 | PV Project Vesting - SUDS - North | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-27 | 2019-02-27 | 2019-04-08 | 2021-04-20 | 2021-07-21 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 21377.65 | 255437.51 | 29486.37 | 306301.53 | 417698.44 | 723999.97 | 808416.23 | [6 empty] | SG7 | 100%
503495 | PV Project Vesting - SUDS - West | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-05-13 | 2021-08-13 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 268250.39 | 244022.73 | 443733.27 | 956006.39 | 44893.63 | 1000900.02 | 808416.23 | [6 empty] | SG7 | 100%
503494 | PV Project Vesting - SUDS- South | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-06-01 | 2021-09-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 69000.22 | 86731.77 | 218670.48 | 374402.47 | 35597.52 | 409999.99 | 808416.23 | [6 empty] | SG7 | 100%
502099 | PV Project Vesting Pump Stations | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWMD | Developer Asset Adoption | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2021-01-28 | 2021-04-30 | Scottish Water Wide | 0 | 15766.36 | 224233.94 | 592013.7 | 1014722.81 | -284753.29 | 389660.62 | 1951644.14 | 16235.88 | 1967880.02 | 1209174.3 | [6 empty] | SG7 | 49.19% | WG7 | 50.81%
502100 | PV Project Vesting SUDS | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 |  | 2021-05-13 | Scottish Water Wide | 0 | 15766.36 | 9999 | 348366.01 | 332527.63 | -87789.72 | 449456.25 | 1068325.53 | 23655.6 | 1091981.13 | 1209174.3 | [6 empty] | SG7 | 8.423% | WG7 | 91.58%
502098 | PV Project Vesting Team and Small Works | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2021-04-30 | 2021-05-03 | Scottish Water Wide | 0 | 15766.36 | 2575110.63 | 3188186.01 | 2766522 | 2969640.91 | 984774.09 | 12500000 | 0 | 12500000 | 0 | [6 empty] | SG5 | 50% | WG5 | 50%
502226 | PVC Water Mains Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2016-05-16 | 2016-09-15 | 2016-10-21 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 0 | 17390.82 | 18132.42 | -668.68 | 0 | -652.6 | 34201.96 | 0 | 34201.96 | 0 | [6 empty] | CM_M&G | 100%
404061 | Q Improvements Yr5 - Chloram Prog Line - Man Del | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-15 | 2014-12-15 | 2015-11-17 | 2017-10-26 |  | Scottish Water Wide | 45000 | 918973 | 1114535.87 | 369383.4 | 581.85 | 0 | 0.01 | 2403474.13 | 0 | 2448474.13 | 0 | [6 empty] | CM_WSNI | 100%
502738 | QCE and Consultant Support Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 1248066.07 | -22924.72 | 0 | 0 | 1225141.35 | 0 | 1225141.35 | 0 | [6 empty] | CM_WSI | 100%
12059 | QS2 SWS Land and Compensation Liability | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2008-04-01 | 2005-01-21 | 2005-02-21 | 2009-03-31 | 2019-01-03 | Scottish Water Wide | 566461.56 | 0 | -566461.56 | 0 | 0 | 0 | 0 | -566461.56 | 0 | 0 | 0 | [6 empty] | Wa6 | 50% | Ww3 | 50%
40020 | QS3 Risk Management Fund Holding Code | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383772.81 | [6 empty] | RISK | 100%
403416 | QS3b AR - Ardersier WWTW - Outfall Extension | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-28 | 2015-03-06 | 2015-03-18 | 2015-03-18 | 2015-03-18 | Highland | 82209 | -48.77 | 0 | 0 | 0 | 0 | 0 | -48.77 | 0 | 82160.23 | 0 | [6 empty] | CM_WWI | 100%
403879 | QS3b AR - Blairlinnans South WQ Improvements | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS6 | 2014-07-31 | 2015-03-30 | 2015-03-30 | 2018-09-30 | 2019-08-31 | Glasgow City | 260097 | 1893215 | 145530.24 | 233049.4 | 224862.74 | 22418.45 | 0.34 | 2519076.17 | 0 | 2779173.17 | 1951306 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-03
403091 | QS3b AR - Burncrooks WTW | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-02-28 | 2014-10-02 | 2014-10-02 | 2014-10-21 | 2014-10-02 | East Renfrewshire | 212280.37 | 171 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 212451.37 | 0 | [6 empty] | DW25 | 100%
402928 | QS3b AR - Cromwell Road CSO Removal of Raw Discharges | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-10-29 | 2015-09-22 | 2015-10-26 | 2016-03-31 | 2016-03-31 | Highland | 58578 | 910251 | 7935.72 | -1416.75 | 36.43 | 0 | 0 | 916806.4 | 0 | 975384.4 | 633026 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-48
402950 | QS3b AR - Davidston Burn - Fish Pass Installation | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-09-17 | 2013-06-12 | 2013-08-23 | 2014-03-13 | 2014-03-25 | Aberdeenshire | 128320 | 728.29 | 0 | 0 | 0 | 0 | 0 | 728.29 | 0 | 129048.29 | 500 | [6 empty] | WR2A | 100%
403504 | QS3b AR - Dumbarton WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-07-20 | 2016-01-31 | 2016-03-31 | West Dunbartonshire | 22655.28 | 142541.09 | 24.85 | -157.78 | 1964.79 | 0 | 0.01 | 144372.96 | 0 | 167028.24 | 62419 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
402986 | QS3b AR - Elmvale Row Flooding Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS7 | 2012-09-28 | 2015-04-03 | 2015-04-07 | 2017-03-31 | 2017-06-30 | Glasgow City | 1958936 | 9030877 | 648905 | 830491.25 | -1026608.63 | 1 | -0.62 | 9483665 | 0 | 11442601 | 8344790 | [6 empty] | CS11A | 30% | CS15 | 70% | bar: Regulatory Outputs OMG-48
403880 | QS3b AR - Forehill Distribution WQ Improvements | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS5 | 2014-07-31 | 2015-06-15 | 2015-06-29 | 2019-03-31 | 2020-03-04 | Aberdeenshire | 124114 | 1230084 | 553928 | 638871 | 1880718 | 2079.39 | -1266.7 | 4304413.69 | 0 | 4428527.69 | 2690241 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-03
403881 | QS3b AR - Glenfarg - Kinnesswood WQ Improvements | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2014-07-31 | 2016-03-17 | 2016-03-17 | 2016-03-11 | 2016-03-17 | Fife | 57331.99 | -48197.19 | 896.71 | 0 | 0 | 0 | 0.49 | -47299.99 | 0 | 10032 | 0 | [6 empty] | DW5 | 100%
402388 | QS3b AR - Internal Flooding Gables Bar Baillieston Road Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-31 | 2014-01-22 | 2014-01-22 | 2014-09-09 | 2014-09-09 | Glasgow City | 1843311 | 0 | 0 | 0 | -5200.16 | 0 | 0 | -5200.16 | 0 | 1838110.84 | 822 | [6 empty] | CS11A | 50% | CS15 | 50%
403090 | QS3b AR - Kaim WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2020-08-24 | 2020-11-18 | East Renfrewshire | 122472.97 | 356178.93 | 5686690.1 | 4554416.43 | 2930634.67 | 906972.63 | 177459.1 | 14612351.86 | 0 | 14734824.83 | 5813947.47 | [6 empty] | DW25D | 10.45% | DW25P | 10.45% | DW2 | 39.55% | DW3C | 39.55%
403503 | QS3b AR - Killylour WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-07-20 | 2016-01-31 | 2016-03-31 | Dumfries and Galloway | 19652.02 | 38798.8 | 469.46 | 1107.63 | 621.19 | 0 | 0 | 40997.08 | 0 | 60649.1 | 63545 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
403502 | QS3b AR - Loch Eck WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-10-30 | 2016-03-31 | 2016-03-31 | Argyll and Bute-Cowal & Bute | 18230.54 | 34967.09 | 322.03 | -299.95 | 1420.75 | 0 | 0 | 36409.92 | 0 | 54640.46 | 71246 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
402738 | QS3b AR - Muirdykes WTW WQ Investigations and Solutions | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-11-05 | 2016-03-09 | 2016-01-06 | 2016-01-06 | 2016-01-06 | Renfrewshire | 1651786.2 | -17126.19 | 0 | 0 | 0 | 0 | 25.31 | -17100.88 | 0 | 1634685.32 | 0 |  |  |  |  | 115944 |  | DW3C | 0.16% | DW3H | 0.29% | DW23 | 99.55%
403087 | QS3b AR - North Harris Regional Scheme | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-01-17 | 2015-03-06 | 2014-12-12 | 2014-12-12 | 2014-12-12 | Na H-Eileanan an Iar | 226427.35 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 226426.35 | 0 | [6 empty] | DW25 | 100%
403093 | QS3b AR - P001 UID In Park at South of Footbridge Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 19000 | 0 | 0 | -104.02 | 0 | 0 | 0 | -104.02 | 0 | 18895.98 | 0 | [6 empty] | EC01B | 100%
403094 | QS3b AR - P002 - UID - 439 Great Western Road CSO Kelvinbridge | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 274379.16 | 1228415.84 | 1012257 | 361968.07 | 76256.04 | -5774.46 | 5774.46 | 2678896.95 | 0 | 2953276.11 | 0 | [6 empty] | EC01B | 100%
403095 | QS3b AR - P003 UID In Park North East of Prince of Wales Bridge Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 20000 | 0 | 0 | -472.63 | 0 | 0 | 0 | -472.63 | 0 | 19527.37 | 0 | [6 empty] | EC01B | 100%
403096 | QS3b AR - P004 UID Rear Of Kelvingrove Museum North 2 Argyle Street Glasgow | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 21191.36 | 284.64 | 286.64 | 3.57 | 0 | 0 | 0 | 574.85 | 0 | 21766.21 | 0 | [6 empty] | EC01B | 100%
403097 | QS3b AR - P005 UID Off Garriochmill Road CSO North Kelvin | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-03-26 | 2019-03-25 | 2020-10-31 | 2021-03-31 | Glasgow City | 30800 | 2500 | 3100 | 1362 | 201766 | 1079177 | 49934 | 1337839 | 2500 | 1371139 | 0 |  |  |  |  | 6050 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403098 | QS3b AR - P006 UID Near the Junction of Kelvindale Road and Balfour Street | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-12-13 | 2020-03-30 | 2021-02-28 | 2021-03-31 | Glasgow City | 64143 | 12608 | 2689 | 3000 | 146091 | 1456619 | 1536655 | 3157662 | 0 | 3221805 | 0 |  |  |  |  | 30400 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403099 | QS3b AR - P007 UID Junction of Bellshaugh Gardens & Bellshaugh Road CSO | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-03-26 | 2019-08-19 | 2020-03-20 | 2020-04-06 | Glasgow City | 57230 | 11500 | 5660.49 | 6039.51 | 223967 | 896658 | 73468 | 1217293 | 0 | 1274523 | 0 |  |  |  |  | 8290 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403100 | QS3b AR - P008 UID At West Bank of Footbridge BGs Addison Road | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS2 | 2012-11-22 | 2019-03-13 | 2020-11-03 | 2020-11-23 | 2020-12-18 | Glasgow City | 24700 | 100 | 0 | 0 | 3677.97 | 12039.03 | 3727 | 19544 | 0 | 44244 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403101 | QS3b AR - P009 UID North of Playground off Garriochmill Road | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-21 | 2019-03-26 | 2019-08-01 | 2021-02-28 | 2021-03-31 | Glasgow City | 27110.26 | 3222.74 | 0 | 0 | 142492.91 | 1275420.09 | 773955 | 2195090.74 | 2862 | 2225063 | 0 |  |  |  |  | 1950 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403102 | QS3b AR - P010 UID Botanic Gardens Nr Junc of Garrioch Drive Garrioch Rd and Shakespeare St | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-21 | 2019-09-11 | 2019-10-15 | 2021-02-28 | 2021-03-31 | Glasgow City | 31778 | 2550.56 | 1049.44 | 0 | 116369 | 952277 | 643192.01 | 1715438.01 | 2862.01 | 1750078.02 | 0 |  |  |  |  | 2950 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403103 | QS3b AR - P011 UID Queen Margaret Road Bridge CSO at Botanical Gardens | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-03-13 | 2020-03-09 | 2020-11-30 | 2021-03-31 | Glasgow City | 22825 | 417 | -417 | 0 | 9523.95 | 65665.05 | 3898 | 79087 | 2300 | 104212 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403104 | QS3b AR - P012 UID 317 Northwoodside Road Glasgow | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-09-11 | 2020-01-24 | 2020-12-31 | 2021-03-01 | Glasgow City | 32865.7 | 49043.3 | 2587 | 769 | 95276 | 1159982 | 540303 | 1847960.3 | 0 | 1880826 | 0 |  |  |  |  | 13640 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403105 | QS3b AR - P013 UID At The Junction of Otago Street and Otago Lane North | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS5 | 2012-11-22 | 2018-03-28 | 2018-06-29 | 2019-12-31 | 2020-03-20 | Glasgow City | 48878 | 3622 | 63285.42 | 73581.58 | 126432.7 | 39950.3 | 2250 | 309122 | 0 | 358000 | 0 |  |  |  |  | 1842.58 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403106 | QS3b AR - P014 UID Westbank Quadrant at Eldon Street Bridge CSO NS273667 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2018-06-07 | 2018-06-25 | 2022-02-28 | 2022-02-28 | Glasgow City | 45703 | 72797 | 151548 | 156613.12 | 525203.16 | 493033.72 | 174552 | 1573747 | 174099 | 1793549 | 0 |  |  |  |  | 4120 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403107 | QS3b AR - P015 UID Westbank Quadrant CSO at Depot Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS6 | 2012-11-22 | 2018-10-24 | 2019-01-14 | 2019-09-30 | 2020-04-01 | Glasgow City | 44967 | -3967 | 7802 | 79655.12 | 482488.88 | 170804 | 0.01 | 736783.01 | 2249.99 | 784000 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403108 | QS3b AR - P016 UID At Rear of Kelvingrove Museum Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 70143 | 5365 | 278635 | -4797.92 | 0 | 0.46 | -0.07 | 279202.47 | 0 | 349345.47 | 0 | [6 empty] | EC10B | 100%
403109 | QS3b AR - P017 UID Junction Of Drymen Road and Thorn Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-12-19 | 2015-04-13 | 2015-11-30 | 2016-01-31 | East Dunbartonshire | 248417 | 175195.06 | 450.55 | 469.39 | -82.37 | 0 | 0 | 176032.63 | 0 | 424449.63 | 209743 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403110 | QS3b AR - P018 UID At the Junction of Hillfoot Drive and Hillside Avenue Bearsden | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2018-11-06 | 2018-12-17 | 2018-11-05 | 2018-12-17 | East Dunbartonshire | 44206 | 6400 | 17800 | 6000 | -5109.76 | 0 | 0.01 | 25090.25 | 0 | 69296.25 | 187891 | [6 empty] | EC10B | 100%
403111 | QS3b AR - P019 UID In Garden of No 10 Leven Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-03 | 2015-02-03 | 2015-03-10 | 2015-03-10 | East Dunbartonshire | 90980 | -513.84 | 0 | 0 | 0 | 0 | 0 | -513.84 | 0 | 90466.16 | 0 | [6 empty] | EC10B | 100%
403112 | QS3b AR - P020 UID Junction of Kessington Road and Inveroran Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-11-24 | 2015-03-09 | 2015-09-30 | 2015-10-31 | East Dunbartonshire | 190902 | 46254 | 1199.98 | -789.05 | 0 | 0 | 0 | 46664.93 | 0 | 237566.93 | 50233 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403113 | QS3b AR - P021 UID At Junction of Rannoch Drive and Maryhill Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2016-03-22 | 2016-03-23 | 2016-03-31 | 2016-04-30 | East Dunbartonshire | 46255 | 253206 | 41648 | 1968 | -358.32 | 0 | 0 | 296463.68 | 0 | 342718.68 | 160020 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403115 | QS3b AR - P023 UID 250 Milngavie Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2018-11-05 | 2018-12-17 | 2018-11-05 | 2018-12-17 | East Dunbartonshire | 51572 | -2156 | 3000.36 | 998.71 | -238.84 | 0 | 0 | 1604.23 | 0 | 53176.23 | 605497 | [6 empty] | EC10B | 100%
403116 | QS3b AR - P024 UID 22 Station Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2019-05-20 | 2019-06-05 | 2019-05-20 | 2019-05-20 | East Dunbartonshire | 37826 | 6656 | -3020 | 6000 | 5000 | -6313.11 | 0 | 8322.89 | 0 | 46148.89 | 21754 | [6 empty] | EC10B | 100%
403117 | QS3b AR - P025 UID 11 Rubislaw Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-03 | 2015-02-03 | 2015-03-10 | 2015-03-10 | East Dunbartonshire | 40092 | -12626.27 | 0 | 0 | 0 | 0 | 0 | -12626.27 | 0 | 27465.73 | 0 | [6 empty] | EC10B | 100%
403118 | QS3b AR - P026 UID Seafield Pumping Station Storage Need | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2012-12-07 | 2016-12-22 | 2017-01-23 | 2017-09-30 | 2018-01-31 | East Dunbartonshire | 56905.19 | 18182.01 | 449506.8 | 262219 | 4154.92 | -246705.03 | 0.01 | 487357.71 | 0 | 544262.9 | 272470 | [6 empty] | CM_WWNI | 45.26% | EC10B | 54.74% | bar: Regulatory Outputs OMG-19
403119 | QS3b AR - P027 UID Duntocher CSO 3 Burnbrae Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-16 | 2015-03-18 | 2015-03-20 | 2015-03-25 | West Dunbartonshire | 59014 | -1153 | 520.94 | -620.4 | 0 | 0 | 0 | -1252.46 | 0 | 57761.54 | 5419 | [6 empty] | EC10B | 100%
403121 | QS3b AR - P029 UID Gavin Burn CSO Upstream of Old Kilpatrick Septic Tank | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-11-28 | 2015-01-24 | 2015-02-26 | 2015-03-11 | West Dunbartonshire | 56644.83 | 8890.17 | 545.87 | -1606.72 | 0 | 0 | 0 | 7829.32 | 0 | 64474.15 | 3372 |  |  |  |  | 12831.53 |  | EC10B | 100%
403356 | QS3b AR - P030 UID Victoria Rd CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2013-03-04 | 2017-06-27 | 2017-09-18 | 2018-12-31 | 2019-03-31 | South Lanarkshire | 29905 | -4444.91 | 88248.91 | 1765050 | 373019 | -8683 | 1905 | 2215095 | 0 | 2245000 | 112386 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
403086 | QS3b AR - Picketlaw WTW | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-02-20 | 2014-10-24 | 2014-10-24 | 2014-10-24 | 2014-10-24 | East Renfrewshire | 231779.18 | 20994.25 | -20108.3 | 0 | 0 | 0 | 885.95 | 1771.9 | 0 | 233551.08 | 0 | [6 empty] | DW25 | 100%
403957 | QS3b AR - Picketlaw WTW Main Out | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2014-11-24 | 2016-05-30 | 2016-05-30 | 2016-06-02 | 2016-06-23 | East Renfrewshire | 53192.17 | -42599.93 | -1340.6 | 0 | 0 | 0 | 0.36 | -43940.17 | 0 | 9252 | 0 | [6 empty] | DW23 | 50% | DW3C | 50%
402936 | QS3b AR - Stage 4 DOMS investigations in 4 zones | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-12-07 | 2013-05-31 | 2013-06-28 | 2014-03-14 | 2014-03-14 | Scottish Water Wide | 773631 | 0 | -176.56 | 0 | 0 | 0 | 0 | -176.56 | 0 | 773454.44 | 6002 | [6 empty] | DW5A | 100%
403501 | QS3b AR - Tighnabruaich WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-11-17 | 2015-11-17 | 2016-02-29 | 2016-02-29 | Argyll and Bute-North Argyll | 22215.7 | 97264.8 | 5158.7 | -1180.1 | -1348.92 | 0 | 0 | 99894.48 | 0 | 122110.18 | 76986 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
402929 | QS3b AR - Toberonochy Isle of Luing - provision of appropriate WWT | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-09-18 | 2013-09-23 | 2013-11-06 | 2014-08-18 | 2014-11-14 | Argyll and Bute-North Argyll | 233415 | 585 | 484.7 | 0 | 0 | 0 | 0 | 1069.7 | 0 | 234484.7 | 0 | [6 empty] | EC01A | 100%
403088 | QS3b AR - Tomatin WTW Upgrade | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-01-17 | 2015-03-06 | 2014-12-12 | 2014-12-12 | 2014-12-12 | Highland | 301686.7 | 0 | 94.9 | 0 | 0 | 0 | 0 | 94.9 | 0 | 301781.6 | 0 | [6 empty] | DW25 | 100%
403222 | QS3b AR - Turriff WWTW Upgrade | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-01-14 | 2015-02-19 | 2015-03-09 | 2015-12-31 | 2016-03-31 | Aberdeenshire | 1171213.1 | 1741332.23 | -46950.64 | 562.67 | -69349.27 | 0 | 0 | 1625594.99 | 0 | 2796808.09 | 439668.53 | [6 empty] | EC10A | 40.91% | CM_WWNI | 59.09% | bar: Regulatory Outputs OMG-48
501678 | Quality Management Systems Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2019-05-27 | 2020-07-23 | 2020-07-23 | 2021-02-23 | 2018-01-08 | Scottish Water Wide | 0 | 0 | 22209.44 | 8568.8 | 6450 | 152520.12 | 5200 | 194948.36 | 0 | 194948.36 | 0 | [6 empty] | CM_M&G | 100%
45803 | Quarter SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-03-21 | 2011-07-29 | 2012-02-06 | 2012-02-13 | South Lanarkshire | 700959.78 | 7562.04 | -12097.51 | 0 | 0 | 0 | 0 | -4535.47 | 0 | 696424.31 | 0 | [6 empty] | WQ01B | 4.308% | WQ01C | 95.69%
403480 | Queen Margaret Drive Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-07-11 | 2014-07-30 | 2014-07-30 | 2014-09-03 | 2014-09-03 | Glasgow City | 63714.91 | 4774.57 | 0.01 | 0 | 0 | 0 | -0.01 | 4774.57 | 0 | 68489.48 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502937 | Quick Hits Critical Spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-11-30 | 2017-11-30 | 2017-12-20 | 2018-01-09 | 2018-01-09 | Glasgow City | 0 | 0 | 0 | 522681.71 | 0 | 0 | 0 | 522681.71 | 0 | 522681.71 | 0 | [6 empty] | CM_WWNI | 100%
502285 | R&D - Innovation projects | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Wastewater |  | SWD | Research and Innovation | MS3 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2021-05-05 | 2021-05-06 | Scottish Water Wide | 0 | 0 | 11649.09 | 34439.64 | 209916.41 | 223001.58 | 0 | 479006.72 | 0 | 479006.72 | 1705308.55 | [6 empty] | I2S_WWNI | 100%
500638 | R&D SR15 Leakage Projects (ELL) | Q&S4 | Improving drinking water availability and resilience of service | Leakage |  |  | Water |  | SWD | Leakage | MS3 | 2015-05-18 | 2015-05-18 | 2015-06-01 | 2021-05-07 | 2021-05-07 | Scottish Water Wide | 0 | 49065.42 | 86310.56 | 88434 | 205451.91 | 83140.4 | 237597.71 | 750000 | 0 | 750000 | 0 | [6 empty] | CS14 | 100%
500640 | R&D SR15 Wastewater Treatment Pilots and Trials | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Wastewater |  | SWD | Research and Innovation | MS3 | 2015-05-20 | 2015-05-20 | 2015-06-01 | 2021-05-07 | 2021-05-07 | Scottish Water Wide | 0 | 229898.78 | 381408.84 | 319675.69 | 359332.69 | 335397.31 | 1374286.69 | 3000000 | 0 | 3000000 | 1705308.55 | [6 empty] | I2S_WWNI | 100%
500641 | R&D SR15 Water PWNT Pilot | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Water |  | SWD | Research and Innovation | MS7 | 2015-05-20 | 2015-05-20 | 2015-10-01 | 2018-09-03 | 2018-09-03 | Scottish Water Wide | 0 | 93194 | 481705 | 195101 | 0 | 0 | 0 | 770000 | 0 | 770000 | 0 | [6 empty] | I2S_WNI | 100%
500639 | R&D SR15 Water Treatment Pilots and Trials | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Water |  | SWD | Research and Innovation | MS3 | 2015-05-20 | 2015-05-20 | 2015-06-01 | 2021-05-07 | 2021-05-07 | Scottish Water Wide | 0 | 543412 | 503258 | 238060 | -59730 | 90334.34 | 852791.23 | 2168125.57 | 61874.44 | 2230000.01 | 1705308.55 |  |  |  |  | 110000 |  | I2S_WNI | 100%
502623 | Raasay WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 20930.23 | 374.31 | 915.54 | -20886.65 | 0 | 1333.43 | 0 | 1333.43 | 136478.56 | [6 empty] | WG1 | 100%
46845 | Raasay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-09-08 | 2013-06-28 | 2013-09-30 | Highland | 2748896.12 | -24865.75 | 0 | 0 | 0 | 0 | 0 | -24865.75 | 0 | 2724030.37 | 3872 | [6 empty] | DW23 | 100%
402493 | Radon Mitigation Work At East Water Treatment Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-01-13 | 2012-08-18 | 2012-10-02 | 2016-03-22 |  | Aberdeenshire | 203810 | -8810 | 78.13 | 0 | 0 | 0 | 0 | -8731.87 | 0 | 195078.13 | 0 | [6 empty] | CM_M&G | 100%
403408 | Ravelrigg PRV Hydro | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2013-03-01 | 2016-07-25 | 2016-07-25 | 2016-04-19 | 2016-07-25 | City of Edinburgh | 151966 | 34348 | 3024.69 | 0 | 0 | 0 | 0 | 37372.69 | 0 | 189338.69 | 0 | [6 empty] | CC1W | 100%
401532 | Raw Water Monitoring - WFD Article 7 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-03 | 2012-06-28 | 2012-07-24 | 2014-06-30 | 2014-08-29 | Scottish Water Wide | 810267 | 1571.09 | 3113.76 | 0 | 0 | 0 | 0 | 4684.85 | 0 | 814951.85 | 15 | [6 empty] | DW24 | 100%
500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWMD | Climate Change | MS7 | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-16 | 2016-12-22 | Scottish Water Wide | 0 | 16453.5 | 171883.5 | 85010.24 | 57019.46 | 0 | 0.03 | 330366.73 | 0 | 330366.73 | 69200.64 | [6 empty] | CC4W | 100%
500036 | Raw Water Security Studies | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2015-02-17 | 2015-06-23 | 2015-06-23 | 2016-07-31 | 2016-07-31 | Scottish Water Wide | 0 | 302831.58 | 213427.42 | 0 | 3263.01 | 0 | 0 | 519522.01 | 0 | 519522.01 | 737042.41 | [6 empty] | DW9G | 100% | [18 empty] | Regulatory Outputs OMG-47: 6
46378 | Raw Water Supplies - Gartmore to Killearn | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2014-03-10 | 2014-03-03 | 2014-03-06 | 2014-03-06 | Stirling | 64706.15 | 422 | 0 | 0 | 0 | 0 | 0 | 422 | 0 | 65128.15 | 0 | [6 empty] | DW10 | 100%
46377 | Raw Water Supplies - Kinlochard | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2014-02-24 | 2014-03-03 | 2014-03-06 | 2014-03-06 | Stirling | 49719.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49719.49 | 0 | [6 empty] | DW10 | 100%
46376 | Raw Water Supplies - Loch Katrine-Trossachs Pier | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-06-22 | 2011-11-01 | 2013-03-22 | 2013-09-25 | Stirling | 2829666.4 | 6549.32 | 5545.52 | 0 | 0 | 0 | 0 | 12094.84 | 0 | 2841761.24 | 0 | [6 empty] | DW10 | 100%
46379 | Raw Water Supplies - Newcastleton Activity Centre | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-03-31 | 2011-03-31 | 2012-02-24 | 2012-03-14 | Scottish Borders | 11672.67 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 11673.24 | 0 | [6 empty] | DW10 | 100%
46380 | Raw Water Supplies - Stronachlacher - Loch Arklet | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-06-22 | 2011-12-19 | 2013-09-30 | 2013-12-10 | Stirling | 2791910.25 | 8317.31 | 19810.69 | 0 | 0 | 0 | 0 | 28128 | 0 | 2820038.25 | 6081 | [6 empty] | DW10 | 100%
501396 | Rawburn WTW Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2028-06-27 | 2028-10-31 | 2030-01-28 | 2030-04-30 | Scottish Borders | 0 | 0 | 45032.93 | 10031.46 | 1158.06 | 0 | 0 | 56222.45 | 3662507.53 | 3718729.98 | 0 | [6 empty] | CM_WSNI | 100%
502359 | Rawburn WTW Sludge Plant Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-02 | 2028-12-21 | 2029-04-25 | 2030-07-09 | 2030-10-09 | Scottish Borders | 0 | 0 | 42934.57 | 6152.19 | 6102.48 | 12568.39 | 32242.36 | 99999.99 | 4209579.05 | 4309579.04 | 0 | [6 empty] | CM_WSNI | 100%
500984 | RCC Programme Incheril Kinlochewe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-09 | 2016-02-22 | 2016-03-29 | 2016-10-27 | 2017-01-12 | Highland | 0 | 46323 | 123651.57 | 3825.93 | 7865.9 | 0 | 0 | 181666.4 | 0 | 181666.4 | 0 | [6 empty] | CM_WSI | 100%
500982 | RCC Programme Wester Teaninch Farm | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-09-05 | 2018-02-21 | 2018-03-19 | 2019-03-22 | 2019-03-22 | Highland | 0 | 0 | 6310.9 | 141719.6 | 540624.88 | -5950.2 | -540.93 | 682164.25 | 6.47 | 682170.72 | 0 | [6 empty] | CM_WSI | 100%
505460 | RCI Arbuthnott DMA (Pitcarry Farm) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | WINF | SR21 Early Start | MS0 | 2020-03-27 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 402.89 | -402.89 | 0 | 720000.01 | 720000.01 | 0 | [6 empty] | SR21_SS | 100%
505439 | RCI Brackenbrae Avenue DMA (Bishopbriggs) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 |  | 2020-03-12 | 2020-07-17 | 2020-10-23 | 2020-11-20 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 9900.84 | 140099.14 | 149999.98 | 0 | 149999.98 | 0 | [6 empty] | SR21_SS | 100%
505442 | RCI Garve DMA (Little Garve) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-02 | 2020-08-06 | 2020-11-12 | 2020-12-10 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 249000 | 249000 | 0 | 249000 | 0 | [6 empty] | CM_WSI | 100%
505504 | RCI High Dykes DMA (Auchincarroch Rd) | Q&S4 |  |  |  |  | General |  | WINF |  | MS0 | 2020-03-31 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348025.38 | 1348025.38 | 0 | [6 empty] | SR21_SS | 100%
505927 | RCI Hilliclay DMA | Q&S4 |  |  |  |  | General |  | SWD |  | MSU | 2022-01-25 | 2023-12-12 | 2024-05-21 | 2025-12-02 | 2026-03-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 17271.03 | 17271.03 | 1022728.97 | 1040000 | 0 | [6 empty] | SR21_SS | 100%
505499 | RCI Kilmun & Ardentinny DMA (Johnstone Avenue) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 |  | 2020-03-17 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 86.12 | 62604.52 | 62690.64 | 0 | 62690.64 | 0 | [6 empty] | SR21_SS | 100%
505445 | RCI Mains Hill DMA (Mains River) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 |  | 2020-03-12 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 13282.92 | 186717.1 | 200000.02 | 0 | 200000.02 | 0 | [6 empty] | SR21_SS | 100%
505503 | RCI Strachur St Catherines DMA (Forest View and HighHall) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 |  | 2020-03-11 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 15382.6 | 216197.13 | 231579.73 | 0 | 231579.73 | 0 | [6 empty] | SR21_SS | 100%
505693 | RCI West Ballochy DMA (Hillside) | Q&S4 |  |  |  |  | General |  | WINF |  | MS0 | 2020-03-27 | 2023-12-12 | 2024-05-21 | 2025-12-02 | 2026-03-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2920000.02 | 2920000.02 | 0 | [6 empty] | SR21_SS | 100%
505633 | RCI West Line DMA (Thusater) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 |  | 2020-03-12 | 2020-08-13 | 2021-04-02 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 255.36 | 206513.88 | 206769.24 | 3230.77 | 210000.01 | 0 | [6 empty] | SR21_SS | 100%
500710 | Reactive Lead Communication Pipe Replacement Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-10-26 | 2021-10-26 | Scottish Water Wide | 0 | 33890 | 137390.05 | 9313 | 401480.46 | 208668.04 | -299908.08 | 490833.47 | -65833.46 | 425000.01 | 808915.39 | [6 empty] | DW1A | 100%
505975 | Reallocation of Get To Site In Half The Time Phase 2 project costs | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2020-03-31 | 2020-12-07 | 2021-04-13 | 2021-10-12 | 2022-01-12 | - | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000 | 0 | 450000 | 332575.73 | [6 empty] | CS11 | 50% | SG1 | 50%
502975 | Red Burn Sewer Crossings | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2020-01-24 | 2020-09-21 | 2020-12-11 | 2021-09-20 | 2021-12-21 | North Lanarkshire | 0 | 0 | 0 | 27146.7 | 51487.27 | 179169.84 | 2258144.52 | 2515948.33 | 1184051.66 | 3699999.99 | 0 | [6 empty] | SR21_WW | 100%
403433 | Redford Avenue Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-16 | 2014-09-15 | 2014-09-22 | 2015-03-30 | 2015-03-30 | City of Edinburgh | 655709 | 32421 | 0 | -26131.25 | 0 | 0 | 0 | 6289.75 | 0 | 661998.75 | 204193.13 |  |  |  |  | 5400 |  | CS11 | 100%
402630 | Redundant Assets Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2012-04-17 | 2013-02-20 | 2013-02-20 | 2016-02-10 | 2016-02-10 | Scottish Water Wide | 360247 | 31652.8 | 0 | 0 | 0 | 0 | 287.82 | 31940.62 | 0 | 392187.62 | 0 | [6 empty] | CM_M&G | 100%
59 | REMOVAL OF RAW WATER SUPPLIES | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 |  | 2005-01-19 | 2001-10-01 | 2003-03-31 | 2009-02-28 | Scottish Water Wide | 782069.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782069.85 | 0 | [6 empty] | DW3 | 33% | Wa13 | 33% | Wa1 | 34%
502391 | Renewable Energy SR15 Holding Line - HL | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWD | Renewable power | MSU | 2021-04-15 | 2022-03-14 | 2022-05-20 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 187123.2 | 187123.2 | 0 | 187123.2 | 2496681.92 | [6 empty] | I2S_WI | 25% | I2S_WWNI | 25% | I2S_WNI | 50%
403885 | Renewables - Horizons Transfers Holding Line (Complete Projects) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2015-01-29 | Scottish Water Wide | 3501204.72 | -4.72 | -5505.38 | 0 | 0 | 0 | 0.07 | -5510.03 | 0 | 3495694.69 | 0 | [6 empty] | CC1W | 100%
403823 | Renewables - Hydro - Glen Ogil Hydro Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-12-18 | 2015-01-23 | Scottish Water Wide | 1048449 | -42384 | 276.34 | 0 | 0 | 0 | 0 | -42107.66 | 0 | 1006341.34 | 0 | [6 empty] | CC1W | 100%
403824 | Renewables - Hydro - Knockjarder SR Difgen Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-04 | 2014-08-04 | 2015-06-09 | 2015-06-10 | 2015-06-10 | Scottish Water Wide | 317483 | -20562.26 | 0 | 0 | 0 | 0 | 0.26 | -20562 | 0 | 296921 | 140792 | [6 empty] | CC1W | 100%
403825 | Renewables - Hydro - Loch Coulter Hydro Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-11-11 | 2015-03-31 | 2015-03-31 | Scottish Water Wide | 1013163 | 15133 | 4704 | 3778.49 | 5248.79 | 0 | 820.23 | 29684.51 | 0 | 1042847.51 | 63171 | [6 empty] | CC1W | 100%
403826 | Renewables - Hydro - Loch Spallander Hydro Scheme | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2014-07-21 | 2014-07-21 | 2014-10-27 | 2015-03-31 | 2015-03-31 | Scottish Water Wide | 1458555 | -3683.63 | 107293.63 | 26898.92 | 0 | 0 | 0 | 130508.92 | 0 | 1589063.92 | 832227.31 | [6 empty] | CC1W | 100% | [18 empty] | Regulatory Outputs OMG-43: 0.52
403827 | Renewables - Hydro - Saline Difgen Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS5 | 2014-08-08 | 2014-08-08 | 2014-11-28 | 2015-03-26 | 2015-03-26 | Scottish Water Wide | 927766 | 299321 | 78583 | 117262.53 | 180283.01 | 115740.89 | 12864.57 | 804055 | 0 | 1731821 | 193814 | [6 empty] | CC1W | 100%
403828 | Renewables - Hydro - Woodend Difgen Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2015-01-23 | 2015-01-29 | Scottish Water Wide | 1032758 | 74094 | 77012.04 | 3946.89 | 0 | 0 | -0.24 | 155052.69 | 0 | 1187810.69 | 2433 | [6 empty] | CC1W | 100%
403877 | Renewables - PV - Balmore WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-11-07 | 2014-11-07 | Scottish Water Wide | 313666 | -5631 | -999.59 | 0 | 0 | 0 | 0 | -6630.59 | 0 | 307035.41 | 0 | [6 empty] | CC1W | 100%
403876 | Renewables - PV - Blairlinnans WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-11-11 | 2014-11-11 | Scottish Water Wide | 292000 | -4906 | -813.67 | 0 | 0 | 0 | 0 | -5719.67 | 0 | 286280.33 | 0 | [6 empty] | CC1W | 100%
403875 | Renewables - PV - Carron Valley WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-11 | 2014-11-11 | Scottish Water Wide | 253767 | -3349 | -813.77 | 0 | 0 | 0 | 0 | -4162.77 | 0 | 249604.23 | 0 | [6 empty] | CC1W | 100%
403874 | Renewables - PV - Forehill WTW & Depot | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 315910 | -5838 | -813.5 | 0 | 0 | 0 | 0 | -6651.5 | 0 | 309258.5 | 0 | [6 empty] | CC1W | 100%
403873 | Renewables - PV - Mannofield WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 313234 | -5592 | -813.38 | 0 | 0 | 0 | 0 | -6405.38 | 0 | 306828.62 | 0 | [6 empty] | CC1W | 100%
403878 | Renewables - PV - Spey Scheme WTW (Badentinan) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-30 | 2014-07-30 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 361340 | -6829 | -813.38 | 0 | 0 | 0 | 0 | -7642.38 | 0 | 353697.62 | 0 | [6 empty] | CC1W | 100%
403577 | Renewables Programme SR15 Early Start | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-08-08 | 2015-11-09 | 2015-11-10 | 2015-11-10 | 2015-11-10 | Scottish Water Wide | 851727 | -85397.54 | 3811.85 | -4701.2 | 0 | 0 | 889.35 | -85397.54 | 0 | 766329.46 | 0 | [6 empty] | CM_M&G | 100%
500929 | Renfrewshire & East Renfrewshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-11-20 | 2017-11-20 | 2017-10-19 | 2017-10-19 | East Renfrewshire | 0 | 5000 | 2000 | -4577.97 | 0 | 0 | 0 | 2422.03 | 0 | 2422.03 | 120964.87 | [6 empty] | CS15A | 100%
503862 | Repair Ore Trunk sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2019-12-03 |  | 2020-03-04 |  | - | 0 | 0 | 0 | 0 | 0 | 21303.71 | 0 | 21303.71 | 0 | 21303.71 | 0 | [6 empty] | CM_WWI | 100%
500983 | Repeat Customer Contact Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-01 | 2015-12-01 | 2016-03-08 | 2017-03-06 | 2017-03-06 | Scottish Water Wide | 0 | 41920 | 215595.71 | -30678.36 | 2145.46 | 0 | 0 | 228982.81 | 0 | 228982.81 | 0 | [6 empty] | CM_WSI | 100%
503591 | Repeat Customer Contacts associated with ageing infrastructure Holding Line | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-03-31 | 2022-11-10 | 2023-03-15 |  | 2024-11-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 33.12 | 33.12 | 60.21 | 93.33 | 0 | [6 empty] | SR21_WA | 100%
403264 | Replace Huber screens at 20 sites | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-06 | 2015-12-16 | 2016-01-29 | 2017-06-30 |  | All East Unitary Authorities | 219801 | 1179233 | 1698270.39 | 317291.56 | 489 | -10147.63 | 0.01 | 3185136.33 | 0 | 3404937.33 | 0 | [6 empty] | CM_WWNI | 100%
504605 | Replace media and structure in no2 lamella repair/renew damaged concrete | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-30 | 2020-08-04 | 2020-12-08 | 2020-11-10 | - | 0 | 0 | 0 | 0 | 0 | 110.82 | 0 | 110.82 | 0 | 110.82 | 0 | [6 empty] | CM_WWNI | 100%
503478 | Replacement Main - Bogleshole Road Cambuslang | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-09-28 | 2022-07-15 | 2022-10-17 | 2023-05-12 | 2023-08-14 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 1368.01 | 0 | 1368.01 | 1495680.96 | 1497048.97 | 0 | [6 empty] | CM_WSI | 100%
400802 | Replacement Marker Buoys Scotland Wide | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-05-05 | 2010-05-05 | 2010-05-01 | 2016-09-20 |  | Scottish Water Wide | 111903.4 | 26010.6 | 2679.79 | 0 | 0 | 0 | 0 | 28690.39 | 0 | 140593.79 | 0 | [6 empty] | CM_WWI | 100%
500945 | Replacement of obsolete portable gas monitoring equipment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-09-01 | 2016-09-28 | Scottish Water Wide | 0 | 155735.23 | 0 | 92.43 | 0 | 0 | -92.43 | 155735.23 | 0 | 155735.23 | 0 | [6 empty] | CM_M&G | 100%
401976 | Replacement of the Monymusk Pumps and Pumping Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2011-03-24 | 2012-05-23 | 2012-07-02 | 2018-05-11 | 2018-05-11 | Aberdeenshire | 1193302.89 | 76197.11 | -73765.76 | 22.32 | 61.22 | 0 | -30.61 | 2484.28 | 0 | 1195787.17 | 0 | [6 empty] | WG5 | 100%
503267 | Replacement Sludge Tank and Mixer - Annan WWTW | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-07-28 | 2028-03-09 | 2028-06-09 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 14107.5 | 14107.5 | 285892.47 | 299999.97 | 0 | [6 empty] | CM_WWNI | 100%
500787 | Reservoir Capital Programme and QCE Support | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-08-13 | 2015-08-13 | 2018-03-22 | 2018-03-14 | 2018-03-05 | Scottish Water Wide | 0 | 114436.17 | 596239.54 | 39974.53 | 0 | 0 | 0 | 750650.24 | 0 | 750650.24 | 0 | [6 empty] | CM_WSI | 100%
402741 | Reservoir Maintenance - Baddinsgill Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-09-20 | 2012-11-12 | 2014-02-12 |  | Scottish Borders | 222737.32 | 155.83 | 0 | 0 | 0 | 0 | 0 | 155.83 | 0 | 222893.15 | 0 | [6 empty] | CM_WSI | 100%
402663 | Reservoir Maintenance - Barcraigs Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-29 | 2013-02-11 | 2013-05-31 | 2014-08-27 |  | Renfrewshire | 298797.82 | 1156.05 | -5832.19 | 0 | 0 | 0 | 0 | -4676.14 | 0 | 294121.68 | 0 | [6 empty] | CM_WSI | 100%
402720 | Reservoir Maintenance - Bradan Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-29 | 2013-02-07 | 2013-07-15 | 2014-03-06 |  | South Ayrshire | 20217.05 | 1044.63 | 0 | 0 | 0 | 0 | 0 | 1044.63 | 0 | 21261.68 | 0 | [6 empty] | CM_WSI | 100%
402721 | Reservoir Maintenance - Camphill Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2013-02-07 | 2013-05-31 | 2014-09-16 |  | North Ayrshire | 111225.75 | -5038.04 | -93.75 | 0 | 0 | 0 | 0 | -5131.79 | 0 | 106093.96 | 0 | [6 empty] | CM_WSI | 100%
402664 | Reservoir Maintenance - Carron Valley | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-08-29 | 2013-02-25 | 2014-03-13 |  | Stirling | 231042.77 | 2910.78 | 0 | 0 | 0 | 0 | 0 | 2910.78 | 0 | 233953.55 | 0 | [6 empty] | CM_WSI | 100%
402665 | Reservoir Maintenance - Daer Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-09-05 | 2012-11-12 | 2014-03-19 |  | Dumfries and Galloway | 316739.68 | 1134.23 | 0 | 0 | 0 | 0 | 0 | 1134.23 | 0 | 317873.91 | 0 | [6 empty] | CM_WSI | 100%
402742 | Reservoir Maintenance - Fruid Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2012-09-05 | 2012-11-19 | 2013-12-22 |  | Scottish Borders | 203750.67 | 362.12 | 0 | 0 | 0 | 0 | 0 | 362.12 | 0 | 204112.79 | 0 | [6 empty] | CM_WSI | 100%
402666 | Reservoir Maintenance - Gladhouse Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-11-29 | 2013-02-25 | 2014-08-04 |  | Midlothian | 187330.67 | 890.97 | -871.01 | 0 | 0 | 0 | 0 | 19.96 | 0 | 187350.63 | 0 | [6 empty] | CM_WSI | 100%
402743 | Reservoir Maintenance - Glenquey Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-08-23 | 2012-11-05 | 2014-01-15 |  | Perth and Kinross | 180562.13 | 171.21 | 0 | 0 | 0 | 0 | 0 | 171.21 | 0 | 180733.34 | 0 | [6 empty] | CM_WSI | 100%
402722 | Reservoir Maintenance - Harelaw Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-20 | 2013-02-07 | 2013-06-03 | 2014-02-27 | 2014-02-27 | Inverclyde | 231365.74 | 151.55 | 0 | 0 | 0 | 0 | 0 | 151.55 | 0 | 231517.29 | 0 | [6 empty] | CM_WSI | 100%
402723 | Reservoir Maintenance - Loch Thom Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2012-11-14 | 2013-02-18 | 2014-03-31 | 2014-03-31 | Inverclyde | 534455.75 | 13036.82 | 341.9 | 0 | 0 | 0 | 0 | 13378.72 | 0 | 547834.47 | 0 | [6 empty] | CM_WSI | 100%
402744 | Reservoir Maintenance - St Marys Loch | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-08-23 | 2012-11-05 | 2013-12-22 |  | Scottish Borders | 128042.11 | 764.17 | 0 | 0 | 0 | 0 | 0 | 764.17 | 0 | 128806.28 | 0 | [6 empty] | CM_WSI | 100%
402667 | Reservoir Maintenance - Thorters | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-09-20 | 2012-11-19 | 2013-09-23 |  | East Lothian | 177924.25 | 893.45 | 0 | 0 | 0 | 0 | 0 | 893.45 | 0 | 178817.7 | 0 | [6 empty] | CM_WSI | 100%
402745 | Reservoir Maintenance - Torduff Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-09-20 | 2013-02-26 | 2013-09-23 |  | Midlothian | 123819.4 | -876.74 | 0 | 0 | 0 | 0 | 0 | -876.74 | 0 | 122942.66 | 0 | [6 empty] | CM_WSI | 100%
402719 | Reservoir Maintenance - Valve Repair Package | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-06 | 2013-05-03 | 2013-05-22 | 2013-05-22 |  | Scottish Water Wide | 7274.52 | -265.62 | 0 | 0 | 0 | 0 | 0 | -265.62 | 0 | 7008.9 | 0 | [6 empty] | CM_WSI | 100%
46337 | Reservoir Maintenance Phase 1 South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-04-01 | 2011-11-14 | 2011-12-01 | 2011-12-06 | 2011-12-06 | Scottish Water Wide | 115498.84 | -132.35 | 0 | 0 | 0 | 0 | -0.49 | -132.84 | 0 | 115366 | 0 | [6 empty] | CM_WSI | 100%
403616 | Reservoir Programme Line for QCE Costs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-10-22 | 2013-10-22 | 2013-10-22 | 2015-06-10 |  | Scottish Water Wide | 27752.94 | 2578.89 | 0 | 0 | 0 | 0 | 0 | 2578.89 | 0 | 30331.83 | 0 | [6 empty] | CM_WSI | 100%
500741 | Reservoir Safety Signs to comply with RA2011 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW2 | 2020-04-01 | 2020-07-06 | 2020-07-27 | 2021-02-18 | 2021-02-19 | Scottish Water Wide | 0 | 4186.05 | 21264.35 | -4329.42 | 13.4 | 140.26 | 0 | 21274.64 | 0 | 21274.64 | 0 | [6 empty] | WR6 | 100%
500595 | Resilience - Mobile Water Treatment Works | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-04-26 | 2019-04-26 | Scottish Water Wide | 0 | 26500.27 | 17550.62 | 105945.11 | 78280.75 | 113079.45 | 0.01 | 341356.21 | 0 | 341356.21 | 638845.62 | [6 empty] | CS16WR | 100%
503111 | Resillience - Perth and Dundee Connectivity | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2021-01-25 | 2021-09-27 | 2021-10-04 | 2021-10-04 | 2021-10-04 | Scottish Water Wide | 0 | 0 | 0 | 581085.65 | 131026.22 | 316946.59 | 685473.22 | 1714531.68 | 2038468.33 | 3753000.01 | 2696105.82 | [6 empty] | CS16WRID | 100%
503347 | Resource Scheduler | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2018-08-20 | 2019-09-24 | 2019-09-24 | 2020-05-26 | 2020-05-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 49869.33 | 360211.56 | 128212.61 | 538293.5 | 0 | 538293.5 | 0 |  |  |  |  | 33000 |  | CM_M&G | 100%
503363 | Rhenigidale WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2022-10-17 | 2027-12-20 | 2028-04-17 | 2029-04-12 | 2029-07-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 20153.02 | -18054.62 | 0 | 2098.4 | 0 | 2098.4 | 136478.56 | [6 empty] | WG1 | 100%
500810 | Rhynie RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-10-19 | 2017-08-10 | 2017-09-22 | 2018-06-30 | 2018-12-31 | Aberdeenshire | 0 | 569.73 | 510.66 | 7389.96 | 13900.97 | -2606.89 | 0 | 19764.43 | 0 | 19764.43 | 2016.36 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 2.87
502420 | Rhynie WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2027-04-01 | 2028-08-08 | 2028-11-28 | 2029-11-16 | 2030-02-18 | Aberdeenshire | 0 | 0 | 20496.52 | 30.81 | 129.13 | 0 | -0.23 | 20656.23 | 27343.77 | 48000 | 0 | [6 empty] | CM_WWNI | 100%
403255 | Rhynie WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-18 | 2016-10-31 | 2016-10-31 | 2016-11-02 |  | Aberdeenshire | 21759.04 | 6219.99 | 4517.13 | 0 | 0 | 0 | 0 | 10737.12 | 0 | 32496.16 | 0 | [6 empty] | CM_WWNI | 100%
503273 | Rigside WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-04-19 | 2022-08-31 | 2023-01-03 | 2024-01-01 | 2024-04-02 | South Lanarkshire | 0 | 0 | 0 | 0 | 74437.32 | 4125.37 | 62461.37 | 141024.06 | 975.96 | 142000.02 | 136478.56 | [6 empty] | SG1 | 100%
501511 | RIGSIDE WWTW 1950 NS872356 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-04-14 | 2020-11-16 | 2020-12-07 | 2022-02-28 | 2022-05-31 | South Lanarkshire | 0 | 0 | 140883.69 | 273681.96 | 39816.74 | 0 | 932424.53 | 1386806.92 | 2308377.1 | 3695184.02 | 0 | [6 empty] | CM_WWNI | 100%
500246 | Ringford WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 | 2017-07-28 | 2020-03-18 | 2020-08-03 | 2021-03-30 | 2021-06-30 | Dumfries and Galloway | 0 | 15732.21 | 64763 | 206670.72 | 58425.93 | 135225.04 | 495197.13 | 976014.03 | 85839.67 | 1061853.7 | 1395918.04 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
400633 | Rising Mains - Pollution Hotspots Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-02-23 | 2012-03-14 | 2014-12-04 |  | Falkirk | 335876 | 151.93 | 0 | 0 | 0 | 0 | 0 | 151.93 | 0 | 336027.93 | 0 | [6 empty] | CM_WWI | 100%
500214 | River Almond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2016-09-14 | 2016-09-26 | 2019-07-31 | 2019-07-31 | Scottish Water Wide | 0 | 11732 | 154334.13 | 154324.87 | 167774 | 55194.81 | -990.34 | 542369.47 | 0 | 542369.47 | 101616.7 | [6 empty] | EC01G | 10% | EC10H | 90% | bar: Regulatory Outputs OMG-23
500090 | River Angus Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2015-03-20 | 2016-12-20 | 2017-01-26 | 2020-01-28 | 2020-04-01 | Scottish Water Wide | 0 | 9185 | 81214.68 | 257316.32 | 292130 | 42032 | 22769 | 704647 | 0 | 704647 | 200273.51 | [6 empty] | EC10E | 50% | EC10H | 50% | bar: Regulatory Outputs OMG-23
504469 | River Blaich burst main replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-12-24 |  | 2020-10-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 5000 | 20000.01 | 25000.01 | 0 | 25000.01 | 0 | [6 empty] | CM_WSI | 100%
500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2020-06-08 | 2020-11-20 | Scottish Water Wide | 0 | 22136 | 82403.66 | 339099.34 | 85335 | 50934.2 | 10091.8 | 590000 | 0 | 590000 | 283015.79 | [6 empty] | EC01G | 0.3636% | CS16D | 1.455% | EC10E | 49.09% | EC10H | 49.09%
500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2020-08-07 | 2020-11-27 | Scottish Water Wide | 0 | 16694 | 110505.38 | 118997.62 | 666587.16 | 165961.81 | 12047.44 | 1090793.41 | 0 | 1090793.41 | 488073.14 | [6 empty] | CS16D | 12.56% | EC10E | 43.72% | EC10H | 43.72%
500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-02-14 | 2020-04-01 | Scottish Water Wide | 0 | 12208 | 89258.13 | 219227.87 | 279335.91 | 145072.14 | 3000 | 748102.05 | 0 | 748102.05 | 221694.31 | [6 empty] | CS16D | 21.28% | EC10E | 39.36% | EC10H | 39.36%
502199 | River Intake Monitoring - Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2016-06-01 | 2016-07-29 | 2016-08-11 | 2017-12-15 | 2017-12-15 | Scottish Water Wide | 0 | 0 | 19600 | 62200 | 1200 | 754.51 | -43.06 | 83711.45 | 0 | 83711.45 | 640245.27 | [6 empty] | WR7 | 100%
506017 | River Kelvin and Dalmuir Aesthetic Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MSU | 2020-05-01 | 2021-01-18 | 2021-05-19 | 2021-11-17 | 2022-02-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 240.6 | 0 | 240.6 | 0 | 240.6 | 0 | [6 empty] | CM_WWI | 100%
501715 | River Kelvin Sewer - Sewer cleaning along river bank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-04-28 | 2018-05-25 | 2018-08-08 | 2019-02-19 | 2019-02-19 | Glasgow City | 0 | 0 | 0 | 4773 | 244736.57 | -5148.01 | 0 | 244361.56 | 0 | 244361.56 | 0 | [6 empty] | CM_WWI | 100%
504217 | River Larroch pipe crossing replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-12-11 | 2020-08-06 | 2020-09-17 | 2020-09-18 | Highland | 0 | 0 | 0 | 0 | 0 | 3720.48 | 31279.52 | 35000 | 0 | 35000 | 0 | [6 empty] | CM_WSI | 100%
501660 | River Leven Trunk Main Sewer - Inspect sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-07-19 | 2017-02-28 | 2017-03-17 | 2017-12-04 | 2017-12-04 | Fife | 0 | 0 | 12000 | 35721.59 | 0 | -0.04 | 0.04 | 47721.59 | 0 | 47721.59 | 0 | [6 empty] | CM_WWI | 100%
501193 | River Leven Trunk Sewer Reinstate River Bank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-12-03 | 2016-08-02 | 2016-08-22 | 2016-11-02 | 2016-11-02 | Fife | 0 | 7794.37 | 104574.72 | -369.14 | 25.01 | 0 | 0.04 | 112025 | 0 | 112025 | 0 | [6 empty] | CM_WWI | 100%
402770 | River Ugie to St Fergus Water Main Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-03 | 2013-05-13 | 2013-08-30 | 2014-10-24 |  | Aberdeenshire | 742867 | 11599.49 | 43071.47 | 0 | 0 | 0 | 0 | 54670.96 | 0 | 797537.96 | 0 | [6 empty] | CM_WSI | 100%
403544 | Rivers Ayr and Doon Strategic Study scoping of capex 3 costs | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-27 | 2015-01-29 | 2015-02-16 | 2017-03-31 | 2017-06-30 | South Ayrshire | 219562 | 709100 | 388924.1 | 100180.28 | 0 | 0 | 0 | 1198204.38 | 0 | 1417766.38 | 1186562 | [6 empty] | EC10B | 0.7053% | EC16 | 99.29% | bar: Regulatory Outputs OMG-48
400593 | RM Customer Sewer Infra East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 2504343.53 | 558810 | 987611.88 | 363029.35 | -357683.69 | 0 | 0 | 1551767.54 | 0 | 4056111.07 | 0 | [6 empty] | CM_WWI | 100%
400594 | RM Customer Sewer Infra North | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-01-21 |  | All North Unitary Authorities | 2047056.48 | 0 | 0 | 62155 | -62155 | 0 | 0 | 0 | 0 | 2047056.48 | 0 | [6 empty] | CM_WWI | 100%
400595 | RM Customer Sewer Infra Others East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 6753275.32 | 1177798.4 | 1488342.97 | 8576.66 | 0 | 0 | 0 | 2674718.03 | 0 | 9427993.35 | 0 | [6 empty] | CM_WWI | 100%
400596 | RM Customer Sewer Infra Others North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2553230.4 | 197238.53 | 236949.07 | 7460.32 | 0 | 0 | 0 | 441647.92 | 0 | 2994878.32 | 0 | [6 empty] | CM_WWI | 100%
400597 | RM Customer Sewer Infra Others South | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 2529132 | 497820 | 696780.57 | 5345.66 | 0 | 0 | 0 | 1199946.23 | 0 | 3729078.23 | 0 | [6 empty] | CM_WWI | 100%
400598 | RM Customer Sewer Infra Others West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2367230 | 472324.63 | 695013.76 | 5345.66 | 0 | 0 | 0 | 1172684.05 | 0 | 3539914.05 | 0 | [6 empty] | CM_WWI | 100%
400599 | RM Customer Sewer Infra South | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 6702907.8 | 1362416.37 | 1792668.06 | 594631 | -589285.34 | 0 | 0 | 3160430.09 | 0 | 9863337.89 | 0 | [6 empty] | CM_WWI | 100%
400600 | RM Customer Sewer Infra West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 5204837.06 | 991533.12 | 1421440.91 | 680907.66 | -675562 | 0 | 0 | 2418319.69 | 0 | 7623156.75 | 0 | [6 empty] | CM_WWI | 100%
400581 | RM Customer Water Infra Bursts East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 4136030.07 | 969008.39 | 92340.39 | 317672.82 | -308093.22 | 0 | 0 | 1070928.38 | 0 | 5206958.45 | 0 | [6 empty] | CM_WSI | 100%
400582 | RM Customer Water Infra Bursts North | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 4662501.65 | 989264.2 | 99915.4 | 396337.86 | -386757.26 | 0 | 0 | 1098760.2 | 0 | 5761261.85 | 0 | [6 empty] | CM_WSI | 100%
400583 | RM Customer Water Infra Bursts South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 11130129.73 | 2709757.91 | 104167.76 | 1119543.79 | -1109964.19 | 0 | 0 | 2823505.27 | 0 | 13953635 | 0 | [6 empty] | CM_WSI | 100%
400584 | RM Customer Water Infra Bursts West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 13756430.89 | 2862936.84 | 110887.6 | 1289452.91 | -1279873.31 | 0 | 0 | 2983404.04 | 0 | 16739834.93 | 0 | [6 empty] | CM_WSI | 100%
400585 | RM Customer Water Infra Others East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 7037156.79 | 1423764.06 | -87945.51 | 589293.49 | -585334.89 | 0 | 0 | 1339777.15 | 0 | 8376933.94 | 0 | [6 empty] | CM_WSI | 100%
400586 | RM Customer Water Infra Others North | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2569930.24 | 635030.87 | -184208.71 | 97852.48 | -93893.88 | 0 | 0 | 454780.76 | 0 | 3024711 | 0 | [6 empty] | CM_WSI | 100%
400587 | RM Customer Water Infra Others South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 5411099.17 | 1080390.56 | 51155.41 | 329204.76 | -325246.16 | 0 | 0 | 1135504.57 | 0 | 6546603.74 | 0 | [6 empty] | CM_WSI | 100%
400588 | RM Customer Water Infra Others West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2140824.78 | 439363.67 | 82164.95 | 174168.56 | -170209.96 | 0 | 0 | 525487.22 | 0 | 2666312 | 0 | [6 empty] | CM_WSI | 100%
400573 | RM Waste Non Infra EM East | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 9522415.05 | 1760182.49 | 791139.81 | 822002.85 | -820042.54 | 0 | 0 | 2553282.61 | 0 | 12075697.66 | 0 | [6 empty] | CM_WWNI | 100%
400574 | RM Waste Non Infra EM North | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2015842 | 45081.6 | -97.43 | 173812.33 | -171852.02 | 0 | 0 | 46944.48 | 0 | 2062786.48 | 0 | [6 empty] | CM_WWNI | 100%
400575 | RM Waste Non Infra EM South | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 9276281.51 | 1784705.14 | 844947.92 | 866542.94 | -893730.92 | 0 | -0.5 | 2602464.58 | 0 | 11878746.09 | 0 | [6 empty] | CM_WWNI | 100%
400576 | RM Waste Non Infra EM West | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 9164354.26 | 1775417.29 | 827201.32 | 984293.43 | -982333.12 | 0 | 0 | 2604578.92 | 0 | 11768933.18 | 0 | [6 empty] | CM_WWNI | 100%
500542 | RM Water East Infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All East Unitary Authorities | 0 | 56706 | 1599048.64 | 176.8 | 95.19 | 0 | 0 | 1656026.63 | 0 | 1656026.63 | 0 | [6 empty] | CM_WSI | 100%
500543 | RM Water East WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 | 2017-08-31 | All East Unitary Authorities | 0 | 4782 | 184250.13 | 0 | 0 | 0 | 0 | 189032.13 | 0 | 189032.13 | 0 | [6 empty] | CM_WSNI | 100%
500544 | RM Water East WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2017-08-31 | 2017-08-31 | All East Unitary Authorities | 0 | 6832 | 292833.38 | 0 | 0 | 0 | 0 | 299665.38 | 0 | 299665.38 | 0 | [6 empty] | CM_WSNI | 100%
400577 | RM Water Non Infra East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 3100000 | 624922.86 | 2654.55 | 273108.73 | -271148.42 | 0 | 0 | 629537.72 | 0 | 3729537.72 | 0 | [6 empty] | CM_WSNI | 100%
400578 | RM Water Non Infra North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2058992 | 441192.96 | 2988.75 | 253335.75 | -253335.75 | 0 | 0 | 444181.71 | 0 | 2503173.71 | 0 | [6 empty] | CM_WSNI | 100%
400579 | RM Water Non Infra South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 2575019.22 | 494071.61 | 42835.41 | 271789.27 | -269828.96 | 0 | 0 | 538867.33 | 0 | 3113886.55 | 0 | [6 empty] | CM_WSNI | 100%
400580 | RM Water Non Infra West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2601663.58 | 589048.86 | 102792.21 | 266511.44 | -264551.13 | 0 | 0 | 693801.38 | 0 | 3295464.96 | 0 | [6 empty] | CM_WSNI | 100%
500545 | RM Water North Infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All North Unitary Authorities | 0 | 36454 | 2263653 | -69412.55 | 0 | 0 | 0 | 2230694.45 | 0 | 2230694.45 | 0 | [6 empty] | CM_WSI | 100%
500546 | RM Water North WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 | 2017-08-31 | All North Unitary Authorities | 0 | 3074 | 188582.44 | 0 | 0 | 0 | 0 | 191656.44 | 0 | 191656.44 | 0 | [6 empty] | CM_WSNI | 100%
500547 | RM Water North WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 | 2017-08-31 | All North Unitary Authorities | 0 | 4392 | 228086.31 | 0 | 0 | 0 | 0 | 232478.31 | 0 | 232478.31 | 0 | [6 empty] | CM_WSNI | 100%
500551 | RM Water South infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All South Unitary Authorities | 0 | 74932 | 3431713.64 | 0 | 0 | 0 | 0 | 3506645.64 | 0 | 3506645.64 | 0 | [6 empty] | CM_WSI | 100%
500552 | RM Water South WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All South Unitary Authorities | 0 | 6320 | 162624.29 | 0 | 0 | 0 | 0 | 168944.29 | 0 | 168944.29 | 0 | [6 empty] | CM_WSNI | 100%
500553 | RM Water South WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All South Unitary Authorities | 0 | 9028 | 621292.09 | 0 | 0 | 0 | 0 | 630320.09 | 0 | 630320.09 | 0 | [6 empty] | CM_WSNI | 100%
500548 | RM Water West infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All West Unitary Authorities | 0 | 76958 | 3274326.7 | 0 | 534446.72 | 0 | 0 | 3885731.42 | 0 | 3885731.42 | 0 | [6 empty] | CM_WSI | 100%
500549 | RM Water West WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All West Unitary Authorities | 0 | 6490 | 193273.2 | 0 | 0 | 0 | 0 | 199763.2 | 0 | 199763.2 | 0 | [6 empty] | CM_WSNI | 100%
500550 | RM Water West WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All West Unitary Authorities | 0 | 9272 | 301306.91 | 318.56 | 150944.09 | 0 | 0 | 461841.56 | 0 | 461841.56 | 0 | [6 empty] | CM_WSNI | 100%
501264 | Roanhead Terrace Kincardine Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-10 | 2017-01-19 | 2017-03-28 | 2017-06-30 | 2017-06-30 | Fife | 0 | 3282 | 134327 | -3604 | -2475.47 | -2710.66 | 181.13 | 129000 | 0 | 129000 | 0 | [6 empty] | CM_WWI | 100%
502935 | Roanheads SPS Rising Main Peterhead | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2018-03-29 | 2019-02-26 | 2019-05-23 | 2020-01-29 | 2020-05-05 | Aberdeenshire | 0 | 0 | 0 | 14300.7 | 73004.3 | 153490 | 0 | 240795 | 2250 | 243045 | 0 | [6 empty] | CM_WWI | 100%
500047 | Roberton WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-06-23 | 2020-02-13 | 2020-02-28 | 2021-11-24 | 2022-02-25 | Scottish Borders | 0 | 98749 | 316067.11 | 109039.73 | 218646.53 | 1225287.81 | 1295161.82 | 3262952 | 971741 | 4234693 | 0 | [6 empty] | CM_WSNI | 100%
503618 | Roberton WTW - pH correction for coagulation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW1 | 2020-06-29 | 2022-03-14 | 2022-07-14 | 2024-02-07 | 2024-04-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 55210.61 | 54037.89 | 109248.5 | 1390751.55 | 1500000.05 | 271314.84 | [6 empty] | DW25P | 100%
501291 | Roberton WTW - Replacement Sludge Holding Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-12-04 | 2017-03-29 | 2017-05-19 | 2020-11-18 | 2020-11-18 | Scottish Borders | 0 | 5481.61 | 92255.69 | 129863.49 | 376999.66 | 117127.5 | 0.02 | 721727.97 | 4323.49 | 726051.46 | 0 |  |  |  |  | 351.98 |  | CM_WSNI | 100%
401311 | Rochomie Reservoir - Breaching embankment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2013-07-30 | 2013-08-13 | 2014-12-02 | 2014-07-01 | Moray | 567875 | 699.38 | -1673.8 | 0 | 0 | 0 | 0.01 | -974.41 | 0 | 566900.59 | 0 | [6 empty] | CM_WSI | 100%
46853 | Rochomie WTW Upgrade (SWS2) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-09-11 | 2012-09-24 | 2013-03-28 | 2013-03-29 | Moray | 1254002.54 | -894.07 | 0 | 0 | 0 | 0 | 0 | -894.07 | 0 | 1253108.47 | 0 | [6 empty] | DW23 | 100%
403951 | Rockcliffe BW - Improvement to Sufficient Status | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | NONINF | OMG180 | MS0 | 2014-11-19 | 2021-03-22 | 2021-06-08 | 2022-09-30 | 2023-02-28 | Dumfries and Galloway | 99678 | 1665 | 13107 | 168598 | 152297 | 318747.75 | 192585.85 | 847000.6 | 5700744.4 | 6647423 | 4452799 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
402772 | Rockcliffe WwTW - Replacement of UV Sludge and Aeration Systems | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-09-10 | 2013-07-24 | 2013-08-30 | 2015-03-13 |  | Dumfries and Galloway | 743005 | 3538 | 2137 | 0 | 0 | 0 | 0 | 5675 | 0 | 748680 | 0 | [6 empty] | CM_WWI | 100%
501566 | Roer to Eela WTW - Raw Water Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-22 | 2027-10-28 | 2028-02-14 | 2029-01-25 | 2029-04-27 | Shetland Islands | 0 | 84187.13 | 22577.06 | 999.81 | 66062 | -60860.02 | 60860.02 | 173826 | 1724601 | 1898427 | 0 | [6 empty] | CM_WSI | 100%
46572 | Rolling Programme - Chlorine to Chloris Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2009-07-14 | 2012-01-26 | 2012-02-20 | 2017-06-30 |  | Scottish Water Wide | 19392597.96 | 1598801.08 | 1770939.22 | 286927.27 | -314845.94 | 41.32 | 0 | 3341862.95 | 0 | 22734460.91 | 0 |  |  |  |  | 1237230.27 |  | CM_WSNI | 100%
46081 | Rolling Programme - GAC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2010-03-11 | 2010-07-28 | 2015-05-29 |  | Scottish Water Wide | 5077805 | 21783.19 | 0 | 0 | 0 | 0 | 0 | 21783.19 | 0 | 5099588.19 | 0 | [6 empty] | CM_WSNI | 100%
400085 | Rolling Programme - Membrane Replacement SR10 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-11-04 | 2010-11-05 | 2010-11-12 | 2015-03-31 |  | Scottish Water Wide | 8595523.47 | 195342.85 | -35396.21 | 0 | 0 | 0 | 0 | 159946.64 | 0 | 8755470.11 | 0 | [6 empty] | CM_WSNI | 100%
500870 | Rosebery Hopes RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-08-17 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | East Lothian | 0 | 5298.78 | 4844.52 | 17739 | -17729.89 | 0 | 0 | 10152.41 | 0 | 10152.41 | 325256.96 | [6 empty] | DW5FS | 100%
503148 | Rosebery WTW - Filter media replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2018-03-15 | 2018-03-30 | 2018-04-19 | 2018-11-30 | 2018-11-30 | Midlothian | 0 | 0 | 0 | 56033.04 | 929858.84 | -73904.21 | 13471.79 | 925459.46 | 0 | 925459.46 | 0 | [6 empty] | CM_WSNI | 100%
502246 | Rosebery WTW Lime to Caustic | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-08-15 | 2019-10-01 | 2019-10-01 | 2021-03-23 | 2021-06-23 | Midlothian | 0 | 0 | 13827.66 | 47520.37 | 805881.81 | 547061.42 | 457291.11 | 1871582.37 | 183872.62 | 2055454.99 | 0 | [6 empty] | CM_WSNI | 100%
403217 | Rosebery WTW- WOA Install Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-07 | 2014-05-13 | 2014-04-16 | 2014-04-16 |  | East Lothian | 98709.96 | 835.7 | 0 | 0 | 0 | 0 | 0 | 835.7 | 0 | 99545.66 | 0 | [6 empty] | CM_WSNI | 100%
403220 | Rosebery WTW- WOA Roof Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-07 | 2014-05-15 | 2014-06-09 | 2015-02-27 |  | Midlothian | 1002055.18 | -48127.1 | 680.68 | 0 | 0 | 0 | 0 | -47446.42 | 0 | 954608.76 | 0 | [6 empty] | CM_WSNI | 100%
403970 | Rosewell WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2016-07-19 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | East Lothian | 904.37 | 16351.35 | 64164.65 | 109540.73 | 24383.68 | 2239.12 | -1669.56 | 215009.97 | 0 | 215914.34 | 0 | [6 empty] | SG1 | 100%
503619 | Rosewell WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-09-21 | 2023-05-01 | 2023-09-01 | 2025-03-27 | 2025-05-20 | Midlothian | 0 | 0 | 0 | 0 | 0 | 193129.61 | 89968.7 | 283098.31 | 1424026.65 | 1707124.96 | 136478.56 | [6 empty] | SG1 | 100%
46124 | Roslin STW Refurb - STW002150 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-16 | 2010-06-28 | 2010-08-09 | 2011-01-26 |  | Midlothian | 297647 | 199.93 | 0 | 0 | 0 | 0 | 0 | 199.93 | 0 | 297846.93 | 0 | [6 empty] | CM_WWNI | 100%
503260 | Roslin WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-04 | 2023-08-24 | 2023-12-19 | 2024-12-12 | 2025-03-14 | Midlothian | 0 | 0 | 0 | 0 | 74866.55 | 6708.47 | 44095.66 | 125670.68 | 1874329.29 | 1999999.97 | 136478.56 | [6 empty] | SG1 | 100%
502951 | Ross Priory - Balmore Surge Vessel Lining | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2020-05-12 | 2021-08-16 | 2021-12-16 | 2022-07-28 | 2022-10-28 | West Dunbartonshire | 0 | 0 | 0 | 6475.1 | 4282.73 | 9700.86 | 34071.03 | 54529.72 | 707018.59 | 761548.31 | 0 | [6 empty] | CM_WSNI | 100%
505139 | Ross Priory RWPS - Blairlinnans No.2 motor coupling replacment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2020-03-31 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 625.68 | 8938.32 | 9564 | 0 | 9564 | 0 | [6 empty] | CM_WSNI | 100%
502927 | Ross Priory to Blmore (Strathblane tunnel) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-02 | 2028-01-20 | 2028-04-21 | 2028-11-23 | 2029-02-23 | Glasgow City | 0 | 0 | 0 | 6024.67 | 4966.52 | 3320.03 | -1111.21 | 13200.01 | 261799.99 | 275000 | 0 | [6 empty] | CM_WSI | 100%
505985 | Rothes RBC No1 Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-04-01 | 2020-07-20 | 2020-10-26 | 2020-11-23 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
503276 | Rothes WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-06-09 | 2023-10-23 | 2024-02-23 | 2025-02-20 | 2025-05-23 | Moray | 0 | 0 | 0 | 0 | 78497.03 | 11136.14 | 32932.89 | 122566.06 | 1377433.95 | 1500000.01 | 136478.56 | [6 empty] | SG1 | 100%
501638 | Rothesay Network Odour | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2020-12-01 | 2021-01-11 | 2021-05-13 | 2021-09-13 | 2021-12-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 166.36 | 19862.39 | 3468.89 | 40895.64 | 64393.28 | 11655.73 | 76049.01 | 0 | [6 empty] | CM_WWNI | 100%
501165 | Rothesay STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-12-03 | 2018-11-29 | 2018-12-17 | 2020-12-03 | 2020-12-04 | Argyll and Bute-Cowal & Bute | 0 | 12056 | 255828.88 | 40930.71 | 352778.46 | 1313001.38 | 146999.79 | 2121595.22 | 23327.78 | 2144923 | 0 | [6 empty] | CM_WWNI | 100%
502724 | Rothienorman Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2018-02-23 | 2018-08-28 | 2018-11-26 | 2019-02-19 | 2019-02-19 | Aberdeenshire | 0 | 0 | 0 | 11822.04 | 36108.49 | -1930.53 | 0 | 46000 | 0 | 46000 | 0 | [6 empty] | CM_WWI | 100%
400068 | Rothienorman STW Upgrade WQ01 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2012-09-05 | 2013-01-07 | 2014-03-19 | 2014-03-26 | Aberdeenshire | 1109218.07 | 45081.75 | -1694.79 | 0 | 0 | 0 | 0 | 43386.96 | 0 | 1152605.03 | 146541.7 | [6 empty] | SG1 | 20% | WQ01 | 80%
503222 | Rothienorman WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-05-31 | 2022-11-04 | 2023-03-08 | 2024-03-04 | 2024-06-04 | Aberdeenshire | 0 | 0 | 0 | 0 | 89094.82 | 15514.39 | 36322.47 | 140931.68 | 2408038.31 | 2548969.99 | 136478.56 | [6 empty] | SG1 | 100%
504068 | Roughrigg Reservoir MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-03-27 | 2022-03-28 | 2022-07-27 | 2023-10-18 | 2024-01-18 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 61603.07 | 45372.22 | 106975.29 | 1693024.71 | 1800000 | 0 | [6 empty] | CM_WSI | 100%
500940 | Roundknowe Road Calderbraes Golf Club Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2015-09-04 | 2018-09-18 | 2018-10-29 | 2019-06-11 | 2019-06-11 | North Lanarkshire | 0 | 26881.08 | 26102.92 | 197586 | 1533546 | 287151 | 18623 | 2089890 | 0 | 2089890 | 0 | [6 empty] | CM_WWI | 100%
45362 | Rousay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-12-07 | 2012-01-30 | 2012-09-27 | 2012-12-11 | Orkney Islands | 1140367.08 | 11889.84 | -16046.76 | 0 | 0 | 0 | 0 | -4156.92 | 0 | 1136210.16 | 0 | [6 empty] | WG1 | 6.758% | DW13 | 7.984% | DW23 | 85.26%
402602 | Rova Head STC Lerwick | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2014-05-23 | 2014-08-29 | 2014-09-01 |  | All East Unitary Authorities | 7460 | -1638.64 | 0 | 0 | 0 | 0 | 0 | -1638.64 | 0 | 5821.36 | 0 | [6 empty] | CM_WWNI | 100%
502200 | Rovahead STC - CM and Biothermic digester | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | Shetland Islands | 0 | 0 | 15906.98 | 249.02 | 47.6 | 0 | -47.6 | 16156 | 0 | 16156 | 0 | [6 empty] | CM_WWNI | 100%
500491 | ROVAHEAD WwTW & STC CM - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-04-21 | 2016-11-30 | 2017-03-24 | 2018-12-17 | 2018-12-17 | Shetland Islands | 0 | 73000 | 388298 | 773512 | 119183 | -1816 | 1519.02 | 1353696.02 | 0 | 1353696.02 | 0 | [6 empty] | CM_WWNI | 100%
503041 | Rowallan Home Farm Kilmarnock - Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2018-08-15 | 2018-10-31 | 2019-01-14 | 2019-07-12 | 2019-07-19 | East Ayrshire | 0 | 0 | 0 | 6395.2 | 365260.58 | 156211.22 | 82635 | 610502 | 0 | 610502 | 0 | [6 empty] | CM_WSI | 100%
502911 | Rowett South Waste Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS0 | 2020-01-16 | 2021-01-28 | 2021-01-29 | 2022-08-25 | 2022-08-25 | Aberdeen City | 0 | 0 | 0 | 0 | 31343.51 | 65855.96 | 344268.5 | 441467.97 | 788740.88 | 1230208.85 | 0 | [6 empty] | SG5 | 100%
502692 | Royal Alexandria Hospital Temporary Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-04-21 | 2018-02-21 | 2018-02-21 | 2018-09-28 | 2018-09-28 | Renfrewshire | 0 | 0 | 0 | 697.56 | 66829.05 | 60043.03 | 31334.37 | 158904.01 | 490.97 | 159394.98 | 0 | [6 empty] | CM_WSNI | 100%
501180 | RTU Replacement and Provision of Emergency Outstations | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-12-07 | 2015-12-07 | 2016-02-10 | 2021-05-04 | 2021-05-05 | Scottish Water Wide | 0 | 82424 | -3233.77 | 977 | 0 | 0 | 60422.35 | 140589.58 | 1902.42 | 142492 | 0 | [6 empty] | CM_WSNI | 100%
502876 | Ruthven Water Pipe Bridge Aberuthven | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-08-15 | 2020-03-31 | 2020-06-08 | 2020-11-13 | 2020-11-13 | Perth and Kinross | 0 | 0 | 0 | 14679.7 | 49361.3 | 145134.99 | 513832.19 | 723008.18 | 0 | 723008.18 | 0 | [6 empty] | CM_WWI | 100%
501676 | RWI000447 - PETERHEAD BALMOOR RWI (Forehill WTW - Comp Flow) 1970 NK117474 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-06-02 | 2016-08-31 | Aberdeenshire | 0 | 0 | 12994.67 | 0 | 0 | 0 | 0 | 12994.67 | 0 | 12994.67 | 0 | [6 empty] | CM_WSNI | 100%
501912 | RWI000705 - NEWMORE RWI 1975 NH690724 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2028-02-14 | 2029-05-25 | 2029-09-28 | 2030-09-23 | 2030-12-24 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1609900.06 | 1609900.06 | 0 | [6 empty] | CM_WSI | 100%
402016 | RWI000743 Loch of Boardhouse RWI Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-11 | 2013-10-31 | 2014-01-27 | 2015-03-26 |  | Orkney Islands | 158625 | 22309 | 0.34 | -57.15 | 0 | 0 | 0 | 22252.19 | 0 | 180877.19 | 0 | [6 empty] | CM_M&G | 100%
502782 | Ryat Linn and Waulkmill Glen MIOS and Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-12-22 | 2017-12-22 | 2018-07-02 | 2018-08-27 | 2018-08-27 | East Renfrewshire | 0 | 0 | 0 | 69300 | 802553.49 | 374.22 | 0 | 872227.71 | 0 | 872227.71 | 0 | [6 empty] | CM_WSI | 100%
504589 | S TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-02-07 | 2022-04-08 | 2022-09-16 | 2024-03-29 | 2024-07-01 | - | 0 | 0 | 0 | 0 | 0 | 1148.09 | 243037.96 | 244186.05 | 0 | 244186.05 | 0 | [6 empty] | CM_WSNI | 100%
401637 | S002 - UID - At junction of No 50 Walkinshaw Street - Queen Mary Street Glasgow Green | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2013-03-18 | 2013-11-25 | 2014-02-26 | 2014-03-18 | Glasgow City | 147401 | 0 | 0 | 0 | -3697.4 | 0 | 0 | -3697.4 | 0 | 143703.6 | 0 | [6 empty] | EC04B | 100%
401638 | S003 - UID - Glasgow Green | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-29 | 2013-05-13 | 2013-05-13 | 2014-03-26 | 2014-03-27 | Glasgow City | 858894 | 0 | 0 | 0 | -2118.51 | 0 | 0 | -2118.51 | 0 | 856775.49 | 0 | [6 empty] | EC04B | 100%
401640 | S005 - UID - Outside No. 2 Orr Street Glasgow Green (GN no 17) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2012-06-21 | 2012-06-25 | 2013-03-01 | 2013-05-30 | Glasgow City | 723704 | -5510.77 | 0 | 0 | 0 | 0 | 0 | -5510.77 | 0 | 718193.23 | 0 | [6 empty] | EC04B | 100%
401642 | S009 - UID - Dalmarnock WwTP Inlet CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2017-09-21 | 2017-09-25 | 2019-02-28 | 2019-03-31 | Glasgow City | 248427 | 346389 | 1280138.7 | 3700201.48 | 5954831.64 | 1307.21 | 0 | 11282868.03 | 129739 | 11661034.03 | 1601836 |  |  |  |  | 1772.5 |  | EC04B | 38% | CM_WWNI | 62% | bar: Regulatory Outputs OMG-19
401608 | S011 - UID - Crookston-Rosshall CSO 144 Cairnhill Circus Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-17 | 2012-11-30 | 2013-01-14 | 2013-06-06 | 2013-09-12 | Renfrewshire | 549863.1 | 14786.15 | 0 | 0 | 0 | 0 | 0 | 14786.15 | 0 | 564649.25 | 5 | [6 empty] | EC04B | 100%
401643 | S014 - UID - Blackhall No.1 C.S.O. Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-01 | 2014-06-30 | 2015-05-25 | 2015-10-31 | 2018-03-31 | Renfrewshire | 201610 | 235520 | -49551.07 | 0 | -5880.25 | 0 | 0 | 180088.68 | 0 | 381698.68 | 64855 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401610 | S015 - UID - Blackhall Syphon CSO 150yrd NW of Jennys Well Road Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-09-18 | 2013-11-04 | 2014-05-26 | 2014-10-27 | Renfrewshire | 796012 | 91098 | 8049.2 | 0 | 0 | 0 | 0 | 99147.2 | 0 | 895159.2 | 2831 | [6 empty] | EC04B | 100%
401645 | S017 - UID - Adelphi Street Rear of Naut. College. | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Renfrewshire | 37343.79 | 1244.21 | -62.03 | 0 | 0 | 0 | 0 | 1182.18 | 0 | 38525.97 | 1721 | [6 empty] | EC10B | 100%
401646 | S018 - UID - Adelphi Street 20m East of Commercial Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-08-12 | 2015-07-31 | 2015-09-30 | Glasgow City | 44582 | 0 | 0 | -646.33 | 0 | 0 | 0 | -646.33 | 0 | 43935.67 | 329 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401647 | S019 - UID - Adelphi Street 20m West of Waddell Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2014-08-12 | 2015-07-31 | 2015-09-30 | Glasgow City | 1276232 | 80691.87 | 4867.82 | 1131.22 | 0 | 0 | -1.99 | 86688.92 | 0 | 1362920.92 | 71978 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401649 | S021 - UID - Adelphi Street at (in Mosque) at Mosque Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Glasgow City | 46859 | 141 | -250.78 | 0 | 0 | 0 | 0 | -109.78 | 0 | 46749.22 | 141 | [6 empty] | EC10B | 100%
401611 | S022 - UID - Adelphi Street at (Sheriff Court) Gorbals Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-12-30 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Glasgow City | 866356 | 5571.14 | 0 | 0 | 0 | 0 | 0 | 5571.14 | 0 | 871927.14 | 6717 | [6 empty] | EC10B | 100%
401650 | S023 - UID - Adelphi Street at Commercial Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-08-12 | 2015-07-31 | 2015-09-30 | Glasgow City | 40667 | 283.06 | 1066.25 | -481.62 | 0 | 0 | 0 | 867.69 | 0 | 41534.69 | 129 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401651 | S024 - UID - Adelphi Street at Crown Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Glasgow City | 2693040 | 34089 | 1696.71 | 0 | 0 | 0 | 0 | 35785.71 | 0 | 2728825.71 | 21445 | [6 empty] | EC10B | 100%
401653 | S026 - UID - Adelphi Street at McNeil Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-27 | 2014-05-05 | 2015-01-19 | 2015-03-24 | Glasgow City | 1358188.53 | 50458.47 | 2439.67 | 0 | 0 | 0 | 0 | 52898.14 | 0 | 1411086.67 | 8424 | [6 empty] | EC04B | 100%
401613 | S028 - UID - Carlton Place at South Portland Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-12-23 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Renfrewshire | 47133 | 1113 | -2649.71 | 0 | 0 | 0 | 0 | -1536.71 | 0 | 45596.29 | 488 | [6 empty] | EC10B | 100%
401654 | S029 - UID - Clyde Place at Commerce Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-30 | 2016-03-31 | Glasgow City | 67927 | 1376.83 | 1861.1 | -114.5 | 0 | 0 | 0 | 3123.43 | 0 | 71050.43 | 866 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401655 | S030 - UID - Clyde Place at Tradeston Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2014-01-06 | 2015-11-30 | 2016-02-29 | Glasgow City | 3055520 | 379657 | 19944 | 30908.44 | 11451.63 | 0 | 0.01 | 441961.08 | 0 | 3497481.08 | 266968 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401656 | S031 - UID - Clyde Place at West Street from 32 St Andrews Road Pollokshields | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-30 | 2018-10-31 | Glasgow City | 100499 | 0 | 0 | 0 | 0 | -1472.74 | 809.26 | -663.48 | 0 | 99835.52 | 5799 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401657 | S032 - UID - Clyde Place at West Street from Paisley Road-West Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-30 | 2016-03-31 | Glasgow City | 53746 | 1213.92 | 598.8 | -190.55 | 0 | 0 | 0 | 1622.17 | 0 | 55368.17 | 232 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401658 | S033 - UID - Junction Of Gorbals Street- Norfolk Street (No.1) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-23 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Glasgow City | 44865 | 0 | -1435.18 | 0 | 0 | 0 | 0 | -1435.18 | 0 | 43429.82 | 135 | [6 empty] | EC10B | 100%
401659 | S034 - UID - Paisley Road At Junction With West Street (No.2) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-30 | 2016-03-31 | Glasgow City | 54752 | 0 | 457.62 | 0 | 0 | 0 | 0 | 457.62 | 0 | 55209.62 | 228 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401660 | S035 - UID - Rutherglen Rd-Polmadie Rd (No. 1) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-30 | 2013-10-21 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 764717 | 2455 | -2012.23 | 0 | 0 | 0 | 0 | 442.77 | 0 | 765159.77 | 2076 | [6 empty] | EC04B | 100%
401661 | S036 - UID - Rutherglen Rd-Polmadie Rd (No. 2) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-30 | 2013-10-21 | 2014-11-13 | 2015-03-06 | Glasgow City | 50131.61 | 79.39 | 0 | 0 | 0 | 0 | -79.39 | 0 | 0 | 50131.61 | 234 | [6 empty] | EC04B | 100%
401662 | S037 - UID - Rutherglen Road at Fauldhouse St (Richmond Park) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2013-12-09 | 2014-07-30 | 2014-10-27 | Glasgow City | 62420 | 0 | 822.24 | 0 | 0 | 0 | 0 | 822.24 | 0 | 63242.24 | 0 | [6 empty] | EC04B | 100%
401663 | S038 - UID - Rutherglen Road in Park (Richmond Park) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-12-15 | 2020-02-11 | 2020-01-13 | 2020-12-31 | 2021-03-31 | South Lanarkshire | 207195.17 | 13292.83 | 8559 | 68130.85 | 152992.15 | 908650.13 | 1057226.86 | 2208851.82 | 8904.22 | 2424951.21 | 1916335 |  |  |  |  | 2950 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401664 | S039 - UID - Rutherglen Road Rear of No 473 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2013-12-09 | 2014-07-30 | 2014-10-27 | Glasgow City | 1004447.51 | 903.49 | -836.26 | 0 | 0 | 0 | 0 | 67.23 | 0 | 1004514.74 | 104.51 | [6 empty] | CM_WWI | 2.331% | CS11A | 5.995% | EC04B | 91.67%
401665 | S040 - UID - Springfield Quay (No. 1) Seaward Street R-O Cinema Kingston | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-11 | 2014-09-01 | 2015-02-10 | 2015-03-20 | Glasgow City | 53736 | 447 | -285.66 | 0 | 0 | 0 | 0 | 161.34 | 0 | 53897.34 | 3375 | [6 empty] | EC10B | 100%
401666 | S041 - UID - Springfield Quay No. 2 Car Park CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-10 | 2014-09-01 | 2015-02-10 | 2015-03-20 | Renfrewshire | 854401 | -21849 | 11405.16 | 0 | 0 | 0 | 0 | -10443.84 | 0 | 843957.16 | 66106 | [6 empty] | EC10B | 100%
401667 | S042 - UID - 83 Borgie Crescent - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-02 | 2011-12-07 | 2011-12-19 | 2012-01-25 | 2012-03-23 | South Lanarkshire | 20999.23 | 0 | 0 | 277.29 | 0 | 0 | 0 | 277.29 | 0 | 21276.52 | 0 | [6 empty] | EC04B | 100%
401668 | S043 - UID - Cambuslang Road Richmond Laundry - South East of Railway Rutherglen | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-12-02 | 2019-03-26 | 2019-05-21 | 2021-03-31 | 2021-07-31 | South Lanarkshire | 174698 | 36209 | 10953.38 | 76885.15 | 306790.47 | 1580192.97 | 575498.03 | 2586529 | 2250 | 2763477 | 2348796 |  |  |  |  | 8280 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401669 | S044 - UID - Clinic Johnson Drive - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-02 | 2013-05-27 | 2013-08-12 | 2014-02-17 | 2014-02-28 | South Lanarkshire | 498527 | 1623 | -1085.38 | 0 | 0 | 0 | 0 | 537.62 | 0 | 499064.62 | 3534 | [6 empty] | EC04B | 100%
401614 | S045 - UID - Clyde Industrial Estate Rutherglen | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS5 | 2010-11-17 | 2018-09-25 | 2019-01-11 | 2019-06-30 | 2019-08-31 | South Lanarkshire | 107706.31 | 15389.93 | 53873.78 | 98909.98 | 602339 | 29934 | 0 | 800446.69 | 847 | 909000 | 410766 |  |  |  |  | 982.22 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401685 | S046 - UID - Downiebrae Road Farme Estate Shieldhall No 39 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-12-03 | 2020-03-19 | 2020-03-27 | 2021-06-30 | 2021-08-31 | South Lanarkshire | 90517 | 5290.44 | 13209.48 | 47328.08 | 181469 | 362182.05 | 2233678.47 | 2843157.52 | 54837.85 | 2988512.37 | 397695 |  |  |  |  | 2990 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401686 | S047 - UID - Eastfield PS EO; Rutherglen | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2015-06-25 | 2015-08-03 | 2015-08-12 | 2015-08-12 | South Lanarkshire | 54503 | -991.23 | 0 | 0 | 0 | 0 | -702 | -1693.23 | 0 | 52809.77 | 0 | [6 empty] | EC04B | 100%
401687 | S048 - UID - Farme Estate PS EO; Downiebrae Road; Shieldhall No.40 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-12-03 | 2020-03-16 | 2020-03-27 | 2021-06-30 | 2021-07-31 | South Lanarkshire | 29320 | 7758 | 6878 | 39700 | 1442 | 5422 | 8437 | 69637 | 9863 | 108820 | 455597 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401688 | S050 - UID - Morriston Street at Monkcastle Drive - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-02-20 | 2013-03-28 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 905260 | 60350 | -12975.08 | -108.76 | 0 | 0 | -29.08 | 47237.08 | 0 | 952497.08 | 67933 | [6 empty] | EC04B | 100%
401689 | S051 - UID - Standford Hall Allison Drive - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-02-19 | 2013-03-28 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 19930 | -1636.96 | 0 | 0 | 0 | 0 | 0 | -1636.96 | 0 | 18293.04 | 0 | [6 empty] | EC04B | 100%
401616 | S053 - UID - Cressy Street off Govan Road in Ship Yards | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS5 | 2010-11-18 | 2018-03-22 | 2018-03-28 | 2020-03-10 | 2020-03-10 | Glasgow City | 172414 | 17738 | 46269.43 | 326611.77 | 950913 | 767720.86 | 1300.53 | 2110553.59 | 906.43 | 2283874.02 | 728927 |  |  |  |  | 5783.82 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
401618 | S055 - UID - Govan Road - Ibrox | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-01 | 2014-12-23 | 2015-09-14 | 2017-02-28 | 2017-03-31 | Glasgow City | 502945 | 290095 | 352959.98 | 210444.43 | 45.02 | 25.78 | -28.81 | 853541.4 | 0 | 1356486.4 | 498170 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401619 | S056 - UID - Govan Road 40177 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2014-12-23 | 2015-09-14 | 2016-09-30 | 2017-02-28 | Glasgow City | 388377 | 795900 | 369661.84 | -8439.04 | 2146.59 | 20.59 | -22.52 | 1159267.46 | 0 | 1547644.46 | 707835 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401620 | S057 - UID - Govan Road 40178 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2014-12-22 | 2015-09-14 | 2016-11-30 | 2017-03-31 | Glasgow City | 361706 | 122769 | 695569.66 | 20455.7 | 2608.84 | 69.06 | -69.06 | 841403.2 | 0 | 1203109.2 | 383746 | [6 empty] | CM_WWI | 13.64% | EC10B | 86.36% | bar: Regulatory Outputs OMG-19
401622 | S059 - UID - Mavisbank Quay at Mavisbank Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2013-02-20 | 2013-08-29 | 2014-03-24 | 2014-03-28 | Glasgow City | 597653.74 | 8442.09 | 0 | 0 | 0 | 0 | 0 | 8442.09 | 0 | 606095.83 | 4174 | [6 empty] | EC10B | 100%
401623 | S060 - UID - McKechnie Street off Govan Road CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2013-09-16 | 2013-11-04 | 2014-03-24 | 2014-03-31 | Glasgow City | 324073 | 25308 | -325.99 | 0 | 0 | 0 | 0 | 24982.01 | 0 | 349055.01 | 2352 | [6 empty] | EC10B | 100%
401400 | S063 - UID - Stag Street at Highland Lane | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-09-10 | 2011-08-22 | 2013-08-19 | 2014-03-12 | 2014-03-28 | Glasgow City | 818243 | 0 | 0 | -39179.19 | 0 | 0 | 35627.77 | -3551.42 | 0 | 814691.58 | 24757 | [6 empty] | EC10B | 100%
401690 | S065 - UID - 10 Holmbank Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-11-11 | 2014-09-22 | 2021-04-30 | 2021-04-30 | Glasgow City | 588476 | 59438 | -382.79 | 0 | 0 | 0 | -2.11 | 59053.1 | 0 | 647529.1 | 65156 | [6 empty] | EC04B | 100%
401692 | S068 - UID - Busby Bridge Downstream on West bank 12 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-15 | 2013-10-28 | 2015-01-19 | 2015-02-16 | East Renfrewshire | 351278.66 | 20784.34 | 2999.87 | -14974.14 | 0 | 0 | -3.71 | 8806.36 | 0 | 360085.02 | 4176 | [6 empty] | EC04B | 100%
401693 | S069 - UID - Busby Bridge Downstream on West Bank 4 inch | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-16 | 2013-10-28 | 2015-01-19 | 2015-02-16 | East Renfrewshire | 21597.1 | 129.16 | 0 | 0 | 0 | 0 | 0 | 129.16 | 0 | 21726.26 | 76 | [6 empty] | EC04B | 100%
401694 | S070 - UID - Cartside Drive Opposite Public Park on East Bank | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-01-09 | 2013-03-21 | 2013-07-04 | 2013-09-12 | East Renfrewshire | 59980 | -656.74 | 0 | 0 | 0 | 0 | 0 | -656.74 | 0 | 59323.26 | 133 | [6 empty] | EC04B | 100%
401626 | S072 - UID - Cartside Street at Sinclair Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 2015-10-30 | Glasgow City | 69769 | -3777.73 | 0 | 0 | 0 | 0 | 0 | -3777.73 | 0 | 65991.27 | 5004 | [6 empty] | EC04B | 100%
401696 | S073 - UID - East of New Bridge on South Bank Margaretta Buildings Clarkston Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2015-02-12 | 2015-03-30 | 2015-10-31 | 2016-03-31 | Glasgow City | 437780 | 671621 | -21212.18 | -1642.62 | 2.12 | 0 | 0 | 648768.32 | 0 | 1086548.32 | 638439 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401697 | S075 - UID - Millbrae Bridge on North Bank Millbrae Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-03 | 2016-03-14 | 2016-03-22 | 2019-01-31 | 2019-09-30 | Glasgow City | 5560 | 1527.05 | 2294.06 | 271.28 | 0 | 18.47 | 0 | 4110.86 | 0 | 9670.86 | 3283 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401698 | S076 - UID - Millbrae Bridge on South Bank Millbrae Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-03 | 2016-03-15 | 2016-03-22 | 2019-01-31 | 2019-03-31 | Glasgow City | 109367.15 | 502080.85 | 808540.82 | 55906.96 | 1361866.24 | 53134.32 | 8047.36 | 2789576.55 | 2210 | 2901153.7 | 3279862 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401699 | S077 - UID - Millholm Road Ejector Station | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-21 | 2013-08-12 | 2014-01-10 | 2014-02-03 | Glasgow City | 283653.19 | 1830.97 | 471.46 | 0 | 0 | 0 | 0 | 2302.43 | 0 | 285955.62 | 3538 | [6 empty] | EC04B | 100%
401700 | S079 - UID - Netherburn Avenue CSO (Williamwood Storm Tank) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2014-01-27 | 2014-11-10 | 2015-02-06 | East Renfrewshire | 514292 | 29253 | 1750.57 | 0 | 0 | 0 | 0 | 31003.57 | 0 | 545295.57 | 4467 | [6 empty] | EC04B | 100%
401702 | S082 - UID - Old Castle Road Junction At Delvin Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2012-11-30 | 2013-02-04 | 2013-03-25 | 2013-05-21 | Glasgow City | 33021 | 849.16 | 0 | 0 | 0 | 0 | 0 | 849.16 | 0 | 33870.16 | 304 | [6 empty] | EC04B | 100%
401703 | S083 - UID - Overflow adjacent to No 1A Moray Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-07-30 | 2014-03-03 | 2014-11-09 | 2015-01-28 | East Renfrewshire | 705152 | -27124 | -8144.4 | 1.05 | 0 | 0 | -52.36 | -35319.71 | 0 | 669832.29 | 10365 | [6 empty] | EC04B | 100%
401856 | S086 - UID - Rear of No 88 Moray Gardens (Overlee Park) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-09-02 | 2013-07-19 | 2014-02-24 | 2014-11-09 | 2015-01-27 | East Renfrewshire | 357124 | 9911 | 1952.41 | 0 | 0 | 0 | 0 | 11863.41 | 0 | 368987.41 | 7776 | [6 empty] | EC04B | 100%
401705 | S087 - UID - Scotwood Overflow North East of Lay-by Busby Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-12-03 | 2020-02-12 | 2020-01-10 | 2021-07-31 | 2021-11-30 | East Renfrewshire | 22780.69 | 26463.49 | 77503.31 | 227139.31 | 326614.2 | 2616647.44 | 3899309.6 | 7173677.35 | 177281.98 | 7373740.02 | 3110294 |  |  |  |  | 63710 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401706 | S088 - UID - Williamwood Storm Tank Netherburn Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2013-10-21 | 2014-10-09 | 2015-01-28 | East Renfrewshire | 251567 | 1993.79 | 1160.85 | 0 | 0 | 0 | 0 | 3154.64 | 0 | 254721.64 | 5718 | [6 empty] | EC04B | 100%
401707 | S089 - UID - Williamwood Storm Tank No1 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2013-10-21 | 2014-10-09 | 2015-03-06 | East Renfrewshire | 338502 | -10367 | 39.62 | 0 | 0 | 0 | 0 | -10327.38 | 0 | 328174.62 | 3619 | [6 empty] | EC04B | 100%
401708 | S090 - UID - Williamwood Storm Tank East of No 76 First Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-16 | 2014-01-27 | 2014-11-10 | 2015-02-06 | East Renfrewshire | 16218.86 | 100.14 | -100.14 | 0 | 0 | 0 | 0 | 0 | 0 | 16218.86 | 274 | [6 empty] | EC04B | 100%
401630 | S092 - UID - 296 Linthaugh Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2013-01-22 | 2013-01-28 | 2013-06-06 | 2013-09-12 | Glasgow City | 740679.28 | 2526.3 | 0 | 0 | 0 | 0 | 0 | 2526.3 | 0 | 743205.58 | 0 | [6 empty] | EC04B | 100%
401709 | S093 - UID - After Footbridge in Dovecothall Field | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS7 | 2010-12-15 | 2016-12-21 | 2017-01-23 | 2017-12-31 | 2018-02-28 | East Renfrewshire | 531925 | 88182 | 2127406 | 3715323 | -45114.52 | -56106.13 | 1921.4 | 5831611.75 | 0 | 6363536.75 | 4793730 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401631 | S094 - UID - At rear of Leverndale Hospital Crookston Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-11-09 | 2012-11-19 | 2012-12-17 | 2013-01-17 | Glasgow City | 26803 | 3313.97 | 0 | 0 | 0 | 0 | 0 | 3313.97 | 0 | 30116.97 | 1159 | [6 empty] | EC04B | 100%
401710 | S096 - UID - Kings Inch Road at Ferry Road Renfrew | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-09 | 2016-07-21 | 2016-10-03 | 2017-10-31 | 2018-01-31 | Renfrewshire | 372283 | 153652 | 364372.88 | 1486484.24 | 0 | -2125.64 | 0 | 2002383.48 | 0 | 2374666.48 | 807733 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401633 | S097 - UID - New PS EO at Provost Drive Court Renfrew | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-07-17 | 2012-11-14 | 2012-12-31 | 2016-10-31 | Glasgow City | 1201151 | 1468404 | 1751817.62 | 13210.68 | 12512.77 | 0 | 0.84 | 3245945.91 | 0 | 4447096.91 | 745277 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401718 | S098 - UID - Pollokshaws Road Pollok Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-24 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 894098 | 24073 | -10347.37 | 0 | 0 | 0 | 0 | 13725.63 | 0 | 907823.63 | 20137 | [6 empty] | EC04B | 100%
401719 | S099 - UID - Renfrew P.S.S. C.S.O. North Lodge Road Renfrew | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2014-04-28 | 2015-04-01 | 2015-04-17 | 2015-04-17 | Renfrewshire | 94561 | -120.52 | 0 | 0 | 0 | 0 | -18.32 | -138.84 | 0 | 94422.16 | 0 | [6 empty] | EC10B | 100%
401721 | S102 - UID - Shawbridge Street North of Bridge | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-23 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 24500.59 | 1620.85 | 1272.03 | 0 | 0 | 0 | 0 | 2892.88 | 0 | 27393.47 | 0 | [6 empty] | EC04B | 100%
401722 | S103 - UID - Shawbridge Street South of Bridge | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-23 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 34998 | 1094.67 | 1238.95 | 0 | 0 | 0 | 0 | 2333.62 | 0 | 37331.62 | 466 | [6 empty] | EC04B | 100%
401635 | S104 - UID - Storm Sewage Overflow 63 Haining Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-07-17 | 2012-11-15 | 2012-12-07 | 2013-01-17 | Renfrewshire | 84062 | 73.41 | 1453.68 | -78.88 | 17.2 | 0 | -17.2 | 1448.21 | 0 | 85510.21 | 7804 | [6 empty] | EC10B | 100%
401723 | S105 - UID - Thornliebank Road Opposite Auldhouse Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-05-22 | 2013-10-21 | 2014-10-09 | 2014-12-19 | Glasgow City | 332879 | 383 | 429.7 | 0 | 0 | 0 | 0 | 812.7 | 0 | 333691.7 | 2644 | [6 empty] | EC04B | 100%
401744 | S106 - UID - Greenlaw Road No8 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-10-15 | 2014-11-17 | 2015-05-31 | 2015-07-31 | Glasgow City | 788607 | 79830 | 1417.71 | -1073.35 | 0 | 0 | 0 | 80174.36 | 0 | 868781.36 | 94950 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401745 | S107 - UID - Works Yard Dock Street Clydebank East | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-12-05 | 2015-02-18 | 2017-12-31 | 2018-02-28 | Glasgow City | 1319164 | -498084 | 416920 | 4577 | 1731 | 619 | 0.03 | -74236.97 | 0 | 1244927.03 | 570745 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401746 | S108 - UID - Millbrae Crescent Railway line CSO Yoker (GN no 45) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-12-05 | 2015-07-08 | 2020-03-02 | 2020-03-02 | Glasgow City | 786743 | 3995559.65 | 3438578.12 | 1220658.21 | 4431310.11 | 1548271.62 | 3916.17 | 14638293.88 | 5000.05 | 15430036.93 | 5121897.06 |  |  |  |  | 1422.9 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
401747 | S109 - UID - Greenlaw Road and 32 Lasswade Street (GN no.67) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-10-14 | 2015-02-18 | 2015-05-31 | 2015-07-31 | Glasgow City | 46682.5 | 900.5 | 279.17 | -248.24 | 0 | 0 | 0 | 931.43 | 0 | 47613.93 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401748 | S110 - UID - Napier St - Glasgow Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-11-28 | 2015-03-02 | 2015-03-19 | 2015-03-31 | Glasgow City | 95250.39 | 359.55 | 141.23 | 0 | 0 | 0 | 0 | 500.78 | 0 | 95751.17 | 1552 | [6 empty] | EC10B | 100%
401749 | S111 - UID - Junction of Dumbarton Road - Dyke Road - Culvert to Clyde | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2014-12-05 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Glasgow City | 281109 | 576163 | 7347.28 | 1405.01 | -383.52 | 0 | 0 | 584531.77 | 0 | 865640.77 | 516437 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401750 | S112 - UID - Agamemnon Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2016-03-15 | 2016-03-24 | 2017-01-31 | 2017-03-31 | Glasgow City | 144601 | 349619 | 2228968.03 | 18909.29 | -1267.89 | 0 | 0 | 2596228.43 | 0 | 2740829.43 | 469621 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401751 | S113 - UID - 49 Dumbarton Road (East) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-14 | 2016-03-24 | 2017-01-31 | 2017-03-31 | Glasgow City | 104453 | 6789 | -0.21 | 0 | 1183.99 | 0 | 0 | 7972.78 | 0 | 112425.78 | 590383 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401752 | S114 - UID - Opposite Lovatt Arms Public House No 2560 Dumbarton Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-11-28 | 2015-06-16 | 2016-03-31 | 2016-03-31 | Glasgow City | 17000 | 0 | 484 | -334.32 | 0 | 0 | 0 | 149.68 | 0 | 17149.68 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401753 | S115 - UID - Junction of South Street - Edzell Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-10-31 | 2017-11-30 | 2018-02-28 | Glasgow City | 45620 | 2783 | 4302.15 | 1572.04 | 517.9 | 365.78 | 0 | 9540.87 | 0 | 55160.87 | 2498 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401754 | S116 - UID - Junction of South Street - Jordan Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-29 | 2016-10-31 | 2017-12-31 | 2018-03-31 | Glasgow City | 90215 | 178011 | 1500183.7 | 1821773.97 | 9711.33 | 8757.5 | 0 | 3518437.5 | 0 | 3608652.5 | 410689 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401755 | S117 - UID - Junction of South Street - Scotstoun Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-05-16 | 2017-06-30 | 2017-08-31 | Glasgow City | 106896 | 117903 | 1829168.2 | 668603.98 | 440992.22 | -6884.11 | 0.01 | 3049783.3 | 0 | 3156679.3 | 610494 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401756 | S118 - UID - Junction of South Street and Ferryden Street (Glasgow N no 61) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-22 | 2016-10-10 | 2017-06-30 | 2017-08-31 | Glasgow City | 19447.73 | 2972.27 | 4223 | -2848.07 | 1558.76 | 0 | 0 | 5905.96 | 0 | 25353.69 | 4994 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401757 | S119 - UID - Junction of South Street - Sawmill Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-06-29 | 2017-08-31 | 2017-10-31 | Glasgow City | 95717 | 28913 | 12776.02 | 290847.51 | 1438.96 | -630.04 | 0 | 333345.45 | 0 | 429062.45 | 524390 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401759 | S121 - UID - Clydeway Expressway South of Sandyford Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 200227 | 18206 | 4337.77 | -4933.12 | 0 | 0 | 0 | 17610.65 | 0 | 217837.65 | 956503 | [6 empty] | EC10B | 100%
401762 | S124 - UID Outside No205 Finnieston Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2012-03-27 | 2015-01-05 | 2015-01-08 | 2015-01-08 | Glasgow City | 205924.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205924.99 | -2971 | [6 empty] | EC10B | 100%
401764 | S126 - UID Junction of Lancefield Quay - Lancefield Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2012-03-26 | 2015-01-05 | 2015-01-09 | 2015-01-09 | Glasgow City | 48327.85 | 50.63 | 0 | 0 | 0 | 0 | 0 | 50.63 | 0 | 48378.48 | 0 | [6 empty] | EC10B | 100%
401773 | S135 - UID 237 South Street Whiteinch | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-22 | 2016-03-29 | 2017-05-31 | 2017-08-31 | Glasgow City | 170582 | 85200 | 1997602.51 | 424098.49 | 2637.69 | 0 | 0 | 2509538.69 | 0 | 2680120.69 | 743049 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401774 | S136 - UID South of Clydeside Expressway roundabout Ferry Road (GN no 40) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2011-09-30 | 2011-09-30 | 2015-05-13 | 2015-06-08 | Glasgow City | 1596.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.22 | 1064 | [6 empty] | EC10B | 100%
401775 | S137 - UID Between Sawmill Road - Castlebank Crescent Castlebank Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-14 | 2016-03-24 | 2017-05-31 | 2017-08-31 | Glasgow City | 117002 | 376543 | 2489028.09 | 653666.86 | 11832.75 | -23421.03 | 0 | 3507649.67 | 0 | 3624651.67 | 947501 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401776 | S138 - UID East of Anderson Street at Castlebank Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-11 | 2016-03-16 | 2017-01-31 | 2017-03-31 | Glasgow City | 107379.23 | 766059.77 | 2117683.52 | -160315.69 | 38798.46 | 0 | -0.01 | 2762226.05 | 0 | 2869605.28 | 1002839 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401782 | S144 - UID - Corkerhill Road at Alness Crescent CSO Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 696259 | -3962.11 | 1050.8 | 0 | 0 | 0 | 0 | -2911.31 | 0 | 693347.69 | 17898 | [6 empty] | EC04B | 100%
401783 | S145 - UID - Corkerhill Road at Arisaig Drive CSO Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-16 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14953 | -1459 | -100.03 | 0 | 0 | 0 | 0 | -1559.03 | 0 | 13393.97 | 0 | [6 empty] | EC04B | 100%
401784 | S146 - UID - 245 Corkerhill Road CSO Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14436.08 | 99.92 | 29.67 | 0 | 0 | 0 | -99.92 | 29.67 | 0 | 14465.75 | 0 | [6 empty] | EC04B | 100%
401785 | S147 - UID - Corkerhill Road at Mosspark Drive Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14286 | -1666.93 | 0 | 0 | 0 | 0 | 0 | -1666.93 | 0 | 12619.07 | 0 | [6 empty] | EC04B | 100%
401787 | S149 - UID - Rear Of No11 Kinnell Avenue Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14991.74 | 100.26 | -100.26 | 0 | 0 | 0 | 0 | 0 | 0 | 14991.74 | 0 | [6 empty] | EC04B | 100%
401788 | S150 - UID - Burnfield Cottages Giffnock Overflow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS7 | 2010-12-15 | 2016-09-14 | 2016-09-21 | 2017-05-31 | 2018-09-30 | East Renfrewshire | 204647 | 77586 | 800305 | 120942.32 | 27496.74 | 113.82 | 2647.12 | 1029091 | 0 | 1233738 | 480445 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401789 | S151 - UID - 899 Aikenhead Road at Curtis Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-08-31 | 2018-10-31 | South Lanarkshire | 21093880 | 32624429.96 | 55445463.24 | 11542999.6 | 4587122.19 | 9234464.6 | -155.91 | 113434323.68 | 0 | 134528203.68 | 95337328 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401790 | S152 - UID - Curtis Avenue at Ardmay Crescent CSO Mount Florida | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-30 | 2018-10-31 | South Lanarkshire | 114680 | 0 | 0 | 0 | 0 | -1517.82 | 2249.78 | 731.96 | 0 | 115411.96 | 3443 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401791 | S153 - UID - Prospecthill Road at Asda Store Entrance | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-30 | 2018-10-31 | South Lanarkshire | 99683 | 0 | 0 | 0 | 0 | -2026.12 | 1362.66 | -663.46 | 0 | 99019.54 | 2474 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401792 | S154 - UID Causeyside St CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-02-29 | 2016-06-20 | 2017-11-30 | 2018-01-31 | Renfrewshire | 18662 | -3035 | 0 | 1074.82 | 15.31 | 1556.62 | 0 | -388.25 | 0 | 18273.75 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401793 | S155 UID Town Centre No2 CSO South Corner of 20 Forbes Place Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-08-02 | 2016-08-03 | 2016-08-31 | 2016-10-31 | Renfrewshire | 19618 | -3963 | -3298.39 | 0 | 0 | 0 | 3.34 | -7258.05 | 0 | 12359.95 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401794 | S156 UID Town Centre West No1 CSO Paisley Cart Walk West of Tannery Bridge Street Abbey Bridge | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2016-02-29 | 2016-06-20 | 2018-02-28 | 2019-08-31 | Renfrewshire | 352644.32 | 279429.93 | 1066187.75 | 1139373 | 49349 | 107347.6 | 795.4 | 2642482.68 | 0 | 2995127 | 3345359 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401795 | S157 UID Seedhill No1 CSO West of 6 Seedhill at Mill Street Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS3 | 2010-12-15 | 2016-09-29 | 2017-11-13 | 2021-01-31 | 2021-04-30 | Renfrewshire | 270046 | 58430 | 95533.85 | 117437.56 | 93799.15 | 522441.35 | 876259.24 | 1763901.15 | 7560.51 | 2041507.66 | 1421093 |  |  |  |  | 5210 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
401798 | S160 UID Love Street CSO 98 New Sneddon Street Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 991076 | 220182 | 2999.97 | -2271.98 | 0 | 0 | 0 | 220909.99 | 0 | 1211985.99 | 17030 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401799 | S161 UID New Sneddon St | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 65129.71 | 17360.29 | 50.02 | -962.31 | 0 | 0 | 0 | 16448 | 0 | 81577.71 | 4554 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401800 | S162 UID Old Sneddon Street Bridge Abercarn Bridge Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 19980 | 1001 | -0.2 | -3385.85 | 0 | 0 | 0 | -2385.05 | 0 | 17594.95 | 286 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401801 | S163 UID Rowan Street CSO 216 Rowan Street Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-28 | 2014-06-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 1001259 | 20674.94 | 685034.39 | -24037 | 0 | 0 | 0 | 681672.33 | 0 | 1682931.33 | 9017 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401803 | S165 UID Rear of No7 Falside Road Paisley Rear of Neilston Road CSO in DAS | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-08-26 | 2014-12-15 | 2015-07-31 | 2015-09-30 | Renfrewshire | 410628.39 | 104956.61 | 11290.12 | -2159.21 | 0 | 0 | 0 | 114087.52 | 0 | 524715.91 | 28238 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401804 | S166 UID Park Road CSO Paisley No4 Park Ave | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-25 | 2014-11-28 | 2015-02-26 | 2015-03-25 | Renfrewshire | 121429 | 215 | 4619.03 | 2660.13 | 0 | 0 | 0 | 7494.16 | 0 | 128923.16 | 1593 | [6 empty] | EC04B | 100%
401817 | S179 - UID - Near River Clyde Walkway South East of Westhorn Playground | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2014-02-12 | 2014-04-01 | 2016-03-31 | 2016-03-31 | Glasgow City | 1755444 | 786200 | 3632 | 0 | -463.56 | 0 | 0 | 789368.44 | 0 | 2544812.44 | 1054 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401819 | S181 - UID - Near junction of Kempock Street - Caimcraig Street GN No20 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-07-23 | 2013-09-02 | 2014-02-27 | 2014-03-25 | Glasgow City | 916410 | 1000 | -0.08 | 0 | -3002.06 | 0 | 0 | -2002.14 | 0 | 914407.86 | 0 | [6 empty] | EC04B | 100%
401820 | S182 - UID - Potter Place at No9 Rattray Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-07-23 | 2013-11-29 | 2014-05-29 | 2014-10-28 | Renfrewshire | 491178 | 1537.4 | 252.56 | 0 | 0 | 0 | 0 | 1789.96 | 0 | 492967.96 | 800 | [6 empty] | EC04B | 100%
401823 | S185 - UID - Tollcross Park at Tollcross Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-26 | 2013-03-27 | 2015-02-26 | 2015-03-31 | Glasgow City | 27630.14 | 243.82 | 0 | 0 | 0 | 0 | 0 | 243.82 | 0 | 27873.96 | 0 | [6 empty] | EC04B | 100%
401824 | S186 - UID - Tollcross Park West of No 785 Tollcross Road GN No8 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-26 | 2013-03-27 | 2015-02-26 | 2015-03-31 | Glasgow City | 809798 | 15626.93 | 2309 | 0 | -285.5 | 0 | 0 | 17650.43 | 0 | 827448.43 | 1719 | [6 empty] | EC04B | 100%
401825 | S187 - UID - Tollcross Park at footbridge of GN No7 Leisure Centre | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-27 | 2014-03-31 | 2015-02-19 | 2015-03-27 | Glasgow City | 2052217 | 20598 | 0.28 | 0 | -191.92 | 0 | 0 | 20406.36 | 0 | 2072623.36 | 2187 | [6 empty] | EC04B | 100%
401826 | S188 - UID - Wellshot Road at Fairburn Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-28 | 2013-03-28 | 2015-02-19 | 2015-03-27 | Glasgow City | 25936.31 | 13.69 | 1240.69 | 0 | -388.69 | 0 | -13.69 | 852 | 0 | 26788.31 | 0 | [6 empty] | EC04B | 100%
401827 | S189 - UID - Opposite No4 Fairholm Street GN No6 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-28 | 2013-03-28 | 2015-02-19 | 2015-03-27 | Glasgow City | 27121 | 694 | 134.89 | 0 | -239.6 | 0 | 0 | 589.29 | 0 | 27710.29 | 0 | [6 empty] | EC04B | 100%
401828 | S190 - UID - 186 Ardgay Street Rear of No182-186 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-12-13 | 2013-03-27 | 2013-03-27 | 2014-01-28 | 2014-03-25 | Glasgow City | 2880550 | 2087.82 | 1740.45 | 7591.22 | -7591.22 | 0 | 0 | 3828.27 | 0 | 2884378.27 | 321.35 | [6 empty] | EC04B | 33.42% | CS15 | 66.58%
401829 | S191 - UID - Storm Sewage Overflow GN No5 Culross Lane | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-07-08 | 2013-11-27 | 2014-03-12 | 2014-03-28 | Glasgow City | 369585 | 0 | 700 | 0 | -7519.52 | 0 | 0 | -6819.52 | 0 | 362765.48 | 348 | [6 empty] | EC04B | 100%
401830 | S192 - UID - Carmyle Pumping Station River Road at Bowling Green | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-29 | 2014-01-06 | 2014-08-14 | 2015-03-19 | Glasgow City | 12882 | 0 | 0 | 0 | -679.5 | 0 | 0 | -679.5 | 0 | 12202.5 | 0 | [6 empty] | EC04B | 100%
401831 | S193 - UID - Outside No19 River Road GN No83 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-13 | 2014-01-13 | 2014-08-14 | 2015-03-19 | Glasgow City | 897049 | 54620 | 0 | 0 | -7924.08 | 0 | 0 | 46695.92 | 0 | 943744.92 | 0 | [6 empty] | EC04B | 100%
401832 | S194 - UID - At junction of River Road - Ardgargie Drive GN No16 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-15 | 2014-01-20 | 2014-08-14 | 2015-02-16 | Glasgow City | 876360 | 0 | 0 | 0 | -4073.78 | 0 | 0 | -4073.78 | 0 | 872286.22 | 0 | [6 empty] | EC04B | 100%
401833 | S195 - UID - West of No149 Baillieston Road GN No4 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-06-27 | 2013-06-28 | 2016-10-31 | 2016-12-31 | Glasgow City | 5747.47 | 194.82 | 70.98 | 0 | 0 | 0 | 0 | 265.8 | 0 | 6013.27 | 0 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401834 | S196 - UID - Baillieston Road CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-06-26 | 2013-06-28 | 2016-10-31 | 2016-12-31 | Glasgow City | 1061129 | 5312.37 | 170340.69 | 25443.01 | 29448.98 | 0 | 0 | 230545.05 | 0 | 1291674.05 | 4525 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401835 | S197 - UID - Springhill Road Roundabout | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-09 | 2014-03-19 | 2014-03-24 | 2014-06-10 | 2015-02-04 | Glasgow City | 648671 | 27135 | 0.27 | 0 | 51000 | 0 | 0 | 78135.27 | 0 | 726806.27 | 27138 | [6 empty] | EC04B | 100%
401671 | S202 - UID - Cambuslang No.1 Pumping Station Cambuslang Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2015-04-10 | 2015-04-22 | 2015-04-29 | 2015-06-08 | Glasgow City | 150546.22 | 2025.77 | 0 | 0 | 0 | 0 | 2.45 | 2028.22 | 0 | 152574.44 | 0 | [6 empty] | EC10B | 100%
401960 | S206 - UID - Corkerhill Road South of Railway Bridge CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-21 | 2013-05-24 | 2013-09-16 | 2014-08-11 | 2014-12-19 | Glasgow City | 418129 | -2286 | -284 | 0 | 0 | 0 | 0 | -2570 | 0 | 415559 | 2581 | [6 empty] | EC04B | 100%
401961 | S207 - UID - In Crossmill Avenue Opposite No. 54 CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS7 | 2011-03-21 | 2016-12-20 | 2017-01-20 | 2017-08-31 | 2017-10-31 | Glasgow City | 18502 | 23413 | 85812 | 157793 | 2078.45 | -3954.3 | -0.15 | 265142 | 0 | 283644 | 12883 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401962 | S208 - UID - Dalmarnock Bridge Overflow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2011-03-21 | 2013-03-26 | 2017-03-29 | 2019-02-28 | 2019-03-31 | Glasgow City | 52000 | 0 | 29972 | 278718.57 | 28297 | 28188.37 | 594.05 | 365769.99 | 350.57 | 418120.56 | 67739 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401967 | S209 - UID - Dalmarnock WWTW Storm Tank Overflow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS3 | 2011-03-21 | 2017-12-21 | 2017-12-22 | 2019-02-28 | 2019-03-31 | Glasgow City | 60000 | 1621.48 | 616641.52 | 1944337 | 3406564 | 1894211.17 | 519446.22 | 8382821.39 | 7178.61 | 8450000 | 529643 |  |  |  |  | 21270 |  | EC04B | 38% | CM_WWNI | 62% | bar: Regulatory Outputs OMG-19
401969 | S210 - UID - CSO UNKNOWN - New CSO Junction of South Street and Scotstoun Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-21 | 2016-03-29 | 2016-11-07 | 2017-06-30 | 2017-08-31 | Glasgow City | 43268.4 | 2070.6 | 6763.8 | -6064.8 | 1495 | -557.87 | 0 | 3706.73 | 0 | 46975.13 | 6434 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401970 | S211 - CSO new 13 Hall Street Clydebank | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-21 | 2016-03-14 | 2016-03-24 | 2017-01-31 | 2017-03-31 | Glasgow City | 31764 | -134 | -0.43 | 0 | 180.86 | 0 | 0.01 | 46.44 | 0 | 31810.44 | 2968 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402483 | S212 - UID - Parkhead - South West Corner of Hospital Grounds (GN No 21) Belvidere Hospital | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-11-16 | 2013-05-27 | 2013-08-19 | 2014-03-21 | 2014-03-31 | Glasgow City | 727845 | 0 | -0.1 | 0 | -5160.89 | 0 | 0 | -5160.99 | 0 | 722684.01 | 0 | [6 empty] | EC04B | 100%
402491 | S213 - UID - Millholm Road Ejector Station | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-12-14 | 2013-05-16 | 2013-08-12 | 2014-01-10 | 2014-02-03 | Glasgow City | 2855 | 573.29 | -471.46 | 0 | 0 | 0 | 0 | 101.83 | 0 | 2956.83 | 145 | [6 empty] | EC04B | 100%
402752 | S217 - Riverside Gardens PS EO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-06-28 | 2013-03-20 | 2013-05-20 | 2013-08-30 | 2013-11-28 | East Renfrewshire | 180757 | -141.27 | 0 | 0 | 0 | 0 | 0 | -141.27 | 0 | 180615.73 | 515 | [6 empty] | EC04B | 100%
402753 | S218 - Polmadie Road (at Calder Street) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2012-06-28 | 2016-03-15 | 2016-03-22 | 2020-03-11 | 2020-03-04 | Glasgow City | 90623 | 225799 | 99356.3 | 9696.78 | 0 | 1160629.38 | 19352.72 | 1514834.18 | 1586.84 | 1607044.02 | 1636394 |  |  |  |  | 1669.35 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
402830 | S220 UID Marshalls Lane PS | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2013-03-20 | 2013-03-28 | 2013-11-26 | 2014-01-30 | Renfrewshire | 96583 | 461.12 | 0 | 0 | 0 | 0 | 0 | 461.12 | 0 | 97044.12 | 267 | [6 empty] | EC04B | 100%
402831 | S221 Piazza PS EO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2013-03-20 | 2013-03-28 | 2013-08-30 | 2013-11-25 | Renfrewshire | 93481 | -331.14 | 0 | 0 | 0 | 0 | 0 | -331.14 | 0 | 93149.86 | 159 | [6 empty] | EC04B | 100%
402832 | S222 Park Road Storage Tank EO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2015-03-25 | 2015-03-25 | 2015-03-25 | 2015-03-27 | Renfrewshire | 22980.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22980.29 | 53754 | [6 empty] | EC04B | 100%
402755 | S224 - 253 Byres Road CSO Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2012-07-10 | 2017-12-20 | 2018-03-26 | 2019-03-31 | 2019-06-30 | Glasgow City | 88596.93 | 58103.29 | 23592.16 | 508965.62 | 901187 | 27555 | 0 | 1519403.07 | 0 | 1608000 | 1127279 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402756 | S225 - Balmoral Street Pumping Station | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2013-03-20 | 2013-03-28 | 2013-11-26 | 2014-01-21 | Glasgow City | 98331.76 | 675.03 | 0 | 0 | 0 | 0 | 0 | 675.03 | 0 | 99006.79 | 260 | [6 empty] | EC10B | 100%
402757 | S226 - In grounds of Corpus Christi Primary School (No 44on Glasgow N List) Alderman Rd | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-06-29 | 2015-10-31 | 2016-01-31 | Glasgow City | 161661 | 199818 | 1358.71 | -1506.28 | 0 | 0 | 0 | 199670.43 | 0 | 361331.43 | 295069 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402758 | S227 - At junction of Alderman Road and (GN no 52) Hermitage Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-08-07 | 2015-12-31 | 2016-01-31 | Glasgow City | 219495 | 324824 | 908.73 | 147.24 | 0 | 0 | 0 | 325879.97 | 0 | 545374.97 | 396268 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402759 | S228 - Strauss Avenue CSO South of No.16 Clydebank | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-06-18 | 2015-10-31 | 2016-01-31 | West Dunbartonshire | 154731 | 194867.75 | 6.59 | -69.25 | 0 | 0 | 0 | 194805.09 | 0 | 349536.09 | 221953 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402760 | S229 - 193 Durban Avenue CSO Mountblow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-26 | 2015-05-18 | 2015-10-31 | 2016-01-31 | West Dunbartonshire | 144915 | 265170.34 | 1647.6 | -301.32 | 0 | 0 | 0 | 266516.62 | 0 | 411431.62 | 326098 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402833 | S233 UID Glencorse St at the junction of Abbeyhill St Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2014-12-22 | 2015-01-12 | 2015-03-30 | 2015-03-31 | Glasgow City | 818636.97 | 167645.96 | 2436.75 | -305.5 | 0 | 0 | 0 | 169777.21 | 0 | 988414.18 | 2594 | [6 empty] | EC04B | 100%
402834 | S234 UID Cranhill SO Cranhill Park Edinburgh Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2014-10-31 | 2014-11-06 | 2015-02-19 | 2015-03-23 | Glasgow City | 499757.51 | 131962.49 | -123.67 | 0 | 0 | 0 | 0 | 131838.82 | 0 | 631596.33 | 2800 | [6 empty] | EC04B | 100%
403140 | S236 - Dalmuir GSS Strategic Solution | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-12-18 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2015-04-30 | Glasgow City | 2239336.14 | 1650.48 | 0 | 0 | 0 | 0 | 2.74 | 1653.22 | 0 | 2240989.36 | 5002 | [6 empty] | EC10B | 100%
403362 | S237 - UID - Monteith Drive WWPS Stamperland | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-03-18 | 2013-05-16 | 2013-10-21 | 2014-01-17 | 2014-03-20 | Glasgow City | 82514 | -3298.09 | 198.8 | 0 | 0 | 0 | 0 | -3099.29 | 0 | 79414.71 | 3916 | [6 empty] | EC04B | 100%
403474 | S238 - UID - Junction of South Street and Dilwara Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-05-13 | 2014-08-29 | 2014-09-01 | 2014-09-03 | 2014-10-27 | Glasgow City | 9904.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9904.75 | 438 | [6 empty] | EC10B | 100%
403564 | S239 - UID - Kelvinside K15 Sth Bnk Hamilton Dr Lane | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-08-27 | 2014-11-28 | 2014-12-03 | 2015-01-12 | 2015-02-27 | Glasgow City | 17536 | 7714 | -4718.24 | 0 | 0 | 0 | 0 | 2995.76 | 0 | 20531.76 | 7936 | [6 empty] | EC10B | 100%
403689 | S240 - UID - City Centre Bell St East-sptmth Cso | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-01-30 | 2014-07-22 | 2014-08-11 | 2014-08-28 | 2014-10-27 | Glasgow City | 16261 | 1031.62 | 0 | 0 | 0 | 0 | 0 | 1031.62 | 0 | 17292.62 | 393 | [6 empty] | EC04B | 100%
404009 | S241 - UID - Renfrew Haining Road CSO (Remedial works) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2014-11-27 | 2015-02-27 | 2017-06-15 | 2017-05-18 | 2017-05-18 | Renfrewshire | 191106 | 618.08 | 6300 | -1381.27 | 0 | 0 | 0 | 5536.81 | 0 | 196642.81 | 618547 | [6 empty] | EC10B | 100%
502608 | Safety Review of Structural Plastic Media Filters | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-10-31 | 2018-08-30 | 2018-10-26 | 2019-07-12 | 2019-07-12 | Scottish Water Wide | 0 | 0 | 1555.14 | 90171.95 | 120274.29 | 27978.86 | 0.05 | 239980.29 | 0 | 239980.29 | 0 | [6 empty] | CM_M&G | 100%
503371 | Saline WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 | 2029-04-16 | Fife | 0 | 0 | 0 | 0 | 77497.49 | 5050.47 | 0 | 82547.96 | 59452.04 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
30737 | Salsburgh STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-08 | 2012-01-24 | 2012-06-11 | 2013-06-20 | 2013-07-12 | North Lanarkshire | 2346209.8 | -3846.6 | 0 | 0 | 0 | 0 | 0 | -3846.6 | 0 | 2342363.2 | 5903.42 | [6 empty] | CM_WWNI | 20% | EC04A | 20% | EC10B | 25% | EC10A | 35%
403547 | Saltcoats and Ardrossan BW Repair Sewerage System and Removal Cross Connections Scoping of Costs | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-23 | 2015-02-16 | 2015-04-22 | 2015-06-18 | 2015-06-18 | North Ayrshire | 134499 | 5450.97 | 0 | 0 | 0 | 0 | -0.03 | 5450.94 | 0 | 139949.94 | 30819 | [6 empty] | EC16A | 100%
501653 | SALTCOATS CANAL PL WWPS NS252413 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2016-07-19 | 2018-03-29 | 2018-08-27 | 2020-03-03 | 2020-04-01 | North Ayrshire | 0 | 0 | 45064 | 402621 | 2392014 | 359763.56 | 20770.44 | 3220233 | 0 | 3220233 | 0 | [6 empty] | CM_WWNI | 100%
402938 | Saltcoats SPS - Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-30 | 2015-02-13 | 2015-01-15 | 2015-01-16 |  | North Ayrshire | 46432 | -1200.52 | 0 | 0 | 0 | 0 | 0 | -1200.52 | 0 | 45231.48 | 0 | [6 empty] | CM_WWNI | 100%
503445 | Sample Tap Replacement- Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2019-01-23 | 2019-01-23 | 2019-06-17 | 2020-02-13 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 26228.66 | 211200.51 | -136.62 | 237292.55 | 287.15 | 237579.7 | 0 | [6 empty] | CM_WSNI | 100%
500952 | SAN Decommissioning | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-12 | 2015-12-14 | 2015-12-14 | 2016-08-11 |  | Scottish Water Wide | 0 | 59841 | 46252.81 | 0 | 0 | 0 | 0 | 106093.81 | 0 | 106093.81 | 0 | [6 empty] | CM_M&G | 100%
45809 | Sand Street SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2012-07-09 | 2012-12-03 | 2013-03-25 | 2013-03-26 | Na H-Eileanan an Iar | 511272.82 | -1112.93 | 142.84 | 0 | 0 | 0 | 0 | -970.09 | 0 | 510302.73 | 0 | [6 empty] | WQ01C | 100%
500871 | Sanday Orkney RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-20 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Orkney Islands | 0 | 1866.84 | 3808.48 | 7110 | -7021.6 | 0 | 0 | 5763.72 | 0 | 5763.72 | 131809.89 | [6 empty] | DW5FS | 100%
501258 | Sanday WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-07-29 | 2018-02-28 | 2018-04-26 | 2021-09-30 | 2022-12-31 | Orkney Islands | 0 | 2924.96 | 74994.65 | 192461.77 | 268030.77 | 829115.85 | 275939 | 1643467 | 0 | 1643467 | 0 | [6 empty] | CM_WSNI | 100% | bar: Regulatory Outputs OMG-04
501211 | Sanday WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-09-30 | 2020-07-20 | 2021-05-17 |  |  | Orkney Islands | 0 | 5860.47 | 417.88 | 5605.82 | 108269.1 | 253669.66 | 989698.23 | 1363521.16 | 2277126.59 | 3640647.75 | 98738.75 | [6 empty] | DW25P | 100%
501539 | Sandbank SR Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-08-24 | 2029-12-28 | 2030-08-14 | 2030-11-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286838.03 | 286838.03 | 0 | [6 empty] | CM_WSNI | 100%
402989 | Sandend Caravan Park Seaview Road Sandend Banff | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2012-12-04 | 2013-02-25 | 2013-10-31 | 2013-10-31 | Aberdeenshire | 82983 | -955.58 | 0 | 0 | 0 | 0 | 960.58 | 5 | 0 | 82988 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503261 | Sandhead WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-15 | 2030-06-12 | 2030-09-12 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 87156.36 | 3340.85 | 0 | 90497.21 | 409502.87 | 500000.08 | 136478.56 | [6 empty] | SG1 | 100%
503407 | Sandhead WwTW CSO | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-29 | 2027-05-20 | 2028-01-12 | 2028-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395999.97 | 395999.97 | 0 | [6 empty] | CM_M&G | 18.75% | CM_WWNI | 37.5% | CM_WWI | 43.75%
502311 | Sandy Loch WOA Bressay WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-14 | 2028-03-02 | 2028-03-10 | 2029-01-22 | 2029-04-24 | Shetland Islands | 0 | 0 | 7599 | 1761 | 439 | -1029.87 | 14174.31 | 22943.44 | 1096556.54 | 1119499.98 | 0 | [6 empty] | CM_WSI | 100%
500018 | Sandy Loch WOA Bressay WSZ - 5000180000 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-04 | 2016-06-17 | 2016-06-20 | 2016-06-23 | 2016-06-30 | Shetland Islands | 0 | 28198 | -11247.84 | 6161.24 | 0 | 0 | 5274.6 | 28386 | 0 | 28386 | 0 | [6 empty] | CM_WSI | 100%
500087 | Sandy Loch WOA Quarff WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-03-13 | 2016-06-17 | 2016-07-27 | 2016-07-12 | 2016-07-27 | Shetland Islands | 0 | 15268.37 | -9407.2 | 5115.33 | 0 | 0 | 0.5 | 10977 | 0 | 10977 | 0 | [6 empty] | CM_WSI | 100%
500086 | Sandy Loch WOA Sandy Loch Lower CWT WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-03-13 | 2016-08-30 | 2016-10-13 | 2017-06-21 | 2017-06-21 | Shetland Islands | 0 | 24797 | 107380.1 | 12320.08 | 4798.05 | -16001.08 | 0 | 133294.15 | 0 | 133294.15 | 0 | [6 empty] | CM_WSI | 100%
501067 | Sandy Loch WOA Scalloway Re-Chlor WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-06 | 2023-06-01 | 2023-07-13 | 2025-06-11 | 2025-08-06 | Shetland Islands | 0 | 94092 | -31736 | 50644 | 76644.9 | 4304.93 | -304.93 | 193644.9 | 2264135.13 | 2457780.03 | 0 | [6 empty] | CM_WSI | 100%
501066 | Sandy Loch WOA Sumburgh WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Shetland Islands | 0 | 26770.15 | -26770.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500958 | Sandy Loch WTW Additional RGF - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-09-11 | 2018-05-31 | 2018-07-30 | 2020-10-13 | 2021-01-19 | Shetland Islands | 0 | 31155 | 141879.91 | 170683.81 | 514217.51 | 920967.78 | 455622 | 2234526.01 | 0 | 2234526.01 | 0 |  |  |  |  | 4750 |  | CM_WSNI | 100%
500872 | Sanna RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-08-03 | 2018-08-29 | 2018-11-27 | 2019-03-31 | 2019-08-31 | Highland | 0 | 544.89 | 2224.49 | 2000 | 22298.49 | 7574.36 | 2304.13 | 36946.36 | 0 | 36946.36 | 9822.09 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.36
502624 | Sanna WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-10-12 | 2033-12-19 | 2034-11-24 | 2035-02-26 | Highland | 0 | 0 | 20930.23 | 520.75 | 1385.35 | 8661.31 | -28219.15 | 3278.49 | 0 | 3278.49 | 136478.56 | [6 empty] | WG1 | 100%
503219 | Sauchen WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-01-08 | 2022-06-24 | 2022-10-19 | 2023-10-16 | 2024-01-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 83105.48 | 26547.58 | 48669.8 | 158322.86 | 1246721.13 | 1405043.99 | 136478.56 | [6 empty] | SG1 | 100%
500841 | Savalbeg RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2016-02-23 | 2016-03-28 | 2017-02-28 | 2018-04-30 | Highland | 0 | 14190 | 36371.91 | 18098.24 | 18743.05 | -17848.29 | -27.55 | 69527.36 | 0 | 69527.36 | 147274.07 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 46.84
502281 | Savalbeg WTW Sludge Lagoon Upgrade | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS3 | 2017-06-27 | 2019-02-28 | 2019-12-12 | 2021-08-31 | 2021-10-31 | Highland | 0 | 0 | 20223.16 | 12546.72 | 49851.04 | 68579.98 | 214522.61 | 365723.51 | 315395.51 | 681119.02 | 290443.35 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
45715 | Savalbeg WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-07-18 | 2012-03-01 | 2012-03-30 | Highland | 83209.32 | 27 | 0 | 0 | 0 | 0 | 1.36 | 28.36 | 0 | 83237.68 | 0 | [6 empty] | DW13 | 100%
402945 | Scalpay Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-01 | 2014-08-28 | 2014-09-18 | 2015-01-28 | 2015-01-28 | Glasgow City | 626693 | 45583 | -1238.03 | -3965.49 | 0 | 0 | 7.18 | 40386.66 | 0 | 667079.66 | 204193.13 | [6 empty] | CS11 | 100%
502353 | Scientific - FOP - Additional Equipment for WW Regulatory Sampling | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2016-11-08 | 2016-11-08 | 2016-12-01 | 2021-06-30 | 2021-06-30 | Scottish Water Wide | 0 | 0 | 252242.41 | 0 | 35863.2 | -426 | 426 | 288105.61 | 0 | 288105.61 | 0 | [6 empty] | CM_M&G | 100%
500489 | Scientific Instrument Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-05 | 2021-06-30 | 2021-06-30 | Scottish Water Wide | 0 | 1110480 | 537819 | 422903 | 973286 | 280441.27 | 595070.74 | 3920000.01 | 0 | 3920000.01 | 0 | [6 empty] | CM_M&G | 100%
400606 | Scientific Services Capital Replacement Programme Chemistry | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-29 | 2011-01-13 | 2011-05-02 | 2015-11-10 |  | Scottish Water Wide | 956683 | -4390.95 | 871.25 | 0 | 0 | 0 | 1110.79 | -2408.91 | 0 | 954274.09 | 0 | [6 empty] | CM_M&G | 100%
400607 | Scientific Services Capital Replacement Programme Micro Crypto - Sampling | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-31 | 2011-01-13 | 2011-05-02 | 2015-11-10 |  | Scottish Water Wide | 895136.6 | 38255.6 | 0 | 0 | 0 | 0 | 0 | 38255.6 | 0 | 933392.2 | 0 | [6 empty] | CM_M&G | 100%
503380 | Scone WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 | 2029-04-16 | Perth and Kinross | 0 | 0 | 0 | 0 | 79058.58 | 14999.37 | 0 | 94057.95 | 47942.05 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
502868 | Scotland Terrace SPS Newburgh - SR15 CM | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | NONINF | SR21 Early Start | MS0 | 2020-02-28 | 2021-06-07 | 2021-09-28 | 2022-05-17 | 2022-08-17 | Fife | 0 | 0 | 0 | 34014.48 | 16801.35 | 8907.3 | 64184.02 | 123907.15 | 658176.28 | 782083.43 | 0 | [6 empty] | SR21_WW | 100%
400061 | Scotland Wide Borehole Inspection Programme | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-12-07 | 2010-11-05 | 2011-01-26 | 2016-03-22 |  | Scottish Water Wide | 1014081.54 | 82778.69 | -31127.98 | 662.28 | 0 | 0 | 0 | 52312.99 | 0 | 1066394.53 | 0 | [6 empty] | CM_WSI | 100%
500930 | Scottish Borders Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | Scottish Borders | 0 | 5927.7 | 1778.05 | 0 | 0 | 0 | 0 | 7705.75 | 0 | 7705.75 | 120964.87 | [6 empty] | CS15A | 100%
45413 | Scottish Water Bylaws | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-21 | 2010-06-28 | 2013-01-28 | 2016-04-01 | Scottish Water Wide | 3815887.15 | -506.11 | 0 | 0 | 0 | 0 | 0 | -506.11 | 0 | 3815381.04 | 0 | [6 empty] | DW11 | 100%
9617 | SCOTTISH WATER PROPERTY RATIONALISATION (Receipt Funded) | Q&S2 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 |  | 2004-03-24 | 2005-03-31 | 2006-03-31 |  | Scottish Water Wide | 3841386.28 | 0 | 139 | 0 | 0 | 0 | 0 | 139 | 0 | 3841525.28 | 0 | [6 empty] | SM3 | 100%
500873 | Scourie RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-08-29 | 2018-08-29 | 2018-11-27 | 2019-03-31 | 2019-08-31 | Highland | 0 | 564.92 | 1604.84 | 757.24 | 14833.16 | 7030.1 | 2848.43 | 27638.69 | 0 | 27638.69 | 12673.9 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 4.46
500629 | SCSP Business Improvement SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 698481.79 | 1609278.26 | 1594575.75 | 1448356.46 | 327790.89 | 1523656.69 | 7202139.84 | 248037.15 | 7450176.99 | 0 | [6 empty] | CM_OVH | 100%
500628 | SCSP Development Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 254433.96 | 747731.44 | 1683188.34 | 1934990.32 | -4620344.06 | 5933780.37 | 5933780.37 | 798149.04 | 6731929.41 | 0 | [6 empty] | CM_OVH | 100%
500627 | SCSP Director of SCSP SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 111843.89 | 154129.87 | 104825.89 | 483156.79 | 72913.01 | 258637.87 | 1185507.32 | 42103.85 | 1227611.17 | 0 | [6 empty] | CM_OVH | 100%
500626 | SCSP Strategic & Economic Regulation SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 345933.08 | 380937.92 | 1156929.2 | 1272922.78 | 3076.64 | 927990.22 | 4087789.84 | 151068.16 | 4238858 | 0 | [6 empty] | CM_OVH | 100%
403016 | SCVW North Berwick WWTW - Scada replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2012-11-30 | 2013-09-30 | 2013-11-04 | 2018-03-02 |  | Scottish Borders | 375274 | 42500 | 79941.88 | 386399.12 | 8000 | 0 | 0 | 516841 | 0 | 892115 | 0 | [6 empty] | CM_WWNI | 100%
500668 | SE 543 John St Dalbeattie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-03-04 | 2020-04-01 | Dumfries and Galloway | 0 | 56912 | 27890.84 | 54138.04 | 31293.12 | -170233 | -301922.41 | -301921.41 | 0 | -301921.41 | 204193.13 | [6 empty] | CS11 | 100%
500011 | SE 843 - Easter Street Duns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2021-04-01 | 2021-04-01 | 2020-02-13 | 2021-04-01 | 2021-04-01 | Scottish Borders | 0 | 44707 | -40777.53 | 12070.53 | 129000 | 123433.21 | 41.6 | 268474.81 | 0 | 268474.81 | 282366.25 | [6 empty] | CS11 | 100%
403236 | SE15 ES - E014 Dukes Road CSO | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-01-23 | 2016-03-22 | 2016-05-13 | 2016-12-21 | 2017-03-14 | South Lanarkshire | 110784 | 454700 | 2086522.01 | 32985.99 | 15884 | -33555.87 | 0 | 2556536.13 | 0 | 2667320.13 | 732260.54 | [6 empty] | EC01F | 45% | CS11 | 55%
500654 | SE246 - Burnswark View Eaglesfield | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2018-07-09 | 2020-03-23 | 2020-05-11 | 2020-11-18 | 2020-11-18 | Dumfries and Galloway | 0 | 80610 | 27390 | 23558.38 | 104352.62 | 248083.06 | 519764.06 | 1003758.12 | 6548.2 | 1010306.32 | 204193.13 | [6 empty] | CS11 | 100%
502582 | SE570 - High St & North Bridge St Hawick | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-04-01 | 2020-04-08 | 2020-04-01 | 2020-04-01 | 2020-04-01 | Scottish Borders | 0 | 0 | 44060.47 | 11939.53 | 31000 | -87000 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11A | 100%
502581 | SE609 - George St Innerleithen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-01-11 | 2021-12-06 | 2022-02-23 | 2022-09-27 | 2022-12-28 | Scottish Borders | 0 | 0 | 43060.47 | 4938.53 | 61481.34 | 43721.09 | -201.44 | 152999.99 | 981999.96 | 1134999.95 | 196097.17 | [6 empty] | CS11A | 100%
502583 | SE842 - Sunnyside Duns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-06-12 | 2019-06-12 | Scottish Borders | 0 | 0 | 43060.47 | 13939.53 | 36000 | -4931.87 | 0.03 | 88068.16 | 0 | 88068.16 | 196097.17 | [6 empty] | CS11A | 100%
500652 | SE847 Church Street Harbour Road Eyemouth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-03-14 | 2020-02-20 | 2020-03-23 | 2021-08-04 | 2021-08-04 | Scottish Borders | 0 | 77062 | 86857.1 | 102921.71 | 240277.19 | 1217130 | 1618966.29 | 3343214.29 | 89283.35 | 3432497.64 | 204193.13 |  |  |  |  | 4800 |  | CS11 | 100%
502229 | Seafield Pumping Station - New Build | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2019-08-26 | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-09-19 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 248748.39 | 0 | 248748.39 | 0 | 248748.39 | 0 | [6 empty] | CM_WWNI | 100%
403549 | Seamill BW UID Summerlea Road CSO and Removal of Flooding Manholes Adjacent to Kilbride Burn | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-23 | 2017-08-03 | 2017-07-19 | 2017-02-03 | 2017-07-31 | North Ayrshire | 53726 | 12272 | 25829.05 | -3151.75 | 0 | 0 | 0 | 34949.3 | 0 | 88675.3 | 131547 | [6 empty] | EC16A | 100%
500683 | SEATON WWPS WWPS 1988 NJ949085 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-06-03 | 2016-03-01 | 2016-05-31 | 2017-02-10 | 2017-02-10 | Aberdeen City | 0 | 85178.25 | 153604.75 | 20995 | -7541 | 0 | 0 | 252237 | 0 | 252237 | 0 | [6 empty] | CM_WWNI | 100%
500594 | Security & End User Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-03-14 | 2016-09-09 | 2016-09-09 | 2021-04-21 | 2021-04-21 | Scottish Water Wide | 0 | 169798 | 190517.85 | 163053.01 | 78768.54 | -9671.12 | 60500 | 652966.28 | 0 | 652966.28 | 0 | [6 empty] | CM_M&G | 100%
404035 | Security Enhancement at 3 WTWs | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2015-02-03 | 2015-09-08 | 2015-09-21 | 2016-03-23 | 2016-03-23 | Scottish Water Wide | 13813.01 | 2772140.99 | 376570 | 2229.48 | 78.75 | 0 | 0 | 3151019.22 | 0 | 3164832.23 | 2627562 | [6 empty] | CM_WSNI | 48% | DW9A | 52%
500990 | Security Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-11-17 | 2016-09-21 | 2016-09-21 | 2020-06-29 | 2020-06-29 | Scottish Water Wide | 0 | 200064 | 2211188.52 | 599023.99 | 493120.83 | -298381.81 | 0 | 3205015.53 | 0 | 3205015.53 | 0 |  |  |  |  | 739677.27 |  | CM_M&G | 100%
404034 | Security improvements at Water Assets | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2015-02-27 | 2015-09-24 | 2015-11-09 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 9088 | 337398 | 1064498.59 | -251032.1 | 0 | 3027.13 | 2972.87 | 1156864.49 | 0 | 1165952.49 | 2919521 | [6 empty] | DW9A | 100%
501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-03-31 | Scottish Water Wide | 0 | 8000 | 3007.49 | 11168.13 | 0 | 0 | 0 | 22175.62 | 0 | 22175.62 | 182288.97 | [6 empty] | DW9F | 100%
501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-29 | 2019-09-30 | Scottish Water Wide | 0 | 95883 | 179559.77 | 1111586.81 | 8418.51 | -262.41 | 390.43 | 1395576.11 | 10.36 | 1395586.47 | 924159.89 | [6 empty] | DW9F | 100%
501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-17 | 2019-03-29 | Scottish Water Wide | 0 | 0 | 36386.12 | 261448.1 | 333655.96 | 3231.04 | 1828.59 | 636549.81 | 676.32 | 637226.13 | 934649.94 | [6 empty] | DW9F | 100%
501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS5 | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-08-16 | 2020-01-15 | Scottish Water Wide | 0 | 0 | 17790.14 | 298445.85 | 1506511.65 | 218023.79 | 3238.62 | 2044010.05 | 2649.8 | 2046659.85 | 961051.18 | [6 empty] | CM_WSNI | 5.869% | DW9F | 94.13%
501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS3 | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-14 | 2020-10-14 | Scottish Water Wide | 0 | 0 | 65391.05 | 65357.95 | 284295.52 | 1698991.29 | 36507.17 | 2150542.98 | 7822.97 | 2158365.95 | 963393.91 | [6 empty] | CM_WSNI | 3.257% | DW9F | 96.74%
402766 | Security of Supply Resource | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2012-06-12 | 2012-06-12 | 2012-07-02 | 2017-06-26 |  | Scottish Water Wide | 31837 | 964 | 0.02 | -1882.99 | 0 | 0 | 0 | -918.97 | 0 | 30918.03 | 15177 | [6 empty] | DW9A | 100%
402626 | Security Review Risk Mitigation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-07-13 | 2012-10-25 | 2012-10-25 | 2015-03-23 |  | Scottish Water Wide | 372475.24 | 1462.5 | 0 | 0 | 0 | 0 | 0 | 1462.5 | 0 | 373937.74 | 0 | [6 empty] | CM_M&G | 100%
500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2016-08-22 | 2017-03-15 | Scottish Water Wide | 0 | 18717 | 8318.02 | 0 | 0 | 0 | 0 | 27035.02 | 0 | 27035.02 | 172763.29 | [6 empty] | WQ01E | 100%
501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS6 | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-15 | Scottish Water Wide | 0 | 886 | 34841.12 | 10591.94 | -3701.53 | 0 | 0 | 42617.53 | 0 | 42617.53 | 172763.29 | [6 empty] | WQ01E | 100%
500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2016-12-06 | 2017-03-31 | Scottish Water Wide | 0 | 20910 | 47724.9 | 410.1 | 0 | 0 | 0 | 69045 | 0 | 69045 | 207623.13 | [6 empty] | WQ01D | 100%
501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS6 | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2020-02-11 | 2020-03-31 | Scottish Water Wide | 0 | 3395.51 | 47007.8 | 528530.82 | 580214.06 | 670346.99 | 3245.72 | 1832740.9 | 1754.28 | 1834495.18 | 207623.13 | [6 empty] | WQ01D | 100%
404116 | Service Contract for Maintenance of Water Resources CAR Licence Monitoring Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2017-04-06 | 2017-04-06 | Scottish Water Wide | 49974 | -48389.36 | 124839.62 | -12526.25 | 0 | 0 | 0 | 63924.01 | 0 | 113898.01 | 0 | [6 empty] | WSNI | 100%
50014 | Service Reservoir - Additional CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 17083205.25 | 17083205.25 | 0 | 17083205.25 | 0 | [6 empty] | CM_WSNI | 100%
503293 | Service Risk Management Tool - SRMT | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-07-17 | 2019-09-30 | 2019-09-30 | 2019-09-02 | 2019-09-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1096017.89 | 2108.09 | -250.63 | 1097875.35 | 0 | 1097875.35 | 0 | [6 empty] | CM_M&G | 100%
403623 | Service Transition Dev Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-24 | 2014-04-11 | 2014-04-11 | 2015-01-13 |  | Scottish Water Wide | 210531.99 | -1260.34 | 0 | 0 | 0 | 0 | 0 | -1260.34 | 0 | 209271.65 | 0 | [6 empty] | CM_M&G | 100%
501937 | Severe Weather - Damaged Water Mains Shieldhill & Cample Mill | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-02-23 | 2017-08-29 | 2017-08-30 | 2018-06-28 | 2018-06-28 | Dumfries and Galloway | 0 | 1185.3 | 14452.93 | 507088.35 | 310346.98 | 631.25 | 23156.58 | 856861.39 | 0 | 856861.39 | 0 | [6 empty] | CM_WSI | 100%
502397 | Sewage Related Debris Strategy & IDP Development | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MS3 | 2017-01-31 | 2017-01-31 | 2017-03-01 | 2021-04-16 | 2021-04-16 | Scottish Water Wide | 0 | 0 | 9158.88 | 1212 | 343.12 | 109665.56 | 19059.87 | 139439.43 | 560.58 | 140000.01 | 0 | [6 empty] | EC16B | 100%
502604 | Sewage Related Debris Strategy & IDP Development_CAPEX element | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | GW2 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-07-29 | Scottish Water Wide | 0 | 0 | 176912.11 | 122631.91 | 39482.12 | 141816.36 | 37641.42 | 518483.92 | 0 | 518483.92 | 0 | [6 empty] | EC16B | 100%
402536 | Sewer Flooding McGeoch Drive Dumfries | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-02-29 | 2013-11-18 | 2014-01-31 | 2014-06-18 | 2014-06-18 | Dumfries and Galloway | 585684 | -46812 | -1476.24 | 0 | 0 | 0 | 0 | -48288.24 | 0 | 537395.76 | 1105.2 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402362 | Sewer Flooding at Elmgrove Scone | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-10-13 | 2013-10-17 | 2013-11-11 | 2014-02-10 | 2014-02-10 | Perth and Kinross | 390503 | -3508.64 | 72.06 | 0 | 0 | 0 | 0 | -3436.58 | 0 | 387066.42 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402197 | Sewer Flooding Burnbank Street Airdrie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2011-06-10 | 2019-08-30 | 2019-10-04 | 2020-08-10 | 2020-11-11 | North Lanarkshire | 330000 | 145015 | 174951 | 113180 | 152439 | 1771070.2 | 804179.8 | 3160835 | 85.76 | 3490920.76 | 204193.13 |  |  |  |  | 3183.91 |  | CS11 | 100%
403498 | Sewer Flooding Campaign Programme Definition & Roadmap | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-10-04 | 2013-10-04 | 2013-10-07 | 2019-02-25 | 2019-02-25 | Scottish Water Wide | 27439.02 | 17534.02 | 270016.37 | -111992.37 | 35941.53 | 0 | -0.01 | 211499.54 | 0 | 238938.56 | 0 | [6 empty] | CM_WWNI | 100%
504146 | Sewer Flooding Focus - EPI Focus Telemetry Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2019-12-11 | 2020-03-06 | 2020-10-29 | 2020-11-26 | - | 0 | 0 | 0 | 0 | 0 | 1962.62 | 0 | 1962.62 | 0 | 1962.62 | 0 | [6 empty] | CM_WWNI | 100%
504158 | Sewer Flooding Focus - Flood Response Trailers - 15k per trailer. Further 4 would be required | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2019-12-11 | 2020-03-10 | 2020-10-22 | 2020-11-19 | - | 0 | 0 | 0 | 0 | 0 | 51493.23 | 0 | 51493.23 | 0 | 51493.23 | 0 | [6 empty] | Ww3 | 100%
504139 | Sewer flooding focus - Installation of Pressure Transducer Interface( PTIs) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-24 |  |  |  | - | 0 | 0 | 0 | 0 | 0 | 12387.32 | 0 | 12387.32 | 0 | 12387.32 | 0 | [6 empty] | CM_WWNI | 100%
504167 | Sewer Flooding focus - Replace defective CCTV Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2019-12-13 | 2020-02-14 | 2020-09-17 | 2020-10-15 | - | 0 | 0 | 0 | 0 | 0 | 88213.08 | 0 | 88213.08 | 0 | 88213.08 | 0 | [6 empty] | Ww3 | 100%
402533 | Sewer Flooding Johnstone Drive Rutherglen | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-28 | 2012-05-25 | 2013-04-22 | 2013-08-01 |  | South Lanarkshire | 52542 | -528.67 | 0 | 0 | 0 | 0 | -0.09 | -528.76 | 0 | 52013.24 | 0 | [6 empty] | CM_WWI | 100%
402236 | Sewer Flooding Steel Street at Cardwell Road Gourock | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-07-22 | 2014-04-02 | 2014-04-02 | 2014-12-16 | 2014-12-16 | Inverclyde | 1727977.31 | 112489.48 | 36.75 | 0 | 0 | 0 | 0 | 112526.23 | 0 | 1840503.54 | 1179 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503073 | Sewer Misconnection Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2018-04-06 | 2018-08-29 | 2018-09-24 | 2019-09-19 | 2019-09-19 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 557223.39 | 275390.61 | 8157.39 | 840771.39 | 0 | 840771.39 | 0 | [6 empty] | EC16 | 100%
45667 | Sewer Network Modelling - DAS Model Maintenance - Early Start Scoping | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-10-15 | 2010-03-24 | 2010-06-01 | 2014-12-08 |  | Scottish Water Wide | 2420315 | 19025.64 | 0 | 0 | 0 | 0 | 0 | 19025.64 | 0 | 2439340.64 | 0 | [6 empty] | CM_WWI | 100%
46622 | Sewer Rehab - Albert Pier Rothesay (Saline Intrusion) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2009-03-19 | 2011-05-05 | 2011-05-16 | 2012-07-05 |  | Argyll and Bute-Cowal & Bute | 938353 | 64 | 0 | -48794.84 | 0 | 0 | 0 | -48730.84 | 0 | 889622.16 | 0 | [6 empty] | CM_WWI | 100%
400510 | Sewer Rehab - Frith and Mossbank Shetland | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-03-24 | 2011-10-31 | 2011-12-12 | 2013-05-24 |  | Shetland Islands | 819365 | -1543.71 | 0 | 0 | 0 | 0 | 0 | -1543.71 | 0 | 817821.29 | 0 | [6 empty] | CM_WWI | 100%
402526 | Sewer Rehab - PMAP Reactive Process Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-05 | 2012-04-24 | 2012-04-24 | 2013-08-12 |  | Scottish Water Wide | 1728836 | -4866.77 | 0 | 0 | 0 | 0 | 0 | -4866.77 | 0 | 1723969.23 | 0 | [6 empty] | CM_WWI | 100%
403349 | Sewer Rehab - PMAP Reactive Process Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-05-29 | 2013-05-29 | 2014-06-04 |  | Scottish Water Wide | 1639081 | 0 | -6060.88 | 0 | 0 | 0 | 0 | -6060.88 | 0 | 1633020.12 | 0 | [6 empty] | CM_WWI | 100%
403348 | Sewer Rehab - PMAP Reactive Process Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-28 | 2014-03-25 | 2014-03-26 | 2015-09-21 |  | Scottish Water Wide | 1090001 | 71217 | 2550.06 | -796.19 | 0 | 0 | 0 | 72970.87 | 0 | 1162971.87 | 0 | [6 empty] | CM_WWI | 100%
46148 | Sewer Rehab - Powburn Rising Main Scheme Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-08-20 | 2012-03-08 | 2012-04-30 | 2014-06-06 |  | South Ayrshire | 4286075 | 0 | -1922.89 | 0 | 0 | 0 | 0 | -1922.89 | 0 | 4284152.11 | 0 | [6 empty] | CM_WWI | 100%
502286 | SFT Building Safety Inspections | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2017-04-03 | 2017-04-10 | 2017-04-10 | 2017-03-14 | 2017-03-14 | Scottish Water Wide | 0 | 0 | 39957.34 | -7943.42 | 0 | 0 | 0 | 32013.92 | 0 | 32013.92 | 0 | [6 empty] | CM_M&G | 100%
503452 | SGA- Blueprint for Sewers | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-13 | 2019-07-18 | 2019-09-09 | 2020-12-31 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1308.41 | 111530.36 | 141827.9 | 254666.67 | 0 | 254666.67 | 295054.03 | [6 empty] | CS25 | 100%
403183 | Shafton Road Glasgow Phase1 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-12-17 | 2013-12-11 | 2013-12-12 | 2014-08-26 | 2014-10-01 | Glasgow City | 1953340 | 15173.45 | 6194.21 | 772.98 | 0 | 0 | 0 | 22140.64 | 0 | 1975480.64 | 451.2 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503834 | Shalloch Park Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2020-09-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 11513.08 | 138486.92 | 150000 | 0 | 150000 | 0 | [6 empty] | SR15_CMA_WWI | 100%
403583 | Shandon Street Edinburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-09-09 | 2013-12-23 | 2014-02-10 | 2014-06-30 | 2014-06-30 | City of Edinburgh | 395847 | 778 | -5213.62 | 0 | 0 | 0 | 2436.64 | -1998.98 | 0 | 393848.02 | 2295.6 | [6 empty] | CM_WWI | 40% | CS11A | 60%
30875 | Shapinsay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2012-01-31 | 2012-02-28 | 2013-03-01 | 2013-03-18 | Orkney Islands | 3353865.31 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3353870.31 | 43 | [6 empty] | DW23 | 100%
503239 | Sharphill Saltcoats | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW1 | 2020-08-20 | 2020-07-20 | 2020-07-29 | 2020-12-08 | 2021-03-16 | North Ayrshire | 0 | 0 | 0 | 0 | 20946.1 | 388667.11 | 2570868.82 | 2980482.03 | 19517.97 | 3000000 | 470181.23 | [6 empty] | WG5 | 100%
502924 | Shawfair Danderhall Waste Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2020-09-15 | 2020-06-26 | Midlothian | 0 | 0 | 0 | 41259.81 | 0 | 762550 | -70663.11 | 733146.7 | -103098.63 | 630048.07 | 0 | [6 empty] | SG5 | 100%
500740 | Shawfair-Zero Waste Water Main Upsize | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 2018-10-25 | 2018-10-25 | East Lothian | 0 | 175962 | 0 | -87999.99 | 0 | 0 | 0 | 87962.01 | 0 | 87962.01 | 470181.23 | [6 empty] | WG5 | 100%
502942 | Shetland Water Strategy | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS5 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2020-01-31 | 2020-03-16 | Shetland Islands | 0 | 0 | 0 | 85259.9 | 229114.76 | 83084.07 | 3900.28 | 401359.01 | 0 | 401359.01 | 3250279.58 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-47
404123 | Shieldaig WOA - Mary Street UITS Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-04-17 | 2015-04-17 | 2015-05-11 | 2016-01-21 | 2016-01-21 | Highland | 0 | 315740.5 | -19.14 | 0 | 0 | 0 | 0 | 315721.36 | 0 | 315721.36 | 0 | [6 empty] | CM_WSI | 100%
45414 | Shieldaig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-03-29 | 2011-09-01 | 2013-03-01 | 2013-03-27 | Highland | 3372234.89 | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 3372279.89 | 0 | [6 empty] | DW13 | 50% | DW23 | 50%
500717 | Shieldhall Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-07-23 | 2015-12-22 | 2016-01-19 | 2017-03-28 | 2017-05-15 | Glasgow City | 0 | 261208 | 56166.43 | 35.36 | 0 | 0 | 0 | 317409.79 | 0 | 317409.79 | 120964.87 | [6 empty] | CS15A | 100%
403772 | Shieldhall PST 4 6 8 Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-05-21 | 2014-05-26 | 2014-05-26 | 2016-08-16 |  | Glasgow City | 676556 | 448549.58 | 13544.76 | 5591.42 | -3962.51 | 0 | 0 | 463723.25 | 0 | 1140279.25 | 0 | [6 empty] | CM_WWNI | 100%
501637 | Shieldhall Storm Return Automation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-03-16 | 2017-11-07 | 2018-01-30 | 2020-07-08 | 2020-07-08 | Glasgow City | 0 | 0 | 179192 | -118989.87 | 514734.68 | 18123.76 | -2662.53 | 590398.04 | 0 | 590398.04 | 0 | [6 empty] | CM_WWNI | 100%
501172 | Shieldhall STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-03-02 | 2017-10-30 | 2017-11-06 | 2020-04-16 | 2020-04-16 | Renfrewshire | 0 | 5161.68 | 1032338.15 | 942738.78 | 5167940.47 | 2250056.8 | 61730.47 | 9459966.35 | 118907.24 | 9578873.59 | 0 | [6 empty] | CM_WWNI | 100%
30878 | Shieldhall STW Refurb - STW000642 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2011-09-23 | 2011-09-23 | 2013-11-27 |  | Glasgow City | 6343385.08 | -6149.5 | 0 | 0 | 0 | 0 | 0 | -6149.5 | 0 | 6337235.58 | 0 |  |  |  |  | 41553 |  | CM_WWNI | 100%
401241 | Shieldhall UID Improvements Cluster 1 - Kinning Park SPS | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-07-19 | 2011-01-14 | 2011-01-27 | 2011-01-27 | 2011-03-14 | Glasgow City | 3021.99 | 0 | 0 | 1195.71 | 228.59 | 0 | 0.01 | 1424.31 | 0 | 4446.3 | 0 | [6 empty] | EC10B | 100%
502938 | Shieldhall WWTW - Odour Control Unit Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-12-11 | 2017-12-11 | 2018-01-08 | 2018-01-09 | 2018-01-09 | Glasgow City | 0 | 0 | 0 | 662951.51 | 0 | 0 | 0.49 | 662952 | 0 | 662952 | 0 | [6 empty] | CM_WWNI | 100%
500757 | Shieldhall WWTW - Storm Tank Scraper Bridge Refurbishment | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS6 | 2015-08-12 | 2015-10-26 | 2016-02-05 | 2017-04-10 | 2017-05-09 | Glasgow City | 0 | 47000 | 705043.97 | -150546.54 | 0 | -7768.64 | 173.97 | 593902.76 | 0 | 593902.76 | 826685.67 | [6 empty] | CS2 | 100%
501683 | Shieldhall WWTW Grade 5 HC Sewer Ph1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-05-16 | 2017-02-13 | 2017-02-17 | 2021-03-09 | 2021-03-09 | Glasgow City | 0 | 0 | 471779.17 | 539039.83 | 190500 | 1054633 | 44702 | 2300654 | 0 | 2300654 | 0 | [6 empty] | CM_WWI | 100%
501747 | Shieldhall WwTW Grade 5 HC Sewer Phase2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-10-31 | 2019-05-31 | 2019-08-26 | 2020-05-11 | 2020-08-03 | Glasgow City | 0 | 0 | 4795.67 | 48.62 | 73732.71 | 241149 | 6577 | 326303 | 2400 | 328703 | 0 | [6 empty] | CM_WWI | 100%
501281 | SHIELDHALL WWTW NS533659 MCC Replacement (Phase 1- PreSed MCC) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2016-01-20 | 2018-01-31 | 2018-01-31 | 2020-01-22 | 2020-04-01 | Glasgow City | 0 | 14033 | 228154.86 | 269413.75 | 1090389.41 | 327858.51 | 14115.12 | 1943964.65 | 8982.35 | 1952947 | 0 | [6 empty] | CM_WWNI | 100%
500197 | Shieldhall WWTW Odour Upgrade | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | NONINF | Odour | MS6 | 2015-07-21 | 2016-09-16 | 2017-02-27 | 2017-06-30 | 2017-11-30 | Glasgow City | 0 | 39577 | 283295.06 | 426634.32 | -57439.96 | -4218.42 | -38 | 687810 | 0 | 687810 | 826685.67 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
403479 | Shotts (Glen Road) - Renew Overland pipeline | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2013-07-11 | 2016-04-08 | 2016-04-11 | 2017-01-25 | 2017-01-25 | North Lanarkshire | 134441 | 589763 | 1236071.78 | 20475.22 | 5257.47 | 0 | 0.53 | 1851568 | 0 | 1986009 | 0 | [6 empty] | CM_M&G | 14.29% | CM_WWI | 85.71%
500177 | Shotts DOA (DOA000554) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-18 | 2018-02-28 | 2018-03-31 | North Lanarkshire | 0 | 80361 | 65629.65 | 31230 | 30919.32 | 0 | 0 | 208139.97 | 0 | 208139.97 | 72047.27 | [6 empty] | CS11 | 43.84% | CS16D | 56.16% | bar: Regulatory Outputs OMG-22
30880 | Shotts STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2012-01-24 | 2012-07-09 | 2013-01-07 | 2013-02-21 | North Lanarkshire | 1601398.3 | 801 | -18226.57 | 0 | 0 | 0 | 0 | -17425.57 | 0 | 1583972.73 | 0 | [6 empty] | EC10A | 11.6% | EC01A | 11.7% | EC04A | 11.7% | CM_WWNI | 65%
503209 | Shotts WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-15 | 2030-06-12 | 2030-09-12 | North Lanarkshire | 0 | 0 | 0 | 0 | 81775.66 | 5565.37 | 0.01 | 87341.04 | 52549.95 | 139890.99 | 136478.56 | [6 empty] | SG1 | 100%
500698 | Sim Replacement and Mobile Device Upgrade Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-07-22 | 2015-07-22 | 2015-07-22 | 2016-05-11 |  | Scottish Water Wide | 0 | 1359603 | -53016.17 | 0 | 0 | 0 | 0 | 1306586.83 | 0 | 1306586.83 | 0 | [6 empty] | CM_M&G | 100%
505212 | Simple Repair at Auchinstarry DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2365.24 | 634.76 | 3000 | 375000 | 378000 | 0 | [6 empty] | CM_WSNI | 100%
504290 | Simple Repair at Burghill Old DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-15 | 2020-03-09 | 2020-12-16 | 2020-12-17 | - | 0 | 0 | 0 | 0 | 0 | 16858.8 | 0 | 16858.8 | 0 | 16858.8 | 0 | [6 empty] | CM_WSNI | 100%
504744 | Simple Repair at Carlochan DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-27 | 2020-02-03 | 2020-12-16 | 2020-12-03 | - | 0 | 0 | 0 | 0 | 0 | 7130.84 | 0 | 7130.84 | 0 | 7130.84 | 0 | [6 empty] | CM_WSNI | 100%
503947 | Simple Repair at Cockburnspath DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-18 | 2020-01-20 | 2020-12-16 | 2020-12-16 | - | 0 | 0 | 0 | 0 | 0 | 27691.82 | 0 | 27691.82 | 0 | 27691.82 | 0 | [6 empty] | CM_WSNI | 100%
505169 | Simple Repair at Four Winds Croft DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-17 | 2020-03-02 | 2020-12-16 | 2021-01-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 22960 | 141040 | 164000 | 0 | 164000 | 0 | [6 empty] | CM_WSNI | 100%
505103 | Simple Repair at Kingston DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-11 | 2020-03-20 | 2020-12-16 | 2020-10-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 27840 | 88160 | 116000 | 0 | 116000 | 0 | [6 empty] | CM_WSNI | 100%
505649 | Simple Repair at Port Ellen DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-01-25 | 2023-12-12 | 2024-05-21 | 2025-12-02 | 2026-03-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 209000 | 211000 | 0 | [6 empty] | CM_WSNI | 100%
504296 | Simple Repair at Raasay CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-27 | 2020-07-23 | 2020-12-16 | 2020-12-16 | - | 0 | 0 | 0 | 0 | 0 | 7000 | 96500 | 103500 | 0 | 103500 | 0 | [6 empty] | CM_WSNI | 100%
504168 | Simple Repair at Seilebost DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-24 | 2020-07-07 | 2020-12-11 | 2020-12-11 | - | 0 | 0 | 0 | 0 | 0 | 6607.48 | 0 | 6607.48 | 0 | 6607.48 | 0 | [6 empty] | CM_WSNI | 100%
504294 | Simple Repair at Threaplands DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-27 | 2020-07-23 | 2021-03-10 | 2020-12-11 | - | 0 | 0 | 0 | 0 | 0 | 21007.69 | 0 | 21007.69 | 0 | 21007.69 | 0 | [6 empty] | CM_WSNI | 100%
505161 | Simple Repair at Westhill Hill of Kier BP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-17 | 2020-03-02 | 2020-12-16 | 2020-12-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 3080 | 18919.98 | 21999.98 | 0 | 21999.98 | 0 | [6 empty] | CM_WSNI | 100%
501701 | Sinclair Drive Cowdenbeath - Reline Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-11-17 | 2017-05-23 | 2017-08-09 | 2019-02-14 | 2019-02-14 | Fife | 0 | 0 | 11110 | 38449 | 17802 | 567 | 2499.53 | 70427.53 | 0 | 70427.53 | 0 | [6 empty] | CM_WWI | 100%
403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-22 | 2017-05-16 | Scottish Water Wide | 73057 | 268995 | 454948 | 15412.52 | 0 | 0 | 0 | 739355.52 | 0 | 812412.52 | 112484.65 | [6 empty] | DW25PS | 10% | DW2_S | 90%
404099 | Skellyton (Larkhall) STW - Transfer project from 030881 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2015-03-06 | 2016-09-02 | 2016-10-17 | 2017-05-05 | 2017-05-05 | South Lanarkshire | 9728.02 | 265470.38 | 1554463.33 | 796925.21 | -267464.6 | -102562.45 | 430.94 | 2247262.81 | 725242.26 | 2982233.09 | 0 |  |  |  |  | 29740 |  | EC01A | 14.33% | EC04A | 14.33% | EC10A | 14.33% | CM_WWNI | 57%
30881 | Skellyton (Larkhall) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-27 | 2011-03-29 | 2012-12-11 | 2016-02-11 | 2016-10-31 | South Lanarkshire | 3362266.45 | 72347.5 | 12732.53 | 692.79 | 0 | 0 | 0 | 85772.82 | 0 | 3448039.27 | 1671325.09 | [6 empty] | CM_WWNI | 19.97% | EC01A | 19.97% | EC04A | 60.05%
500178 | Skellyton DOA (DOA002580) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-11-26 | 2019-03-28 | South Lanarkshire | 0 | 108775 | 107165 | 44040 | 65020 | 4691.07 | 0 | 329691.07 | 0 | 329691.07 | 82391.31 | [6 empty] | EC01G | 1.092% | CS11 | 45.28% | CS16D | 53.62%
503328 | Skellyton Pipebridge | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-07-20 | 2028-07-17 | 2028-09-11 | 2029-05-04 | 2029-08-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16784.46 | 16784.46 | 470714.49 | 487498.95 | 0 | [6 empty] | CM_M&G | 100%
503212 | Skellyton WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-03 | 2023-01-16 | 2023-05-17 | 2024-05-13 | 2024-08-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 76112.23 | 52991.4 | 29791.86 | 158895.49 | 1841104.54 | 2000000.03 | 136478.56 | [6 empty] | SG1 | 100%
501205 | Skerries WTW- QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS5 | 2017-03-28 | 2017-12-27 | 2018-09-21 | 2019-12-31 | 2020-03-30 | Shetland Islands | 0 | 1710.33 | 11767.64 | 44307.11 | 68078.73 | 156875.82 | 10744.95 | 293484.58 | 1515.39 | 294999.97 | 62107.87 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403402 | Skye and Lochaber Area - Removal of Small Diameter AC Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-27 | 2013-04-27 | 2014-08-19 | 2015-10-07 |  | Highland | 182976.33 | 9713.72 | 85.2 | 0 | 0 | 0 | 0 | 9798.92 | 0 | 192775.25 | 0 | [6 empty] | CM_WSI | 100%
503658 | Sludge Management - Stabilisation of Monitoring Systems | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2020-06-03 | 2020-06-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 409032.54 | 1649.03 | 410681.57 | 0 | 410681.57 | 0 | [6 empty] | CM_M&G | 100%
501300 | Sludge Management Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-05-26 | 2017-05-26 | 2017-04-04 | 2017-04-04 | Scottish Water Wide | 0 | 21300 | -299.13 | -58.24 | 0 | 0 | 0 | 20942.63 | 0 | 20942.63 | 0 | [6 empty] | CM_M&G | 100%
501283 | Small Value Holding Line - SR15 Yr2-6 -Wastewater - Managed Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 0 | 131.08 | 0 | 0 | 0 | 5896647 | 5896778.08 | 0 | 5896778.08 | 0 | [6 empty] | CM_WWI | 34% | CM_WWNI | 66%
501284 | Small Value Holding Line - SR15 Yr2-6 -Wastewater - Scottish Water Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 92.23 | 0 | 0 | 140.88 | 0 | 26055583 | 26055816.11 | 0 | 26055816.11 | 0 | [6 empty] | CM_WWI | 34% | CM_WWNI | 66%
501285 | Small Value Holding Line - SR15 Yr2-6 -Water - Managed Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7379406 | 7379406 | 0 | 7379406 | 0 | [6 empty] | CM_WSI | 48% | CM_WSNI | 52%
501286 | Small Value Holding Line - SR15 Yr2-6 -Water - Scottish Water Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-15 |  |  |  | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 25911048.1 | 25911048.1 | 0 | 25911048.1 | 0 | [6 empty] | CM_WSI | 48% | CM_WSNI | 52%
502959 | Smith Place Dumfries - Sewer Upgrade | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-06-11 | 2028-01-13 | 2028-04-14 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 38006.1 | 38006.1 | 311993.9 | 350000 | 0 | [6 empty] | CM_WWI | 100%
401883 | SOA Foundation Environment Build and TGS | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-10 | 2011-04-04 | 2011-04-04 | 2014-06-06 |  | Scottish Water Wide | 2113143.51 | -4028 | 0 | 0 | 0 | 0 | 0 | -4028 | 0 | 2109115.51 | 0 | [6 empty] | CM_M&G | 100%
403868 | SOA Rebuild | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-08-20 | 2014-12-19 | 2014-12-19 | 2015-07-07 |  | Scottish Water Wide | 2165495 | -258737.66 | 0 | 0 | 0 | 0 | -13218.3 | -271955.96 | 0 | 1893539.04 | 0 | [6 empty] | CM_M&G | 100%
403043 | Sollas AC Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2012-12-17 | 2013-04-29 |  | Na H-Eileanan an Iar | 147648 | 155.03 | 0 | 0 | 0 | 0 | 0 | 155.03 | 0 | 147803.03 | 0 | [6 empty] | CM_WSI | 100%
501317 | South SPS MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-02-27 | 2018-06-05 | 2018-09-03 | 2020-05-28 | 2020-09-01 | Scottish Water Wide | 0 | 0 | 55035.59 | 58430.41 | 451894 | 90200.32 | -922.85 | 654637.47 | 0 | 654637.47 | 0 | [6 empty] | CM_WWNI | 100%
400818 | South Area Network Infiltration Investigations Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-18 | 2012-03-27 | 2012-03-27 | 2012-03-30 |  | North Lanarkshire | 61726.93 | 0 | 0 | 1421.47 | 0 | 0 | 0 | 1421.47 | 0 | 63148.4 | 0 | [6 empty] | CM_WWI | 100%
500509 | South Edinburgh Service Resilience | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS3 | 2016-03-23 | 2018-02-26 | 2018-03-26 | 2020-12-18 | 2021-03-18 | All South Unitary Authorities | 0 | 131852.98 | 341784.02 | 1923969 | 9660635.41 | 9478374.14 | 877616.42 | 22414231.97 | 0 | 22414231.97 | 5935596.51 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
502567 | South Hoy WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2020-08-04 | 2020-08-17 | 2020-08-26 | 2020-08-27 | 2020-08-28 | Orkney Islands | 0 | 0 | 20930.23 | 3708.12 | 99061.71 | 24608.98 | 23690.95 | 171999.99 | 0 | 171999.99 | 136478.56 | [6 empty] | WG1 | 100%
500931 | South Lanarkshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2016-11-04 | 2016-11-04 | 2016-10-25 | 2016-11-04 | South Lanarkshire | 0 | 8001.06 | 490.05 | 0 | 0 | 0 | 0 | 8491.11 | 0 | 8491.11 | 120964.87 | [6 empty] | CS15A | 100%
500700 | South Medwyn RW Pipeline - Landslides & Pipe Supports | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-08-03 | 2016-07-27 | 2016-08-17 | 2017-10-26 | 2017-10-26 | Scottish Borders | 0 | 4080 | 60431.06 | 128235.66 | 9220.18 | 0 | 0 | 201966.9 | 0 | 201966.9 | 0 | [6 empty] | CM_WSI | 100%
500874 | South Moorhouse RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-09-20 | 2018-09-26 | 2018-12-03 | 2019-06-30 | 2020-03-31 | East Renfrewshire | 0 | 10252.59 | 12747.41 | 35476.14 | 135071.89 | 81760.84 | -1375.45 | 273933.42 | 0 | 273933.42 | 451751.94 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 85.03
503286 | South Queensferry WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-06 | 2023-08-18 | 2023-12-21 | 2024-12-18 | 2025-03-20 | West Lothian | 0 | 0 | 0 | 0 | 75860.69 | 139.95 | 45780.47 | 121781.11 | 1878218.9 | 2000000.01 | 136478.56 | [6 empty] | SG1 | 100%
403193 | South SVCM CID WWI Improvements Yr 3-4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-14 | 2013-04-25 | 2013-08-12 | 2015-01-26 |  | All South Unitary Authorities | 105295 | -3580.5 | 0 | 0 | 0 | 0 | 11.59 | -3568.91 | 0 | 101726.09 | 0 | [6 empty] | CM_WWI | 100%
403044 | South Uist WOA - Bornish to Mingarraidh junction. AC Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2012-12-03 | 2013-10-01 |  | Na H-Eileanan an Iar | 198401.69 | 19.77 | 0 | 0 | 0 | 0 | 0 | 19.77 | 0 | 198421.46 | 0 | [6 empty] | CM_WSI | 100%
503082 | South Uist WTW New Source | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS1 | 2015-11-02 | 2021-01-04 | 2021-02-12 | 2022-06-06 | 2023-08-14 | Na H-Eileanan an Iar | 0 | 0 | 0 | 16149.58 | 38587.42 | 193062.82 | 1603922.11 | 1851721.93 | 8648278.07 | 10500000 | 4353935.43 | [6 empty] | DW3B | 7.484% | DW3C | 7.484% | WG4 | 24.95% | DW25P | 60.08%
403594 | South Wastewater Treatment - Health and Safety Interventions (Various) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-10-02 | 2013-10-02 | 2013-10-02 | 2015-09-01 |  | All South Unitary Authorities | 430299.85 | 48331.02 | 0 | 0 | 0 | 0 | 0 | 48331.02 | 0 | 478630.87 | 0 | [6 empty] | CM_WWNI | 100%
501550 | South West Telemetry Radio Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-01-21 | 2016-02-29 | 2016-02-29 | 2016-11-21 | 2018-03-22 | Scottish Water Wide | 0 | 157730.98 | 471676.93 | 0 | 0 | 0 | 0 | 629407.91 | 0 | 629407.91 | 0 | [6 empty] | CM_M&G | 100%
403067 | South WWCM Inlet screen refurbishment programme | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-10-16 | 2012-10-16 | 2012-10-16 | 2015-06-11 |  | All South Unitary Authorities | 520000 | 7824.56 | 0 | 0 | 0 | 0 | 0 | 7824.56 | 0 | 527824.56 | 0 | [6 empty] | CM_WWNI | 100%
502231 | South WWTW MCC Replacements Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-06-29 | 2018-12-19 | 2019-03-04 | 2020-06-19 | 2020-09-23 | Scottish Water Wide | 0 | 0 | 26001.93 | 159111.07 | 1052348 | 2145455.91 | 30795.11 | 3413712.02 | 2400 | 3416112.02 | 0 | [6 empty] | CM_WWNI | 100%
30891 | South Yell - Mid Yell and Cullivoe WTWs - Upgrade (incl 30524 - 30169) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2006-06-07 | 2007-09-26 | 2007-11-30 | 2012-03-26 | 2012-03-30 | Shetland Islands | 8603592.02 | 30559.38 | 0 | 0 | 0 | 0 | 0 | 30559.38 | 0 | 8634151.4 | 0 | [6 empty] | DW13 | 19% | DW2 | 19% | DW3G | 19% | WSNI | 43%
45415 | Southdean Mill WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-12-20 | 2012-07-30 | 2013-05-29 | 2013-08-22 | Scottish Borders | 940494.06 | -24762.39 | 0 | 0 | 0 | 0 | 0 | -24762.39 | 0 | 915731.67 | 2136 | [6 empty] | DW23 | 100%
501599 | Southpark Avenue Barrhead - Repair Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-01-19 | 2019-02-25 | 2019-03-25 | 2020-09-10 | 2020-12-11 | Renfrewshire | 0 | 0 | 11388 | 197363.19 | 344702.81 | 1614005 | 250845 | 2418304 | 2249 | 2420553 | 0 | [6 empty] | CM_WWI | 100%
403529 | Spence Court East Kilbride | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-07-12 | 2014-12-16 | 2015-01-05 | 2016-03-22 | 2016-04-01 | South Lanarkshire | 318870 | 54633 | 45497 | 0 | -4115.9 | 0 | 0 | 96014.1 | 0 | 414884.1 | 204193.13 | [6 empty] | CS11A | 100%
503340 | Spey Abstraction Scheme - Emergency Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2018-10-02 | 2018-10-02 | 2018-10-08 | 2019-06-26 | 2019-06-26 | Moray | 0 | 0 | 0 | 0 | 1085031.12 | -94925.59 | 1948.39 | 992053.92 | 0 | 992053.92 | 0 | [6 empty] | CM_WSNI | 100%
45614 | Spey Scheme (Badentinan) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-07-13 | 2014-01-08 | 2014-03-21 | Moray | 627236.87 | 2006.11 | 0 | 0 | 0 | 0 | 0 | 2006.11 | 0 | 629242.98 | 1300 | [6 empty] | DW1A | 100%
503490 | SPG Allocation for Emerging Needs Holding Line | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4443764.78 | 4443764.78 | 0 | 4443764.78 | 0 | [6 empty] | CM_M&G | 100%
402355 | Spiral Membrane Supply Incident | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2011-08-26 | 2011-08-26 | 2011-08-26 | 2015-09-30 |  | Scottish Water Wide | 1188218 | 44582.08 | 0 | 0 | 0 | 0 | 0 | 44582.08 | 0 | 1232800.08 | 0 | [6 empty] | CM_WSNI | 100%
400927 | Sponsorship of MGSDP and GSS Project | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-21 | 2013-05-08 | 2013-05-09 | 2018-06-22 | 2011-03-14 | Glasgow City | 301676.37 | 6000.63 | 0.44 | 0 | -1125.03 | 0 | 1125.03 | 6001.07 | 0 | 307677.44 | 0 | [6 empty] | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.34%
502830 | Springbank Alyth Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2018-03-29 | 2018-11-21 | 2019-04-01 | 2019-08-29 | 2019-08-29 | Perth and Kinross | 0 | 0 | 0 | 13684.4 | 51221.6 | 130094 | 0 | 195000 | 0 | 195000 | 0 | [6 empty] | CM_WWI | 100%
500784 | Springfield WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-09-07 | 2019-02-01 | 2019-03-29 | 2020-09-25 | 2020-12-24 | Fife | 0 | 108131 | 100990 | 204703.93 | 659425.76 | 1368640.31 | 699782.32 | 3141673.32 | 24390.68 | 3166064 | 0 | [6 empty] | CM_WWNI | 100%
504129 | Springhill Farm WWPS - Site Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2021-09-15 | 2023-02-15 | 2023-06-19 | 2024-02-12 | 2024-05-14 | - | 0 | 0 | 0 | 0 | 0 | 1904.64 | -1904.64 | 0 | 0 | 0 | 0 | [6 empty] | WWI | 100%
503287 | Springholm WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-08 | 2023-06-22 | 2023-10-25 | 2024-10-22 | 2025-01-22 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 65954.87 | 96.89 | 57415.62 | 123467.38 | 1876532.65 | 2000000.03 | 136478.56 | [6 empty] | SG1 | 100%
401739 | SPS - Critical Assets Data Quality Testing and Remedials - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2011-01-10 | 2011-05-16 | 2011-06-15 | 2016-01-27 |  | Scottish Water Wide | 212157 | -2222.44 | 0 | 0 | 0 | 0 | 0 | -2222.44 | 0 | 209934.56 | 0 | [6 empty] | CM_WSNI | 100%
501362 | SPS 1881 Prestonpans WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-07-19 | 2017-07-17 | 2018-01-08 | 2019-03-14 | 2019-03-14 | East Lothian | 0 | 0 | 32194 | 516016 | 414115 | 29491 | 0 | 991816 | 0 | 991816 | 0 | [6 empty] | CM_WWNI | 100%
502406 | SPS Data Quality Priority and Remedials Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS0 | 2017-11-07 | 2021-04-05 | 2023-08-02 | 2024-08-30 | 2024-08-30 | Scottish Water Wide | 0 | 0 | 2814.95 | 22170.17 | 40406.71 | 2135.57 | 0.01 | 67527.41 | 144038.42 | 211565.83 | 0 | [6 empty] | CM_WSNI | 100%
501364 | SPS001544 East Mains WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-08-29 | 2020-04-22 | 2020-04-22 | 2019-07-12 | 2019-07-12 | South Lanarkshire | 0 | 0 | 21521 | -8673 | 0 | -714.77 | 0 | 12133.23 | 0 | 12133.23 | 0 | [6 empty] | CM_WWNI | 100%
404066 | SR 15 ES - Milngavie WOA M5 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-01-05 | 2015-07-30 | 2015-10-12 | 2020-03-31 | 2018-09-04 | Glasgow City | 50457 | 1141083.7 | 1947685.3 | 2718082 | 829969.89 | -38443.14 | 50531.55 | 6648909.3 | 0 | 6699366.3 | 0 | [6 empty] | CM_WSI | 100%
404005 | SR 15 ES - PSCD Newmore Raw Water Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | GW2 | 2020-09-28 | 2021-07-19 | 2021-08-13 | 2022-02-09 | 2022-12-23 | Highland | 244 | 53159 | 42940 | 103126 | 3777.07 | 384.62 | 4500 | 207886.69 | 115.38 | 208246.07 | 0 | [6 empty] | SR15_EXC_EXC | 100%
404081 | SR 15 ES - W298-SW325-SW326 Byres Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS0 | 2015-07-27 | 2020-12-14 | 2021-03-12 | 2022-02-07 | 2022-05-09 | Glasgow City | 0 | 30000 | 0 | 3894 | 13106 | 10937.5 | 100020.89 | 157958.39 | 830775.44 | 988733.83 | 196097.17 | [6 empty] | CS11 | 100%
500438 | SR 15 SWD SVCW Waste East Infra | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-03-03 | 2017-03-03 | All East Unitary Authorities | 0 | 865019.51 | 101287.61 | -72858.42 | 0 | 0 | 0 | 893448.7 | 0 | 893448.7 | 0 | [6 empty] | CM_WWI | 100%
501951 | SR 15 Western Isles SR Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-02-15 | 2016-02-15 | 2016-04-26 | 2021-02-26 | 2020-10-19 | All North Unitary Authorities | 0 | 435588.61 | 1029390.99 | 381953.9 | 178775.04 | 8858.25 | 470830.39 | 2505397.18 | 6146.29 | 2511543.47 | 0 | [6 empty] | CM_WSNI | 100%
504210 | SR Bacti WQ Instruments | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-21 | 2020-07-15 | 2020-08-26 | 2020-08-27 | - | 0 | 0 | 0 | 0 | 0 | 102647.17 | 54352.83 | 157000 | 0 | 157000 | 0 | [6 empty] | CM_WSNI | 100%
400921 | SR Data Quality | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2010-06-02 | 2011-01-18 | 2011-01-18 | 2016-06-07 |  | Scottish Water Wide | 1057007 | 53761 | -54375.89 | 0 | -89697.58 | 0 | 0 | -90312.47 | 0 | 966694.53 | 0 | [6 empty] | CM_WWNI | 100%
500079 | SR Level Controls - New | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2017-08-18 | 2017-10-02 | Scottish Water Wide | 0 | 152689 | -94078 | -7556.63 | 0 | 0 | 0 | 51054.37 | 0 | 51054.37 | 0 | [6 empty] | CM_WSI | 100%
500083 | SR Level Controls - Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2021-05-10 | 2021-05-10 | Scottish Water Wide | 0 | 119135 | 74295 | 34778 | 66734 | 52374 | 62472 | 409788 | 0 | 409788 | 0 | [6 empty] | CM_WSI | 100%
503874 | SR Mission Simple Repairs T3 East C Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-02 | 2020-02-03 | 2020-12-11 | 2020-12-11 | - | 0 | 0 | 0 | 0 | 0 | 20000 | 230000 | 250000 | 0 | 250000 | 0 | [6 empty] | CM_WSNI | 100%
503833 | SR Mission Simple Repairs T3 East D Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-11-28 | 2020-02-03 | 2020-12-16 | 2020-12-11 | - | 0 | 0 | 0 | 0 | 0 | 35342.16 | 0 | 35342.16 | 0 | 35342.16 | 0 | [6 empty] | CM_WSNI | 100%
503836 | SR Mission Simple Repairs T3 East E Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-02 | 2020-02-03 | 2020-12-16 | 2020-12-16 | - | 0 | 0 | 0 | 0 | 0 | 12735.95 | 0 | 12735.95 | 0 | 12735.95 | 0 | [6 empty] | CM_WSNI | 100%
504740 | SR Mission Simple Repairs T3 South B Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-27 | 2020-02-03 | 2020-12-16 | 2020-12-16 | - | 0 | 0 | 0 | 0 | 0 | 16000 | 234000 | 250000 | 0 | 250000 | 0 | [6 empty] | CM_WSNI | 100%
504317 | SR Mission Simple Repairs T3 West B Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-20 | 2020-02-03 | 2020-12-16 | 2020-12-16 | - | 0 | 0 | 0 | 0 | 0 | 97663.39 | 0 | 97663.39 | 0 | 97663.39 | 0 | [6 empty] | CM_WSNI | 100%
504399 | SR Mission Simple Repairs T3 West C Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-27 | 2020-02-03 | 2020-12-16 | 2021-01-06 | - | 0 | 0 | 0 | 0 | 0 | 17000 | 233000 | 250000 | 0 | 250000 | 0 | [6 empty] | CM_WSNI | 100%
37714 | SR06 Water Resource Strategic Studies - WFD Implementation Stage (SW Initiated CAR Licence) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-02 | 2013-07-11 | 2008-12-02 | 2008-12-02 | 2011-01-01 | Scottish Water Wide | 327104 | 2586.48 | 440.93 | 0 | 0 | 0 | 0 | 3027.41 | 0 | 330131.41 | 806 | [6 empty] | WR1 | 100%
400609 | SR10 Access Land Reform | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2004-03-30 | 2010-06-07 | 2010-06-07 | 2015-10-01 |  | Scottish Water Wide | 41631 | -3537.58 | 0 | 0 | 0 | 0 | 0 | -3537.58 | 0 | 38093.42 | 0 | [6 empty] | CM_M&G | 100%
403041 | SR10 Back Tolsta WOA - Stage 2 Additional Re-hab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-03-25 | 2013-04-25 | 2014-11-03 |  | Na H-Eileanan an Iar | 206343 | 0 | -1718.41 | 0 | 0 | 0 | 0 | -1718.41 | 0 | 204624.59 | 0 | [6 empty] | CM_WSI | 100%
402532 | SR10 EAST SR Inlet Control New Installations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-09 | 2012-02-09 | 2012-04-02 | 2015-06-15 |  | Scottish Water Wide | 238970 | -25768.73 | 0 | 0 | 0 | 0 | 9 | -25759.73 | 0 | 213210.27 | 0 | [6 empty] | CM_WSI | 100%
400610 | SR10 Legacy Legal Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2014-06-23 | 2014-06-24 | 2015-12-08 |  | Scottish Water Wide | 750000 | -57291.57 | 0 | 42515 | 0 | 0 | -42515 | -57291.57 | 0 | 692708.43 | 0 | [6 empty] | CM_M&G | 100%
402459 | SR10 Low Pressure Boundary Box Installations | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-22 | 2012-09-27 | 2012-09-28 | 2014-03-11 | 2014-03-27 | Scottish Water Wide | 28434.08 | 860 | 0 | 0 | 0 | 0 | 0 | 860 | 0 | 29294.08 | 587 | [6 empty] | CS1 | 100%
400261 | SR10 Low Pressure Enhancement Cluster 1 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-02-09 | 2012-03-05 | 2014-03-28 | 2013-11-07 | All East Unitary Authorities | 142000 | 0 | -999.84 | 0 | 0 | 0 | 0 | -999.84 | 0 | 141000.16 | 0 | [6 empty] | CM_WSI | 29.08% | CS1 | 70.92%
400262 | SR10 Low Pressure Enhancement Cluster 2 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-01-30 | 2012-02-14 | 2016-11-15 | 2015-03-09 | Aberdeenshire | 353098.8 | 3747.2 | 21351.73 | 10130.77 | -93.4 | 0 | 0 | 35136.3 | 0 | 388235.1 | 6361 | [6 empty] | CS1 | 100%
400263 | SR10 Low Pressure Enhancement Cluster 3 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-01-18 | 2011-02-07 | 2013-09-30 | 2013-03-31 | Highland | 357574 | -1793.51 | 0 | 0 | 0 | 0 | 0 | -1793.51 | 0 | 355780.49 | 0 | [6 empty] | CS1 | 100%
400264 | SR10 Low Pressure Enhancement Cluster 4 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-03-10 | 2011-03-14 | 2013-08-12 | 2013-08-20 | Perth and Kinross | 406748 | -4451.26 | 0 | 0 | 0 | 0 | 0 | -4451.26 | 0 | 402296.74 | 252 | [6 empty] | CS1 | 100%
400269 | SR10 Low Pressure Enhancement WSZ001013 Lochgilphead WSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-11-19 | 2013-03-12 | 2014-06-09 | 2014-03-19 | Argyll and Bute-North Argyll | 147536.55 | 147.65 | 0 | 0 | 0 | 0 | 0 | 147.65 | 0 | 147684.2 | 0 | [6 empty] | CS1 | 100%
400272 | SR10 Low Pressure Enhancement WSZ001467 Tobermory WSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-11-22 | 2012-03-05 | 2013-03-29 | 2013-03-29 | Argyll and Bute-North Argyll | 560049.77 | 181.4 | 0 | 0 | 0 | 0 | 0 | 181.4 | 0 | 560231.17 | 0 | [6 empty] | CS1 | 100%
400273 | SR10 Low Pressure Enhancement WSZ001495 Towerhill WSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-06-29 | 2012-07-30 | 2013-01-15 | 2013-01-15 | Orkney Islands | 471168.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471168.67 | 0 | [6 empty] | CS1 | 50% | DW5 | 50%
403999 | SR10 Membrane Replacement Purchase Code | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-11-21 | 2014-11-21 | 2014-11-24 | 2016-07-04 |  | Scottish Water Wide | 1479670 | 37191.44 | 0 | 0 | 0 | 0 | 0 | 37191.44 | 0 | 1516861.44 | 0 | [6 empty] | CM_WSNI | 100%
400611 | SR10 Milngavie Reservoirs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-03-30 | 2013-03-05 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 204150 | -2511.5 | 0 | 0 | 0 | 0 | 0 | -2511.5 | 0 | 201638.5 | 0 | [6 empty] | CM_M&G | 100%
403042 | SR10 Ness WOA Swainbost Re-hab Stage 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-08-22 | 2014-04-08 | 2015-03-03 |  | Na H-Eileanan an Iar | 295618 | 500 | -1676.36 | 0 | 0 | 0 | 0 | -1176.36 | 0 | 294441.64 | 0 | [6 empty] | CM_WSI | 100%
46150 | SR10 New DAS Models | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-10-15 | 2010-03-24 | 2010-06-01 | 2015-03-11 |  | Scottish Water Wide | 452054 | 2544.13 | 0 | 0 | 0 | 0 | 0 | 2544.13 | 0 | 454598.13 | 0 | [6 empty] | CM_WWI | 100%
400727 | SR10 NEW PRV Installs- Distribution Mains EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-08 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 1318480.55 | 74517.32 | 13929.55 | 0 | 0 | 0 | 0 | 88446.87 | 0 | 1406927.42 | 0 | [6 empty] | CM_WSI | 100%
400728 | SR10 NEW PRV Installs- Distribution Mains WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-06 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 1893371 | -57216.24 | 214.5 | 0 | 0 | 0 | 0 | -57001.74 | 0 | 1836369.26 | 0 | [6 empty] | CM_WSI | 100%
400729 | SR10 New PRV Installs- Trunk Mains EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-09 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 204535 | -70.85 | 0 | 0 | 0 | 0 | 0 | -70.85 | 0 | 204464.15 | 0 | [6 empty] | CM_WSI | 100%
400726 | SR10 New PRV Installs- Trunk Mains WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2011-06-06 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 257228 | -47486.49 | 0 | 0 | 0 | 0 | 0 | -47486.49 | 0 | 209741.51 | 0 | [6 empty] | CM_WSI | 100%
400086 | SR10 New PVR Installs - Glasgow Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2009-12-17 | 2011-02-03 | 2011-04-04 | 2017-11-01 |  | Glasgow City | 538492 | 25363.01 | 66144.99 | -29590.36 | 0 | 0 | 0 | 61917.64 | 0 | 600409.64 | 0 | [6 empty] | CM_WSI | 100%
400872 | SR10 Redundant Assets | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2011-09-14 | 2011-09-14 | 2015-12-01 |  | Scottish Water Wide | 375022.09 | 73675 | 0 | 0 | 0 | 0 | 0 | 73675 | 0 | 448697.09 | 0 | [6 empty] | CM_M&G | 100%
400612 | SR10 Rural Landlord Liability | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2010-06-15 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 448460 | -17155.07 | 0 | 0 | 0 | 0 | 0 | -17155.07 | 0 | 431304.93 | 0 | [6 empty] | CM_M&G | 100%
400752 | SR10 Service Reservoir Outlet Metering - New Installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2011-06-30 | 2011-07-04 | 2015-07-02 |  | Scottish Water Wide | 272261 | -28507 | -6469 | -5307.29 | 0 | 0 | 0 | -40283.29 | 0 | 231977.71 | 0 | [6 empty] | CM_WSI | 100%
400613 | SR10 Tenant Housing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2010-06-15 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 222390 | 4857.53 | 0 | 0 | 0 | 0 | 0 | 4857.53 | 0 | 227247.53 | 0 | [6 empty] | CM_M&G | 100%
502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-01 | 2017-09-14 | Scottish Water Wide | 0 | 0 | 7194.94 | -2289.28 | 1723.76 | 0 | 0 | 6629.42 | 0 | 6629.42 | 273508.41 | [6 empty] | DW9D | 100%
400750 | SR10 Trunk Main Metering - New Installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2011-06-06 | 2011-06-20 | 2015-07-02 |  | Scottish Water Wide | 825774 | 12448.37 | 979.27 | 0 | 0 | 0 | 0 | 13427.64 | 0 | 839201.64 | 0 | [6 empty] | CM_WSI | 100%
402531 | SR10 WEST SR Inlet Control New Installations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-07 | 2012-02-07 | 2012-04-02 | 2015-06-15 |  | Scottish Water Wide | 73297 | -4304.37 | 0 | 0 | 0 | 0 | 0 | -4304.37 | 0 | 68992.63 | 0 | [6 empty] | CM_WSI | 100%
402505 | SR10 WWTW Odour Investigations | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2012-01-27 | 2012-05-16 | 2012-06-06 | 2013-05-23 |  | Scottish Water Wide | 53570.03 | 0.97 | -974.87 | 0 | 0 | 0 | -0.97 | -974.87 | 0 | 52595.16 | 0 | [6 empty] | QS4EQS | 100%
402740 | SR15 - Additional Support for Development of SR15 Capital Maintence Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-12 | 2012-12-10 | 2016-03-03 | 2016-03-03 |  | Scottish Water Wide | 621170.81 | -60854.82 | 0 | 0 | 0 | 0 | 0 | -60854.82 | 0 | 560315.99 | 0 | [6 empty] | CM_M&G | 100%
502904 | SR15 - Blackwood WWTW CM Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-11-23 | 2028-09-27 | 2029-02-07 | 2030-04-26 | 2030-07-29 | South Lanarkshire | 0 | 0 | 0 | 36613.03 | 8653.26 | 1957.72 | 19587.37 | 66811.38 | 2733188.71 | 2800000.09 | 0 | [6 empty] | CM_WWNI | 100%
500503 | SR15 Katrine | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-15 | 2021-06-04 | 2021-06-04 | Scottish Water Wide | 0 | 102535.26 | 27164.74 | -28700 | 71568.58 | 78931.42 | 99500 | 351000 | 0 | 351000 | 0 | [6 empty] | CM_M&G | 100%
404067 | SR15 - Reactive & Opportunistic Lead Communication Pipe Replacement Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-06-15 | 2015-07-22 | 2015-07-22 |  | 2021-05-07 | Scottish Water Wide | 0 | 36200 | 1252.6 | 0 | 154319.4 | 364321.4 | 879285.28 | 1435378.68 | 40621.34 | 1476000.02 | 808915.39 | [6 empty] | DW1B | 100%
502302 | SR15 WW Temporary Chemical Dosing Systems Upgrade - Phase 4 (EAST) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-05-29 | 2022-02-16 | 2022-06-15 | 2023-09-01 | 2023-12-04 | Scottish Water Wide | 0 | 0 | 38371.6 | 24145.73 | 2825.76 | 30184.33 | 135541.11 | 231068.53 | 2365931.51 | 2597000.04 | 0 | [6 empty] | SR21_WW | 100%
503663 | SR15 _SPG balance line for unpromoted needs_HOLDING LINE | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0.98 | 0 | 0.98 | 0 | [6 empty] | CM_M&G | 100%
500962 | SR15 Aids to Navigation repair and replacement programme | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-09 | 2015-12-09 | 2016-01-05 | 2021-05-31 | 2021-05-31 | Scottish Water Wide | 0 | 106216 | 5863 | 19156 | 2416 | 22081.23 | 44267.77 | 200000 | 0 | 200000 | 0 | [6 empty] | CM_WWI | 100%
503581 | SR15 Asset Disposals (Finance) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2019-05-20 | 2022-02-14 | 2022-02-21 |  | 2022-04-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 4782.77 | -4781.97 | 0.8 | 0.18 | 0.98 | 0 | [6 empty] | CM_M&G | 100%
504207 | SR15 Balgray MIOS Phase 3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-01-22 | 2020-10-01 | 2021-05-05 | 2021-05-05 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 2105.57 | 216465.84 | 218571.41 | 2428.59 | 221000 | 0 | [6 empty] | CM_WSI | 100%
500975 | SR15 Borehole Programme (Phase 1) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-26 | 2016-07-13 | 2016-09-07 | 2021-04-21 | 2021-04-22 | Scottish Water Wide | 0 | 129944.09 | 936820.91 | 102512.78 | 395762.71 | 524873.39 | 142476.46 | 2232390.34 | 172804.08 | 2405194.42 | 0 | [6 empty] | CM_WSI | 100%
502274 | SR15 Borehole Programme (Phase 2B) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-02 | 2028-10-19 | 2029-02-07 | 2030-01-29 | 2030-01-29 | Scottish Water Wide | 0 | 0 | 4500 | 24720.73 | 3721.76 | 12057.51 | 0 | 45000 | 1782455.02 | 1827455.02 | 0 | [6 empty] | CM_WSI | 100%
500625 | SR15 Capital Overhead Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | -34702577.7 | -44115891.23 | -39541230.01 | -43137127.91 | -31292317.36 | -37783364.72 | -230572508.93 | -25188909.84 | -255761418.77 | 0 | [6 empty] | CM_OVH | 100%
500936 | SR15 CMAP CSD Identified Sewer Rehabilitation Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-12-16 | 2015-12-16 | 2016-02-01 | 2016-06-29 | 2016-07-29 | Scottish Water Wide | 0 | 933715.54 | 0 | 0 | 0 | 0 | 0 | 933715.54 | 0 | 933715.54 | 0 | [6 empty] | CM_WWI | 100%
502283 | SR15 CMAP CSD Identified Sewer Rehabilitation Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-08-19 | 2016-08-19 | 2016-09-01 | 2017-04-06 | 2017-04-28 | Scottish Water Wide | 0 | 0 | 900000.13 | 0 | 0 | 0 | 0 | 900000.13 | 0 | 900000.13 | 0 | [6 empty] | CM_WWI | 100%
505763 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2020-04-01 | 2020-03-31 | 2021-04-13 | 2021-10-12 | 2022-01-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000 | 0 | 900000 | 0 | [6 empty] | CM_WWI | 100%
502717 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-04-24 | 2017-04-24 | 2017-08-15 | 2018-08-21 | 2018-08-21 | Scottish Water Wide | 0 | 0 | 0 | 829912.14 | 28758.87 | 0 | 0 | 858671.01 | 0 | 858671.01 | 0 | [6 empty] | CM_WWI | 100%
503233 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2019-08-28 | 2019-08-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 860214.1 | 0 | 0 | 860214.1 | 0 | 860214.1 | 0 | [6 empty] | CM_WWI | 100%
503561 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-03-26 | 2019-03-26 | 2019-12-03 |  | 2020-07-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 856726.32 | 43273.68 | 900000 | 0 | 900000 | 0 | [6 empty] | CM_WWI | 100%
402734 | SR15 Cost Management Support | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-06-05 | 2012-08-07 | 2012-08-07 | 2015-11-02 |  | Scottish Water Wide | 346644.96 | 4293.72 | 0 | -1602.35 | 0 | 0 | 0 | 2691.37 | 0 | 349336.33 | 0 | [6 empty] | CM_M&G | 100%
500582 | SR15 Energy Improvement Prog Accelerated Energy Consumption Reduction Prog (W & WW) | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2017-04-13 | 2017-05-15 | Scottish Water Wide | 0 | 670608.82 | 434191.63 | -54695.79 | 0 | 0 | -3154.6 | 1046950.06 | 0 | 1046950.06 | 189507.73 | [6 empty] | I2S_WNI | 4.484% | I2S_WWNI | 95.52%
500488 | SR15 Enhanced Non Domestic Meter Replacement Programme | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | Water |  | SWD | Meter Accuracy | MS3 | 2015-08-21 | 2017-02-16 | 2017-02-16 | 2021-05-21 | 2021-05-21 | Scottish Water Wide | 0 | 598398 | 3540587.47 | 2846271.62 | 3014742.91 | 2061519.36 | 2406480.64 | 14468000 | 0 | 14468000 | 4004712.5 | [6 empty] | CS4 | 100%
500648 | SR15 Environment Costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-02 | 2015-09-02 | 2015-09-02 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 2254837 | 1460752.51 | 1795834.49 | 898486.43 | 290571.58 | 243624 | 6944106.01 | 0 | 6944106.01 | 0 | [6 empty] | CM_M&G | 100%
403962 | SR15 ES - 3 TWPs - West Area Cluster 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-05-08 | 2018-09-20 | 2018-09-24 | 2020-04-24 | 2020-07-31 | All West Unitary Authorities | 416.92 | 56415.08 | 73026.3 | 168417.32 | 384498.78 | 108742.6 | 0 | 791100.08 | 1575 | 793092 | 0 | [6 empty] | CM_WSNI | 100%
403961 | SR15 ES - 7 TWPs - West Area Cluster 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-07-06 | 2018-09-25 | 2018-10-02 | 2020-07-31 | 2020-10-27 | All West Unitary Authorities | 1592 | 79112 | 90786.65 | 411886.8 | 750001.34 | 382583.11 | 155100.1 | 1869470 | 16828 | 1887890 | 0 |  |  |  |  | 12828 |  | CM_WSNI | 100%
403124 | SR15 ES - Achmelvich WTW - Main out | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2013-01-14 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Highland | 124761.87 | 248383.46 | 745428.63 | 1239258.04 | 336579.23 | -20491.64 | -242522.89 | 2306634.83 | 0 | 2431396.7 | 773016.66 | [6 empty] | DW25P | 10% | DW2 | 90% | bar: Regulatory Outputs OMG-01
403912 | SR15 ES - Ailsa Drive - Kirkintilloch | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-03-30 | 2020-02-17 | 2020-02-21 | 2020-10-06 | 2021-01-20 | East Dunbartonshire | 2862 | 100419.25 | 198122.71 | 112857.57 | 96770.47 | 20067.72 | 87443.28 | 615681 | 0 | 618543 | 1456386.61 | [6 empty] | EC01C | 100%
403332 | SR15 ES - Ailsa Road - Craig Street | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2020-12-21 | 2020-08-10 | 2020-09-03 | 2021-05-27 | 2021-07-27 | North Lanarkshire | 153299.6 | 151055.4 | 107149.83 | 41027.88 | -32532.71 | 58716.12 | 95858.11 | 421274.63 | 15959.77 | 590534 | 1528054.73 | [6 empty] | CS15 | 13.41% | CS11 | 86.59%
403339 | SR15 ES - Airlie Street | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2013-03-08 | 2015-10-01 | 2016-01-05 | 2020-10-21 | 2021-02-04 | Glasgow City | 48494.57 | 322929.43 | 121396 | 2883 | -84190 | 90186 | 356473 | 809677.43 | 41827 | 899999 | 134102.5 | [6 empty] | CS15 | 100%
403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2019-03-18 | 2022-12-16 | East Ayrshire | 184566.88 | 11479642.12 | 31562741 | 10316182.69 | 990858.24 | 504557.21 | 0 | 54853981.26 | 0 | 55038548.14 | 4507587.62 |  |  |  |  | 467820 |  | SR15_EXC_EXC | 4.3% | DW2 | 38.7% | CM_WSNI | 57%
403886 | SR15 ES - Assynt WTW - CWT Additional Storage | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | Highland | 5971.54 | 10521.58 | -16374.67 | 72.56 | 0 | 0 | -190.01 | -5970.54 | 0 | 1 | 1823900.39 | [6 empty] | CS16W | 100%
403578 | SR15 ES - Assynt WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS7 | 2013-10-02 | 2015-03-26 | 2015-03-31 | 2015-11-30 | 2016-03-31 | Highland | 102089.25 | 451535.75 | 289362.83 | 6160 | -4194.01 | 0 | 0 | 742864.57 | 0 | 844953.82 | 389777.9 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
403132 | SR15 ES - Avonspark Street and Edgefauld Road Internal and External Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2012-12-10 | 2015-06-25 | 2015-09-15 | 2017-03-16 | 2017-03-16 | Glasgow City | 272215 | 2577916.96 | 613135.7 | 50348.75 | -4402.09 | 659.25 | -320.46 | 3237338.11 | 0 | 3509553.11 | 2185798.47 | [6 empty] | CS11 | 100%
403989 | SR15 ES - Back Tolsta WTW - SR15 WQ Technical Expression Resolution | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-05-18 | 2018-01-23 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Na H-Eileanan an Iar | 469.7 | 2055.3 | -2525 | 5691.23 | 70.44 | 593.33 | 152.02 | 6037.32 | 0 | 6507.02 | 1511352.29 | [6 empty] | DW3B | 10% | DW25 | 90%
404037 | SR15 ES - Balmore South Region Nith WOA Brackenhirst WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-17 | 2017-06-30 | 2017-09-11 | 2019-09-16 | 2018-03-26 | North Lanarkshire | 1240.88 | 9265.12 | 89805 | 740954 | 951091.8 | -100575.82 | -234.4 | 1690305.7 | 0 | 1691546.58 | 0 | [6 empty] | CM_WSI | 100%
404036 | SR15 ES - Balmore South Region Nith WOA Dalmacoulter WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2027-05-10 | 2027-06-08 | 2029-03-01 | 2029-05-31 | North Lanarkshire | 2572.61 | 9110.76 | 171397.63 | 64409 | -6074 | 3090.04 | 0 | 241933.43 | 3271384 | 3515890.04 | 0 | [6 empty] | CM_WSI | 100%
403773 | SR15 ES - Balquhidder WTW manganese issues and Capital Maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS6 | 2015-05-08 | 2016-03-30 | 2016-06-30 | 2017-06-30 | 2017-10-31 | Stirling | 464 | 87176 | 195777.05 | 114061.64 | -1638.08 | 12202.39 | 0 | 407579 | 0 | 408043 | 270378.76 | [6 empty] | DW25P | 6.127% | CM_WSI | 19.61% | CM_WSNI | 74.27% | bar: Regulatory Outputs OMG-04
403126 | SR15 ES - Bayhead WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2013-02-06 | 2016-07-22 | 2016-09-12 | 2019-09-30 | 2020-01-31 | Na H-Eileanan an Iar | 115146.46 | 434026.54 | 1902777 | 179318 | 170104.64 | 105397.68 | -187.52 | 2791436.34 | 0 | 2906582.8 | 3227592.16 |  |  |  |  | -85927.05 |  | DW25 | 10% | DW3G | 20% | DW2 | 70% | bar: Regulatory Outputs OMG-01
403699 | SR15 ES - Black Esk WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2014-03-31 | 2016-03-23 | 2016-03-28 | 2017-11-23 | 2021-06-18 | Dumfries and Galloway | 123564.93 | 334376.41 | 1263109.66 | 2469421.75 | 16588.2 | 1241.25 | 5323.13 | 4090060.4 | 11591.47 | 4225216.8 | 740960.62 |  |  |  |  | 8662 |  | DW3J | 9.313% | DW25P | 17.59% | DW3C | 73.1%
404052 | SR15 ES - Bradan WOA Bradan WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2028-06-06 | 2028-08-23 | 2029-01-02 | 2029-03-27 | South Ayrshire | 960.29 | 1576.71 | 6608 | 0 | 54134 | -59060.53 | 59060.53 | 62318.71 | 724160.99 | 787439.99 | 0 | [6 empty] | CM_WSI | 100%
404051 | SR15 ES - Bradan WOA Stafflar WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2027-06-15 | 2027-07-07 | 2029-02-08 | 2029-05-11 | South Ayrshire | 2137.71 | 170738.29 | 351711 | -313672.87 | 85515 | -32010.05 | 142328.59 | 404609.96 | 1346162.29 | 1752909.96 | 0 | [6 empty] | CM_WSI | 100%
403821 | SR15 ES - Bradan WTW - Improving Drinking Water Quality Reliability | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS7 | 2015-07-16 | 2018-06-28 | 2018-06-22 | 2018-06-20 | 2018-06-28 | South Ayrshire | 133140.04 | 177866.96 | -311007 | 471183.53 | -336267.16 | -387.78 | 0 | 1388.55 | 0 | 134528.59 | 1184912.67 | [6 empty] | DW25 | 100%
403453 | SR15 ES - Bruichladdich Islay - provision of new septic tank and extend outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-05-08 | 2015-02-27 | 2015-04-09 | 2015-07-31 | 2015-09-30 | Argyll and Bute-North Argyll | 128562 | 99557.72 | 1185.91 | 12.36 | 0 | 0 | 0 | 100755.99 | 0 | 229317.99 | 443023.62 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403333 | SR15 ES - Burnham Road | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-03-11 | 2017-04-07 | 2017-08-09 | 2016-10-11 | 2017-08-09 | Glasgow City | 54885 | 7541 | 29116.75 | -8192.38 | 0 | 0 | 0 | 28465.37 | 0 | 83350.37 | 1635990.1 | [6 empty] | CS11 | 100%
403964 | SR15 ES - Camphill to Barcraigs Raw Water Transfer Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-07-23 | 2028-08-07 | 2028-09-07 | 2029-11-19 | 2030-08-16 | North Ayrshire | 1369 | 52099 | -5027 | 740.47 | 5752.19 | 427.07 | 1954.84 | 55946.57 | 2841777.41 | 2899092.98 | 0 | [6 empty] | CM_WSI | 100%
403703 | SR15 ES - Camps Road Carnock - Dunfermline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2014-03-17 | 2018-12-17 | 2019-02-28 | 2018-11-20 | 2018-11-20 | Fife | 90696 | 25304 | 47801.81 | 32198.19 | 12726.65 | 0 | 0 | 118030.65 | 0 | 208726.65 | 204193.13 | [6 empty] | CS11 | 100%
403986 | SR15 ES - Carron Valley WTW Scada Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-07-06 | 2019-06-28 | 2019-09-02 | 2022-05-25 | 2022-09-07 | Stirling | 4578 | 45522 | 61549.95 | 134763.29 | 270042.19 | 1253305.57 | 1417781.35 | 3182964.35 | 1418400.65 | 4605943 | 0 | [6 empty] | CM_WSNI | 100%
403340 | SR15 ES - Clarence Gardens | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-03-08 | 2015-11-24 | 2016-04-04 | 2017-03-31 | 2017-03-31 | Glasgow City | 94114 | 1388608 | 419184 | 9406.05 | 5933.65 | 1 | -0.7 | 1823132 | 0 | 1917246 | 904764.02 | [6 empty] | CS15 | 100%
403985 | SR15 ES - Cochno Craigend Baljaffray SRs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2030-07-30 | 2031-12-08 | 2032-04-06 | 2019-05-07 | 2019-05-07 | West Dunbartonshire | 457 | 154.96 | 6682.74 | 12781.92 | 0 | 0 | 0 | 19619.62 | 0 | 20076.62 | 0 | [6 empty] | CM_WSNI | 100%
404046 | SR15 ES - Craigendoran Helensburgh Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-02-03 | 2016-04-22 | 2016-04-08 | 2017-05-30 | 2017-05-26 | Argyll and Bute-Cowal & Bute | 9046.26 | 1051930.74 | 1247733 | 1015124 | 26 | -16681.99 | 0.01 | 3298131.76 | 0 | 3307178.02 | 0 | [6 empty] | CM_WWI | 100%
403321 | SR15 ES - Craigneuk Avenue Airdrie Internal and External Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS1 | 2013-02-26 | 2020-06-15 | 2020-08-07 | 2022-04-19 | 2022-04-19 | North Lanarkshire | 219212 | 108646 | 81632 | 12281 | 115328 | 828766.71 | 4384530.01 | 5531183.72 | 4124888.37 | 9875284.09 | 3900700.83 |  |  |  |  | 1500 |  | CS11 | 100%
403341 | SR15 ES - Crow Wood Terrace | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS2 | 2013-03-11 | 2020-03-17 | 2020-05-12 | 2020-05-20 | 2020-05-20 | North Lanarkshire | 47744 | 8110 | -608.41 | 60557.41 | 120197 | 82613.23 | -18613.23 | 252256 | 0 | 300000 | 999635.37 | [6 empty] | CS15 | 100%
404068 | SR15 ES - Customer Requested Lead Pipe Replacement | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-03-19 | 2015-09-08 | 2015-10-01 |  | 2021-03-29 | Scottish Water Wide | 0 | 500800 | 1118772.17 | 831609.17 | 607138.78 | 823410.55 | 767265.03 | 4648995.7 | 51004.3 | 4700000 | 2008341.65 | [6 empty] | DW1C | 100%
403822 | SR15 ES - Daer Network Disinfection Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2014-05-27 | 2015-12-04 | 2016-01-08 | 2017-03-31 | 2017-05-31 | South Lanarkshire | 268.29 | 63731.71 | 58000 | -694.21 | 652.6 | 0 | -652.6 | 121037.5 | 0 | 121305.79 | 117323.06 | [6 empty] | DW25TS | 100% | bar: Regulatory Outputs OMG-47
403517 | SR15 ES - Dalderse AAD - Recovering Value from Wastewater | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-08-20 | 2015-03-23 | 2015-03-23 | 2020-07-06 | 2020-07-06 | Falkirk | 187681 | 8427.43 | 0 | 0 | 0 | 0 | 0 | 8427.43 | 0 | 196108.43 | 0 | [6 empty] | EC06 | 100%
403696 | SR15 ES - Dealston Road Barrhead | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2014-03-03 | 2014-12-05 | 2015-01-12 | 2015-09-28 | 2015-09-28 | East Renfrewshire | 731680 | 160320 | 0 | 6568.36 | 0 | 0 | 8.49 | 166896.85 | 0 | 898576.85 | 603995.95 | [6 empty] | CS11 | 100%
404043 | SR15 ES - Deans 2 SPS Livingston Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-01-21 | 2016-01-11 | 2016-02-15 | 2016-04-22 | 2016-08-08 | West Lothian | 762.62 | 143071.38 | 10671.53 | 358.8 | -2527.96 | 0 | 3.63 | 151577.38 | 0 | 152340 | 0 | [6 empty] | CM_WWI | 100%
403074 | SR15 ES - DOMS level 2b (water quality) investigations in 13 zones | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2013-07-29 | 2013-12-20 | 2013-12-20 | 2015-04-08 | 2015-04-08 | Scottish Water Wide | 248517 | -3112.38 | 0 | 0 | 0 | 0 | 0 | -3112.38 | 0 | 245404.62 | 5758.32 | [6 empty] | DW5A | 100%
403963 | SR15 ES - Dougliehill SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2015-07-06 | 2018-03-01 | 2018-03-16 | 2020-04-01 | 2020-06-23 | Renfrewshire | 903 | 119394 | 20772.71 | 320664.15 | 2240762.01 | 2136731.45 | 76656 | 4914980.32 | 8089 | 4923972.32 | 0 | [6 empty] | CM_M&G | 3.7% | CM_WSNI | 8.07% | DW25 | 88.23% | bar: Regulatory Outputs OMG-05
403695 | SR15 ES - Dumbarton Road (Clydebank Town Hall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2014-04-09 | 2017-02-10 | 2016-06-28 | 2016-06-28 | 2017-02-10 | West Dunbartonshire | 8887 | 113 | -6.49 | 0 | 0 | 0 | 0 | 106.51 | 0 | 8993.51 | 145185.89 | [6 empty] | CS11 | 100%
403223 | SR15 ES - E001 Glenmavis R-O 22 Glenwell ST CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2015-12-18 | 2016-02-22 | 2016-07-31 | 2017-03-31 | North Lanarkshire | 69532.94 | 168732.06 | 100767.23 | 1681.99 | -5603.92 | 0 | 1.7 | 265579.06 | 0 | 335112 | 293378.6 | [6 empty] | EC01F | 100% | [18 empty] | Regulatory Outputs OMG-18: 4
403224 | SR15 ES - E002 Glenmavis opp new Monkland Primary | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-21 | 2016-03-08 | 2016-06-23 | 2017-03-31 | North Lanarkshire | 20388.55 | 45678.45 | 10898.6 | 0.02 | 1538.96 | 0 | 0.42 | 58116.45 | 0 | 78505 | 293378.6 | [6 empty] | EC01F | 100%
403225 | SR15 ES - E003 Beechcroft WWPS NS685648 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-12-20 | 2015-07-23 | 2015-07-29 | 2015-08-11 | 2015-08-11 | Na H-Eileanan an Iar | 8010 | -60.59 | -637.62 | 0 | 0 | -145.66 | 153.61 | -690.26 | 0 | 7319.74 | 0 | [6 empty] | EC10B | 100%
403226 | SR15 ES - E004 DALDOWIE - Cluster 7 - Old Monkland 53-55 Woodside ST CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2012-12-20 | 2018-11-21 | 2019-01-18 | 2019-02-28 | 2019-03-31 | North Lanarkshire | 8700.18 | 3490.81 | 4084.86 | 53724.15 | 11816 | 669.33 | 136.6 | 73921.75 | 44.06 | 82665.99 | 46023.48 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403227 | SR15 ES - E005 Raebog Rd-Windsor Drive Dual Manhole | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS4 | 2012-12-21 | 2019-07-22 | 2019-08-27 | 2020-03-17 | 2020-03-02 | North Lanarkshire | 10425.84 | 61.56 | 2269.21 | 23243.39 | 22220 | 208229 | 0 | 256023.16 | 2100 | 268549 | 293378.6 | [6 empty] | EC01C | 100%
403228 | SR15 ES - E006 Raebog Rd Dual Manhole | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-20 | 2015-08-30 | 2016-06-23 | 2016-06-23 | North Lanarkshire | 80851 | 800519 | 223218.25 | 8411.75 | -4571.44 | 0 | 0.44 | 1027578 | 0 | 1108429 | 293378.6 | [6 empty] | EC01C | 100%
403229 | SR15 ES - E007 190 Wraes View Gateside | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2012-12-20 | 2015-10-09 | 2015-10-12 | 2015-10-31 | 2015-10-31 | East Renfrewshire | 4032 | 111.61 | 0 | 0 | 0 | 0 | 0.37 | 111.98 | 0 | 4143.98 | 41238.38 | [6 empty] | EC10B | 100% | [18 empty] | Regulatory Outputs OMG-18: 2
403230 | SR15 ES - E008 36 Vardar Avenue CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2012-12-21 | 2015-08-27 | 2015-08-27 | 2015-08-31 | 2015-11-30 | East Renfrewshire | 32828 | -635.43 | 0 | 0 | 0 | 0 | 0 | -635.43 | 0 | 32192.57 | 328268.38 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-18
403231 | SR15 ES - E009 At rear of 9 Glasgow Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2016-03-21 | 2016-03-29 | 2016-12-31 | 2017-03-31 | Renfrewshire | 24966.1 | 137033.9 | 503705.12 | -762.61 | 3947.28 | 0 | 0.21 | 643923.9 | 0 | 668890 | 430077.7 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403232 | SR15 ES - E010 Bankholm Place SPS CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2012-12-21 | 2017-03-27 | 2017-03-27 | 2016-09-12 | 2017-03-27 | East Renfrewshire | 38936 | 3607.64 | -40950.01 | 317.9 | 49.31 | 0.5 | -0.5 | -36975.16 | 0 | 1960.84 | 20016.79 | [6 empty] | EC01F | 100%
403233 | SR15 ES - E011 Busby WwPS (Bankholm Place) | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2012-12-21 | 2018-01-31 | 2018-01-31 | 2016-02-23 | 2018-01-31 | East Renfrewshire | 3657.39 | 77.97 | 62.88 | 61.56 | 0 | 0 | 0 | 202.41 | 0 | 3859.8 | 0 | [6 empty] | EC01B | 100%
403234 | SR15 ES - E012 Cartside Rd Pumping Station EO at New Housing Dev Outside No 21 Newford Grove | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2012-12-20 | 2016-03-31 | 2016-03-31 | 2018-07-31 | 2018-10-31 | East Renfrewshire | 41666 | 332748 | 300030 | 1206760.65 | 386457.05 | 3096.31 | 0 | 2229092.01 | 0 | 2270758.01 | 297558.71 | [6 empty] | EC01F | 100% | [18 empty] | Regulatory Outputs OMG-18: 2
403235 | SR15 ES - E013 Cartside Rd Pumping Station at New Housing Dev Outside No 21 Newford Grove | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-12-20 | 2015-02-25 | 2015-02-25 | 2015-02-26 | 2015-02-26 | East Renfrewshire | 5437.62 | 1027.19 | -3700.97 | 0 | 0 | -0.7 | 0.7 | -2673.78 | 0 | 2763.84 | 0 | [6 empty] | EC10B | 100%
403237 | SR15 ES - E015 Fishescoates Avenue CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-07-24 | 2015-09-01 | 2016-12-31 | 2017-03-31 | South Lanarkshire | 77028.21 | 322971.79 | 35277 | 0 | -17784.96 | 0 | 0 | 340463.83 | 0 | 417492.04 | 528067.42 | [6 empty] | EC01F | 100% | [18 empty] | Regulatory Outputs OMG-18: 3
403238 | SR15 ES - E016 Field off North Park Avenue CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2012-12-21 | 2019-11-04 | 2020-03-02 | 2021-02-28 | 2021-05-31 | Renfrewshire | 71950 | -6946 | 16017.85 | 83978.15 | 138362 | 747533 | 580290 | 1559235 | 2250 | 1633435 | 396528.45 |  |  |  |  | 2970 |  | EC01F | 100% | bar: Regulatory Outputs OMG-18
403239 | SR15 ES - E017 Gateside SPS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-18 | 2015-08-03 | 2015-09-07 | 2016-01-28 | South Lanarkshire | 6249 | 29129 | 1609 | 769 | -940.03 | 0 | 0.03 | 30567 | 0 | 36816 | 41238.38 | [6 empty] | EC01F | 100%
403240 | SR15 ES - E018 Hugh Murray Grove | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-08-06 | 2015-11-09 | 2016-08-31 | 2017-03-31 | South Lanarkshire | 109784.3 | 1086326.7 | 268191 | -14511.82 | 1569.1 | 0 | 0.72 | 1341575.7 | 0 | 1451360 | 399121.3 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403241 | SR15 ES - E019 Junction Of Speirsbridge Road and Rouken Glen Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2016-02-24 | 2016-03-31 | 2016-09-30 | 2017-03-31 | East Renfrewshire | 145218.94 | 351196.06 | 543503 | 0 | -20315.03 | 0 | 0.03 | 874384.06 | 0 | 1019603 | 171646.02 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403242 | SR15 ES - E020 Just off Florence Drive in the grass area CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2012-12-20 | 2015-03-30 | 2015-03-30 | 2015-07-31 | 2015-11-30 | East Renfrewshire | 65947 | -823.51 | 142.35 | 0 | 0 | 0 | 0.65 | -680.51 | 0 | 65266.49 | 683130.6 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-18
403243 | SR15 ES - E021 Mains avenue rear off (Timbers) CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2013-02-11 | 2018-05-25 | 2018-07-06 | 2019-02-28 | 2019-03-31 | East Renfrewshire | 82052 | 37660 | 40158 | 170133 | 363640 | -10903.68 | 3987.68 | 604675 | 0 | 686727 | 261224.8 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403244 | SR15 ES - E022 21 Robslee Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2013-02-18 | 2018-06-27 | 2018-08-17 | 2020-04-01 | 2020-04-01 | East Renfrewshire | 36223 | 14990 | 23121 | 145959 | 2094062 | 1351943.06 | -43.06 | 3630032 | 2250 | 3668505 | 736772.65 |  |  |  |  | 12780 |  | CS11 | 49.19% | EC01F | 50.81% | [16 empty] | Regulatory Outputs OMG-18: 4
403245 | SR15 ES - E023 Rear of gardens at Moorburn Avenue No 41 CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-13 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 14875 | -1968.8 | 293.8 | 707 | -221 | -246.96 | -0.17 | -1436.13 | 0 | 13438.87 | 216640.81 | [6 empty] | EC01F | 100%
403246 | SR15 ES - E024 Rear of gardens at Moorburn Avenue No 51 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-13 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 14897 | -1610 | -87 | 909 | -840.84 | -6.73 | 6.73 | -1628.84 | 0 | 13268.16 | 216640.81 | [6 empty] | EC01F | 100%
403247 | SR15 ES - E025 On grass outside Our Lady of the Missions primary school off Wood Farm Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-18 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 5745 | -698.56 | 153.56 | 601 | 1247.15 | 0 | 0.86 | 1304.01 | 0 | 7049.01 | 216640.81 | [6 empty] | EC01F | 100%
403248 | SR15 ES - E026 10 Castlemilk Crescent Ashcroft | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-03-08 | 2015-07-30 | 2015-09-07 | 2016-02-29 | 2016-04-30 | Glasgow City | 51628.36 | 294074.64 | 7888.5 | 809.5 | -4047.09 | 0 | 0.09 | 298725.64 | 0 | 350354 | 165136.88 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403249 | SR15 ES - E027 Eaglesham Road Busby | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2013-02-18 | 2016-12-13 | 2017-01-23 | 2018-03-31 | 2018-03-31 | East Renfrewshire | 71777 | 14454 | 532981 | 268563.32 | -26961.61 | 8.29 | 0 | 789045 | 0 | 860822 | 633507.04 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403250 | SR15 ES - E028 East Side of Airdrie Road South of Police Station 30 Arch Way Kilsyth | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-18 | 2015-08-11 | 2015-10-26 | 2016-02-29 | 2016-04-30 | North Lanarkshire | 51161.17 | 186672.83 | -2155.91 | 658.22 | -1733.63 | 0 | 0.32 | 183441.83 | 0 | 234603 | 351587.81 | [6 empty] | EC01F | 3.036% | EC01B | 96.96% | bar: Regulatory Outputs OMG-18
403251 | SR15 ES - E029 Glenside Drive CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-11 | 2015-10-27 | 2016-01-25 | 2016-09-20 | 2017-03-31 | South Lanarkshire | 79127.31 | 425520.69 | 405314 | 5038 | -12783.97 | 0 | 0.97 | 823089.69 | 0 | 902217 | 528067.42 | [6 empty] | EC01F | 100%
403640 | SR15 ES - E031 - Busby Cartside Lower SPS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2013-12-06 | 2016-12-14 | 2016-12-14 | 2016-12-15 | 2017-01-13 | East Renfrewshire | 5656.83 | 2640.68 | -7465.53 | 0 | 0 | 0.3 | 191.5 | -4633.05 | 0 | 1023.78 | 297558.71 | [6 empty] | EC01F | 100%
403639 | SR15 ES - E032 - South of Birchview Drive CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2013-12-17 | 2018-02-26 | 2018-03-13 | 2018-06-26 | 2018-10-16 | East Renfrewshire | 420.54 | 160.98 | 149.88 | 18698.6 | 3488 | 0 | 0 | 22497.46 | 0 | 22918 | 297558.71 | [6 empty] | EC01F | 100%
403747 | SR15 ES - E033 DALDOWIE - Cluster 7 - COATBRIDGE 30M W-O WOODSIDE ST CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2014-03-17 | 2018-11-22 | 2019-01-18 | 2019-02-28 | 2019-03-31 | North Lanarkshire | 105900 | 77125 | 75913.11 | 54061.89 | 79000 | 1129.17 | 342 | 287571.17 | 122.85 | 393594.02 | 46023.48 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403746 | SR15 ES - E035 - Deaconsbank WwPS | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-03-17 | 2015-02-25 | 2015-03-09 | 2015-02-26 | 2020-02-11 | East Renfrewshire | 16150.62 | -0.01 | -427.05 | 0 | 0 | -0.35 | 427.4 | -0.01 | 0 | 16150.61 | 0 | [6 empty] | EC01B | 100%
403913 | SR15 ES - E036 Rutherglen Stonelaw Rd-Buchanan Dr CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2015-10-27 | 2017-06-30 | 2017-12-05 | 2019-01-31 | 2019-03-31 | South Lanarkshire | 2994.55 | 28764.45 | 48579 | 494189 | 722792.32 | 6680.68 | 0 | 1301005.45 | 0 | 1304000 | 373919.8 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
404031 | SR15 ES - E037 - In Field off Victoria Place behind No. 50 CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2018-05-10 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | East Renfrewshire | 1040 | 7210 | 84923.72 | 38009.23 | 20210.99 | 59.93 | -33.37 | 150380.5 | 0 | 151420.5 | 855170.77 | [6 empty] | EC01B | 100%
403922 | SR15 ES - E1052 - Dalkeith Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-08 | City of Edinburgh | 610 | 18500 | 39493.61 | 24896.39 | 37500 | -121000 | 0 | -610 | 0 | 0 | 204193.13 | [6 empty] | CS11 | 100%
404039 | SR15 ES - E1134 - Kirknewton Mains Farm | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2018-06-07 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | West Lothian | 976 | 8000 | 43718.92 | 43207.08 | 3256.49 | 0 | -0.02 | 98182.47 | 0 | 99158.47 | 587389.06 | [6 empty] | CS11 | 100%
404027 | SR15 ES - E1254 - Waterside Haddington | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-06-14 | 2019-06-14 | 2019-05-28 | 2019-05-28 | 2019-05-28 | East Lothian | 610 | 12000 | 44545.69 | 17844.31 | 20000 | -94034.88 | -964.12 | -609 | 0 | 1 | 588103.68 | [6 empty] | CS11 | 100%
403919 | SR15 ES - E1270 - Station Road Slamannan Falkirk | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-06-28 | 2016-12-16 | - | 0 | 37221 | -37221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11 | 100%
404083 | SR15 ES - E1404 - Old Mill Road Craigrothie Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-09-06 | 2016-10-14 | Fife | 0 | 37062 | -17890.07 | 0 | 0 | 0 | 0 | 19171.93 | 0 | 19171.93 | 66122.5 | [6 empty] | CS11 | 100%
404023 | SR15 ES - E1446 - Main Street Limekilns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-09-28 | 2020-09-28 | Fife | 244 | 36256 | 33122.89 | 31801.5 | 8575.61 | 33312.4 | 34013.17 | 177081.57 | 0 | 177325.57 | 204193.13 | [6 empty] | CS11 | 100%
404028 | SR15 ES - E1452 - Townhill Road Dunfirmline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2017-10-17 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Fife | 610 | 10000 | 28818.95 | -39428.95 | 0 | 0 | 1 | -609 | 0 | 1 | 33096.33 | [6 empty] | CS11 | 100%
403923 | SR15 ES - E1618 - Rose Street Annan (14 33 and 35) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2018-02-28 | 2020-02-28 | 2020-05-14 | 2021-09-23 | 2021-12-24 | Dumfries and Galloway | 1053 | 89584 | 19354.29 | 42161.29 | 249364.42 | 1058360 | 2551789.09 | 4010613.09 | 2242090.2 | 6253756.29 | 204193.13 |  |  |  |  | 5070 |  | CS11 | 100%
403924 | SR15 ES - E1619 - Hospital Road Annan | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-06-05 | 2018-06-05 | 2018-02-26 | 2018-06-05 | 2018-06-05 | Dumfries and Galloway | 702 | 35056 | 28244 | -63433.07 | 222.2 | -0.07 | -790.06 | -701 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
403133 | SR15 ES - Eaglesham Road Clarkston Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2012-11-30 | 2019-03-29 | 2019-06-07 | 2019-04-10 | 2019-04-10 | East Renfrewshire | 217087.56 | 144912.44 | 29853 | -10860.82 | 37007.82 | -196130.17 | -4283.29 | 498.98 | 0 | 217586.54 | 737559.72 | [6 empty] | CS11 | 100%
402948 | SR15 ES - Easdale Isle of Seil - provision of appropriate Ww Treatment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS1 | 2012-09-17 | 2020-08-24 | 2020-11-09 | 2022-01-12 | 2022-04-14 | Argyll and Bute-North Argyll | 76322 | 179928 | 378616 | 130911.78 | 805375.3 | 842109.16 | 44321.02 | 2381261.26 | 3787873.74 | 6245457 | 0 |  |  |  |  | 31500 |  | CM_WWI | 100%
402868 | SR15 ES - Estimating support | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-08-21 | 2012-08-21 | 2012-09-05 | 2016-06-28 | 2016-09-29 | Scottish Water Wide | 439421.78 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0.22 | 0 | 439422 | 0 | [6 empty] | QS4EQS | 50% | QS4EQW | 50%
403641 | SR15 ES - Fair Isle WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2014-01-13 | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2020-11-23 | Shetland Islands | 66493.66 | 807226.83 | 350121.99 | 32658.13 | 6091.48 | 2642.63 | -597.28 | 1198143.78 | 0 | 1264637.44 | 1374557.36 | [6 empty] | DW23 | 50% | DW25 | 50%
404019 | SR15 ES - Fettercairn WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2027-04-01 | 2028-01-19 | 2028-03-30 | 2028-10-11 | 2028-10-12 | Aberdeen City | 1830 | 25289.01 | 26223.67 | 728.63 | 0 | 831.23 | 0 | 53072.54 | 893304.54 | 948207.08 | 0 | [6 empty] | SG1 | 100%
403511 | SR15 ES - Flooding Model Maintenance Programme Batch 1 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2013-09-09 | 2014-05-30 | 2014-06-23 | 2018-11-26 | 2017-03-26 | Scottish Water Wide | 2081306 | 43366 | 333457 | 2500 | 193414.2 | 162.9 | -162.9 | 572737.2 | 0 | 2654043.2 | 558366.35 | [6 empty] | CS11 | 50% | CS15 | 50%
402747 | SR15 ES - Flow Gauging Strategy - Installation of Long Term Strategic Analogues | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-11-27 | 2013-08-20 | 2014-04-28 | 2018-12-12 | 2017-09-15 | Scottish Water Wide | 96082 | 35531 | 38287 | 39700 | 50551.9 | 0 | 0.04 | 164069.94 | 0 | 260151.94 | 0 | [6 empty] | WG4 | 100%
403714 | SR15 ES - Furnace WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-04-08 | 2014-09-30 | 2014-11-03 | 2015-02-28 | 2015-06-30 | Argyll and Bute-Cowal & Bute | 123559.37 | -11670.37 | 0 | 0 | 0 | 0 | 0.43 | -11669.94 | 0 | 111889.43 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
404006 | SR15 ES - Geospatial SR15 Viewer | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-11-27 | 2015-07-22 | 2015-07-22 | 2015-07-22 |  | Scottish Water Wide | 365.85 | 949.71 | 0 | 0 | 0 | 0 | 0 | 949.71 | 0 | 1315.56 | 0 | [6 empty] | DW5 | 100%
403304 | SR15 ES - Glasgow Strategic Study PEF Production | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-01-11 | 2013-07-08 | 2013-07-15 | 2016-09-27 |  | Scottish Water Wide | 69898 | 0 | 0 | 0 | -733.84 | 0 | 733.84 | 0 | 0 | 69898 | 0 | [6 empty] | QS4EQS | 100%
403715 | SR15 ES - Glendyes WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2014-11-21 | 2014-12-08 | 2015-03-31 | 2015-06-30 | Aberdeenshire | 77085.5 | -22774.08 | 0 | 0 | 0 | 0 | 0.97 | -22773.11 | 0 | 54312.39 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403987 | SR15 ES - Gowanbank WPS CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2027-11-10 | 2028-02-08 | 2028-12-11 | 2029-03-26 | Falkirk | 1037 | 115199 | 126148.87 | -43517.72 | 8889.91 | 15545.53 | 0 | 222265.59 | 1436270.37 | 1659572.96 | 0 | [6 empty] | CM_WSNI | 100%
403134 | SR15 ES - Greenlaw Road Newton Mearns Internal and External Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2012-12-10 | 2021-04-09 | 2021-05-07 | 2021-10-20 | 2021-10-20 | East Renfrewshire | 157504.8 | 89711.2 | 31098 | 39104.51 | 34581.49 | 13235.28 | 23163.27 | 230893.75 | 17817.87 | 406216.42 | 1797150 | [6 empty] | CS11 | 100%
404093 | SR15 ES - Greenock WTW - SCADA Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2015-07-06 | 2020-04-27 | 2020-07-20 | 2022-09-26 | 2023-02-22 | Inverclyde | 0 | 49622 | 35985.38 | 127284.67 | 57923.55 | 297159.7 | 1498224.08 | 2066199.38 | 2142011.62 | 4208211 | 0 | [6 empty] | CM_WSNI | 100%
404022 | SR15 ES - Hay Street Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-02-11 | 2021-12-27 | 2022-03-23 | 2022-10-31 | 2023-01-16 | Perth and Kinross | 610 | 9000 | 1699 | 3691 | 10000 | 38021.55 | 15367.36 | 77778.91 | 221611.06 | 299999.97 | 204193.13 | [6 empty] | CS11 | 100%
403334 | SR15 ES - Hillhead Drive | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2013-03-08 | 2020-08-04 | 2020-08-21 | 2020-08-21 | 2020-08-21 | North Lanarkshire | 103900 | 369283 | -155711.77 | 44484.23 | 57044.54 | 20380 | 5620 | 341100 | 0 | 445000 | 193147.85 |  |  |  |  | 800 |  | CS11A | 100%
403978 | SR15 ES - Innellan Ashburne Lodge UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-06-30 | 2018-08-31 | Argyll and Bute-Cowal & Bute | 294.85 | 75490.15 | 132349.34 | 623547.66 | 15230 | 10930.1 | 0 | 857547.25 | 0 | 857842.1 | 387175.01 | [6 empty] | EC01A | 100% | [18 empty] | Regulatory Outputs OMG-17: 2
403977 | SR15 ES - Innellan Dunadd UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-06-21 | 2018-06-21 | All West Unitary Authorities | 4055.75 | 5727.25 | 1217 | 0 | -3508.16 | 0 | 0.01 | 3436.1 | 0 | 7491.85 | 387175.01 | [6 empty] | EC01A | 100%
404077 | SR15 ES - Invercannie & Mannofield WOA Mannofield WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-07-06 | 2016-07-06 | 2016-07-06 | 2016-07-06 | Aberdeen City | 10.63 | 0 | 955.43 | 0 | 0 | 0 | -0.06 | 955.37 | 0 | 966 | 0 | [6 empty] | CM_WSI | 100%
404076 | SR15 ES - Invercannie & Mannofield WOA Pitfodels WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-23 | 2016-03-02 | 2016-03-02 | 2016-02-25 | 2016-03-02 | Aberdeen City | 173.85 | 5707.27 | 955.44 | 0 | 0 | 0 | 0.44 | 6663.15 | 0 | 6837 | 0 | [6 empty] | CM_WSI | 100%
404078 | SR15 ES - Invercannie & Mannofield WOA Rosehill Aberdeen WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-02 | Aberdeen City | 129.07 | 3621.82 | 955.45 | 0 | 0 | 0 | -0.34 | 4576.93 | 0 | 4706 | 0 | [6 empty] | CM_WSI | 100%
404079 | SR15 ES - Invercannie WOA Megray WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-02 | Aberdeenshire | 54.27 | 4018.52 | 1715.52 | -45.97 | 0 | 0 | -0.34 | 5687.73 | 0 | 5742 | 0 | [6 empty] | CM_WSI | 100%
403965 | SR15 ES - Katrine Aqueducts | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-02 | 2018-08-15 | 2018-10-08 | 2021-03-04 | 2021-03-04 | Stirling | 4148 | 122014 | 325241.13 | 161719.87 | 2853686.95 | 8400203.57 | 3560705.69 | 15423571.21 | 700116 | 16127835.21 | 0 | [6 empty] | CM_WSI | 100%
403754 | SR15 ES - Killin WTW manganse Issues and Capital maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2014-04-04 | 2015-03-24 | 2016-03-29 | 2017-03-31 | 2018-03-31 | Stirling | 44420.33 | 135629.67 | 186254.23 | 323509.7 | 65756.64 | 1011.31 | 1104.74 | 713266.29 | 0 | 757686.62 | 487318.6 | [6 empty] | DW3C | 3.33% | CM_WSNI | 96.67% | bar: Regulatory Outputs OMG-01
403971 | SR15 ES - Kilmun Lagganbhuie UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2019-05-31 | 2019-08-31 | Argyll and Bute-Cowal & Bute | 8825.01 | 26162.08 | 285814.91 | 254671 | -49000 | -40480 | 0 | 477167.99 | 0 | 485993 | 433363.43 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403335 | SR15 ES - Kirkview Crescent | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-03-08 | 2019-04-30 | 2019-06-19 | 2019-05-03 | 2019-06-19 | East Renfrewshire | 135662 | 201461 | 2251 | 3626 | 34498.95 | -241139.57 | 1.13 | 698.51 | 0 | 136360.51 | 176952.24 | [6 empty] | CS11 | 100%
403532 | SR15 ES - Kyle of Lochalsh WTW - Water Resource Strategic Study | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS3 | 2013-08-27 | 2016-10-31 | 2017-03-27 | 2020-10-31 | 2021-01-31 | Highland | 298171 | 119457 | 131619.98 | 689711.18 | 54630.26 | 81855.86 | 202193.88 | 1279468.16 | 9354.52 | 1586993.68 | 1007001.41 |  |  |  |  | 15000 |  | WG4A | 10% | WG4 | 90% | bar: Regulatory Outputs OMG-08
404007 | SR15 ES - Laighpark Paisley WWTW NS485655 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-03-26 | 2019-03-13 | 2019-03-15 | 2021-06-10 | 2021-09-03 | Renfrewshire | 2446.9 | 80574.1 | 145801.3 | -476.98 | 450339.82 | 2009023.85 | 1465353 | 4150615.09 | 671282.47 | 4824344.46 | 0 | [6 empty] | CM_WWNI | 100%
403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-02-27 | 2019-03-28 | Scottish Water Wide | 142211.46 | 645864.54 | 272100.84 | 371172.33 | 273425.5 | 163994.22 | -0.35 | 1726557.08 | 0 | 1868768.54 | 0 | [6 empty] | EC06 | 100%
404092 | SR15 ES - Lindean SEP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-05-08 | 2016-12-21 | 2017-01-24 | 2017-10-25 | 2017-10-25 | Scottish Water Wide | 0 | 65609 | 91570 | 214265 | 6868.91 | 2359.31 | 0 | 380672.22 | 0 | 380672.22 | 0 | [6 empty] | CM_WWNI | 100%
404054 | SR15 ES - Lintrathen WOA Lintrathen TM WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-01-05 | 2016-09-23 | 2016-10-17 | 2017-08-10 | 2017-09-12 | Perth and Kinross | 26905 | 117253 | 736079 | 379687 | 148192.43 | 95104.91 | 0 | 1476316.34 | 0 | 1503221.34 | 0 | [6 empty] | CM_WSI | 100%
403452 | SR15 ES - Lismore Oban - provision of septic tank and extended outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-05-08 | 2015-03-10 | 2015-06-22 | 2015-12-31 | 2016-02-29 | Argyll and Bute-North Argyll | 45212.23 | 122343.32 | 6983.74 | -3939.25 | 0 | 0 | 0 | 125387.81 | 0 | 170600.04 | 144686.4 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
404044 | SR15 ES - Loch Calder WOA Brabster WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2014-12-19 | 2021-07-19 | 2021-08-23 | 2021-12-10 | 2018-06-28 | Highland | 4644 | 74372 | -35878 | 44477 | 14924.43 | 7725.48 | -2725.48 | 102895.43 | 834195.57 | 941735 | 0 | [6 empty] | CM_WSI | 100%
404045 | SR15 ES - Loch Calder WOA Toftcarl WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-01-05 | 2027-05-04 | 2027-06-02 | 2028-04-07 | 2028-05-10 | Highland | 1760.27 | 37997.73 | 15157 | 12962.46 | 38605.54 | -38605.54 | 38605.54 | 104722.73 | 641667.01 | 748150.01 | 0 | [6 empty] | CM_WSI | 100%
403127 | SR15 ES - Loch Ness Regional WTW Scheme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2013-03-04 | 2018-02-28 | 2018-03-27 | 2021-01-31 | 2022-07-31 | Highland | 339720.5 | 331010.5 | 332847.72 | 1797860.93 | 8866701.47 | 9539077.87 | 3582973.39 | 24450471.88 | 1104345.22 | 25894537.6 | 4843787.87 | [6 empty] | DW25P | 8.232% | DW3G | 8.232% | CM_WSI | 9.655% | DW2 | 73.88% | [12 empty] | Regulatory Outputs OMG-01: 2
403996 | SR15 ES - Lochaline WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2016-04-25 | 2018-11-30 | 2019-01-07 | 2019-11-27 | 2020-03-02 | Highland | 3416 | 61388.08 | 61046.45 | 299936.29 | 777663.69 | 440494.63 | -240.11 | 1640289.03 | 14579.68 | 1658284.71 | 1855121.96 | [6 empty] | DW23 | 100%
403774 | SR15 ES - Lochearnhead WTW manganese Issues and Capital maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS7 | 2015-05-08 | 2016-03-31 | 2016-08-02 | 2017-06-30 | 2018-03-31 | Stirling | 700 | 98793 | 206717.76 | 153149.62 | -17264.03 | -16690.85 | 14952.5 | 439658 | 0 | 440358 | 536209.65 | [6 empty] | DW3C | 5.723% | CM_WSNI | 94.28% | bar: Regulatory Outputs OMG-01
403995 | SR15 ES - Londornoch WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS1 | 2016-04-01 | 2020-09-14 | 2021-01-27 | 2022-09-30 | 2022-10-31 | Highland | 0 | 644.54 | 3773.58 | 67044.82 | -17463.93 | 81603.43 | 875372.1 | 1010974.54 | 991689.48 | 2002664.02 | 2386562.75 | [6 empty] | DW25 | 100% | bar: Regulatory Outputs OMG-04
403604 | SR15 ES - Londornoch WTW Lagoons - Legacy Sludge LA01 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2015-03-10 | 2015-03-23 | 2015-10-31 | 2016-03-31 | Highland | 97229.41 | 103702.59 | -11534.14 | 0 | 0 | 0 | 2603.09 | 94771.54 | 0 | 192000.95 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2022-10-21 | 2022-11-25 | Glasgow City | 1820434 | 1130117.6 | 2092680.58 | 6926138.82 | -2905717 | 3567273.69 | 7788853.29 | 18599346.98 | 10850252.02 | 31270033 | 12880893.85 |  |  |  |  | 712964 |  | EC10B | 6.4% | EC10A | 93.6%
404026 | SR15 ES - Main Street Newtonmore | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2015-10-12 | 2020-10-19 | 2021-01-11 | 2021-10-04 | 2021-10-04 | Highland | 244 | 41126 | 187359 | 166004 | 56695.68 | 72883.32 | 350698.35 | 874766.35 | 920542.65 | 1795553 | 0 | [6 empty] | CS11A | 100%
404048 | SR15 ES - Milngavie WOA C4 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-01-05 | 2016-12-19 | 2017-01-30 | 2019-08-20 | 2018-08-24 | Glasgow City | 12059 | 162196 | 293871 | 1842709 | -51126.53 | 1697.64 | -140.64 | 2249206.47 | 0 | 2261265.47 | 0 | [6 empty] | CM_WSI | 100%
404049 | SR15 ES - Milngavie WOA M1 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-01-05 | 2023-08-08 | 2023-11-01 | 2025-02-04 | 2019-08-27 | Glasgow City | 6780 | 260236 | -114904 | 169966 | -52858.42 | 31884.7 | 103945.27 | 398269.55 | 693704.48 | 1098754.03 | 0 | [6 empty] | CM_WSI | 100%
404050 | SR15 ES - Milngavie WOA M3 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS1 | 2015-01-05 | 2021-04-12 | 2021-05-31 | 2022-06-16 | 2019-01-28 | Glasgow City | 6112 | 123117 | 66329 | 25847 | -78507.25 | 12804.52 | -12804.52 | 136785.75 | 1484739.29 | 1627637.04 | 0 | [6 empty] | CM_WSI | 100%
403694 | SR15 ES - Mingulay Crescent - Scaraway Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2014-03-31 | 2016-08-02 | 2016-08-31 | 2017-10-31 | 2017-10-31 | Glasgow City | 84629 | 166871 | 2343175 | 121304 | -5652 | 7673 | 0 | 2633371 | 0 | 2718000 | 3226654.89 | [6 empty] | CS11 | 42.22% | CS15 | 57.78%
403693 | SR15 ES - Moraine Avenue (Lower) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2014-04-28 | 2016-07-22 | 2016-09-05 | 2017-05-29 | 2017-05-29 | Glasgow City | 35139 | 320861 | 1286538 | -49219.82 | 1788.82 | 1987.87 | 648.13 | 1562604 | 0 | 1597743 | 1064623.02 | [6 empty] | CS11 | 100%
403692 | SR15 ES - Moraine Avenue (Upper) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2014-04-28 | 2019-03-20 | 2019-03-28 | 2019-01-28 | 2019-03-28 | Glasgow City | 91368 | 265132 | -70491 | 111991 | -4073.92 | 1028.5 | -1028.53 | 302558.05 | 0 | 393926.05 | 1709599.7 | [6 empty] | CS11 | 100%
403579 | SR15 ES - National Substance Strategy for Scotland - Priority Substances Directive | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2013-10-08 | 2013-12-13 | 2013-12-13 | 2016-09-29 | 2016-10-26 | Scottish Water Wide | 19064.8 | 2435.2 | -260.2 | 0 | 0 | 0 | 0 | 2175 | 0 | 21239.8 | 0 | [6 empty] | EC10A | 100%
404024 | SR15 ES - NE451 - Howard Place Dysart Kirkcaldy | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2018-04-11 | 2019-02-07 | 2019-02-25 | 2019-06-21 | 2019-06-21 | Fife | 366 | 1500 | 14986.31 | 17129.73 | 68494.96 | 233920 | 0 | 336031 | 603 | 337000 | 204193.13 | [6 empty] | CS11 | 100%
404038 | SR15 ES - NE53 - Queens Road Turriff | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-05-25 | 2017-05-25 | Aberdeenshire | 488 | 26000 | 4922.11 | 2654.09 | 0 | 0.11 | -0.11 | 33576.2 | 0 | 34064.2 | 62492.89 | [6 empty] | CS11 | 100%
403926 | SR15 ES - NE539 - Eilidh Fowlis Road Liff Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-07-18 | 2019-07-18 | Angus | 893 | 3700 | 36413.94 | 43993.06 | 56000 | -138859.14 | -2139.86 | -892 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
403925 | SR15 ES - NE59 - 4 Sutherland Crescent Buckie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-11-11 | 2017-10-25 | 2018-01-29 | 2019-01-15 | 2019-01-15 | Moray | 610 | 34190.61 | 73980.39 | 289156.02 | 253056.98 | 26866.58 | -2186.58 | 675064 | 0 | 675674 | 204193.13 | [6 empty] | CS11 | 100%
403336 | SR15 ES - Nelson Street - South Scott Street Baillieston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2013-03-11 | 2016-03-02 | 2017-01-23 | 2018-03-21 | 2018-03-21 | Glasgow City | 139543.94 | 520803.06 | 1101543 | 2342888.98 | 9595.03 | 204.99 | 0 | 3975035.06 | 0 | 4114579 | 1549518.41 | [6 empty] | CS11 | 100%
403990 | SR15 ES - Ness WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28 | Na H-Eileanan an Iar | 0 | 0 | 396 | 211.29 | 311.19 | 0 | -311.19 | 607.29 | 0 | 607.29 | 1020606.26 | [6 empty] | DW25 | 100%
403944 | SR15 ES - Network Modelling (Creation of new all-mains models & strategic models) | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWMD | Interruptions to Supply | MS3 | 2014-10-13 | 2015-10-16 | 2015-10-19 | 2021-07-28 | 2021-07-28 | Scottish Water Wide | 106206 | 710125 | 879993.95 | 559554.98 | 639866.14 | 243417.54 | 272558 | 3305515.61 | 115867.39 | 3527589 | 1887455.39 | [6 empty] | CM_WSI | 12.32% | CS12 | 43.84% | CS16W | 43.84%
403991 | SR15 ES - Newmore WTW - WQ & Essential Related CM Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-04-01 | 2018-08-29 | 2018-09-28 | 2021-07-31 | 2021-11-30 | Highland | 0 | 3639.03 | 309249.46 | 459203.43 | 852209.52 | 3468448.56 | 1898520.02 | 6991270.02 | 1114905.98 | 8106176 | 1741832.73 |  |  |  |  | 245040 |  | DW25P | 35% | CM_WSNI | 65% | bar: Regulatory Outputs OMG-04
403992 | SR15 ES - North Lochs WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-04-01 | 2018-02-28 | 2018-03-28 | 2020-04-08 | 2020-09-30 | Na H-Eileanan an Iar | 0 | 1219.51 | 42732.58 | 220633.8 | 1117098.61 | 192093.5 | 5902.7 | 1579680.7 | 9251.3 | 1588932 | 427866.62 |  |  |  |  | 14200 |  | DW25 | 100% | bar: Regulatory Outputs OMG-04
403691 | SR15 ES - Number 6 Viewpark Drive | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2014-04-25 | 2017-06-30 | 2017-09-18 | 2018-12-11 | 2018-12-11 | South Lanarkshire | 44470 | 260905 | 104023 | 259728.68 | 43226.32 | -2353 | 0 | 665530 | 0 | 710000 | 145594.05 | [6 empty] | CS11 | 100%
404020 | SR15 ES - NW95 - Princes Street Thurso | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2017-11-27 | 2020-04-01 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Highland | 1220 | 193590 | 846 | 54601.4 | 11459.94 | -261399.66 | -316.68 | -1219 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
403630 | SR15 ES - Old Calder WTW Legacy Sludge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-02-11 | 2015-03-02 | 2015-03-30 | 2015-05-31 | 2015-05-31 | Highland | 39547.38 | 200730.54 | 0 | 30.88 | 0 | 0 | -0.42 | 200761 | 0 | 240308.38 | 0 | [6 empty] | CM_WWNI | 100% | bar: Regulatory Outputs OMG-24
403135 | SR15 ES - Old Street Clydebank Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2012-12-10 | 2015-08-06 | 2015-09-21 | 2016-07-29 | 2016-07-29 | Glasgow City | 137215.96 | 1604972.04 | 64671 | 17907 | -35788.99 | 0 | 0 | 1651761.05 | 0 | 1788977.01 | 1691921.82 | [6 empty] | CS11 | 100%
403337 | SR15 ES - Orbiston Street | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-03-08 | 2019-04-30 | 2019-05-23 | 2019-02-25 | 2019-05-23 | North Lanarkshire | 95524.22 | 173523.78 | 35996.04 | 32947.13 | 9134.11 | 1932.23 | 0.98 | 253534.27 | 0 | 349058.49 | 470562.95 | [6 empty] | CS11 | 100%
403631 | SR15 ES - Papa Stour WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2016-09-28 | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2020-11-23 | Shetland Islands | 34087.82 | 8713.18 | 25968.59 | -17959.89 | 489.67 | 1773.63 | -1730.57 | 17254.61 | 0 | 51342.43 | 400486.38 | [6 empty] | DW25 | 10% | DW23 | 40% | DW2 | 50%
403958 | SR15 ES - Proactive Meter Maintenance (2015-17) | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | Water |  | SWD | Meter Accuracy | MS7 | 2016-12-21 | 2017-01-18 | 2017-01-18 | 2016-10-26 |  | Scottish Water Wide | 185621.8 | 196563.7 | -172732.48 | 0 | 0 | 0 | 0 | 23831.22 | 0 | 209453.02 | 4004712.5 | [6 empty] | CS4 | 100%
403587 | SR15 ES - Programme Development - SWS2 Resource Support Costs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWMD | Wastewater non infrastructure | MS7 | 2013-09-17 | 2014-07-10 | 2016-08-23 | 2016-08-23 | 2016-08-23 | Scottish Water Wide | 952475.44 | -256552.7 | 40048.41 | 0 | 0 | 0 | 0 | -216504.29 | 0 | 735971.15 | 0 | [6 empty] | CM_WSNI | 25% | CM_WWNI | 25% | WG1 | 25% | WQ01 | 25%
404075 | SR15 ES - PSC Treated Water Storage Tanks Inspections Scotland Wide Program | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-01-26 | 2015-05-21 | 2015-06-15 | 2017-03-24 | 2016-12-16 | Scottish Water Wide | 23000 | 1243563 | 614632.42 | 32049.7 | 0 | 0 | -0.12 | 1890245 | 0 | 1913245 | 0 | [6 empty] | CM_WSNI | 46.88% | CM_WWI | 53.12%
404002 | SR15 ES - PSCD Blairlinnans to Old Kilpatrick Trunk Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | GW2 | 2020-04-27 | 2020-08-17 | 2020-10-13 | 2021-12-03 | 2022-01-31 | West Dunbartonshire | 41.1 | 164111.9 | -63335 | 110610 | -6379 | 2469.35 | 0 | 207477.25 | 0 | 207518.35 | 0 | [6 empty] | SR15_EXC_EXC | 100%
404003 | SR15 ES - PSCD Bradan Trunk Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS3 | 2016-01-29 | 2016-09-29 | 2016-09-29 | 2020-10-16 | 2018-05-14 | North Ayrshire | 1470.59 | 3427861.41 | 12866245 | 4900423 | 2360218.97 | 130328.5 | 0 | 23685076.88 | 0 | 23686547.47 | 0 | [6 empty] | SR15_EXC_EXC | 100%
404004 | SR15 ES - PSCD Glenhove to Gowanbank Rising Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS7 | 2015-08-19 | 2015-10-16 | 2015-10-19 | 2017-03-31 | 2017-03-31 | North Lanarkshire | 1952 | 512225 | 201288 | 19931 | -23948 | -2294.1 | 81.9 | 707283.8 | 0 | 709235.8 | 0 | [6 empty] | SR15_EXC_EXC | 100%
403982 | SR15 ES - Rhu Armadale Road UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2017-02-21 | 2018-03-27 | 2018-08-30 | 2018-08-30 | Argyll and Bute-Cowal & Bute | 3938 | 3000 | 0 | 1129.6 | 2875.4 | 2671.59 | 1.41 | 9678 | 0 | 13616 | -1016925.7 | [6 empty] | EC01A | 100%
403981 | SR15 ES - Rhu Artarman Road UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2017-02-11 | 2018-03-27 | 2018-08-30 | 2018-08-30 | Argyll and Bute-Cowal & Bute | 3938 | 31229 | 301811 | 179004.71 | 350017.29 | 0 | 0 | 862062 | 0 | 866000 | -1016925.7 | [6 empty] | EC01A | 100%
403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-05-18 | 2018-11-01 | Argyll and Bute-Cowal & Bute | 3930 | 61549 | 143268.49 | 884537.19 | -48104.68 | 0 | 0 | 1041250 | 0 | 1045180 | -1016925.7 | [6 empty] | EC01A | 100%
403700 | SR15 ES - Roberton WTW - Manganese Polution Control & Automatic Coagulant Dosing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2014-02-17 | 2016-03-23 | 2016-03-28 | 2017-03-31 | 2021-09-30 | Scottish Borders | 76358.91 | 355686.09 | 701969.63 | 31569.95 | 7028.16 | 2975.88 | 9622.81 | 1108852.52 | 3104.31 | 1188315.74 | 542629.68 | [6 empty] | DW25P | 21.36% | DW3C | 78.64% | bar: Regulatory Outputs OMG-01
403595 | SR15 ES - Robslee Drive - Burnfield Cottages | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2014-01-29 | 2018-06-29 | 2018-06-29 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 114677 | 72063 | 63795 | 134382.34 | 76828.86 | 8026.54 | -861.74 | 354234 | 0 | 468911 | 520131.84 | [6 empty] | CS11 | 100%
401806 | SR15 ES - S168 UID East of 1 Espedair Street Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS5 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-31 | 2019-12-10 | Renfrewshire | 16089 | -1532 | 7699.37 | -5116.37 | 800 | 764.77 | 0 | 2615.77 | 0 | 18704.77 | 1420376.56 | [6 empty] | EC04B | 100% | [18 empty] | Regulatory Outputs OMG-18: 7
401808 | SR15 ES - S170 UID Storm Water Overflow Rear of 27 Barterholm Road Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 6898 | 0 | 642 | 83 | 4275 | 1752.7 | 0 | 6752.7 | 0 | 13650.7 | 1420376.56 | [6 empty] | EC04B | 100%
401809 | SR15 ES - S171 UID Ardgowan Street South No1 CSO South end of Ardgowan Street Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-31 | 2020-03-31 | Renfrewshire | 14625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14625 | 0 | [6 empty] | EC04B | 100% | [18 empty] | Regulatory Outputs OMG-18: 2
401811 | SR15 ES - S173 UID Charleston No1 CSO Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 13025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13025 | 0 | [6 empty] | EC04B | 100%
401812 | SR15 ES - S174 UID Charleston No2 CSO Paisley Rowan St behind St Charles Primary School | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 10864 | -1579 | 150 | 158 | 550 | 0 | 0 | -721 | 0 | 10143 | 1420376.56 | [6 empty] | EC04B | 100%
401813 | SR15 ES - S175 UID 113 Neilston Road at end of Kilncroft Lane Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 10138 | -5053 | 56.08 | 1643.92 | 1569 | 0 | 0 | -1784 | 0 | 8354 | 1420376.56 | [6 empty] | EC04B | 100%
401814 | SR15 ES - S176 UID 129 Neilston Road Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 852148.01 | 858162.99 | 1062885 | 7722678 | 3931849 | 276622.47 | -15349.29 | 13836848.17 | 11.85 | 14689008.03 | 1420376.56 |  |  |  |  | 780.54 |  | EC04B | 100%
401815 | SR15 ES - S177 UID Charleston No3 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 4825 | 0 | 2000 | 1017 | 4305 | 3000 | 0 | 10322 | 0 | 15147 | 1420376.56 | [6 empty] | EC04B | 100%
401816 | SR15 ES - S178 UID Rowan Street No2 Police Station Rowan Street Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 6711 | -711 | 712 | 488 | 2709 | 0 | 0 | 3198 | 0 | 9909 | 1420376.56 | [6 empty] | EC04B | 100%
403716 | SR15 ES - Sanday Sludge Storage Area and Drying Beds | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS0 | 2014-04-08 | 2021-10-25 | 2021-12-13 | 2022-03-31 | 2022-07-31 | Orkney Islands | 26305.36 | 45419.64 | 3003.16 | 29924.84 | 18591.54 | 25775.43 | 3695.99 | 126410.6 | 312284.12 | 465000.08 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
404086 | SR15 ES - Sandy Loch WOA Sandwick WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-01-26 | 2016-09-20 | 2017-08-09 | 2018-05-23 | 2017-09-07 | Shetland Islands | 3486 | 33255 | 50419 | 195036.71 | 77459.79 | -1938.65 | 37297.77 | 391529.62 | 0 | 395015.62 | 0 | [6 empty] | CM_WSI | 100%
404085 | SR15 ES - Sandy Loch WOA South Burra WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-08-31 | 2016-11-21 | 2017-08-31 | 2017-06-09 | Shetland Islands | 650 | 25426 | 291414 | 175367 | -35684.52 | -1214.08 | 0 | 455308.4 | 0 | 455958.4 | 0 | [6 empty] | CM_WSI | 100%
403629 | SR15 ES - Savalbeg (Lairg) WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-02-11 | 2015-03-12 | 2015-03-23 | 2015-10-31 | 2016-03-31 | Highland | 119710.12 | 88280.88 | -2316.97 | 0 | 0 | 0 | 0 | 85963.91 | 0 | 205674.03 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403917 | SR15 ES - Savalbeg WTW - WQ & Essential CM Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-03-29 | 2018-03-29 | 2018-03-29 | 2020-04-30 | 2021-07-30 | Highland | 0 | 39934.41 | 171557.33 | 688634.15 | 2636722.35 | 3548049.77 | -359860.04 | 6725037.97 | 13896.12 | 6738934.09 | 2744156.38 |  |  |  |  | 77246.99 |  | DW25 | 13% | DW2 | 87% | bar: Regulatory Outputs OMG-01
404040 | SR15 ES - SE 390 - Main Street Newtongrange | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | Midlothian | 2440 | 6500 | 39544.07 | 22515.93 | 79556.77 | 59443.23 | 0 | 207560 | 0 | 210000 | 158866.79 | [6 empty] | CS15 | 100%
404029 | SR15 ES - SE 663 - Marine Drive Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2017-02-08 | 2017-11-08 | 2017-11-08 | 2017-05-23 | 2017-11-08 | City of Edinburgh | 976 | 17768 | 43112.66 | -61803.62 | 0 | 0 | 0 | -922.96 | 0 | 53.04 | 79433.4 | [6 empty] | CS11 | 100%
404025 | SR15 ES - SE 730 - Harburn Road West Calder | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | West Lothian | 244 | 37000 | 6293 | 31544.32 | -75080.32 | 0.29 | -0.29 | -243 | 0 | 1 | 204193.13 | [6 empty] | CS11A | 100%
402746 | SR15 ES - Security of Supply - Flow Gauging | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-08-08 | 2013-02-06 | 2013-02-07 | 2017-08-08 | 2017-09-15 | Scottish Water Wide | 121680 | 40837.8 | 42982.2 | 7807.53 | 0 | 0 | 0 | 91627.53 | 0 | 213307.53 | 0 | [6 empty] | WG4 | 100%
403993 | SR15 ES - South Uist WTW - SR15 WQ Improvements | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-02 | 2020-04-13 | 2020-01-07 | 2020-01-07 | 2020-04-13 | Na H-Eileanan an Iar | 101.77 | 8398.78 | -8500.55 | 8399.93 | 9.35 | 11558.51 | -628.87 | 19237.15 | 0 | 19338.92 | 3206476.5 | [6 empty] | WG4 | 8.13% | DW25 | 10% | DW3B | 10% | DW3C | 71.87%
404053 | SR15 ES - Staffin WTW - CWT Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-11-22 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | Highland | 0 | 0 | 356.51 | 8.84 | 0 | 0 | -8.84 | 356.51 | 0 | 356.51 | 0 | [6 empty] | CM_WSNI | 100%
402924 | SR15 ES - Stage 4 DOMS investigations in 31 zones | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2012-12-10 | 2013-10-24 | 2013-11-29 | 2017-03-27 | 2017-03-27 | Scottish Water Wide | 1907722 | 330992 | 142938.72 | 148437.28 | 0 | -10984.25 | 0 | 611383.75 | 0 | 2519105.75 | 215809.58 | [6 empty] | DW5A | 100%
403125 | SR15 ES - Stoer WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2013-01-14 | 2016-03-31 | 2016-07-18 | 2017-12-31 | 2019-03-31 | Highland | 164265.76 | 122286.34 | 2636754.28 | 1068327.48 | 63204.78 | 7098.41 | 0 | 3897671.29 | 0 | 4061937.05 | 2374619.47 | [6 empty] | DW23 | 50% | DW25P | 50% | bar: Regulatory Outputs OMG-01
403013 | SR15 ES - Strathpeffer Fish pass | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-11-19 | 2012-11-19 | 2013-11-19 | 2013-12-13 | 2016-01-27 | Highland | 25239.04 | 1760.96 | -1487.51 | 0 | 0 | 0 | 0 | 273.45 | 0 | 25512.49 | 0 | [6 empty] | CM_WWNI | 100%
403753 | SR15 ES - Strathyre WTW manganse Issues and Capital maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS6 | 2014-04-04 | 2015-03-24 | 2016-03-31 | 2018-01-31 | 2018-10-31 | Stirling | 40033.25 | 95509.75 | 105723.06 | 376392.96 | 56183.55 | 1214.04 | 711.71 | 635735.07 | 0 | 675768.32 | 521662.35 | [6 empty] | DW25P | 3.4% | CM_WSNI | 96.6% | bar: Regulatory Outputs OMG-04
403980 | SR15 ES - Strone Dunselma Lodge WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-17 | 2016-03-23 | 2016-03-29 | 2019-02-28 | 2019-03-31 | Argyll and Bute-Cowal & Bute | 4700.32 | 83170.68 | 84606.08 | 684974.37 | 5854.55 | 38055 | 1059.98 | 897720.66 | 0 | 902420.98 | 448120.02 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403702 | SR15 ES - Summerhill Road - Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2014-04-28 | 2015-06-25 | 2015-08-03 | 2016-03-11 | 2016-03-11 | Glasgow City | 42977 | 1103672 | 69893 | 410 | -13697.38 | 0 | 0.38 | 1160278 | 0 | 1203255 | 204193.13 | [6 empty] | CS11A | 100%
403930 | SR15 ES - SW1377 - 697 & 699 Clarkston Road | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-08-23 | 2020-01-29 | 2020-01-06 | 2020-07-27 | 2020-10-19 | Glasgow City | 732 | 28888 | 14112 | 55474.83 | 95681.17 | 323843.88 | 198524.82 | 716524.7 | 0 | 717256.7 | 204193.13 |  |  |  |  | 1080 |  | CS11 | 100%
404080 | SR15 ES - SW161 - Riverside Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS6 | 2015-05-11 | 2015-11-19 | 2016-03-22 | 2019-01-28 | 2019-01-28 | Glasgow City | 0 | 3000 | 10260.76 | 0 | 75688.41 | 0 | 0 | 88949.17 | 0 | 88949.17 | 204193.13 | [6 empty] | CS11 | 100%
403920 | SR15 ES - SW670 - Newfield Road Stonehouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-27 | 2018-02-23 | 2018-02-19 | 2018-02-19 | 2018-02-19 | South Lanarkshire | 488 | 32012 | 34512 | -67012 | 0 | 0.49 | 0.51 | -487 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
403929 | SR15 ES - SW854 - 66 & 68 Burns Wynd Stonehouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-10-13 | 2018-03-20 | 2018-04-03 | 2018-08-21 | 2018-08-21 | South Lanarkshire | 488 | 44122 | 29960.38 | 463655.62 | 214597.19 | 32676.81 | 0 | 785012 | 0 | 785500 | 204193.13 | [6 empty] | CS11 | 100%
403655 | SR15 ES - SWS2 Establishment Cost Capture for SR15 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-02-03 | 2016-09-21 | 2016-09-21 | 2016-08-23 | 2016-11-28 | Scottish Water Wide | 1271837.55 | 373397.45 | -161315.26 | 0 | 0 | 0 | 0 | 212082.19 | 0 | 1483919.74 | 0 | [6 empty] | DW23 | 100%
403895 | SR15 ES - Tighnabruaich WTW & CWT - WQ & Captial Maintenance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS4 | 2015-04-27 | 2016-09-30 | 2017-03-20 | 2017-03-31 | 2019-12-31 | Argyll and Bute-Cowal & Bute | 15000 | 60178 | 155004.5 | 603987.98 | -43516.4 | 129446.29 | 90000 | 995100.37 | 156798.63 | 1166899 | 1575488.44 | [6 empty] | DW3C | 5% | DW25P | 13% | CM_WSNI | 33% | DW25T | 49% | bar: Regulatory Outputs OMG-01
403713 | SR15 ES - Tiree WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2015-03-26 | 2015-05-11 | 2015-07-31 | 2015-08-31 | Argyll and Bute-Cowal & Bute | 16907.4 | 30250.21 | 0 | 0 | 0 | 0 | 1.29 | 30251.5 | 0 | 47158.9 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403712 | SR15 ES - Torra WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-22 | 2014-12-18 | 2015-01-26 | 2015-03-31 | 2016-03-31 | Argyll and Bute-North Argyll | 57358.58 | 8917.42 | -5545.44 | 0 | 0 | 0 | 0 | 3371.98 | 0 | 60730.56 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403979 | SR15 ES - Toward Old Pier House WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-22 | 2016-03-29 | 2017-03-31 | 2017-05-31 | Argyll and Bute-Cowal & Bute | 3938 | 54576 | 202288.71 | -79487.71 | 205.11 | 0 | 0.89 | 177583 | 0 | 181521 | 139868.94 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403816 | SR15 ES - Trunk Mains Strategy | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2014-06-20 | 2016-12-12 | 2016-12-12 | 2017-01-25 | 2017-01-25 | Scottish Water Wide | 5475.3 | 28802.7 | -7100.46 | 0 | 0 | 0 | 0 | 21702.24 | 0 | 27177.54 | 1134309.94 | [6 empty] | CS16W | 100%
404094 | SR15 ES - Turret WTW Scada Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-07-06 | 2027-08-19 | 2028-01-21 | 2029-04-25 | 2029-07-24 | All West Unitary Authorities | 0 | 44370 | 4050.5 | -204.34 | 0 | -4691.75 | 5360.1 | 48884.51 | 916907.51 | 965792.02 | 0 | [6 empty] | CM_WSNI | 100%
403994 | SR15 ES - Uig WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-02-29 | 2018-03-30 | 2018-06-27 | 2021-07-31 | 2021-10-31 | Na H-Eileanan an Iar | 0 | 2237.14 | 235534.58 | 516568.22 | 161408.22 | 1800704.28 | 1268645 | 3985097.44 | 69977.59 | 4055075.03 | 742727.04 |  |  |  |  | 2180 |  | DW25 | 100% | bar: Regulatory Outputs OMG-04
403338 | SR15 ES - Viewpark Road The Loaning | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-03-11 | 2018-12-06 | 2018-12-07 | 2018-12-07 | 2018-12-07 | North Lanarkshire | 150441.4 | 190700.6 | 14775 | 16298 | 76214.19 | 3396.61 | -1524.8 | 299859.6 | 0 | 450301 | 1469853.01 | [6 empty] | CS11 | 100%
403949 | SR15 ES - W125 - Trinley Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | Glasgow City | 1425 | 25862.22 | 54137.78 | 37632.57 | 304452.65 | 169202.43 | 157637.35 | 748925 | 0 | 750350 | 196097.17 | [6 empty] | CS11 | 100%
404041 | SR15 ES - W406 - Lilybank Street Hamilton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2018-02-26 | 2019-06-07 | 2019-07-12 | 2020-04-01 | 2020-07-07 | South Lanarkshire | 976 | 42524 | 12722.01 | 29606.35 | 119993.64 | 896056.99 | 38721.01 | 1139624 | 0 | 1140600 | 352094.6 | [6 empty] | CS11 | 100%
403921 | SR15 ES - W441 - Machan Road Larkhall | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-30 | 2018-07-09 | 2018-07-09 | 2018-04-18 | 2018-04-18 | South Lanarkshire | 976 | 37000 | 34505.91 | 4397.65 | 1336.97 | -0.27 | 0.27 | 77240.53 | 0 | 78216.53 | 204193.13 | [6 empty] | CS11 | 100%
404042 | SR15 ES - W773 - The Cresent Lesmahagow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS2 | 2018-07-25 | 2020-03-17 | 2020-05-06 | 2020-08-20 | 2020-11-12 | South Lanarkshire | 488 | 3000 | 30512 | 21117.97 | 98746.03 | 339426 | 274394.76 | 767196.76 | 3475.4 | 771160.16 | 443610.3 | [6 empty] | CS11 | 100%
403948 | SR15 ES - Water of Leith | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-01-16 | 2019-04-29 | City of Edinburgh | 4500.97 | 52617.03 | 418833.97 | -407652.99 | -61675.26 | 1602.94 | -4484.92 | -759.23 | 0 | 3741.74 | 220192.97 | [6 empty] | EC01F | 50% | EC10B | 50%
403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS4 | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2016-07-01 | 2021-06-23 | Scottish Water Wide | 305681.28 | 557605.72 | 1085514.81 | 277459.19 | 77470.25 | 94405.74 | 90598.94 | 2183054.65 | 5180.04 | 2493915.97 | 1134309.94 | [6 empty] | CS16W | 100%
403690 | SR15 ES - Weavers Court - Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2014-04-28 | 2018-03-12 | 2019-04-17 | 2018-03-14 | 2019-04-17 | Renfrewshire | 108048 | 110960.51 | -9695.51 | 3687 | 29255.29 | 100.71 | 181.4 | 134489.4 | 0 | 242537.4 | 2468138.89 | [6 empty] | CS11 | 100%
403697 | SR15 ES - Wellhouse Crescent | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS4 | 2014-04-28 | 2020-02-12 | 2020-02-18 | 2020-02-18 | 2020-04-01 | Glasgow City | 89131 | 44422 | 8612.03 | 35911.02 | 97923.95 | 142143.78 | -3143.78 | 325869 | 0 | 415000 | 1345230.68 | [6 empty] | CS15 | 100%
403988 | SR15 ES - West Lewis WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS4 | 2016-09-30 | 2018-02-28 | 2018-03-28 | 2020-03-31 | 2020-06-19 | Na H-Eileanan an Iar | 0 | 10691.12 | 42469.69 | 217914.57 | 864642.93 | 118066.69 | 9960.26 | 1263745.26 | 1612.74 | 1265358 | 2024560.16 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403998 | SR15 ES - West Shore Pittenweem | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-11-09 | 2022-07-04 | 2022-07-04 | 2023-01-20 | 2023-03-03 | Fife | 1220 | 29500 | 64668.97 | 50361.22 | 120249.82 | 46382.44 | -82382.44 | 228780.01 | 3391960 | 3621960.01 | 204193.13 | [6 empty] | CS11 | 100%
403128 | SR15 ES - Yarrowfues WTW Main Out | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2013-03-18 | 2020-11-02 | 2020-12-17 | 2021-09-14 | 2021-12-15 | Scottish Borders | 127138.87 | 17399.4 | 37572.39 | 159540.87 | -14789.85 | -17284.75 | -3451.56 | 178986.5 | 0 | 306125.37 | 356832.64 | [6 empty] | DW25 | 100%
403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS3 | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2021-01-13 | 2021-04-15 | Highland | 123835.35 | 503725.65 | 150267 | 276438.09 | 967203.56 | 4007134.49 | 1475993.58 | 7380762.37 | 1308480.79 | 8813078.51 | 5734275.92 | [6 empty] | LA01 | 100%
500653 | SR15 ES Internal Sewer Flooding APNRV Programme Phase1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2015-06-29 | 2015-06-29 | 2015-08-31 | 2017-09-12 | 2017-09-12 | Scottish Water Wide | 0 | 225769 | 259370.22 | 452492.36 | -103028.98 | 0 | -85.15 | 834517.45 | 0 | 834517.45 | 737583.44 | [6 empty] | CS11 | 19.24% | CS11A | 80.76%
502020 | SR15 ESD Core Balancing Team Payment Line | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-02-15 | 2016-02-15 | 2016-02-15 |  | 2022-07-22 | Scottish Water Wide | 0 | 3248659 | 2290134.6 | 2221100.48 | -1048799.05 | -2494785.13 | -4216309.9 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 25% | CM_WWNI | 25% | DW2 | 50%
500584 | SR15 Heavy Goods Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2017-01-19 | 2017-05-15 | Scottish Water Wide | 0 | 1556315 | -128066.18 | 0 | 0 | 0 | 0 | 1428248.82 | 0 | 1428248.82 | 0 | [6 empty] | CM_M&G | 100%
503580 | SR15 Internal Sewer Flooding Alternative Solutions Phase 10 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2019-06-26 | 2019-06-26 | 2019-08-19 | 2021-02-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 581529.01 | 1780731.59 | 2362260.6 | 18239.38 | 2380499.98 | 593438.15 | [6 empty] | CS11 | 49.46% | CS11A | 50.54%
502939 | SR15 Internal Sewer Flooding Alternative Solutions Phase 2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-10-11 | 2017-10-11 | 2017-11-01 | 2019-03-14 | 2019-03-14 | Scottish Water Wide | 0 | 0 | 0 | 569917.99 | 726547.23 | -43185.89 | -48.81 | 1253230.52 | 0 | 1253230.52 | 535891.78 | [6 empty] | CS11A | 7.692% | CS11 | 92.31%
502976 | SR15 Internal Sewer Flooding Alternative Solutions Phase 3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2017-12-12 | 2017-12-12 | 2018-02-08 | 2020-09-03 | 2020-09-03 | Scottish Water Wide | 0 | 0 | 0 | 296794.39 | 1177800.04 | -23056.94 | -6595.36 | 1444942.13 | 1935 | 1446877.13 | 400290.3 | [6 empty] | CS11A | 100%
503080 | SR15 Internal Sewer Flooding Alternative Solutions Phase 4 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2018-02-26 | 2018-02-26 | 2018-04-02 | 2020-03-13 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 93859.49 | 771792.73 | 49971.87 | 108407.61 | 1024031.7 | 0 | 1024031.7 | 400290.3 | [6 empty] | CS11A | 100%
503294 | SR15 Internal Sewer Flooding Alternative Solutions Phase 5 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS5 | 2018-07-04 | 2018-07-04 | 2018-07-09 | 2019-03-05 | 2019-03-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 441794.39 | -39773.38 | 0 | 402021.01 | 0 | 402021.01 | 196097.17 | [6 empty] | CS11A | 100%
503389 | SR15 Internal Sewer Flooding Alternative Solutions Phase 6 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2020-08-18 | 2020-08-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 395511.17 | 67754.2 | 186735.01 | 650000.38 | 0 | 650000.38 | 196097.17 | [6 empty] | CS11A | 100%
503390 | SR15 Internal Sewer Flooding Alternative Solutions Phase 7 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2021-01-21 | 2021-01-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 158404.72 | 729005.69 | -106106.94 | 781303.47 | 9896.9 | 791200.37 | 196097.17 | [6 empty] | CS11A | 100%
503489 | SR15 Internal Sewer Flooding Alternative Solutions Phase 8 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-16 | 2021-02-22 | 2021-05-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 106086.14 | 938707.46 | 267423.52 | 1312217.12 | 23252.26 | 1335469.38 | 2680397.06 | [6 empty] | CS11A | 11.26% | CS11 | 88.74%
503579 | SR15 Internal Sewer Flooding Alternative Solutions Phase 9 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2019-06-21 | 2019-06-21 | 2019-07-01 | 2020-12-21 | 2020-12-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 690225.56 | 1973413.04 | 2663638.6 | 17254.09 | 2680892.69 | 1035627.36 | [6 empty] | CS11 | 40.07% | CS11A | 59.93%
500504 | SR15 Legacy Legal | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-04 | 2021-06-04 | Scottish Water Wide | 0 | 70532 | 199468 | 0 | 47500 | 87625.08 | 214874.92 | 620000 | 0 | 620000 | 0 | [6 empty] | CM_M&G | 100%
500583 | SR15 Light Commercial Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2017-01-19 | 2017-05-15 | Scottish Water Wide | 0 | 3286121.99 | -153159.01 | 0 | 0 | 0 | 0 | 3132962.98 | 0 | 3132962.98 | 0 | [6 empty] | CM_M&G | 100%
502801 | SR15 LRC3 - Daldowie WWTW Increase in Full Flow to Treatment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2018-08-30 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | South Lanarkshire | 0 | 0 | 0 | 68250.6 | -68249.6 | 387.54 | -387.54 | 1 | 0 | 1 | 3550582.52 | [6 empty] | EC01B | 50% | EC10B | 50%
502400 | SR15 LRC3 - Short Term UWWTD Compliance at Dalmarnock & Daldowie WWTWs | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-01-26 | 2017-01-26 | 2017-06-13 | 2018-05-31 | 2018-11-30 | Glasgow City | 0 | 0 | 326367 | 357093.42 | 59347.12 | 0 | 0 | 742807.54 | 0 | 742807.54 | 11105602.59 | [6 empty] | EC01A | 100% | [18 empty] | Regulatory Outputs OMG-23: 2
500487 | SR15 Meter Maintenance and Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-05-21 | 2021-05-21 | Scottish Water Wide | 0 | 3117885.42 | 386245.58 | 1417021.8 | 1491308 | 1073849.39 | 3293689.81 | 10780000 | 0 | 10780000 | 0 | [6 empty] | CM_WWI | 100%
505407 | SR15 Milnby Weir | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MSU |  | 2020-06-08 | 2020-07-24 | 2020-04-01 | 2020-04-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
500505 | SR15 Milngavie | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-15 | 2021-06-04 | 2021-06-04 | Scottish Water Wide | 0 | 70745.59 | 26421.97 | 72932.44 | 85762.43 | 70314.68 | 93922.89 | 420100 | 0 | 420100 | 0 | [6 empty] | CM_M&G | 100%
504539 | SR15 Mugdock and Craigmaddie Strategic Approach | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2020-01-30 | 2020-02-12 | 2020-02-17 | 2020-12-24 | 2021-03-10 | - | 0 | 0 | 0 | 0 | 0 | 69631.78 | 180368.22 | 250000 | 0 | 250000 | 0 | [6 empty] | CM_M&G | 100%
500486 | SR15 Non Domestic Meters - New Installations | Q&S4 | Supporting economic development | First Time Meters |  |  | Water |  | SWD | First Time Meters | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-05-21 | 2021-05-21 | Scottish Water Wide | 0 | 842536 | 2163574.9 | 909392.2 | 1484611.9 | 1553234.3 | 2739650.7 | 9693000 | 0 | 9693000 | 10184396.32 | [6 empty] | WG6 | 100%
500506 | SR15 Outdoor Access | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-04 | 2021-06-04 | Scottish Water Wide | 0 | 6892 | 2108 | 5900 | 4500 | 8348.46 | 20251.54 | 48000 | 0 | 48000 | 0 | [6 empty] | CM_M&G | 100%
402243 | SR15 Planning - Activity Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-08-01 | 2012-10-22 | 2012-11-12 | 2016-06-14 |  | Scottish Water Wide | 831840.17 | 213570.68 | 49699.57 | 2416.25 | 0 | 0 | -2416.25 | 263270.25 | 0 | 1095110.42 | 0 | [6 empty] | QS4EQS | 100%
500585 | SR15 Plant | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2016-12-19 | 2017-05-15 | Scottish Water Wide | 0 | 112694.23 | -26613.11 | 0 | 0 | 0 | 0 | 86081.12 | 0 | 86081.12 | 0 | [6 empty] | CM_M&G | 100%
500507 | SR15 Redundant Assets | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 |  | 2021-03-12 | Scottish Water Wide | 0 | 776 | 408499 | 396808.95 | 492585.96 | 427023.13 | 639206.46 | 2364899.5 | 0 | 2364899.5 | 0 | [6 empty] | CM_M&G | 100%
504344 | SR15 Rosebery WTW T&O - Contingency PAC Dosing Plant | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-06-08 | 2021-12-06 | 2022-04-06 | 2022-11-30 | 2023-03-02 | Midlothian | 0 | 0 | 0 | 0 | 0 | 33463.08 | 521659.02 | 555122.1 | 944877.9 | 1500000 | 0 | [6 empty] | CM_WSNI | 100%
500574 | SR15 Rural Estates | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2021-06-11 | 2021-06-11 | Scottish Water Wide | 0 | 94837.75 | 46162.25 | 91925.27 | 81074.73 | 88415.18 | 113584.82 | 516000 | 0 | 516000 | 0 | [6 empty] | CM_M&G | 100%
502041 | SR15 Security Capital Maintenance Bundle 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-23 | 2017-03-23 | 2017-06-22 | 2017-12-19 | 2017-12-19 | Scottish Water Wide | 0 | 0 | 13327.74 | 81707.36 | 0 | 0 | -141.36 | 94893.74 | 0 | 94893.74 | 0 | [6 empty] | CM_WSNI | 100%
502042 | SR15 Security Capital Maintenance Bundle 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS6 | 2016-08-23 | 2017-02-24 | 2017-04-20 | 2017-12-12 | 2017-12-12 | Scottish Water Wide | 0 | 0 | 18306.39 | 166315.49 | 1659.74 | 0 | 0 | 186281.62 | 0 | 186281.62 | 0 | [6 empty] | CM_WSNI | 100%
502044 | SR15 Security Capital Maintenance Bundle 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-23 | 2017-08-16 | 2017-08-16 | 2017-08-03 | 2017-08-03 | Scottish Water Wide | 0 | 0 | 6208.69 | -2726.15 | 0 | 0 | 177.36 | 3659.9 | 0 | 3659.9 | 0 | [6 empty] | CM_WSNI | 100%
502255 | SR15 Security Capital Maintenance Bundle 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2017-11-08 | 2018-02-21 | 2018-03-15 | 2021-06-18 | 2021-06-18 | Scottish Water Wide | 0 | 0 | 25805.39 | 98357.6 | 50680.55 | 242639.52 | 300839.57 | 718322.63 | 54753.34 | 773075.97 | 0 | [6 empty] | CM_WSNI | 100%
502596 | SR15 Security Capital Maintenance Bundle 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS3 | 2017-10-30 | 2019-05-14 | 2019-07-08 | 2020-07-06 | 2020-10-06 | Scottish Water Wide | 0 | 0 | 2093.02 | 26067.44 | 72082.58 | 1340375.08 | 56436.62 | 1497054.74 | 3780.26 | 1500835 | 0 | [6 empty] | CM_WSNI | 100%
502597 | SR15 Security Capital Maintenance Bundle 7 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS4 | 2017-10-24 | 2018-10-29 | 2019-04-22 | 2019-12-17 | 2020-04-15 | Scottish Water Wide | 0 | 0 | 1046.51 | 4932.82 | 33722.03 | 196808.5 | 5163.97 | 241673.83 | 532.75 | 242206.58 | 0 | [6 empty] | CM_WSNI | 100%
502594 | SR15 Security Capital Maintenance Bundle 8 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2017-10-24 | 2018-06-11 | 2018-07-10 | 2020-07-15 | 2020-07-16 | Scottish Water Wide | 0 | 0 | 2093.02 | 2906.98 | 5932.64 | 30594 | 7724.37 | 49251.01 | 0 | 49251.01 | 0 | [6 empty] | CM_WSNI | 100%
502595 | SR15 Security Capital Maintenance Bundle 9 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS3 | 2017-10-24 | 2019-05-21 | 2019-06-06 | 2020-08-28 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 2093.02 | 4779.5 | 8968.68 | 629312.89 | 83423.29 | 728577.38 | 2039.62 | 730617 | 0 | [6 empty] | CM_WSNI | 100%
502254 | SR15 Security Capital Maintenance IDP costs & emerging needs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2016-11-30 | 2017-03-28 | 2017-03-29 | 2021-05-03 | 2021-05-03 | Scottish Water Wide | 0 | 0 | 98699.92 | 93300.08 | 22889.14 | 54838.82 | 91129.16 | 360857.12 | 6611.88 | 367469 | 0 | [6 empty] | CM_WSNI | 100%
500980 | SR15 SPS Data Quality Testing & Priority Remedials Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-05-31 | 2016-11-08 | 2016-11-30 | 2021-02-02 | 2021-02-02 | Scottish Water Wide | 0 | 0 | 105487.75 | 149063.7 | 60067.54 | 36021.19 | 34681.03 | 385321.21 | 19678.76 | 404999.97 | 0 | [6 empty] | CM_WSNI | 100%
501192 | SR15 SR Repairs Additional Cells | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-23 | 2015-11-23 | 2016-01-14 | 2017-07-10 | 2017-07-10 | All North Unitary Authorities | 0 | 351514 | 838956.23 | -158862.81 | 105.07 | -105.07 | 0 | 1031607.42 | 0 | 1031607.42 | 0 | [6 empty] | CM_WSNI | 100%
403730 | SR15 Start Early Delivery Plan Development Wastewater Central - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2015-12-01 |  | Scottish Water Wide | 20000 | -159.27 | 389.43 | 42.55 | 0 | 0 | -24.59 | 248.12 | 0 | 20248.12 | 0 | [6 empty] | CM_WWNI | 100%
403732 | SR15 Start Early Delivery Plan Development Wastewater East - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-09-30 | 2016-09-30 | All East Unitary Authorities | 432263.69 | 250862.31 | 1140.09 | 455.14 | 0 | 0 | -7 | 252450.54 | 0 | 684714.23 | 0 | [6 empty] | CM_WWNI | 100%
403734 | SR15 Start Early Delivery Plan Development Wastewater North - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-01-13 | 2016-02-17 | All North Unitary Authorities | 4341 | -2833.53 | 0 | 0 | 0 | 0 | 0 | -2833.53 | 0 | 1507.47 | 0 | [6 empty] | CM_WWNI | 100%
403728 | SR15 Start Early Delivery Plan Development Wastewater South - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-15 | 2017-05-15 | All South Unitary Authorities | 337395.87 | 383353.58 | -34579.15 | 2051.89 | 0 | 0 | 0 | 350826.32 | 0 | 688222.19 | 0 | [6 empty] | CM_WWNI | 100%
403731 | SR15 Start Early Delivery Plan Development Water Central - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-07 |  | Scottish Water Wide | 361041.47 | 132065.53 | 8673.13 | 1362.71 | 0 | 0 | 597.67 | 142699.04 | 0 | 503740.51 | 0 | [6 empty] | CM_WSNI | 100%
403733 | SR15 Start Early Delivery Plan Development Water East - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-06-07 | 2016-06-07 | All East Unitary Authorities | 240906.27 | 182605.79 | 5545.02 | 0 | 0 | 0 | 0 | 188150.81 | 0 | 429057.08 | 0 | [6 empty] | CM_WSNI | 100%
403735 | SR15 Start Early Delivery Plan Development Water North - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-08 | 2016-12-08 | All North Unitary Authorities | 171670.62 | 426948.38 | -25211.45 | 1712.66 | 0 | 0 | 0 | 403449.59 | 0 | 575120.21 | 0 | [6 empty] | CM_WSNI | 100%
403729 | SR15 Start Early Delivery Plan Development Water South - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-19 | 2017-02-01 | All South Unitary Authorities | 156565.39 | -6565.39 | -17405.82 | 0 | 0 | 0 | 0 | -23971.21 | 0 | 132594.18 | 0 | [6 empty] | CM_WSNI | 100%
403736 | SR15 Start Early Delivery Plan Development Water West - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-15 | 2017-11-22 | All West Unitary Authorities | 194289.16 | 183500.17 | 15479.81 | -8604.1 | 0 | 0 | 0 | 190375.88 | 0 | 384665.04 | 0 | [6 empty] | CM_WWNI | 100%
403737 | SR15 Start Early Delivery Plan Development Water West - HL - 4037370000 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-05-10 | 2016-05-12 | All West Unitary Authorities | 277227.52 | 34192.9 | 0 | 0 | 0 | 0 | 0 | 34192.9 | 0 | 311420.42 | 0 | [6 empty] | CM_WSNI | 100%
501001 | SR15 TE CM Staney Hill North (Q Sandy Loch WTW) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2015-09-28 | 2018-09-21 | 2018-09-24 | 2021-10-31 | 2022-01-31 | Shetland Islands | 0 | 31287 | 141658.16 | 361096.4 | 1376955.69 | 783861.76 | 3289130 | 5983989.01 | 55055 | 6039044.01 | 0 |  |  |  |  | -5000 |  | DW25D | 100% | bar: Regulatory Outputs OMG-05
403424 | SR15 Technology and Innovation strategy work | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-03-14 | 2013-03-14 | 2013-04-03 | 2018-03-12 |  | Scottish Water Wide | 174282.61 | 0.39 | 0 | 0 | 0 | 0 | 0 | 0.39 | 0 | 174283 | 0 | [6 empty] | CM_M&G | 100%
501005 | SR15 Telemetry RTU Replacement - Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS4 | 2016-02-25 | 2016-07-22 | 2016-08-31 | 2020-02-28 | 2020-03-02 | Scottish Water Wide | 0 | 14482.71 | 588592.43 | 182330.85 | 37624.64 | 46869.08 | 37667.43 | 907567.14 | 5118.78 | 912685.92 | 0 | [6 empty] | CM_WWNI | 23.59% | CM_WSNI | 76.41%
501006 | SR15 Telemetry RTU Replacement - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2016-01-25 | 2016-05-26 | 2016-06-10 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 198402 | 146023.97 | -2525.15 | 12.46 | 255 | -225.86 | 341942.42 | 0 | 341942.42 | 0 | [6 empty] | CM_WSNI | 40.13% | CM_WWNI | 59.87%
501007 | SR15 Telemetry RTU Replacement - Phase 3 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2017-07-26 | 2017-08-31 | 2020-11-25 | 2020-11-25 | Scottish Water Wide | 0 | 0 | 145119.88 | 657878.56 | 289095.84 | 298210.62 | 125405.44 | 1515710.34 | 15107.87 | 1530818.21 | 0 | [6 empty] | CM_WWNI | 28.21% | CM_WSNI | 71.79%
501008 | SR15 Telemetry RTU Replacement - Phase 4 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2018-01-25 | 2018-02-28 | 2020-09-02 | 2020-09-02 | Scottish Water Wide | 0 | 0 | 38882.64 | 228845.78 | 329270.5 | 452321.16 | 63999.79 | 1113319.87 | 8272.91 | 1121592.78 | 0 | [6 empty] | CM_WWNI | 38.1% | CM_WSNI | 61.9%
501009 | SR15 Telemetry RTU Replacement - Phase 5 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2017-12-15 | 2018-02-05 | 2020-12-04 | 2020-12-04 | Scottish Water Wide | 0 | 0 | 42565.39 | 225201.29 | 696607.96 | 803030.4 | 171438.51 | 1938843.55 | 16447.97 | 1955291.52 | 0 | [6 empty] | CM_WWNI | 36.89% | CM_WSNI | 63.11%
500948 | SR15 Telemetry RTU Upgrading - Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2016-05-13 | 2016-12-13 | 2016-12-14 | 2019-04-23 | 2019-04-23 | Scottish Water Wide | 0 | 0 | 54909.96 | 117508.41 | 10424.25 | -4687.35 | 12624.27 | 190779.54 | 664.44 | 191443.98 | 0 | [6 empty] | CM_WWNI | 100%
500949 | SR15 Telemetry RTU Upgrading - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-30 | 2017-06-01 | 2021-01-05 | 2021-01-05 | Scottish Water Wide | 0 | 0 | 18917.56 | 303371 | 87504.25 | 201359.22 | 39428.05 | 650580.08 | 2645.78 | 653225.86 | 0 | [6 empty] | CM_WWNI | 24.68% | CM_WSNI | 75.32%
500502 | SR15 Tenant Housing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-08 | 2021-06-08 | Scottish Water Wide | 0 | 37532.26 | 18047.74 | 29798.9 | 27969.89 | 24352.21 | 42299 | 180000 | 0 | 180000 | 0 | [6 empty] | CM_M&G | 100%
500201 | SR15 Waste Water DOA Telemetry Schematics Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-03-23 | 2015-03-23 | 2015-03-23 | 2018-08-09 | 2018-08-09 | Scottish Water Wide | 0 | 146264.15 | -14402.15 | 36408 | 10317.27 | 0 | 0.01 | 178587.28 | 0 | 178587.28 | 0 | [6 empty] | CM_WSNI | 100%
504292 | SR15 White Loch MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-01-27 | 2020-02-28 | 2021-04-01 | 2021-04-02 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 3461.42 | 0 | 3461.42 | 0 | 3461.42 | 0 | [6 empty] | CM_WSI | 100%
502303 | SR15 WW Temporary Chemical Dosing Systems Upgrade -Phase 5 (NORTH) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-05-29 | 2022-02-14 | 2022-06-03 | 2023-08-28 | 2023-11-28 | Scottish Water Wide | 0 | 0 | 21103.73 | 14401.03 | 542.61 | 18708.38 | 75027.71 | 129783.46 | 1310216.46 | 1439999.92 | 0 | [6 empty] | SR21_WW | 100%
49576 | SR15_CMA_MAG - Management and General - Adjustment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1645588 | [6 empty] | SR15_CMA_MAG | 100%
49577 | SR15_CMA_UNP - Unpromoted Capital Maintenance - Adjustment | Q&S4 | Sustaining existing high service for customers | CM Risk Drawdown |  |  | General |  | SWD | CM Risk Drawdown | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -2838285.12 | -2838285.12 | 0 | -2838285.12 | 0 | [6 empty] | SR15_CMA_UNP | 100%
49580 | SR15_CMA_WSI - Water infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2957874.55 | [6 empty] | SR15_CMA_WSI | 100%
49581 | SR15_CMA_WSNI - Water non infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Water non infrastructure |  |  | General |  | SWD | Water non infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SR15_CMA_WSNI | 100%
49578 | SR15_CMA_WWI - Wastewater infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SR15_CMA_WWI | 100%
49579 | SR15_CMA_WWNI - Wastewater non infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SR15_CMA_WWNI | 100%
49585 | SR15_CMP_LATE - Late - Adjustment | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3089071.93 | [6 empty] | SR15_CMP_LATE | 100%
49584 | SR15_CMP_PLAN - Planned - Adjustment | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20922630.12 | [6 empty] | SR15_CMP_PLAN | 100%
49575 | SR15_COS_RAI - Research and Innovation - Adjustment | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | General |  | SWD | Research and Innovation | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630290.41 | [6 empty] | SR15_COS_RAI | 100%
49545 | SR15_DWA_SOSI - SOSI - Adjustment | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | General |  | SWD | SOSI | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4110618.39 | 4110618.39 | -4110618.39 | 0 | 0 | [6 empty] | SR15_DWA_SOSI | 100%
49542 | SR15_DWQ_COM - DWQ Compliance - Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -17168.66 | -17168.66 | 17168.66 | 0 | 1752927.89 | [6 empty] | SR15_DWQ_COM | 100%
49543 | SR15_DWQ_REL - DWQ Reliability - Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | General |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -2572618.24 | -2572618.24 | 2572618.24 | 0 | 5673016.18 | [6 empty] | SR15_DWQ_REL | 100%
49561 | SR15_ENV_ENVS - Environmental Studies - Adjustment | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | General |  | SWD | Environmental Studies | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4216938.43 | [6 empty] | SR15_ENV_ENVS | 100%
49554 | SR15_ENV_RBWD - Revised Bathing Waters Directive - Adjustment | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | General |  | SWD | Revised Bathing Waters Directive | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375046 | [6 empty] | SR15_ENV_RBWD | 100%
49556 | SR15_ENV_SHEL - Ringfenced Environmental Adjustment | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | General |  | SWD | Ring Fenced Environmental | MS0 | 2018-04-01 |  |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000986.04 | [6 empty] | SR15_ENV_SHEL | 100%
49555 | SR15_ENV_SLU - Sludge - Adjustment | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | General |  | SWD | Sludge | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086034.12 | [6 empty] | SR15_ENV_SLU | 100%
49612 | SR15_EXC - Exceptional - Adjustment | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119785532.51 | [6 empty] | SR15_EXC_EXC | 100%
49538 | SR15_IR18_IR18 - IR18 - Adjustment | Q&S4 | IR18 Allowance | IR18 |  |  | Wastewater |  | SWD | IR18 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2128065.6 | 2128065.6 | -2128065.6 | 0 | 12117737.85 | [6 empty] | SR15_IR18_IR18 | 100%
49536 | SR15_RSK_CMR - Maintenance Risk - Adjustment | Q&S4 | Programme Risk | Maintenance Risk |  |  | General |  | SWD | Maintenance Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2821099.8 | 2821099.8 | 0 | 2821099.8 | 281321099.8 | [6 empty] | SR15_RSK_CMR | 100%
49535 | SR15_RSK_COMP - Completion Risk - Adjustment | Q&S4 | Programme Risk | Completion Risk |  |  | General |  | SWD | Completion Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000 | [6 empty] | SR15_RSK_COMP | 100%
49537 | SR15_RSK_EHR - Enhanced Risk - Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1828011.86 | 1828011.86 | 20698513.68 | 22526525.54 | 136670650.92 | [6 empty] | SR15_RSK_EHR | 100%
50003 | SR15_RSK_EHR - Risk CEO- Adjustment | Q&S4 | Programme Risk | Enhanced Risk - Forecast Variance |  |  | General |  | SWD | Enhanced Risk - Forecast Variance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23343000 | [6 empty] | SR15_RSK_EHU | 100%
49586 | SR15_RSK_RINF - Ringfenced for Inflation - Adjustment | Q&S4 | Programme Risk | Ringfenced for Inflation |  |  | General |  | SWD | Ringfenced for Inflation | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 46882289.13 | 46882289.13 | 0 | 46882289.13 | 46882289.13 | [6 empty] | SR15_RSK_RINF | 100%
49569 | SR15_SED_DAA - Developer Asset Adoption - Adjustment | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWD | Developer Asset Adoption | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2019676.46 | 2019676.46 | 0 | 2019676.46 | 2199945.14 | [6 empty] | SR15_SED_DAA | 100%
49570 | SR15_SED_FTM - First Time Meters - Adjustment | Q&S4 | Supporting economic development | First Time Meters |  |  | General |  | SWD | First Time Meters | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 542763.14 | 542763.14 | 0 | 542763.14 | 0 | [6 empty] | SR15_SED_FTM | 100%
49582 | SR15_SED_INFC - Infra Charge - Adjustment | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -8024208.71 | -8024208.71 | 0 | -8024208.71 | 0 | [6 empty] | SG5 | 50% | WG5 | 50%
49571 | SR15_SED_NRSW - NRSWA - Adjustment | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWD | NRSWA | MS2 |  | 2018-04-01 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -2771647.03 | -2771647.03 | 0 | -2771647.03 | 6818375.67 | [6 empty] | SR15_SED_NRSW | 100%
49567 | SR15_SED_RCC - RCC - Adjustment | Q&S4 | Supporting economic development | RCC |  |  | General |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1795401.55 | 1795401.55 | 0 | 1795401.55 | 64840488.47 | [6 empty] | SG2 | 50% | WG2 | 50%
49568 | SR15_SED_SCAP - Strategic Capacity - Adjustment | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -30919122.49 | -30919122.49 | 0 | -30919122.49 | 74218069.25 | [6 empty] | SR15_SED_SCAP | 100%
49565 | SR15_SEW_EFR - External Flooding - Adjustment | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 27257548.75 | 27257548.75 | 0 | 27257548.75 | 0 | [6 empty] | SR15_SEW_EFR | 100%
49564 | SR15_SEW_IFR - Internal Flooding - Adjustment | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 948719.57 | 948719.57 | 0 | 948719.57 | 2254174.59 | [6 empty] | SR15_SEW_IFR | 100%
49613 | SR15_UID_UWWD - UWWTD - UIDs - Adjustment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS2 | 2015-03-31 | 2015-03-31 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -5136151.75 | -5136151.75 | 5136151.75 | 0 | 1951080.45 | [6 empty] | SR15_UID_UWWD | 100%
503634 | SR21 Abergeldie Road Ballater | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-01-22 | 2021-12-23 | 2022-03-15 | 2022-10-03 | 2022-12-19 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 8769.57 | 23193.11 | 31962.68 | 168037.36 | 200000.04 | 0 | [6 empty] | SR21_WW | 100%
503635 | SR21 Beech Cottage Rothienorman Surface Water Culvert | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2021-01-14 | 2022-03-23 | 2022-06-16 | 2023-05-10 | 2023-08-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 10595.54 | 24808.46 | 35404 | 414596.04 | 450000.04 | 0 | [6 empty] | SR21_WW | 100%
503761 | SR21 Bonnycraig WTW Growth and Quality | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2019-09-30 | 2021-03-15 | 2021-04-13 | 2023-03-13 | 2023-06-13 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1825358.23 | 10084848.21 | 11910206.44 | 9889793.54 | 21799999.98 | 0 | [6 empty] | SR21_WA | 100%
505409 | SR21 Bradan_WTW Future Plan | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 125581.4 | 494264.77 | 619846.17 | 59380153.77 | 59999999.94 | 0 | [6 empty] | SR21_WA | 100%
503638 | SR21 Carstairs Junction Overland Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2020-11-13 | 2021-05-31 | 2021-07-26 | 2021-09-03 | 2021-10-27 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 31905.02 | 241221.66 | 273126.68 | 1126873.31 | 1399999.99 | 0 | [6 empty] | SR21_WW | 100%
502443 | SR21 CM Raw Water Intake Surveys | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-02-10 | 2020-12-03 | 2020-12-03 | Scottish Water Wide | 0 | 0 | 10509.26 | 9004.01 | 29654.7 | 20916.78 | 44224.23 | 114308.98 | 691 | 114999.98 | 0 | [6 empty] | CM_WSI | 100%
503640 | SR21 Culroy Burn Crossing Minishant Maybole | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-11-20 | 2022-01-17 | 2022-04-04 | 2023-03-03 | 2023-06-06 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 11058.44 | 47490.92 | 58549.36 | 341450.67 | 400000.03 | 0 | [6 empty] | SR21_WW | 100%
503641 | SR21 Duntocher Burn Pipe Bridge Glasgow | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2020-12-04 | 2021-11-29 | 2022-02-24 | 2022-12-01 | 2023-03-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 38005.93 | 139551.08 | 177557.01 | 1522442.97 | 1699999.98 | 0 | [6 empty] | SR21_WW | 100%
503666 | SR21 ES - Afton Drought Resilience | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-03-31 | 2022-08-16 | 2022-12-08 | 2024-06-04 | 2024-09-03 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 46480.81 | 65685.85 | 112166.66 | 4887833.31 | 4999999.97 | 0 | [6 empty] | SR21_WA | 100%
503656 | SR21 ES Forfar STW SCADA replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-01-26 | 2022-10-03 | 2023-02-03 | 2024-08-29 | 2024-10-22 | Angus | 0 | 0 | 0 | 0 | 0 | 51992.64 | 59629.45 | 111622.09 | 1288377.94 | 1400000.03 | 0 | [6 empty] | SR21_WW | 100%
503667 | SR21 ES - Turret Drought Resilience | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-03-31 | 2022-09-15 | 2023-01-16 | 2024-12-17 | 2025-03-17 | Stirling | 0 | 0 | 0 | 0 | 0 | 118353.2 | 102646.79 | 220999.99 | 9778999.99 | 9999999.98 | 0 | [6 empty] | SR21_WA | 100%
503733 | SR21 ES Aird aMhachair - Benbecula DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-03 | 2020-06-08 | 2020-07-06 | 2021-09-30 | 2021-11-22 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 22869.98 | 2142307.66 | 2165177.64 | 234822.36 | 2400000 | 0 | [6 empty] | SR21_WA | 100%
503727 | SR21 ES Alyth Loyal - Cothelhill DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS2 | 2019-10-03 | 2020-03-31 | 2020-08-03 | 2021-03-11 | 2021-05-04 | Angus | 0 | 0 | 0 | 0 | 0 | 75696.73 | 569987.52 | 645684.25 | 3913.75 | 649598 | 0 | [6 empty] | SR21_WA | 100%
503659 | SR21 ES Assynt WOA - Easter Bennetsfield mains rehab | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 | 2019-09-02 | 2019-09-02 | 2019-12-09 | 2021-04-09 | 2021-06-02 | Highland | 0 | 0 | 0 | 0 | 0 | 145499.25 | 280952.26 | 426451.51 | 19048.49 | 445500 | 0 | [6 empty] | SR21_WA | 100%
503717 | SR21 ES Balgillie Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2020-09-16 | 2020-10-12 | 2020-10-19 | 2023-12-15 | 2024-02-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 343311.82 | 343311.82 | 2406688.13 | 2749999.95 | 0 | [6 empty] | SR21_WA | 100%
503681 | SR21 ES Balgray Reservoir MIOS -Top Water Lowering | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-09-10 | 2020-10-26 | 2020-11-25 | 2022-08-26 | 2023-05-02 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 172344.28 | 254156.86 | 426501.14 | 1573498.81 | 1999999.95 | 0 | [6 empty] | SR21_WA | 100%
503725 | SR21 ES Barcraigs VT Bridge | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2020-05-01 | 2020-07-20 | 2020-08-03 | 2020-12-01 | 2021-09-16 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 101848.39 | 764487.77 | 866336.16 | 206267.78 | 1072603.94 | 0 | [6 empty] | SR21_WA | 100%
503653 | SR21 ES Bathgate STW SCADA replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-11-30 | 2022-08-12 | 2022-12-15 | 2024-07-10 | 2024-09-02 | West Lothian | 0 | 0 | 0 | 0 | 0 | 48895.88 | 45298.03 | 94193.91 | 805806.11 | 900000.02 | 0 | [6 empty] | SR21_WW | 100%
503723 | SR21 ES Battock Terrace - Torphins DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-03 | 2020-05-25 | 2020-09-14 | 2021-02-23 | 2021-04-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 24605.31 | 171412.95 | 196018.26 | 3981.74 | 200000 | 0 | [6 empty] | SR21_WA | 100%
504549 | SR21 ES Black Esk WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-02-26 | 2023-01-19 | 2023-06-29 | 2025-01-09 | 2025-04-11 | - | 0 | 0 | 0 | 0 | 0 | 23154.51 | 599942.99 | 623097.5 | 25376902.53 | 26000000.03 | 0 | [6 empty] | SR21_WA | 100%
503636 | SR21 ES Bonny Water Pipe Bridge Gateside Avenue Bonnybridge | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-10-16 | 2021-11-24 | 2022-02-17 | 2023-01-18 | 2023-04-19 | Falkirk | 0 | 0 | 0 | 0 | 0 | 24044.41 | 42849.59 | 66894 | 391767.28 | 458661.28 | 0 | [6 empty] | SR21_WW | 100%
503746 | SR21 ES Brechin STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-05-21 | 2025-09-23 | 2026-08-10 | 2026-10-01 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 24185.99 | 24185.99 | 1435814.03 | 1460000.02 | 0 | [6 empty] | SR21_WW | 100%
503722 | SR21 ES Brownhill Farm - Drongan DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-03 | 2020-05-25 | 2020-07-06 | 2021-03-11 | 2021-05-04 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 17843.91 | 699162.83 | 717006.74 | 32993.26 | 750000 | 0 | [6 empty] | SR21_WA | 100%
503687 | SR21 ES Caaf Spillway and Scour Contol | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2020-08-28 | 2021-05-10 | 2022-03-15 | 2022-07-12 | 2023-10-02 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 15642.37 | 4098.66 | 19741.03 | 116151.43 | 135892.46 | 0 | [6 empty] | SR21_WA | 100%
503715 | SR21 ES Cameron | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2020-07-06 | 2021-06-07 | 2021-08-18 | 2022-03-21 | 2022-06-20 | Fife | 0 | 0 | 0 | 0 | 0 | 18290.38 | 96313.62 | 114604 | 285396.01 | 400000.01 | 0 | [6 empty] | SR21_WA | 100%
503678 | SR21 ES Camps | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2020-03-26 | 2022-03-28 | 2022-07-25 | 2023-10-20 | 2024-01-22 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 12843.87 | 5839.53 | 18683.4 | 1609868.15 | 1628551.55 | 0 | [6 empty] | SR21_WA | 100%
504849 | SR21 ES Carman Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 12820.68 | 12820.68 | 532633.34 | 545454.02 | 0 | [6 empty] | SR21_WA | 100%
503637 | SR21 ES Carmel Water Pipe Bridge Crosshouse | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-04-24 | 2021-07-02 | 2021-10-04 | 2022-09-02 | 2022-12-02 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 22545.91 | 112217.49 | 134763.4 | 484002.59 | 618765.99 | 0 | [6 empty] | SR21_WW | 100%
504391 | SR21 ES Carron Valley WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-11-09 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | Stirling | 0 | 0 | 0 | 0 | 0 | 28880.76 | 2726259.45 | 2755140.21 | 85244859.66 | 87999999.87 | 0 | [6 empty] | SR21_WA | 100%
503657 | SR21 ES CCTV Phase 5A Paisley & Glasgow | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-04-17 | 2020-11-30 | 2021-01-22 | 2021-03-04 | 2021-04-27 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 45436.28 | 2784170.15 | 2829606.43 | 205160.58 | 3034767.01 | 0 | [6 empty] | SR21_WW | 100%
503639 | SR21 ES CCTV Phase 5B Edinburgh | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-04-17 | 2020-11-16 | 2021-01-15 | 2021-02-25 | 2021-04-20 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 39315.11 | 1726885.28 | 1766200.39 | 61069.61 | 1827270 | 0 | [6 empty] | SR21_WW | 100%
503765 | SR21 ES Core WTW Pilots | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS0 | 2019-09-30 | 2020-12-07 | 2021-01-08 | 2021-05-07 | 2021-07-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 8259.14 | 937878.35 | 946137.49 | 553862.52 | 1500000.01 | 0 | [6 empty] | SR21_WA | 100%
504850 | SR21 ES Corsehouse Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 10883.72 | 948.44 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503682 | SR21 ES Corsehouse Reservoir -Spillway Repairs | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-08-07 | 2021-07-19 | 2021-09-29 | 2022-05-02 | 2022-07-29 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 11731.77 | 56082.24 | 67814.01 | 232186 | 300000.01 | 0 | [6 empty] | SR21_WA | 100%
504851 | SR21 ES Coulter Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 10883.72 | 948.44 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503679 | SR21 ES Cowgill Upper and Lower | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-07-09 | 2021-06-07 | 2021-08-18 | 2022-05-25 | 2022-08-23 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 35708.18 | 230181.82 | 265890 | 734110.02 | 1000000.02 | 0 | [6 empty] | SR21_WA | 100%
503747 | SR21 ES Dalderse STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-06-18 | 2025-10-21 | 2026-11-02 | 2026-12-24 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 31143.59 | 31143.59 | 1848856.47 | 1880000.06 | 0 | [6 empty] | SR21_WW | 100%
503738 | SR21 ES Darnhay Farm - Mauchline DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 | 2019-10-04 | 2019-10-04 | 2019-11-11 | 2020-08-20 | 2020-10-13 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 244864.72 | 17140.55 | 262005.27 | 0 | 262005.27 | 0 | [6 empty] | SR21_WA | 100%
503671 | SR21 ES DI Replacement Meters Verification Chambers Bypasses and Redundant DI Site Tidy Up | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 | 2019-09-18 | 2020-03-06 | 2020-02-25 | 2021-07-05 | 2021-10-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 60714.87 | 618449.48 | 679164.35 | 200835.65 | 880000 | 0 | [6 empty] | SR21_WA | 100%
504852 | SR21 ES Drumbowie Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 11832.16 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503757 | SR21 ES DSEAR Compliance (Desktop) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2020-01-23 | 2020-08-24 | 2020-12-11 | 2021-12-07 | 2022-01-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 119182.98 | 494001.18 | 613184.16 | 420815.82 | 1033999.98 | 0 | [6 empty] | SR21_WW | 100%
503748 | SR21 ES Dunfermline STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-07-02 | 2025-11-04 | 2026-09-21 | 2026-11-12 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 27167.83 | 27167.83 | 1612832.2 | 1640000.03 | 0 | [6 empty] | SR21_WW | 100%
503680 | SR21 ES Dunside Upper and Lower | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-07-09 | 2021-06-07 | 2021-08-18 | 2022-05-25 | 2022-08-23 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 39105.92 | 226784.08 | 265890 | 734110.02 | 1000000.02 | 0 | [6 empty] | SR21_WA | 100%
503728 | SR21 ES Edzell Rural DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS3 | 2019-10-03 | 2020-01-31 | 2020-03-03 | 2021-05-11 | 2021-07-02 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 440310.14 | 1023068.84 | 1463378.98 | 0 | 1463378.98 | 0 | [6 empty] | SR21_WA | 100%
503731 | SR21 ES Elsrickle DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-02 | 2020-07-20 | 2020-07-31 | 2021-12-15 | 2022-02-04 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 40053.63 | 304717.28 | 344770.91 | 855229.09 | 1200000 | 0 | [6 empty] | SR21_WA | 100%
503755 | SR21 ES Energy Efficiency Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MSU | 2020-04-01 | 2021-07-26 | 2021-11-26 | 2022-11-23 | 2023-01-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 174500 | 174500 | 1625500.01 | 1800000.01 | 0 | [6 empty] | SR21_FS | 100%
503907 | SR21 ES Finlas WTW Mainout | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-12-30 | 2022-06-17 | 2022-10-19 | 2023-06-14 | 2023-09-14 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 20339 | 90135.65 | 110474.65 | 1489525.33 | 1599999.98 | 0 | [6 empty] | SR21_WA | 100%
503643 | SR21 ES Gills Burn Pipe Bridge Allanvale Dunlop | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-06-19 | 2021-08-06 | 2021-11-03 | 2022-10-04 | 2023-01-03 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 17368.98 | 32106.01 | 49474.99 | 200525.01 | 250000 | 0 | [6 empty] | SR21_WW | 100%
503750 | SR21 ES Girvan STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-03-12 | 2025-07-15 | 2026-03-09 | 2026-04-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 15031.06 | 15031.06 | 814968.99 | 830000.05 | 0 | [6 empty] | SR21_WW | 100%
503646 | SR21 ES Glen Water Pipe Bridge Causeway Road Darvel | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-06-19 | 2021-09-01 | 2021-12-02 | 2022-10-31 | 2023-01-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 16846.9 | 26153.09 | 42999.99 | 207000.04 | 250000.03 | 0 | [6 empty] | SR21_WW | 100%
503672 | SR21 ES Glenfarg WTW upgrade | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2020-07-02 | 2021-12-20 | 2022-04-27 | 2024-04-22 | 2024-07-19 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 288096.38 | 1352624.63 | 1640721.01 | 38359278.97 | 39999999.98 | 0 | [6 empty] | SR21_WA | 100%
503647 | SR21 ES Gremista SPS Rising Main | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2020-11-13 | 2021-06-28 | 2021-08-23 | 2021-10-01 | 2021-11-24 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 35757.67 | 167575.66 | 203333.33 | 2296666.65 | 2499999.98 | 0 | [6 empty] | SR21_WW | 100%
503676 | SR21 ES Gryfe 1 and 2 VT Bridge | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2019-09-30 | 2020-08-03 | 2020-10-12 | 2021-07-20 | 2021-10-18 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 10171.26 | 1097309.97 | 1107481.23 | 392518.77 | 1500000 | 0 | [6 empty] | SR21_WA | 100%
504854 | SR21 ES Hopes Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 11832.16 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503758 | SR21 ES HV Dalgrain SPS Transformer & LV MCC Replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2022-02-07 | 2023-10-13 | 2024-02-06 | 2025-05-06 | 2025-06-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 73573.25 | 0 | 73573.25 | 2426426.7 | 2499999.95 | 0 | [6 empty] | SR21_WW | 100%
503675 | SR21 ES HV Earthing surveys | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS0 | 2019-10-01 | 2020-07-27 | 2020-08-27 | 2021-08-05 | 2021-08-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 28361.93 | 342004.11 | 370366.04 | 55443.95 | 425809.99 | 0 | [6 empty] | SR21_WW | 100%
503654 | SR21 ES Kinneil Kerse SCADA replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2021-03-15 | 2022-11-18 | 2023-03-23 | 2024-10-16 | 2024-12-09 | Falkirk | 0 | 0 | 0 | 0 | 0 | 58677.67 | 35481.94 | 94159.61 | 1305840.46 | 1400000.07 | 0 | [6 empty] | SR21_WW | 100%
503752 | SR21 ES Kinneil Kerse STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-03-12 | 2025-07-15 | 2026-03-09 | 2026-04-30 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 5251.25 | 5251.25 | 964748.8 | 970000.05 | 0 | [6 empty] | SR21_WW | 100%
503754 | SR21 ES Kirkwall STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-03-12 | 2025-07-15 | 2026-03-09 | 2026-04-30 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 17731 | 17731 | 952268.95 | 969999.95 | 0 | [6 empty] | SR21_WW | 100%
503720 | SR21 ES Lamlash DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 | 2019-10-04 | 2019-10-04 | 2020-02-05 | 2020-11-18 | 2021-01-15 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 395325.16 | 158698.58 | 554023.74 | 0 | 554023.74 | 0 | [6 empty] | SR21_WA | 100%
503655 | SR21 ES Lanark STW SCADA replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2021-03-01 | 2022-11-04 | 2023-03-09 | 2024-10-02 | 2024-11-25 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 52240.48 | 48352.33 | 100592.81 | 1299407.25 | 1400000.06 | 0 | [6 empty] | SR21_WW | 100%
503759 | SR21 ES Liberton Trunk Mains | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-10-29 | 2022-08-18 | 2022-11-22 | 2024-08-14 | 2024-10-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 152332.08 | -2332.08 | 150000 | 14849999.93 | 14999999.93 | 0 | [6 empty] | SR21_WA | 100%
504855 | SR21 ES Lintrathen Loch Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Angus | 0 | 0 | 0 | 0 | 0 | 10883.72 | 948.44 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
504856 | SR21 ES Loch Assapol Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 11832.16 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
504857 | SR21 ES Loch Glow Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Fife | 0 | 0 | 0 | 0 | 0 | 10883.72 | 948.44 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503685 | SR21 ES Loch Mhor an Stairr | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2020-07-28 | 2021-07-05 | 2021-09-15 | 2022-04-19 | 2022-07-18 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 20129.92 | 81613.4 | 101743.32 | 1309123.66 | 1410866.98 | 0 | [6 empty] | SR21_WA | 100%
503684 | SR21 ES Loch Riecawr Concrete Repairs | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-10-26 | 2021-10-11 | 2021-12-22 | 2022-07-25 | 2022-10-24 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 11731.77 | 31738.22 | 43469.99 | 256530.01 | 300000 | 0 | [6 empty] | SR21_WA | 100%
503683 | SR21 ES Loch Spallander Spillway Concrete Repairs | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-09-28 | 2021-09-13 | 2021-11-24 | 2022-06-27 | 2022-09-26 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 11731.77 | 32503.23 | 44235 | 255765 | 300000 | 0 | [6 empty] | SR21_WA | 100%
503688 | SR21 ES Loch Venachar MIoS Upgrade | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-07-09 | 2021-01-18 | 2021-03-08 | 2021-11-09 | 2022-08-29 | Stirling | 0 | 0 | 0 | 0 | 0 | 17854.08 | 174954.79 | 192808.87 | 307191.14 | 500000.01 | 0 | [6 empty] | SR21_WA | 100%
504858 | SR21 ES Loch Whinyeon Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 10883.72 | 948.44 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503649 | SR21 ES Lochanbank Farm Pipe Bridge Kirkmuirhill | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS4 | 2020-05-01 | 2021-07-23 | 2021-10-25 | 2020-01-23 | 2022-12-09 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1287.35 | -548.11 | 739.24 | 0 | 739.24 | 0 | [6 empty] | SR21_WW | 100%
504860 | SR21 ES Long Loch Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 10883.72 | 948.44 | 11832.16 | 533621.84 | 545454 | 0 | [6 empty] | SR21_WA | 100%
503734 | SR21 ES Low and High Askomil Mains Rehabilitation (2 No. DMAs) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2019-10-01 | 2021-01-18 | 2021-04-12 | 2021-11-08 | 2021-12-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 20022.38 | 130689.79 | 150712.17 | 309287.84 | 460000.01 | 0 | [6 empty] | SR21_WA | 100%
504971 | SR21 ES Lower Largo Bathing Water Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS0 | 2020-03-16 | 2020-11-09 | 2021-03-16 | 2021-09-14 | 2021-12-15 | Fife | 0 | 0 | 0 | 0 | 0 | 20185.95 | 0 | 20185.95 | 0 | 20185.95 | 0 | [6 empty] | EC16 | 100%
503719 | SR21 ES M1 and C1 WSZ Cluster Various DMAs Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS3 | 2019-10-03 | 2020-03-02 | 2020-03-09 | 2021-05-26 | 2021-07-22 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 141687.14 | 969924.19 | 1111611.33 | 12542.67 | 1124154 | 0 | [6 empty] | SR21_WA | 100%
503735 | SR21 ES Mains of Moyness - Non DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2019-10-01 | 2021-01-04 | 2021-03-16 | 2021-10-12 | 2021-12-03 | Highland | 0 | 0 | 0 | 0 | 0 | 18103.65 | 50008.35 | 68112 | 231887.98 | 299999.98 | 0 | [6 empty] | SR21_WA | 100%
503674 | SR21 ES MCC Priority 1 Condition Surveys | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2019-10-01 | 2021-09-06 | 2021-12-28 | 2022-08-15 | 2022-10-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 32611.9 | 14616 | 47227.9 | 400915.12 | 448143.02 | 0 | [6 empty] | SR21_WW | 100%
503729 | SR21 ES Meikle Tullo WSZ Dykehead DMA - Memus Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS2 | 2019-10-03 | 2020-02-28 | 2020-08-03 | 2021-02-04 | 2021-03-30 | Angus | 0 | 0 | 0 | 0 | 0 | 136370.54 | 343805.67 | 480176.21 | 153.79 | 480330 | 0 | [6 empty] | SR21_WA | 100%
503716 | SR21 ES Mill Glen Breach | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2020-04-02 | 2020-09-28 | 2021-05-31 | 2021-09-20 | 2022-10-14 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 79776 | 820511.16 | 900287.16 | 1414925.13 | 2315212.29 | 0 | [6 empty] | SR21_WA | 100%
503739 | SR21 ES Muir of Ord - Leanaig to Tore DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 | 2019-10-01 | 2019-10-01 | 2019-11-11 | 2021-03-19 | 2021-05-12 | Highland | 0 | 0 | 0 | 0 | 0 | 142498.5 | 414937.24 | 557435.74 | 12564.21 | 569999.95 | 0 | [6 empty] | SR21_WA | 100%
503686 | SR21 ES Munnoch Breach | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-07-09 | 2021-03-29 | 2022-02-01 | 2022-08-31 | 2023-11-20 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 63591.27 | 335962.06 | 399553.33 | 800446.62 | 1199999.95 | 0 | [6 empty] | SR21_WA | 100%
503726 | SR21 ES Neilston and Uplawmoor Rd - Neilston High DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-03 | 2020-05-25 | 2020-07-27 | 2021-09-06 | 2021-10-28 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 88899.52 | 1324510.55 | 1413410.07 | 138265.89 | 1551675.96 | 0 | [6 empty] | SR21_WA | 100%
503714 | SR21 ES North Third | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2020-05-01 | 2020-09-28 | 2021-02-08 | 2021-07-23 | 2021-11-10 | Stirling | 0 | 0 | 0 | 0 | 0 | 74000 | 1248647.65 | 1322647.65 | 677352.37 | 2000000.02 | 0 | [6 empty] | SR21_WA | 100%
503745 | SR21 ES P1 Pipe Bridge Repair-Replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-09-21 | 2021-08-16 | 2021-11-12 | 2022-08-19 | 2022-11-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 94202.48 | 183827.51 | 278029.99 | 1221970.02 | 1500000.01 | 0 | [6 empty] | SR21_WA | 100%
503463 | SR21 ES PMO Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW0 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1046811.03 | 1733188.98 | 2780000.01 | 0 | 2780000.01 | 0 | [6 empty] | SR21_SS | 100%
504558 | SR21 ES Port Charlotte WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-03-04 | 2023-01-19 | 2023-06-29 | 2025-01-09 | 2025-04-11 | - | 0 | 0 | 0 | 0 | 0 | 23042.34 | 656010.8 | 679053.14 | 5320946.83 | 5999999.97 | 0 | [6 empty] | SR21_WA | 100%
503464 | SR21 ES Portfolio Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW0 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 3909782.44 | 3990217.56 | 7900000 | 0 | 7900000 | 0 | [6 empty] | SR21_SS | 100%
503732 | SR21 ES Portree - Braes DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2019-10-02 | 2021-04-26 | 2021-06-28 | 2022-02-18 | 2022-04-13 | Highland | 0 | 0 | 0 | 0 | 0 | 12903.95 | 58353 | 71256.95 | 748743.05 | 820000 | 0 | [6 empty] | SR21_WA | 100%
503664 | SR21 ES PSTN Investigation and Proposals | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS0 | 2019-09-12 | 2020-07-27 | 2020-07-27 | 2021-02-23 | 2021-03-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 462164.93 | 40339 | 502503.93 | 0 | 502503.93 | 0 | [6 empty] | SR21_SS | 100%
503660 | SR21 ES Pumping Mains Inspections Phase 1 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-09-30 | 2021-12-13 | 2022-03-15 | 2023-01-30 | 2023-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 5835.61 | 28836.19 | 34671.8 | 215328.19 | 249999.99 | 0 | [6 empty] | SR21_WW | 100%
503756 | SR21 ES Reservoir Safety Signs West | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS0 | 2019-09-30 | 2021-02-01 | 2021-06-03 | 2022-01-19 | 2022-03-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 22359.49 | 85633.72 | 107993.21 | 732006.79 | 840000 | 0 | [6 empty] | SR21_WA | 100%
503677 | SR21 ES Rosebery | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2020-08-03 | 2021-07-05 | 2021-09-15 | 2022-04-18 | 2022-07-18 | Midlothian | 0 | 0 | 0 | 0 | 0 | 19552.95 | 82190.37 | 101743.32 | 398256.72 | 500000.04 | 0 | [6 empty] | SR21_WA | 100%
503744 | SR21 ES Rosebery WTW Taste & Odour Issues | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-01-29 | 2022-10-21 | 2023-02-10 | 2024-05-13 | 2024-07-04 | Midlothian | 0 | 0 | 0 | 0 | 0 | 125447.1 | 141685.76 | 267132.86 | 3232867.14 | 3500000 | 0 | [6 empty] | SR21_WA | 100%
503741 | SR21 ES SCADA Surveys | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2019-10-01 | 2021-07-08 | 2021-10-26 | 2022-03-08 | 2022-04-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 34113.63 | -13979.63 | 20134 | 104866 | 125000 | 0 | [6 empty] | SR21_WW | 100%
503737 | SR21 ES Stewarton & Machrihanish DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 | 2020-04-01 | 2019-10-04 | 2020-02-18 | 2020-12-10 | 2021-03-22 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 530041.76 | 314102.93 | 844144.69 | 6444.69 | 850589.38 | 0 | [6 empty] | SR21_WA | 100%
503749 | SR21 ES Stirling STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-04-02 | 2025-08-05 | 2026-06-22 | 2026-08-13 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 11596.03 | 11596.03 | 688403.96 | 699999.99 | 0 | [6 empty] | SR21_WW | 100%
503778 | SR21 ES Stoer WOA - Clashnessie DMA and Achnacarnin DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS3 | 2019-10-04 | 2019-10-04 | 2019-11-11 | 2021-07-07 | 2021-07-07 | Highland | 0 | 0 | 0 | 0 | 0 | 238984.71 | 23232.34 | 262217.05 | 317782.94 | 579999.99 | 0 | [6 empty] | SR21_WA | 100%
503730 | SR21 ES Stonebyres DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-01 | 2020-07-20 | 2020-07-31 | 2021-12-16 | 2022-02-07 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 36022.43 | 244817.03 | 280839.46 | 319160.54 | 600000 | 0 | [6 empty] | SR21_WA | 100%
503753 | SR21 ES Thurso STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-03-12 | 2025-07-15 | 2026-03-09 | 2026-04-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 15515.7 | 15515.7 | 814484.32 | 830000.02 | 0 | [6 empty] | SR21_WW | 100%
504393 | SR21 ES Tighnabruaich WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2020-11-09 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 14093.03 | 487251.07 | 501344.1 | 3498655.83 | 3999999.93 | 0 | [6 empty] | SR21_WA | 100%
504557 | SR21 ES Torra WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-03-29 | 2023-02-13 | 2023-07-24 | 2025-02-03 | 2025-05-06 | - | 0 | 0 | 0 | 0 | 0 | 33636.64 | 1619441.89 | 1653078.53 | 13346921.57 | 15000000.1 | 0 | [6 empty] | SR21_WA | 100%
503751 | SR21 ES Underwood Cumnock STC - Capital Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2023-12-07 | 2025-03-12 | 2025-07-15 | 2026-03-09 | 2026-04-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 3735.43 | 3735.43 | 686264.57 | 690000 | 0 | [6 empty] | SR21_WW | 100%
503462 | SR21 ES Waste Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW0 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1371139.94 | 5328860.05 | 6699999.99 | 0 | 6699999.99 | 0 | [6 empty] | SR21_SS | 100%
504208 | SR21 ES Water MCC Replacement | Q&S4 | Sustaining existing high service for customers | Water non infrastructure |  |  | General |  | SWD | Water non infrastructure | MSU | 2020-08-14 | 2022-02-14 | 2022-06-15 | 2023-02-08 | 2023-05-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 8570.28 | 135159.72 | 143730 | 0 | 143730 | 0 | [6 empty] | SR15_CMA_WSNI | 100%
503461 | SR21 ES Water Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW0 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 2277335.35 | 4222664.64 | 6499999.99 | 0 | 6499999.99 | 0 | [6 empty] | SR21_SS | 100%
504996 | SR21 ES Water Supply Strategy Review Session | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2020-10-07 | 2021-10-11 | 2022-02-09 | 2023-10-04 | 2024-01-04 | - | 0 | 0 | 0 | 0 | 0 | 20000 | 80000 | 100000 | 0 | 100000 | 0 | [6 empty] | SR21_WA | 100%
503724 | SR21 ES Westmuir - Kingoldrum DMA Mains Rehabilitation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS3 | 2019-10-03 | 2020-03-17 | 2020-03-30 | 2021-06-14 | 2021-08-04 | Angus | 0 | 0 | 0 | 0 | 0 | 147693.32 | 451523.54 | 599216.86 | 5591.14 | 604808 | 0 | [6 empty] | SR21_WA | 100%
504553 | SR21 ES Winterhope WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-02-26 | 2023-01-19 | 2023-06-29 | 2025-01-09 | 2025-04-11 | - | 0 | 0 | 0 | 0 | 0 | 23456.22 | 972819.89 | 996276.11 | 8003723.87 | 8999999.98 | 0 | [6 empty] | SR21_WA | 100%
503610 | SR21 ES_Inverness WOA - Nairnside mains rehab | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 | 2019-07-30 | 2019-07-30 | 2019-09-30 | 2020-06-09 | 2020-06-09 | Highland | 0 | 0 | 0 | 0 | 0 | 271345 | 95536.83 | 366881.83 | 3118.17 | 370000 | 0 | [6 empty] | SR21_WA | 100%
503613 | SR21 ES_Loch Calder WOA - Roster Occumster Mains Rehab | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | WINF | SR21 Early Start | MS0 | 2019-10-03 | 2020-07-06 | 2020-07-13 | 2021-02-11 | 2021-04-06 | Highland | 0 | 0 | 0 | 0 | 0 | 74509.6 | 1232490.4 | 1307000 | 0 | 1307000 | 0 | [6 empty] | SR21_WA | 100%
503642 | SR21 Garnock Water Pipe Bridge Dalry Road Kilwinning | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-11-20 | 2022-02-02 | 2022-04-28 | 2023-03-31 | 2023-06-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 11307.99 | 20359.27 | 31667.26 | 218332.78 | 250000.04 | 0 | [6 empty] | SR21_WW | 100%
503645 | SR21 Glen Ave Pipe Bridge Cumnock | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2020-12-11 | 2022-03-04 | 2022-06-06 | 2023-04-14 | 2023-07-14 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 21458.05 | 54123.96 | 75582.01 | 824417.98 | 899999.99 | 0 | [6 empty] | SR21_WW | 100%
503648 | SR21 Kirkhouse Burn Killearn Pipe Bridges | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-11-13 | 2021-12-29 | 2022-03-31 | 2023-02-15 | 2023-05-17 | Stirling | 0 | 0 | 0 | 0 | 0 | 14417.77 | 53668.15 | 68085.92 | 551914.11 | 620000.03 | 0 | [6 empty] | SR21_WW | 100%
503776 | SR21 Legacy Sludge - Big Breck STC Quarry and Drying Beds | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-31 | 2023-09-14 | 2024-01-12 | 2025-07-10 | 2025-09-02 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5834000.01 | 5834000.01 | 0 | [6 empty] | SR21_WA | 100%
503774 | SR21 Legacy Sludge - Cupar STC Sludge Beds | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | 2021-12-31 | 2023-08-24 | 2024-01-10 | 2025-04-15 | 2025-06-06 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4697000.01 | 4697000.01 | 0 | [6 empty] | SR21_WW | 100%
503777 | SR21 Legacy Sludge - Invercannie WTW Lagoons | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-31 | 2023-06-01 | 2023-10-04 | 2024-10-15 | 2024-12-06 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1998000.02 | 1998000.02 | 0 | [6 empty] | SR21_WA | 100%
503775 | SR21 Legacy Sludge - Loch Eck WTW Lagoons | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-31 | 2023-09-14 | 2024-01-12 | 2025-04-17 | 2025-06-10 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 520 | -520 | 0 | 2964000.01 | 2964000.01 | 0 | [6 empty] | SR21_WA | 100%
503773 | SR21 Legacy Sludge - Westray STC Lunnon Quarry and Drying Beds | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-31 | 2023-06-22 | 2023-10-25 | 2024-10-22 | 2024-12-13 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245000 | 1245000 | 0 | [6 empty] | SR21_WA | 100%
503767 | SR21 Mannofield WTW inlet improvements | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MSU | 2020-10-02 | 2022-01-31 | 2022-05-26 | 2023-05-22 | 2023-07-13 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 197.05 | 153321.44 | 153518.49 | 1142505.01 | 1296023.5 | 1295905.08 | [6 empty] | DW23 | 100%
503650 | SR21 South Calder Water Riverside Walk Motherwell | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-09-04 | 2021-04-16 | 2021-06-14 | 2021-07-23 | 2021-09-15 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 24907.72 | 152542.29 | 177450.01 | 422550 | 600000.01 | 0 | [6 empty] | SR21_WW | 100%
503652 | SR21 Toll Bridge Eyemouth Rising Main Pipe Bridge | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2020-11-13 | 2021-12-29 | 2022-03-31 | 2023-02-15 | 2023-05-17 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 12467.42 | 53389.91 | 65857.33 | 534142.66 | 599999.99 | 0 | [6 empty] | SR21_WW | 100%
503644 | SR21 Tulloch Road Perth | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-01-22 | 2021-12-23 | 2022-03-18 | 2022-09-13 | 2022-12-13 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 10924.13 | 21293.48 | 32217.61 | 87782.39 | 120000 | 0 | [6 empty] | SR21_WW | 100%
502925 | SR21 Wastewater Business Plan Development | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2029-04-02 | 2028-03-27 | 2028-03-27 | 2028-03-27 | 2028-03-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | [6 empty] | CM_WWI | 100%
503628 | SR21ES Herricks WTW upgrade | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2020-07-02 | 2022-03-28 | 2022-07-28 | 2024-03-28 | 2024-05-21 | Moray | 0 | 0 | 0 | 0 | 0 | 149469.04 | 129338.65 | 278807.69 | 13721192.29 | 13999999.98 | 0 | [6 empty] | SR21_WA | 100%
500084 | SR-TM Meters - New | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-05-10 | 2021-05-10 | Scottish Water Wide | 0 | 385150 | 293876 | 169763.36 | 231610.64 | 319884 | 223434 | 1623718 | 0 | 1623718 | 0 | [6 empty] | CM_WSI | 100%
500085 | SR-TM Meters - Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-25 | 2015-03-25 | 2021-05-10 | 2021-05-10 | Scottish Water Wide | 0 | 260879 | 101882 | 200992 | 196164 | 151444 | 159524 | 1070885 | 0 | 1070885 | 0 | [6 empty] | CM_WSI | 100%
503588 | SSD - SW support of Profibus remedial works | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | GW2 | 2020-12-04 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 138642.42 | 61357.55 | 199999.97 | 0 | 199999.97 | 0 | [6 empty] | CM_WSNI | 30% | CM_WWNI | 70%
503999 | S-S-NI-271119-Daer WTW - Redundant settlement tank fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 11374.63 | -374.63 | 11000 | 0 | 11000 | 0 | [6 empty] | CM_WSNI | 100%
500173 | St Andrews DOA (DOA000247) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2019-03-27 | 2019-07-31 | Fife | 0 | 13937 | 153569.12 | 83863.88 | 71014 | 37043.39 | 0.09 | 359427.48 | 0 | 359427.48 | 45716.78 | [6 empty] | EC01D | 12.3% | EC01G | 17.1% | CS16D | 33.63% | EC10E | 36.97%
502814 | St Andrews WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-04-09 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Fife | 0 | 0 | 0 | 97236.65 | 36451.59 | 4862.53 | 17176.57 | 155727.34 | 608272.64 | 763999.98 | 136478.56 | [6 empty] | SG1 | 100%
500695 | St Andrews WwTW & St Andrews STC SR15-CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-06-30 | 2018-09-18 | 2019-03-29 | 2020-07-24 | 2020-10-22 | Fife | 0 | 130610 | 46330.1 | 122609.4 | 398068.48 | 873025.02 | 103636.88 | 1674279.88 | 5603.12 | 1679883 | 0 | [6 empty] | CM_WWNI | 100%
500174 | St Boswells DOA (DOA000039) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2017-02-27 | 2017-02-27 | 2017-03-31 | 2017-03-31 | Scottish Borders | 0 | 13526 | 7500 | -8014.76 | 0 | 0 | 0 | 13011.24 | 0 | 13011.24 | 82349.38 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
505049 | St Fergus Scotston WWPS rising main repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-02-28 |  | 2020-03-31 | 2020-05-07 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 108951.33 | -179.33 | 108772 | 0 | 108772 | 0 | [6 empty] | CM_WWNI | 100%
502428 | St Fort Road Outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2016-11-21 | 2018-01-29 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Fife | 0 | 0 | 9239.06 | 93697.94 | 76740 | 0 | 0 | 179677 | 0 | 179677 | 30997.67 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
500577 | St Margarets Hope WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | Orkney Islands | 0 | 24641.68 | 6457.9 | 841.89 | 35.22 | 0 | 0 | 31976.69 | 0 | 31976.69 | 136478.56 | [6 empty] | SG1 | 100%
500055 | St Marys Loch Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2015-02-18 | 2015-03-09 | 2015-03-09 | 2015-11-30 | 2016-03-31 | Scottish Borders | 4670 | 223830 | 153.53 | 0 | 0 | 0 | 0 | 223983.53 | 0 | 228653.53 | 346337.12 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
402748 | St Marys ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-07-20 | 2014-10-30 | 2014-11-24 | 2016-07-29 | 2016-07-29 | Orkney Islands | 175129 | 79634 | 65000 | 0 | -1821.48 | 0 | 1821.48 | 144634 | 0 | 319763 | 0 | [6 empty] | SG1 | 100%
500175 | St Monans DOA (DOA000252) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-30 | 2018-01-30 | Fife | 0 | 64064 | 54379 | 12620 | 123.85 | 0 | 0 | 131186.85 | 0 | 131186.85 | 142324.28 | [6 empty] | EC01G | 4.722% | CS11 | 22.55% | CS16D | 27.6% | EC01D | 45.13%
501817 | St Monans WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Fife | 0 | 10465 | 0.12 | 0 | 0 | 0 | 0 | 10465.12 | 0 | 10465.12 | 136478.56 | [6 empty] | SG1 | 100%
503476 | St Vigeans Avenue Newton Mearns | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2019-02-20 | 2019-02-20 | 2019-02-21 | 2019-03-14 | 2019-03-14 | East Renfrewshire | 0 | 0 | 0 | 0 | 45732.77 | 3853.8 | 0 | 49586.57 | 0 | 49586.57 | 5935596.51 | [6 empty] | CS16WR | 100%
500876 | Staffin Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-08-19 | 2018-11-21 | 2018-11-21 | 2018-11-30 | 2018-11-30 | Highland | 0 | 1267.34 | 2229.31 | 4197.8 | -4197.8 | 0 | 0 | 3496.65 | 0 | 3496.65 | 77494.38 | [6 empty] | DW5FS | 100%
500752 | Staffin WTW CWT Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-08-25 | 2017-05-12 | 2017-07-31 | 2018-08-30 | 2018-08-30 | Highland | 0 | 93419 | 136262.78 | 681176.41 | 156789.76 | 69.05 | 0 | 1067717 | 0 | 1067717 | 0 | [6 empty] | CM_WSNI | 100%
45416 | Staffin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2011-11-14 | 2016-06-21 | 2016-06-29 | Highland | 2709580.83 | 531173.1 | 422069.57 | 0 | 45945.79 | 25985.99 | 0 | 1025174.45 | 0 | 3734755.28 | 589524 |  |  |  |  | 20540 |  | DW23 | 100%
400928 | Stakeholder Management - Liasion of MGSDP and GSS Project | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-21 | 2013-05-08 | 2013-05-09 | 2018-06-22 | 2011-03-14 | Glasgow City | 266000 | 9001 | 0 | 0 | -6589.08 | 0 | -312.96 | 2098.96 | 0 | 268098.96 | 0 | [6 empty] | EC01D | 33.33% | EC04C | 33.33% | EC10E | 33.33%
500104 | Standby Generators Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-05-19 | 2016-03-29 | 2016-04-19 | 2020-01-14 | 2020-01-14 | Scottish Water Wide | 0 | 540169 | 976312.31 | 1088756.86 | 367321.28 | 348309.14 | 85256.28 | 3406124.87 | 1077.25 | 3407202.12 | 0 | [6 empty] | CM_WSNI | 100%
502337 | Standby Generators Phase 2A Multiple Sites East & North Mobile & Seasonal Hired | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-09-23 | 2018-10-25 | 2019-01-28 | 2021-01-07 | 2021-04-09 | Scottish Water Wide | 0 | 0 | 8307.47 | 225073.04 | 353804.88 | 1045986.19 | 1310296.16 | 2943467.74 | 29142.03 | 2972609.77 | 0 |  |  |  |  | 43700 |  | CM_WSNI | 100%
501687 | Standby Generators Phase 2B East & North Fixed Units | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2017-11-15 | 2027-09-15 | 2028-01-10 | 2029-03-28 | 2029-03-28 | Scottish Water Wide | 0 | 0 | 12087.64 | 60587.36 | 364733.73 | 735.34 | -735.34 | 437408.73 | 6022030.43 | 6459439.16 | 0 | [6 empty] | CM_WSNI | 100%
402867 | Stanely Reservoir -Installation of Drawdown Facility & Emergency Plan | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-21 | 2012-11-27 | 2013-02-25 | 2014-11-05 | 2014-11-05 | Renfrewshire | 237484 | 7170.37 | 0 | 0 | 0 | 0 | 0 | 7170.37 | 0 | 244654.37 | 0 | [6 empty] | CM_WSI | 100%
501339 | STANELY SR | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-03 | 2028-08-17 | 2028-12-21 | 2030-03-20 | 2030-06-20 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9300000.03 | 9300000.03 | 0 | [6 empty] | CM_WSNI | 100%
502763 | Stanley WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-06-30 | 2022-11-15 | 2023-03-16 | 2024-03-05 | 2024-06-05 | Perth and Kinross | 0 | 0 | 0 | 36725.76 | 31403.75 | 7998.13 | 189889.87 | 266017.51 | 7123982.51 | 7390000.02 | 136478.56 | [6 empty] | SG1 | 100%
501703 | Station Rd - Nairn Rd Ardersier - replace sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2018-08-27 | 2028-01-13 | 2028-04-05 | 2028-07-25 | 2028-10-25 | Highland | 0 | 0 | 2418.28 | 7529.5 | 7923.92 | 0 | -2860.37 | 15011.33 | 598795 | 613806.33 | 0 | [6 empty] | CM_WWI | 100%
400926 | Station Road Plockton External Flooding - Sewer Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-31 | 2011-10-31 | 2012-10-31 | 2013-06-20 |  | Highland | 386000 | -1048.5 | 0 | 0 | 0 | 0 | 0 | -1048.5 | 0 | 384951.5 | 0 | [6 empty] | CM_WWI | 100%
402168 | Stenness Village WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-06-13 | 2014-03-17 | 2014-05-28 | 2014-11-27 |  | Orkney Islands | 29749 | 694.46 | 0 | 0 | 0 | 0 | 0 | 694.46 | 0 | 30443.46 | 0 | [6 empty] | CM_WWNI | 100%
504387 | Stevenston DOA - Sewer Inspection | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | GW1 |  | 2020-06-08 | 2020-09-11 | 2021-04-08 | 2021-04-09 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 4566.1 | 14932.75 | 19498.85 | 501.15 | 20000 | 0 | [6 empty] | WWI | 100%
500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS4 | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-03-09 | 2020-08-06 | North Ayrshire | 0 | 58109 | 284709 | 290872.61 | 273798.39 | 134491.93 | 18749.07 | 1060730 | 0 | 1060730 | 410312.28 | [6 empty] | EC01G | 0.35% | EC01D | 1.33% | EC10E | 5.65% | CS11 | 20.23% | CS16D | 72.44%
403513 | Stevenston Point - Inlet Works Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2016-06-30 |  | North Ayrshire | 519494.81 | 25000.19 | -23678.78 | 0 | 0 | 0 | 0 | 1321.41 | 0 | 520816.22 | 0 | [6 empty] | CM_WWNI | 100%
502779 | Stevenston Point Headworks Coarse Screens CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2017-06-20 | 2020-04-06 | 2020-07-07 | 2021-02-19 | 2021-02-22 | North Ayrshire | 0 | 0 | 0 | 3207.75 | 135734.43 | 50723.94 | 0 | 189666.12 | 0 | 189666.12 | 0 | [6 empty] | CM_WWNI | 100%
500932 | Stevenston Point Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | North Ayrshire | 0 | 6000 | 2000 | -4075.53 | 0 | 0 | 0 | 3924.47 | 0 | 3924.47 | 120964.87 | [6 empty] | CS15A | 100%
501518 | STEVENSTON POINT WWTW NS275404 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-09-05 | 2019-03-13 | 2019-03-28 | 2021-01-29 | 2021-05-18 | North Ayrshire | 0 | 0 | 16616.29 | 334708.33 | 774930.14 | 2961157.88 | 1859798.58 | 5947211.22 | 31319.58 | 5978530.8 | 0 | [6 empty] | CM_WWNI | 100%
502249 | Stewart Drive Stornoway | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2017-06-29 | 2027-04-05 | 2027-06-02 | 2027-09-03 | 2027-12-06 | Na H-Eileanan an Iar | 0 | 0 | 16665.34 | 3766.06 | 9462.41 | 4955.77 | 0 | 34849.58 | 329043.43 | 363893.01 | 0 | [6 empty] | CM_WWI | 100%
502617 | Stewarton & Machrihanish DMA - Machrihanish Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2018-07-31 | 2019-09-18 | 2019-11-14 | 2020-03-03 | 2020-08-18 | Argyll and Bute-North Argyll | 0 | 0 | 18400 | 409.92 | 26024.95 | -43547.93 | 0 | 1286.94 | 0 | 1286.94 | 0 | [6 empty] | CM_WSI | 100%
500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-01-31 | 2019-06-18 | East Ayrshire | 0 | 12315 | 39020 | 83759.78 | 66446.63 | 8368.57 | 0 | 209909.98 | 0 | 209909.98 | 74991.76 | [6 empty] | EC01G | 0.9528% | EC10E | 21.91% | EC01D | 31.88% | CS16D | 45.26%
45019 | Stewarton STW Refurb - STW000671 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-13 | 2012-09-26 | 2013-01-14 | 2014-01-06 | 2014-04-17 | East Ayrshire | 1773514.9 | 1356.47 | 0 | 0 | 0 | 0 | 0 | 1356.47 | 0 | 1774871.37 | 0 | [6 empty] | CM_WWNI | 100%
403939 | Stewarton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2018-06-13 | 2020-04-03 | 2020-03-30 | 2021-03-26 | 2021-03-29 | East Ayrshire | 0 | 21902 | 20763.9 | 29496.67 | 27638.26 | 427392.7 | 2118724.83 | 2645918.36 | 814131.64 | 3460050 | 0 | [6 empty] | SG1 | 100%
502216 | Stichill ST Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2017-04-28 | 2019-02-12 | 2019-05-13 | 2020-03-19 | 2020-04-01 | Scottish Borders | 0 | 0 | 20488.01 | 87105.99 | 207009 | 597856 | 0 | 912459 | 2250 | 914709 | 0 | [6 empty] | CM_WWI | 100%
500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS5 | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-08-29 | 2020-03-11 | Stirling | 0 | 36395 | 167369 | 89745 | 125000 | 78597 | 24698 | 521804 | 0 | 521804 | 287748.65 | [6 empty] | EC01G | 16.49% | CS16D | 83.51%
402779 | Stirling Falkirk Yr 3 Promotion Health and Safety needs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-27 | 2012-06-27 | 2012-08-01 | 2016-05-19 |  | Stirling | 406809.05 | 26858.71 | 0 | 0 | 0 | 0 | 0 | 26858.71 | 0 | 433667.76 | 0 | [6 empty] | CM_WWNI | 100%
500933 | Stirling Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-11-04 | 2016-11-04 | 2016-10-25 | 2016-11-04 | Stirling | 0 | 6000 | -918.81 | 0 | 0 | 0 | 0 | 5081.19 | 0 | 5081.19 | 120964.87 | [6 empty] | CS15A | 100%
403542 | Stirling Villages WwTWs - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-04-01 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2015-04-13 | Stirling | 57217.35 | 2276.45 | 0 | 0 | 0 | 0 | 0 | 2276.45 | 0 | 59493.8 | 0 | [6 empty] | SG1 | 100%
403656 | Stobsmuir Dundee | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2014-01-23 | 2014-01-23 | 2014-01-23 | 2015-02-05 |  | Dundee City | 40000 | -4807.02 | 0 | 0 | 0 | 0 | 0 | -4807.02 | 0 | 35192.98 | 0 | [6 empty] | CM_M&G | 100%
30909 | Stonehouse STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-09-20 | 2010-11-29 | 2015-03-25 | 2015-03-31 | South Lanarkshire | 3384163.86 | -1850.83 | -15828.93 | 10 | 0 | 0 | 0 | -17669.76 | 0 | 3366494.1 | -144.16 | [6 empty] | CM_WWNI | 30.06% | EC04A | 69.94%
501560 | Storm Tank Cleaning - Network Capacity Restoration Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2017-03-28 | 2017-03-29 | 2019-01-30 | 2019-01-30 | Scottish Water Wide | 0 | 3271.03 | -3271.03 | 585229.18 | 488936.63 | 13451.08 | -18.47 | 1087598.42 | 0 | 1087598.42 | 0 | [6 empty] | CM_WWI | 100%
501559 | Storm Tank Cleaning - Treatment Capacity Restoration Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2016-02-22 | 2016-04-18 | 2016-04-18 | 2018-01-24 | 2018-01-24 | Scottish Water Wide | 0 | 47647.82 | 256245.64 | 6106.54 | 141.11 | 181345.58 | 8513.32 | 500000.01 | 0 | 500000.01 | 0 | [6 empty] | CM_WWNI | 100%
502230 | Stornoway DOA Saline Intrusion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-05 | 2017-10-25 | Na H-Eileanan an Iar | 0 | 0 | 29318.35 | 3748.32 | 0 | 0 | -44.67 | 33022 | 0 | 33022 | 0 | [6 empty] | CM_WWI | 100%
403040 | Stornoway WOA - North Lochs Augmentation Line - Airiadh Na Lic tanks to Marybank PS - (Stage 2) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-12-13 | 2014-02-11 | 2014-09-01 |  | Na H-Eileanan an Iar | 60675.52 | 1662.48 | -198.03 | 0 | 0 | 0 | 0 | 1464.45 | 0 | 62139.97 | 0 | [6 empty] | CM_WSI | 100%
503421 | Stornoway WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2018-10-31 | 2020-08-17 | 2020-09-14 | 2021-04-22 | 2021-07-09 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 15992.7 | 98396.68 | 1134864.97 | 1249254.35 | 247727.56 | 1496981.91 | 0 | [6 empty] | CM_WSNI | 100%
46842 | Storr Forest WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2013-01-30 | 2015-01-13 | 2015-01-13 | 2015-01-13 | Highland | 1195343.9 | 1096.16 | 0 | 0 | 0 | 0 | 0 | 1096.16 | 0 | 1196440.06 | 0 | [6 empty] | DW23 | 100%
45556 | Stow STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-21 | 2011-07-29 | 2011-10-20 | 2011-11-28 | South Lanarkshire | 158832.66 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 159582.66 | 0 | [6 empty] | WQ01 | 100%
502829 | Strabathie ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-07-05 | 2022-07-15 | 2022-11-07 | 2023-10-26 | 2024-01-26 | Aberdeen City | 0 | 0 | 0 | 64381.93 | 32910.79 | 22897.31 | 20719.41 | 140909.44 | 2589090.51 | 2729999.95 | 136478.56 | [6 empty] | SG1 | 100%
501488 | STRAN LARG ROAD WWPS(No 1) NX048623 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS1 | 2016-07-19 | 2020-05-18 | 2020-07-24 | 2020-12-10 | 2020-12-10 | Dumfries and Galloway | 0 | 0 | 36764 | 127915 | 37261 | 182004 | 655051.59 | 1038995.59 | 48938.27 | 1087933.86 | 0 |  |  |  |  | 10000 |  | CM_WWNI | 100%
400097 | Stranraer Catchment UID Improvements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2011-10-13 | 2012-01-16 | 2013-03-12 | 2013-03-29 | Dumfries and Galloway | 240483 | -3079.97 | 0 | 0 | 0 | 0 | 0 | -3079.97 | 0 | 237403.03 | 0 | [6 empty] | EC01C | 35.24% | EC01B | 64.76%
402629 | Stranraer Catchment UID Improvements - Chevron Lochview Road Bishopburn Storm Overflow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-03-23 | 2012-08-24 | 2012-10-22 | 2013-03-28 | 2013-03-28 | Dumfries and Galloway | 1074575 | 18325 | 1362 | -2818.2 | 0 | 0 | 0 | 16868.8 | 0 | 1091443.8 | 33240.05 | [6 empty] | CS11A | 4.398% | CM_WWI | 26.13% | EC01B | 69.47%
402004 | Stranraer Catchment UID Improvements (Complex Solutions) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-21 | 2012-03-27 | 2012-05-21 | 2014-03-31 | 2014-02-14 | Dumfries and Galloway | 1530026 | 0 | 3244 | -574.62 | 0 | 0 | 0 | 2669.38 | 0 | 1532695.38 | 0 | [6 empty] | EC01B | 100%
50018 | Strategic Capacity SG1 Adjustment | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS2 |  | 2018-04-01 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG1 | 100%
402130 | Strategic Drainage Impact Assessment for Old Dalkeith Road Edinburgh | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2011-07-19 | 2011-08-18 | 2011-08-18 | 2011-12-09 |  | City of Edinburgh | 13656.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13656.78 | 0 | [6 empty] | SG5 | 100%
500014 | Strategic Infrastructure - Bradan Pipe Inspection | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-01 | 2028-08-23 | 2028-12-15 | 2030-03-11 | 2030-06-26 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2447845.06 | 2447845.06 | 0 | [6 empty] | CM_WSI | 100%
503532 | Strategic Lead Sampling Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-03-26 | 2019-03-26 | 2019-08-12 | 2021-05-31 | 2021-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 20934.58 | 78732.8 | 176137.06 | 275804.44 | 44325 | 320129.44 | 19191.74 | [6 empty] | DW25TS | 100%
501784 | Strategic Network Modelling | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-05-03 | 2022-09-21 | 2023-01-25 | 2024-04-23 | 2024-07-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | 0 | [6 empty] | CM_WWI | 100%
30913 | Strathaven STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-09-20 | 2010-11-29 | 2012-03-16 | 2012-03-21 | South Lanarkshire | 1421096.89 | 256.56 | 0 | 0 | 0 | 0 | 0 | 256.56 | 0 | 1421353.45 | 0 | [6 empty] | CM_WWNI | 25% | EC10A | 75%
503274 | Strathaven WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2020-04-01 | 2020-05-20 | 2020-05-20 | 2020-05-27 | 2020-05-28 | South Lanarkshire | 0 | 0 | 0 | 0 | 78644.4 | 814.07 | -814.07 | 78644.4 | 0 | 78644.4 | 136478.56 | [6 empty] | SG1 | 100%
501365 | STRATHBLANE WWTW NS547801 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-07-11 | 2028-06-20 | 2028-06-20 | 2028-11-07 | 2028-11-07 | Stirling | 0 | 0 | 61666.51 | 157031.29 | -13994.03 | 0 | 0 | 204703.77 | 993752.21 | 1198455.98 | 0 | [6 empty] | CM_WWNI | 100%
500110 | Strathclyde Loch Bathing Water Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 6834 | 60093.09 | 110167.91 | 246119 | 134844.37 | -0.04 | 558058.33 | 0 | 558058.33 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
45805 | Strathclyde Park SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2012-02-21 | 2012-07-31 | 2013-03-22 | 2013-03-22 | North Lanarkshire | 865314.3 | -1126.52 | 0 | 0 | 0 | 0 | 0 | -1126.52 | 0 | 864187.78 | 0 | [6 empty] | CM_WWNI | 10% | WQ01C | 90%
45557 | Strathmiglo STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2010-09-20 | 2011-07-07 | 2012-03-15 | 2012-03-26 | Fife | 880246.03 | 63492.33 | 0 | 0 | 0 | 0 | 0 | 63492.33 | 0 | 943738.36 | 0 | [6 empty] | CM_WWNI | 40% | WQ01 | 60%
501590 | Strathpeffer - Spa Pavillion Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-06-29 | 2017-09-12 | 2018-01-22 | 2020-06-01 | 2020-06-01 | Highland | 0 | 0 | 21107 | 403681 | 64765 | 10298 | 0 | 499851 | 0 | 499851 | 0 | [6 empty] | CM_WWI | 100%
45369 | Strathyre WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2012-07-29 | 2015-03-06 | Stirling | 211152.95 | 40.93 | 0 | 0 | 0 | 0 | 0 | 40.93 | 0 | 211193.88 | 0 | [6 empty] | DW13 | 100%
46846 | Strollamus WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-05-25 | 2012-06-25 | 2012-08-02 | 2012-09-05 | Highland | 163858.09 | 2506.89 | 0 | 0 | 0 | 0 | 0 | 2506.89 | 0 | 166364.98 | 0 | [6 empty] | DW23 | 100%
403938 | Stromness UWWTW (Transfer from 400089) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | WWINF | Non OMG180 | MS6 | 2009-11-16 | 2015-10-29 | 2015-11-23 | 2018-02-23 | 2018-03-02 | Orkney Islands | 96078.05 | 3722788.95 | 4047033 | 537937 | 31163 | 0 | 0 | 8338921.95 | 0 | 8435000 | 8757358.12 | [6 empty] | CM_WWI | 8% | EC01A | 92%
400089 | Stromness UWWTW Improvements Phase 3 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-11-16 | 2015-03-23 | 2014-12-01 | 2014-12-01 | 2015-02-03 | Orkney Islands | 1710547.5 | 1717.3 | -4686.13 | 20.8 | 0 | 0 | 0.01 | -2948.02 | 0 | 1707599.48 | 0 | [6 empty] | EC01A | 100%
500877 | Stronsay RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Orkney Islands | 0 | 1392.07 | 2846.53 | 4955.33 | -4955.33 | 0 | 0 | 4238.6 | 0 | 4238.6 | 89419.4 | [6 empty] | DW5FS | 100%
501092 | Stronsay WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-10-28 | 2018-03-16 | 2018-03-27 | 2020-07-31 | 2020-10-31 | Orkney Islands | 0 | 27114.34 | 73480.8 | 514856.22 | 2447921.68 | 1041194.05 | 91596.91 | 4196164 | 48477 | 4244641 | 3614665.71 |  |  |  |  | 2747.93 |  | DW25P | 100% | bar: Regulatory Outputs OMG-04
500878 | Strontian RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-10-28 | 2018-09-27 | 2018-12-04 | 2019-03-31 | 2019-08-31 | Highland | 0 | 691.03 | 1308.97 | 3005.65 | 13696.33 | 6073.88 | 0 | 24775.86 | 0 | 24775.86 | 36779.09 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 10.71
45370 | Strontian WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-18 | 2011-07-22 | 2012-02-09 | 2012-03-14 | Highland | 189878.28 | 670.2 | 0 | 0 | 0 | 0 | 0 | 670.2 | 0 | 190548.48 | 0 | [6 empty] | DW13 | 100%
505543 | Structural Condition of Drumboyhill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-06 |  | 2020-08-01 | 2020-09-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 2616.82 | 37383.18 | 40000 | 0 | 40000 | 0 | [6 empty] | WSNI | 100%
501553 | Structural-Strategic Mains- SWD interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-23 | 2016-02-23 | 2016-04-01 | 2017-08-15 | 2017-08-15 | Scottish Water Wide | 0 | 99367.08 | 187182.91 | 4996.8 | 0 | 0 | 0 | 291546.79 | 0 | 291546.79 | 0 | [6 empty] | CM_WSI | 100%
500809 | Stuartfield WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2018-04-16 | 2021-12-13 | 2022-05-02 | 2023-07-21 | 2023-10-20 | Aberdeenshire | 0 | 21343.43 | 78503.63 | 31227.73 | 23929.21 | 98666.89 | 74043.6 | 327714.49 | 1647660.87 | 1975375.36 | 136478.56 | [6 empty] | CM_WWNI | 1% | SG1 | 99%
500212 | Suainaval Western Isles- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-04-25 | 2016-06-20 | 2017-03-31 | 2018-06-30 | Na H-Eileanan an Iar | 0 | 422.12 | 32168.73 | -10634.73 | 1360 | -4845.4 | 550.7 | 19021.42 | 0 | 19021.42 | 39674.04 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500879 | Suainaval Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-31 | 2016-03-31 | 2016-07-18 | 2017-01-31 | 2017-11-30 | Na H-Eileanan an Iar | 0 | 2783.36 | 13967.64 | 21110.69 | 1137.95 | 487.61 | -275.2 | 39212.05 | 0 | 39212.05 | 11740.11 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.69
501647 | Sub-sea Pipeline Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2017-04-20 | 2017-08-10 | 2017-09-08 | 2018-01-30 | 2018-02-14 | Scottish Water Wide | 0 | 0 | 0 | 188568.53 | 102.9 | 0 | 0 | 188671.43 | 0 | 188671.43 | 0 | [6 empty] | CM_M&G | 100%
502795 | Suffolkhill Avenue Dumfries - Sewer Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-07-26 | 2017-07-26 | 2017-12-04 | 2018-05-24 | 2018-05-24 | Dumfries and Galloway | 0 | 0 | 0 | 383643 | 138894.41 | -185.99 | 0 | 522351.42 | 0 | 522351.42 | 0 | [6 empty] | CM_WWI | 100%
46231 | Sunnyside Fortrose and Rosemarkie CCTV and Pipe Refurb | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2008-10-01 | 2019-02-05 | 2019-02-01 | 2019-02-01 | 2017-09-15 | Highland | 60708.56 | 0.44 | 0 | 0 | 0 | 0 | 0 | 0.44 | 0 | 60709 | 0 | [6 empty] | CM_WWI | 100%
50008 | Supplier Rebates Finance - SR15 - 2016-17 | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MS3 | 2017-03-31 | 2017-03-31 | 2017-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | -10383243 | 0 | 0 | 0 | 0 | -10383243 | 0 | -10383243 | 0 | [6 empty] | SR15_DWA_PRE | 0.009351% | SR15_DWA_LEAK | 0.01524% | SR15_SEW_SWO | 0.02105% | SR15_ENV_RBWD | 0.03286% | SR15_DWA_EFA | 0.03337% | SR15_ENV_CAS | 0.04926% | SR15_ENV_WFD | 0.06576% | SR15_CCH_CC | 0.0748% | SR15_COS_REN | 0.08905% | SR15_ENV_SLU | 0.09834%
50013 | Supplier Rebates Finance - SR15 - 2017-18 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MS3 | 2017-04-01 | 2017-04-01 | 2017-04-01 |  |  | Scottish Water Wide | 0 | 0 | 0 | -7474506.12 | 0 | 0 | 0 | -7474506.12 | 0 | -7474506.12 | 0 | [6 empty] | WG3 | 0.00211% | SR15_DWA_LEAK | 0.0154% | SR15_DWQ_FUT | 0.02205% | SR15_DWA_PRE | 0.02408% | SR15_DWA_EFA | 0.02429% | SR15_CEX_IT | 0.03021% | SR15_ENV_WFD | 0.04004% | SR15_ENV_RBWD | 0.04744% | SR15_SEW_SWO | 0.05645% | SR15_CCH_CC | 0.06165%
50024 | Supplier Rebates Finance - SR15 - 2018-19 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | -7809782.84 | 0 | 0 | -7809782.84 | 0 | -7809782.84 | 0 | [6 empty] | SR15_ENV_HABD | -0.2676% | SR15_DWA_PRE | -0.0005853% | SR15_CCH_CC | 0.00682% | SR15_CMP_PFI | 0.01122% | SR15_ENV_ODO | 0.01573% | SR15_CEX_CMGT | 0.01869% | WG3 | 0.02248% | SR15_CEX_STU | 0.02634% | SR15_DWA_EFA | 0.02637% | SR15_DWA_LEAK | 0.03528%
50025 | Supplier Rebates Finance - SR15 - 2019-20 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2020-03-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | -7652612.27 | 0 | -7652612.27 | 0 | -7652612.27 | 769432.92 | [6 empty] | SR15_ENV_HABD | -0.007139% | SR15_IR18_IR18 | 0.001434% | SR15_CEX_CMGT | 0.003294% | SR15_SEW_SWO | 0.006776% | WG3 | 0.01374% | SR15_DWA_LEAK | 0.01403% | SR15_CEX_STU | 0.01582% | SR15_DWA_PRE | 0.01668% | SR15_DWA_EFA | 0.02056% | SR15_ENV_PSD | 0.02125%
50026 | Supplier Rebates Finance - SR15 - 2020-21 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -5000000 | -5000000 | 0 | -5000000 | 769432.92 | [6 empty] | SR15_ENV_ODO | -0.01186% | SR15_SEW_SWO | -0.000949% | SR15_ENV_SGR | -1.987e-05% | SR15_DWA_PRE | 0.000385% | SR15_ENV_HABD | 0.0008357% | SR15_IR18_IR18 | 0.001737% | SR15_ENV_PSD | 0.008889% | SR15_DWA_SEMD | 0.009584% | SR15_DWA_EFA | 0.01266% | SR15_DWA_ITS | 0.02093%
402078 | Supplier Rebates (Finance) | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS1 | 2011-03-23 | 2021-03-02 | 2021-03-02 |  |  | Scottish Water Wide | -23954419.94 | -3689233.89 | 0 | 0 | 0 | 0 | 0 | -3689233.89 | 0 | -27643653.83 | 0 | [6 empty] | REB | 100%
502802 | Survey work to support Permanent Chemical Dosing at Daldowie WWTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-08-30 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | South Lanarkshire | 0 | 0 | 0 | 149563.71 | -149562.71 | 0 | 0 | 1 | 0 | 1 | 11105602.59 | [6 empty] | EC01A | 100%
502805 | Survey work to support Permanent Chemical Dosing at Dalmarnock WWTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-09-03 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | Glasgow City | 0 | 0 | 0 | 350093.38 | -350092.38 | 0 | 0 | 1 | 0 | 1 | 11105602.59 | [6 empty] | EC01A | 100%
502900 | Surveys and Rectification of Redundant Assets | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS3 | 2017-09-20 | 2017-09-20 | 2017-12-20 |  | 2021-02-17 | Scottish Water Wide | 0 | 0 | 0 | 237464 | 20390 | 102590.37 | 139555.63 | 500000 | 0 | 500000 | 0 | [6 empty] | CM_M&G | 100%
503454 | Sustainable Catchment Decisions | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2019-01-30 | 2019-04-18 | 2019-04-22 | 2021-01-14 | 2021-01-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 37800 | 109611.4 | 157588.6 | 305000 | 0 | 305000 | 295054.03 | [6 empty] | CS25 | 100%
503096 | Sustainable Regulation Projects- Value from Waste | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2019-01-04 | 2019-04-18 | 2019-04-22 | 2021-01-14 | 2021-01-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 56000 | 131866.62 | 67133.38 | 255000 | 0 | 255000 | 295054.03 | [6 empty] | CS25 | 100%
402124 | Sustainable Solutions for Tackling Cryptosporidium | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-06-20 | 2012-09-26 | 2012-10-22 | 2014-12-22 | 2015-03-10 | Scottish Water Wide | 1669909 | -7521.29 | 0 | 0 | 0 | 0 | 0 | -7521.29 | 0 | 1662387.71 | 0 | [6 empty] | DW23A | 100%
401268 | Sustainable Treatment 1 Varying WwTW Performance In Relation To Environmental Conditions | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-15 | 2012-05-28 | 2012-09-24 | 2017-06-30 | 2017-09-30 | Scottish Water Wide | 989839.74 | 286982.51 | 120045.03 | 72219.37 | 0 | 0 | 5947.43 | 485194.34 | 0 | 1475034.08 | 207999 | [6 empty] | CC5S | 100% | bar: Regulatory Outputs OMG-45
401270 | Sustainable Treatment 3 Wetland Reed Bed Only Sustainability Trail | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-15 | 2011-02-18 | 2011-02-21 | 2014-12-24 | 2015-03-27 | Aberdeenshire | 364159 | 440.69 | 0 | 0 | 0 | 0 | 0 | 440.69 | 0 | 364599.69 | 0 | [6 empty] | CC5S | 100%
503806 | SVCD App Development Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-02-05 | 2020-02-28 | 2020-07-24 | 2020-09-25 | 2020-09-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 321018.15 | 8981.85 | 330000 | 0 | 330000 | 0 | [6 empty] | CM_WSNI | 100%
503022 | SVCD ATOM (LUBRICATION IMPROVEMENTS) PLANNED (SWD) - Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS6 | 2018-03-16 |  | 2018-04-02 | 2018-12-12 | 2018-12-12 | Scottish Water Wide | 0 | 0 | 0 | 6214.95 | -6214.95 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 100%
502087 | SVCD Reservoir Maintenance 16-17 East Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-02-29 | 2016-02-29 | 2016-04-01 |  | 2020-03-02 | All East Unitary Authorities | 0 | 34383 | 298008 | 436585.64 | 181180.51 | -203223.82 | 4651.18 | 751584.51 | 0 | 751584.51 | 0 | [6 empty] | CM_WSI | 100%
502090 | SVCD Reservoir Maintenance 16-17 North Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-02-19 | 2016-02-19 | 2016-05-02 | 2020-09-30 | 2020-03-09 | All North Unitary Authorities | 0 | 16355.14 | 390215.03 | 500605.17 | 24827.71 | 46628.27 | 42724.27 | 1021355.59 | 0 | 1021355.59 | 0 | [6 empty] | CM_WSI | 100%
502088 | SVCD Reservoir Maintenance 16-17 South Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-01 | 2016-03-01 | 2016-05-02 | 2019-12-24 | 2019-12-24 | All South Unitary Authorities | 0 | 69905 | 337763.25 | 1416479.05 | 345608.35 | 263539.68 | 0 | 2433295.33 | 0 | 2433295.33 | 0 | [6 empty] | CM_WSI | 100%
502089 | SVCD Reservoir Maintenance 16-17 West Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-01 | 2016-03-01 | 2016-05-13 |  | 2020-01-17 | All West Unitary Authorities | 0 | 98130.84 | 956621.3 | 2088023.29 | 516442.95 | -169256.44 | 0 | 3489961.94 | 0 | 3489961.94 | 0 | [6 empty] | CM_WSI | 100%
502590 | SVCD Reservoir Maintenance 17-18 East Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-05-30 |  | 2020-04-27 | All East Unitary Authorities | 0 | 0 | 49065.42 | 128742.28 | 256842.31 | 5000 | 0 | 439650.01 | 0 | 439650.01 | 0 | [6 empty] | CM_WSI | 100%
502591 | SVCD Reservoir Maintenance 17-18 North Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-07-11 | 2019-12-06 | 2019-12-06 | All North Unitary Authorities | 0 | 0 | 34653.45 | 95661.83 | 137348.48 | 151496.76 | 2937.67 | 422098.19 | 1295.27 | 423393.46 | 0 | [6 empty] | CM_WSI | 100%
502592 | SVCD Reservoir Maintenance 17-18 South Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-14 | 2017-02-14 | 2017-05-01 |  | 2019-02-14 | All South Unitary Authorities | 0 | 0 | 65552.1 | 638097.6 | 309920.44 | -41443.98 | 0 | 972126.16 | 0 | 972126.16 | 0 | [6 empty] | CM_WSI | 100%
502593 | SVCD Reservoir Maintenance 17-18 SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-28 | 2017-02-28 | 2018-06-05 |  | 2019-12-03 | Scottish Water Wide | 0 | 0 | 51321.72 | 569457.62 | 152782.04 | -157129.32 | 0 | 616432.06 | 0 | 616432.06 | 0 | [6 empty] | CM_WSI | 100%
502589 | SVCD Reservoir Maintenance 17-18 West Area | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-17 | 2021-07-31 | 2021-07-31 | All West Unitary Authorities | 0 | 0 | 130841.12 | 1396243 | 1114617.28 | 260554.68 | 98776.01 | 3001032.09 | 0 | 3001032.09 | 357551.71 | [6 empty] | WR6 | 17% | CM_WSI | 83% | bar: Regulatory Outputs OMG-13
503157 | SVCD Reservoir Maintenance Yr4 to Yr6 SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-28 | 2018-05-28 | 2018-06-01 |  | 2021-07-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 148090.8 | 444621.06 | 3685.26 | 596397.12 | 3602.84 | 599999.96 | 0 | [6 empty] | CM_WSI | 100%
502291 | SVCD Responsive Wastewater East Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2016-10-25 | 2017-11-06 | 2017-11-06 | All East Unitary Authorities | 0 | 0 | 147749.31 | 82951.19 | -37048.53 | 0 | 0 | 193651.97 | 0 | 193651.97 | 0 | [6 empty] | CM_WWNI | 100%
502292 | SVCD Responsive Wastewater North Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2017-01-23 | 2017-05-22 | 2017-05-22 | All North Unitary Authorities | 0 | 0 | 891.04 | 0 | 0 | 0 | 0 | 891.04 | 0 | 891.04 | 0 | [6 empty] | CM_WWI | 50% | CM_WWNI | 50%
502293 | SVCD Responsive Wastewater South Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2016-10-25 | 2017-04-21 | 2017-04-21 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
502294 | SVCD Responsive Wastewater West Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2017-05-22 | 2017-05-22 | 2017-05-22 | All West Unitary Authorities | 0 | 0 | 8618.63 | 0 | 0 | 0 | 0 | 8618.63 | 0 | 8618.63 | 0 | [6 empty] | CM_WWI | 50% | CM_WWNI | 50%
502295 | SVCD Responsive Water East Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2016-08-04 | 2016-08-04 | 2016-10-25 | 2018-02-06 | 2018-02-06 | All East Unitary Authorities | 0 | 0 | 239987.32 | 397254.35 | 994.51 | 7802.59 | -7802.59 | 638236.18 | 0 | 638236.18 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
502296 | SVCD Responsive Water North Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2017-01-23 | 2017-05-22 | 2017-05-22 | All North Unitary Authorities | 0 | 0 | 14833.02 | 631.08 | 0 | 0 | 0 | 15464.1 | 0 | 15464.1 | 0 | [6 empty] | CM_WSI | 25.34% | CM_WSNI | 74.66%
502297 | SVCD Responsive Water South Year 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2016-10-25 | 2017-04-21 | 2017-04-21 | All South Unitary Authorities | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSI | 100%
502298 | SVCD Responsive Water West Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2017-03-01 | 2017-05-22 | 2017-05-22 | All West Unitary Authorities | 0 | 0 | 13711.75 | 84086.37 | 0 | 0 | -14.77 | 97783.35 | 0 | 97783.35 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503414 | SVCD SWD ATOM - Yr 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-10-25 | 2018-10-25 | 2018-10-31 |  | 2021-05-27 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 130841.12 | 220.4 | 1796827.25 | 1927888.77 | 72111.2 | 1999999.97 | 0 | [6 empty] | CM_WWI | 100%
503477 | SVCD WASTE ALL AREAS Infra (SWD) Reactive -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-03-01 | 2019-03-01 | 2019-11-14 |  | 2020-09-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 213271.03 | 8530631.15 | -1593902.17 | 7150000.01 | 0 | 7150000.01 | 0 | [6 empty] | CM_WWI | 100%
503005 | SVCD WASTE EAST INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-04-02 |  | 2019-12-31 | All East Unitary Authorities | 0 | 0 | 0 | 53644.86 | 1501977.04 | 47002.14 | 0.05 | 1602624.09 | 0 | 1602624.09 | 0 | [6 empty] | CM_WWI | 100%
503483 | SVCD WASTE EAST INFRA (SWD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-07-01 |  | 2021-04-29 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 67496.64 | 480592.56 | 136338.12 | 684427.32 | 4575.06 | 689002.38 | 0 | [6 empty] | CM_WWI | 100%
502979 | SVCD WASTE EAST INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-23 |  | 2021-01-22 | All East Unitary Authorities | 0 | 0 | 0 | 39906.54 | 219508.07 | 500319.31 | 315946.51 | 1075680.43 | 971.99 | 1076652.42 | 0 | [6 empty] | CM_WWI | 100%
502980 | SVCD WASTE EAST INFRA RESPONSIVE (MD)-Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2019-07-08 | 2019-07-08 | All East Unitary Authorities | 0 | 0 | 0 | 18009 | 255441.9 | -6302.04 | 204.32 | 267353.18 | 0 | 267353.18 | 0 | [6 empty] | CM_WWI | 100%
503482 | SVCD WASTE EAST NON INFRA (SWD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-03-01 | 2019-03-01 | 2019-07-01 |  | 2021-01-14 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 410964.27 | 2076135.11 | -243628.69 | 2243470.69 | 31344 | 2274814.69 | 0 | [6 empty] | CM_WWNI | 100%
503484 | SVCD WASTE EAST PLANNED (MD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-20 |  | 2020-11-26 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 157009.35 | 768785.91 | 526689.72 | 1452484.98 | 0 | 1452484.98 | 0 | [6 empty] | CM_WWI | 33.33% | CM_WWNI | 66.67%
503485 | SVCD WASTE EAST RESPONSIVE (MD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-01 |  | 2020-10-13 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 78700.31 | 1574550.85 | 250454.75 | 1903705.91 | 10645.73 | 1914351.64 | 0 | [6 empty] | CM_WWNI | 43.33% | CM_WWI | 56.67%
503006 | SVCD WASTE EAST WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-04-02 |  | 2019-12-31 | All East Unitary Authorities | 0 | 0 | 0 | 128644.86 | 827793.11 | 102899.59 | -7174.48 | 1052163.08 | 0 | 1052163.08 | 0 | [6 empty] | CM_WWNI | 100%
502981 | SVCD WASTE EAST WWPS PLANNED (MD)-Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-23 |  | 2020-05-04 | All East Unitary Authorities | 0 | 0 | 0 | 40176.88 | 424985.61 | 120734.52 | 0 | 585897.01 | 0 | 585897.01 | 0 | [6 empty] | CM_WWI | 100%
502982 | SVCD WASTE EAST WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 2019-11-13 | All East Unitary Authorities | 0 | 0 | 0 | 19009 | 325323.74 | 31325.59 | -77.64 | 375580.69 | 0 | 375580.69 | 0 | [6 empty] | CM_WWI | 100%
503007 | SVCD WASTE EAST WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-04-02 |  | 2019-12-31 | All East Unitary Authorities | 0 | 0 | 0 | 288694.35 | 1722125.91 | 8431.01 | -3182.28 | 2016068.99 | 0 | 2016068.99 | 0 | [6 empty] | CM_WWNI | 100%
502983 | SVCD WASTE EAST WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-08 |  | 2020-01-23 | All East Unitary Authorities | 0 | 0 | 0 | 80696.04 | 118971.26 | 248652.52 | -15724.81 | 432595.01 | 0 | 432595.01 | 0 | [6 empty] | CM_WWNI | 100%
502984 | SVCD WASTE EAST WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 2020-03-23 | All East Unitary Authorities | 0 | 0 | 0 | 69257 | 1061028.79 | 1061387.9 | 0 | 2191673.69 | 0 | 2191673.69 | 0 | [6 empty] | CM_WWI | 100%
503003 | SVCD WASTE EMERGING NEEDS (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2020-09-25 | 2020-03-12 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 436945.89 | 47441.87 | 34485.2 | 518872.96 | 0 | 518872.96 | 0 | [6 empty] | CM_WWI | 100%
503472 | SVCD WASTE NORTH (MD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-01 | 2019-03-01 | 2019-06-10 |  | 2021-04-13 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 153267.7 | 1366512.63 | 697442.45 | 2217222.78 | 102907.7 | 2320130.48 | 0 | [6 empty] | CM_WWI | 13.48% | CM_WWNI | 86.52%
503442 | SVCD WASTE NORTH (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-06-03 |  | 2020-08-24 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 236.8 | 2216985.63 | 892777.57 | 3110000 | 0 | 3110000 | 0 | [6 empty] | CM_WWI | 7.193% | CM_WWNI | 92.81%
503008 | SVCD WASTE NORTH INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-10 | 2019-09-10 | All North Unitary Authorities | 0 | 0 | 0 | 70626.17 | 575220.51 | 76317.88 | -5203.16 | 716961.4 | 0 | 716961.4 | 0 | [6 empty] | CM_WWI | 100%
502985 | SVCD WASTE NORTH INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-05-13 | 2019-05-13 | All North Unitary Authorities | 0 | 0 | 0 | 22562.99 | -20231.77 | 124.73 | 0 | 2455.95 | 0 | 2455.95 | 0 | [6 empty] | CM_WWI | 100%
502986 | SVCD WASTE NORTH INFRA RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-05-06 | 2019-05-06 | All North Unitary Authorities | 0 | 0 | 0 | 12524.81 | 53236.5 | -1737.93 | 0 | 64023.38 | 0 | 64023.38 | 0 | [6 empty] | CM_WWI | 100%
503009 | SVCD WASTE NORTH WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-02 | 2019-09-02 | All North Unitary Authorities | 0 | 0 | 0 | 98495.33 | 774630.13 | 61102.53 | -1743.92 | 932484.07 | 0 | 932484.07 | 0 | [6 empty] | CM_WWI | 100%
502987 | SVCD WASTE NORTH WWPS PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-21 |  | 2020-01-07 | All North Unitary Authorities | 0 | 0 | 0 | 22758.61 | 83179.65 | 136712.8 | 0 | 242651.06 | 0 | 242651.06 | 0 | [6 empty] | CM_WWI | 100%
502988 | SVCD WASTE NORTH WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-05-13 | 2019-05-13 | All North Unitary Authorities | 0 | 0 | 0 | 9478.88 | 19803.37 | -1239.56 | 0 | 28042.69 | 0 | 28042.69 | 0 | [6 empty] | CM_WWI | 100%
503010 | SVCD WASTE NORTH WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-10 | 2019-09-10 | All North Unitary Authorities | 0 | 0 | 0 | 272626.17 | 2165938.19 | 205486.85 | 2661.28 | 2646712.49 | 0 | 2646712.49 | 0 | [6 empty] | CM_WWI | 100%
502989 | SVCD WASTE NORTH WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2018-01-31 | 2018-01-31 | 2018-02-21 |  | 2019-09-04 | All North Unitary Authorities | 0 | 0 | 0 | 119553.64 | 537082.12 | 30863.6 | -5500 | 681999.36 | 0 | 681999.36 | 0 | [6 empty] | CM_WWI | 100%
502990 | SVCD WASTE NORTH WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-30 | 2018-01-30 | 2018-02-21 | 2019-05-06 | 2019-05-06 | All North Unitary Authorities | 0 | 0 | 0 | 18637.76 | 48403.33 | -633.09 | 0 | 66408 | 0 | 66408 | 0 | [6 empty] | CM_WWI | 100%
503465 | SVCD WASTE South (MD) Planned-Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-04-01 |  | 2021-03-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 170093.46 | 421668.24 | 235774.28 | 827535.98 | 0 | 827535.98 | 0 | [6 empty] | CM_WWI | 100%
503466 | SVCD WASTE SOUTH (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-03-26 |  | 2020-09-11 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 105673.38 | 1133446.97 | 0 | 1239120.35 | 0 | 1239120.35 | 0 | [6 empty] | CM_WWI | 100%
503011 | SVCD WASTE SOUTH INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-22 | 2018-01-22 | 2018-04-02 |  | 2019-12-09 | All South Unitary Authorities | 0 | 0 | 0 | 179964.33 | 1651499.22 | 33153.85 | -3449.91 | 1861167.49 | 0 | 1861167.49 | 0 | [6 empty] | CM_WWI | 100%
503460 | SVCD WASTE SOUTH Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-02-28 | 2019-02-28 | 2019-12-30 |  | 2021-02-26 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 204161.74 | 195432.16 | 1308808.19 | 1708402.09 | 20477.64 | 1728879.73 | 0 | [6 empty] | CM_WWI | 100%
502991 | SVCD WASTE SOUTH INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-08 |  | 2020-06-19 | All South Unitary Authorities | 0 | 0 | 0 | 58878.5 | 114151 | 83096.84 | 0 | 256126.34 | 0 | 256126.34 | 0 | [6 empty] | CM_WWI | 100%
502992 | SVCD WASTE SOUTH INFRA RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-26 | 2018-01-26 | 2018-02-08 |  | 2019-05-13 | All South Unitary Authorities | 0 | 0 | 0 | 90093.46 | 1020084.33 | 513655.63 | 1556.75 | 1625390.17 | 0 | 1625390.17 | 0 | [6 empty] | CM_WWI | 100%
503459 | SVCD WASTE SOUTH Non Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-03-20 | 2019-03-20 | 2019-04-01 |  | 2020-07-21 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 247242.71 | 2791957.86 | 1716307.79 | 4755508.36 | 0 | 4755508.36 | 0 | [6 empty] | CM_WWNI | 100%
503012 | SVCD WASTE SOUTH WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-26 |  | 2019-12-09 | All South Unitary Authorities | 0 | 0 | 0 | 87081.56 | 496275.28 | 31516.85 | 585126.31 | 1200000 | 0 | 1200000 | 0 | [6 empty] | CM_WWI | 100%
502993 | SVCD WASTE SOUTH WWPS PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-30 |  | 2020-06-29 | All South Unitary Authorities | 0 | 0 | 0 | 58920.09 | 124866.91 | 238237.42 | 0 | 422024.42 | 0 | 422024.42 | 0 | [6 empty] | CM_WWI | 100%
502994 | SVCD WASTE SOUTH WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-26 | 2018-01-26 | 2018-02-08 |  | 2020-02-27 | All South Unitary Authorities | 0 | 0 | 0 | 24859.81 | 205646.57 | 129045.73 | 0 | 359552.11 | 0 | 359552.11 | 0 | [6 empty] | CM_WWI | 100%
503013 | SVCD WASTE SOUTH WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-26 |  | 2019-12-09 | All South Unitary Authorities | 0 | 0 | 0 | 226700.96 | 3374770.66 | 865641.47 | 158213.98 | 4625327.07 | 0 | 4625327.07 | 0 | [6 empty] | CM_WWI | 100%
502995 | SVCD WASTE SOUTH WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-17 | 2018-01-17 | 2018-01-30 |  | 2020-06-19 | All South Unitary Authorities | 0 | 0 | 0 | 117102.8 | 731507.26 | 558913.06 | 42855.79 | 1450378.91 | 0 | 1450378.91 | 0 | [6 empty] | CM_WWI | 100%
502996 | SVCD WASTE SOUTH WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-08 |  | 2019-05-13 | All South Unitary Authorities | 0 | 0 | 0 | 50373.83 | 1248908.87 | 974126.25 | 0 | 2273408.95 | 0 | 2273408.95 | 0 | [6 empty] | CM_WWI | 100%
503004 | SVCD WASTE STC (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-22 | 2018-01-22 | 2018-01-30 | 2021-09-27 | 2021-09-27 | All South Unitary Authorities | 0 | 0 | 0 | 98130.84 | 31000 | 346025.63 | 981031.31 | 1456187.78 | 269414.18 | 1725601.96 | 0 | [6 empty] | CM_WWI | 100%
503471 | SVCD WASTE WEST (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-04-01 |  | 2020-06-19 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 137671.18 | 434917.51 | 638977.15 | 1211565.84 | 0 | 1211565.84 | 0 | [6 empty] | CM_WWI | 33.33% | CM_WWNI | 66.67%
503468 | SVCD WASTE WEST (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-04-01 |  | 2020-03-19 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 78504.67 | 591163.73 | 243289.91 | 912958.31 | 0 | 912958.31 | 0 | [6 empty] | CM_WWI | 16.67% | CM_WWNI | 83.33%
503014 | SVCD WASTE WEST INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 |  | 2020-01-29 | All West Unitary Authorities | 0 | 0 | 0 | 230015.05 | 2828179.03 | -344650.71 | 12407.4 | 2725950.77 | 0 | 2725950.77 | 0 | [6 empty] | CM_WWI | 100%
503458 | SVCD WASTE WEST Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-02-27 | 2019-02-27 | 2019-12-30 |  | 2021-02-26 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 280093.17 | 33534.61 | 901939.05 | 1215566.83 | 0 | 1215566.83 | 0 | [6 empty] | CM_WWI | 100%
502997 | SVCD WASTE WEST INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-04-09 |  | 2019-12-06 | All West Unitary Authorities | 0 | 0 | 0 | 42523.36 | 24098.29 | 43120.37 | 155309.36 | 265051.38 | 0 | 265051.38 | 0 | [6 empty] | CM_WWI | 100%
502998 | SVCD WASTE WEST INFRA RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-26 | 2018-02-26 | 2018-06-08 | 2019-12-16 | 2019-12-17 | All West Unitary Authorities | 0 | 0 | 0 | 22897.2 | 921874.19 | -327113.36 | 64437.65 | 682095.68 | 0 | 682095.68 | 0 | [6 empty] | CM_WWI | 100%
503457 | SVCD WASTE WEST Non Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-03-13 | 2019-03-13 | 2019-04-01 |  | 2020-07-21 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 311070.09 | 2496094.34 | 1252835.86 | 4060000.29 | 0 | 4060000.29 | 0 | [6 empty] | CM_WWNI | 100%
503015 | SVCD WASTE WEST WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 |  | 2020-01-29 | All West Unitary Authorities | 0 | 0 | 0 | 128794.68 | 1099398.57 | 320832.34 | 19397.87 | 1568423.46 | 0 | 1568423.46 | 0 | [6 empty] | CM_WWI | 100%
502999 | SVCD WASTE WEST WWPS PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2018-02-28 | 2018-04-09 |  | 2020-01-31 | All West Unitary Authorities | 0 | 0 | 0 | 34866.48 | 156015.08 | 34336.99 | 120001 | 345219.55 | 0 | 345219.55 | 0 | [6 empty] | CM_WWI | 100%
503000 | SVCD WASTE WEST WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2018-02-28 | 2018-06-08 |  | 2019-11-19 | All West Unitary Authorities | 0 | 0 | 0 | 21588.79 | 46941.93 | 421615.7 | -128.42 | 490018 | 0 | 490018 | 0 | [6 empty] | CM_WWI | 100%
503016 | SVCD WASTE WEST WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 |  | 2020-01-29 | All West Unitary Authorities | 0 | 0 | 0 | 243794.17 | 2902456.98 | 324957.72 | -21209.31 | 3449999.56 | 0 | 3449999.56 | 0 |  |  |  |  | 69282 |  | CM_WWI | 100%
503001 | SVCD WASTE WEST WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-04-09 |  | 2019-12-23 | All West Unitary Authorities | 0 | 0 | 0 | 65420.56 | 251819.79 | 111907.22 | 0 | 429147.57 | 0 | 429147.57 | 0 | [6 empty] | CM_WWI | 100%
503002 | SVCD WASTE WEST WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-06-08 |  | 2020-02-14 | All West Unitary Authorities | 0 | 0 | 0 | 36064.49 | 466483.56 | -77974.71 | 0 | 424573.34 | 0 | 424573.34 | 0 | [6 empty] | CM_WWI | 100%
502444 | SVCD Wastewater - Infra - East (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2018-06-21 | 2018-06-21 | All East Unitary Authorities | 0 | 0 | 40209.39 | 259372.15 | 20728 | -57794.19 | 0 | 262515.35 | 0 | 262515.35 | 0 | [6 empty] | CM_WWI | 100%
502445 | SVCD Wastewater - Infra - East (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-12 | 2018-07-12 | 2018-07-12 | All East Unitary Authorities | 0 | 0 | 17271.81 | 289275.37 | -26808.17 | 1175.07 | -1175.39 | 279738.69 | 0 | 279738.69 | 0 | [6 empty] | CM_WWI | 100%
502446 | SVCD Wastewater - Infra - East (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 |  | 2019-12-31 | All East Unitary Authorities | 0 | 0 | 54130.98 | 794080.88 | 1107052 | -24001.28 | 0.01 | 1931262.59 | 0 | 1931262.59 | 0 | [6 empty] | CM_WWI | 100%
502447 | SVCD Wastewater - Infra - North (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2019-02-14 | 2019-02-14 | All North Unitary Authorities | 0 | 0 | 23030.38 | 349732.23 | 108802.91 | -383.2 | 0 | 481182.32 | 0 | 481182.32 | 0 | [6 empty] | CM_WWI | 100%
502448 | SVCD Wastewater - Infra - North (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-12 | 2017-01-12 | 2017-06-05 | 2018-03-01 | 2018-03-01 | All North Unitary Authorities | 0 | 0 | 9158.88 | 21530.45 | 122.99 | 0 | 0 | 30812.32 | 0 | 30812.32 | 0 | [6 empty] | CM_WWI | 100%
502449 | SVCD Wastewater - Infra - North (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-04 | 2019-05-30 | 2019-05-30 | All North Unitary Authorities | 0 | 0 | 58048.82 | 511951.18 | -10000 | -2365.17 | 1110 | 558744.83 | 0 | 558744.83 | 0 | [6 empty] | CM_WWI | 100%
502450 | SVCD Wastewater - Infra - South (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-04-12 |  | 2019-12-20 | All South Unitary Authorities | 0 | 0 | 58878.5 | 159000 | 128071 | 0 | 0 | 345949.5 | 0 | 345949.5 | 0 | [6 empty] | CM_WWI | 100%
502451 | SVCD Wastewater - Infra - South (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-03 | 2019-06-04 | 2019-06-04 | All South Unitary Authorities | 0 | 0 | 29859.81 | 1188240.72 | 131076.16 | 117605.03 | 0 | 1466781.72 | 0 | 1466781.72 | 0 | [6 empty] | CM_WWI | 100%
502452 | SVCD Wastewater - Infra - South (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-04-10 | 2019-03-13 | 2019-03-13 | All South Unitary Authorities | 0 | 0 | 78504.67 | 951441.69 | 1144589.39 | 68335.91 | -118.42 | 2242753.24 | 0 | 2242753.24 | 0 | [6 empty] | CM_WWI | 100%
502453 | SVCD Wastewater - Infra - West (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-04-12 |  | 2020-03-19 | All West Unitary Authorities | 0 | 0 | 50373.83 | 287587.66 | 499933.33 | 89437.79 | 49787.98 | 977120.59 | 0 | 977120.59 | 0 | [6 empty] | CM_WWI | 100%
502454 | SVCD Wastewater - Infra - West (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-14 | 2019-02-04 | 2019-02-04 | All West Unitary Authorities | 0 | 0 | 21588.79 | 431943.87 | -57922.51 | 510.73 | 298.29 | 396419.17 | 0 | 396419.17 | 0 | [6 empty] | CM_WWI | 100%
502455 | SVCD Wastewater - Infra - West (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-11-17 | 2019-03-12 | 2019-03-12 | All West Unitary Authorities | 0 | 0 | 118889.89 | 682155.96 | 1074403.71 | 60546.96 | -974.86 | 1935021.66 | 0 | 1935021.66 | 0 | [6 empty] | CM_WWI | 100%
502475 | SVCD Wastewater - Responsive WWTW - South (MD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-07 | 2017-02-07 | 2017-05-09 |  | 2019-12-17 | All South Unitary Authorities | 0 | 0 | 50373.83 | 731308.98 | 519465.24 | 109683.16 | 4070.79 | 1414902 | 0 | 1414902 | 0 | [6 empty] | CM_WWNI | 100%
502456 | SVCD Wastewater - WWPS - East (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2018-06-21 | 2018-06-21 | All East Unitary Authorities | 0 | 0 | 40169.02 | 9921.77 | -43592.23 | -406.27 | 406.27 | 6498.56 | 0 | 6498.56 | 0 | [6 empty] | CM_WWNI | 100%
502457 | SVCD Wastewater - WWPS - East (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-18 |  | 2019-02-06 | All East Unitary Authorities | 0 | 0 | 17261.7 | 320845.65 | 373084.19 | 31033 | -25563.89 | 716660.65 | 0 | 716660.65 | 0 | [6 empty] | CM_WWNI | 100%
502458 | SVCD Wastewater - WWPS - East (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 |  | 2019-12-31 | All East Unitary Authorities | 0 | 0 | 57984.24 | 899798.95 | 423490.27 | 34288.75 | 0.01 | 1415562.22 | 0 | 1415562.22 | 0 | [6 empty] | CM_WWNI | 100%
502459 | SVCD Wastewater - WWPS - North (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2018-03-01 | 2018-03-01 | All North Unitary Authorities | 0 | 0 | 22529.71 | 2366.72 | 123.23 | 0 | 0.01 | 25019.67 | 0 | 25019.67 | 0 | [6 empty] | CM_WWNI | 100%
502460 | SVCD Wastewater - WWPS - North (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-12 | 2017-01-12 | 2017-06-05 | 2018-04-23 | 2018-04-23 | All North Unitary Authorities | 0 | 0 | 9158.88 | 31153.46 | -38090.39 | 0 | 0 | 2221.95 | 0 | 2221.95 | 0 | [6 empty] | CM_WWNI | 100%
502461 | SVCD Wastewater - WWPS - North (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2019-03-19 | 2019-03-19 | All North Unitary Authorities | 0 | 0 | 37148.49 | 456010.3 | 271350.53 | 35538.12 | 0 | 800047.44 | 0 | 800047.44 | 0 | [6 empty] | CM_WWNI | 100%
502463 | SVCD Wastewater - WWPS - South (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-01-17 | 2017-01-17 | 2017-04-03 |  | 2019-11-07 | All South Unitary Authorities | 0 | 0 | 24859.81 | 431596 | 371520 | 86966 | 0 | 914941.81 | 0 | 914941.81 | 0 | [6 empty] | CM_WWNI | 100%
502462 | SVCD Wastewater - WWPS - South (MD)Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-05-18 |  | 2019-12-23 | All South Unitary Authorities | 0 | 0 | 58878.5 | 237285 | 169121 | 0 | 0 | 465284.5 | 0 | 465284.5 | 0 | [6 empty] | CM_WWNI | 100%
502464 | SVCD Wastewater - WWPS - South (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-11-17 | 2019-03-13 | 2019-03-13 | All South Unitary Authorities | 0 | 0 | 100800.1 | 486923.44 | 221643.57 | -50.7 | 50.71 | 809367.12 | 0 | 809367.12 | 0 | [6 empty] | CM_WWNI | 100%
502465 | SVCD Wastewater - WWPS - West (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-01-19 | 2017-01-19 | 2017-04-24 | 2019-03-05 | 2019-03-05 | All West Unitary Authorities | 0 | 0 | 50373.83 | 170024.68 | 292801.17 | 0 | 0 | 513199.68 | 0 | 513199.68 | 0 | [6 empty] | CM_WWNI | 100%
502466 | SVCD Wastewater - WWPS - West (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-06-05 | 2018-09-27 | 2018-09-27 | All West Unitary Authorities | 0 | 0 | 21588.79 | 153500 | 98000 | -8971.17 | 0 | 264117.62 | 0 | 264117.62 | 0 | [6 empty] | CM_WWNI | 100%
502467 | SVCD Wastewater - WWPS - West (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-13 | 2017-01-13 | 2017-11-17 | 2019-03-12 | 2019-03-12 | All West Unitary Authorities | 0 | 0 | 117589.11 | 970455.16 | 211791.45 | 19588.5 | 0 | 1319424.22 | 0 | 1319424.22 | 0 | [6 empty] | CM_WWNI | 100%
502468 | SVCD Wastewater - WWTW - East (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-04-03 | 2019-05-29 | 2019-05-29 | All East Unitary Authorities | 0 | 0 | 80810.37 | 545906.92 | 439971.76 | -23779.82 | 4660.22 | 1047569.45 | 0 | 1047569.45 | 0 | [6 empty] | CM_WWNI | 100%
502469 | SVCD Wastewater - WWTW - East (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-06-06 |  | 2019-12-13 | All East Unitary Authorities | 0 | 0 | 34915.11 | 1444276.71 | 1417660.79 | 184033.5 | -164980.76 | 2915905.35 | 0 | 2915905.35 | 0 | [6 empty] | CM_WWNI | 100%
502470 | SVCD Wastewater - WWTW - East (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-04-03 | 2019-12-31 | 2019-12-31 | All East Unitary Authorities | 0 | 0 | 250598.84 | 1340246.56 | 813085.74 | -40565.2 | 0 | 2363365.94 | 0 | 2363365.94 | 0 | [6 empty] | CM_WWNI | 100%
502471 | SVCD Wastewater - WWTW - North (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-02-24 | 2017-02-24 | 2017-07-18 | 2019-09-04 | 2019-09-04 | All North Unitary Authorities | 0 | 0 | 44160.79 | 592584.24 | 300191.07 | 115471.75 | -35889.76 | 1016518.09 | 0 | 1016518.09 | 0 | [6 empty] | CM_WWNI | 100%
502472 | SVCD Wastewater - WWTW - North (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2018-04-19 | 2018-04-19 | All North Unitary Authorities | 0 | 0 | 18317.76 | 212592 | -2031.77 | 0 | 0 | 228877.99 | 0 | 228877.99 | 0 | [6 empty] | CM_WWNI | 100%
502473 | SVCD Wastewater - WWTW - North (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-05-09 | 2019-03-19 | 2019-03-19 | All North Unitary Authorities | 0 | 0 | 61701.45 | 1493864.88 | 189210.8 | -69012.52 | 0.01 | 1675764.62 | 0 | 1675764.62 | 0 | [6 empty] | CM_WWNI | 100%
502474 | SVCD Wastewater - WWTW - South (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-03-06 |  | 2020-09-15 | All South Unitary Authorities | 0 | 0 | 122102.8 | 633470.69 | 1044401.21 | 314212.29 | -14186.69 | 2100000.3 | 0 | 2100000.3 | 0 | [6 empty] | CM_WWNI | 100%
502476 | SVCD Wastewater - WWTW - South (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-21 | 2017-02-21 | 2017-11-17 | 2019-05-14 | 2019-05-14 | All South Unitary Authorities | 0 | 0 | 267845.74 | 2324769.46 | 655911.42 | 9081 | 6552.01 | 3264159.63 | 0 | 3264159.63 | 0 | [6 empty] | CM_WWNI | 100%
502477 | SVCD Wastewater - WWTW - West (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-04-17 |  | 2019-12-02 | All West Unitary Authorities | 0 | 0 | 100093.46 | 4171.78 | 141863.59 | 11654.21 | 19421.96 | 277205 | 0 | 277205 | 0 | [6 empty] | CM_WWNI | 100%
502478 | SVCD Wastewater - WWTW - West (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2019-01-18 | 2019-01-18 | All West Unitary Authorities | 0 | 0 | 43177.57 | 253073.11 | 462100.99 | -21922.52 | -6417.9 | 730011.25 | 0 | 730011.25 | 0 | [6 empty] | CM_WWNI | 100%
502479 | SVCD Wastewater - WWTW - West (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-11-24 | 2019-03-12 | 2019-03-12 | All West Unitary Authorities | 0 | 0 | 162750.5 | 2210274.09 | 624813.65 | 66348.68 | 0 | 3064186.92 | 0 | 3064186.92 | 0 | [6 empty] | CM_WWNI | 100%
501946 | SVCD Wastewater East Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-08-22 | 2018-08-22 | All East Unitary Authorities | 0 | 80284.31 | 93835.69 | 42115.26 | -45735.63 | 0 | 0 | 170499.63 | 0 | 170499.63 | 0 | [6 empty] | CM_WWI | 100%
502107 | SVCD Wastewater East Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-04-11 | 2018-04-11 | All East Unitary Authorities | 0 | 0 | 941016.01 | 44658.66 | 0 | 0 | 0.33 | 985675 | 0 | 985675 | 0 | [6 empty] | CM_WWI | 100%
502110 | SVCD Wastewater East SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2017-11-07 | 2017-11-07 | All East Unitary Authorities | 0 | 69226 | 202912.72 | 93310.06 | 0 | 0 | 1998.8 | 367447.58 | 0 | 367447.58 | 0 | [6 empty] | CM_WWNI | 100%
502115 | SVCD Wastewater East SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2019-03-01 | 2019-03-01 | All East Unitary Authorities | 0 | 0 | 1160765.69 | 291718.1 | 49803.29 | 0 | 0.01 | 1502287.09 | 0 | 1502287.09 | 0 | [6 empty] | CM_WWNI | 100%
502116 | SVCD Wastewater East WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2017-11-06 | 2017-11-06 | All East Unitary Authorities | 0 | 138452 | 350558.18 | -12279.76 | 395.52 | 0 | 107.42 | 477233.36 | 0 | 477233.36 | 0 | [6 empty] | CM_WWNI | 100%
502117 | SVCD Wastewater East WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-03-31 | 2019-03-01 | 2019-03-01 | All East Unitary Authorities | 0 | 69566.77 | 2689689.9 | 325123.9 | 33171.56 | -10124.86 | 10124.86 | 3117552.13 | 0 | 3117552.13 | 0 |  |  |  |  | 26166 |  | CM_WWNI | 100%
502118 | SVCD Wastewater North Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-03-21 | 2016-03-21 | 2016-04-08 | 2018-06-01 | 2018-06-01 | All North Unitary Authorities | 0 | 0 | 165357.12 | 159245.06 | 1637.1 | 0 | -0.1 | 326239.18 | 0 | 326239.18 | 0 | [6 empty] | CM_WWI | 100%
502119 | SVCD Wastewater North Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-03-21 | 2016-03-21 | 2016-04-08 | 2017-11-07 | 2017-11-07 | All North Unitary Authorities | 0 | 21261.68 | 348851.63 | 14068.72 | 0 | 0 | 0 | 384182.03 | 0 | 384182.03 | 0 | [6 empty] | CM_WWI | 100%
502120 | SVCD Wastewater North SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-04-01 | 2016-04-01 | 2016-07-12 | 2018-02-12 | 2018-02-12 | All North Unitary Authorities | 0 | 0 | 46596.44 | 66090.32 | 0 | 0 | 0.43 | 112687.19 | 0 | 112687.19 | 0 | [6 empty] | CM_WWNI | 100%
502121 | SVCD Wastewater North SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-07-15 | 2017-11-07 | 2017-11-07 | All North Unitary Authorities | 0 | 0 | 872058.84 | 26855.82 | 0 | 0 | 0 | 898914.66 | 0 | 898914.66 | 0 | [6 empty] | CM_WWNI | 100%
502122 | SVCD Wastewater North WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-31 | 2016-03-31 | 2016-04-08 | 2018-02-12 | 2018-02-12 | All North Unitary Authorities | 0 | 99766 | 418520.19 | 184681.9 | 6335.47 | -3369.78 | -946.31 | 704987.47 | 0 | 704987.47 | 0 | [6 empty] | CM_WWNI | 100%
502123 | SVCD Wastewater North WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-07-05 | 2017-12-11 | 2017-12-11 | All North Unitary Authorities | 0 | 789.82 | 1601184.3 | 485071.12 | -34756 | 0 | 0 | 2052289.24 | 0 | 2052289.24 | 0 | [6 empty] | CM_WWNI | 100%
502108 | SVCD Wastewater South Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-04-22 | 2016-04-22 | 2016-05-03 | 2017-11-02 | 2017-11-02 | All South Unitary Authorities | 0 | 0 | 1382308.47 | -314033.12 | -15967.48 | 0 | 274.67 | 1052582.54 | 0 | 1052582.54 | 0 | [6 empty] | CM_WWI | 100%
502109 | SVCD Wastewater South Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2018-03-07 | 2018-03-07 | All South Unitary Authorities | 0 | 0 | 715123.96 | 152602.15 | 0 | 0 | 0 | 867726.11 | 0 | 867726.11 | 0 | [6 empty] | CM_WWI | 100%
502111 | SVCD Wastewater South SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-06-01 | 2017-09-18 | 2017-09-18 | All South Unitary Authorities | 0 | 85049 | 240592.28 | 163393.66 | -29604.72 | 0 | 9.78 | 459440 | 0 | 459440 | 0 | [6 empty] | CM_WWNI | 100%
502112 | SVCD Wastewater South SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2018-03-07 | 2018-03-07 | All South Unitary Authorities | 0 | 0 | 710417.27 | 56800.92 | 0 | 0 | 0 | 767218.19 | 0 | 767218.19 | 0 | [6 empty] | CM_WWNI | 100%
502113 | SVCD Wastewater South WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-08-22 | 2018-08-22 | All South Unitary Authorities | 0 | 174054 | 1485077.91 | 437811.62 | -183756.91 | -76839.16 | 0 | 1836347.46 | 0 | 1836347.46 | 0 | [6 empty] | CM_WWNI | 100%
502114 | SVCD Wastewater South WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-06-22 | 2018-03-30 | 2018-03-30 | All South Unitary Authorities | 0 | 0 | 3072628.91 | 399426.78 | 0 | 0 | 0 | 3472055.69 | 0 | 3472055.69 | 0 | [6 empty] | CM_WWNI | 100%
502101 | SVCD Wastewater West Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2019-02-04 | 2019-02-04 | All West Unitary Authorities | 0 | 0 | 898415.53 | 606132.34 | 150456.15 | -41261.84 | 0.01 | 1613742.19 | 0 | 1613742.19 | 0 | [6 empty] | CM_WWI | 100%
502102 | SVCD Wastewater West Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-11-01 | 2018-11-01 | All West Unitary Authorities | 0 | 100000 | 895393.46 | 11368.5 | -16603.94 | 0 | 0 | 990158.02 | 0 | 990158.02 | 0 | [6 empty] | CM_WWI | 100%
502103 | SVCD Wastewater West SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2019-01-08 | 2019-01-08 | All West Unitary Authorities | 0 | 0 | 445790.08 | 295399.79 | 31726.99 | -40395.87 | 0.03 | 732521.02 | 0 | 732521.02 | 0 | [6 empty] | CM_WWNI | 100%
502104 | SVCD Wastewater West SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2018-11-01 | 2018-11-01 | All West Unitary Authorities | 0 | 0 | 1150817.3 | 141092.28 | 62554.29 | 0 | 0 | 1354463.87 | 0 | 1354463.87 | 0 | [6 empty] | CM_WWNI | 100%
502105 | SVCD Wastewater West WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-08-24 | 2018-08-24 | All West Unitary Authorities | 0 | 0 | 942656.67 | 292059.72 | -25524.26 | 0 | 0 | 1209192.13 | 0 | 1209192.13 | 0 | [6 empty] | CM_WWNI | 100%
502106 | SVCD Wastewater West WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2018-11-01 | 2018-11-01 | All West Unitary Authorities | 0 | 0 | 2538780.7 | 458187.21 | 119331.16 | 0 | 0 | 3116299.07 | 0 | 3116299.07 | 0 | [6 empty] | CM_WWNI | 100%
502482 | SVCD Water - Infra - Central - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-11-22 | 2019-04-15 | 2019-04-15 | Scottish Water Wide | 0 | 0 | 17009.35 | 161645.82 | -5482.44 | -5640.3 | 0.01 | 167532.44 | 0 | 167532.44 | 0 | [6 empty] | CM_WSI | 100%
502484 | SVCD Water - Infra - East - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-14 | 2017-02-14 | 2017-05-08 |  | 2018-12-10 | All East Unitary Authorities | 0 | 0 | 33364.49 | 313277.09 | 239090.96 | 1596.38 | 0 | 587328.92 | 0 | 587328.92 | 0 | [6 empty] | CM_WSI | 100%
502485 | SVCD Water - Infra - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-04-03 |  | 2019-12-13 | All East Unitary Authorities | 0 | 0 | 147850.47 | 307366.77 | 2239581.09 | 110102.22 | 0 | 2804900.55 | 0 | 2804900.55 | 0 | [6 empty] | CM_WSI | 100%
502487 | SVCD Water - Infra - North - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-01-17 | 2019-01-17 | All North Unitary Authorities | 0 | 0 | 29439.25 | 86552.46 | 52894.17 | 103.94 | 0 | 168989.82 | 0 | 168989.82 | 0 | [6 empty] | CM_WSI | 100%
502488 | SVCD Water - Infra - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-05-05 | 2018-11-29 | 2018-11-29 | All North Unitary Authorities | 0 | 0 | 134724.68 | 467986.45 | 1462279.4 | -19515.66 | 0 | 2045474.87 | 0 | 2045474.87 | 0 | [6 empty] | CM_WSI | 100%
502490 | SVCD Water - Infra - South - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-05-17 | 2018-06-07 | 2018-06-07 | All South Unitary Authorities | 0 | 0 | 31401.87 | 181507 | 69097 | -5604.1 | 0 | 276401.77 | 0 | 276401.77 | 0 | [6 empty] | CM_WSI | 100%
502491 | SVCD Water - Infra - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-11-10 | 2019-07-08 | 2019-07-08 | All South Unitary Authorities | 0 | 0 | 152104.4 | 715323.03 | 3255613.81 | -19885.99 | 2088.74 | 4105243.99 | 0 | 4105243.99 | 0 | [6 empty] | CM_WSI | 100%
502493 | SVCD Water - Infra - West - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2018-11-05 | 2018-11-05 | All West Unitary Authorities | 0 | 0 | 35327.1 | 116871.76 | 102885.86 | 7960.47 | 0.03 | 263045.22 | 0 | 263045.22 | 0 | [6 empty] | CM_WSI | 100%
502494 | SVCD Water - Infra - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-23 | 2017-02-23 | 2017-11-24 | 2019-06-18 | 2019-06-18 | All West Unitary Authorities | 0 | 0 | 157009.35 | 289282.63 | 3921969.37 | -142418.54 | 0.01 | 4225842.82 | 0 | 4225842.82 | 0 | [6 empty] | CM_WSI | 100%
502481 | SVCD Water - Planned Infra - Central - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-10 | 2017-02-10 | 2017-04-28 | 2019-06-12 | 2019-06-12 | Scottish Water Wide | 0 | 0 | 15046.73 | 8000 | 53274.25 | 13144.9 | 0 | 89465.88 | 0 | 89465.88 | 0 | [6 empty] | CM_WSI | 100%
502483 | SVCD Water - Planned Infra - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2020-07-31 | 2020-08-03 | All East Unitary Authorities | 0 | 0 | 78504.67 | 122522 | 178973.33 | 49477.12 | 175522.88 | 605000 | 0 | 605000 | 0 | [6 empty] | CM_WSI | 100%
502486 | SVCD Water - Planned Infra - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2019-07-05 | 2019-07-05 | All North Unitary Authorities | 0 | 0 | 68217.38 | 708205.98 | 1060727.58 | 66594.7 | 0 | 1903745.64 | 0 | 1903745.64 | 0 | [6 empty] | CM_WSI | 100%
502489 | SVCD Water - Planned Infra - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-17 | 2017-02-17 | 2017-05-17 |  | 2019-01-18 | All South Unitary Authorities | 0 | 0 | 72616.82 | 329027.71 | 78385.82 | -35727.92 | 0 | 444302.43 | 2469.88 | 446772.31 | 0 | [6 empty] | CM_WSI | 100%
502492 | SVCD Water - Planned Infra - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-24 | 2020-02-20 | 2020-02-21 | All West Unitary Authorities | 0 | 0 | 81775.7 | 563023 | 450110.57 | 207780.92 | -277.05 | 1302413.14 | 0 | 1302413.14 | 0 | [6 empty] | CM_WSI | 100%
502495 | SVCD Water - Planned TWS - Central - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-24 | 2018-09-06 | 2018-09-06 | Scottish Water Wide | 0 | 0 | 28130.84 | 76905.27 | 557.79 | -23087.88 | 0.01 | 82506.03 | 0 | 82506.03 | 0 | [6 empty] | CM_WSNI | 100%
502496 | SVCD Water - Planned TWS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-01-31 | 2017-01-31 | 2017-06-22 |  | 2020-10-30 | All East Unitary Authorities | 0 | 0 | 16355.14 | -367.02 | 4708.48 | 32723.89 | 17020.63 | 70441.12 | 0 | 70441.12 | 0 | [6 empty] | CM_WSNI | 100%
502499 | SVCD Water - Planned TWS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-01 | 2017-02-01 | 2017-06-05 |  | 2020-02-03 | All North Unitary Authorities | 0 | 0 | 13738.32 | 300564.4 | 218564.64 | 92795.77 | -35635.99 | 590027.14 | 0 | 590027.14 | 0 | [6 empty] | CM_WSNI | 100%
502502 | SVCD Water - Planned TWS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-01 | 2017-02-01 | 2017-06-05 |  | 2020-12-31 | All South Unitary Authorities | 0 | 0 | 15046.73 | 16335 | 37460 | 51293.38 | 233256.31 | 353391.42 | 0 | 353391.42 | 0 | [6 empty] | CM_WSNI | 100%
502505 | SVCD Water - Planned TWS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-01-31 | 2017-01-31 | 2017-04-17 |  | 2019-11-05 | All West Unitary Authorities | 0 | 0 | 16355.14 | 1161.54 | 20369.71 | 0 | 0 | 37886.39 | 0 | 37886.39 | 0 | [6 empty] | CM_WSNI | 100%
502508 | SVCD Water - Planned WPS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-11-29 | 2018-11-29 | All East Unitary Authorities | 0 | 0 | 8504.67 | 73000 | 107902.44 | 150.11 | 0.15 | 189557.37 | 0 | 189557.37 | 0 | [6 empty] | CM_WSNI | 100%
502511 | SVCD Water - Planned WPS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-06-05 |  | 2020-02-25 | All North Unitary Authorities | 0 | 0 | 7196.26 | 33135.09 | 96370.82 | 186660.15 | 0 | 323362.32 | 0 | 323362.32 | 0 | [6 empty] | CM_WSNI | 100%
502514 | SVCD Water - Planned WPS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-09 | 2017-02-09 | 2017-05-05 | 2018-06-26 | 2018-06-26 | All South Unitary Authorities | 0 | 0 | 7226.53 | 25269.73 | -6290.61 | 0 | 0.01 | 26205.66 | 0 | 26205.66 | 0 | [6 empty] | CM_WSNI | 100%
502517 | SVCD Water - Planned WPS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-04-17 |  | 2020-01-10 | All West Unitary Authorities | 0 | 0 | 8504.67 | 28000 | 49037.57 | 23483.47 | -9073.55 | 99952.16 | 0 | 99952.16 | 0 | [6 empty] | CM_WSNI | 100%
502520 | SVCD Water - Planned WTW - Central - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-10 | 2017-02-10 | 2017-04-17 | 2018-09-26 | 2018-09-26 | Scottish Water Wide | 0 | 0 | 15046.73 | 1354.33 | 162661.1 | 0 | 3127.76 | 182189.92 | 0 | 182189.92 | 0 | [6 empty] | CM_WSNI | 100%
502522 | SVCD Water - Planned WTW - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-07-25 |  | 2021-03-19 | All East Unitary Authorities | 0 | 0 | 54299.07 | 437948.09 | 47984.65 | 205222.26 | 0 | 745454.07 | 0 | 745454.07 | 0 | [6 empty] | CM_WSNI | 100%
502525 | SVCD Water - Planned WTW - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-05-25 |  | 2020-03-10 | All North Unitary Authorities | 0 | 0 | 47222.8 | 298041.76 | 898741.96 | 110707.65 | 12.92 | 1354727.09 | 0 | 1354727.09 | 0 | [6 empty] | CM_WSNI | 100%
502528 | SVCD Water - Planned WTW - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-04-03 |  | 2021-05-17 | All South Unitary Authorities | 0 | 0 | 51155.71 | 390012.09 | 406816.33 | 62861.92 | 36169.73 | 947015.78 | 10096.64 | 957112.42 | 0 | [6 empty] | CM_WSNI | 100%
502531 | SVCD Water - Planned WTW - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-04-24 |  | 2019-12-23 | All West Unitary Authorities | 0 | 0 | 57570.09 | 18500 | 4581.97 | 494.81 | -1286.01 | 79860.86 | 0 | 79860.86 | 0 | [6 empty] | CM_WSNI | 100%
502497 | SVCD Water - Responsive TWS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-01-31 | 2017-01-31 | 2017-05-15 |  | 2019-04-24 | All East Unitary Authorities | 0 | 0 | 7196.26 | 186881.82 | 368988.77 | 7667.38 | 0.01 | 570734.24 | 0 | 570734.24 | 0 | [6 empty] | CM_WSNI | 100%
502500 | SVCD Water - Responsive TWS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-01 | 2017-02-01 | 2017-06-05 |  | 2019-09-06 | All North Unitary Authorities | 0 | 0 | 5887.85 | 67664.62 | 15030.37 | 20397.94 | 116.55 | 109097.33 | 0 | 109097.33 | 0 | [6 empty] | CM_WSNI | 100%
502503 | SVCD Water - Responsive TWS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-05-01 | 2018-10-16 | 2018-10-16 | All South Unitary Authorities | 0 | 0 | 6542.06 | 138266 | 132663.48 | 11741.12 | -0.01 | 289212.65 | 0 | 289212.65 | 0 | [6 empty] | CM_WSNI | 100%
502506 | SVCD Water - Responsive TWS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-09 | 2017-02-09 | 2017-06-05 |  | 2019-11-26 | All West Unitary Authorities | 0 | 0 | 7196.26 | 417547.21 | 3587.25 | 1426.89 | -1512.77 | 428244.84 | 0 | 428244.84 | 0 | [6 empty] | CM_WSNI | 100%
502509 | SVCD Water - Responsive WPS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-08-06 | 2018-08-06 | All East Unitary Authorities | 0 | 0 | 3271.03 | 9739.25 | -13009.28 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSNI | 100%
502512 | SVCD Water - Responsive WPS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2018-04-19 | 2018-04-19 | All North Unitary Authorities | 0 | 0 | 3271.03 | 144435.23 | -5610.95 | 0 | 0 | 142095.31 | 0 | 142095.31 | 0 | [6 empty] | CM_WSNI | 100%
502515 | SVCD Water - Responsive WPS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-11-05 | 2018-11-05 | All South Unitary Authorities | 0 | 0 | 3271.03 | 4000 | 7082.19 | 0 | 0.02 | 14353.24 | 0 | 14353.24 | 0 | [6 empty] | CM_WSNI | 100%
502518 | SVCD Water - Responsive WPS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-09-28 | 2018-09-28 | All West Unitary Authorities | 0 | 0 | 3271.03 | 66085.96 | 11.47 | 4137.28 | -350.92 | 73154.82 | 0 | 73154.82 | 0 | [6 empty] | CM_WSNI | 100%
502523 | SVCD Water - Responsive WTW - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-13 | 2017-02-13 | 2017-06-22 |  | 2019-01-21 | All East Unitary Authorities | 0 | 0 | 23551.4 | 476577.86 | 30344.87 | -17346.99 | 0 | 513127.14 | 0 | 513127.14 | 0 | [6 empty] | CM_WSNI | 100%
502526 | SVCD Water - Responsive WTW - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-03-04 | 2019-03-04 | All North Unitary Authorities | 0 | 0 | 20280.37 | 309836.02 | 180527.24 | -7462.75 | -201.92 | 502978.96 | 0 | 502978.96 | 0 | [6 empty] | CM_WSNI | 100%
502529 | SVCD Water - Responsive WTW - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-04-24 |  | 2020-01-24 | All South Unitary Authorities | 0 | 0 | 21588.79 | 91954 | 93663 | 1975.29 | 0 | 209181.08 | 0 | 209181.08 | 0 | [6 empty] | CM_WSNI | 100%
502532 | SVCD Water - Responsive WTW - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-06-05 |  | 2019-11-29 | All West Unitary Authorities | 0 | 0 | 24859.81 | 251781.66 | 7582.52 | 3870.69 | 0 | 288094.68 | 0 | 288094.68 | 0 |  |  |  |  | 379189.43 |  | CM_WSNI | 100%
502498 | SVCD Water - TWS - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-04-03 |  | 2019-12-13 | All East Unitary Authorities | 0 | 0 | 30093.46 | 476924.73 | 48640.61 | 4139.61 | 0.01 | 559798.42 | 0 | 559798.42 | 0 | [6 empty] | CM_WSNI | 100%
502501 | SVCD Water - TWS - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-15 | 2017-02-15 | 2017-05-09 | 2018-10-23 | 2018-10-23 | All North Unitary Authorities | 0 | 0 | 25514.02 | 126581.97 | 25889.43 | 0 | 0.01 | 177985.43 | 0 | 177985.43 | 0 | [6 empty] | CM_WSNI | 100%
502504 | SVCD Water - TWS - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-03 | 2019-07-08 | 2019-07-08 | All South Unitary Authorities | 0 | 0 | 36829.43 | 243343.72 | 125745.07 | 0 | 0 | 405918.22 | 0 | 405918.22 | 0 | [6 empty] | CM_WSNI | 100%
502507 | SVCD Water - TWS - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-24 |  | 2019-08-06 | All West Unitary Authorities | 0 | 0 | 31601.87 | 252881.98 | 130734.12 | -74362.7 | 0 | 340855.27 | 0 | 340855.27 | 0 | [6 empty] | CM_WSNI | 100%
502510 | SVCD Water - WPS - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-16 | 2017-02-16 | 2017-04-03 |  | 2019-12-13 | All East Unitary Authorities | 0 | 0 | 17224.93 | 178302.8 | 1938209.68 | 124519.11 | 0.01 | 2258256.53 | 0 | 2258256.53 | 0 | [6 empty] | CM_WSNI | 100%
502513 | SVCD Water - WPS - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-05-05 | 2018-08-01 | 2018-08-01 | All North Unitary Authorities | 0 | 0 | 21368.42 | 95116.91 | -10926.97 | 0 | 0 | 105558.36 | 0 | 105558.36 | 0 | [6 empty] | CM_WSNI | 100%
502516 | SVCD Water - WPS - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-11-17 | 2019-07-08 | 2019-07-08 | All South Unitary Authorities | 0 | 0 | 14392.52 | 26318 | 1365314.36 | 4674.95 | 0 | 1410699.83 | 0 | 1410699.83 | 0 | [6 empty] | CM_WSNI | 100%
502519 | SVCD Water - WPS - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-09 | 2017-02-09 | 2017-11-24 |  | 2020-02-03 | All West Unitary Authorities | 0 | 0 | 15046.73 | 74121.03 | 1260551.48 | -58282.84 | 0.01 | 1291436.41 | 0 | 1291436.41 | 0 | [6 empty] | CM_WSNI | 100%
502521 | SVCD Water - WTW - Central - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-15 | 2018-08-09 | 2018-08-09 | Scottish Water Wide | 0 | 0 | 17009.35 | 222365.37 | 27709.43 | 0 | 0 | 267084.15 | 0 | 267084.15 | 0 | [6 empty] | CM_WSNI | 100%
502524 | SVCD Water - WTW - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-23 | 2017-02-23 | 2017-04-03 |  | 2019-12-13 | All East Unitary Authorities | 0 | 0 | 126302.07 | 1583071.16 | 528832.93 | 6542.06 | 0 | 2244748.22 | 0 | 2244748.22 | 0 | [6 empty] | CM_WSNI | 100%
502527 | SVCD Water - WTW - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-05-05 | 2019-05-03 | 2019-05-03 | All North Unitary Authorities | 0 | 0 | 121398.58 | 1476037.16 | 564341.53 | 0 | 0.01 | 2161777.28 | 0 | 2161777.28 | 0 | [6 empty] | CM_WSNI | 100%
502530 | SVCD Water - WTW - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-24 |  | 2019-12-02 | All South Unitary Authorities | 0 | 0 | 149801.52 | 1548484.61 | 768112.99 | 39587.45 | -172.18 | 2505814.39 | 0 | 2505814.39 | 0 | [6 empty] | CM_WSNI | 100%
502533 | SVCD Water - WTW - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-24 |  | 2019-12-13 | All West Unitary Authorities | 0 | 0 | 108598.13 | 1437275.46 | 1632266.81 | -260915.43 | 260915.43 | 3178140.4 | 0 | 3178140.4 | 0 | [6 empty] | CM_WSNI | 100%
503515 | SVCD WATER CENTRAL (MD) - Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-21 | 2019-03-21 | 2019-04-02 |  | 2020-04-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 29439.25 | 0 | 0 | 29439.25 | 0 | 29439.25 | 0 | [6 empty] | CM_WSI | 37.5% | CM_WSNI | 62.5%
503516 | SVCD WATER CENTRAL (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-03-21 | 2019-03-21 | 2019-04-02 |  | 2020-10-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 19626.17 | 188749.11 | 112624.72 | 321000 | 0 | 321000 | 0 | [6 empty] | CM_WSI | 37.5% | CM_WSNI | 62.5%
502032 | SVCD Water Central Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-05-23 | 2017-11-22 | 2017-11-22 | Scottish Water Wide | 0 | 0 | 45000 | 0 | -44999 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSI | 100%
502033 | SVCD Water Central Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-02-29 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 32710.28 | 502748.49 | -334919.11 | -13294.48 | 0 | 19204.24 | 206449.42 | 0 | 206449.42 | 0 | [6 empty] | CM_WSI | 100%
503031 | SVCD WATER CENTRAL PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 |  | 2020-03-16 | Scottish Water Wide | 0 | 0 | 0 | 98130.84 | 445611.51 | 119007.73 | 3998.68 | 666748.76 | 0 | 666748.76 | 0 | [6 empty] | CM_WSNI | 100%
503021 | SVCD WATER CENTRAL RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 |  | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 130841.12 | 894315.38 | 937644.2 | -262800.7 | 1700000 | 0 | 1700000 | 0 | [6 empty] | CM_WSNI | 100%
502138 | SVCD Water Central TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2017-03-27 | 2017-03-27 | Scottish Water Wide | 0 | 0 | 67316.24 | -67316.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
502139 | SVCD Water Central WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2018-03-19 | 2018-03-19 | Scottish Water Wide | 0 | 0 | 121710.28 | 101500 | -7255.1 | 0 | -19.76 | 215935.42 | 0 | 215935.42 | 0 | [6 empty] | CM_WSI | 100%
502140 | SVCD Water Central WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 32710.28 | 202735.38 | 7542.04 | -16813.89 | 872.69 | 15941.2 | 242987.7 | 0 | 242987.7 | 0 | [6 empty] | CM_WSI | 100%
503520 | SVCD WATER EAST (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-11 | 2019-03-11 | 2019-12-09 |  | 2021-09-01 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 23704.55 | 185784.11 | 36854 | 246342.66 | 116.98 | 246459.64 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503521 | SVCD WATER EAST (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-05-01 |  | 2020-12-30 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 107512.98 | 1071459.68 | 564689.83 | 1743662.49 | 0 | 1743662.49 | 0 | [6 empty] | CM_WSI | 29.53% | CM_WSNI | 70.47%
503519 | SVCD WATER EAST (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-03-13 | 2019-03-13 | 2019-09-02 |  | 2020-08-31 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 256947.94 | 4217590.22 | -465048.15 | 4009490.01 | 0 | 4009490.01 | 0 | [6 empty] | CM_WSI | 32.82% | CM_WSNI | 67.18%
502034 | SVCD Water East Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-03-31 | 2018-09-21 | 2018-09-21 | All East Unitary Authorities | 0 | 145953.27 | 255999.73 | 32587 | -41812.62 | 0 | 0.02 | 392727.4 | 0 | 392727.4 | 0 | [6 empty] | CM_WSI | 100%
502035 | SVCD Water East Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-02-29 | 2016-02-29 | 2016-04-01 |  | 2019-12-13 | All East Unitary Authorities | 0 | 62542.06 | 204859 | 14148 | -47931.31 | 0 | 0 | 233617.75 | 0 | 233617.75 | 0 | [6 empty] | CM_WSI | 100%
503027 | SVCD WATER EAST PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-25 | 2018-01-25 | 2018-01-30 |  | 2021-04-29 | All East Unitary Authorities | 0 | 0 | 0 | 141075 | 183536.47 | 338369.81 | 185205.43 | 848186.71 | 2944.83 | 851131.54 | 0 | [6 empty] | CM_WSNI | 100%
503028 | SVCD WATER EAST RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-02-20 |  | 2020-03-19 | All East Unitary Authorities | 0 | 0 | 0 | 203521.96 | 203593.12 | 590630.36 | -80199.2 | 917546.24 | 0 | 917546.24 | 0 | [6 empty] | CM_WSNI | 100%
503019 | SVCD WATER EAST RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-04-02 |  | 2020-02-20 | All East Unitary Authorities | 0 | 0 | 0 | 337074.17 | 5862329.77 | 815554.69 | 458449.72 | 7473408.35 | 0 | 7473408.35 | 0 | [6 empty] | CM_WSNI | 100%
502141 | SVCD Water East TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-04-18 | 2017-08-29 | 2017-08-29 | All East Unitary Authorities | 0 | 0 | 269177.57 | 37130.24 | 0 | 0 | 2673.64 | 308981.45 | 0 | 308981.45 | 0 | [6 empty] | CM_WSI | 100%
502142 | SVCD Water East TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-04-08 |  | 2019-12-13 | Scottish Water Wide | 0 | 0 | 388640.88 | 127289.64 | -34226.25 | 0 | 0 | 481704.27 | 0 | 481704.27 | 0 | [6 empty] | CM_WSI | 100%
502143 | SVCD Water East WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-29 | 2016-03-29 | 2016-04-08 |  | 2019-11-25 | All East Unitary Authorities | 0 | 0 | 24588.79 | 80000 | 228.88 | 24281.81 | -21510.68 | 107588.8 | 0 | 107588.8 | 0 | [6 empty] | CM_WSI | 100%
502144 | SVCD Water East WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-29 | 2016-03-29 | 2016-04-01 |  | 2019-12-13 | All East Unitary Authorities | 0 | 0 | 271746.44 | 66372.56 | -32058.85 | 0 | 0 | 306060.15 | 0 | 306060.15 | 0 | [6 empty] | CM_WSI | 100%
502145 | SVCD Water East WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-27 |  | 2020-07-17 | All East Unitary Authorities | 0 | 0 | 673737.69 | 951148.04 | -241284.5 | 26166.29 | 33047.88 | 1442815.4 | 0 | 1442815.4 | 0 | [6 empty] | CM_WSI | 100%
502146 | SVCD Water East WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-01 |  | 2019-12-13 | All East Unitary Authorities | 0 | 43766.36 | 1637034.29 | 522640.5 | 61527.13 | 1038.97 | 0 | 2266007.25 | 0 | 2266007.25 | 0 | [6 empty] | CM_WSI | 100%
503509 | SVCD WATER NORTH (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-03-21 | 2019-03-21 | 2019-06-10 |  | 2021-07-06 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 106670.38 | 1011794.39 | 489491.66 | 1607956.43 | 71.92 | 1608028.35 | 0 | [6 empty] | CM_WSNI | 45% | CM_WSI | 55%
503510 | SVCD WATER NORTH (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-20 | 2019-03-20 | 2019-07-05 |  | 2021-06-08 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 23704.55 | 549663.54 | 46896.89 | 620264.98 | 0 | 620264.98 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
503508 | SVCD WATER NORTH (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-26 | 2019-03-26 | 2020-02-06 |  | 2021-12-08 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 200.37 | 4158752.64 | 815887.01 | 4974840.02 | 391656.03 | 5366496.05 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
502036 | SVCD Water North Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-04-08 | 2018-12-11 | 2018-12-11 | All North Unitary Authorities | 0 | 110757.01 | 652461.22 | 1081310.1 | 116422.09 | 2701.79 | 0.04 | 1963652.25 | 0 | 1963652.25 | 0 | [6 empty] | CM_WSI | 100%
502037 | SVCD Water North Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-15 | 2017-11-02 | 2017-11-02 | All North Unitary Authorities | 0 | 49720 | 348294.43 | -9814.17 | 0 | 0 | 0 | 388200.26 | 0 | 388200.26 | 0 | [6 empty] | CM_WSI | 100%
503023 | SVCD WATER NORTH PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-07 | 2018-02-07 | 2018-02-21 |  | 2020-06-26 | All North Unitary Authorities | 0 | 0 | 0 | 362716.97 | 3048347.65 | 864972.93 | 545.91 | 4276583.46 | 0 | 4276583.46 | 0 | [6 empty] | CM_WSNI | 100%
503024 | SVCD WATER NORTH RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-21 |  | 2020-04-21 | All North Unitary Authorities | 0 | 0 | 0 | 70456.69 | 441765.39 | 127498.44 | 1127.89 | 640848.41 | 0 | 640848.41 | 0 | [6 empty] | CM_WSNI | 100%
503017 | SVCD WATER NORTH RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2019-09-11 | 2019-09-11 | All North Unitary Authorities | 0 | 0 | 0 | 252897.2 | 4588934.28 | 344429.01 | -2261.32 | 5183999.17 | 0 | 5183999.17 | 0 | [6 empty] | CM_WSNI | 100%
502147 | SVCD Water North TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-04-25 | 2018-09-03 | 2018-09-03 | All North Unitary Authorities | 0 | 0 | 209475.38 | 230476.25 | -102975.12 | 0 | 0.13 | 336976.64 | 0 | 336976.64 | 0 | [6 empty] | CM_WSI | 100%
502148 | SVCD Water North TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2018-07-26 | 2018-07-26 | All North Unitary Authorities | 0 | 15832 | 146168 | 26135.14 | 0 | 0 | 0 | 188135.14 | 0 | 188135.14 | 0 | [6 empty] | CM_WSI | 100%
502149 | SVCD Water North WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2018-04-19 | 2018-04-19 | All North Unitary Authorities | 0 | 12300 | 1285.71 | 9841.53 | -32.79 | 0 | 0.01 | 23394.46 | 0 | 23394.46 | 0 | [6 empty] | CM_WSI | 100%
502150 | SVCD Water North WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2017-11-01 | 2017-11-01 | All North Unitary Authorities | 0 | 5299 | 125701 | -3882.42 | 0 | 0 | 0 | 127117.58 | 0 | 127117.58 | 0 | [6 empty] | CM_WSI | 100%
502151 | SVCD Water North WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-22 | 2016-04-22 | 2016-04-25 | 2018-09-03 | 2018-09-03 | All North Unitary Authorities | 0 | 0 | 218846.77 | 340785.59 | 17515.54 | 0 | 0.01 | 577147.91 | 0 | 577147.91 | 0 | [6 empty] | CM_WSI | 100%
502152 | SVCD Water North WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2018-07-26 | 2018-07-26 | All North Unitary Authorities | 0 | 36897.2 | 1392363.33 | 325043.84 | 0 | 0 | 0 | 1754304.37 | 0 | 1754304.37 | 0 | [6 empty] | CM_WSNI | 100%
503513 | SVCD WATER SOUTH (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-06-24 |  | 2021-03-31 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 35556.79 | 389637.17 | 296468.84 | 721662.8 | 0 | 721662.8 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503514 | SVCD WATER SOUTH (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-05-01 |  | 2020-08-03 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 47409.04 | 1135052.11 | 0 | 1182461.15 | 0 | 1182461.15 | 0 | [6 empty] | CM_WSI | 40% | CM_WSNI | 60%
503512 | SVCD WATER SOUTH (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-27 | 2019-03-27 | 2020-02-06 |  | 2021-03-30 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 6596968.96 | -913797.29 | 5683171.67 | 164.34 | 5683336.01 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
502038 | SVCD Water South Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-03-22 | 2016-03-22 | 2016-04-08 | 2018-06-26 | 2018-06-26 | All South Unitary Authorities | 0 | 165579.44 | 253284.43 | 2138667.06 | 415059.18 | 12848.88 | 2424.47 | 2987863.46 | 0 | 2987863.46 | 0 | [6 empty] | CM_WSI | 100%
502039 | SVCD Water South Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-08-24 | 2018-02-01 | 2018-02-01 | All South Unitary Authorities | 0 | 70981.31 | 482034.06 | 54779.44 | 0 | 0 | 0.01 | 607794.82 | 0 | 607794.82 | 0 | [6 empty] | CM_WSI | 100%
503025 | SVCD WATER SOUTH PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-06 | 2018-02-06 | 2018-02-08 |  | 2020-09-29 | All South Unitary Authorities | 0 | 0 | 0 | 140367.72 | 626293.31 | 383617.71 | 533482.26 | 1683761 | 71900.47 | 1755661.47 | 0 | [6 empty] | CM_WSNI | 100%
503026 | SVCD WATER SOUTH RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-06 | 2018-02-06 | 2018-02-08 |  | 2020-03-24 | All South Unitary Authorities | 0 | 0 | 0 | 52336.45 | 834902.36 | 522152.24 | 92677.2 | 1502068.25 | 0 | 1502068.25 | 0 | [6 empty] | CM_WSNI | 100%
503018 | SVCD WATER SOUTH RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-21 | 2018-02-21 | 2018-02-21 |  | 2019-12-19 | All South Unitary Authorities | 0 | 0 | 0 | 413617.36 | 6053747.66 | 554389.94 | -71754.96 | 6950000 | 0 | 6950000 | 0 | [6 empty] | CM_WSNI | 100%
502153 | SVCD Water South TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-04-06 | 2016-04-06 | 2016-04-25 | 2018-09-27 | 2018-09-27 | All South Unitary Authorities | 0 | 0 | 70949.7 | 381751.72 | 109276.17 | 8266.44 | 3178.98 | 573423.01 | 0 | 573423.01 | 0 | [6 empty] | CM_WSI | 100%
502154 | SVCD Water South TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-06-08 | 2017-09-08 | 2017-09-08 | All South Unitary Authorities | 0 | 0 | 127167.83 | 56685.77 | 0 | 0 | 0 | 183853.6 | 0 | 183853.6 | 0 | [6 empty] | CM_WSI | 100%
502155 | SVCD Water South WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2017-11-21 | 2017-11-21 | All South Unitary Authorities | 0 | 0 | 17595.14 | 79419.08 | -8664.8 | 0 | 0.01 | 88349.43 | 0 | 88349.43 | 0 | [6 empty] | CM_WSI | 100%
502156 | SVCD Water South WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2017-09-08 | 2017-09-08 | All South Unitary Authorities | 0 | 0 | 53560.59 | 53286.22 | 0 | 0 | 1034.22 | 107881.03 | 0 | 107881.03 | 0 | [6 empty] | CM_WSI | 100%
502157 | SVCD Water South WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-04-22 | 2016-04-22 | 2016-04-25 |  | 2019-08-08 | All South Unitary Authorities | 0 | 0 | 99583.18 | 107261.47 | 162301.46 | -61007.82 | 9229.11 | 317367.4 | 0 | 317367.4 | 0 | [6 empty] | CM_WSI | 100%
502158 | SVCD Water South WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-05-09 | 2018-02-01 | 2018-02-01 | All South Unitary Authorities | 0 | 0 | 1077856.28 | 330233.7 | 0 | 0 | 0.01 | 1408089.99 | 0 | 1408089.99 | 0 | [6 empty] | CM_WSI | 100%
503535 | SVCD WATER WEST (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-27 | 2019-03-27 | 2019-04-08 | 2019-12-23 | 2020-01-23 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 174203.92 | 6165.18 | 180369.1 | 0 | 180369.1 | 0 | [6 empty] | CM_WSI | 30% | CM_WSNI | 70%
503536 | SVCD WATER WEST (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-28 | 2019-03-28 | 2019-05-02 |  | 2019-12-23 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 1071008.72 | 212507.27 | 1283515.99 | 0 | 1283515.99 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
503534 | SVCD WATER WEST (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2019-03-28 | 2019-03-28 | 2020-02-06 |  | 2021-03-02 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 8182025.18 | -1981093.19 | 6200931.99 | 0 | 6200931.99 | 0 | [6 empty] | CM_WSNI | 40% | CM_WSI | 60%
502048 | SVCD Water West Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-02 | 2016-03-02 | 2016-05-19 |  | 2019-12-09 | All West Unitary Authorities | 0 | 183439.25 | 281320.18 | 507766.29 | 16550.53 | 331616.99 | 64911.76 | 1385605 | 0 | 1385605 | 0 | [6 empty] | CM_WSI | 100%
502047 | SVCD Water West Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-05-13 |  | 2019-02-20 | All West Unitary Authorities | 0 | 78635.51 | 60045.48 | 32529.88 | -74136.95 | 0 | 0.08 | 97074 | 0 | 97074 | 0 | [6 empty] | CM_WSI | 100%
503029 | SVCD WATER WEST PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 |  | 2020-01-03 | All West Unitary Authorities | 0 | 0 | 0 | 213640.19 | 1051143.9 | 687377.74 | 379517.76 | 2331679.59 | 0 | 2331679.59 | 0 | [6 empty] | CM_WSNI | 100%
503030 | SVCD WATER WEST RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 |  | 2020-01-31 | All West Unitary Authorities | 0 | 0 | 0 | 249845.79 | 1106561.68 | 810904.12 | -12956.79 | 2154354.8 | 0 | 2154354.8 | 0 |  |  |  |  | 88547 |  | CM_WSNI | 100%
503020 | SVCD WATER WEST RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-26 | 2018-02-26 | 2018-03-01 |  | 2020-01-17 | All West Unitary Authorities | 0 | 0 | 0 | 219485.98 | 6637546.25 | 602557.11 | 333624.5 | 7793213.84 | 0 | 7793213.84 | 0 | [6 empty] | CM_WSNI | 100%
502160 | SVCD Water West TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-04-22 |  | 2019-12-09 | All West Unitary Authorities | 0 | 0 | 138020.41 | 186358.95 | -15285.33 | 37765.06 | 0 | 346859.09 | 0 | 346859.09 | 0 | [6 empty] | CM_WSI | 100%
502161 | SVCD Water West TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-05-23 |  | 2020-02-21 | All West Unitary Authorities | 0 | 0 | 105365.81 | 41659.55 | 0 | -4564.24 | 4564.24 | 147025.36 | 0 | 147025.36 | 0 | [6 empty] | CM_WSI | 100%
502162 | SVCD Water West WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-11 | 2016-04-11 | 2016-04-11 |  | 2020-01-15 | All West Unitary Authorities | 0 | 0 | 237004.65 | 146493.16 | 49794.97 | 53485.52 | 69914.48 | 556692.78 | 0 | 556692.78 | 0 | [6 empty] | CM_WSI | 100%
502163 | SVCD Water West WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-06-13 | 2019-06-12 | 2019-06-12 | All West Unitary Authorities | 0 | 0 | 165119.01 | 57968 | 40937.33 | -2353.55 | 0 | 261670.79 | 0 | 261670.79 | 0 | [6 empty] | CM_WSI | 100%
502164 | SVCD Water West WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-11 | 2016-04-11 | 2016-04-11 |  | 2020-01-10 | All West Unitary Authorities | 0 | 0 | 319960.53 | 491106 | 20074.58 | -18497.8 | 260000 | 1072643.31 | 0 | 1072643.31 | 0 | [6 empty] | CM_WSI | 100%
502165 | SVCD Water West WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-04-06 | 2016-04-06 | 2016-06-13 | 2020-12-31 | 2020-01-07 | All West Unitary Authorities | 0 | 0 | 624710.98 | 130681.07 | 51154.95 | -21746.03 | 20289.68 | 805090.65 | 0 | 805090.65 | 0 | [6 empty] | CM_WSI | 100%
402878 | SVCM Brachmont TWP Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-08-31 | 2013-02-11 | 2013-03-04 | 2013-07-23 |  | Aberdeenshire | 142224.8 | 7729.6 | 0 | 0 | 0 | 0 | 0 | 7729.6 | 0 | 149954.4 | 0 | [6 empty] | CM_WSNI | 100%
402291 | SVCM Domestic Night Use Allowance Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-08-29 | 2014-11-03 | 2014-11-03 | 2015-10-30 |  | Scottish Water Wide | 75444.39 | 12743.6 | 0 | 0 | 0 | 0 | 0 | 12743.6 | 0 | 88187.99 | 0 | [6 empty] | CM_WSI | 100%
401355 | SVCM Lochmill Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-11-18 | 2011-12-05 | 2015-10-02 | 2012-06-20 | Fife | 32773 | -2504.75 | 0 | 0 | 0 | 0 | 0 | -2504.75 | 0 | 30268.25 | 0 | [6 empty] | CM_WSI | 100%
400851 | SVCM South Trunk Main Restoration of Cathodic Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-05-10 | 2011-10-03 | 2012-01-13 | 2015-08-20 |  | Aberdeenshire | 48958 | 0 | 0.28 | -206.91 | 0 | 0 | 206.91 | 0.28 | 0 | 48958.28 | 0 | [6 empty] | CM_WSI | 100%
402458 | SVCM Strategic Network Modelling of Central Belt | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-12-01 | 2012-01-16 | 2012-01-16 | 2017-06-12 |  | Scottish Water Wide | 141733 | 0 | 0 | -136295.02 | 0 | 0 | 0 | -136295.02 | 0 | 5437.98 | 0 | [6 empty] | CM_WSI | 100%
500554 | SVCM Water East Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-30 | 2015-06-30 | 2015-07-24 | 2018-02-12 | 2018-02-12 | All East Unitary Authorities | 0 | 840292 | 515764.24 | 391710.38 | 0 | 0 | 733.64 | 1748500.26 | 0 | 1748500.26 | 0 | [6 empty] | CM_WSI | 100%
500522 | SVCM Water East Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-05-19 | 2015-05-19 | 2015-05-19 |  | 2019-12-13 | All East Unitary Authorities | 0 | 562180 | -93179 | 180067 | -211699.91 | 0 | 0 | 437368.09 | 0 | 437368.09 | 0 | [6 empty] | CM_WSI | 100%
402677 | SVCW - Chryston (Berryknowes) - Install new pumping station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-06-07 | 2013-01-18 | 2013-04-23 | 2016-08-08 |  | North Lanarkshire | 70817 | 336926.18 | 47013.59 | 118.59 | 554.49 | 0 | 0.17 | 384613.02 | 0 | 455430.02 | 0 | [6 empty] | CM_WWNI | 100%
403258 | SVCW Montrose WwTW Inlet Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-01-14 | 2013-04-18 | 2013-09-10 | 2015-02-10 |  | Moray | 251584.98 | -584.98 | 0 | -776.74 | 0 | 0 | 0 | -1361.72 | 0 | 250223.26 | 0 | [6 empty] | CM_WWNI | 100%
402693 | SVCW Philip Murry Rd Bellshill - EMERGENCY Sewer repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-06-13 | 2012-09-14 | 2012-11-28 | 2014-01-13 |  | North Lanarkshire | 109228 | -155.99 | 0 | 0 | 0 | 0 | 0 | -155.99 | 0 | 109072.01 | 0 | [6 empty] | CM_WWI | 100%
401867 | SVCW Baddingsgill Reservoir Failed Bridges Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-22 | 2016-06-29 | 2016-07-01 | 2018-02-16 | 2018-02-16 | Scottish Borders | 40851 | 23526 | 16363.87 | -113.38 | 0 | 0 | -232.73 | 39543.76 | 0 | 80394.76 | 0 | [6 empty] | CM_WSI | 100%
401359 | SVCW Balgillie Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2012-10-29 | 2013-02-11 | 2013-08-02 | 2013-08-02 | Fife | 211365 | -183.73 | 0 | 0 | 0 | 0 | 0 | -183.73 | 0 | 211181.27 | 0 | [6 empty] | CM_WSI | 100%
401422 | SVCW Belmore WTW - provision of raw water colour - turbidity monitors | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-23 | 2011-06-21 | 2011-05-24 | 2011-07-30 |  | Argyll and Bute-Cowal & Bute | 25106.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25106.47 | 0 | [6 empty] | CM_WSNI | 100%
403560 | SVCW Black Esk WTW - CWT Roof Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-08-26 | 2014-01-24 | 2014-02-20 | 2014-09-17 |  | Dumfries and Galloway | 182048 | 0 | -268.82 | 0 | 0 | 0 | 0 | -268.82 | 0 | 181779.18 | 0 | [6 empty] | CM_WSNI | 100%
402189 | SVCW Blackhills Collection System Final Decommissioning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-15 | 2017-11-28 | 2017-11-28 | 2017-09-29 |  | Aberdeenshire | 3000 | 0 | 2962.5 | 3968.51 | 0 | 0 | 0 | 6931.01 | 0 | 9931.01 | 0 | [6 empty] | CM_WSI | 100%
400875 | SVCW Boardhouse WTW Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-20 | 2012-01-12 | 2012-01-30 | 2012-07-16 |  | Orkney Islands | 65294 | 4255.47 | 0 | 0 | 0 | 0 | 0 | 4255.47 | 0 | 69549.47 | 0 | [6 empty] | CM_WSNI | 100%
402249 | SVCW Braeface Burst Control | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-18 | 2011-12-21 | 2012-01-30 | 2013-12-18 |  | Falkirk | 195235 | -176.88 | 0 | 0 | 0 | 0 | 0 | -176.88 | 0 | 195058.12 | 0 | [6 empty] | CM_WSI | 100%
403194 | SVCW Broxburn Greendyke Rd External Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-18 | 2013-09-26 | 2013-12-05 | 2014-07-07 |  | West Lothian | 160073 | 904 | -475.73 | 0 | 0 | 0 | 0 | 428.27 | 0 | 160501.27 | 0 | [6 empty] | CM_WWI | 100%
403783 | SVCW Business Change Stabilisation and Improvement Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-07 | 2014-05-07 | 2014-11-17 | 2015-10-30 |  | Scottish Water Wide | 597788 | -53131.97 | 0 | 0 | 0 | 0 | -49.33 | -53181.3 | 0 | 544606.7 | 0 | [6 empty] | CM_M&G | 100%
402977 | SVCW Calliness Road SPS Drummore - Replacment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-19 | 2013-04-24 | 2013-12-13 | 2016-04-29 |  | Dumfries and Galloway | 180690 | 3000 | 108895.97 | 0 | -2394.77 | 0 | 0 | 109501.2 | 0 | 290191.2 | 0 | [6 empty] | CM_WWI | 100%
400976 | SVCW Cameron Reservoir - Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-15 | 2011-06-28 | 2011-10-24 | 2012-12-18 | 2012-12-18 | Fife | 32244 | 261.71 | 0 | 0 | 0 | 0 | 0 | 261.71 | 0 | 32505.71 | 0 | [6 empty] | CM_WSI | 100%
403049 | SVCW Carmunnock Road Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-05-17 | 2014-02-04 | 2014-02-17 | 2014-08-22 |  | Glasgow City | 257873 | 401 | -798.67 | 0 | 0 | 0 | 0 | -397.67 | 0 | 257475.33 | 0 | [6 empty] | CM_WWI | 100%
500637 | SVCW Coastguard SPS - Replacement of 7nr Sets of Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-26 | 2015-06-17 | 2015-09-11 | 2015-10-02 | 2016-01-25 | Na H-Eileanan an Iar | 0 | 195031.16 | 0 | 0 | 0 | 0 | 0 | 195031.16 | 0 | 195031.16 | 0 | [6 empty] | CM_WWNI | 100%
400897 | SVCW Coulter WTW Second Stage Filter Remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-25 | 2012-10-31 | 2012-11-19 | 2015-06-25 |  | South Lanarkshire | 151320 | 37704.53 | 0 | 0 | 0 | 0 | 0 | 37704.53 | 0 | 189024.53 | 0 | [6 empty] | CM_WSNI | 100%
403892 | SVCW Cowdenbeath Perth Road Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-06-30 | 2014-10-23 | 2014-12-19 | 2015-05-04 |  | Fife | 222925 | -1330 | -0.3 | -237.35 | 0 | 0 | 0 | -1567.65 | 0 | 221357.35 | 0 | [6 empty] | CM_WWI | 100%
401966 | SVCW Craigluscar EW Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-04-01 | 2011-10-25 | 2011-11-21 | 2012-10-22 | 2012-10-22 | Fife | 26953 | -368.26 | 0 | 0 | 0 | 0 | 0 | -368.26 | 0 | 26584.74 | 0 | [6 empty] | CM_WSI | 100%
403492 | SVCW Deanburn Park Linlithgow Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-05-15 | 2013-08-12 | 2013-08-26 | 2014-03-25 |  | West Lothian | 272203 | 619 | -1246.19 | 0 | 0 | 0 | 0 | -627.19 | 0 | 271575.81 | 0 | [6 empty] | CM_WWI | 100%
403632 | SVCW DI Metering Estate Investment SR15 - ES | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-01-24 | 2016-10-13 | 2016-10-13 | 2016-09-23 |  | Scottish Water Wide | 127094.78 | 1.22 | 0 | 0 | 0 | 0 | -1.22 | 0 | 0 | 127094.78 | 0 | [6 empty] | CM_WSI | 100%
403719 | SVCW DMA Optimisation East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-04-24 | 2014-05-12 | 2014-05-12 | 2015-10-26 |  | Scottish Water Wide | 100000 | -4099.41 | 0 | 0 | 0 | 0 | 0 | -4099.41 | 0 | 95900.59 | 0 | [6 empty] | CM_WSI | 100%
403720 | SVCW DMA Optimisation West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-04-24 | 2014-05-12 | 2014-05-12 | 2015-10-26 |  | Scottish Water Wide | 143000 | -40405.45 | 0 | 0 | 0 | 0 | 0 | -40405.45 | 0 | 102594.55 | 0 | [6 empty] | CM_WSI | 100%
403083 | SVCW Don Area Emergency Generators | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2012-11-12 | 2012-11-12 | 2012-12-10 | 2020-03-23 |  | All East Unitary Authorities | 177164.84 | 0.16 | 0 | 0 | 0 | 65.87 | -0.16 | 65.87 | 0 | 177230.71 | 0 | [6 empty] | CM_WSNI | 100%
401214 | SVCW Don Cluster 1 Aldroughty Hotspot | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2013-07-28 | 2013-11-28 | 2016-05-20 |  | Aberdeenshire | 42093 | 142263 | 6182 | 831.14 | -221.88 | 0 | 0.01 | 149054.27 | 0 | 191147.27 | 0 | [6 empty] | CM_WSI | 100%
403056 | SVCW Dreghorn Sewer Network EPI Resolution | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2016-06-13 | 2016-06-13 | 2016-06-13 |  | North Ayrshire | 30390 | 9056 | -511.3 | 0 | 0 | 0 | 0 | 8544.7 | 0 | 38934.7 | 0 | [6 empty] | CM_WWI | 100%
402570 | SVCW East Wastewater Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-04-23 | 2015-04-24 |  | All East Unitary Authorities | 175520 | -3520 | 0 | -1916.37 | 0 | 0 | 0 | -5436.37 | 0 | 170083.63 | 0 | [6 empty] | CM_WWI | 100%
402569 | SVCW East Wastewater Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-04-09 | 2015-07-14 |  | All East Unitary Authorities | 261995 | 5 | 0 | -2460.31 | 0 | 0 | 0 | -2455.31 | 0 | 259539.69 | 0 | [6 empty] | CM_WWI | 100%
402562 | SVCW East Water Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-22 | 2012-02-22 | 2012-04-23 | 2015-07-14 |  | All East Unitary Authorities | 345333 | 7483.79 | 7183.46 | -6875.05 | 0 | 0 | 0 | 7792.2 | 0 | 353125.2 | 0 | [6 empty] | CM_WSI | 100%
402543 | SVCW East Water Non-Infra - 2012-2013 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2016-05-30 |  | All East Unitary Authorities | 1214989 | -5250.47 | 0 | 0 | 0 | 0 | 0 | -5250.47 | 0 | 1209738.53 | 0 | [6 empty] | CM_WSNI | 100%
402561 | SVCW East Water Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2016-09-26 | 2015-08-26 | All East Unitary Authorities | 472428 | 47865.24 | 18536.06 | 1401.7 | 0 | 0 | 250.68 | 68053.68 | 0 | 540481.68 | 0 | [6 empty] | CM_WSNI | 100%
403508 | SVCW Facilities East Office Review | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-04-29 | 2015-06-22 | 2015-06-22 | 2015-06-18 |  | Scottish Water Wide | 65000 | -5797 | 0 | 0 | 0 | 0 | 778.06 | -5018.94 | 0 | 59981.06 | 0 | [6 empty] | CM_M&G | 100%
403509 | SVCW Facilities North Office Inverness Review | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-04-29 | 2015-06-08 | 2015-06-08 | 2015-06-08 |  | Highland | 5000 | -3837.5 | 0 | 0 | 0 | 0 | 1583.02 | -2254.48 | 0 | 2745.52 | 0 | [6 empty] | CM_M&G | 100%
403173 | SVCW Fort William Ben Nevis Distillery WWPS - Access Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-21 | 2017-08-22 | 2017-10-24 | 2018-01-18 |  | Highland | 24971 | 60 | 12908.06 | 46880.38 | 280 | 0 | 0 | 60128.44 | 0 | 85099.44 | 0 | [6 empty] | CM_WWNI | 100%
402954 | SVCW Gatehouse STW - Surcharging Problem | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-19 | 2018-03-23 | 2018-03-23 | 2018-03-23 |  | Dumfries and Galloway | 44238 | 0 | 1732.15 | 5480.06 | 0 | 0 | 0 | 7212.21 | 0 | 51450.21 | 0 | [6 empty] | CM_WWI | 100%
402639 | SVCW Glasgow Sludge Pumping Mains monitoring equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-03-29 | 2012-03-29 | 2012-10-10 | 2019-08-06 |  | Glasgow City | 35000 | 0 | -3132.34 | -641.24 | 0 | 0 | 0 | -3773.58 | 0 | 31226.42 | 0 | [6 empty] | CM_WWNI | 100%
401358 | SVCW Glendevon Upper Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-10 | 2012-11-30 | 2013-01-09 | 2014-04-17 | 2014-04-07 | Perth and Kinross | 99055 | -1558 | 174.82 | 0 | 0 | 0 | 0 | -1383.18 | 0 | 97671.82 | 0 | [6 empty] | CM_WSI | 100%
402504 | SVCW Glenfarg (East) Reservoir - valve refurbishment and safety work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-02 | 2013-12-17 | 2014-02-24 | 2014-08-15 | 2014-05-01 | Perth and Kinross | 28574 | -4127.67 | 0 | 0 | 0 | 0 | 0 | -4127.67 | 0 | 24446.33 | 0 | [6 empty] | CM_WSI | 100%
401360 | SVCW Glenogil Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2012-02-17 | 2012-08-27 | 2013-07-11 | 2013-07-11 | Angus | 65091.92 | 3392.39 | 0 | 0 | 0 | 0 | 0 | 3392.39 | 0 | 68484.31 | 0 | [6 empty] | CM_WSI | 100%
401363 | SVCW Glensherup Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2013-05-28 | 2013-08-08 | 2014-10-10 | 2014-12-10 | Perth and Kinross | 155192 | -913 | -259.51 | 0 | 0 | 0 | 0 | -1172.51 | 0 | 154019.49 | 0 | [6 empty] | CM_WSI | 100%
402699 | SVCW Gonfirth WSZ Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2014-05-16 | 2014-07-01 | 2014-12-17 |  | Shetland Islands | 28303 | -20043.02 | 0 | 0 | 0 | 0 | 0 | -20043.02 | 0 | 8259.98 | 0 | [6 empty] | CM_WSI | 100%
401986 | SVCW Gowanbank SR Flowmeter Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-23 | 2012-02-23 | 2012-04-23 | 2015-01-12 |  | Falkirk | 65817 | -10228.77 | 0 | 0 | 0 | 0 | 0 | -10228.77 | 0 | 55588.23 | 0 | [6 empty] | CM_WSI | 100%
403740 | SVCW Grantown WWTW - Temporary SAF Plant - ASP Selector zone | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-26 | 2014-03-11 | 2014-03-11 | 2015-01-13 |  | Highland | 82655.27 | 71.69 | 0 | 0 | 0 | 0 | 0 | 71.69 | 0 | 82726.96 | 0 | [6 empty] | CM_WWNI | 100%
402163 | SVCW Head of Works STC Lime Dust Extraction System | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-08-01 | 2012-07-31 | 2012-11-12 | 2015-03-25 |  | Orkney Islands | 143701 | -7018.14 | 0 | 0 | 0 | 0 | 0 | -7018.14 | 0 | 136682.86 | 0 | [6 empty] | CM_M&G | 100%
403073 | SVCW HL Central Water Infra SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-11-07 | 2012-11-07 | 2013-01-04 | 2017-03-17 |  | Scottish Water Wide | 532500 | 17500 | -100492.18 | -2451.02 | 0 | 0 | 0 | -85443.2 | 0 | 447056.8 | 0 | [6 empty] | CM_WSI | 100%
403072 | SVCW HL Central Water Non-Infra SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-11-07 | 2012-11-07 | 2013-01-04 | 2016-12-07 |  | Scottish Water Wide | 581099 | 618901 | -144867.18 | -3263 | 0 | 0 | 3263 | 474033.82 | 0 | 1055132.82 | 0 | [6 empty] | CM_WSNI | 100%
403364 | SVCW HL East Wastewater Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2016-06-17 |  | All East Unitary Authorities | 250000 | -10000 | -41888.96 | 0 | 0 | 0 | 0 | -51888.96 | 0 | 198111.04 | 0 | [6 empty] | CM_WWI | 100%
403366 | SVCW HL East Wastewater Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2016-02-01 |  | All East Unitary Authorities | 23510 | 51146.37 | 2398.26 | -1518.57 | 0 | 0 | 0 | 52026.06 | 0 | 75536.06 | 0 | [6 empty] | CM_WWI | 100%
403365 | SVCW HL East Wastewater Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2016-08-01 |  | All East Unitary Authorities | 6000000 | -436606 | -153872.78 | -3441 | 0 | 0 | 3441 | -590478.78 | 0 | 5409521.22 | 0 | [6 empty] | CM_WWI | 100%
403367 | SVCW HL East Wastewater Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2016-01-05 |  | All East Unitary Authorities | 151539 | 92090 | -17848 | -973.95 | 0 | 0 | 0 | 73268.05 | 0 | 224807.05 | 0 | [6 empty] | CM_WWNI | 100%
403384 | SVCW HL East Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-25 | 2013-02-25 | 2013-03-01 | 2016-06-29 |  | All East Unitary Authorities | 1047033 | 194319 | -103308.95 | 0 | 0 | 0 | 2380.14 | 93390.19 | 0 | 1140423.19 | 0 | [6 empty] | CM_WSI | 100%
403386 | SVCW HL East Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-08 | 2016-12-20 |  | All East Unitary Authorities | 628606 | 270671 | -142822.88 | -10514.7 | 0 | 0 | 101.5 | 117434.92 | 0 | 746040.92 | 0 | [6 empty] | CM_WSI | 100%
403385 | SVCW HL East Water Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-02-25 | 2013-02-25 | 2013-03-01 | 2018-08-14 |  | All East Unitary Authorities | 2899130 | 231703.85 | 17163 | -5626.81 | 0 | 0 | 0 | 243240.04 | 0 | 3142370.04 | 0 | [6 empty] | CM_WSNI | 100%
403387 | SVCW HL East Water Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2017-01-23 |  | All East Unitary Authorities | 1169471 | 217035 | -38245.73 | 354.86 | 140.3 | -8.22 | 8.23 | 179284.44 | 0 | 1348755.44 | 0 | [6 empty] | CM_WSNI | 100%
403370 | SVCW HL North Wastewater Non-Infra (Treatment) 2013-2014 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-04-12 | 2015-01-06 |  | All North Unitary Authorities | 1436032.84 | -1151.65 | 0 | 0 | 0 | 0 | 0 | -1151.65 | 0 | 1434881.19 | 0 | [6 empty] | CM_WWI | 100%
403388 | SVCW HL North Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-15 | 2013-02-15 | 2013-03-29 | 2015-08-19 |  | All North Unitary Authorities | 530000 | 121604.76 | 0 | 0 | 0 | 0 | 0 | 121604.76 | 0 | 651604.76 | 0 | [6 empty] | CM_WSI | 100%
403390 | SVCW HL North Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2015-12-15 |  | All North Unitary Authorities | 1054647 | 162833.39 | 1638.05 | -5140.5 | 0 | 0 | 0 | 159330.94 | 0 | 1213977.94 | 0 | [6 empty] | CM_WSI | 100%
403391 | SVCW HL North Water Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-08 | 2015-12-15 |  | All North Unitary Authorities | 1239176 | 365485.68 | 0 | 0 | 0 | 0 | 0 | 365485.68 | 0 | 1604661.68 | 0 | [6 empty] | CM_WSNI | 100%
403372 | SVCW HL South Wastewater Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2015-09-01 |  | All South Unitary Authorities | 300000 | 126662.21 | 0 | 0 | 0 | 0 | 0 | 126662.21 | 0 | 426662.21 | 0 | [6 empty] | CM_WWI | 100%
403374 | SVCW HL South Wastewater Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2017-03-01 |  | All South Unitary Authorities | 238883 | 214057 | -85874.38 | 13231.27 | 0 | 0 | -166.36 | 141247.53 | 0 | 380130.53 | 0 | [6 empty] | CM_WWI | 100%
403373 | SVCW HL South Wastewater Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-01 | 2016-05-30 |  | All South Unitary Authorities | 4571700 | 481915.02 | 60 | 0 | 0 | 0 | 0.23 | 481975.25 | 0 | 5053675.25 | 0 | [6 empty] | CM_WWI | 100%
403392 | SVCW HL South Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-15 | 2013-02-15 | 2013-03-29 | 2015-09-10 |  | All South Unitary Authorities | 1408805.24 | -36530.38 | 0 | 0 | 0 | 0 | 0 | -36530.38 | 0 | 1372274.86 | 0 | [6 empty] | CM_WSI | 100%
403394 | SVCW HL South Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2015-11-27 |  | All South Unitary Authorities | 44268 | 532 | -1228.4 | 17.68 | 0 | 0 | -17.68 | -696.4 | 0 | 43571.6 | 0 | [6 empty] | CM_WSI | 100%
403393 | SVCW HL South Water Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-02-21 | 2013-02-21 | 2013-03-29 | 2015-10-08 |  | All South Unitary Authorities | 2800000 | -73845.04 | 0 | 0 | 0 | 0 | 0 | -73845.04 | 0 | 2726154.96 | 0 | [6 empty] | CM_WSNI | 100%
403377 | SVCW HL West Wastewater Infra 2013-2015 CID | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-20 | 2013-02-20 | 2013-03-01 | 2016-06-30 |  | All West Unitary Authorities | 1088995.75 | 257342.25 | 871.4 | 0 | 0 | 0 | 0 | 258213.65 | 0 | 1347209.4 | 0 | [6 empty] | CM_WWI | 100%
403396 | SVCW HL West Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-29 | 2016-05-30 |  | All West Unitary Authorities | 275000 | 49000 | -74700.09 | 0 | 0 | 0 | 0 | -25700.09 | 0 | 249299.91 | 0 | [6 empty] | CM_WSI | 100%
403398 | SVCW HL West Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2013-03-05 | 2013-03-05 | 2013-04-08 |  |  | All West Unitary Authorities | 890559 | 72519 | 0.09 | -28901.37 | 0 | 41.33 | -41.33 | 43617.72 | 0 | 934176.72 | 0 | [6 empty] | CM_WSI | 100%
403397 | SVCW HL West Water Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-05-01 | 2016-05-31 |  | All West Unitary Authorities | 1320165.79 | 489483.22 | 110.85 | 0 | 0 | 0 | 13650.2 | 503244.27 | 0 | 1823410.06 | 0 | [6 empty] | CM_WSNI | 100%
403399 | SVCW HL West Water Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2013-03-05 | 2013-03-05 | 2013-04-15 | 2019-12-31 |  | All West Unitary Authorities | 1096526 | 655561 | -183354.22 | 51430 | 500 | -341685.78 | 0 | 182451 | 0 | 1278977 | 0 | [6 empty] | CM_WSNI | 100%
403160 | SVCW Inverness WTW Acid Room Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-11-20 | 2015-01-29 | 2015-08-24 | 2017-06-21 |  | Highland | 151032 | 1041321 | 102666.21 | 14074.1 | 3754 | 0 | 0.01 | 1161815.32 | 0 | 1312847.32 | 0 | [6 empty] | CM_WSNI | 100%
403188 | SVCW Jerusalem Hotspot | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-14 | 2013-10-31 | 2014-02-17 | 2014-06-17 |  | Midlothian | 159355 | 1072 | -1826.11 | 0 | 0 | 0 | 0 | -754.11 | 0 | 158600.89 | 0 | [6 empty] | CM_WSI | 100%
402169 | SVCW Kingoldrum Low Pressure Alleviation Scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-26 | 2012-09-28 | 2012-11-26 | 2013-11-19 | 2013-11-28 | Angus | 127509 | -1774.82 | 0 | 0 | 0 | 0 | 0 | -1774.82 | 0 | 125734.18 | 0 | [6 empty] | CM_WSI | 100%
403178 | SVCW Kingsknowe Crescent - External Sewer Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-10 | 2013-07-01 | 2013-07-01 | 2014-07-07 |  | City of Edinburgh | 529369 | 665 | -2226.34 | 0 | 0 | 0 | 0 | -1561.34 | 0 | 527807.66 | 0 | [6 empty] | CM_WWI | 100%
403530 | SVCW Kishorn Sewer Diversion - SWS1 Legacy land issue | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-07-26 | 2016-07-20 | 2017-10-19 | 2018-02-05 |  | Highland | 7185.63 | 7174.37 | 7979.31 | 7215.46 | 175.44 | 0 | 0.01 | 22544.59 | 0 | 29730.22 | 0 | [6 empty] | CM_WWI | 100%
402765 | SVCW Kyle WTW - Abstraction and Land Legacy Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-07-05 | 2013-10-16 | 2013-11-29 | 2017-05-04 |  | Highland | 91999 | 0 | 23001 | -82340.3 | 0 | 0 | 0 | -59339.3 | 0 | 32659.7 | 0 | [6 empty] | CM_WSI | 100%
403123 | SVCW Kype Reservoir Spillway repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-11-06 | 2015-08-27 | 2015-09-18 | 2016-05-17 | 2016-05-17 | South Lanarkshire | 107413.31 | 78968.69 | -0.42 | -254.11 | 0 | 0 | 0 | 78714.16 | 0 | 186127.47 | 0 | [6 empty] | CM_WSI | 100%
402636 | SVCW Leggate SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2012-04-23 | 2018-03-27 | 2018-04-25 | 2019-07-22 | 2019-07-22 | South Ayrshire | 98320.44 | 15179.56 | 96660 | 175889.77 | 655226.23 | 47147 | 0 | 990102.56 | 1212 | 1089635 | 0 | [6 empty] | CM_WWNI | 100%
401474 | SVCW Levenwick Water Pumping Station Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-11-25 | 2011-12-09 | 2011-12-12 | 2015-07-23 |  | Shetland Islands | 148835 | -3828 | -3178.34 | -288.15 | 0 | 0 | 0 | -7294.49 | 0 | 141540.51 | 0 | [6 empty] | CM_WSNI | 100%
402344 | SVCW Lintrathen - Clatto 40inch Raw Water Main Rehabilitation works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-07 | 2014-10-20 | 2014-10-20 | 2014-10-20 |  | Angus | 25393.08 | 0 | 161.4 | 40.43 | 0 | 0 | -201.83 | 0 | 0 | 25393.08 | 0 | [6 empty] | CM_WSI | 100%
401356 | SVCW Loch Glow Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-08-19 | 2011-11-29 | 2015-10-02 | 2012-09-21 | Fife | 34940.52 | -97.06 | 0 | 0 | 0 | 0 | 0 | -97.06 | 0 | 34843.46 | 0 | [6 empty] | CM_WSI | 100%
400971 | SVCW Loch Romach - Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-15 | 2011-06-28 | 2011-09-26 | 2013-07-15 | 2013-07-15 | Aberdeenshire | 40653 | -493.88 | 0 | 0 | 0 | 0 | 0 | -493.88 | 0 | 40159.12 | 0 | [6 empty] | CM_WSI | 100%
403551 | SVCW Loch Whinyeon MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-11 | 2014-07-09 | 2014-08-19 | 2015-02-27 | 2015-02-27 | Scottish Water Wide | 103149 | 0 | -637.99 | 0 | 0 | 0 | 0 | -637.99 | 0 | 102511.01 | 0 | [6 empty] | CM_WSI | 100%
403599 | SVCW Lochgilphead A&BC Former Hospital Site Surface Water Removal | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-10-23 | 2013-11-22 | 2014-02-25 | 2015-08-07 |  | Argyll and Bute-North Argyll | 25372 | 174802.58 | 757.38 | 0 | 0 | 0 | 0 | 175559.96 | 0 | 200931.96 | 0 | [6 empty] | CM_WWI | 100%
403608 | SVCW Lochmaddy - DOA Sewer Works | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-10-22 | 2013-11-22 | 2013-11-28 | 2015-02-02 |  | Na H-Eileanan an Iar | 83920.69 | 13517.31 | 0 | 0 | 0 | 0 | 0 | 13517.31 | 0 | 97438 | 0 | [6 empty] | CM_WWI | 100%
402465 | SVCW Lochnaw Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-11-23 | 2013-07-18 | 2013-08-12 | 2015-03-24 | 2015-03-24 | Dumfries and Galloway | 161203 | 51172.04 | 0 | 0 | 0 | 0 | 0 | 51172.04 | 0 | 212375.04 | 0 | [6 empty] | CM_WSI | 100%
402729 | SVCW Lochwinnoch WwTW Inlet and Storm Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-06-07 | 2013-10-21 | 2014-03-28 | 2015-01-14 |  | Renfrewshire | 288005 | 8891.39 | 0 | 0 | 0 | 0 | 0 | 8891.39 | 0 | 296896.39 | 0 | [6 empty] | CM_WWI | 100%
401310 | SVCW Lower Glendevon Reservoir - Valve Tower | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-07-15 | 2012-01-13 | 2015-10-02 | 2013-03-15 | Perth and Kinross | 190986 | -466.83 | 0 | 0 | 0 | 0 | 0 | -466.83 | 0 | 190519.17 | 0 | [6 empty] | CM_WSI | 100%
402953 | SVCW Lumphinans Farm - Sewer Rehabilitation-Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-13 | 2016-12-13 |  | Fife | 2337.89 | 18604.11 | 36613.29 | 0 | 0 | 0 | 0 | 55217.4 | 0 | 57555.29 | 0 | [6 empty] | CM_WWI | 100%
402696 | SVCW Mains Hotspot - Carnock Fife | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-19 | 2012-11-30 | 2012-12-10 | 2013-09-01 |  | Fife | 86331.34 | 366.03 | 0 | 0 | 0 | 0 | 0 | 366.03 | 0 | 86697.37 | 0 | [6 empty] | CM_WSI | 100%
46668 | SVCW Mains Rehab - WSZ000107 Badentinan CWT Findlay Road Birnie Place | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2012-11-14 | 2012-12-03 | 2013-04-12 |  | Aberdeenshire | 110871 | -437.57 | 0 | 0 | 0 | 0 | 0 | -437.57 | 0 | 110433.43 | 0 | [6 empty] | CM_WSI | 100%
46665 | SVCW Mains Rehab - WSZ000812 Huntershill Balmanno Cottages | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-06 | 2009-03-06 | 2012-09-26 | 2014-07-17 |  | Angus | 61984 | 73 | -272 | 0 | 0 | 0 | 34.81 | -164.19 | 0 | 61819.81 | 0 | [6 empty] | CM_WSI | 100%
46666 | SVCW Mains Rehab - WSZ000812 Huntershill North Lodge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-06 | 2009-03-06 | 2012-10-08 | 2013-05-13 |  | Angus | 156842 | -797.97 | 0 | 0 | 0 | 0 | 0 | -797.97 | 0 | 156044.03 | 0 | [6 empty] | CM_WSI | 100%
402587 | SVCW Milngavie - Security Fence Removal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-23 | 2012-09-25 | 2012-11-12 | 2013-03-05 |  | East Dunbartonshire | 233172.08 | -31.72 | 0 | 0 | 0 | 0 | 0 | -31.72 | 0 | 233140.36 | 0 | [6 empty] | CM_WSI | 100%
403282 | SVCW Neilston Low DMA Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-18 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | East Renfrewshire | 35958 | -1908.81 | 0 | 0 | 0 | 0 | 0 | -1908.81 | 0 | 34049.19 | 0 | [6 empty] | CM_WSI | 100%
402009 | SVCW Newmore Raw Water Main Embankment Failure | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-03-21 | 2013-11-18 | 2013-12-02 | 2014-07-07 |  | Highland | 113585.03 | -257.76 | 0 | 0 | 0 | 0 | 0 | -257.76 | 0 | 113327.27 | 0 | [6 empty] | CM_WSI | 100%
403443 | SVCW North - Wastewater Non-Infra (Treatment) - 2014-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-05-16 | 2013-05-16 | 2014-04-04 | 2016-01-13 |  | All North Unitary Authorities | 1830750 | 224248.71 | 0 | 0 | 0 | 0 | 0 | 224248.71 | 0 | 2054998.71 | 0 |  |  |  |  | 105104 |  | CM_WWI | 100%
403441 | SVCW North - Wastewater Infra - 2014-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2016-01-13 |  | All North Unitary Authorities | 527800 | 41660.88 | 0 | 0 | 0 | 0 | 0 | 41660.88 | 0 | 569460.88 | 0 | [6 empty] | CM_WWI | 100%
403442 | SVCW North - Wastewater Non-Infra (SPS & Network Structures) - 2014-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-05-13 | 2013-05-13 | 2013-05-13 | 2016-01-13 |  | All North Unitary Authorities | 1052185 | 176625.31 | 0 | 0 | 0 | 0 | 0 | 176625.31 | 0 | 1228810.31 | 0 | [6 empty] | CM_WWNI | 100%
401299 | SVCW North Hoy WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-08-19 | 2012-08-03 | 2013-05-20 | 2015-03-02 |  | Orkney Islands | 52102 | -2815.54 | 0 | 0 | 0 | 0 | 0 | -2815.54 | 0 | 49286.46 | 0 |  |  |  |  | 50000 |  | CM_WSNI | 100%
402584 | SVCW North Water Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-03-09 | 2012-03-09 | 2012-04-23 | 2015-03-10 |  | All North Unitary Authorities | 814970 | 927.5 | 0 | 0 | 0 | 0 | 0 | 927.5 | 0 | 815897.5 | 0 | [6 empty] | CM_WSI | 100%
403308 | SVCW NT SCADA Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-25 | 2014-11-14 | 2015-01-16 | 2017-10-27 |  | All East Unitary Authorities | 83558 | 80721 | 22504 | -19283 | 0 | -832.2 | 0 | 83109.8 | 0 | 166667.8 | 0 | [6 empty] | CM_WSNI | 100%
500581 | SVCW Reservoir Maintenance 15-16 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-10 | 2019-11-22 | 2019-11-22 | Scottish Water Wide | 0 | 1514816 | 2059139.23 | 3051188.96 | -367633.44 | -531879.85 | -3885.81 | 5721745.09 | 0 | 5721745.09 | 0 | [6 empty] | CM_WSI | 100%
500646 | SVCW Reservoir Maintenance 15-16 SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2018-05-30 | 2018-05-30 | Scottish Water Wide | 0 | 359243.03 | 761822.98 | 251719.77 | 92152.18 | -1322.86 | 0 | 1463615.1 | 0 | 1463615.1 | 0 | [6 empty] | CM_WSI | 100%
402555 | SVCW Reservoir Maintenance 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2017-06-28 | 2017-06-28 | Scottish Water Wide | 3200167 | 216805 | 251042.99 | 34654.78 | 0 | 0 | 0 | 502502.77 | 0 | 3702669.77 | 0 | [6 empty] | CM_WSI | 100%
402541 | SVCW Reservoir Maintenance 2012-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-13 | 2012-02-13 | 2012-02-13 | 2018-07-19 | 2018-07-19 | Scottish Water Wide | 1065234.29 | 208099.25 | 46881.4 | 10207.67 | 0 | 0 | 0 | 265188.32 | 0 | 1330422.61 | 0 | [6 empty] | CM_WSI | 100%
400977 | SVCW Roscobie Reservoir - Emergency Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-05-30 | 2011-08-08 | 2012-08-01 | 2012-08-01 | Fife | 58732.06 | -531.94 | 0 | 0 | 0 | 0 | 0 | -531.94 | 0 | 58200.12 | 0 | [6 empty] | CM_WSI | 100%
403500 | SVCW Sewers & Water for Scotland 3rd Ed - WRc Support | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MS7 | 2013-07-03 | 2013-07-03 | 2013-08-01 | 2016-01-13 | 2016-02-11 | Scottish Water Wide | 118256.02 | 3050 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 121306.02 | 0 | [6 empty] | SG1 | 50% | WG1 | 50%
403053 | SVCW South Park Avenue Barrhead - Lift and Relay Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-15 | 2014-09-30 | 2014-10-06 | 2015-02-24 |  | Renfrewshire | 906306 | -38847.82 | 0 | 0 | 0 | 0 | 0 | -38847.82 | 0 | 867458.18 | 0 | [6 empty] | CM_WWI | 100%
402560 | SVCW South Wastewater Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-03-01 | 2015-03-10 |  | All South Unitary Authorities | 1066868.46 | 84.38 | 0 | 0 | 0 | 0 | -0.09 | 84.29 | 0 | 1066952.75 | 0 | [6 empty] | CM_WWI | 100%
402553 | SVCW South Water Non-Infra - 2012-2013 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-15 | 2012-02-15 | 2012-04-02 | 2013-12-16 |  | All South Unitary Authorities | 1189244.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189244.93 | 0 | [6 empty] | CM_WSNI | 100%
402558 | SVCW South Water Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-22 | 2012-02-22 | 2012-04-23 | 2015-11-04 |  | All South Unitary Authorities | 157706.3 | 1529.42 | 0 | 0 | 0 | 0 | 0 | 1529.42 | 0 | 159235.72 | 0 | [6 empty] | CM_WSNI | 100%
402435 | SVCW SP East Water Infra 2011-12 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-31 | 2011-10-31 | 2011-11-07 | 2014-12-18 |  | All East Unitary Authorities | 257031 | 1500 | -1246.83 | 0 | 0 | 0 | -35.5 | 217.67 | 0 | 257248.67 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
402432 | SVCW SP East Water Non-Infra 2011-12 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-10-31 | 2011-10-31 | 2011-11-07 | 2015-04-02 |  | All East Unitary Authorities | 85089 | 4400.45 | 0 | 0 | 0 | 0 | 0 | 4400.45 | 0 | 89489.45 | 0 | [6 empty] | CM_WSNI | 100%
402400 | SVCW SP South Water Non-Infra 2011-12 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-11-16 | 2011-11-16 | 2011-12-07 | 2015-12-11 |  | All South Unitary Authorities | 178187 | -9957.11 | 0 | 0 | 0 | 0 | 0 | -9957.11 | 0 | 168229.89 | 0 | [6 empty] | CM_WSNI | 100%
401115 | SVCW SP West Water Non-Infra 2010-12 SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-07-01 | 2010-07-01 | 2011-04-29 | 2012-10-03 |  | All West Unitary Authorities | 446434.74 | 0 | 0 | 41.59 | 0 | 0 | 121.11 | 162.7 | 0 | 446597.44 | 0 | [6 empty] | CM_WSI | 100%
402268 | SVCW SPS000923 - Blaikies Quay WWPS Replacement Covers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-10-25 | 2012-02-23 | 2012-07-31 | 2012-11-29 |  | Aberdeen City | 125845 | -1549.47 | 0 | 0 | 0 | 0 | 0 | -1549.47 | 0 | 124295.53 | 0 | [6 empty] | CM_M&G | 100%
403153 | SVCW Stornoway WOA - Point WSZ Braighe AC Main Replacment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-15 | 2013-09-19 | 2014-04-04 | 2015-06-25 |  | Na H-Eileanan an Iar | 220541 | 31727.61 | 0 | 0 | 0 | 0 | 0 | 31727.61 | 0 | 252268.61 | 0 | [6 empty] | CM_WSI | 100%
402106 | SVCW Stronsay WOA Water Mains Renewals | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-18 | 2013-01-26 | 2013-02-25 | 2014-11-24 |  | Orkney Islands | 63535 | -508.25 | 0 | 0 | 0 | 0 | 0 | -508.25 | 0 | 63026.75 | 0 | [6 empty] | CM_WSI | 100%
403184 | SVCW Swinstie WwTW Elevated approach sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-04 | 2015-03-06 | 2018-12-03 | 2019-07-24 |  | North Lanarkshire | 140973.67 | 355844.33 | -7999.52 | 1243.9 | 1551.71 | 0 | 0 | 350640.42 | 0 | 491614.09 | 0 | [6 empty] | CM_WWI | 100%
401223 | SVCW Tay Cluster 1 Pitlessie Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-03-19 | 2012-05-04 | 2014-05-21 |  | Perth and Kinross | 468915 | -743.96 | -187.77 | 0 | 0 | 0 | 0 | -931.73 | 0 | 467983.27 | 0 | [6 empty] | CM_WSI | 100%
401221 | SVCW Tay Cluster 3 WSZ001080 Gannochy SR TOWM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-07-30 | 2012-08-29 | 2014-04-23 |  | Dundee City | 97438 | 8079.82 | 99.5 | 0 | 0 | 0 | 0 | 8179.32 | 0 | 105617.32 | 0 | [6 empty] | CM_WSI | 100%
403137 | SVCW Telemetry - WMS Migration SR10 Ph1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2013-03-06 | 2013-11-13 | 2013-12-02 | 2016-08-30 |  | Scottish Water Wide | 142804 | 66060.46 | 19480.21 | 5308.65 | 0 | 0 | 0 | 90849.32 | 0 | 233653.32 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
403138 | SVCW Telemetry RTU Replacement SR10 phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2013-01-17 | 2013-07-24 | 2013-09-09 | 2015-07-31 |  | Scottish Water Wide | 247968 | -1769 | -1157.62 | 0 | 0 | 0 | 0 | -2926.62 | 0 | 245041.38 | 0 | [6 empty] | CM_WWNI | 46.99% | CM_WSNI | 53.01%
403739 | SVCW Thankerton - Install new sewer pipe under West Coast Railway Line | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-08-25 | 2015-04-27 | 2015-04-27 | 2015-04-27 |  | South Lanarkshire | 18157.18 | -1272.93 | 0 | 0 | 0 | 0 | 0 | -1272.93 | 0 | 16884.25 | 0 | [6 empty] | CM_WWI | 100%
403490 | SVCW Troqueer commissioning review | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-07-05 | 2013-07-05 | 2013-07-05 | 2016-10-10 |  | Dumfries and Galloway | 48713.41 | 11286.59 | -11561.88 | 0 | 0 | 0 | 275.29 | 9.6634e-13 | 0 | 48713.41 | 0 | [6 empty] | CM_WWNI | 100%
402365 | SVCW Troqueer WwTW Inlet Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2011-09-28 | 2011-10-07 | 2012-01-09 | 2016-10-10 |  | Dumfries and Galloway | 174168.61 | 7831.39 | -7728.2 | 0 | 0 | 0 | 0 | 103.19 | 0 | 174271.8 | 0 | [6 empty] | CM_WWNI | 100%
401494 | SVCW TWS001417 Turriff Prosptect Hill Internal Refurbishment of Service Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-22 | 2012-07-24 | 2012-10-22 | 2013-04-26 |  | Aberdeenshire | 111363 | -1841.58 | 0 | 0 | 0 | 0 | 0 | -1841.58 | 0 | 109521.42 | 0 | [6 empty] | CM_WSNI | 100%
403167 | SVCW Ullapool WOA - Upper Braes WPS Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2014-02-07 | 2014-06-30 | 2018-07-09 |  | Highland | 164354 | 29705 | -15311.51 | 126731.92 | -45843.47 | 10.77 | 0.01 | 95292.72 | 0 | 259646.72 | 0 | [6 empty] | CM_WSNI | 100%
403019 | SVCW Uphall WwPS Rising Main - Renewal | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-11-30 | 2016-03-29 | 2016-06-10 | 2016-11-17 |  | West Lothian | 33410 | 103470 | 282094 | 3207 | -1136.37 | 0 | 0.37 | 387635 | 0 | 421045 | 0 | [6 empty] | CM_WWI | 100%
403312 | SVCW Upper Morton Small Reservoir Enhancement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-30 | 2015-07-13 | 2015-07-13 | 2014-04-22 | 2014-04-22 | West Lothian | 14962 | -1602.8 | 0 | 0 | 0 | 0 | 0 | -1602.8 | 0 | 13359.2 | 0 | [6 empty] | CM_WSI | 100%
403701 | SVCW Water Balance Supply Pipe Leakage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-02-12 | 2014-04-24 | 2014-04-24 | 2015-10-30 |  | Scottish Water Wide | 93797 | -283.65 | 0 | 0 | 0 | 0 | 0 | -283.65 | 0 | 93513.35 | 0 | [6 empty] | CM_WSI | 100%
500570 | SVCW Water Central Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2016-11-24 | 2016-11-24 | Scottish Water Wide | 0 | 250300.53 | -200357.95 | 20.8 | 0 | 0 | 1573.5 | 51536.88 | 0 | 51536.88 | 0 | [6 empty] | CM_WSI | 100%
500539 | SVCW Water Central Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2016-12-21 | 2016-12-21 | Scottish Water Wide | 0 | 249979.18 | -1228.46 | 17.8 | 0 | 0 | 0 | 248768.52 | 0 | 248768.52 | 0 | [6 empty] | CM_WSI | 100%
500572 | SVCW Water Central Other (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-27 | 2017-04-28 | 2017-04-28 | Scottish Water Wide | 0 | 78328.28 | 9841.64 | -1399.36 | 0 | 0 | -80.25 | 86690.31 | 0 | 86690.31 | 0 | [6 empty] | CM_WSNI | 100%
500541 | SVCW Water Central Other (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2016-12-21 | 2016-12-21 | Scottish Water Wide | 0 | 16836 | -14264.54 | 0 | 0 | 0 | 0 | 2571.46 | 0 | 2571.46 | 0 | [6 empty] | CM_WSNI | 100%
500571 | SVCW Water Central WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2016-08-23 | 2016-08-23 | Scottish Water Wide | 0 | 177650.35 | -133356.32 | 3877.32 | 0 | 0 | 0 | 48171.35 | 0 | 48171.35 | 0 | [6 empty] | CM_WSNI | 100%
500540 | SVCW Water Central WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2018-02-26 | 2018-02-26 | Scottish Water Wide | 0 | 149499.68 | 316799.56 | 15709.28 | 98.63 | 0 | -98.63 | 482008.52 | 0 | 482008.52 | 0 | [6 empty] | CM_WSNI | 100%
500557 | SVCW Water East SR (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-05-22 | 2015-05-22 | 2015-05-29 |  | 2020-06-26 | All East Unitary Authorities | 0 | 197317 | 288945.53 | 306580.94 | 199228.29 | 15872.26 | 0 | 1007944.02 | 0 | 1007944.02 | 0 | [6 empty] | CM_WSNI | 100%
500526 | SVCW Water East SR (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-28 | 2015-04-28 | 2015-04-28 |  | 2019-12-13 | All East Unitary Authorities | 0 | 206922 | 81201 | 15254 | -25006.8 | 0 | 0 | 278370.2 | 0 | 278370.2 | 0 | [6 empty] | CM_WSNI | 100%
500555 | SVCW Water East WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-29 | 2016-09-28 | 2016-09-28 | All East Unitary Authorities | 0 | 8792.52 | 0 | 0 | 0 | 0 | 0 | 8792.52 | 0 | 8792.52 | 0 | [6 empty] | CM_WSNI | 100%
500524 | SVCW Water East WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-04-28 | 2015-04-28 | 2015-04-28 |  | 2019-12-13 | All East Unitary Authorities | 0 | 265988 | 187409.69 | 62692 | -64990.2 | 0 | 0 | 451099.49 | 0 | 451099.49 | 0 | [6 empty] | CM_WSNI | 100%
500556 | SVCW Water East WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2018-02-08 | 2018-02-08 | All East Unitary Authorities | 0 | 491516 | 694380.58 | 12552.78 | 0 | 0 | 344.65 | 1198794.01 | 0 | 1198794.01 | 0 | [6 empty] | CM_WSNI | 100%
500525 | SVCW Water East WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-05-19 | 2015-05-19 | 2015-05-19 |  | 2019-12-13 | All East Unitary Authorities | 0 | 2306909.23 | 709531.32 | 249391.45 | -238806.23 | 0 | 0 | 3027025.77 | 0 | 3027025.77 | 0 | [6 empty] | CM_WSNI | 100%
500558 | SVCW Water North Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-25 | 2018-03-21 | 2018-03-21 | All North Unitary Authorities | 0 | 669722 | 815300.91 | 597568.78 | 1849.51 | 0 | 0.01 | 2084441.21 | 0 | 2084441.21 | 0 | [6 empty] | CM_WSI | 100%
500527 | SVCW Water North Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2017-01-04 | 2017-01-04 | All North Unitary Authorities | 0 | 380900 | 74723.83 | 728.89 | 0 | 0 | 0 | 456352.72 | 0 | 456352.72 | 0 | [6 empty] | CM_WSI | 100%
500561 | SVCW Water North SR (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-05-25 | 2018-07-11 | 2018-07-11 | All North Unitary Authorities | 0 | 306765 | 51933.99 | 68044.42 | -11716.12 | 55.41 | 0 | 415082.7 | 0 | 415082.7 | 0 | [6 empty] | CM_WSNI | 100%
500530 | SVCW Water North SR (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-12-15 | 2017-01-31 | All North Unitary Authorities | 0 | 219313 | 41874.68 | 0 | 0 | 0 | 0 | 261187.68 | 0 | 261187.68 | 0 | [6 empty] | CM_WSNI | 100%
500559 | SVCW Water North WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-05-25 | 2017-02-21 | 2017-02-21 | All North Unitary Authorities | 0 | 11131 | 7874.01 | 53.04 | 0 | 0 | 0 | 19058.05 | 0 | 19058.05 | 0 | [6 empty] | CM_WSNI | 100%
500528 | SVCW Water North WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-08-31 | 2016-09-13 | All North Unitary Authorities | 0 | 65138.21 | 9165.42 | 0 | 0 | 0 | 0 | 74303.63 | 0 | 74303.63 | 0 | [6 empty] | CM_WSNI | 100%
500560 | SVCW Water North WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-25 | 2018-06-22 | 2018-06-22 | All North Unitary Authorities | 0 | 808598 | 120025.43 | 52462.62 | -28429.36 | 0 | 0.01 | 952656.7 | 0 | 952656.7 | 0 | [6 empty] | CM_WSNI | 100%
500529 | SVCW Water North WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-01-04 | 2017-01-04 | All North Unitary Authorities | 0 | 1694113.79 | 614611.46 | 1701.32 | 0 | 0 | 0.01 | 2310426.58 | 0 | 2310426.58 | 0 | [6 empty] | CM_WSNI | 100%
500643 | SVCW Water Resources - Monitoring Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2015-05-11 | 2015-05-11 | 2015-05-11 |  | 2018-08-10 | Scottish Water Wide | 0 | 302440 | 98911.91 | 3129 | 3139.13 | 172.19 | -172.19 | 407620.04 | 0 | 407620.04 | 0 | [6 empty] | CM_WSI | 100%
500566 | SVCW Water South Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2017-11-22 | 2017-11-22 | All South Unitary Authorities | 0 | 116855 | 832361.93 | 170684.51 | -6424.13 | 0 | 17277.6 | 1130754.91 | 0 | 1130754.91 | 0 | [6 empty] | CM_WSI | 100%
500535 | SVCW Water South Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-02-01 | 2017-02-17 | All South Unitary Authorities | 0 | 859734 | 709.66 | 0 | 0 | 0 | 0 | 860443.66 | 0 | 860443.66 | 0 | [6 empty] | CM_WSI | 100%
500569 | SVCW Water South SRs (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-25 | 2016-03-03 | 2016-03-03 | All South Unitary Authorities | 0 | 3011.43 | 0 | 0 | 0 | 0 | 0 | 3011.43 | 0 | 3011.43 | 0 | [6 empty] | CM_WSNI | 100%
500538 | SVCW Water South SRs (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-08 | 2017-03-16 | All South Unitary Authorities | 0 | 286276 | -25443.47 | 0 | 0 | 0 | 0 | 260832.53 | 0 | 260832.53 | 0 | [6 empty] | CM_WSNI | 100%
500567 | SVCW Water South WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-25 | 2016-03-03 | 2016-03-03 | All South Unitary Authorities | 0 | 6869.16 | 0 | 0 | 0 | 0 | 0 | 6869.16 | 0 | 6869.16 | 0 | [6 empty] | CM_WSNI | 100%
500536 | SVCW Water South WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-08-02 | 2016-08-02 | All South Unitary Authorities | 0 | 63788 | -1703.29 | 0 | 0 | 0 | 0 | 62084.71 | 0 | 62084.71 | 0 | [6 empty] | CM_WSNI | 100%
500568 | SVCW Water South WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2018-05-30 | 2018-05-30 | All South Unitary Authorities | 0 | 198027 | 320140.89 | 233840.24 | 36667.74 | 168.14 | -207.79 | 788636.22 | 0 | 788636.22 | 0 | [6 empty] | CM_WSNI | 100%
500537 | SVCW Water South WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-06-01 | 2017-06-01 | All South Unitary Authorities | 0 | 1971276 | 27327 | -69741.79 | 0 | 0 | 4407.35 | 1933268.56 | 0 | 1933268.56 | 0 | [6 empty] | CM_WSNI | 100%
500562 | SVCW Water West Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-25 |  | 2019-12-31 | All West Unitary Authorities | 0 | 551946 | 2071586.31 | 962346.85 | 17136.41 | 25349.08 | 0 | 3628364.65 | 0 | 3628364.65 | 0 | [6 empty] | CM_WSI | 100%
500531 | SVCW Water West Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 161402 | -42252.53 | 45850.53 | -66161.03 | 0 | 0 | 98838.97 | 0 | 98838.97 | 0 | [6 empty] | CM_WSI | 100%
500565 | SVCW Water West SR (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-27 | 2017-06-09 | 2017-06-09 | All West Unitary Authorities | 0 | 261073 | 71787.36 | 1044.68 | 0 | 0 | -125.48 | 333779.56 | 0 | 333779.56 | 0 | [6 empty] | CM_WSNI | 100%
500534 | SVCW Water West SR (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 217820.42 | 98500.5 | 11060.02 | 24145.25 | 0 | 0 | 351526.19 | 0 | 351526.19 | 0 | [6 empty] | CM_WSNI | 100%
500563 | SVCW Water West WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-27 | 2018-03-07 | 2018-03-07 | All West Unitary Authorities | 0 | 417698 | 448826.6 | 94730.29 | -17225.21 | 0 | 0 | 944029.68 | 0 | 944029.68 | 0 | [6 empty] | CM_WSNI | 100%
500532 | SVCW Water West WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 46708 | 8395.79 | 14896.21 | -20374.27 | 0 | 0 | 49625.73 | 0 | 49625.73 | 0 | [6 empty] | CM_WSNI | 100%
500564 | SVCW Water West WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-11-02 | 2015-06-05 | 2015-06-25 | 2017-08-24 | 2017-09-01 | All West Unitary Authorities | 0 | 275953.49 | 299227.23 | 15731.05 | 0 | 0 | 0 | 590911.77 | 0 | 590911.77 | 0 | [6 empty] | CM_WSNI | 100%
500533 | SVCW Water West WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 674910.5 | 280780.26 | 0 | 9419.51 | 0 | 0 | 965110.27 | 0 | 965110.27 | 0 | [6 empty] | CM_WSNI | 100%
402556 | SVCW West Water Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-09 | 2016-01-14 |  | All West Unitary Authorities | 1002831 | -28267.36 | 0 | 0 | 0 | 0 | 0 | -28267.36 | 0 | 974563.64 | 0 | [6 empty] | CM_WSNI | 100%
402199 | SVCW Weyland Bay WWPS Replace Screen Covers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-09-12 | 2012-05-21 | 2012-06-25 | 2016-06-17 |  | Orkney Islands | 10000 | 0 | -2675.68 | 0 | 0 | 0 | 0 | -2675.68 | 0 | 7324.32 | 0 | [6 empty] | CM_M&G | 100%
402112 | SVCW Whalsay Old WSZ Low Pressure | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-18 | 2012-05-15 | 2012-05-30 | 2012-07-13 | 2012-07-13 | Shetland Islands | 30631.65 | 62.5 | 0 | 0 | 0 | 0 | 0.32 | 62.82 | 0 | 30694.47 | 0 | [6 empty] | CM_WSI | 100%
403471 | SVCW WQ OPA North Hoy WTW Temporary Filtration | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-18 | 2014-05-12 | 2014-07-21 | 2016-03-09 |  | Orkney Islands | 233231 | 32979 | 11294.63 | 40.67 | -430.16 | 0 | 0 | 43884.14 | 0 | 277115.14 | 0 | [6 empty] | CM_WSNI | 100%
403448 | SVCW WQ OPA Savalbeg WTW Quality Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-05-13 | 2015-03-12 | 2015-03-02 | 2015-03-03 |  | Highland | 103000 | -27.1 | 0 | 0 | 0 | 0 | 0 | -27.1 | 0 | 102972.9 | 0 | [6 empty] | CM_WSNI | 100%
403449 | SVCW WQ OPA SR Sample Tap Replacement Programme Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-23 | 2013-07-29 | 2013-09-09 | 2015-03-30 |  | Scottish Water Wide | 590036 | -14947.82 | 88.75 | 0 | 0 | 0 | 0 | -14859.07 | 0 | 575176.93 | 0 | [6 empty] | CM_WSNI | 100%
401865 | SVCW WSZ 000663 Gallowhill WSZ Highfield Place Birkhill Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-23 | 2012-07-24 | 2012-09-28 | 2013-04-25 |  | Angus | 54674 | -2065.62 | 0 | 0 | 0 | 0 | 0 | -2065.62 | 0 | 52608.38 | 0 | [6 empty] | CM_WSI | 100%
400797 | SVCW WSZ001402 Stobsmuir WSZand DMA004274 Perth Road - Thomson Street WMR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-21 | 2011-06-23 | 2010-08-23 | 2012-03-29 |  | Dundee City | 100098 | -8492.87 | 0 | 0 | 0 | 0 | 0 | -8492.87 | 0 | 91605.13 | 0 | [6 empty] | CM_WSI | 100%
402019 | SVCW WTW000606 Sandy Loch WTW Chemical Handling and Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-27 | 2014-12-17 | 2015-03-26 | 2017-06-21 |  | Shetland Islands | 194347 | 358958 | 65000 | 56453.09 | 0 | -3706 | 0 | 476705.09 | 0 | 671052.09 | 0 | [6 empty] | CM_M&G | 100%
401051 | SVCW WTW000616 Kirbister WTW Replace 8 Remaining High Lift Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-06 | 2014-06-30 | 2015-01-23 | 2016-03-29 |  | Orkney Islands | 352366 | 55145.9 | 91109.3 | 0 | -6595.29 | 0 | 0 | 139659.91 | 0 | 492025.91 | 0 | [6 empty] | CM_WSNI | 100%
400978 | SVCW WW - Pre QH CAPEX CID Development Holding Line | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-31 | 2010-05-24 | 2013-02-08 | 2015-12-14 | 2017-01-05 08:00 | Highland | 91772 | 197113.42 | 0 | 0 | 0 | 0 | 0 | 197113.42 | 0 | 288885.42 | 0 | [6 empty] | CM_WWI | 100%
402077 | SW CMA Data Reconciliation Tables | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-09-20 | 2011-09-20 | 2011-09-20 | 2015-03-17 |  | Scottish Water Wide | 2231.71 | -677.27 | 0 | 0 | 0 | 0 | 0 | -677.27 | 0 | 1554.44 | 0 | [6 empty] | CS20 | 100%
502639 | SW Managed Delivery - Post-Project Land Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2017-03-09 | 2017-03-09 | 2017-03-13 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 18938.32 | 110072.03 | 265654.41 | 153335.24 | 385755 | 933755 | 0 | 933755 | 0 | [6 empty] | CM_M&G | 100%
404118 | SW Scanning Radio Hardware Procurement (Telemetry) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-01-22 |  | Scottish Water Wide | 0 | 447836.14 | 0 | 0 | 0 | 0 | 0 | 447836.14 | 0 | 447836.14 | 0 | [6 empty] | CM_M&G | 100%
403580 | SW Wide Strategic Modelling - Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2013-09-25 | 2018-12-19 | 2018-12-19 | 2020-05-25 |  | Scottish Water Wide | 124143.59 | 51328.41 | 91609.79 | 8000 | -15455.58 | 37957.54 | 2416.25 | 175856.41 | 0 | 300000 | 0 | [6 empty] | CM_WSI | 100%
501017 | SW1015 - Shieldaig Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS1 | 2018-01-30 | 2021-02-08 | 2021-04-21 | 2022-01-31 | 2022-04-22 | Glasgow City | 0 | 21930 | 66070 | 87000 | 135431 | 378943 | 119112.64 | 808486.64 | 732513.34 | 1540999.98 | 204193.13 | [6 empty] | CS11 | 100%
500651 | SW1025 - 26 Afton Bridgend New Cumnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-02-08 | 2018-03-27 | 2018-03-27 | 2017-10-17 | 2018-03-27 | East Ayrshire | 0 | 38389 | 46428 | -79879.75 | 968.97 | -0.02 | 0.03 | 5906.23 | 0 | 5906.23 | 204193.13 | [6 empty] | CS11 | 100%
502895 | SW1392 - Third Avenue Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2020-03-24 | 2021-03-22 | 2021-03-30 | 2022-03-29 | 2022-06-29 | Glasgow City | 0 | 0 | 0 | 41860.47 | 97139.53 | 81635.5 | 125031.5 | 345667 | 560333 | 906000 | 196097.17 | [6 empty] | CS11A | 100%
502228 | SW1616 - Gartcraig Rd - Fettes Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-08-21 | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2020-12-02 | Glasgow City | 0 | 0 | 37030.23 | 43969.77 | 85000 | 31197.34 | 242802.66 | 440000 | 0 | 440000 | 196097.17 | [6 empty] | CS11A | 100%
503318 | SW1617 - Newhills Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-07-27 | 2021-07-09 | 2021-09-22 | 2022-04-26 | 2022-07-27 | Glasgow City | 0 | 0 | 0 | 0 | 44000 | 92200 | 87092.02 | 223292.02 | 376707.97 | 599999.99 | 196097.17 | [6 empty] | CS11A | 100%
500999 | SW163 - Broompark Drive Newton Mearns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS5 | 2018-03-30 | 2019-05-16 | 2019-07-01 | 2019-09-30 | 2019-09-30 | East Renfrewshire | 0 | 22930 | 46633.66 | 57997.49 | 113889.85 | 216846 | 0 | 458297 | 1703 | 460000 | 204193.13 |  |  |  |  | 900 |  | CS11 | 100%
500202 | SW167 - Aikenhead Road - Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-09-03 | 2019-09-24 | 2019-09-24 | 2019-09-04 | 2019-09-04 | Glasgow City | 0 | 66930 | 57070 | 15000 | 45000 | 89990.12 | 0 | 273990.12 | 0 | 273990.12 | 520131.84 | [6 empty] | CS11 | 100%
503172 | SW1670 - Borrowmeadow Road Stirling | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-10-05 | 2021-09-02 | 2021-11-23 | 2022-06-27 | 2022-09-27 | Stirling | 0 | 0 | 0 | 0 | 84000 | 58606.75 | 66852.31 | 209459.06 | 1983309.97 | 2192769.03 | 196097.17 | [6 empty] | CS11A | 100%
503771 | SW1905 - Wellhouse Crescent Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW0 | 2021-09-07 | 2022-08-08 | 2022-10-20 | 2023-05-24 | 2023-07-17 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 265000 | 0 | 265000 | 0 | 265000 | 1345230.68 | [6 empty] | CS11 | 100%
500743 | SW1907 - Sandy Road Carluke | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-02-25 | 2019-02-25 | South Lanarkshire | 0 | 15500 | 19500 | 12000 | -45905.09 | -1093.92 | 0.01 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 100%
500003 | SW195 - 2560-2562 Dumbarton Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2015-03-26 | 2015-06-25 | 2015-06-26 | 2017-12-20 | 2017-12-20 | West Dunbartonshire | 0 | 848820 | -19597.9 | 560701.79 | 1369.11 | 179.02 | -43.05 | 1391428.97 | 0 | 1391428.97 | 196097.17 | [6 empty] | CS11A | 100%
504017 | S-W-271119-Steele Avenue Lochfoot - Water Quality | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WSI | 100%
501016 | SW330 - Muirhead Way Bishopbriggs Glasgow | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WWINF | Infra Charge | MS3 | 2018-02-22 | 2019-07-19 | 2019-09-30 | 2020-06-02 | 2020-09-08 | East Dunbartonshire | 0 | 0 | 65306.81 | 120693.19 | 202200.64 | 511205.36 | 29284 | 928690 | 966 | 929656 | 1830849.77 | [6 empty] | SG5 | 100%
502891 | SW343 - Peat Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS4 | 2020-10-16 | 2020-03-05 | 2020-10-16 | 2020-03-10 | 2020-10-16 | Glasgow City | 0 | 0 | 0 | 43000 | 96000 | 47026.95 | -6246.58 | 179780.37 | 0 | 179780.37 | 196097.17 | [6 empty] | CS11A | 100%
502892 | SW344 Braidholm Road Giffnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-06-12 | 2021-01-11 | 2021-03-24 | 2021-12-28 | 2022-03-30 | East Renfrewshire | 0 | 0 | 0 | 42564.57 | 91935.43 | 76299.52 | 544439.24 | 755238.76 | 1644761.24 | 2400000 | 196097.17 | [6 empty] | CS11A | 100%
502893 | SW346 Beech Avenue Newton Mearns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2020-03-12 | 2021-01-25 | 2021-03-08 | 2021-07-29 | 2021-10-28 | East Renfrewshire | 0 | 0 | 0 | 43000 | 64000 | 83124.13 | 235546.79 | 425670.92 | 512329.09 | 938000.01 | 196097.17 | [6 empty] | CS11A | 100%
500748 | SW383 - Stanley Primary School Stanley Road Ardrossan - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-09-01 | 2021-04-29 | 2021-04-30 | 2021-04-30 | 2021-04-30 | North Ayrshire | 0 | 23500 | 24530.23 | 55435.3 | 44534.47 | 82472.25 | 303070.43 | 533542.68 | 59772.34 | 593315.02 | 204193.13 | [6 empty] | CS11 | 100%
501011 | SW409 - Riddon Place Glasgow Flooding Project | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2021-04-01 | 2021-04-01 | 2020-03-19 | 2021-04-01 | 2021-04-01 | Glasgow City | 0 | 31056.93 | 34027.07 | 22916 | 6000 | 40775.14 | 0 | 134775.14 | 0 | 134775.14 | 204193.13 | [6 empty] | CS11 | 100%
500663 | SW522 - East Shaw Street Kilmarnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2020-12-18 | 2020-12-24 | 2020-12-30 | 2021-01-05 | 2021-01-05 | East Ayrshire | 0 | 23100 | 30930.23 | 16969.77 | 20000 | 73915.61 | 27084.39 | 192000 | 0 | 192000 | 368809.14 | [6 empty] | CS11 | 100%
502425 | SW599 - Laighlands Road Bothwell | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-08-28 | 2021-05-28 | 2021-08-13 | 2021-12-27 | 2022-03-29 | South Lanarkshire | 0 | 0 | 41860.47 | 16139.53 | 34000 | 181367 | 141279.67 | 414646.67 | 2811248.35 | 3225895.02 | 196097.17 | [6 empty] | CS11A | 100%
501000 | SW609 - Main Street Newmilns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-04-09 | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01 | East Ayrshire | 0 | 26523 | 42109 | 12369 | 29581.77 | 43234.8 | 0 | 153817.57 | 0 | 153817.57 | 204193.13 | [6 empty] | CS11 | 100%
502376 | SW615 - Baker Street Stirling | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-04-17 | 2020-05-04 | 2020-05-04 | 2020-05-15 | 2020-05-18 | Stirling | 0 | 0 | 42522.01 | 2477.99 | 29000 | 71331.41 | 20668.59 | 166000 | 0 | 166000 | 196097.17 | [6 empty] | CS11A | 100%
502894 | SW666 - Bay Street Port Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-08-17 | 2021-07-23 | 2021-10-06 | 2022-05-10 | 2022-08-10 | Inverclyde | 0 | 0 | 0 | 41860.47 | 4139.53 | 33665.99 | 46939.02 | 126605.01 | 198394.96 | 324999.97 | 196097.17 | [6 empty] | CS11A | 100%
501014 | SW741 - Kilbride Drive Helensburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2019-02-08 | 2019-12-16 | 2020-01-27 | 2020-08-19 | 2020-11-20 | Argyll and Bute-Cowal & Bute | 0 | 22930 | 44566.68 | 51503.32 | 93383.97 | 396285.17 | 249768.16 | 858437.3 | 2297.73 | 860735.03 | 204193.13 | [6 empty] | CS11 | 100%
502328 | SW759 - Woodlands Grove Kilmarnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-05-15 | 2021-04-29 | 2021-07-21 | 2022-04-18 | 2022-07-15 | East Ayrshire | 0 | 0 | 43360.47 | 25639.53 | 77000 | 102878.6 | 119282.22 | 368160.82 | 889839.16 | 1257999.98 | 196097.17 | [6 empty] | CS11A | 100%
500681 | SW843 - Wellgate Lanark | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2020-02-21 | 2021-02-08 | 2021-02-25 | 2022-02-25 | 2022-05-20 | South Lanarkshire | 0 | 62556 | 20783.9 | 24660.1 | 31000 | 131189.32 | 673350.93 | 943540.25 | 1490218.77 | 2433759.02 | 281012.82 | [6 empty] | CS11 | 100%
500682 | SW857 - Townhead Street Stonehouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2019-04-29 | 2020-08-24 | 2020-07-01 | 2021-04-08 | 2021-04-08 | South Lanarkshire | 0 | 56500 | 20886.26 | 26210.11 | 37403.63 | 179971 | 843248.57 | 1164219.57 | 201780.43 | 1366000 | 466541.85 | [6 empty] | CS11 | 100%
500732 | SW92 - Dukes Road Troon | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-03-14 | 2019-03-14 | 2019-03-14 | 2019-02-25 | 2019-02-25 | South Ayrshire | 0 | 22930 | 23500 | 20570 | -66999 | 0 | 0 | 1 | 0 | 1 | 60189.23 | [6 empty] | CS11 | 100%
403300 | SWCW Thurso STW Access Remedial Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-17 | 2013-01-17 | 2013-03-21 | 2018-08-13 |  | Highland | 32987.1 | -0.1 | 120 | 0 | 0 | 0 | 0.1 | 120 | 0 | 33107.1 | 0 | [6 empty] | CM_WWI | 100%
49720 | SWD - DWQ Reliability - Profile Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | General |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -5000058.4 | -5000058.4 | 5000058.4 | 0 | 0 | [6 empty] | SR15_DWQ_REL | 100%
49605 | SWD - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | RISK | 100%
50035 | SWD - SR21 Early Start - Profile Adjustment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -13940114.68 | -13940114.68 | 13940114.68 | 0 | 0 | [6 empty] | SR21_SS | 100%
403710 | SWD Non Infra 2014-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-20 | 2014-02-20 | 2014-04-04 | 2015-11-18 | 2016-03-31 | Highland | 2200000 | 727291.7 | -2033 | 0 | 0 | 0 | 0 | 725258.7 | 0 | 2925258.7 | 0 | [6 empty] | CM_WSNI | 100%
500711 | Sweet Thorn Drive East Kilbride | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WWINF | Infra Charge | MS4 | 2018-03-28 | 2019-09-19 | 2019-11-25 | 2020-03-31 | 2020-04-17 | South Lanarkshire | 0 | 85125 | 50875 | 28855.88 | 117628.12 | 563513 | 53043 | 899040 | 0 | 899040 | 1830849.77 | [6 empty] | SG5 | 100%
506031 | S-W-I-010420-Talla Aqueduct - Cleaves Well building and wall repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 5700 | 0 | 5700 | 0 | [6 empty] | CM_WSI | 100%
504151 | S-W-I-041219-Mosshall Street Transfers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 | 2020-03-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 32100 | 0 | 32100 | 0 | 32100 | 0 | [6 empty] | CM_WSI | 100%
504538 | S-W-I-070120-South Calder Bridge - Valve Installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-27 | 2020-08-07 | 2020-12-11 | 2021-03-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3051.61 | 39948.4 | 43000.01 | 0 | 43000.01 | 0 | [6 empty] | CM_WSI | 100%
505107 | S-W-I-100220-Elsrickle DMA Modelling Work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 1100 | 0 | 1100 | 0 | [6 empty] | CM_WSI | 100%
504627 | S-W-I-130120-Camps WTW Private Supply Water Tank Access | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 10991.63 | 8.37 | 11000 | 0 | 11000 | 0 | [6 empty] | CM_WSI | 100%
505720 | S-W-I-13032020-Sunnyside monitoring | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS2 |  | 2020-04-01 | 2020-07-24 | 2021-03-11 | 2020-10-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_M&G | 100%
504380 | S-W-I-171219-Burnbank Dunragit | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 32101.94 | -1.94 | 32100 | 0 | 32100 | 0 | [6 empty] | CM_WSI | 100%
504376 | S-W-I-171219-Meikleholm Langholm - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 9000 | 0 | [6 empty] | CM_WSI | 100%
505270 | S-W-I-180220-Bridgebank Stranraer - Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 15623.1 | 76.9 | 15700 | 0 | 15700 | 0 | [6 empty] | CM_WSI | 100%
505277 | S-W-I-180220-Hightown Of Craigs Dumfries - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | 5700 | 0 | 5700 | 0 | [6 empty] | CM_WSI | 100%
504408 | S-W-I-181219-Camps Private Water Supply Tank | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2626.64 | 73.36 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSI | 100%
505851 | S-W-I-200320-Kelloholm SR - Cut & Cap Enabling Abandonment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1050 | 15000 | 16050 | 0 | 16050 | 0 | [6 empty] | CM_WSI | 100%
505855 | S-W-I-200320-Kirkconnel DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 883.18 | 12616.82 | 13500 | 0 | 13500 | 0 | [6 empty] | CM_WSI | 100%
505836 | S-W-I-200320-Lanark Road West Link Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 1400 | 20000.02 | 21400.02 | 0 | 21400.02 | 0 | [6 empty] | CM_WSI | 100%
505345 | S-W-I-210220-Chesser Pipebridge Safety Gate | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 2250 | 0 | [6 empty] | CM_WSI | 100%
503955 | S-W-I-251119-Millisle Street Dalbeattie - Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 9364.95 | 35.05 | 9400 | 0 | 9400 | 0 | [6 empty] | CM_WSI | 100%
503966 | S-W-I-251119-Pennersaughs Farm Eaglesfied - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 32696.15 | -2696.15 | 30000 | 0 | 30000 | 0 | [6 empty] | CM_WSI | 100%
503976 | S-W-I-261119-Mill Road Lochmaben Link Main 90m | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 17992.36 | -492.36 | 17500 | 0 | 17500 | 0 | [6 empty] | CM_WSI | 100%
503984 | S-W-I-Cowgill Road Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2696.64 | 3.36 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WSNI | 100%
503977 | S-W-I-Lovedale Road and Euchan St Sanquhar - Mains Abandonment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 16567.77 | -467.77 | 16100 | 0 | 16100 | 0 | [6 empty] | CM_WSI | 100%
30934 | Swinstie (Cleland) STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-08 | 2010-11-16 | 2011-07-11 | 2012-03-16 | 2012-03-26 | North Lanarkshire | 966437.16 | 738.1 | 0 | 0 | 0 | 0 | 0 | 738.1 | 0 | 967175.26 | 0 | [6 empty] | CM_WWNI | 100%
500183 | Swinstie DOA (DOA000553) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-18 | 2018-01-31 | 2018-01-31 | North Lanarkshire | 0 | 90527 | 79975 | 30582.11 | 141.17 | 0 | 0.39 | 201225.67 | 0 | 201225.67 | 0 | [6 empty] | CS16D | 100% | bar: Regulatory Outputs OMG-22
501314 | Swinstie Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-12-23 | 2018-01-23 | 2018-01-24 | 2019-02-13 | 2019-02-13 | South Lanarkshire | 0 | 289255 | 174822 | 775529 | 2337639.6 | 754.4 | 0 | 3578000 | 0 | 3578000 | 0 | [6 empty] | CM_WWI | 100%
501166 | Swinstie STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-11-25 | 2018-06-22 | 2018-06-28 | 2020-08-31 | 2020-08-31 | South Lanarkshire | 0 | 17500 | 136005.61 | 72979.6 | 1052101.05 | 1020024.44 | 73937.14 | 2372547.84 | 7055.15 | 2379602.99 | 0 | [6 empty] | CM_WWNI | 100%
403191 | Swinstie WwTW Automatic Control | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-12-18 | 2013-03-25 | 2013-04-15 | 2015-09-25 |  | South Lanarkshire | 414909 | 0 | 177 | 7722.33 | 0 | 0 | 0 | 7899.33 | 0 | 422808.33 | 0 | [6 empty] | CM_WWI | 100%
45558 | Swinton STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-02-14 | 2011-08-26 | 2012-03-21 | 2012-03-30 | Scottish Borders | 866115.65 | 542.49 | 0 | 0 | 0 | 0 | 0 | 542.49 | 0 | 866658.14 | 0 | [6 empty] | CM_WWNI | 50% | WQ01 | 50%
500970 | SWM - Impact & Analysis - Stakeholder Engagement -Education and Communication | Q&S4 | Reducing flooding and pollution from sewers | Surface Water |  |  | Wastewater |  | SWD | Surface Water | MS3 | 2016-03-15 | 2016-03-15 | 2016-06-24 | 2021-04-23 | 2021-04-23 | Scottish Water Wide | 0 | 58977.37 | 101022.63 | 326694.3 | 376600.43 | 40151.39 | -6446.12 | 897000 | 0 | 897000 | 1335609.71 | [6 empty] | CS15C | 100%
49606 | SWMD - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWMD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | RISK | 100%
50036 | SWMD - SR21 Early Start - Profile Adjustment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -11591257.28 | -11591257.28 | 11591257.28 | 0 | 0 | [6 empty] | SR21_SS | 100%
49775 | SWMD - UWWTD - Works - Profile Adjustment | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | General |  | SWD | UWWTD - Works | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -8000000 | -8000000 | 8000000 | 0 | 0 | [6 empty] | SR15_ENV_UWWD | 100%
506035 | S-W-NI-010420- Fruid DIR Menzion intake replacement door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WSNI | 100%
506022 | S-W-NI-010420-Castle Moffat WTW septic tank flooding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 2050 | 0 | 2050 | 0 | [6 empty] | CM_WSNI | 100%
506034 | S-W-NI-010420-Hopes WTW Outlet Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 8300 | 8300 | 0 | 8300 | 0 | [6 empty] | CM_WSNI | 100%
506038 | S-W-NI-010420-Rosebery WTW Chlorine changeover unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 8100 | 0 | 8100 | 0 | [6 empty] | CM_WSNI | 100%
506039 | S-W-NI-010420-Strutherhill DSR Altitude Valve & Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 18400 | 18400 | 0 | 18400 | 0 | [6 empty] | CM_WSNI | 100%
504993 | S-W-NI-030220-Castle Moffat WTW- Sludge Plant Pipework Tanker Mods | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WSNI | 100%
504982 | S-W-NI-030220-Crosswood Reservoir fence remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 11200 | 0 | 11200 | 0 | [6 empty] | CM_WSNI | 100%
504540 | S-W-NI-070120-Rawburn wtw Poly Plant Fault Emergency Shutdown | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-15 | 2020-08-12 | 2020-11-11 | 2020-10-02 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4340.54 | 40659.5 | 45000.04 | 0 | 45000.04 | 0 | [6 empty] | CM_WSNI | 100%
505066 | S-W-NI-07022020-Glencorse Lime Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-09-30 | 2020-10-30 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 26500 | 0 | 26500 | 0 | 26500 | 0 | [6 empty] | CM_WSNI | 100%
505078 | S-W-NI-070220-Drumpellier PBS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-27 | 2020-08-27 | 2021-05-24 | 2021-05-25 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 230.71 | 0 | 230.71 | 0 | 230.71 | 0 | [6 empty] | WSNI | 100%
504247 | S-W-NI-091219-Rosebery WTW Alba dosing pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WSNI | 100%
504629 | S-W-NI-130120-Carrickstone Low path | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2979.46 | 20.54 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WSNI | 100%
504632 | S-W-NI-130120-Rawburn WTW - Handrailing at Clarifier Steps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WSNI | 100%
504631 | S-W-NI-130220-Daer WTW Security Gate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WSNI | 100%
505717 | S-W-NI-13032020 - Legbrannock Hammer Test | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-01 | 2020-08-05 | 2021-03-22 | 2020-10-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 40000 | 0 | [6 empty] | CM_WSNI | 100%
504680 | S-W-NI-160120-Carsphairn WTW - Generator Control Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5622.9 | 77.1 | 5700 | 0 | 5700 | 0 | [6 empty] | CM_WSNI | 100%
504693 | S-W-NI-160120-Glengap WTW - Sample waste pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 8850 | 0 | 8850 | 0 | 8850 | 0 | [6 empty] | CM_WSNI | 100%
504686 | S-W-NI-160120-Lochfoot Store WTW - Access Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5073.64 | 26.36 | 5100 | 0 | 5100 | 0 | [6 empty] | CM_WSNI | 100%
504703 | S-W-NI-170120-Glencorse WTW Ammonia Bund | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW1 |  | 2020-06-08 | 2020-07-29 | 2021-03-26 | 2021-03-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 230.82 | 0 | 230.82 | 0 | 230.82 | 0 | [6 empty] | CM_WSNI | 100%
505235 | S-W-NI-17022020-Glencorse DIR Road repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 18500 | 0 | 18500 | 0 | 18500 | 0 | [6 empty] | CM_WSNI | 100%
505230 | S-W-NI-170220-Castle Moffat WTW Alum Dosing Line | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WSNI | 100%
505232 | S-W-NI-170220-Castle Moffat WTW Raw water colour monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 21000 | 0 | 21000 | 0 | 21000 | 0 | [6 empty] | CM_WSNI | 100%
504383 | S-W-NI-171219-Chalkieside DSR Sample Point | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 6257.52 | -257.52 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WSNI | 100%
504386 | S-W-NI-171219-Fountainhall TWS Flow control valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 0 | [6 empty] | CM_WSNI | 100%
504367 | S-W-NI-171219-Glengap WTW - Hypo Dosing Kiosk and Tank Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 15474.02 | 25.98 | 15500 | 0 | 15500 | 0 | [6 empty] | CM_WSNI | 100%
504369 | S-W-NI-171219-Glengap WTW - Poly Dosing Tank Screens Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 9000 | 0 | [6 empty] | CM_WSNI | 100%
504371 | S-W-NI-171219-GlengapWTW - Sludge Press Cloth Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2465.55 | 34.45 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WSNI | 100%
504372 | S-W-NI-171219-Kettleton WTW - Access Path Handrail & Steps Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2003.94 | -353.94 | 1650 | 0 | 1650 | 0 | [6 empty] | CM_WSNI | 100%
505274 | S-W-NI-180220-Gubhill WPS - Pumps Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 17300 | 0 | 17300 | 0 | 17300 | 0 | [6 empty] | CM_WSNI | 100%
505255 | S-W-NI-180220-Hungry Snout WPS Upgrading of Site Fire Alarm System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WSNI | 100%
505257 | S-W-NI-180220-Megget DIR Dehumidifiers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 19000 | 0 | 19000 | 0 | [6 empty] | CM_WSNI | 100%
505262 | S-W-NI-180220-Rosebery WTW Supernatant pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WSNI | 100%
505790 | S-W-NI-180320-Limefield DSR - Inlet Flow Controllers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 487.38 | 6962.64 | 7450.02 | 0 | 7450.02 | 0 | [6 empty] | CM_WSNI | 100%
504412 | S-W-NI-181219-Camps Road Re-instatement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 3700 | 0 | 3700 | 0 | [6 empty] | CM_WSNI | 100%
504404 | S-W-NI-181219-Marchbank WTW Filter 3A and 4B backwash valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 22000 | 0 | [6 empty] | CM_WSNI | 100%
504403 | S-W-NI-181219-Rawburn WTW Replacement generator fuel tank & fuel station | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4136.77 | 63.23 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WSNI | 100%
504397 | S-W-NI-181219-Rosebery WTW Compressor refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 7457.39 | -2957.39 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WSNI | 100%
504400 | S-W-NI-181219-Rosebery WTW Supernatant pump repacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 2057.66 | 42.34 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WSNI | 100%
505293 | S-W-NI-190220-Kettleton WTW - New Handrail | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2650 | 0 | 2650 | 0 | 2650 | 0 | [6 empty] | CM_WSNI | 100%
505299 | S-W-NI-190220-Kettleton WTW - Refurbish steps - stairways in Main Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 4300 | 0 | 4300 | 0 | [6 empty] | CM_WSNI | 100%
505288 | S-W-NI-190220-Kettleton WTW - Caustic Tank Screens Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WSNI | 100%
505289 | S-W-NI-190220-Kettleton wtw plc alarm changes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4250 | 0 | 4250 | 0 | 4250 | 0 | [6 empty] | CM_WSNI | 100%
505330 | S-W-NI-200220-Eskdalemuir DSR - Telemetry Outstation Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WSNI | 100%
505318 | S-W-NI-200220-Killylour WTW - Recovered water turbidity meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3966.95 | 33.05 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WSNI | 100%
505326 | S-W-NI-200220-Langholm Whita DSR - Telemetry Building Access Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2463.55 | 36.45 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WSNI | 100%
505324 | S-W-NI-200220-Penwhirn WTW - UPS Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 6663.76 | -463.76 | 6200 | 0 | 6200 | 0 | [6 empty] | CM_WSNI | 100%
505321 | S-W-NI-200220-Terregles BH - Pump 2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | [6 empty] | CM_WSNI | 100%
505848 | S-W-NI-200320-Kettleton WTW - H&S Ground work Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 206.07 | 2943.93 | 3150 | 0 | 3150 | 0 | [6 empty] | CM_WSNI | 100%
505843 | S-W-NI-200320-Legbrannock Sample Building Flat Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 157.01 | 2242.99 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WSNI | 100%
505857 | S-W-NI-200320-Penwhirn WTW Old Sludge Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 870.09 | 12429.93 | 13300.02 | 0 | 13300.02 | 0 | [6 empty] | CM_WSNI | 100%
505845 | S-W-NI-200320-Winterhope WTW - Caustic Tank Heater Repalcement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 677.1 | 9672.9 | 10350 | 0 | 10350 | 0 | [6 empty] | CM_WSNI | 100%
505358 | S-W-NI-210220-Bonnycraig WTW Temporary Pressure Filter Housing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3883.5 | 316.5 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WSNI | 100%
505351 | S-W-NI-210220-Marchbank wtw - WW settlement tank No4 inlet actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 3400 | 0 | 3400 | 0 | 3400 | 0 | [6 empty] | CM_WSNI | 100%
505348 | S-W-NI-210220-Pateshill wtw - Pre-cip stop logs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 3050 | 0 | 3050 | 0 | [6 empty] | CM_WSNI | 100%
505356 | S-W-NI-210220-Rawburn WTW Replacement Press Filter Cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 212.62 | 3037.38 | 3250 | 0 | 3250 | 0 | [6 empty] | CM_WSNI | 100%
505361 | S-W-NI-210220-Strutherhill DSR Altitude Valve & Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-24 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 18500 | 0 | 18500 | 0 | 18500 | 0 | [6 empty] | CM_WSNI | 100%
505881 | S-W-NI-230320-Bonnycraig WTW - Welfare Cabin Service Connections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 330.37 | 4719.65 | 5050.02 | 0 | 5050.02 | 0 | [6 empty] | CM_WSNI | 100%
505877 | S-W-NI-230320-Howden WTW CIP Warm Water Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 153.74 | 2196.28 | 2350.02 | 0 | 2350.02 | 0 | [6 empty] | CM_WSNI | 100%
505875 | S-W-NI-230320-Watch Water - South Shore Replacement Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1373.83 | 19626.17 | 21000 | 0 | 21000 | 0 | [6 empty] | CM_WSNI | 100%
505882 | S-W-NI-230320-Yarrowfeus WTW - Redundant Sample Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-03-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 281.31 | 4018.71 | 4300.02 | 0 | 4300.02 | 0 | [6 empty] | CM_WSNI | 100%
503948 | S-W-NI-251119-AUCHNEEL WTW DRAINAGE WORKS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WSNI | 100%
503979 | S-W-NI-261119-Carnduff WPS Sump pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WSNI | 100%
503981 | S-W-NI-261119-Coulter WTW Sodium Hypochlorite Dosing System Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 15965.73 | 34.27 | 16000 | 0 | 16000 | 0 | [6 empty] | CM_WSNI | 100%
503990 | S-W-NI-261119-Daer WTW Aluminium Pump Additions | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 8015.91 | 84.09 | 8100 | 0 | 8100 | 0 | [6 empty] | CM_WSNI | 100%
504002 | S-W-NI-271119-Bonnycraig WTW Aluminium & Phosphate monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 29000 | 0 | 29000 | 0 | [6 empty] | CM_WSNI | 100%
504008 | S-W-NI-271119-Dingleton TWP Concrete Plinth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WSNI | 100%
504011 | S-W-NI-271119-Manse Street WTW Storage Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2045.63 | 54.37 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WSNI | 100%
504015 | S-W-NI-271119-Rawburn WTW Phosphate Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WSNI | 100%
504013 | S-W-NI-271119-Roberton WTW - Crane Hoist attachment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WSNI | 100%
504023 | S-W-NI-281119-Castle Moffat WTW - Access Road improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 7450.15 | 49.85 | 7500 | 0 | 7500 | 0 | [6 empty] | CM_WSNI | 100%
504039 | S-W-NI-281119-Castle Moffat WTW - DOC monitor refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 2183.96 | 1316.04 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WSNI | 100%
504025 | S-W-NI-281119-Castle Moffat WTW Clarifier 2 Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 0 | 17500 | 0 | [6 empty] | CM_WSNI | 100%
504042 | S-W-NI-281119-Castle Moffat WTW replacement lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 3061.75 | 38.25 | 3100 | 0 | 3100 | 0 | [6 empty] | CM_WSNI | 100%
504059 | S-W-NI-281119-Kettleton WTW Road Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3548.97 | -48.97 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WSNI | 100%
504051 | S-W-NI-281119-Longplantings TWS - Wall repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WSNI | 100%
504045 | S-W-NI-281119-Rosbery WTW - Washwater bays cleaning | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | 12500 | 0 | 12500 | 0 | [6 empty] | CM_WSNI | 100%
504032 | S-W-NI-28112019-Castle Moffat WTW - Phosphate monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 14598.14 | 1.86 | 14600 | 0 | 14600 | 0 | [6 empty] | CM_WSNI | 100%
503988 | S-W-NI-Daer WTW Aluminium Analyser replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 14010.5 | 89.5 | 14100 | 0 | 14100 | 0 | [6 empty] | CM_WSNI | 100%
505721 | S-W-NI-Daer WTW translucent panel replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW1 |  | 2020-06-08 | 2020-08-07 | 2021-03-25 | 2020-10-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WSNI | 100%
505719 | S-W-NI-Tannochside roof refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-01 | 2020-07-24 | 2021-04-08 | 2020-10-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 9090.91 | 9090.91 | 909.09 | 10000 | 0 | [6 empty] | CM_WSNI | 100%
30947 | SWO - Deans Industrial Estate North SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-10-27 | 2012-01-16 | 2014-03-07 | 2014-03-24 | West Lothian | 191500 | 7.27 | 0 | 0 | 0 | 0 | 0 | 7.27 | 0 | 191507.27 | 0 | [6 empty] | EC09B | 50% | EC10D | 50%
45240 | SWO - Edgefield Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-24 | 2012-02-06 | 2014-03-07 | 2014-03-24 | Midlothian | 157383 | -0.2 | 0 | 0 | 0 | 0 | 0 | -0.2 | 0 | 157382.8 | 0 | [6 empty] | EC09B | 50% | EC10D | 50%
30948 | SWO - Greendykes Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-10-27 | 2012-01-18 | 2013-07-24 | 2013-10-09 | West Lothian | 139722 | -125.19 | 0 | 0 | 0 | 0 | 0 | -125.19 | 0 | 139596.81 | 509 | [6 empty] | EC09B | 50% | EC10D | 50%
30952 | SWO - Pentland Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-14 | 2012-02-07 | 2014-08-22 | 2014-08-29 | Midlothian | 178935 | 734 | 0 | 0 | 0 | 0 | 0 | 734 | 0 | 179669 | 733 | [6 empty] | EC09B | 50% | EC10D | 50%
30953 | SWO - Pentland Retail Park SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-14 | 2012-02-06 | 2014-08-28 | 2014-10-22 | Midlothian | 192617 | 271.57 | 0 | 0 | 0 | 0 | 0 | 271.57 | 0 | 192888.57 | 393 | [6 empty] | EC09B | 50% | EC10D | 50%
30943 | SWO - Righead Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-24 | 2012-02-08 | 2014-08-22 | 2014-10-02 | North Lanarkshire | 237194 | 3003.4 | 0 | 0 | 0 | 0 | 0 | 3003.4 | 0 | 240197.4 | 47 | [6 empty] | EC09B | 50% | EC10D | 50%
300031 | SWS1 QS II Land Acquisition | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2015-11-03 | 2016-03-01 | Scottish Water Wide | 652554 | -25204.52 | 0 | 0 | 0 | 0 | 44.78 | -25159.74 | 0 | 627394.26 | 0 | [6 empty] | CM_M&G | 100%
300030 | SWS1 QS II Land Compensation Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2015-11-03 | 2016-03-01 | Scottish Water Wide | 529090.85 | 7926.05 | 0 | 0 | 0 | 0 | 1041.91 | 8967.96 | 0 | 538058.81 | 0 | [6 empty] | CM_M&G | 100%
300036 | SWS1 QS3a Land Acquisition | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2012-07-31 | 2012-07-31 | 2012-08-06 | 2015-11-03 | 2016-02-03 | Scottish Water Wide | 421388.47 | 1575.16 | 0 | 0 | 0 | 0 | 0 | 1575.16 | 0 | 422963.63 | 0 | [6 empty] | CM_M&G | 100%
401033 | SWS1 Waste Water (Allocation) CX5-6 costs | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | 288394.24 | 2.76 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 288397 | 0 | [6 empty] | OHDW1 | 100%
401031 | SWS1 Water (Allocated) CX5-6 costs | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | 154448.05 | 1.95 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 154450 | 0 | [6 empty] | OHDS1 | 100%
401030 | SWS1 Water (Managed) CX5-6 costs | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | -18550.59 | 33.32 | 114.45 | 0 | 0 | 0 | 0 | 147.77 | 0 | -18402.82 | 0 | [6 empty] | OHDW1 | 100%
47196 | SWS2 Early Start Costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS2 | 2001-02-25 | 2017-03-27 | 2022-05-30 | 2022-05-30 |  | Scottish Water Wide | 444841.06 | -57358.55 | -199844.5 | 313291.28 | -141782.53 | 168963.41 | 113579.56 | 196848.67 | 58310.38 | 700000.11 | 0 | [6 empty] | CM_M&G | 100%
402011 | SWS2 Fee reallocation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-02-24 | 2016-04-18 | 2016-03-08 | 2016-03-08 | 2016-03-08 | Scottish Water Wide | -487440 | 487440 | 0 | 0 | 0 | 0 | 1 | 487441 | 0 | 1 | 0 | [6 empty] | WSNI | 100%
402010 | SWS2 Overhead reallocation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS5 | 2011-02-24 |  |  | 2019-01-15 | 2019-01-15 | Scottish Water Wide | -800000 | 1330580 | 2484997 | 661852.97 | -942668.54 | -4994.72 | 0 | 3529766.71 | 0 | 2729766.71 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
47197 | SWS2 Transition Costs | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWMD | Non OMG180 | MS4 | 2001-02-25 | 2012-01-04 | 2018-04-30 | 2019-02-13 |  | Scottish Water Wide | -2150000 | -20771288 | 0 | 0 | 0 | 0 | 0 | -20771288 | 0 | -22921288 | -21921586.73 | [6 empty] | RISK_SWS2 | 100%
402382 | SWW Sulphuric Acid Plant Interventions - Reputational | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-29 | 2012-06-05 | 2012-07-25 | 2014-09-01 |  | Scottish Water Wide | 4056919 | 3800 | -3629.15 | 0 | 0 | 0 | 0 | 170.85 | 0 | 4057089.85 | 0 | [6 empty] | CM_WSNI | 100%
504278 | S-WW-I-101219-Blackwood -Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-11 |  | 2020-08-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 185000 | 0 | 185000 | 0 | 185000 | 0 | [6 empty] | CM_WWI | 100%
504275 | S-WW-I-101219-Kircudbright-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-11 |  | 2020-01-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 17564.96 | 2435.04 | 20000 | 0 | 20000 | 0 | [6 empty] | CM_WWI | 100%
505658 | S-WW-I-110320-26 Cultins Road Edinburgh-Engage jetting contractor to attempt retrieval of two jetting hoses | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 654.21 | 9345.81 | 10000.02 | 0 | 10000.02 | 0 | [6 empty] | CM_WWNI | 100%
505320 | S-WW-I-200220-Primrose Cottage Dalbeattie-Patching & Dig Up to Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5000 | 34999.98 | 39999.98 | 0 | 39999.98 | 0 | [6 empty] | CM_WWNI | 100%
504451 | S-WW-I-201219-Bellshill By-Pass-Repairs to brick chamber supporting the elevated sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-23 |  | 2020-08-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 21728.11 | -1728.11 | 20000 | 0 | 20000 | 0 | [6 empty] | CM_WWI | 100%
504464 | S-WW-I-201219-Scotts St Annan-Sewer Relay | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-23 |  | 2020-09-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 49000 | 0 | 49000 | 0 | 49000 | 0 | [6 empty] | CM_WWI | 100%
504786 | S-WW-I-220120-Tuphole Braidwood Rd Carluke-Rebuild Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-08-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 25000 | 8670 | 33670 | 0 | 33670 | 0 | [6 empty] | CM_WWNI | 100%
504354 | S-WW-I-New Troys Road Lesmahagow-Excavate & repair pipe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-16 |  | 2020-04-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 20100 | 0 | 20100 | 0 | 20100 | 0 | [6 empty] | CM_WWI | 100%
505521 | S-WW-MD RESPONSIVE - Beatsons Builders - Penicuik - Repair Damaged Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-03-05 |  | 2021-03-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3972.61 | 46027.38 | 49999.99 | 0 | 49999.99 | 0 | [6 empty] | CM_WWI | 100%
505524 | S-WW-MD RESPONSIVE - Burst Rising Main - Backlowther SPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-03-05 |  | 2021-03-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2616.82 | 37383.18 | 40000 | 0 | 40000 | 0 | [6 empty] | CM_WWI | 100%
504788 | S-WW-NI=220120-Troqueer WWTW-Relpace RAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 16002.57 | 0 | 16002.57 | 0 | 16002.57 | 0 | [6 empty] | CM_WWNI | 100%
506042 | S-WW-NI-01042020-Allers WWTW-Replacement Motor for Grit Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 5211.65 | 5211.65 | 88.33 | 5299.98 | 0 | [6 empty] | CM_WWNI | 100%
506019 | S-WW-NI-01042020-Bernard Steert Culvert-Flooding Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-04-01 |  | 2021-04-30 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 29500 | 500 | 30000 | 0 | [6 empty] | CM_WWI | 100%
506021 | S-WW-NI-01042020-Lockerbie WWTW-New Critical Spare Humus Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-04-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2360 | 2360 | 40 | 2400 | 0 | [6 empty] | CM_WWNI | 100%
506023 | S-WW-NI-01042020-Oxton WWTW-Suply & Fit Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 9636.65 | 9636.65 | 163.33 | 9799.98 | 0 | [6 empty] | CM_WWNI | 100%
506037 | S-WW-NI-01042020-Troqueer Final WWPS-Replacement of approx 150m chainlink fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 7768.35 | 7768.35 | 131.67 | 7900.02 | 0 | [6 empty] | CM_WWNI | 100%
503784 | S-WW-NI-011119-Philipshill WWTW-Storm Mixer Removal | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WWNI | 100%
506048 | S-WW-NI-02042020-Daldowie WWTW-Critical Spares for NTF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10325 | 10325 | 175 | 10500 | 0 | [6 empty] | CM_WWNI | 100%
506066 | S-WW-NI-02042020-Innerwick WWTW-Lifting Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3736.65 | 3736.65 | 63.33 | 3799.98 | 0 | [6 empty] | CM_WWNI | 100%
506054 | S-WW-NI-02042020-Mennock SEP-Replacment of path and steps to sample point | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3441.65 | 3441.65 | 58.33 | 3499.98 | 0 | [6 empty] | CM_WWNI | 100%
506058 | S-WW-NI-02042020-Olivers Tank SST-Install overland pipe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 6981.65 | 6981.65 | 118.33 | 7099.98 | 0 | [6 empty] | CM_WWI | 100%
506062 | S-WW-NI-02042020-Shotts WWTW-Replace compactor gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 6195 | 6195 | 105 | 6300 | 0 | [6 empty] | CM_WWNI | 100%
506064 | S-WW-NI-02042020-Tyneholm WWPS-Replacement of 2No Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-04-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 13963.35 | 13963.35 | 236.67 | 14200.02 | 0 | [6 empty] | CM_WWNI | 100%
504092 | S-WW-NI-021219-Bathgate WWTW-Repair to Boiler Room Roof | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 5705.96 | -2160.05 | 3545.91 | 0 | 3545.91 | 0 | [6 empty] | CM_WWNI | 100%
504104 | S-WW-NI-021219-Dunbar WWTW-Replace Permeate Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 1205.06 | -334.13 | 870.93 | 0 | 870.93 | 0 | [6 empty] | CM_WWNI | 100%
504089 | S-WW-NI-021219-Haddington WWTW-Replace Lower bearing on screw pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 36.94 | 2824.67 | 2861.61 | 0 | 2861.61 | 0 | [6 empty] | CM_WWNI | 100%
504097 | S-WW-NI-021219-North Berwick WWTW-Replacement Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 37473.98 | -15576.41 | 21897.57 | 0 | 21897.57 | 0 | [6 empty] | CM_WWNI | 100%
504085 | S-WW-NI-021219-Ormiston WWTW-Critical Spare Basket | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 2824.32 | -124.32 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504106 | S-WW-NI-021219-Troqueer WWTW-Replacement ball cock & float | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2491.3 | -1122.7 | 1368.6 | 0 | 1368.6 | 0 | [6 empty] | CM_WWNI | 100%
504125 | S-WW-NI-031219-Allers WWTW-Replacement Radio Link | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1938.89 | -138.89 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
504123 | S-WW-NI-031219-Port Rodie WWPS-Replacement Modems for SCADA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1868.36 | -468.36 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
504156 | S-WW-NI-041219-Annan WWTW-Screen Motor & Bearings Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 6187.46 | -2641.55 | 3545.91 | 0 | 3545.91 | 0 | [6 empty] | CM_WWNI | 100%
504137 | S-WW-NI-041219-Dunnswood WWTW-Refurb RAS Pump Set | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 9997.56 | -4149.91 | 5847.65 | 0 | 5847.65 | 0 | [6 empty] | CM_WWNI | 100%
504141 | S-WW-NI-041219-Eaglesham WWTW-Scraper Assembly Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3856.81 | -1679.49 | 2177.32 | 0 | 2177.32 | 0 | [6 empty] | CM_WWNI | 100%
505040 | S-WW-NI-050220-Dunnswood WWTW-Ferric Kiosk Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 8200 | 0 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WWNI | 100%
505038 | S-WW-NI-050220-Eastfield WWPS-Refurb Pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 8200 | 0 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WWNI | 100%
505043 | S-WW-NI-050220-Ravenscraig Main WWPS-Generator Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504186 | S-WW-NI-051219-Greengairs WWTW-Replace Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 5117.47 | -317.47 | 4800 | 0 | 4800 | 0 | [6 empty] | CM_WWNI | 100%
504177 | S-WW-NI-051219-Greengairs WWTW-Wallhead Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-06-30 | 2020-06-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 66102.05 | -15002.05 | 51100 | 0 | 51100 | 0 | [6 empty] | CM_WWNI | 100%
504184 | S-WW-NI-051219-Hamilton WWTW-Install External Lighting- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2878.48 | -1198.84 | 1679.64 | 0 | 1679.64 | 0 | [6 empty] | CM_WWNI | 100%
504165 | S-WW-NI-051219-Stonehouse WWTW-Critical Spare Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4043.59 | 0 | 4043.59 | 0 | 4043.59 | 0 | [6 empty] | CM_WWNI | 100%
505051 | S-WW-NI-060220-Blackridge WWTW-Parts for Storm Pump Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 1565.01 | 34.99 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
505063 | S-WW-NI-060220-Dumfries Loganbarns WWPS-Removal and resealing of exisitng multi-pane metal gable windows | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1491.46 | -91.46 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505058 | S-WW-NI-060220-Eyemouth WWTW-SBR2 Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505050 | S-WW-NI-060220-Linhouse Burn Pipe Bridge-H&S Bollard | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 1323.7 | -23.7 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
505060 | S-WW-NI-060220-Troqueer WWTW-Supply & Install Keypads for Access Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1284.64 | 0 | 1284.64 | 0 | 1284.64 | 0 | [6 empty] | CM_WWNI | 100%
505569 | S-WW-NI-060320-Bothwellbank WWTW-Building Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 663.44 | 9336.58 | 10000.02 | 0 | 10000.02 | 0 | [6 empty] | CM_WWNI | 100%
505591 | S-WW-NI-060320-Eccles WWTW-Repair Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 293.82 | 2506.2 | 2800.02 | 0 | 2800.02 | 0 | [6 empty] | CM_WWNI | 100%
505577 | S-WW-NI-060320-Glentrool WWTW-Refurb Centre Column | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3382.64 | -482.66 | 2899.98 | 0 | 2899.98 | 0 | [6 empty] | CM_WWNI | 100%
505585 | S-WW-NI-060320-Kirkinner WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  |  |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 192.9 | 2957.87 | 3150.77 | 49.23 | 3200 | 0 | [6 empty] | CM_WWNI | 100%
505586 | S-WW-NI-060320-Lauder WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3360.63 | -160.65 | 3199.98 | 0 | 3199.98 | 0 | [6 empty] | CM_WWNI | 100%
505588 | S-WW-NI-060320-Reston WWTW-Refurb Blower No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 196.26 | 2803.74 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
505571 | S-WW-NI-060320-Rose Lane WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 799.96 | 7200.02 | 7999.98 | 0 | 7999.98 | 0 | [6 empty] | CM_WWNI | 100%
504229 | S-WW-NI-061219-Capability Studies | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | [5 empty] | - | 0 | 0 | 0 | 0 | 0 | 24902.4 | 96508.34 | 121410.74 | 0 | 121410.74 | 0 | [6 empty] | CM_WWNI | 100%
504204 | S-WW-NI-061219-Coldstream WWTW-Replace Aerator No1 Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2610.66 | -310.66 | 2300 | 0 | 2300 | 0 | [6 empty] | CM_WWNI | 100%
504214 | S-WW-NI-061219-Coldstream WWTW-Replace Aerator No2 Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2291.04 | -291.04 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504198 | S-WW-NI-061219-Hamilton Grammar School CSO-Level Sensor Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWI | 100%
504552 | S-WW-NI-070120-Daldowie WWTW-Replace Pulley on NTF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1568.34 | -691.49 | 876.85 | 0 | 876.85 | 0 | [6 empty] | CM_WWNI | 100%
504547 | S-WW-NI-070120-Dumfries Rasgill WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2708.16 | -1283.27 | 1424.89 | 0 | 1424.89 | 0 | [6 empty] | CM_WWNI | 100%
504541 | S-WW-NI-070120-Kirkconnel WWTW-Replace 3 Solenoid Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1740.78 | -754.32 | 986.46 | 0 | 986.46 | 0 | [6 empty] | CM_WWNI | 100%
504536 | S-WW-NI-070120-Loch Ryan WWTW-Replacement Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2334.68 | -1074.2 | 1260.48 | 0 | 1260.48 | 0 | [6 empty] | CM_WWNI | 100%
505067 | S-WW-NI-070220-Fauldhouse WWTW-Replace manual desludge valves with actuators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 21100 | 0 | 21100 | 0 | 21100 | 0 | [6 empty] | CM_WWNI | 100%
505072 | S-WW-NI-070220-Gifford WWTW-Replacement Railings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 10100 | 0 | 10100 | 0 | 10100 | 0 | [6 empty] | CM_WWNI | 100%
505076 | S-WW-NI-070220-Hamilton WWTW-Refurbish ASP Feed Pump No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 17300 | 0 | 17300 | 0 | 17300 | 0 | [6 empty] | CM_WWNI | 100%
505084 | S-WW-NI-070220-Hutton WWTW-Supply & Fit Sprinkler Arms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 6600 | 0 | 6600 | 0 | [6 empty] | CM_WWNI | 100%
505073 | S-WW-NI-070220-Priory Bridge WWPS-Replace Foul Pump No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 9900 | 0 | 9900 | 0 | [6 empty] | CM_WWNI | 100%
505082 | S-WW-NI-070220-Reston WWTW-Refurbush Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3070.91 | -2260.91 | 810 | 0 | 810 | 0 | [6 empty] | CM_WWNI | 100%
505080 | S-WW-NI-070220-Troqueer STC-Supply & Fit 2no Valves onto decant pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3077.12 | -77.12 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
505077 | S-WW-NI-070220-Troqueer WWTW-Replacement Lighting at STC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5942.88 | -42.88 | 5900 | 0 | 5900 | 0 | [6 empty] | CM_WWNI | 100%
504571 | S-WW-NI-080120-Eyemoth WWTW-Inlet Screen Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 11034.64 | -4951.47 | 6083.17 | 0 | 6083.17 | 0 | [6 empty] | CM_WWNI | 100%
504561 | S-WW-NI-080120-Hagmill WWPS-2 Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 7562.86 | 0 | 7562.86 | 0 | 7562.86 | 0 | [6 empty] | CM_WWNI | 100%
504587 | S-WW-NI-090120-Bothwellbank WWTW-Replace Combi Compaction | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-05-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1210.63 | -459.76 | 750.87 | 0 | 750.87 | 0 | [6 empty] | CM_WWNI | 100%
504575 | S-WW-NI-090120-Carbarns WWTW-Replace Sludge Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-06-26 | 2020-02-26 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 19400.38 | 0 | 19400.38 | 0 | 19400.38 | 0 | [6 empty] | CM_WWNI | 100%
504578 | S-WW-NI-090120-Crossford WWTW-Refurb Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 6396.96 | -2889.55 | 3507.41 | 0 | 3507.41 | 0 | [6 empty] | CM_WWNI | 100%
504582 | S-WW-NI-090120-Lochmaben WWTW-PST Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-05-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4519.94 | -2108.59 | 2411.35 | 0 | 2411.35 | 0 | [6 empty] | CM_WWNI | 100%
504580 | S-WW-NI-090120-Troqueer STC-2No. Replacement Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 10631.65 | -4877.3 | 5754.35 | 0 | 5754.35 | 0 | [6 empty] | CM_WWNI | 100%
505615 | S-WW-NI-090320-Granton WWPS-Installation and commissioning of storm rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 300.93 | 4299.09 | 4600.02 | 0 | 4600.02 | 0 | [6 empty] | CM_WWNI | 100%
505592 | S-WW-NI-090320-Motehill WWPS-Replacement Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1125.23 | 16074.79 | 17200.02 | 0 | 17200.02 | 0 | [6 empty] | CM_WWNI | 100%
505600 | S-WW-NI-090320-North Middleton WWTW-Screen Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 719.63 | 10280.35 | 10999.98 | 0 | 10999.98 | 0 | [6 empty] | CM_WWNI | 100%
505593 | S-WW-NI-090320-Ormiston WWTW-Scraper Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 451.4 | 6448.6 | 6900 | 0 | 6900 | 0 | [6 empty] | CM_WWNI | 100%
504252 | S-WW-NI-091219-Dalscone WWTW-Overhaul of Grit Seperator Extra Costs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4116.44 | -216.44 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
504243 | S-WW-NI-091219-Dunnswood WWTW-Replace Grit Removal Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2009.2 | -109.2 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
504248 | S-WW-NI-091219-Woodbush WWPS-Safe Lifting Operation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-07-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 9567.46 | 432.54 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
505095 | S-WW-NI-100220-Ayton WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 4300 | 0 | 4300 | 0 | [6 empty] | CM_WWNI | 100%
505111 | S-WW-NI-100220-Broughton WWTW-Dismantle Drive & Fit New Chain | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2295.06 | -195.06 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
505100 | S-WW-NI-100220-Hawick WWTW-Replace Pressure Gauge on Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3224.13 | 75.88 | 3300.01 | 0 | 3300.01 | 0 | [6 empty] | CM_WWNI | 100%
505093 | S-WW-NI-100220-Hutton WWTW-Supply & Fit Scumboards & Brackets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3400 | 0 | 3400 | 0 | 3400 | 0 | [6 empty] | CM_WWNI | 100%
505097 | S-WW-NI-100220-Troqueer STC-Repair 3 sections of pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 9121.87 | 78.13 | 9200 | 0 | 9200 | 0 | [6 empty] | CM_WWNI | 100%
505637 | S-WW-NI-100320-Crossford WWTW-Parts to refurb the F.E turbidity meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2123.93 | 76.09 | 2200.02 | 0 | 2200.02 | 0 | [6 empty] | CM_WWNI | 100%
505645 | S-WW-NI-100320-Galashiels WWTW-Replacement PST 2 Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1514.31 | 85.71 | 1600.02 | 0 | 1600.02 | 0 | [6 empty] | CM_WWNI | 100%
505622 | S-WW-NI-100320-Haddington WWTW-Install Davit Arm for Safe Lifting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 490.65 | 7009.35 | 7500 | 0 | 7500 | 0 | [6 empty] | CM_WWNI | 100%
505634 | S-WW-NI-100320-Harthill WWTW-Replace the damaged rendering on the bothy | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 98.13 | 1401.87 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505620 | S-WW-NI-100320-PENICUIK VALLEYFIELD ROAD NO1 CSO - Repair CSO Screen Ram | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 4621.38 | -21.36 | 4600.02 | 0 | 4600.02 | 0 | [6 empty] | CM_WWI | 100%
505631 | S-WW-NI-100320-Philipshill WWTW-Cover legal costs for removal of persons illegaly occupying SW land | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.97 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
505619 | S-WW-NI-100320-Woodbush WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 392.52 | 5607.48 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504265 | S-WW-NI-101219-Port William WWTW-Replace Tank Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5783.04 | 216.97 | 6000.01 | 0 | 6000.01 | 0 | [6 empty] | CM_WWNI | 100%
505135 | S-WW-NI-110220-Broughton WWTW-Replace Corroded Pipework to Holding Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505143 | S-WW-NI-110220-Daldowie WWTW-Repair 2No Pot Holes in Access Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 621 | 0 | 621 | 0 | 621 | 0 | [6 empty] | CM_WWNI | 100%
505133 | S-WW-NI-110220-Newton Stewart WWTW-Emergency Light Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1369.88 | 30.13 | 1400.01 | 0 | 1400.01 | 0 | [6 empty] | CM_WWNI | 100%
505678 | S-WW-NI-110320-Castle Douglas WWTW-Supply & Fit Motor & Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 642.09 | 6657.93 | 7300.02 | 0 | 7300.02 | 0 | [6 empty] | CM_WWNI | 100%
505681 | S-WW-NI-110320-Dryffe Rd Lockerbie-Replacement Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 549.53 | 7850.47 | 8400 | 0 | 8400 | 0 | [6 empty] | CM_WWNI | 100%
505680 | S-WW-NI-110320-Eastriggs WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 346.73 | 4953.25 | 5299.98 | 0 | 5299.98 | 0 | [6 empty] | CM_WWNI | 100%
505666 | S-WW-NI-110320-HEATHHALL WHISKEY SPS CSO-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 425.23 | 6074.75 | 6499.98 | 0 | 6499.98 | 0 | [6 empty] | CM_WWI | 100%
505674 | S-WW-NI-110320-Loch Ryan WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1576.64 | 22523.38 | 24100.02 | 0 | 24100.02 | 0 | [6 empty] | CM_WWNI | 100%
505677 | S-WW-NI-110320-MINIGAFF HOLM PARK WWPS NX413652-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 703.18 | 7096.82 | 7800 | 0 | 7800 | 0 | [6 empty] | CM_WWNI | 100%
505660 | S-WW-NI-110320-Mosside WWPS-Replacement Grinder Critical Spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 1036.05 | 12263.97 | 13300.02 | 0 | 13300.02 | 0 | [6 empty] | CM_WWNI | 100%
505664 | S-WW-NI-110320-S Queensferry WWTW-Repair Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 4024.22 | 75.76 | 4099.98 | 0 | 4099.98 | 0 | [6 empty] | CM_WWI | 100%
505673 | S-WW-NI-110320-Troqueer STC-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 10501.56 | -1.56 | 10500 | 0 | 10500 | 0 | [6 empty] | CM_WWNI | 100%
505668 | S-WW-NI-110320-Troqueer STC-Supply and Replacement of 2No. Sludge Press Belts | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 14616.97 | 83.03 | 14700 | 0 | 14700 | 0 | [6 empty] | CM_WWNI | 100%
505671 | S-WW-NI-110320-Troqueer WWPS-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 700 | 9999.98 | 10699.98 | 0 | 10699.98 | 0 | [6 empty] | CM_WWNI | 100%
505662 | S-WW-NI-110320-Winchburgh WWTW-Upsize pump for the purpose of the tertiary SAF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 506.15 | 4693.87 | 5200.02 | 0 | 5200.02 | 0 | [6 empty] | CM_WWNI | 100%
503794 | S-WW-NI-111119-SKELLYTON WWTW-REPLACEMENT VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 7285.51 | 14.49 | 7300 | 0 | 7300 | 0 | [6 empty] | CM_WWNI | 100%
504297 | S-WW-NI-111219-Eastriggs WWTW-Sludge Pump Lagging | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4567 | -267 | 4300 | 0 | 4300 | 0 | [6 empty] | CM_WWNI | 100%
504302 | S-WW-NI-111219-Plains WWTW-Replace Dry Bearing Shaft | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 8830.46 | -530.46 | 8300 | 0 | 8300 | 0 | [6 empty] | CM_WWNI | 100%
505160 | S-WW-NI-120220-22 Lower Gilmore Place-Internal Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-04-30 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 50000 | 0 | [6 empty] | CM_WWI | 100%
505158 | S-WW-NI-120220-Auchencrow WWTW-Filter Arms Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505165 | S-WW-NI-120220-Gorebridge WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 1393.79 | 6.21 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505157 | S-WW-NI-120220-Hawick WWTW-Remote Telemetry Units | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
505167 | S-WW-NI-120220-Penicuik WWTW-Replacement Level Transmitter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505155 | S-WW-NI-120220-Penpont Sep-Construction of Layby | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-10-01 |  | 2020-11-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1771.86 | 13928.14 | 15700 | 0 | 15700 | 0 | [6 empty] | CM_WWNI | 100%
505163 | S-WW-NI-120220-Philipshill WWTW-Replace Motor on Fine Screen A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505685 | S-WW-NI-120320-Ayton WWPS-Replacement Transfer Pump2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 463.91 | 4936.09 | 5400 | 0 | 5400 | 0 | [6 empty] | CM_WWNI | 100%
505701 | S-WW-NI-120320-Cairnryan WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 130.84 | 1869.14 | 1999.98 | 0 | 1999.98 | 0 | [6 empty] | CM_WWNI | 100%
505700 | S-WW-NI-120320-Dladowie WWTW-Replace Actuator Supports | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 256.63 | 3243.35 | 3499.98 | 0 | 3499.98 | 0 | [6 empty] | CM_WWNI | 100%
505689 | S-WW-NI-120320-Dunnswood WWTW-Replace Motor & Gearbox on Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 289.34 | 3710.68 | 4000.02 | 0 | 4000.02 | 0 | [6 empty] | CM_WWNI | 100%
505705 | S-WW-NI-120320-Eyemouth WWTW-installing spindles within the Hydro Brake chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 91.59 | 1308.39 | 1399.98 | 0 | 1399.98 | 0 | [6 empty] | CM_WWNI | 100%
505702 | S-WW-NI-120320-Hawick stc-Replacement Motors x2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1225.25 | 74.77 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
505683 | S-WW-NI-120320-Leet Green WWPS-Refurb 2No Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3851.87 | -51.89 | 3799.98 | 0 | 3799.98 | 0 | [6 empty] | CM_WWNI | 100%
505692 | S-WW-NI-120320-Leet Green WWPS-Replace Damaged Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2712.31 | -112.33 | 2599.98 | 0 | 2599.98 | 0 | [6 empty] | CM_WWNI | 100%
505695 | S-WW-NI-120320-Leet Green WWPS-Replacement Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2870.66 | -70.64 | 2800.02 | 0 | 2800.02 | 0 | [6 empty] | CM_WWNI | 100%
505682 | S-WW-NI-120320-Lockerbie WWTW-Refurbish Filter Bed Column 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 183.18 | 2616.84 | 2800.02 | 0 | 2800.02 | 0 | [6 empty] | CM_WWNI | 100%
505688 | S-WW-NI-120320-Powfoot WWPS-Replace 2x Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 261.68 | 3738.34 | 4000.02 | 0 | 4000.02 | 0 | [6 empty] | CM_WWNI | 100%
505704 | S-WW-NI-120320-Shotts Network Enforcement Notice EN | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 353.27 | 5046.73 | 5400 | 0 | 5400 | 0 | [6 empty] | CM_WWI | 100%
504334 | S-WW-NI-121219-Hamilton WWTW-Install Sludge Blanket Detectors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-10-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WWNI | 100%
504325 | S-WW-NI-121219-Harleyholm SEP-Blocked Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-09-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 21715.9 | 3284.1 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WWNI | 100%
504311 | S-WW-NI-121219-Hawick WWTW-Structural Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 7246.38 | -746.38 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WWNI | 100%
504307 | S-WW-NI-121219-Kelso WWTW-Blower Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4229.78 | -329.78 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
504318 | S-WW-NI-121219-Loch Ryan WWTW-Site Inv & Condition Report | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3105.04 | -405.04 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504331 | S-WW-NI-121219-South Vennel Lanark-re lay approx 100m of sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-13 |  | 2020-08-31 | 2020-08-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 120000 | 0 | [6 empty] | CM_WWI | 100%
504322 | S-WW-NI-121219-Thornhill WWTW-Replace NRV & Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1468.08 | -268.08 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
504315 | S-WW-NI-121219-Troqueer WWTW-PST 3 Scum Scrapers Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 7805.25 | -405.25 | 7400 | 0 | 7400 | 0 | [6 empty] | CM_WWNI | 100%
504310 | S-WW-NI-121219-Tweed Bank WWPS-Rising Main Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 24800 | 0 | 24800 | 0 | 24800 | 0 | [6 empty] | CM_WWNI | 100%
504624 | S-WW-NI-130120-Foulden WWTW-Storm tank repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1612.32 | -845.07 | 767.25 | 0 | 767.25 | 0 | [6 empty] | CM_WWNI | 100%
504621 | S-WW-NI-130120-Walkerburn WWTW-Screen Hinges Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2010.7 | -969.44 | 1041.26 | 0 | 1041.26 | 0 | [6 empty] | CM_WWNI | 100%
505182 | S-WW-NI-130220-Burnhead SEP-Road Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 459 | 0 | 459 | 0 | 459 | 0 | [6 empty] | CM_WWNI | 100%
505177 | S-WW-NI-130220-Dunragit WWTW-Demolition and make safe of old PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 540 | 0 | 540 | 0 | 540 | 0 | [6 empty] | CM_WWNI | 100%
505691 | S-WW-NI-130320-Dunbar WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 3175.23 | -275.25 | 2899.98 | 0 | 2899.98 | 0 | [6 empty] | CM_WWNI | 100%
503816 | S-WW-NI-131119-Coldstream WWTW-Outfall Pipe Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4152.4 | -252.4 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
503818 | S-WW-NI-131119-Dumfries St Marys WWPS-Civil Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1210.64 | -110.64 | 1100 | 0 | 1100 | 0 | [6 empty] | CM_WWNI | 100%
503811 | S-WW-NI-131119-Plains WWTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 9927.66 | -27.66 | 9900 | 0 | 9900 | 0 | [6 empty] | CM_WWI | 100%
503814 | S-WW-NI-131119-Port Rodie SPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 28238.59 | -2638.59 | 25600 | 0 | 25600 | 0 | [6 empty] | CM_WWNI | 100%
503822 | S-WW-NI-131119-ST ABBS NORTH SPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2424.5 | -224.5 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WWNI | 100%
503815 | S-WW-NI-131119-Troqueer WWTW-Klampress Belt Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 13151.27 | -442.56 | 12708.71 | 0 | 12708.71 | 0 | [6 empty] | CM_WWI | 100%
503812 | S-WW-NI-13112019-Dalscone WWTW-Refurb Scraper Supports | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4456.16 | -1710.61 | 2745.55 | 0 | 2745.55 | 0 | [6 empty] | CM_WWI | 100%
504641 | S-WW-NI-140120-Daldowie WWTW-FST Gearbox Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1712.62 | -780.96 | 931.66 | 0 | 931.66 | 0 | [6 empty] | CM_WWNI | 100%
504639 | S-WW-NI-140120-Shotts WWTW-Refurb Anoxic Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1306.91 | -594.47 | 712.44 | 0 | 712.44 | 0 | [6 empty] | CM_WWNI | 100%
505191 | S-WW-NI-140220-Auchencairn SEP-Reinstate Grasscrete | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
505205 | S-WW-NI-140220-Eyemouth WWTW-Replace Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
505194 | S-WW-NI-140220-Lilliesleaf WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505202 | S-WW-NI-140220-Lockerbie WWTW-Filter Bed Access Steps & Handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | [6 empty] | CM_WWNI | 100%
505196 | S-WW-NI-140220-Newcastleton WWTW-Replacement Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-10-01 |  | 2020-11-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4740.5 | 45159.5 | 49900 | 0 | 49900 | 0 | [6 empty] | CM_WWNI | 100%
504356 | S-WW-NI-161219-Haddington WWTW-Hydraullic Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-10-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 8578.8 | 1421.2 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504361 | S-WW-NI-161219-Maxwell Park Dalbeattie-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-16 |  | 2020-09-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 35700 | 0 | 35700 | 0 | 35700 | 0 | [6 empty] | CM_WWI | 100%
504357 | S-WW-NI-161219-North Berwick WWTW-6 month Outfall Bouy Repair Checks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-06-26 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 17376.16 | -2376.16 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WWNI | 100%
504359 | S-WW-NI-161219-Wester Dunnes WWPS-Install chamber over rising main and install an isolation valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2020-08-31 | 2020-08-31 | East Lothian | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | [6 empty] | CM_WWNI | 100%
504700 | S-WW-NI-17012020-Eastfield WWPS-Replacement DWF Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 12440.36 | 0 | 12440.36 | 0 | 12440.36 | 0 | [6 empty] | CM_WWNI | 100%
504702 | S-WW-NI-17012020-Pathhead WWTW-Filterbed Centre Column Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 9611.15 | -4350.03 | 5261.12 | 0 | 5261.12 | 0 | [6 empty] | CM_WWNI | 100%
504705 | S-WW-NI-170120-Annan WWTW-Repairs to Grit plant & pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 5455.8 | -2551.22 | 2904.58 | 0 | 2904.58 | 0 | [6 empty] | CM_WWNI | 100%
504706 | S-WW-NI-170120-Carfin WWPS-Refurb Submersible Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2815.38 | -1390.49 | 1424.89 | 0 | 1424.89 | 0 | [6 empty] | CM_WWNI | 100%
504701 | S-WW-NI-170120-Eastfield WWPS-Refurbish Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 7836.88 | 0 | 7836.88 | 0 | 7836.88 | 0 | [6 empty] | CM_WWNI | 100%
504716 | S-WW-NI-170120-Gullane WWTW-Replacement FE Pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 5315.92 | 0 | 5315.92 | 0 | 5315.92 | 0 | [6 empty] | CM_WWNI | 100%
504708 | S-WW-NI-170120-Hamilton WWTW-Critical Spare Grinder | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 8713.73 | 0 | 8713.73 | 0 | 8713.73 | 0 | [6 empty] | CM_WWNI | 100%
504714 | S-WW-NI-170120-Hawick WWTW-Refurb Compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 10892.88 | -5248.14 | 5644.74 | 0 | 5644.74 | 0 | [6 empty] | CM_WWNI | 100%
504712 | S-WW-NI-170120-Kirkconnel WWTW-Modify Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 9654.46 | -733.32 | 8921.14 | 0 | 8921.14 | 0 | [6 empty] | CM_WWNI | 100%
504718 | S-WW-NI-170120-North Berwick WWTW-Screen Critical Spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 10613.93 | -4804.78 | 5809.15 | 0 | 5809.15 | 0 | [6 empty] | CM_WWNI | 100%
505228 | S-WW-NI-170220-Galashiels STC-Digester Mixer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 32100 | 0 | 32100 | 0 | 32100 | 0 | [6 empty] | CM_WWNI | 100%
505240 | S-WW-NI-170220-Galashiels WWTW-Replacement PST2 Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2896.69 | -296.69 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WWNI | 100%
505238 | S-WW-NI-170220-Granton WWPS-Replace pumps with Flygt pumps with a new VSD panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-06-26 |  | 2020-07-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 5000 | 23600 | 28600 | 0 | 28600 | 0 | [6 empty] | CM_WWNI | 100%
505782 | S-WW-NI-170320-Dunnswood WWTW-Replacement Inlet Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 132.33 | 1467.69 | 1600.02 | 0 | 1600.02 | 0 | [6 empty] | CM_WWNI | 100%
505778 | S-WW-NI-170320-Galashiels WWTW-Replacement Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 208.77 | 1291.23 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505783 | S-WW-NI-170320-Hamilton WWTW-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 171.59 | 2028.43 | 2200.02 | 0 | 2200.02 | 0 | [6 empty] | CM_WWNI | 100%
505770 | S-WW-NI-170320-Lanark WWTW-Replacement Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 78.5 | 1121.5 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
505780 | S-WW-NI-170320-Linthaugh WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 209.35 | 2990.63 | 3199.98 | 0 | 3199.98 | 0 | [6 empty] | CM_WWNI | 100%
505768 | S-WW-NI-170320-Lockerbie WWTW-Filter Bed Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 143.93 | 2056.09 | 2200.02 | 0 | 2200.02 | 0 | [6 empty] | CM_WWNI | 100%
505765 | S-WW-NI-170320-MILLDOWN WWPS-installing spindles within the Hydro Brake chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 228.4 | 1571.6 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
505772 | S-WW-NI-170320-Reston WWTW-move blowers and associated pipework away from the SAF unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2121.9 | -221.88 | 1900.02 | 0 | 1900.02 | 0 | [6 empty] | CM_WWNI | 100%
504385 | S-WW-NI-171219-Mauldslie WWTW-Replace Rotork Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1347.59 | 52.41 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
503853 | S-WW-NI-181119-Dalry WWTW-Rotork Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1743.73 | -43.73 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
503843 | S-WW-NI-181119-Rigside WWTW-Replacement Brackets | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2112.84 | -112.84 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWI | 100%
503845 | S-WW-NI-181119-Shotts WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1614.51 | -114.51 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
503852 | S-WW-NI-181119-Swinstie WWTW-Refurb Desludge Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4244.68 | -244.68 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
503842 | S-WW-NI-181119-Swinstie WWTW-Replacement MCC Component | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1089.2 | -361.45 | 727.75 | 0 | 727.75 | 0 | [6 empty] | CM_WWNI | 100%
503850 | S-WW-NI-181119-Troqueer WWTW-Blower Diaphragm Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1392.14 | -292.14 | 1100 | 0 | 1100 | 0 | [6 empty] | CM_WWNI | 100%
503848 | S-WW-NI-181119-Troqueer WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2108.65 | -208.65 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
503847 | S-WW-NI-181119-Wanlockhead WWTW-Replacement Do Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1451.75 | -151.75 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504398 | S-WW-NI-181219-Bothwellbank WWTW-Refurbish Sludge Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3415.56 | -15.56 | 3400 | 0 | 3400 | 0 | [6 empty] | CM_WWNI | 100%
504402 | S-WW-NI-181219-Galashiels STC-Thickened Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 6300 | 0 | 6300 | 0 | 6300 | 0 | [6 empty] | CM_WWNI | 100%
504405 | S-WW-NI-181219-Gretna WWTW-Refurb Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3952.37 | -152.37 | 3800 | 0 | 3800 | 0 | [6 empty] | CM_WWNI | 100%
504407 | S-WW-NI-181219-Gretna WWTW-Replacement Pump panels & VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 8500 | 0 | 8500 | 0 | [6 empty] | CM_WWNI | 100%
504410 | S-WW-NI-181219-Hamilton WWTW-Internal lining of the sludge holding tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-06-26 | 2020-02-25 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 80000 | 0 | 80000 | 0 | [6 empty] | CM_WWNI | 100%
504396 | S-WW-NI-181219-Philipshill WWTW-Replacement Rotork for Storm Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1262.31 | 37.69 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
504413 | S-WW-NI-181219-Shotts WWTW-Replacement Showers & Toilets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4022.9 | 277.11 | 4300.01 | 0 | 4300.01 | 0 | [6 empty] | CM_WWNI | 100%
504394 | S-WW-NI-181219-Skellyton WWTW-Refurbish Storm Screen Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-18 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2140.6 | 59.4 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WWNI | 100%
504401 | S-WW-NI-181219-South Queensferry WWTW-Tank Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-08-31 | 2020-08-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 10700 | 0 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_WWNI | 100%
505282 | S-WW-NI-190220-Bothwellbank WWTW-Repair Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 339.03 | 4560.98 | 4900.01 | 0 | 4900.01 | 0 | [6 empty] | CM_WWNI | 100%
505284 | S-WW-NI-190220-Galashiels STC-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 8093.41 | -193.41 | 7900 | 0 | 7900 | 0 | [6 empty] | CM_WWNI | 100%
505286 | S-WW-NI-190220-Galashiels STC-Sludge Pump Shelter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 440.44 | 4459.58 | 4900.02 | 0 | 4900.02 | 0 | [6 empty] | CM_WWNI | 100%
505300 | S-WW-NI-190220-Gretna WWTW-Replacement Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 247.44 | 2881.26 | 3128.7 | 0 | 3128.7 | 0 | [6 empty] | CM_WWNI | 100%
505295 | S-WW-NI-190220-Shotts WWTW-Refurb Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4030.3 | 69.71 | 4100.01 | 0 | 4100.01 | 0 | [6 empty] | CM_WWNI | 100%
505291 | S-WW-NI-190220-Swinstie WWTW-Screen Compactor Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 7706.12 | 93.88 | 7800 | 0 | 7800 | 0 | [6 empty] | CM_WWNI | 100%
505817 | S-WW-NI-190320-Blackridge WWTW-Refurb Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 464.49 | 6635.49 | 7099.98 | 0 | 7099.98 | 0 | [6 empty] | CM_WWNI | 100%
505810 | S-WW-NI-190320-Bothwellbank WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 132.33 | 1467.69 | 1600.02 | 0 | 1600.02 | 0 | [6 empty] | CM_WWNI | 100%
505811 | S-WW-NI-190320-Chapelton WWTW-Replace inlet penstock actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 85.05 | 1214.97 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
505823 | S-WW-NI-190320-Dunbar WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 2533.03 | 66.95 | 2599.98 | 0 | 2599.98 | 0 | [6 empty] | CM_WWNI | 100%
505824 | S-WW-NI-190320-Eaglesham WWTW-Installation of Handrailing around unprotected edge at FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 217.38 | 2682.6 | 2899.98 | 0 | 2899.98 | 0 | [6 empty] | CM_WWNI | 100%
505827 | S-WW-NI-190320-Ladywell SPS-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 465.98 | 6234.04 | 6700.02 | 0 | 6700.02 | 0 | [6 empty] | CM_WWNI | 100%
505826 | S-WW-NI-190320-Lauder WWTW-H&S Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 875.49 | 9124.53 | 10000.02 | 0 | 10000.02 | 0 | [6 empty] | CM_WWNI | 100%
505814 | S-WW-NI-190320-NEWTOWN ST BOSWELLS WWTW-Replacement of the spool valves on the sprinkler arm drives | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 202.23 | 1197.75 | 1399.98 | 0 | 1399.98 | 0 | [6 empty] | CM_WWNI | 100%
505815 | S-WW-NI-190320-Shotts WWTW-Supply and Fit Handrails H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 184.67 | 2215.33 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WWNI | 100%
505816 | S-WW-NI-190320-Stonehouse WWTW-Replace motor on NTF with better IP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 124.3 | 1775.72 | 1900.02 | 0 | 1900.02 | 0 | [6 empty] | CM_WWNI | 100%
505820 | S-WW-NI-190320-Strathaven WWTW-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 189.72 | 2710.26 | 2899.98 | 0 | 2899.98 | 0 | [6 empty] | CM_WWNI | 100%
503859 | S-WW-NI-191119-Bridgend WWTW-Fabrication Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 16315.4 | -1115.4 | 15200 | 0 | 15200 | 0 | [6 empty] | CM_WWNI | 100%
503866 | S-WW-NI-191119-Cockenzie WWPS-Replacement Hydranger Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
503863 | S-WW-NI-191119-Eastfield WWPS-Replacement Fan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 4081.66 | -1501.46 | 2580.2 | 0 | 2580.2 | 0 | [6 empty] | CM_WWNI | 100%
503857 | S-WW-NI-191119-Gordon WWTW-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1845.95 | -245.95 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
503869 | S-WW-NI-191119-Kelso WWTW-Refurb Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 1100 | 0 | 1100 | 0 | [6 empty] | CM_WWNI | 100%
503870 | S-WW-NI-191119-Lochmaben WWTW-Refurb Faulty MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1311.14 | -517.24 | 793.9 | 0 | 793.9 | 0 | [6 empty] | CM_WWNI | 100%
503867 | S-WW-NI-191119-Tyneholm WWPS-Replacement Impellor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 1638.95 | -38.95 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
504429 | S-WW-NI-191219-Eastfield WWPS-Replacement GRP Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 2291.71 | 8.3 | 2300.01 | 0 | 2300.01 | 0 | [6 empty] | CM_WWNI | 100%
504436 | S-WW-NI-191219-Eastfield WWPS-VSD Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 3949.46 | 50.54 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504431 | S-WW-NI-191219-Philipshill WWTW-Install Handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-10-30 | 2020-10-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 105784.53 | 44215.47 | 150000 | 0 | 150000 | 0 | [6 empty] | CM_WWNI | 100%
504420 | S-WW-NI-191219-Troqueer STC-Cake Conveyor Lids | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3728.66 | 71.35 | 3800.01 | 0 | 3800.01 | 0 | [6 empty] | CM_WWNI | 100%
504418 | S-WW-NI-191219-Troqueer WWTW-Tanker Imports Transfer Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5652.42 | -152.42 | 5500 | 0 | 5500 | 0 | [6 empty] | CM_WWNI | 100%
504421 | S-WW-NI-191219-Whitecross WWTW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-12-01 | 2020-12-01 | East Lothian | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 0 | [6 empty] | CM_WWNI | 100%
505328 | S-WW-NI-200220-Carronbridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 182.99 | 3417.02 | 3600.01 | 0 | 3600.01 | 0 | [6 empty] | CM_WWNI | 100%
505329 | S-WW-NI-200220-Dalscone WWTW-Supply and fit gate valve on outfall pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2903.14 | -3.14 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
505325 | S-WW-NI-200220-Refurb Sludge Holding Tank Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2813.45 | 86.55 | 2900 | 0 | 2900 | 0 | [6 empty] | CM_WWNI | 100%
505837 | S-WW-NI-200320-Ashgill WWTW-Handrailing Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 431.78 | 6168.22 | 6600 | 0 | 6600 | 0 | [6 empty] | CM_WWNI | 100%
505852 | S-WW-NI-200320-Athelstaneford WWTW-Repair Footpaths | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 471.03 | 6728.97 | 7200 | 0 | 7200 | 0 | [6 empty] | CM_WWNI | 100%
505835 | S-WW-NI-200320-Bothwellbank WWTW-Supply and Fit Handrails and Steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 256.63 | 3243.35 | 3499.98 | 0 | 3499.98 | 0 | [6 empty] | CM_WWNI | 100%
505850 | S-WW-NI-200320-Coursington WWTW-Refurb Tanker Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2813.08 | 40186.94 | 43000.02 | 0 | 43000.02 | 0 | [6 empty] | CM_WWNI | 100%
505832 | S-WW-NI-200320-Daldowie WWTW-Supply and Fit Handrails and Kickplate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 217.38 | 2682.6 | 2899.98 | 0 | 2899.98 | 0 | [6 empty] | CM_WWNI | 100%
505831 | S-WW-NI-200320-Hamilton WWTW-Handrails & Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 223.92 | 2776.08 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
505849 | S-WW-NI-200320-Harthill WWTW-Replace the 2 slip rings on the PSTs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3994.8 | 5.22 | 4000.02 | 0 | 4000.02 | 0 | [6 empty] | CM_WWNI | 100%
505847 | S-WW-NI-200320-Hawick STC-Wall Alteration Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3602.95 | 46397.03 | 49999.98 | 0 | 49999.98 | 0 | [6 empty] | CM_WWNI | 100%
505838 | S-WW-NI-200320-Lesmahagow WWTW-Install Handrailing around Site Office | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 366.36 | 5233.62 | 5599.98 | 0 | 5599.98 | 0 | [6 empty] | CM_WWNI | 100%
505853 | S-WW-NI-200320-Oxton WWTW-Replace existing perimeter fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2289.72 | 32710.26 | 34999.98 | 0 | 34999.98 | 0 | [6 empty] | CM_WWNI | 100%
505846 | S-WW-NI-200320-Troqueer Final WWPS-Refurb Walkways around SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 556.07 | 7943.95 | 8500.02 | 0 | 8500.02 | 0 | [6 empty] | CM_WWNI | 100%
505841 | S-WW-NI-200320-Troqueer WWTW-Correct the safe turning point for the Artic | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1177.57 | 16822.43 | 18000 | 0 | 18000 | 0 | [6 empty] | CM_WWNI | 100%
503884 | S-WW-NI-201119-Biggar WWTW-Replacement Motor | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3558.64 | -158.64 | 3400 | 0 | 3400 | 0 | [6 empty] | CM_WWI | 100%
503885 | S-WW-NI-201119-Carstairs Junc WWTW-Supply and fit GRP Walkway | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4885.35 | -285.35 | 4600 | 0 | 4600 | 0 | [6 empty] | CM_WWI | 100%
503878 | S-WW-NI-201119-Glassford WWTW-Repair Basket | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4002.55 | -202.55 | 3800 | 0 | 3800 | 0 | [6 empty] | CM_WWI | 100%
503891 | S-WW-NI-201119-Newton Stewart WWTW-Lifting Equipment Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2842.02 | -242.02 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WWNI | 100%
503892 | S-WW-NI-201119-Newton Stewart WWTW-Refurb Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 8611.7 | -511.7 | 8100 | 0 | 8100 | 0 | [6 empty] | CM_WWNI | 100%
503889 | S-WW-NI-201119-Newton Stewart WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 11162.09 | -662.09 | 10500 | 0 | 10500 | 0 | [6 empty] | CM_WWI | 100%
504460 | S-WW-NI-201219-Eastriggs WWTW-Sludge Thickener Stairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-09-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 17157.59 | 2842.41 | 20000 | 0 | 20000 | 0 | [6 empty] | CM_WWNI | 100%
504452 | S-WW-NI-201219-Windygoul Replacement Control Panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-09-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 55259 | 18741 | 74000 | 0 | 74000 | 0 | [6 empty] | CM_WWNI | 100%
504444 | S-WW-NI-202119-Kirkconnel WWTW-Replacement Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-10-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 54904.3 | 9095.71 | 64000.01 | 0 | 64000.01 | 0 | [6 empty] | CM_WWNI | 100%
504755 | S-WW-NI-210120 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2779.98 | -1300.29 | 1479.69 | 0 | 1479.69 | 0 | [6 empty] | CM_WWNI | 100%
504761 | S-WW-NI-210120-Troqueer WWTW-Replacement Grit Detritor Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1479.69 | 0 | 1479.69 | 0 | 1479.69 | 0 | [6 empty] | CM_WWNI | 100%
505344 | S-WW-NI-2102202-Newton Stewart WWTW-Aerator Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 541.26 | 5758.73 | 6299.99 | 0 | 6299.99 | 0 | [6 empty] | CM_WWNI | 100%
505352 | S-WW-NI-210220-North Berwick WWTW-Replacement Lights | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 1400.82 | -0.82 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505340 | S-WW-NI-210220-Selkirk WWTW-Aeration Gearbox Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-06-01 | 2020-06-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2626.99 | 26240.39 | 28867.38 | 1132.62 | 30000 | 0 | [6 empty] | CM_WWNI | 100%
505347 | S-WW-NI-210220-Skellyton WWTW-Pipework Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 709.24 | 10590.77 | 11300.01 | 0 | 11300.01 | 0 | [6 empty] | CM_WWNI | 100%
503919 | S-WW-NI-211119-Annan Riverside WWPS-Install fall arrest protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2501.89 | -1178.71 | 1323.18 | 0 | 1323.18 | 0 | [6 empty] | CM_WWNI | 100%
503902 | S-WW-NI-211119-Gifford WWTW-Replace Handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 6615.88 | 0 | 6615.88 | 0 | 6615.88 | 0 | [6 empty] | CM_WWNI | 100%
503898 | S-WW-NI-211119-Kirkcudbright SPS-Replacement Pump & Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 30300 | 0 | 30300 | 0 | 30300 | 0 | [6 empty] | CM_WWNI | 100%
503914 | S-WW-NI-211119-Moniaive WWTW-Provide H&S Hoist | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2663.74 | -263.74 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WWNI | 100%
503916 | S-WW-NI-211119-Newton St Boswells WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2605.69 | -305.69 | 2300 | 0 | 2300 | 0 | [6 empty] | CM_WWNI | 100%
503897 | S-WW-NI-211119-Strathaven WWTW-Replace Burst Sludge Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 10010.21 | -610.21 | 9400 | 0 | 9400 | 0 | [6 empty] | CM_WWNI | 100%
504777 | S-WW-NI-220120-Allers WWTW-Repair Roads | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 10336.18 | -4691.44 | 5644.74 | 0 | 5644.74 | 0 | [6 empty] | CM_WWNI | 100%
504778 | S-WW-NI-220120-Daldowie WWTW-Replacement Gearbox for FST6 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3940.98 | -1803.65 | 2137.33 | 0 | 2137.33 | 0 | [6 empty] | CM_WWNI | 100%
504783 | S-WW-NI-220120-Hawick WWTW-Refurb Blower No3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4767.89 | 0 | 4767.89 | 0 | 4767.89 | 0 | [6 empty] | CM_WWNI | 100%
504775 | S-WW-NI-220120-Lesmahagow WWTW- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 9154.73 | -4112.82 | 5041.91 | 0 | 5041.91 | 0 | [6 empty] | CM_WWNI | 100%
504773 | S-WW-NI-220120-Lesmahagow WWTW-Refurb Storm Screen No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 5813.5 | 0 | 5813.5 | 0 | 5813.5 | 0 | [6 empty] | CM_WWNI | 100%
504811 | S-WW-NI-230120-Castle Kennedy WWTW-Installation of Access Path | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1783.7 | 0 | 1783.7 | 0 | 1783.7 | 0 | [6 empty] | CM_WWNI | 100%
504803 | S-WW-NI-230120-Eaglesfield WWTW-Replacement Geared Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3197.54 | -1498.64 | 1698.9 | 0 | 1698.9 | 0 | [6 empty] | CM_WWNI | 100%
504806 | S-WW-NI-230120-Eastriggs WWPS-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3064.49 | -815.47 | 2249.02 | 0 | 2249.02 | 0 | [6 empty] | CM_WWNI | 100%
504814 | S-WW-NI-230120-Philipshill WWTW-Tank Inspection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1648.1 | -329.71 | 1318.39 | 0 | 1318.39 | 0 | [6 empty] | CM_WWNI | 100%
504801 | S-WW-NI-230120-Troqueer Final WWPS-DO Probes & Controller | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4755.79 | -2180.03 | 2575.76 | 0 | 2575.76 | 0 | [6 empty] | CM_WWNI | 100%
505894 | S-WW-NI-23032020-Airds Point WWTW-Standby Generator Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1699.98 | 1699.98 | 0 | 1699.98 | 0 | [6 empty] | CM_WWNI | 100%
505892 | S-WW-NI-23032020-Troqueer STC-Refurbish Strainpress no2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 421.5 | 1678.5 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
505880 | S-WW-NI-23032020-Troqueer WWTW-investigate the Fire System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1699.98 | 1699.98 | 0 | 1699.98 | 0 | [6 empty] | CM_WWNI | 100%
505876 | S-WW-NI-230320-Gorebridge WWTW-Repair Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 1200 | 100.02 | 1300.02 | 0 | 1300.02 | 0 | [6 empty] | CM_WWNI | 100%
504479 | S-WW-NI-231219-Earlston WWTW-Distribution Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
504473 | S-WW-NI-231219-Hawick WWTW-Supply & fit GRP door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
504475 | S-WW-NI-231219-Jedburgh WWTW-Repair damaged roof to Aeration Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
504468 | S-WW-NI-231219-New Abbey WWTW-Replace Telemetry Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2071.04 | -171.04 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
504471 | S-WW-NI-231219-Newton Stewart WWTW-Install Heating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  |  |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2217.96 | -217.96 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504481 | S-WW-NI-231219-Newton Stewart WWTW-Replacement PumpA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 8210.92 | -510.92 | 7700 | 0 | 7700 | 0 | [6 empty] | CM_WWNI | 100%
504484 | S-WW-NI-231219-Prestonpans WWPS-PLC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-07-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 212815.82 | 32184.19 | 245000.01 | 0 | 245000.01 | 0 | [6 empty] | CM_WWNI | 100%
504467 | S-WW-NI-231219-Troqueer WWTW-Fill Pot Holes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2137.64 | -337.64 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
505889 | S-WW-NI-23-32020-Loganbarns WWPS-Investigate Fire System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
504830 | S-WW-NI-240120-Bathgate WWTW-Replacement Safety Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 1371.32 | -285.59 | 1085.73 | 0 | 1085.73 | 0 | [6 empty] | CM_WWNI | 100%
504832 | S-WW-NI-240120-Broughton WWTW-Washwater Kiosk Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1008.18 | 0 | 1008.18 | 0 | 1008.18 | 0 | [6 empty] | CM_WWNI | 100%
504836 | S-WW-NI-240120-Ormiston WWTW-Replacement Lighting & Heating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 1395.94 | 0 | 1395.94 | 0 | 1395.94 | 0 | [6 empty] | CM_WWNI | 100%
504825 | S-WW-NI-240120-Troqueer WWTW-2No Pressure Control Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2491.72 | -630.47 | 1861.25 | 0 | 1861.25 | 0 | [6 empty] | CM_WWNI | 100%
505385 | S-WW-NI-240220-Blackwood WWTW-Replace Wash Water Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1393.07 | 106.94 | 1500.01 | 0 | 1500.01 | 0 | [6 empty] | CM_WWNI | 100%
505383 | S-WW-NI-240220-Dumfries Loganbarns WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 110.06 | 1289.94 | 1400 | 0 | 1400 | 0 | [6 empty] | CM_WWNI | 100%
505387 | S-WW-NI-240220-Haddington WWTW-Replacement of 2No pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 342.54 | 5757.48 | 6100.02 | 0 | 6100.02 | 0 | [6 empty] | CM_WWNI | 100%
505381 | S-WW-NI-240220-Thornhill WWTW-H&S Mods | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1648.06 | -48.06 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
505900 | S-WW-NI-24032020-Roslin WWTW-Supply and fit panel heater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 1399.98 | 1399.98 | 0 | 1399.98 | 0 | [6 empty] | CM_WWNI | 100%
504491 | S-WW-NI-241219-Rosewell WWTW-Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-04 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | CM_WWNI | 100%
503962 | S-WW-NI-251119-Lauder WWPS-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1464.1 | -264.1 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
505421 | S-WW-NI-260220-Allers WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 129.15 | 2170.86 | 2300.01 | 0 | 2300.01 | 0 | [6 empty] | CM_WWNI | 100%
505429 | S-WW-NI-260220-Douglas WWTW-Replacement Gearbox & bearings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1566.4 | 133.58 | 1699.98 | 0 | 1699.98 | 0 | [6 empty] | CM_WWNI | 100%
505418 | S-WW-NI-260220-Eyemouth WWTW-Replace Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 110.64 | 1689.37 | 1800.01 | 0 | 1800.01 | 0 | [6 empty] | CM_WWNI | 100%
505424 | S-WW-NI-260220-Foreland Place WWPS-Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-07-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 23280.72 | 5303.5 | 28584.22 | 1415.76 | 29999.98 | 0 | [6 empty] | CM_WWNI | 100%
505941 | S-WW-NI-26032020-BURNHEAD WWPS-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
505943 | S-WW-NI-26032020-Dunbar WWTW-Replacement DO Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
505952 | S-WW-NI-26032020-Fauldhouse WWTW-Refurbishment of the inlet screen basket | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 4082.61 | 117.39 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
505945 | S-WW-NI-26032020-Loch Ryan WWTW-Generator Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5121.84 | 178.14 | 5299.98 | 0 | 5299.98 | 0 | [6 empty] | CM_WWNI | 100%
505947 | S-WW-NI-26032020-Philipshill WWTW-For fitting a telemetry signal to the ICC for the fire alarm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 27.66 | 3372.36 | 3400.02 | 0 | 3400.02 | 0 | [6 empty] | CM_WWNI | 100%
505950 | S-WW-NI-26032020-Whitecross WWTW-Replacement of badly rusted gratings hatches and support brackets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 165.96 | 4034.04 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
503993 | S-WW-NI-261119-Kelso WWTW-Refurb Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1257.02 | 0 | 1257.02 | 0 | 1257.02 | 0 | [6 empty] | CM_WWNI | 100%
503975 | S-WW-NI-261119-Kirkconnel WWTW-FE Pumping Station Steelwork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 4990.68 | -290.68 | 4700 | 0 | 4700 | 0 | [6 empty] | CM_WWNI | 100%
504869 | S-WW-NI-270120-Allers WWTW-Replace Brush Assembly | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1783.7 | 0 | 1783.7 | 0 | 1783.7 | 0 | [6 empty] | CM_WWNI | 100%
504859 | S-WW-NI-270120-Dunnswood WWTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 6335.28 | -1449.48 | 4885.8 | 0 | 4885.8 | 0 | [6 empty] | CM_WWNI | 100%
504876 | S-WW-NI-270120-Philipshill WWTW-Replacement Parts for HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1177.01 | 22.99 | 1200 | 0 | 1200 | 0 | [6 empty] | CM_WWNI | 100%
504853 | S-WW-NI-270120-Rosewell WWTW-Refurb Submersible Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 1783.7 | 0 | 1783.7 | 0 | 1783.7 | 0 | [6 empty] | CM_WWNI | 100%
505965 | S-WW-NI-27032020-Galashiels WWTW-Replace Recirculation Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3799.98 | 3799.98 | 0 | 3799.98 | 0 | [6 empty] | CM_WWNI | 100%
505966 | S-WW-NI-27032020-Hawick WWTW-Replacement RAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 9400.02 | 9400.02 | 0 | 9400.02 | 0 | [6 empty] | CM_WWNI | 100%
505964 | S-WW-NI-27032020-Loch Ryan WWTW-Replacement PST2 Scrapers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3799.98 | 3799.98 | 0 | 3799.98 | 0 | [6 empty] | CM_WWNI | 100%
505972 | S-WW-NI-27032020-North Berwick WWTW-Replacememt Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3100.02 | 3100.02 | 0 | 3100.02 | 0 | [6 empty] | CM_WWNI | 100%
505973 | S-WW-NI-27032020-Pond Hall WWPS-Replace UPS Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 3600 | 0 | [6 empty] | CM_WWNI | 100%
505974 | S-WW-NI-27032020-Trinity WWPS-Investigation and refurbishment of the long sea outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 5200.02 | 5200.02 | 0 | 5200.02 | 0 | [6 empty] | CM_WWNI | 100%
505963 | S-WW-NI-27032020-Troqueer WWTW-Folomatic control works on inlet actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3100.02 | 3100.02 | 0 | 3100.02 | 0 | [6 empty] | CM_WWNI | 100%
505967 | S-WW-NI-27032020-Walkerburn WWTW-Pump Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3463.43 | 236.59 | 3700.02 | 0 | 3700.02 | 0 | [6 empty] | CM_WWNI | 100%
504005 | S-WW-NI-271119-Ancrum WWTW-Microstrainer Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3519.92 | -319.92 | 3200 | 0 | 3200 | 0 | [6 empty] | CM_WWNI | 100%
504000 | S-WW-NI-271119-Ashgill WWTW-Remedial Works on Sand Filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 10391.52 | 16408.46 | 26799.98 | 0 | 26799.98 | 0 | [6 empty] | CM_WWNI | 100%
504003 | S-WW-NI-271119-Bathgate WWTW-Install Decant Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 7082.28 | -2781.96 | 4300.32 | 0 | 4300.32 | 0 | [6 empty] | CM_WWNI | 100%
504010 | S-WW-NI-271119-Galashiels STC-Refurb Pump 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 3300 | 0 | 3300 | 0 | [6 empty] | CM_WWNI | 100%
503997 | S-WW-NI-271119-Glassford WWTW-Replace Inlet Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 2794.98 | -942.53 | 1852.45 | 0 | 1852.45 | 0 | [6 empty] | CM_WWNI | 100%
503996 | S-WW-NI-271119-Lesmahagow WWTW-Grit Rake Overhaul | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 14741.35 | -841.35 | 13900 | 0 | 13900 | 0 | [6 empty] | CM_WWNI | 100%
504890 | S-WW-NI-280120-Langholm WWTW-Replacement Access Stairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4435.44 | -35.44 | 4400 | 0 | 4400 | 0 | [6 empty] | CM_WWNI | 100%
504024 | S-WW-NI-281119- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4367.91 | 0 | 4367.91 | 0 | 4367.91 | 0 | [6 empty] | CM_WWNI | 100%
504050 | S-WW-NI-281119-Amisfield WWTW-Provide Sound Booth | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 3833.61 | -1649.65 | 2183.96 | 0 | 2183.96 | 0 | [6 empty] | CM_WWNI | 100%
504028 | S-WW-NI-281119-Annan WWTW - Repalce Slip Ring on FST1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4382.93 | -1762.19 | 2620.74 | 0 | 2620.74 | 0 | [6 empty] | CM_WWNI | 100%
504041 | S-WW-NI-281119-Dunnswood WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 3677.06 | -377.06 | 3300 | 0 | 3300 | 0 | [6 empty] | CM_WWNI | 100%
504021 | S-WW-NI-281119-Galashiels WWTW-Replace Recirc Pump3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 6881.59 | -4697.63 | 2183.96 | 0 | 2183.96 | 0 | [6 empty] | CM_WWNI | 100%
504035 | S-WW-NI-281119-Hamilton WWTW-Survey & Repair Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 8798.22 | 0 | 8798.22 | 0 | 8798.22 | 0 | [6 empty] | CM_WWNI | 100%
504022 | S-WW-NI-281119-Leet Green WWPS-Install VSD on 2pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-28 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4384.96 | -1889.01 | 2495.95 | 0 | 2495.95 | 0 | [6 empty] | CM_WWNI | 100%
504060 | S-WW-NI-281119-Loch Ryan WWTW-Refurb Launder Trough | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 8923.67 | -3869.38 | 5054.29 | 0 | 5054.29 | 0 | [6 empty] | CM_WWNI | 100%
504030 | S-WW-NI-281119-Moffat WWTW-Replacement FST Wheel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 3227.94 | -1418.38 | 1809.56 | 0 | 1809.56 | 0 | [6 empty] | CM_WWNI | 100%
504031 | S-WW-NI-281119-Newton St Boswells WWTW-Refurb Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 6901.97 | -801.97 | 6100 | 0 | 6100 | 0 | [6 empty] | CM_WWNI | 100%
504044 | S-WW-NI-281119-Port Rodie WWPS- Replacement of UPS batteries & panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 2508.54 | -1198.17 | 1310.37 | 0 | 1310.37 | 0 | [6 empty] | CM_WWNI | 100%
504048 | S-WW-NI-281119-Troqueer WWTW-Replace Sludge Tank Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 7023.14 | -2967.22 | 4055.92 | 0 | 4055.92 | 0 | [6 empty] | CM_WWNI | 100%
504902 | S-WW-NI-290120-Bathgate WWTW-Various H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 29700 | 0 | 29700 | 0 | 29700 | 0 | [6 empty] | CM_WWNI | 100%
504920 | S-WW-NI-290120-Coldstream WWTW-Gantry for lifting Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 5300 | 0 | 5300 | 0 | 5300 | 0 | [6 empty] | CM_WWNI | 100%
504917 | S-WW-NI-290120-Coldstream WWTW-Refurb Sludge Tank Stairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 9800 | 0 | 9800 | 0 | 9800 | 0 | [6 empty] | CM_WWNI | 100%
504914 | S-WW-NI-290120-Cove WWTW-H&S around final sample chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 8900 | 0 | 8900 | 0 | 8900 | 0 | [6 empty] | CM_WWNI | 100%
504898 | S-WW-NI-290120-Daldowie WWTW-Replacement Screen Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 5100 | 0 | 5100 | 0 | [6 empty] | CM_WWNI | 100%
504922 | S-WW-NI-290120-Doonside Towers WWPS-Repalcement Duckfoot | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504915 | S-WW-NI-290120-Galashiels STC-Repalcement Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 5872.02 | -72.02 | 5800 | 0 | 5800 | 0 | [6 empty] | CM_WWNI | 100%
504905 | S-WW-NI-290120-Loch Ryan WWTW-Refurb Launder Trough | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 8983.41 | -383.41 | 8600 | 0 | 8600 | 0 | [6 empty] | CM_WWNI | 100%
504908 | S-WW-NI-290120-Newbridge WWPS-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 5055.17 | -155.17 | 4900 | 0 | 4900 | 0 | [6 empty] | CM_WWNI | 100%
504924 | S-WW-NI-290120-Ormiston WWTW-Supply & Fit Air Vents | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 3438.21 | 61.8 | 3500.01 | 0 | 3500.01 | 0 | [6 empty] | CM_WWNI | 100%
504901 | S-WW-NI-290120-Philipshill WWTW-Replace Site Drainage | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 11200 | 0 | 11200 | 0 | [6 empty] | CM_WWNI | 100%
504911 | S-WW-NI-290120-Troqueer STC-Installation of Perpex & Heaters at Poly Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 6074.24 | -474.24 | 5600 | 0 | 5600 | 0 | [6 empty] | CM_WWNI | 100%
504082 | S-WW-NI-291119-Ormiston WWTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2020-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 3350.11 | 0 | 3350.11 | 0 | 3350.11 | 0 | [6 empty] | CM_WWNI | 100%
504933 | S-WW-NI-300120-Lauder WWTW-Removal of Aerator for investigation and repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 4759.59 | -59.59 | 4700 | 0 | 4700 | 0 | [6 empty] | CM_WWNI | 100%
504941 | S-WW-NI-300120-Strathaven WWTW-Replace the DB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4836.25 | 63.76 | 4900.01 | 0 | 4900.01 | 0 | [6 empty] | CM_WWNI | 100%
504936 | S-WW-NI-300130-Fillyside WWPS-Crane Issue - Investigation and Repair hoist | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  |  |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 11800 | 0 | 11800 | 0 | 11800 | 0 | [6 empty] | CM_WWNI | 100%
505979 | S-WW-NI-30032020-Haddington WWTW-Replacement tank bridge motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2800.02 | 2800.02 | 0 | 2800.02 | 0 | [6 empty] | CM_WWNI | 100%
505986 | S-WW-NI-30032020-Haddington WWTW-To get existing aerator removed and evaluated | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 6799.98 | 6799.98 | 0 | 6799.98 | 0 | [6 empty] | CM_WWNI | 100%
505988 | S-WW-NI-30032020-Harvesters WWPS-supply and installation of new pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 6199.98 | 6199.98 | 0 | 6199.98 | 0 | [6 empty] | CM_WWNI | 100%
506012 | S-WW-NI-31032020-Kirkconnel WWTW-Replacment of path and steps to sample point on site | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 2700 | 0 | 2700 | 0 | [6 empty] | CM_WWNI | 100%
505036 | S-WW-NI-Eastriggs WWTW-Mechanical Seal on Sludge Feed Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 1631.74 | -31.74 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
504219 | S-WW-NI-Kirkubright Harbour WWPS-Screen Adjustments & Weir Plate | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-11 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WWI | 100%
504584 | S-WW-NI-North Kirkliston WWPS-Replace 2No Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-05-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 6495.2 | 700.67 | 7195.87 | 0 | 7195.87 | 0 | [6 empty] | CM_WWNI | 100%
503958 | S-WW-NI-SWINSTON WWTW-Gearbox for Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1899.17 | -199.17 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
45540 | Symington A STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2011-02-07 | 2011-07-04 | 2012-03-16 | 2012-03-22 | South Lanarkshire | 1003868.54 | 311.36 | 0 | 0 | 0 | 0 | 0 | 311.36 | 0 | 1004179.9 | 0 | [6 empty] | CM_WWI | 2.471% | CS11A | 6.355% | WQ01 | 91.17%
45541 | Symington B STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2011-02-07 | 2011-10-24 | 2012-06-24 | 2012-06-28 | South Lanarkshire | 1066244.65 | 812.77 | 0 | 0 | 0 | 0 | 0 | 812.77 | 0 | 1067057.42 | 0 | [6 empty] | WQ01 | 100%
501154 | Syskeside SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2016-02-17 | 2018-11-05 | 2019-02-04 | 2020-02-18 | 2020-03-02 | North Lanarkshire | 0 | 909.35 | 70857.33 | 34689.32 | 544359.36 | 377835.66 | 11048.98 | 1039700 | 2500 | 1042200 | 0 |  |  |  |  | 1327.59 |  | CM_WWNI | 100%
502182 | T&I - Telemetry Service Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-06-29 | 2016-10-28 | 2016-10-28 | 2021-03-15 | 2021-04-09 | Scottish Water Wide | 0 | 0 | 389447.89 | 561273.96 | 127091.1 | 125945.22 | 33303.97 | 1237062.14 | 0 | 1237062.14 | 0 |  |  |  |  | 25000 |  | CM_M&G | 100%
501645 | T&I Portfolio Risk | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW2 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-03-12 | 2021-03-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 966542.46 | 966542.46 | 0 | 966542.46 | 0 | [6 empty] | CM_M&G | 100%
501253 | Tain additional FST (Growth funded) plus various CM ( inlet screen PFT if required MCC refurbishm | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-03-02 | 2018-09-28 | 2018-10-30 | 2020-04-13 | 2020-07-08 | Highland | 0 | 5728.8 | 215606.6 | 136996.21 | 646956.48 | 1666254.82 | 36452.82 | 2707995.73 | 67666.26 | 2775661.99 | 136478.56 |  |  |  |  | 2940 |  | CM_WWNI | 35% | SG1 | 65%
501420 | Talla Aqueduct - 2019 Walk through Inspection | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2028-01-28 | 2029-01-08 | 2029-03-22 | 2030-04-23 | 2030-07-16 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000.01 | 4500000.01 | 0 | [6 empty] | CM_WSI | 100%
501617 | Talla Aqueduct - Broughton Siphons | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-23 | 2028-05-30 | 2028-08-16 | 2029-09-17 | 2029-12-14 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4971751 | 4971751 | 0 | [6 empty] | CM_WSI | 100%
504961 | Talla Aqueduct - Full Inspection ASV2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-03-02 | 2020-06-08 | 2020-10-07 | 2021-04-13 | 2021-07-14 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 27987.45 | 571236.67 | 599224.12 | 775.88 | 600000 | 0 | [6 empty] | CM_WSI | 100%
503366 | Talla Aqueduct - Inspection Planning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-09-28 | 2018-09-28 | 2019-09-16 | 2020-06-23 | 2020-09-23 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 28976.48 | 193072.36 | 27951.15 | 249999.99 | 0 | 249999.99 | 0 | [6 empty] | CM_WSI | 100%
45651 | Talla Aqueduct Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-08-30 | 2012-09-17 | 2015-07-30 |  | Scottish Borders | 7179571 | 121113 | 199945.35 | -5520.81 | 0 | -0.01 | -145.56 | 315391.97 | 0 | 7494962.97 | 0 | [6 empty] | CM_WSNI | 100%
401972 | Talla Reservoir Safe Operation of Scour Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-04-01 | 2014-03-31 | 2014-04-21 | 2015-01-12 | 2015-01-12 | Scottish Borders | 641437 | -7222 | -249.73 | 0 | 0 | 0 | 0 | -7471.73 | 0 | 633965.27 | 0 | [6 empty] | CM_WSI | 100%
45280 | Tanker Fill Point Balmore WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-06-14 | 2011-03-30 | 2011-06-23 | East Dunbartonshire | 547741.6 | 1.3 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 547742.9 | 0 | [6 empty] | DW8 | 100%
45282 | Tanker Fill Point Blairlinnans WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2012-01-16 | 2012-02-23 | 2012-03-14 | West Dunbartonshire | 263100.22 | 108.68 | 0 | 0 | 0 | 0 | 0 | 108.68 | 0 | 263208.9 | 0 | [6 empty] | DW8 | 100%
45284 | Tanker Fill Point Carron Valley WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-10-11 | 2011-01-28 | 2011-06-23 | Falkirk | 190609.51 | -22.51 | 0 | 0 | 0 | 0 | 0 | -22.51 | 0 | 190587 | 0 | [6 empty] | DW8 | 100%
45285 | Tanker Fill Point Fairmilehead WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-09-24 | 2010-11-08 | 2011-05-24 | 2012-03-30 | City of Edinburgh | 339120.29 | 498.71 | 0 | -22.02 | 0 | 0 | 0 | 476.69 | 0 | 339596.98 | 0 | [6 empty] | DW8 | 100%
45286 | Tanker Fill Point Finmont WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-02 | 2011-07-29 | 2011-10-05 | Fife | 436124.05 | 6019.55 | -6019.58 | 0 | 0 | 0 | 0 | -0.03 | 0 | 436124.02 | 0 | [6 empty] | DW8 | 100%
45287 | Tanker Fill Point Forehill WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-09 | 2011-03-29 | 2011-06-23 | Aberdeenshire | 351447.31 | 242.99 | 0 | 0 | 0 | 0 | 0 | 242.99 | 0 | 351690.3 | 0 | [6 empty] | DW8 | 100%
45288 | Tanker Fill Point Mannofield WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-23 | 2012-02-23 | 2012-03-14 | Aberdeen City | 483724.01 | 286 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 484010.01 | 0 | [6 empty] | DW8 | 100%
45289 | Tanker Fill Point Overton Greenock WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2011-01-17 | 2012-02-19 | 2012-03-14 | Inverclyde | 471461.33 | 6.89 | 0 | 0 | 0 | 0 | 0 | 6.89 | 0 | 471468.22 | 0 | [6 empty] | DW8 | 100%
45291 | Tanker Fill Point Perth WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-02 | 2011-03-03 | 2011-06-23 | Perth and Kinross | 367773.39 | 214.72 | 0 | 0 | 0 | 0 | 0 | 214.72 | 0 | 367988.11 | 0 | [6 empty] | DW8 | 100%
45292 | Tanker Fill Point Whitehillocks WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-11-08 | 2011-03-02 | 2011-06-23 | Angus | 272223.68 | 158.16 | 0 | 0 | 0 | 0 | 0 | 158.16 | 0 | 272381.84 | 0 | [6 empty] | DW8 | 100%
502872 | Tarbert (WI) WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2027-04-02 | 2033-10-13 | 2034-02-03 | 2035-01-26 | 2035-04-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 21238 | 1489.88 | 9066.04 | 18206.09 | 50000.01 | 7950000.19 | 8000000.2 | 136478.56 | [6 empty] | WG1 | 100%
500184 | Tarbert DOA (DOA002408) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-11 | 2017-02-28 | 2017-05-31 | Argyll and Bute-Cowal & Bute | 0 | 42286 | 40471 | 15399.18 | 41.28 | 0 | -0.28 | 98197.18 | 0 | 98197.18 | 72047.27 | [6 empty] | CS16D | 40.17% | CS11 | 59.83% | bar: Regulatory Outputs OMG-22
500880 | Tarbert Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2019-03-27 | 2019-09-30 | Na H-Eileanan an Iar | 0 | 1581.68 | 3568.21 | 6367 | 73562.87 | 17237.92 | -1333.1 | 100984.58 | 0 | 100984.58 | 0 | [6 empty] | DW5FS | 100%
502835 | Tarbert WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-07-18 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 | Na H-Eileanan an Iar | 0 | 0 | 0 | 57254.81 | 23277.41 | 0 | 0 | 80532.22 | 0 | 80532.22 | 0 | [6 empty] | CM_WSNI | 100%
504203 | Tarbert WTW - CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-07-26 | 2022-12-26 | 2023-04-27 | 2023-12-21 | 2024-03-22 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 176556.28 | 64776.65 | 241332.93 | 3258667.14 | 3500000.07 | 0 | [6 empty] | CM_WSNI | 100%
500686 | Tarbolton Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-06-11 | 2016-05-18 | 2016-06-13 | 2016-09-30 | 2016-09-30 | South Ayrshire | 0 | 66557 | 738874 | 26386.76 | 20214.18 | 11722.64 | 0 | 863754.58 | 0 | 863754.58 | 0 | [6 empty] | CM_WWI | 100%
501270 | Tarbolton SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-07-19 | 2017-11-07 | 2018-03-26 | 2018-10-30 | 2018-10-30 | South Ayrshire | 0 | 0 | 30180 | 318820 | 424542.92 | 9733.29 | -0.2 | 783276.01 | 0 | 783276.01 | 0 | [6 empty] | CM_WWNI | 100%
500881 | Tarskavaig Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-20 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 490.79 | 1083.55 | 0 | 0 | 0 | 0 | 1574.34 | 0 | 1574.34 | 10180.72 | [6 empty] | DW5FS | 100%
46847 | Tarskavaig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-01 | 2011-03-14 | 2014-12-01 | 2015-03-27 | Na H-Eileanan an Iar | 1053408.29 | 44948.52 | -10506.85 | 24820.97 | -11082.13 | 0 | 22708.09 | 70888.6 | 0 | 1124296.89 | 3002 | [6 empty] | DW23 | 100%
502827 | Tarves WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2020-01-23 | 2021-08-09 | 2021-11-29 | 2022-11-17 | 2023-02-17 | Aberdeenshire | 0 | 0 | 0 | 64604.45 | 17150.63 | 5266.13 | 246857.69 | 333878.9 | 485222.5 | 819101.4 | 136478.56 | [6 empty] | SG1 | 100%
400279 | Tay Cluster 2 Capital Maintenance Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-30 | 2012-07-31 | 2012-09-03 | 2013-08-02 |  | Perth and Kinross | 886307 | 2696.48 | 0 | 0 | 0 | 0 | 0 | 2696.48 | 0 | 889003.48 | 0 | [6 empty] | CM_WSI | 100%
401222 | Tay Cluster 2 Lintrathen (5 WSZs) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-12-11 | 2013-01-30 | 2014-05-09 |  | Perth and Kinross | 1175950 | 25185 | -5181.03 | 0 | 0 | 0 | 0 | 20003.97 | 0 | 1195953.97 | 0 | [6 empty] | CM_WSI | 100%
500108 | Tay Coastal Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2019-04-04 | 2020-01-08 | Scottish Water Wide | 0 | 21309 | 41063.07 | 29834.93 | 60313 | 7009.51 | 0.01 | 159529.52 | 0 | 159529.52 | 217279.54 | [6 empty] | EC01G | 0.5128% | EC10E | 49.74% | EC10H | 49.74%
501048 | Tay Large Middle Ground Scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-10-09 | 2018-06-26 | 2018-08-06 | 2020-10-15 | 2020-10-15 | Fife | 0 | 30750 | 55000 | 30950.11 | 478929.88 | 75536.7 | 53300.26 | 724466.95 | 3614.08 | 728081.03 | 0 | [6 empty] | CM_WSI | 100%
401491 | Tay Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-08 | 2012-03-15 | 2012-03-15 | 2015-07-31 |  | All East Unitary Authorities | 1188388 | 73871 | 0 | -1383.22 | 0 | 0 | 0 | 72487.78 | 0 | 1260875.78 | 0 | [6 empty] | CM_WSI | 100%
501105 | Tay PFI Hatton Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-12-19 | 2017-01-20 | 2018-06-30 | 2018-12-31 | Dundee City | 0 | 608 | 14339.25 | 22299.75 | 13647.85 | 25 | -25 | 50894.85 | 0 | 50894.85 | 74466.1 | [6 empty] | EC01G | 3.809% | EC10E | 96.19% | bar: Regulatory Outputs OMG-23
501831 | Tay PFI Hatton PFI Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW2 | 2020-06-22 | 2020-12-14 | 2021-01-22 | 2021-03-04 | 2021-04-01 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 28030.85 | 28030.85 | 1148.18 | 29179.03 | 0 | [6 empty] | SR21_WW | 100%
403899 | TCM - Non Infra Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-30 | 2014-10-08 | 2014-10-08 | 2017-01-26 | 2017-01-26 | Scottish Water Wide | 1813801 | 374097 | 40578.37 | 1123.2 | 0 | 0 | -1123.2 | 414675.37 | 0 | 2228476.37 | 0 | [6 empty] | CM_M&G | 100%
402679 | Teangue WTW - Raw Water Main Upsize | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-21 | 2012-09-21 | 2012-10-22 | 2013-09-23 |  | Highland | 650602 | 29593 | 3425.08 | -44789.92 | -644.4 | 0 | 0 | -12416.24 | 0 | 638185.76 | 0 | [6 empty] | CM_WSI | 100%
402952 | Teangue WTW - Standby Filtomat Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-09 | 2014-06-20 | 2014-06-23 | 2015-07-17 |  | Highland | 1280423 | 229577 | 0 | 160.05 | 0 | 0 | 0 | 229737.05 | 0 | 1510160.05 | 0 | [6 empty] | CM_WSNI | 100%
503365 | Teangue WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2021-05-13 | 2022-11-04 | 2023-03-03 | 2024-02-28 | 2024-05-30 | Highland | 0 | 0 | 0 | 0 | 20233.02 | -13949.42 | -1270.97 | 5012.63 | 0 | 5012.63 | 136478.56 | [6 empty] | WG1 | 100%
400486 | Teangue WTW Supply Zone Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS5 | 2001-02-25 | 2005-01-21 | 2005-02-21 | 2018-10-08 | 2018-10-08 | Highland | 1195.74 | 75.23 | 0 | 0 | 0 | -1270.97 | 0 | -1195.74 | 0 | 0 | 0 | [6 empty] | WG1 | 100%
404108 | Technology for Water and Waste Water Operatives | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-04 | 2016-03-03 | 2016-03-03 | 2016-03-03 | 2016-03-03 | Scottish Water Wide | 50000 | 1219.51 | 0 | 0 | 0 | 0 | 0 | 1219.51 | 0 | 51219.51 | 0 | [6 empty] | CM_M&G | 100%
500624 | Technology Information & Business Change SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 5728557.08 | 5006873.51 | 10092169.84 | 10310257.53 | 13530071.84 | 7123093.13 | 51791022.93 | 1159573.28 | 52950596.21 | 0 | [6 empty] | CM_OVH | 100%
502288 | TEL - Private Wire comms. replacement phase1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2016-09-15 | 2016-12-20 | 2017-01-16 | 2018-01-18 | 2018-01-18 | Scottish Water Wide | 0 | 0 | 21380.91 | 16985.92 | 905.95 | 138.5 | -138.5 | 39272.78 | 0 | 39272.78 | 0 | [6 empty] | CM_WSNI | 17.17% | CM_WWNI | 82.83%
502234 | TEL - SR15 Telemetry RTU Replacement - Phase 6 Datacall | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2018-05-31 | 2018-07-30 | 2021-07-08 | 2021-07-08 | Scottish Water Wide | 0 | 0 | 38317.97 | 75109.82 | 172048.43 | 427353.65 | 891107.31 | 1603937.18 | 66317.56 | 1670254.74 | 0 | [6 empty] | CM_WWNI | 41.29% | CM_WSNI | 58.71%
502237 | TEL - SR15 Telemetry RTU Upgrading - Phase 3 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS4 | 2016-08-18 | 2017-03-23 | 2017-05-15 | 2020-01-13 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 30207.82 | 179639.03 | 30883.71 | 13884.25 | 337.93 | 254952.74 | 0 | 254952.74 | 0 | [6 empty] | CM_WWNI | 31.93% | CM_WSNI | 68.07%
502238 | TEL - SR15 Telemetry RTU Upgrading - Phase 4 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-30 | 2017-06-26 | 2021-01-05 | 2021-01-05 | Scottish Water Wide | 0 | 0 | 33520.74 | 118436.78 | 142538.21 | 50236.09 | 32808.44 | 377540.26 | 801.95 | 378342.21 | 0 | [6 empty] | CM_WWNI | 29.7% | CM_WSNI | 70.3%
502239 | TEL - SR15 Telemetry RTU Upgrading - Phase 5 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-28 | 2017-06-05 | 2021-01-05 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 26143.22 | 136793.19 | 108175.33 | 112820.33 | 12549.59 | 396481.66 | 655.32 | 397136.98 | 0 | [6 empty] | CM_WWNI | 13.3% | CM_WSNI | 86.7%
35821 | Telemetry - Data Quality End to End Testing Ph 2 Ness Area | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2007-05-09 | 2007-06-26 | 2007-07-16 | 2015-12-21 | 2015-10-13 | Scottish Water Wide | 4687190 | -200.12 | 0 | 0 | 0 | 0 | 0 | -200.12 | 0 | 4686989.88 | 0 | [6 empty] | DW14 | 100%
404017 | Telemetry - Exo RDI and Ellipse Synch improvement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-01-06 | 2015-01-06 | 2015-01-06 | 2017-11-08 |  | Scottish Water Wide | 15000 | 10000 | -3024.24 | 0 | 0 | 0 | 0 | 6975.76 | 0 | 21975.76 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
401200 | Telemetry - First Time provision of Telemetry at 25 WWTWs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2012-12-10 | 2013-01-22 | 2014-12-01 |  | Scottish Water Wide | 250819.49 | 98.85 | 0 | 0 | 0 | 0 | 0 | 98.85 | 0 | 250918.34 | 0 | [6 empty] | CM_WSNI | 100%
401199 | Telemetry - First Time provision of Telemetry at SPSs Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2011-03-01 | 2011-04-25 | 2015-11-20 |  | Scottish Water Wide | 1149804 | 12077.72 | 120 | 0 | 0 | 0 | 0 | 12197.72 | 0 | 1162001.72 | 0 | [6 empty] | CM_WSNI | 100%
401201 | Telemetry - SPS Data Quality Phase 1 Testing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2011-02-28 | 2011-04-01 | 2016-02-25 |  | Scottish Water Wide | 658829.62 | 1493.55 | 0 | 0 | 0 | 0 | 0 | 1493.55 | 0 | 660323.17 | 0 | [6 empty] | CM_WSNI | 100%
500490 | Telemetry - SR Data Quality Phase1 (SR15) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-25 | 2021-02-02 | 2021-02-02 | Scottish Water Wide | 0 | 309469 | 220032.46 | 229508.85 | 203791.53 | 95638.98 | 150818.19 | 1209259.01 | 106058.81 | 1315317.82 | 0 | [6 empty] | CM_WSNI | 100%
402695 | Telemetry - TSAT - Replacement of Unsupported equipment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2012-06-22 | 2013-01-30 | 2013-02-18 | 2015-02-19 |  | Scottish Water Wide | 698495 | 15431.84 | 218.96 | 0 | 0 | 0 | 0 | 15650.8 | 0 | 714145.8 | 0 | [6 empty] | CM_WSNI | 18.17% | CM_WWNI | 81.83%
500736 | Telemetry - Water DMA logger Alarming Phase1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2018-07-12 | 2018-07-12 | Scottish Water Wide | 0 | 29174 | 38482 | 68418 | 6953.36 | 0 | 0 | 143027.36 | 0 | 143027.36 | 0 | [6 empty] | CM_WWNI | 100%
500944 | Telemetry - Water Time of Travel Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-09-07 | 2015-09-07 | 2015-11-02 | 2016-10-20 | 2016-10-20 | Scottish Water Wide | 0 | 5290 | 21658.54 | 0 | 0 | 0 | 0 | 26948.54 | 0 | 26948.54 | 0 | [6 empty] | CM_WWNI | 100%
501639 | Telemetry Application Consolidation | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | General |  | SWD | Meter Accuracy | MS3 | 2016-02-15 | 2016-08-29 | 2016-08-29 | 2020-07-06 |  | Scottish Water Wide | 0 | 173356 | 855060.64 | 487281.96 | 788910.87 | 1200598.53 | 36894 | 3542102 | 0 | 3542102 | 4004712.5 |  |  |  |  | 73550 |  | CS4 | 20.25% | CM_M&G | 79.75%
403947 | Telemetry Communication - Clatto (Fife) Scanner Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-29 | 2015-05-05 | 2015-05-05 | 2015-09-14 |  | Fife | 96952 | 170635.88 | 0 | 0 | 0 | 0 | 0 | 170635.88 | 0 | 267587.88 | 0 | [6 empty] | CM_M&G | 100%
502721 | Telemetry ICC Water Initiatives | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-05-12 | 2017-05-12 | 2017-06-15 | 2020-09-29 | 2020-09-29 | Scottish Water Wide | 0 | 0 | 0 | 91469.43 | 115461.23 | 85216.34 | 7853 | 300000 | 0 | 300000 | 0 | [6 empty] | CM_WSNI | 100%
402582 | Telemetry Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-03-15 | 2017-01-23 | 2017-01-23 | 2016-07-01 |  | Scottish Water Wide | 1533818 | 612688 | 53108.1 | 0 | 0 | 0 | 0 | 665796.1 | 0 | 2199614.1 | 0 | [6 empty] | CM_M&G | 100%
403603 | Telemetry Logger Alarming | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2016-08-15 |  | Scottish Water Wide | 90870 | 1650.61 | 79.88 | 0 | 0 | 0 | 0 | 1730.49 | 0 | 92600.49 | 0 | [6 empty] | CM_WWNI | 100%
400341 | Telemetry Low Voltage Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2008-11-25 | 2009-07-28 | 2010-07-29 | 2015-02-19 |  | Scottish Water Wide | 8206 | -149.84 | 0 | 0 | 0 | 0 | 0 | -149.84 | 0 | 8056.16 | 0 | [6 empty] | CM_WWNI | 100%
501679 | Telemetry Networks Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-28 | 2017-03-22 | 2017-03-22 | 2018-03-28 | 2018-03-28 | Scottish Water Wide | 0 | 0 | 1014968.9 | 92217.05 | -33.21 | 0 | 0 | 1107152.74 | 0 | 1107152.74 | 0 | [6 empty] | CM_M&G | 100%
403593 | Telemetry Scanning Radio - Risk Mitigation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-03 | 2014-06-17 | 2014-06-17 | 2015-07-24 |  | Fife | 358938.66 | 117815.56 | 0 | 0 | 0 | 0 | 0 | 117815.56 | 0 | 476754.22 | 0 | [6 empty] | CM_M&G | 100%
402690 | Telemetry WWTW Critical Data Quality | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-13 | 2013-02-20 | 2013-03-04 | 2017-04-25 |  | Scottish Water Wide | 299353 | 151221 | 35770.21 | -6265.13 | 0 | 0 | 0 | 180726.08 | 0 | 480079.08 | 0 | [6 empty] | CM_WSNI | 100%
402689 | Telemetry WWTW Data Quality | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-21 | 2013-02-20 | 2013-03-06 | 2017-03-28 |  | Scottish Water Wide | 2574126 | 328317 | -2790.63 | 100.56 | 0 | 0 | 0 | 325626.93 | 0 | 2899752.93 | 0 | [6 empty] | CM_WSNI | 100%
502774 | Temporary Phosphorus Treatment at Peebles WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2017-08-01 | 2017-08-01 | 2017-12-05 | 2017-12-31 | 2018-01-31 | Scottish Borders | 0 | 0 | 0 | 15151.06 | -15151.06 | 0 | 1 | 1 | 0 | 1 | 11105602.59 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403033 | Terregles BH Water Supply Augmentation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-04 | 2014-07-31 | 2014-07-31 | 2015-09-21 |  | Dumfries and Galloway | 1140346 | 320930 | 2799.26 | 7058.45 | 0 | 0 | 0 | 330787.71 | 0 | 1471133.71 | 0 | [6 empty] | CM_WSNI | 100%
500477 | Terregles WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-07-21 | 2018-11-27 | 2019-06-26 | 2019-09-30 | 2019-09-30 | Dumfries and Galloway | 0 | 13294.54 | 33699.51 | 23994.85 | 12209.83 | 738.25 | 2690.03 | 86627.01 | 0 | 86627.01 | 463259.66 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
45572 | Terregles WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-01-13 | 2011-09-22 | 2011-05-03 | 2011-12-01 | 2011-03-14 | Dumfries and Galloway | 73079.17 | 314.53 | 0 | 0 | 0 | 0 | 0 | 314.53 | 0 | 73393.7 | 0 | [6 empty] | DW1A | 100%
501299 | Test Service Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-04-25 | 2017-04-25 | 2018-04-18 | 2018-04-18 | Scottish Water Wide | 0 | 93569 | 169065.48 | 45688.39 | 0 | 0 | 0 | 308322.87 | 0 | 308322.87 | 0 | [6 empty] | CM_M&G | 100%
501685 | Thankerton Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2016-07-19 | 2021-04-30 | 2021-07-20 | 2021-11-25 | 2022-07-22 | South Lanarkshire | 0 | 0 | 5700 | 2000 | 0 | 3032 | 0 | 10732 | 58768 | 69500 | 0 | [6 empty] | CM_WWI | 100%
402961 | The Grove Ewanfield Crieff | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2014-12-15 | 2015-09-01 | 2016-01-11 | 2016-01-11 | Perth and Kinross | 235559 | 395012 | -3542.22 | 1016.72 | 0 | 0 | 0 | 392486.5 | 0 | 628045.5 | 204193.13 | [6 empty] | CS11A | 100%
403273 | The Ness - Dollar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-02-01 | 2014-12-05 | 2015-04-13 | 2015-09-29 | 2015-10-01 | Clackmannanshire | 578381 | 685403 | 0.42 | -39152.78 | 0 | 0 | 0 | 646250.64 | 0 | 1224631.64 | 204193.13 | [6 empty] | CS11 | 100%
403001 | Theatre Lane at Regent Quay Aberdeen - Odour-Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2012-10-04 | 2017-05-08 | 2017-06-30 | 2018-01-17 | 2018-01-17 | Aberdeen City | 1000 | 14585.88 | 16263.12 | 56627 | 3903.93 | -2251.1 | 0.17 | 89129 | 0 | 90129 | 0 | [6 empty] | CM_WWI | 100%
502767 | THM Study 1 - West | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS4 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All West Unitary Authorities | 0 | 0 | 0 | 21508.78 | 23672.39 | 157866.86 | 89451.98 | 292500.01 | 0 | 292500.01 | 337621.75 | [6 empty] | DW25PS | 100%
502768 | THM Study 2 - North A | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS4 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All North Unitary Authorities | 0 | 0 | 0 | 33370.8 | 28521.24 | 236988.8 | 139669.17 | 438550.01 | 0 | 438550.01 | 337621.75 | [6 empty] | DW25PS | 100%
502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS4 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All South Unitary Authorities | 0 | 0 | 0 | 31187.42 | 61469.41 | 219698.11 | 126645.06 | 439000 | 0 | 439000 | 506432.62 | [6 empty] | DW25PS | 100%
502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS4 | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-02-26 | 2020-06-29 | All East Unitary Authorities | 0 | 0 | 0 | 30984.25 | 39677.79 | 213850.61 | 153837.35 | 438350 | 0 | 438350 | 673842.56 | [6 empty] | DW25PS | 100%
502771 | THM Study 5 - North B | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS7 | 2017-06-21 | 2019-04-18 | 2019-04-18 | 2020-04-01 | 2020-04-01 | All North Unitary Authorities | 0 | 0 | 0 | 3662.62 | -39.85 | 0 | 0 | 3622.77 | 0 | 3622.77 | 168810.87 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503302 | Thorn Drive Bearsden Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-29 | 2021-08-04 | 2021-10-21 | 2022-03-08 | 2022-06-08 | East Dunbartonshire | 0 | 0 | 0 | 0 | 51000 | 41413.02 | 31186.98 | 123600 | 176399.94 | 299999.94 | 196097.17 | [6 empty] | CS11A | 100%
503386 | Thornhill WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-16 | 2028-02-23 | 2028-06-27 | 2028-12-18 | 2029-03-20 | Stirling | 0 | 0 | 0 | 0 | 80052.86 | 3286.1 | 0 | 83338.96 | 58661.04 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
46412 | Thornliebank TWP Refurb - TWP000223 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-20 | 2011-12-29 | 2011-12-19 |  | Glasgow City | 46611.64 | 1343.85 | 0 | 0 | 0 | 0 | 0 | 1343.85 | 0 | 47955.49 | 0 | [6 empty] | CM_WSNI | 100%
500434 | Thornton Main SPS Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2015-06-11 | 2017-02-17 | 2017-03-27 | 2017-08-28 | 2017-08-28 | Fife | 0 | 9631 | -379.02 | 33108.93 | 0.01 | 0 | 0 | 42360.92 | 0 | 42360.92 | 0 | [6 empty] | CM_WWI | 100%
45808 | Thorntonhall SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-02-24 | 2011-04-11 | 2014-03-31 | 2014-03-31 | South Lanarkshire | 1668302.47 | 5850.63 | -7830.11 | 0 | 0 | 0 | 0 | -1979.48 | 0 | 1666322.99 | 7917.3 | [6 empty] | CM_WWNI | 10% | WQ01C | 90%
500185 | Thurso DOA (DOA001050) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-02 | 2016-01-11 | 2017-05-31 | 2017-07-31 | Highland | 0 | 55719 | 164000.19 | 18344.09 | 0 | 0 | 0 | 238063.28 | 0 | 238063.28 | 72047.27 | [6 empty] | CS11 | 47.31% | CS16D | 52.69% | bar: Regulatory Outputs OMG-22
502284 | TI&BC - Browser Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-13 | 2017-02-24 | 2017-02-24 | 2017-07-03 |  | Scottish Water Wide | 0 | 0 | 449768.03 | 74721.03 | 0 | 0 | 0 | 524489.06 | 0 | 524489.06 | 0 | [6 empty] | CM_M&G | 100%
502124 | TI&BC - Technology for Water & Waste Water Operatives | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS4 | 2016-03-25 | 2017-04-04 | 2017-04-04 | 2020-01-20 |  | Scottish Water Wide | 0 | 36200.61 | 699080.87 | 675812 | 555790.83 | 28729.71 | 0 | 1995614.02 | 0 | 1995614.02 | 0 | [6 empty] | CM_M&G | 100%
502219 | TI&BC Dual Communications for Telemetry | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-04-29 | 2017-03-30 | 2017-03-30 | 2017-03-03 | 2017-03-03 | Scottish Water Wide | 0 | 0 | 91554.02 | 0 | 0 | 0 | 0 | 91554.02 | 0 | 91554.02 | 0 | [6 empty] | CM_M&G | 100%
501308 | TI&BC SR15 Portfolio Delivery Resources | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2020-10-08 | 2016-02-17 | Scottish Water Wide | 0 | 341940 | 956278.05 | 785286.34 | 307441.51 | 77722.64 | 17725.22 | 2486393.76 | 0 | 2486393.76 | 0 | [6 empty] | CM_M&G | 100%
502351 | TIBC SAN @ Stepps Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2017-02-02 | 2016-12-12 | Scottish Water Wide | 0 | 0 | 457663.94 | 0 | 0 | 0 | 0 | 457663.94 | 0 | 457663.94 | 0 | [6 empty] | CM_M&G | 100%
501540 | Tighnabruaich SR Refurb | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2027-11-11 | 2028-03-16 | 2028-07-26 | 2028-10-26 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 3076.43 | 3076.43 | 123000.58 | 126077.01 | 0 | [6 empty] | CM_WSNI | 100%
502432 | Tighnabruaich WTW - Ardlamont SR and SDN | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-03-21 | 2019-08-28 | 2019-08-28 | 2019-05-28 | 2019-05-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 166.63 | 340.64 | -117.91 | -48.72 | 340.64 | 0 | 340.64 | 0 | [6 empty] | DW25T | 100%
502310 | Tighnabruaich WTW - Portavadie DSR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2015-04-27 | 2016-09-30 | 2018-02-21 | 2018-07-31 | 2018-10-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 8967.13 | 44642.05 | 60990.03 | 204.24 | 57.79 | 114861.24 | 0 | 114861.24 | 0 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502431 | Tighnabruaich WTW - Portavadie SR and SDN | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-06 | 2019-06-21 | 2019-06-05 | 2019-05-28 | 2019-05-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0.02 | 0 | 85.16 | 0 | 0 | 85.18 | 0 | 85.18 | 0 | [6 empty] | DW25T | 100%
502575 | Tighnabruaich WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-06-04 | 2021-12-06 | 2022-02-16 | 2023-01-26 | 2023-04-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 20930.23 | 276.28 | 6167.27 | 8909.76 | 13167.8 | 49451.34 | 950548.67 | 1000000.01 | 136478.56 | [6 empty] | WG1 | 100%
500181 | Tillicoultry DOA (DOA000310) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-12-19 | 2016-12-20 | 2017-01-31 | 2017-02-28 | Clackmannanshire | 0 | 13425 | 5203 | -5389.94 | 0 | 0 | 0 | 13238.06 | 0 | 13238.06 | 85931.02 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
501156 | Tillicoultry STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-11 | 2018-12-20 | 2019-02-04 | 2021-01-15 | 2021-03-16 | Clackmannanshire | 0 | 0 | 148181.94 | 252197.65 | 461532.27 | 1212128.93 | 708390.21 | 2782431 | 38990 | 2821421 | 0 | [6 empty] | CM_WWNI | 100%
503305 | Tillicoultry WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-15 | 2019-04-15 | Clackmannanshire | 0 | 0 | 0 | 0 | 24921.03 | 0 | 0 | 24921.03 | 0 | 24921.03 | 136478.56 | [6 empty] | SG1 | 100%
505070 | Tillicoultry WwTW Replacement Air compressor Units | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 | 2020-07-17 | 2020-10-23 | 2020-11-20 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 1962.62 | 0 | 1962.62 | 0 | 1962.62 | 0 | [6 empty] | Ww3 | 100%
403131 | Tiree Crossapol Replacement Septic Tank and New Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-30 | 2013-09-17 | 2014-01-21 | 2014-11-30 | 2015-03-31 | Argyll and Bute-North Argyll | 310492 | 2000 | 5259.41 | 0 | 0 | 0 | 0 | 7259.41 | 0 | 317751.41 | 56717112.68 | [6 empty] | CM_WWNI | 100% | bar: Regulatory Outputs OMG-17
500900 | Tiree WOA Caolas SR (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-18 | 2017-02-27 | 2017-02-27 | 2019-07-23 | 2019-07-23 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 186.92 | -186.92 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25D | 100%
500910 | Tiree WOA Ruaig SDN (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-03-15 | 2017-03-23 | 2017-03-23 | 2020-06-09 | 2020-06-09 | Argyll and Bute-North Argyll | 0 | 16704 | 7033.02 | 574.14 | 2382 | 1502.35 | 0.01 | 28195.52 | 0 | 28195.52 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
500902 | Tiree WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2018-03-31 | 2018-03-31 | Argyll and Bute-North Argyll | 0 | 83.72 | -83.72 | 123.03 | 0 | -123.03 | 0.01 | 0.01 | 0 | 0.01 | 1773.42 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501199 | Tiree WTW Boreholes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-07-13 | 2017-08-23 | 2017-09-25 | 2022-01-11 | 2022-01-11 | Argyll and Bute-North Argyll | 0 | 0 | 42762.22 | 95686.73 | 32236.48 | -23648.78 | 5818.17 | 152854.82 | 385649.31 | 538504.13 | 0 | [6 empty] | CM_WSNI | 100%
404033 | Tobermory (Craignure WQ) - Man Del Completion Project TR 045029 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS3 | 2009-03-12 | 2012-11-01 | 2013-11-20 | 2020-04-20 | 2020-04-20 | Argyll and Bute-North Argyll | 26875 | 289842.67 | 3007982.5 | 1834478.49 | 1087259 | 48950.8 | 5764.99 | 6274278.45 | 19246.82 | 6320400.27 | 1848054.6 |  |  |  |  | 64160 |  | DW23 | 30.5% | WG1 | 69.5%
403165 | Tobermory Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2014-07-28 | 2014-07-23 | 2014-05-16 | 2014-05-16 | Argyll and Bute-North Argyll | 63442.19 | 1452 | 0 | 0 | 0 | 0 | 0 | 1452 | 0 | 64894.19 | 0 | [6 empty] | CM_WSI | 100%
500912 | Tobermory WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-09-30 | 2016-09-30 | Argyll and Bute-North Argyll | 0 | 6480 | -3258.38 | 231.9 | 0 | 0 | 0 | 3453.52 | 0 | 3453.52 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
500882 | Tolsta Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-06-25 | 2020-03-19 | Na H-Eileanan an Iar | 0 | 5113.05 | 7883.52 | 18934.79 | 109738.09 | 62707.8 | 1330.78 | 205708.03 | 0 | 205708.03 | 432810.51 | [6 empty] | DW5FS | 100%
404134 | Tomatin WTW - Cartridge Filters + UV | Q&S3B | Completion | OMG180 |  |  | Water |  | NONINF | OMG180 | MS3 | 2016-03-31 | 2018-12-20 | 2018-12-21 | 2021-01-31 | 2021-05-31 | Highland | 0 | 0 | 0 | 500250.07 | 1803305.64 | 1897574.56 | 363120 | 4564250.27 | 172234.09 | 4736484.36 | 0 |  |  |  |  | 219280 |  | DW25 | 100% | bar: Regulatory Outputs OMG-03
404103 | Tomatin WTW Upgrade | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS7 | 2016-03-31 | 2018-01-23 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Highland | 0 | 22912.75 | -22912.75 | 6776.65 | 0 | 18.47 | -331.74 | 6463.38 | 0 | 6463.38 | 0 | [6 empty] | DW25 | 100%
503527 | Tomatin WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-09-27 | 2024-05-06 | 2024-09-06 | 2025-11-27 | 2026-02-27 | Highland | 0 | 0 | 0 | 0 | 59441.86 | 14565.38 | 36716.09 | 110723.33 | 1889276.71 | 2000000.04 | 136478.56 | [6 empty] | SG1 | 100%
502576 | Tomich WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2033-06-07 | 2033-08-19 | 2034-07-31 | 2034-10-31 | Highland | 0 | 0 | 20930.23 | 671.68 | 2160.9 | 25078.91 | -43969.68 | 4872.04 | 0 | 4872.04 | 136478.56 | [6 empty] | WG1 | 100%
403588 | Tomnavoulin Catchment - Intake and treatment Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-09-17 | 2013-10-14 | 2013-11-08 | 2015-02-12 |  | Moray | 264315 | 20484.38 | 151.33 | 64.22 | 0 | 0 | 0 | 20699.93 | 0 | 285014.93 | 0 | [6 empty] | CM_WSI | 100%
501201 | Tomnavoulin WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2028-10-25 | 2029-02-27 | 2030-05-14 | 2030-08-14 | Aberdeenshire | 0 | 14830.71 | 0 | 0 | 0 | 0 | 0 | 14830.71 | 0 | 14830.71 | 0 | [6 empty] | CM_WSNI | 100%
501736 | Torcross DSR Mainout | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2028-07-24 | 2029-05-09 | 2029-09-12 | 2030-01-22 | 2030-04-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.97 | 99999.97 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
505092 | Torduff and Clubbiedean road repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-04 | 2020-07-17 | 2020-10-23 | 2020-11-20 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 49029.9 | 0 | 49029.9 | 0 | 49029.9 | 0 | [6 empty] | CM_WSI | 100%
502387 | Tornagrain Development Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2018-12-18 | 2018-12-18 | 2019-02-04 | 2019-02-21 | 2019-02-21 | Highland | 0 | 0 | 0 | 0 | 856598.13 | 0 | 0 | 856598.13 | 0 | 856598.13 | 470181.23 | [6 empty] | WG5 | 100%
31091 | Torphichen STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-29 | 2010-11-01 | 2011-02-01 | 2014-01-07 | 2014-01-24 | West Lothian | 3119049.89 | 154475.41 | 11385.81 | 0 | 0 | 0 | 0 | 165861.22 | 0 | 3284911.11 | 31762 | [6 empty] | EC10A | 10% | EC04A | 90%
403427 | Torphichen WMR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-03 | 2013-09-24 | 2013-09-30 | 2015-01-07 |  | West Lothian | 793801 | 14217 | -3705.55 | 0 | 0 | 0 | 0 | 10511.45 | 0 | 804312.45 | 0 | [6 empty] | CM_WSI | 100%
45543 | Torphins STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2012-03-27 | 2012-11-12 | 2014-02-21 | 2014-02-25 | Aberdeenshire | 1096857.19 | 22714.05 | 0 | 0 | 0 | 0 | 0 | 22714.05 | 0 | 1119571.24 | 121969.6 | [6 empty] | CM_WWNI | 20% | WQ01 | 80%
500883 | Torra Islay RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-10-06 | 2018-09-18 | 2018-11-19 | 2019-03-31 | 2020-02-29 | Argyll and Bute-North Argyll | 0 | 1899.35 | 8208.97 | 11362.09 | 42833.48 | 11547.79 | 0 | 75851.68 | 0 | 75851.68 | 126571.05 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 18.37
502371 | Torra WOA Airport SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-04-23 | 2019-04-23 | Argyll and Bute-North Argyll | 0 | 0 | 10046.51 | 410.1 | 1489.68 | -9446.56 | 0 | 2499.73 | 0 | 2499.73 | 0 | [6 empty] | CM_WSNI | 100%
500901 | Torra WOA Airport SR (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-12-22 | 2017-03-01 | 2017-03-01 | 2017-12-31 | 2017-12-31 | Argyll and Bute-North Argyll | 0 | 3139.53 | 0 | 451.11 | 0 | 0 | 0 | 3590.64 | 0 | 3590.64 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502374 | Torra WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWMD | Strategic Capacity | GW2 | 2020-04-01 | 2022-04-20 | 2022-08-17 | 2023-12-19 | 2024-03-18 | Argyll and Bute-North Argyll | 0 | 0 | 8583.6 | 1212.88 | 13318.8 | 86414.4 | 257991.95 | 367521.63 | 11632478.37 | 12000000 | 136478.56 | [6 empty] | WG1 | 100%
503551 | Torra WTW Growth - Emergency Tankering | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2019-05-01 | 2019-05-01 | 2019-06-17 | 2020-08-21 | 2020-11-23 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 67151.61 | -22151.51 | 45000.1 | 0 | 45000.1 | 136478.56 | [6 empty] | SG1 | 100%
503562 | Torra WTW Growth - TTU Installation | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2019-04-30 | 2020-03-17 | 2020-03-31 | 2021-04-15 | 2021-03-15 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 718160.6 | 1771938.72 | 2490099.32 | 57698.69 | 2547798.01 | 136478.56 | [6 empty] | SG1 | 100%
502279 | Torra WTW Sludge Lagoon Upgrade | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS6 | 2017-06-16 | 2018-03-21 | 2018-05-28 | 2018-11-30 | 2019-01-31 | Highland | 0 | 0 | 21819.82 | 72449.6 | 69587.68 | 275.83 | 185.54 | 164318.47 | 0 | 164318.47 | 207663.58 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
500842 | Torridon RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-10-28 | 2017-03-23 | 2017-04-25 | 2017-06-30 | 2018-03-31 | Highland | 0 | 3000 | 10403.97 | 11972.43 | 12450.16 | 1706.7 | -1006.26 | 38527 | 0 | 38527 | 13518.27 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 4.07
500903 | Torridon WTW (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-02-27 | 2017-03-16 | 2017-03-16 | 2017-07-31 | 2017-07-31 | Highland | 0 | 2160 | 2171.48 | -792.99 | 0 | 0 | 0 | 3538.49 | 0 | 3538.49 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
46826 | Torrin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2012-06-20 | 2012-11-19 | 2015-03-31 | 2015-03-31 | Highland | 7865477.59 | 387478.79 | 10084.71 | -15946.3 | 0 | 0 | 0 | 381617.2 | 0 | 8247094.79 | 386275 | [6 empty] | WG4 | 20.04% | DW23 | 79.96%
402676 | Torwood WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2012-06-19 | 2020-06-15 | 2020-06-22 | 2021-10-08 | 2021-10-08 | Falkirk | 236252 | 112617 | 7437.6 | 14127.4 | 71434.5 | 479737.4 | 1017014.98 | 1702368.88 | 689471.02 | 2628091.9 | 0 |  |  |  |  | 2920 |  | SG1 | 100%
403613 | Toughbook Replacement Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2015-03-12 |  | Scottish Water Wide | 4546746 | -55361.66 | 0 | 0 | 0 | 0 | 0 | -55361.66 | 0 | 4491384.34 | 0 | [6 empty] | CM_M&G | 100%
502973 | Townholm Pipe Bridge Kilmarnock | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2018-06-18 | 2021-01-11 | 2021-03-26 | 2021-10-27 | 2022-01-27 | East Ayrshire | 0 | 0 | 0 | 13214.19 | 6301.35 | 1223.37 | 193768.48 | 214507.39 | 368541.56 | 583048.95 | 0 | [6 empty] | SR21_WW | 100%
403411 | TR61 Version 12 Software (WRc CP500) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-03-04 | 2013-03-04 | 2013-04-01 | 2016-02-02 |  | Scottish Water Wide | 27297.44 | 5940 | 0 | 0 | 0 | 0 | 0 | 5940 | 0 | 33237.44 | 0 | [6 empty] | WSI | 0.25% | WSNI | 0.25% | WWNI | 0.25% | WWI | 99.25%
501327 | Trade Effluent Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2019-03-04 | 2018-02-12 | Scottish Water Wide | 0 | 0 | 90592.02 | 409407.98 | 365980.55 | 0 | 0 | 865980.55 | 0 | 865980.55 | 0 | [6 empty] | CM_M&G | 100%
503593 | Transformational Change Project | Q&S4 | Sustaining existing high service for customers | Transformation Demonstrators |  |  | General |  | SWD | Transformation Demonstrators | MSU | 2020-05-21 | 2022-01-31 | 2022-06-02 | 2023-12-27 | 2024-02-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 3468562.99 | 531437.01 | 4000000 | 0 | 4000000 | 0 | [6 empty] | SR15_CMA_TD | 100%
402152 | Treated Water Sample tap replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-06-13 | 2011-08-08 | 2011-09-12 | 2013-10-08 |  | Scottish Water Wide | 1843533.56 | 3.59 | 0 | 0 | 0 | 0 | 0 | 3.59 | 0 | 1843537.15 | 0 | [6 empty] | CM_WSNI | 100%
401431 | Treated Water Sample Tap Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-24 | 2011-11-04 | 2012-02-01 | 2015-11-20 |  | Scottish Water Wide | 279973 | -2103.28 | 0 | 0 | 0 | 0 | 0 | -2103.28 | 0 | 277869.72 | 0 | [6 empty] | CM_WSNI | 100%
503253 | Treated Water Storage Water Quality Improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-07 | 2021-04-12 | 2021-04-19 | 2021-05-28 | 2021-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1496070.64 | 2383590.29 | 0 | 3879660.93 | 0 | 3879660.93 | 0 | [6 empty] | CM_WSNI | 100%
503065 | Treated Water Storage Water Quality Improvements - Phase 1 East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2018-04-19 | 2018-06-21 | 2018-06-21 | 2020-03-23 | 2020-03-23 | All East Unitary Authorities | 0 | 0 | 0 | 53891.2 | 2011256.74 | 717270.95 | 636232.12 | 3418651.01 | 0 | 3418651.01 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503066 | Treated Water Storage Water Quality Improvements - Phase 1 North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2018-04-19 | 2018-06-21 | 2018-06-21 | 2020-03-23 | 2020-03-23 | All North Unitary Authorities | 0 | 0 | 0 | 18837.21 | 306326.12 | 68642.88 | -371.21 | 393435 | 0 | 393435 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503067 | Treated Water Storage Water Quality Improvements - Phase 1 South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2018-04-17 | 2018-06-18 | 2018-06-18 | 2020-03-23 | 2020-03-23 | All South Unitary Authorities | 0 | 0 | 0 | 12558.14 | 741048.22 | -19257.25 | 269382.89 | 1003732 | 0 | 1003732 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503068 | Treated Water Storage Water Quality Improvements - Phase 1 West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2018-04-17 | 2018-06-18 | 2018-06-18 | 2020-03-23 | 2020-03-23 | All West Unitary Authorities | 0 | 0 | 0 | 12558.14 | 1495718.6 | 15614.09 | 407678.17 | 1931569 | 0 | 1931569 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503553 | Treated Water Storage Water Quality Improvements - Phase 2 East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2021-03-22 | 2020-12-16 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 2560996 | 1592940.72 | 4153936.72 | -118.71 | 4153818.01 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
503554 | Treated Water Storage Water Quality Improvements - Phase 2 North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2021-03-16 | 2020-12-16 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 1090004.12 | 1133096.06 | 2223100.18 | -197.18 | 2222903 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
503555 | Treated Water Storage Water Quality Improvements - Phase 2 South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2021-03-16 | 2020-12-16 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 1349014.29 | 1731440.71 | 3080455 | 0 | 3080455 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
503556 | Treated Water Storage Water Quality Improvements - Phase 2 West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2021-03-16 | 2020-12-16 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 2086737.07 | 2339239.9 | 4425976.97 | 0 | 4425976.97 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
500238 | Trinity SPS Rising Main - Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-05-07 | 2016-12-14 | 2017-02-28 | 2017-10-23 | 2017-10-23 | City of Edinburgh | 0 | 86983 | 325249 | 422267.63 | 0.37 | -6637.24 | 0.24 | 827863 | 0 | 827863 | 0 | [6 empty] | CM_WWI | 100%
402824 | Trinity SPS Rising main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-14 | 2014-01-30 | 2014-02-24 | 2015-03-25 |  | City of Edinburgh | 209763 | 929 | 925.72 | -4288.08 | 0 | 0 | 0 | -2433.36 | 0 | 207329.64 | 0 | [6 empty] | CM_WWI | 100%
500851 | Trislaig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2015-11-04 | 2016-03-25 | 2016-05-24 | 2018-03-31 | 2018-06-30 | Highland | 0 | 1736.99 | 6788.87 | 456.88 | 45638.47 | 2653.4 | -176.77 | 57097.84 | 0 | 57097.84 | 5909.44 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 33.34
402263 | Tronafirth ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-08-17 | 2013-09-30 | 2013-12-02 | 2014-03-28 | 2014-03-28 | Shetland Islands | 349978.5 | 1181.5 | -214.63 | 0 | 0 | 0 | 0 | 966.87 | 0 | 350945.37 | 0 | [6 empty] | SG1 | 100%
402520 | Troon Pan Rocks SPS EO Outfall Extension | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-06 | 2016-02-15 | 2016-02-01 | 2016-02-19 |  | South Ayrshire | 49398.28 | 3152.8 | 0 | 0 | 0 | 0 | 0 | 3152.8 | 0 | 52551.08 | 0 | [6 empty] | CM_WWI | 100%
403550 | Troqueer WWTW - Critical items for compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-08-02 | 2014-01-15 | 2014-01-15 | 2015-11-05 |  | Dumfries and Galloway | 530000 | 81884.68 | 4940 | 0 | 0 | 0 | 0.32 | 86825 | 0 | 616825 | 0 | [6 empty] | CM_WWNI | 100%
500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2020-01-07 | 2020-03-03 | Dumfries and Galloway | 0 | 15707 | 39892.66 | 73449.34 | 37250 | 33701 | 0 | 200000 | 0 | 200000 | 117149.49 | [6 empty] | EC01G | 6.06% | EC01D | 44.79% | CS16D | 49.15%
402881 | Troqueer Sewage Pump Station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2012-08-27 | 2017-06-20 | 2017-06-20 | 2017-06-20 |  | Dumfries and Galloway | 235896 | 185439 | 232493.57 | 4132.23 | 419.39 | 732.69 | -732.69 | 422484.19 | 0 | 658380.19 | 0 | [6 empty] | CM_WWNI | 100%
402628 | Troqueer WwTW DO Plant Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-04-16 | 2012-08-08 | 2012-09-28 | 2013-09-16 |  | Dumfries and Galloway | 336759.98 | 466.27 | 0 | 0 | 0 | 0 | 0 | 466.27 | 0 | 337226.25 | 0 | [6 empty] | CM_WWNI | 100%
400605 | TS 3rd Party Services | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -1577562.8 | 26893.83 | 28990.15 | -113146.26 | 146799.59 | 10672.33 | -10989.59 | 89220.05 | 0 | -1488342.75 | 0 | [6 empty] | OHDS1 | 100%
400474 | TS AIM indirect overhead | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 19124680.68 | 12228.52 | -13293.38 | -4185.27 | 170.32 | 0 | 0 | -5079.81 | 0 | 19119600.87 | 0 | [6 empty] | OHDS1 | 100%
403896 | TS Alliance Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-29 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 625772.54 | 9696.46 | 0 | 0 | 0 | 0 | 0 | 9696.46 | 0 | 635469 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
400479 | TS AS indirect overhead | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 9050647.78 | 14880.53 | -2872.23 | 499.08 | 0 | 0 | 0 | 12507.38 | 0 | 9063155.16 | 0 | [6 empty] | OHDS1 | 100%
403897 | TS Business Improvement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-29 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 202665.79 | 185.64 | 0 | 368.78 | 0 | 0 | 0 | 554.42 | 0 | 203220.21 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
400541 | TS Corporate Comms indirect overhead | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 3623275.23 | 7037.13 | 0 | 2651.96 | 0 | 0 | 0 | 9689.09 | 0 | 3632964.32 | 0 | [6 empty] | OHDS1 | 100%
400537 | TS Financial Control indirect overhead | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 1771807.55 | 96120 | 0 | 3306.49 | 0 | 2144.55 | 0 | 101571.04 | 0 | 1873378.59 | 0 | [6 empty] | EC01A | 100%
400477 | TS GIV indirect overhead | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 5361088.34 | 0 | 0 | 5182.33 | 0 | 0 | 0 | 5182.33 | 0 | 5366270.67 | 0 | [6 empty] | OHDS1 | 100%
400539 | TS I.T. indirect overhead | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 23134684.93 | -70104.94 | 611.64 | 0 | 0 | 0 | 0 | -69493.3 | 0 | 23065191.63 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
400542 | TS Regulation indirect overhead | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 3163070.15 | 2136.94 | 0 | 0 | 0 | 0 | 0 | 2136.94 | 0 | 3165207.09 | 0 | [6 empty] | OHDS1 | 100%
400543 | TS SW Overhead reallocation project | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -63886696.7 | -922004.76 | 0 | 0 | 0 | 0 | 0 | -922004.76 | 0 | -64808701.46 | 0 | [6 empty] | OHDS1 | 100%
403499 | Tullibardine WSZ - Orchil Road Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-06-12 | 2014-03-20 | 2014-03-27 | 2014-11-13 |  | Perth and Kinross | 503061 | 673.32 | 393.91 | 0 | 0 | 0 | 0 | 1067.23 | 0 | 504128.23 | 0 | [6 empty] | CM_WSI | 100%
503661 | Tullich PAC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-08-13 | 2020-02-24 | 2020-02-24 | 2020-11-23 | 2020-11-23 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 446325.27 | 365101.22 | 811426.49 | 4809.51 | 816236 | 0 | [6 empty] | CM_WSNI | 100%
500852 | Tullich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-03 | 2018-03-08 | Argyll and Bute-North Argyll | 0 | 6651.26 | 23530.25 | 38979.6 | 4076.69 | -393.93 | 0 | 72843.87 | 0 | 72843.87 | 65608.63 | [6 empty] | DW5FS | 100%
500573 | Tullich WOA - Oban North & South TWS Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-06-08 | 2020-03-27 | 2020-03-10 | 2021-03-19 | 2021-06-10 | Highland | 0 | 103505 | 155182.55 | 195899.59 | 302107 | 901362.17 | 4751813 | 6409869.31 | 1607981.69 | 8017851 | 0 | [6 empty] | CM_WSNI | 100%
503617 | Tullich WOA Oban 12 Main Refurbishment (CWA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2019-07-05 | 2020-04-13 | 2020-07-06 | 2021-08-26 | 2021-10-19 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 469003.46 | 941851.69 | 1410855.15 | 557932.63 | 1968787.78 | 0 | [6 empty] | CM_WSI | 100%
501111 | Tullich WOA Oban 12inch Da Main Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2017-03-21 | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-06-08 | Argyll and Bute-North Argyll | 0 | 36000 | 9752.93 | 96614.05 | 74192.43 | -178370.28 | -30750.29 | 7438.84 | 0 | 7438.84 | 0 | [6 empty] | CM_WSI | 100%
500054 | Tullich WOA Oban South WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-18 | 2016-11-18 | 2017-06-26 | 2018-09-11 | 2018-09-11 | Argyll and Bute-North Argyll | 0 | 8235 | 40129 | 145882.98 | -30676.99 | -10108.21 | 0 | 153461.78 | 0 | 153461.78 | 0 | [6 empty] | CM_WSI | 100%
502233 | Tullich WTW Temporary UV treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2017-01-25 | 2017-01-25 | Highland | 0 | 0 | 1418228.74 | -20597.01 | 572.75 | 0 | 0 | 1398204.48 | 0 | 1398204.48 | 0 | [6 empty] | CM_WSNI | 100%
46838 | Tullich WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2015-03-27 | 2016-04-01 | 2014-10-24 | 2016-04-01 | Argyll and Bute-North Argyll | 1956538.93 | 776.76 | 142.35 | 0 | 0 | 0 | 0 | 919.11 | 0 | 1957458.04 | 31759.8 | [6 empty] | CM_WSNI | 40% | DW23 | 60%
403862 | Tullich WTW Upgrade TR from 046838 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | NONINF | Non OMG180 | MS5 | 2014-06-24 | 2015-10-29 | 2016-01-18 | 2019-03-31 | 2019-03-31 | Argyll and Bute-North Argyll | 273058 | 2137845 | 13785345.59 | 11311547.68 | 4309739.19 | 2351399.2 | 85999.8 | 33981876.46 | 8600.04 | 34263534.5 | 7947519.6 |  |  |  |  | 133847 |  | DW23 | 40% | CM_WSNI | 60% | bar: Regulatory Outputs OMG-03
501633 | Turbidity Scanning Compliance | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-10-07 | 2028-12-13 | 2029-04-17 | 2030-03-26 | 2030-06-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529999.98 | 529999.98 | 0 | [6 empty] | CM_WSNI | 100%
46181 | Turnberry SPS Refurb - SPS001936 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-21 | 2012-02-20 | 2012-04-24 | 2013-03-15 |  | South Ayrshire | 744283.11 | -187.14 | 0 | 0 | 0 | 0 | 0 | -187.14 | 0 | 744095.97 | 0 | [6 empty] | CM_WWNI | 100%
502409 | Turnberry SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-07-25 | 2018-12-20 | 2019-03-08 | 2019-08-13 | 2019-08-13 | South Ayrshire | 0 | 0 | 4083.9 | 61710.57 | 282400.53 | 226898 | 0 | 575093 | 1907 | 577000 | 0 | [6 empty] | CM_WWI | 100%
500889 | Turret - Balmoe - Carron Valley RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-11-21 | 2018-09-26 | 2018-11-29 | 2019-09-30 | 2020-11-02 | Falkirk | 0 | 7916.89 | 7696.89 | 11925.39 | 36955.5 | 66415.56 | -1156.84 | 129753.39 | 0 | 129753.39 | 403640.09 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 34.05
500888 | Turret A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Stirling | 0 | 2431.21 | 1345.28 | 1427.16 | -1427.16 | 0 | 0 | 3776.49 | 0 | 3776.49 | 69065.41 | [6 empty] | DW5FS | 100%
402737 | Turret Cathodic Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2012-07-23 | 2020-07-20 | 2020-07-20 | 2020-04-03 |  | Stirling | 23500 | 69914.83 | 10224.17 | 93286 | 103890.2 | -58644 | 0 | 218671.2 | 0 | 242171.2 | 0 | [6 empty] | CM_WSI | 100%
503525 | Turret Lower Powerhouse HV Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2019-04-08 | 2021-01-18 | 2021-03-15 | 2021-09-27 | 2021-12-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 110659.9 | 1649684.1 | 1760344 | 0 | 1760344 | 0 | [6 empty] | CM_WSNI | 100%
505933 | Turret No auto shutdown on low Chlorine | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 | 2020-07-24 | 2020-10-30 | 2020-11-27 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 10000 | 79911852.97 | [6 empty] | WSNI | 100%
502586 | Turret WTW Legacy Sludge Sludge Removal & Lagoon Modifications | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS0 | 2017-12-29 | 2021-03-15 | 2021-07-28 | 2022-11-17 | 2023-02-17 | Perth and Kinross | 0 | 0 | 35216.4 | 42964.42 | 169993.29 | 103052.6 | 54259.6 | 405486.31 | 4276776.45 | 4682262.76 | 1024271.42 | [6 empty] | LA01 | 100%
500213 | Turriff - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-05-30 | 2017-03-31 | 2018-06-30 | Aberdeenshire | 0 | 15457 | 15932.34 | 12093.36 | 1400 | -9319.52 | 0 | 35563.18 | 0 | 35563.18 | 127087.8 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500890 | Turriff RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-27 | 2020-02-28 | Aberdeenshire | 0 | 26600 | 18676.6 | 37000 | 112827.28 | 81449.83 | 816.51 | 277370.22 | 0 | 277370.22 | 1297898.84 | [6 empty] | DW5FS | 100%
501195 | Turriff TWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-06 | 2027-05-06 | 2027-05-06 | 2027-05-06 | 2027-05-06 | Aberdeenshire | 0 | 12679.79 | 1278.36 | 641.93 | 0 | 0 | 0 | 14600.08 | 0 | 14600.08 | 0 | [6 empty] | CM_WSNI | 100%
503537 | Turriff WTW - Ceramac Pilot Plant - Design Installation and Operation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2019-03-19 | 2020-09-14 | 2020-09-15 | 2020-09-15 | 2020-09-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 7001.41 | 707804.45 | 5194.13 | 719999.99 | 0 | 719999.99 | 0 | [6 empty] | CM_WSNI | 100%
501002 | Turriff WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2029-02-14 | 2029-04-19 | 2032-04-29 | 2032-07-30 | Aberdeenshire | 0 | 107967.82 | 12302.74 | 106357.55 | 877424.94 | -490987.17 | -283.82 | 612782.06 | 0 | 612782.06 | 0 | [6 empty] | CM_WSNI | 100%
503072 | Turriff WTW - Essential CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-02-11 | 2021-01-04 | 2021-04-06 | 2022-10-27 | 2023-01-27 | Aberdeenshire | 0 | 0 | 0 | 58430.17 | 6012.61 | 678860.08 | 766497.29 | 1509800.15 | 6139830.92 | 7649631.07 | 0 | [6 empty] | CM_WSNI | 100%
503054 | Turriff WTW - installation of UV treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-01-24 | 2018-01-24 | 2018-02-12 | 2018-12-03 | 2018-12-03 | Aberdeenshire | 0 | 0 | 0 | 1454419.03 | 905667.32 | 255.74 | 940.79 | 2361282.88 | 303.49 | 2361586.37 | 0 |  |  |  |  | 39196 |  | CM_WSNI | 100%
502781 | Turriff WTW - RGF Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-08-29 | 2017-08-29 | 2017-09-25 | 2020-11-03 | 2020-11-03 | Aberdeenshire | 0 | 0 | 0 | 215793.35 | 101408.15 | 1782960.57 | 594705.1 | 2694867.17 | 8274.16 | 2703141.33 | 0 | [6 empty] | CM_WSNI | 100%
501027 | Turriff WTW QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2016-03-25 | 2017-10-27 | 2018-02-28 | 2018-10-31 | 2020-03-31 | Aberdeenshire | 0 | 18483 | 24190.54 | 166279.82 | 57089.98 | -8397.58 | 1961.25 | 259607.01 | 392.99 | 260000 | 471905.77 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403307 | Turriff WTW RGFs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-29 | 2015-08-10 | 2015-07-29 | 2015-07-29 |  | Aberdeenshire | 665889.26 | -4538.14 | 0 | 0 | 0 | 0 | 0 | -4538.14 | 0 | 661351.12 | 0 | [6 empty] | CM_WSNI | 100%
45615 | Turriff WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-07-08 | 2013-10-03 | 2014-03-21 | Aberdeenshire | 638026.03 | -2852.39 | 23.73 | 0 | 0 | 0 | 0 | -2828.66 | 0 | 635197.37 | 2334 | [6 empty] | DW1A | 100%
503277 | Turriff WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-23 | 2023-01-04 | 2023-05-09 | 2024-05-06 | 2024-08-06 | Moray | 0 | 0 | 0 | 0 | 82034.53 | 15615.27 | 47990.06 | 145639.86 | 2854360.14 | 3000000 | 136478.56 | [6 empty] | SG1 | 100%
503565 | Turriff WWTW- Flocor tower replacement | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2020-01-24 | 2020-09-07 | 2020-11-13 | 2021-12-01 | 2022-03-03 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 150540.91 | 42281.22 | 192822.13 | 1449177.87 | 1642000 | 136478.56 | [6 empty] | SG1 | 100%
401377 | Turriff WwTW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-02-07 | 2014-10-31 | 2015-07-06 | 2015-07-06 | 2015-07-06 | Aberdeenshire | 1239884.83 | -5432.72 | 0 | 0 | 0 | 0 | 0 | -5432.72 | 0 | 1234452.11 | 0 | [6 empty] | SG1 | 30% | CM_WWNI | 70%
45376 | Tweedsmuir WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2012-02-20 | 2015-02-13 | 2015-09-18 | Scottish Borders | 2959028.28 | 240268.92 | 31454.31 | -4235.02 | -1642.92 | 0 | 1642.92 | 267488.21 | 0 | 3226516.49 | 311388 | [6 empty] | DW23 | 100%
402206 | TWP 0000488 - Shenval Water Pumping Station Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-19 | 2011-10-10 | 2012-01-23 | 2012-09-06 |  | Perth and Kinross | 151129 | 472.01 | 0 | 0 | 0 | 0 | 0 | 472.01 | 0 | 151601.01 | 0 | [6 empty] | CM_WSNI | 100%
402385 | TWP000444 - Mannofield MPS2 - Feasibility Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-27 | 2012-12-07 | 2013-02-18 | 2013-08-30 |  | Aberdeen City | 388655.95 | 122929.4 | 0 | 0 | 0 | 0 | 0 | 122929.4 | 0 | 511585.35 | 0 | [6 empty] | CM_WSNI | 100%
501950 | TWPs - West Area Cluster 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-03-31 | 2019-03-01 | 2019-03-01 | 2020-12-16 | 2020-12-16 | All West Unitary Authorities | 0 | 1942 | 139658.24 | 420963.08 | 329702.78 | 707751.9 | 905623.98 | 2505641.98 | 19611 | 2525252.98 | 0 | [6 empty] | CM_WSNI | 100%
505405 | TWS Asset Repair Mission m2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2020-04-01 | 2020-11-09 | 2021-03-16 | 2021-09-14 | 2021-12-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1127.08 | 2204191.12 | 2205318.2 | 1794681.81 | 4000000.01 | 0 | [6 empty] | CM_WSNI | 100%
500853 | Tyndrum RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-04-07 | 2017-03-23 | 2017-05-23 | 2018-11-30 | 2019-08-31 | Stirling | 0 | 1409.4 | 1982.6 | 9674.87 | 3270.82 | 1317.04 | 0.01 | 17654.74 | 0 | 17654.74 | 12415.64 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 2.44
500724 | Udny Green WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-02-03 | 2022-05-12 | 2022-09-05 | 2024-04-12 | 2024-07-15 | Aberdeenshire | 0 | 27767.26 | 58914.31 | 81297.33 | 10654.69 | 35058.78 | 93413.18 | 307105.55 | 2675631.58 | 2982737.13 | 136478.56 | [6 empty] | SG1 | 100%
500725 | Udny Station WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2018-03-27 | 2022-01-03 | 2022-06-03 | 2023-08-22 | 2023-11-21 | Aberdeenshire | 0 | 28907.67 | 51671.7 | 81673.28 | 11458.99 | 96973.77 | 74588.31 | 345273.72 | 1649714.91 | 1994988.63 | 136478.56 | [6 empty] | SG1 | 100%
31251 | UID - Cowdenbeath WWPS- Storm Tank | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-06 | 2010-08-23 | 2010-09-06 | 2014-03-21 | 2014-03-24 | Fife | 8791421 | 4000 | -60245.46 | 0 | 0 | 0 | 0 | -56245.46 | 0 | 8735175.54 | 19752 |  |  |  |  | 10506 |  | EC01 | 50% | EC10 | 50%
37781 | UID - Cumbernauld uSWO | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-11 | 2011-02-24 | 2011-03-07 | 2013-02-07 | 2013-02-26 | North Lanarkshire | 3551162 | -3483.02 | 0 | 0 | 0 | 0 | 0 | -3483.02 | 0 | 3547678.98 | 0 | [6 empty] | EC09 | 50% | EC10 | 50%
31284 | UID - Elderslie-Old Patrick Water No2 CSO 242 Main Road at Elderslie Bridge | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-08-13 | 2009-10-06 | 2009-09-14 | 2010-03-22 | 2010-06-07 | Renfrewshire | 2610022.19 | 374.85 | 0 | 0 | 0 | 0 | 0.15 | 375 | 0 | 2610397.19 | 0 | [6 empty] | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31388 | UID - Laighstonehall Road at 193 Chantinghall Road | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-08-23 | 2010-09-20 | 2011-03-24 | 2011-03-25 | South Lanarkshire | 571183.12 | 104.21 | 0 | 0 | 0 | 0 | 0 | 104.21 | 0 | 571287.33 | 0 | [6 empty] | EC04 | 33.21% | EC10 | 33.21% | EC01 | 33.58%
300014 | UID - Lamont Drive - Rubie Crescent | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-01-31 | 2011-10-14 | 2011-10-31 | 2012-03-16 | 2012-03-30 | North Ayrshire | 342236 | -1509.63 | 0 | 0 | 0 | 0 | 0 | -1509.63 | 0 | 340726.37 | 0 | [6 empty] | EC02 | 33% | EC10 | 33% | EC01 | 34%
31412 | UID - Meikle Earnock Road at Irvine Terrace | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-03-07 | 2011-07-05 | 2011-11-17 | 2011-12-15 | South Lanarkshire | 665235.75 | 87.58 | 0 | 0 | 0 | 0 | 0 | 87.58 | 0 | 665323.33 | 0 | [6 empty] | EC04 | 33.02% | EC10 | 33.02% | EC01 | 33.96%
31417 | UID - Millerpark Wellhall Road Bridge | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-03-07 | 2011-05-20 | 2011-12-15 | 2011-12-15 | South Lanarkshire | 555406 | -772 | 0 | 0 | 0 | 0 | 0 | -772 | 0 | 554634 | 0 | [6 empty] | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31426 | UID - Mote Hill Palace Grounds Road Hamilton | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-01-25 | 2011-02-21 | 2012-03-22 | 2012-03-23 | South Lanarkshire | 5037430 | -896.37 | 0 | 0 | 0 | 0 | 0 | -896.37 | 0 | 5036533.63 | 0 | [6 empty] | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31429 | UID - Neilsland Road at Burnhouse Road | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-03-25 | 2010-04-06 | 2011-03-24 | 2011-03-25 | South Lanarkshire | 843318.96 | 87.59 | 0 | 0 | 0 | 0 | 0 | 87.59 | 0 | 843406.55 | 0 | [6 empty] | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31439 | UID - Off Path 72 Westwood Crescent | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-03-25 | 2010-03-05 | 2010-12-15 | 2010-12-21 | South Lanarkshire | 693080.99 | 104.21 | 0 | 0 | 0 | 0 | -0.03 | 104.18 | 0 | 693185.17 | 0 | [6 empty] | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
49514 | UID Adjustment | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11469103.67 | [6 empty] | EC04B | 100%
403807 | UID Output Support - Sewer Cleaning | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2014-06-23 | 2015-02-12 | 2015-02-19 | 2018-02-23 | 2018-02-26 | Glasgow City | 262022 | 1248840 | 129327.93 | 171199.43 | 5743.12 | 256.88 | 0 | 1555367.36 | 0 | 1817389.36 | 1305151 | [6 empty] | EC10B | 100%
31434 | UID WP6.1 Kilmarnock Gravity Transfer Scheme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-20 | 2010-01-14 | 2011-11-08 | 2013-10-23 | 2013-12-23 | East Ayrshire | 25070886.8 | 153702.21 | 56789.08 | 1241.24 | 2293.2 | 24.44 | -24.43 | 214025.74 | 0 | 25284912.54 | 15867 | [6 empty] | EC01A | 33.33% | EC02A | 33.33% | EC10A | 33.33%
36868 | UID WP6.2 Gatehead Tank to Meadowhead Inlet Works Transfer Scheme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-20 | 2010-01-14 | 2010-12-08 | 2012-03-16 | 2012-03-30 | East Ayrshire | 15410452.69 | 54051.19 | 30946.28 | 11109.28 | 764.4 | 10423.68 | -10423.68 | 96871.15 | 0 | 15507323.84 | 14975 | [6 empty] | EC02 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
36860 | UID WP6.3 Irvine Transfer Scheme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-21 | 2010-01-14 | 2010-12-08 | 2013-01-31 | 2013-02-26 | North Ayrshire | 24666791 | 23582.35 | 95.13 | 7.41 | 0 | 0 | -7.41 | 23677.48 | 0 | 24690468.48 | 45486 |  |  |  |  | 18747 |  | EC02 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
403468 | UIDs Legacy Issues | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-07-12 | 2014-06-30 | 2014-08-01 | 2015-12-07 | 2016-01-08 | All West Unitary Authorities | 215071.05 | 99547.95 | 0 | -3911.63 | 0 | 0 | 0 | 95636.32 | 0 | 310707.37 | 52470 | [6 empty] | EC01D | 100%
402611 | UITS Recurring Bursts Remedial Actions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-04-24 | 2012-04-24 | 2012-05-29 | 2015-11-20 |  | Scottish Water Wide | 3677107 | 180946 | 123187.85 | 2756.28 | 0 | 0 | -0.13 | 306890 | 0 | 3983997 | 0 | [6 empty] | CM_WSI | 100%
505518 | Ullapool DSR - H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 | 2026-01-30 | Highland | 0 | 0 | 0 | 0 | 0 | 1133.42 | 0 | 1133.42 | 0 | 1133.42 | 0 | [6 empty] | CM_WSNI | 100%
500907 | Ullapool WOA SRs (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2016-01-12 | 2016-03-30 | 2016-03-30 | 2020-07-31 | 2020-08-31 | Highland | 0 | 0.35 | 0 | 8.84 | 407.07 | 220 | 0 | 636.26 | 0 | 636.26 | 466277.79 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
50030 | Unallocated Programme Overheads | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 23000000 | 23000000 | 0 | 23000000 | 769432.92 | [6 empty] | SR15_IR18_IR18 | 0.0005518% | SR15_ENV_SGR | 0.001169% | SR15_DWA_PRE | 0.007921% | SR15_CEX_STU | 0.01115% | WG3 | 0.01276% | SR15_DWA_LEAK | 0.02031% | SR15_DWA_EFA | 0.02182% | SR15_ENV_HABD | 0.02196% | SR15_SEW_SWO | 0.02504% | SR15_CCH_CC | 0.03964%
500966 | Underwood (Cumnock) STC CHP replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-11-16 | 2016-03-30 | 2016-09-26 | 2017-03-30 | 2017-04-10 | East Ayrshire | 0 | 1087.98 | 218352.27 | 2438.36 | -1209.04 | 0 | 0 | 220669.57 | 0 | 220669.57 | 0 | [6 empty] | CM_WWNI | 100%
31596 | Underwood (Cumnock) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-12-23 | 2011-02-14 | 2014-03-27 | 2014-05-12 | East Ayrshire | 5374135.85 | 295403.3 | 680174.44 | 372.47 | 0 | 0 | 0 | 975950.21 | 0 | 6350086.06 | 104837.95 |  |  |  |  | 32779 |  | EC04A | 3.025% | EC10A | 9.188% | CM_WWNI | 32.83% | EC01A | 54.95%
500186 | Underwood Cumnock DOA (DOA000144) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-27 | 2018-06-25 | East Ayrshire | 0 | 2000 | 21798.7 | 14298.31 | -865.45 | 0 | 0 | 37231.56 | 0 | 37231.56 | 10344.04 | [6 empty] | EC01G | 46.22% | CS16D | 53.78%
503420 | Unst WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2018-10-31 | 2020-03-31 | 2020-09-14 | 2021-02-24 | 2021-05-25 | Shetland Islands | 0 | 0 | 0 | 0 | 16736.04 | 41074.19 | 698211.84 | 756022.07 | 52797.99 | 808820.06 | 0 |  |  |  |  | 2500 |  | CM_WSNI | 100%
502568 | Unst WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-08-04 | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 | Shetland Islands | 0 | 0 | 20930.23 | 0 | -20695.43 | 0 | -233.8 | 1 | 0 | 1 | 136478.56 | [6 empty] | SG1 | 100%
46856 | Unst WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-09-15 | 2013-02-08 | 2013-02-21 | Shetland Islands | 3933525.59 | -38444.27 | 166.09 | 0 | 0 | 0 | 0 | -38278.18 | 0 | 3895247.41 | 0 | [6 empty] | DW23 | 100%
500672 | Update the National Sludge Strategy | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-07 | 2016-03-21 | 2016-03-30 | 2018-06-30 | 2019-03-31 | Scottish Water Wide | 0 | 120000 | 608983.33 | 742453.71 | 200115.96 | 1679.69 | -0.03 | 1673232.66 | 0 | 1673232.66 | 0 | [6 empty] | EC06C | 100% | bar: Regulatory Outputs OMG-23
503211 | Upgrade - Investigation and Scope Definition for potential Growth Project post 2021 at Silver Sand | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-02-04 | 2019-02-04 | Fife | 0 | 0 | 0 | 0 | 25841.58 | 0 | 0 | 25841.58 | 0 | 25841.58 | 136478.56 | [6 empty] | SG1 | 100%
31598 | Uplawmoor STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-04-29 | 2011-06-10 | 2011-09-30 | 2012-03-26 | 2012-04-26 | East Renfrewshire | 268383.52 | 816.3 | 0 | 0 | 0 | 0 | 0 | 816.3 | 0 | 269199.82 | 136478.56 | [6 empty] | SG1 | 3.019% | EC10A | 8.388% | EC04A | 12.58% | CM_WWNI | 76.01%
503304 | Uplawmoor WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-15 | 2028-10-04 | 2029-02-06 | 2029-10-01 | 2030-01-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 28480.15 | 6687.96 | 0 | 35168.11 | 106831.89 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
501514 | UPLAWMOOR WWTW 1972 NS431552 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-08-19 | 2018-12-20 | 2019-03-15 | 2020-05-15 | 2020-08-14 | East Renfrewshire | 0 | 0 | 69116.28 | 173603.27 | 428299.17 | 820356.37 | 68753 | 1560128.09 | 17167.91 | 1577296 | 0 | [6 empty] | CM_WWNI | 100%
500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-08-14 | 2020-12-10 | Scottish Water Wide | 0 | 14176 | 83616.52 | 235096.48 | 504047 | 728380.78 | 283756.81 | 1849073.59 | 926.42 | 1850000.01 | 700505.53 | [6 empty] | EC01G | 0.1114% | CS16D | 9.192% | EC10H | 45.35% | EC10E | 45.35%
400506 | Upper Muir Street SPS Refurb - SPS000452 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-04-28 | 2011-06-15 | 2011-07-25 | 2012-01-16 |  | South Lanarkshire | 137308.01 | 0 | 0 | 124.77 | 0 | 0 | 0 | 124.77 | 0 | 137432.78 | 0 | [6 empty] | CM_WWNI | 100%
502419 | Uryside Drainage Mitigation Works Design & Build Proposal | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2017-03-30 | 2017-03-30 | 2018-06-01 | 2021-07-30 | 2021-07-30 | Aberdeenshire | 0 | 0 | 0 | 5578.53 | -3090 | 0 | 14837.06 | 17325.59 | 20713.39 | 38038.98 | 136478.56 | [6 empty] | SG1 | 100%
402731 | VACANT - GAP SITE METERING PHASE 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-06-13 | 2012-06-13 | 2012-07-02 | 2015-10-26 |  | Scottish Water Wide | 5168000 | 29924.22 | 0 | 0 | 0 | 0 | 0 | 29924.22 | 0 | 5197924.22 | 0 | [6 empty] | CM_WSI | 100%
500727 | Validation of External Flooding due to Overloading Sewers (EFOS) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS3 | 2016-01-08 | 2016-03-21 | 2016-03-22 | 2020-04-24 | 2020-04-27 | Scottish Water Wide | 0 | 213282.25 | 99529.75 | -85812 | 43479.38 | 74520.62 | 5000 | 350000 | 0 | 350000 | 120964.87 | [6 empty] | CS15A | 100%
500187 | Valleyfield DOA (DOA000204) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-21 | 2016-02-15 | 2018-04-30 | 2018-07-31 | Fife | 0 | 85850 | 101081.21 | 33947 | 35631.81 | 0 | -46.73 | 256463.29 | 0 | 256463.29 | 72047.27 | [6 empty] | CS11 | 45.89% | CS16D | 54.11% | bar: Regulatory Outputs OMG-22
401339 | Various Low Pressure Enhancement Investigations | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-10-31 | 2012-11-29 | 2015-10-15 | 2015-10-15 | Scottish Water Wide | 119774 | -9759.31 | 0 | 0 | 0 | 0 | 0 | -9759.31 | 0 | 110014.69 | 31875 | [6 empty] | CS1 | 100%
3495 | VARIOUS WWTWS - SUPPLY AND INSTALLATION OF FLOW MONITORS | Q&S2 | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2003-05-19 | 2004-02-13 | 2004-05-24 | 2007-12-21 | 2011-03-15 | Scottish Water Wide | 2367792.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2367792.7 | 0 | [6 empty] | EC1/2 | 50% | WQ1/1 | 50%
500096 | Varying Treatment Studies | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS7 | 2015-03-31 | 2017-09-25 | 2017-10-25 | 2018-03-31 | 2019-01-31 | Scottish Water Wide | 0 | 163.55 | 0 | 66297.48 | 5066.53 | 0 | -0.02 | 71527.54 | 0 | 71527.54 | 34072.29 | [6 empty] | CC3S | 100% | [18 empty] | Regulatory Outputs OMG-45: 2
402846 | Vere Terrace Kirkmuirhill Blackwood | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2014-09-04 | 2014-10-20 | 2015-02-11 | 2015-02-11 | South Lanarkshire | 366946 | 87276 | -3771.83 | 0 | 0 | 0 | 0 | 83504.17 | 0 | 450450.17 | 204193.13 | [6 empty] | CS11 | 100%
500678 | Victoria Parade & Milverton Dunoon | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-11-12 | 2022-01-24 | 2022-03-31 | 2023-03-06 | 2023-06-02 | Argyll and Bute-Cowal & Bute | 0 | 23500 | 1339.12 | 4460.88 | 16700 | 104820.01 | 46884.49 | 197704.5 | 425752.53 | 623457.03 | 204193.13 | [6 empty] | CS11 | 100%
500769 | Victoria St Craigellachie Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-27 | 2016-07-20 | 2016-10-24 | 2017-08-24 | 2017-08-24 | Moray | 0 | 30000 | 148446 | 74979 | 258.33 | -843.82 | 0.32 | 252839.83 | 0 | 252839.83 | 0 | [6 empty] | CM_WWI | 100%
502633 | Victory Avenue sewer replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-03-15 | 2018-01-29 | 2018-02-13 | 2018-09-25 | 2018-09-25 | Dumfries and Galloway | 0 | 0 | 2355.14 | 48069.86 | 299033.09 | 20158.39 | -3784.82 | 365831.66 | 188.43 | 366020.09 | 0 | [6 empty] | CM_WWI | 100%
403360 | Viewpark Drive Rutherglen Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-03-04 | 2015-10-15 | 2015-10-15 | 2015-10-15 | 2015-11-02 | South Lanarkshire | 248868 | -248489.1 | 207.4 | 116.69 | 0 | 0 | 0 | -248165.01 | 0 | 702.99 | 204193.13 | [6 empty] | CS11 | 100%
404112 | Vodafone to EE SIM Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-04 | 2015-03-31 | 2015-03-31 | 2016-03-03 |  | Scottish Water Wide | 1174445 | 271.67 | 0 | 0 | 0 | 0 | 0 | 271.67 | 0 | 1174716.67 | 0 | [6 empty] | CM_M&G | 100%
501646 | Voice Networks Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-08-29 | 2017-09-27 | 2017-09-27 | 2020-05-05 | 2020-05-05 | Scottish Water Wide | 0 | 0 | 326336.5 | 1417280.21 | 1716223.4 | 83107.28 | 0.05 | 3542947.44 | 0 | 3542947.44 | 0 |  |  |  |  | -238000 |  | CM_M&G | 100%
504591 | W TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-02-07 | 2022-01-31 | 2022-07-08 | 2024-01-19 | 2024-04-22 | - | 0 | 0 | 0 | 0 | 0 | 1432.61 | 340427.86 | 341860.47 | 0 | 341860.47 | 0 | [6 empty] | CM_WSNI | 100%
502207 | W101 - Oak Mall Hamilton Way Greenock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2017-03-31 | 2017-09-26 | 2018-01-08 | 2018-11-30 | 2018-11-30 | Inverclyde | 0 | 0 | 386909.09 | 1405261.71 | 1102047.2 | 0 | 609 | 2894827 | 0 | 2894827 | 196097.17 | [6 empty] | CS11A | 100%
503074 | W101 - Oak Mall Hamilton Way Greenock (1B) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2019-05-20 | 2021-02-08 | 2021-04-21 | 2021-09-17 | 2021-12-20 | Inverclyde | 0 | 0 | 0 | 20930.23 | 25069.77 | 181440 | 347707.07 | 575147.07 | 355852.93 | 931000 | 196097.17 | [6 empty] | CS11A | 100%
500664 | W172 - Annbank Road Mossblown | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS0 | 2019-02-08 | 2021-10-18 | 2022-05-19 | 2023-05-30 | 2023-08-30 | South Ayrshire | 0 | 30430 | 49600 | 74891.1 | 135923.9 | 45498.13 | 39622.66 | 375965.79 | 346194.21 | 722160 | 2702815.6 | [6 empty] | CS11 | 100%
500301 | W20 - 7 Nether Walk Mauchline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-06-07 | 2019-06-07 | East Ayrshire | 0 | 23813 | 70425.89 | 31649.57 | 26111.54 | -149793.87 | -2205.13 | 1 | 0 | 1 | 204193.13 | [6 empty] | CS11 | 50% | CS15 | 50%
501543 | W250 - Milngavie Road Bearsden Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-02-14 | 2020-07-09 | East Dunbartonshire | 0 | 22930 | 25661.23 | 111223.27 | 190518.14 | 84014.82 | -20577.8 | 413769.66 | 0 | 413769.66 | 204193.13 | [6 empty] | CS11 | 100%
503538 | W335 Viewpark Road Motherwell (SR15) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW0 | 2021-02-04 | 2021-12-27 | 2022-03-14 | 2022-11-04 | 2023-02-06 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 55161.12 | 60410.31 | 115571.43 | 2288353.56 | 2403924.99 | 1469853.01 | [6 empty] | CS11 | 100%
500302 | W462 - Coalburn Road Coalburn | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-10-08 | 2020-03-18 | 2020-03-30 | 2021-01-19 | 2021-04-07 | South Lanarkshire | 0 | 58000 | 74971.65 | 44021.64 | 92898.71 | 346847 | 1183560.67 | 1800299.67 | 11989.7 | 1812289.37 | 204193.13 |  |  |  |  | 12150 |  | CS11 | 100%
500017 | W473 - Conon Avenue | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-12-07 | 2019-07-15 | 2019-09-23 | 2021-01-12 | 2021-04-15 | East Dunbartonshire | 0 | 35685.64 | 81314.36 | 100000 | 547559 | 4142952 | 1313008 | 6220519 | 156989.03 | 6377508.03 | 1913792.83 |  |  |  |  | 1980 |  | CS11 | 100%
501020 | W481 - Moncrieff Avenue Lenzie Kirkintilloch Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-05-09 | 2019-05-09 | East Dunbartonshire | 0 | 21930 | 46086 | 73251.05 | 6870.1 | -148085.95 | -50.19 | 1.01 | 0 | 1.01 | 204193.13 | [6 empty] | CS11 | 100%
502327 | W571 - Dolphin Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2020-11-30 | 2021-12-06 | 2022-02-25 | 2022-07-13 | 2022-10-11 | Glasgow City | 0 | 0 | 44060.47 | 27939.53 | 80004.91 | 58441.51 | 56926.93 | 267373.35 | 1532626.73 | 1800000.08 | 196097.17 | [6 empty] | CS11A | 100%
502375 | W574 1-21 Clarkston Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2019-07-02 | 2021-04-05 | 2021-07-07 | 2021-11-25 | 2022-03-11 | Glasgow City | 0 | 0 | 0 | 57000 | 58000 | 163965 | 174302.44 | 453267.44 | 211732.56 | 665000 | 196097.17 | [6 empty] | CS11A | 100%
502907 | W574 Clarkston Road Flooding - Short Term Solution | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | Glasgow City | 0 | 0 | 0 | 12000 | -756.6 | 0 | 0.01 | 11243.41 | 0 | 11243.41 | 196097.17 | [6 empty] | CS11A | 100%
500913 | W6 - Fisher Avenue Kilsyth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-11-22 | 2019-08-27 | 2019-09-24 | 2020-04-29 | 2020-08-04 | Glasgow City | 0 | 341602 | 52835.14 | 33478.9 | 124988.96 | 356849.98 | 27222.19 | 936977.17 | 441.83 | 937419 | 204193.13 |  |  |  |  | 290 |  | CS11 | 100%
502887 | W630 - High Street Mauchline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2021-04-01 | 2021-04-01 | 2020-02-03 | 2021-04-01 | 2021-04-01 | East Ayrshire | 0 | 0 | 0 | 42398.14 | 54601.86 | 16367.02 | 0.01 | 113367.03 | 0 | 113367.03 | 196097.17 | [6 empty] | CS11A | 100%
500662 | W646 - Brandon Gardens Prestwick | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2020-02-19 | 2020-08-24 | 2020-10-26 | 2021-03-01 | 2021-03-30 | South Ayrshire | 0 | 23500 | 17530.23 | 28343.4 | 73626.37 | 677844.89 | 957955.11 | 1778800 | 21200 | 1800000 | 304107.44 | [6 empty] | CS11 | 100%
502689 | W691 - Geilston Park Cardross | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-28 | 2021-12-24 | 2022-03-15 | 2022-10-17 | 2023-01-17 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 58628.26 | 21598.74 | 32845.09 | 79880.76 | 192952.85 | 407047.15 | 600000 | 196097.17 | [6 empty] | CS11A | 100%
501191 | W701 3 Glen Road Shotts | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-02-25 | 2019-02-25 | North Lanarkshire | 0 | 23611 | 13419.23 | 32525.91 | 13266.8 | 0.23 | -0.23 | 82822.94 | 0 | 82822.94 | 204193.13 | [6 empty] | CS11 | 100%
502410 | W775 - Dumbarton Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-02-25 | 2019-02-25 | West Dunbartonshire | 0 | 0 | 12465.12 | 13534.88 | -24650.14 | 1924.47 | -3273.33 | 1 | 0 | 1 | 196097.17 | [6 empty] | CS11A | 100%
501542 | W92 - Buchlyvie Road Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-12-17 | 2019-08-29 | 2019-10-07 | 2020-04-01 | 2020-06-23 | Renfrewshire | 0 | 29855 | 48219.66 | 31925.34 | 159371 | 574158 | 8765.54 | 852294.54 | 3431.29 | 855725.83 | 400290.3 |  |  |  |  | 4870 |  | CS11A | 33.33% | CS11 | 66.67%
500941 | Walker Street Paisley Survey & Reline Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2017-10-27 | 2017-12-01 | 2018-03-22 | 2018-03-22 | Renfrewshire | 0 | 6000 | 4544 | 102040.47 | 23631.92 | -0.39 | 0 | 136216 | 0 | 136216 | 0 | [6 empty] | CM_WWI | 100%
502602 | Wallyford - WIA Network Reinforcements | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 | 2019-09-18 | 2019-09-18 | 2020-09-21 | 2022-01-04 | 2022-03-29 | East Lothian | 0 | 0 | 0 | 0 | 0 | 39775.7 | 568224.3 | 608000 | 0 | 608000 | 470181.23 | [6 empty] | WG5 | 100%
501689 | WAN Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2020-07-14 | 2020-07-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 375217.61 | 372240.01 | 5000 | 752457.62 | 0 | 752457.62 | 0 |  |  |  |  | 354057.8 |  | CM_M&G | 100%
500439 | Waste East SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 2019-07-05 | 2019-07-05 | All East Unitary Authorities | 0 | 101933 | 804842.88 | 533492.38 | 281392.88 | 121853.3 | -1219.98 | 1842294.46 | 0 | 1842294.46 | 0 | [6 empty] | CM_WWNI | 100%
500440 | Waste East SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2015-11-25 | 2015-11-26 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWNI | 100%
500441 | Waste East SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2016-11-23 | 2017-02-07 | All East Unitary Authorities | 0 | 1095069 | 215104.32 | 126.21 | 0 | 0 | -126.21 | 1310173.32 | 0 | 1310173.32 | 0 | [6 empty] | CM_WWNI | 100%
500442 | Waste East WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2018-12-19 | 2018-12-19 | All East Unitary Authorities | 0 | 711824 | 1420372.47 | 1486222.83 | -600528.43 | 4385.24 | -3019.76 | 3019256.35 | 0 | 3019256.35 | 0 | [6 empty] | CM_WWNI | 100%
500443 | Waste East WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-11-26 | 2015-11-26 | All East Unitary Authorities | 0 | 59.06 | 0 | 0 | 0 | 0 | 0 | 59.06 | 0 | 59.06 | 0 | [6 empty] | CM_WWNI | 100%
500444 | Waste East WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-05-17 | 2017-05-17 | All East Unitary Authorities | 0 | 3175049.85 | 703786.15 | 53107.6 | 0 | 0 | -23.11 | 3931920.49 | 0 | 3931920.49 | 0 | [6 empty] | CM_WWNI | 100%
500445 | Waste North Infra MD SVCW SR 15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-21 | 2017-02-21 | All North Unitary Authorities | 0 | 108943 | 111609.62 | 3626.3 | 0 | 0 | 0 | 224178.92 | 0 | 224178.92 | 0 | [6 empty] | CM_WWI | 100%
500446 | Waste North Infra OPS SVCW SR 15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 | 2015-08-21 | All North Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWI | 100%
500447 | Waste North Infra SWD SVCW SR 15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-19 | 2017-01-19 | All North Unitary Authorities | 0 | 547194 | 93210.28 | 0 | 0 | 0 | 0 | 640404.28 | 0 | 640404.28 | 0 | [6 empty] | CM_WWI | 100%
500448 | Waste North SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-13 | 2015-05-13 | 2015-05-13 | 2017-02-01 | 2017-02-01 | All North Unitary Authorities | 0 | 8420 | 291866.13 | 352.25 | 0 | 0 | 0 | 300638.38 | 0 | 300638.38 | 0 | [6 empty] | CM_WWNI | 100%
500449 | Waste North SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 | 2015-08-21 | All North Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWNI | 100%
500450 | Waste North SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2017-01-19 | 2017-01-19 | All North Unitary Authorities | 0 | 694036.16 | 139180.94 | 2332 | 0 | 0 | 0 | 835549.1 | 0 | 835549.1 | 0 | [6 empty] | CM_WWNI | 100%
500451 | Waste North WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-08 | 2017-08-10 | 2017-08-10 | All North Unitary Authorities | 0 | 578912 | 466341.71 | 55571.52 | 0 | 0 | 0.03 | 1100825.26 | 0 | 1100825.26 | 0 | [6 empty] | CM_WWNI | 100%
500452 | Waste North WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 | 2015-08-03 | All North Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWNI | 100%
500453 | Waste North WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-19 | 2017-01-19 | All North Unitary Authorities | 0 | 2532790 | 310809.16 | 23984.78 | 0 | 0 | 0 | 2867583.94 | 0 | 2867583.94 | 0 | [6 empty] | CM_WWNI | 100%
500454 | Waste South Infra MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-20 | 2017-02-20 | All South Unitary Authorities | 0 | 1162069 | 772870.46 | -215007.27 | 0 | 0 | -20.8 | 1719911.39 | 0 | 1719911.39 | 0 | [6 empty] | CM_WWI | 100%
500455 | Waste South Infra OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 1335925 | -82223.9 | 18645.28 | 0 | 0 | 0 | 1272346.38 | 0 | 1272346.38 | 0 | [6 empty] | CM_WWI | 100%
500456 | Waste South Infra SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 538257 | -538257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
500457 | Waste South SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-20 | 2017-02-20 | All South Unitary Authorities | 0 | 768013 | 1402632.3 | 70694.47 | 4310.56 | 0 | -84.62 | 2245565.71 | 0 | 2245565.71 | 0 | [6 empty] | CM_WWNI | 100%
500458 | Waste South SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 565459.64 | 218822.43 | 10099.74 | 0 | 43.06 | -43.06 | 794381.81 | 0 | 794381.81 | 0 | [6 empty] | CM_WWNI | 100%
500459 | Waste South SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWNI | 100%
500460 | Waste South WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-29 | 2017-03-21 | 2017-03-21 | All South Unitary Authorities | 0 | 2085118 | 1850463.43 | -9132.43 | 0 | 0 | 716.91 | 3927165.91 | 0 | 3927165.91 | 0 | [6 empty] | CM_WWNI | 100%
500461 | Waste South WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 2596838.58 | 927113.79 | 20053.27 | 18.22 | 0 | 0.01 | 3544023.87 | 0 | 3544023.87 | 0 | [6 empty] | CM_WWNI | 100%
500462 | Waste South WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2018-09-19 | 2018-09-19 | All South Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWNI | 100%
401136 | Waste Water CAR License Variation - North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-07-01 | 2010-07-01 | 2011-05-02 | 2016-01-13 |  | All North Unitary Authorities | 45998.58 | -6120 | 4602.75 | 0 | 0 | 0 | 0 | -1517.25 | 0 | 44481.33 | 0 | [6 empty] | CM_WWI | 100%
403306 | Waste Water DOA Telemetry Schematics Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-14 | 2013-11-05 | 2013-11-06 | 2016-01-28 |  | Scottish Water Wide | 637205 | -17916.95 | 16.14 | 0 | 0 | 0 | 0 | -17900.81 | 0 | 619304.19 | 0 | [6 empty] | CM_WWNI | 100%
503150 | Waste Water Energy Improvement Programme FOP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2018-03-29 | 2018-03-29 | 2018-09-03 | 2021-04-29 | 2021-04-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1056012.95 | 1530172.42 | -33450.03 | 2552735.34 | 5298.81 | 2558034.15 | 0 |  |  |  |  | -204000 |  | CM_WWNI | 100%
501786 | Waste Water Lifting Chains | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-02 | 2028-08-08 | 2028-12-12 | 2030-03-11 | 2030-06-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 12193.91 | 12193.91 | 241943.09 | 254137 | 0 | [6 empty] | CM_WWNI | 100%
402530 | Waste Water Pipe Bridges - HS Assessment - Remedials Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-09 | 2013-10-29 | 2013-11-08 | 2014-11-28 |  | Scottish Water Wide | 597701 | 20591 | -1379.64 | 0 | 0 | 0 | 0 | 19211.36 | 0 | 616912.36 | 0 | [6 empty] | CM_M&G | 100%
500463 | Waste West Infra MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2018-07-10 | 2018-07-10 | All West Unitary Authorities | 0 | 122076 | 359263.45 | 206931.01 | 7628.77 | 0 | 0 | 695899.23 | 0 | 695899.23 | 0 | [6 empty] | CM_WWI | 100%
500464 | Waste West Infra OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-02 | 2017-09-01 | All West Unitary Authorities | 0 | 1131944.59 | 68297.16 | -77608.44 | 0 | 0 | 0 | 1122633.31 | 0 | 1122633.31 | 0 | [6 empty] | CM_WWI | 100%
500465 | Waste West Infra SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-16 | 2017-09-01 | All West Unitary Authorities | 0 | 82196 | -60900.49 | 0 | 0 | 0 | 0 | 21295.51 | 0 | 21295.51 | 0 | [6 empty] | CM_WWI | 100%
500466 | Waste West SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2019-06-12 | 2019-06-12 | All West Unitary Authorities | 0 | 106735 | 427628.57 | 285937.5 | -7590.92 | 1226.47 | 0.01 | 813936.63 | 0 | 813936.63 | 0 | [6 empty] | CM_WWNI | 100%
500467 | Waste West SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-01-17 | 2018-01-17 | All West Unitary Authorities | 0 | 1438300 | 541198.46 | -277.96 | 0 | 0 | 52521.23 | 2031741.73 | 0 | 2031741.73 | 0 | [6 empty] | CM_WWI | 100%
403376 | Waste West SPS OPS SVCW QSIV - 4033760000 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2017-03-03 |  | All West Unitary Authorities | 6215000 | 675425 | 20377.03 | -41861.48 | 0 | 0 | 71541.04 | 725481.59 | 0 | 6940481.59 | 0 | [6 empty] | CM_WWI | 100%
500468 | Waste West SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-15 | 2015-04-15 | 2015-04-15 | 2017-01-02 | 2018-01-02 | All West Unitary Authorities | 0 | 46252 | -16108.07 | -2439.93 | 0 | 0 | 0 | 27704 | 0 | 27704 | 0 | [6 empty] | CM_WWNI | 100%
500469 | Waste West WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2019-05-08 | 2019-05-08 | All West Unitary Authorities | 0 | 649389 | 1105633.37 | 635561.76 | -33020.57 | -13873.92 | -259.8 | 2343429.84 | 0 | 2343429.84 | 0 | [6 empty] | CM_WWNI | 100%
500470 | Waste West WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-17 | 2018-01-15 | All West Unitary Authorities | 0 | 3903196.55 | 1089666.73 | -1072781.69 | 0 | 0 | 0 | 3920081.59 | 0 | 3920081.59 | 0 | [6 empty] | CM_WWNI | 100%
500471 | Waste West WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-17 | 2018-01-17 | All West Unitary Authorities | 0 | 305166.13 | 67274.19 | 9826.12 | 0 | 0 | 0 | 382266.44 | 0 | 382266.44 | 0 | [6 empty] | CM_WWNI | 100%
502722 | Wastewater Asset Capability | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-03-24 | Scottish Water Wide | 0 | 0 | 0 | 259404.71 | 280625.1 | 112971.6 | 3909.6 | 656911.01 | 0 | 656911.01 | 0 | [6 empty] | CM_WWNI | 100%
500065 | Wastewater Security - Site Risk Assessments and Survey and Scoping Studies | Q&S4 | Protecting and enhancing the environment | Scottish Government Requirements |  |  | Wastewater |  | SWD | Scottish Government Requirements | MS7 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | Scottish Water Wide | 0 | 21986.16 | 0 | 0 | 0 | 0 | -135 | 21851.16 | 0 | 21851.16 | 0 | [6 empty] | EC21D | 100%
403771 | Water & Waste Water Chemical Dosing Systems - Improvements at High Priority Sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2014-04-25 | 2014-10-15 | 2014-10-08 | 2020-04-06 |  | Scottish Water Wide | 3034266 | 6061547 | 3222277.44 | 1525021.1 | 325443.89 | 225924.75 | 30726.49 | 11390940.67 | 9219.71 | 14434426.38 | 0 | [6 empty] | CM_M&G | 100%
402052 | Water Balance Field Trough Studies | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2014-04-16 | 2014-04-16 | 2015-10-30 |  | Scottish Water Wide | 122490 | 3108.57 | 0 | 0 | 0 | 0 | 0 | 3108.57 | 0 | 125598.57 | 0 | [6 empty] | CM_WSI | 100%
402055 | Water Balance Model Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2014-11-03 | 2014-11-03 | 2015-10-30 |  | Scottish Water Wide | 33640 | 8787.44 | 0 | 0 | 0 | 0 | 0 | 8787.44 | 0 | 42427.44 | 0 | [6 empty] | CM_WSI | 100%
402057 | Water Balance Property Count | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2015-11-13 | 2016-02-29 | 2015-10-30 |  | Scottish Water Wide | 5690.39 | -592.93 | 0 | 0 | 0 | 0 | 0 | -592.93 | 0 | 5097.46 | 0 | [6 empty] | CM_WSI | 100%
402049 | Water Balance Service Reservoir Leakage Estimation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-20 | 2015-01-23 | 2015-01-23 | 2015-10-30 |  | Scottish Water Wide | 13453 | -241.04 | 0 | 0 | 0 | 0 | 0 | -241.04 | 0 | 13211.96 | 0 | [6 empty] | CM_WSI | 100%
402050 | Water Balance Trunk Mains Leakage Estimation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2015-11-13 | 2016-02-01 | 2015-10-30 |  | Scottish Water Wide | 39034.83 | -334.65 | 0 | 0 | 0 | 0 | 0 | -334.65 | 0 | 38700.18 | 0 | [6 empty] | CM_WSI | 100%
401974 | Water Balance WwTW Potable Water Consumption | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-02-15 | 2011-08-02 | 2011-08-02 | 2015-10-30 |  | Scottish Water Wide | 114252.1 | -79.92 | 0 | 0 | 0 | 0 | 0 | -79.92 | 0 | 114172.18 | 0 | [6 empty] | CM_WSI | 100%
503572 | Water Byelaw Compliance at SW Assets - Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-09-17 | 2020-02-21 | 2020-07-07 | 2021-08-20 | 2021-10-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 293201.52 | 2583629.08 | 2876830.6 | 123969.41 | 3000800.01 | 0 | [6 empty] | CM_WWNI | 100%
502188 | Water bylaws Compliance at SW Assets- Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-04 | 2017-04-27 | 2017-05-15 | 2018-02-14 | 2018-02-14 | Scottish Water Wide | 0 | 0 | 72419.76 | 651751.14 | -10067.21 | 0 | 0.01 | 714103.7 | 0 | 714103.7 | 0 | [6 empty] | CM_WSNI | 9.911% | CM_WWNI | 90.09%
502325 | Water bylaws Compliance at SW Assets- Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-27 | 2017-05-23 | 2017-07-19 | 2018-12-18 | 2018-12-18 | Scottish Water Wide | 0 | 0 | 9438.82 | 270716.72 | 221358.01 | 14262.57 | 3675.59 | 519451.71 | 0 | 519451.71 | 0 | [6 empty] | CM_WWNI | 48% | CM_WSNI | 52%
503053 | Water Central- DWQR Chloramination & Chemical Dosing Flow Switches Inspections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-02-26 | 2018-02-26 | 2018-03-05 | 2018-03-20 | 2018-03-20 | Scottish Water Wide | 0 | 0 | 0 | 291484.71 | 0 | 0 | 0 | 291484.71 | 0 | 291484.71 | 0 | [6 empty] | CM_WSNI | 100%
500431 | Water Efficiency Advice and Water Saving Packs and Trials | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice |  |  | Water |  | SWD | Efficency Advice | MS3 | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 118343 | 188916.58 | 139547.49 | 153589.93 | 121828.67 | 85974.46 | 808200.13 | 2799.86 | 810999.99 | 673425.52 | [6 empty] | CS18W | 100%
402771 | Water Efficiency Trial | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2012-07-09 | 2014-04-29 | 2014-04-29 | 2016-05-06 | 2016-06-09 | Scottish Water Wide | 1400000 | -48721.45 | 142.35 | 871.72 | 0 | 0 | -871.72 | -48579.1 | 0 | 1351420.9 | 0 | [6 empty] | CS19 | 100%
503202 | Water Mains Flooding Risk Assessment | Q&S4 | Improving the customer experience | Customer Experience Studies |  |  | Wastewater |  | SWD | Customer Experience Studies | MS0 | 2019-09-09 | 2020-07-20 | 2020-10-08 | 2021-02-25 | 2021-05-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 19302.22 | 52068.51 | 162903.95 | 234274.68 | 10164.76 | 244439.44 | 1106452.62 | [6 empty] | CS17_S | 100%
500636 | Water Network Model Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-02 | 2015-11-02 | 2015-12-01 | 2021-04-06 | 2021-06-30 | Scottish Water Wide | 0 | 247489 | 928755.72 | 465090.96 | 317056.61 | 158645.67 | 112748 | 2229785.96 | 42709.09 | 2272495.05 | 0 | [6 empty] | CM_WSI | 100%
500473 | Water of Leith Strategic Solution Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-03-01 | 2016-03-14 | 2018-11-30 | 2019-08-31 | City of Edinburgh | 0 | 121378 | 273843.73 | 435256.27 | 550968 | 49242.04 | 0.01 | 1430688.05 | 0 | 1430688.05 | 203233.4 | [6 empty] | EC01D | 50% | EC10E | 50% | bar: Regulatory Outputs OMG-23
400113 | Water of Leith Strategic Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-02-23 | 2011-01-17 | 2011-01-17 | 2013-03-13 | 2013-05-14 | City of Edinburgh | 338663.04 | 0 | 0 | 1081.74 | 1541.97 | 0 | -2623.71 | 0 | 0 | 338663.04 | 0 | [6 empty] | EC04C | 100%
502764 | WATER OF LEITH UIDs - BATCH 6.2 - Colinton Rd @ St Cuthberts Court CSO. | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-02 | 2021-01-25 | 2021-03-22 | 2021-09-01 | 2021-09-01 | City of Edinburgh | 0 | 0 | 0 | 82811 | 50783 | 32702 | 46815.73 | 213111.73 | 298527.62 | 511639.35 | 110096.49 | [6 empty] | EC01F | 100%
502751 | WATER OF LEITH UIDs - BATCH 0 - 2 x STUDY OUTPUTS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-05-31 | 2017-10-30 | City of Edinburgh | 0 | 0 | 0 | 48304.64 | 0 | 0 | 0 | 48304.64 | 0 | 48304.64 | 110096.49 | [6 empty] | EC01F | 100%
502740 | WATER OF LEITH UIDs - BATCH 1 - South Gyle Gogarloch SPS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-05-31 | 2019-03-27 | 2020-02-24 | 2020-09-23 | 2020-12-31 | City of Edinburgh | 0 | 0 | 0 | 54066 | 2638 | 58426 | 6059 | 121189 | 2478 | 123667 | 110096.49 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-10-31 | 2020-03-31 | 2020-03-31 | 2021-04-01 | 2021-07-08 | City of Edinburgh | 0 | 0 | 0 | 125823 | 17418 | 168480.53 | 1288598.79 | 1600320.32 | 64616.52 | 1664936.84 | 110096.49 |  |  |  |  | 2990 |  | EC01F | 100%
502750 | WATER OF LEITH UIDs - BATCH 11 - Curriehill Storm Tank CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2017-10-24 | 2017-12-19 | 2018-01-17 | 2018-01-31 | 2018-05-31 | City of Edinburgh | 0 | 0 | 0 | 42645.34 | 108592.01 | 0 | 0 | 151237.35 | 0 | 151237.35 | 220192.97 | [6 empty] | EC10B | 50% | EC01F | 50% | bar: Regulatory Outputs OMG-18
502741 | WATER OF LEITH UIDs - BATCH 2 - Currie Old Mill Off Lanark Road CSO and Juniper Green | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-06-01 | 2020-01-29 | 2020-03-23 | 2020-09-01 | 2020-12-02 | City of Edinburgh | 0 | 0 | 0 | 113342 | 23332 | 155261 | 269921.73 | 561856.73 | 1399.41 | 563256.14 | 110096.49 |  |  |  |  | 3040 |  | EC01F | 100%
502742 | WATER OF LEITH UIDs - BATCH 3 - Juniper Green Off Lanark Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-06-01 | 2020-01-21 | 2020-02-24 | 2021-01-31 | 2021-05-31 | City of Edinburgh | 0 | 0 | 0 | 93222 | 29088 | 175051.92 | 298638.63 | 596000.55 | 3935.41 | 599935.96 | 110096.49 |  |  |  |  | 2040 |  | EC01F | 100% | bar: Regulatory Outputs OMG-18
502743 | WATER OF LEITH UIDs - BATCH 4 - Balerno Bridge Road CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-06-02 | 2020-03-31 | 2020-03-31 | 2021-10-31 | 2022-01-31 | City of Edinburgh | 0 | 0 | 0 | 118843 | 64688 | 144280 | 754811.06 | 1082622.06 | 175546.79 | 1258168.85 | 110096.49 |  |  |  |  | 2990 |  | EC01F | 100% | bar: Regulatory Outputs OMG-18
502744 | WATER OF LEITH UIDs - BATCH 5 - Currie Kinauld Farm CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS1 | 2017-06-02 | 2020-06-15 | 2020-08-24 | 2021-07-06 | 2021-07-06 | City of Edinburgh | 0 | 0 | 0 | 101315 | 21298 | 90482 | 193908.5 | 407003.5 | 76380.53 | 483384.03 | 110096.49 |  |  |  |  | 2950 |  | EC01F | 100%
502745 | WATER OF LEITH UIDs - BATCH 6.1 - Colinton Redford Drive CSO No. 2 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2017-06-02 | 2019-08-21 | 2019-09-02 | 2019-09-19 | 2019-09-19 | City of Edinburgh | 0 | 0 | 0 | 120424 | 39702 | 17416.14 | 0.44 | 177542.58 | 0 | 177542.58 | 110096.49 | [6 empty] | EC01F | 100%
502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-10-30 | 2020-12-14 | 2021-02-08 | 2021-11-10 | 2022-02-24 | City of Edinburgh | 0 | 0 | 0 | 206894 | 109276 | 56477 | 560410.37 | 933057.37 | 1095867.82 | 2028925.19 | 110096.49 | [6 empty] | EC01F | 100%
502747 | WATER OF LEITH UIDs - BATCH 8 - Kingsknowe R-O 29 Dovecot Grove CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-10-31 | 2020-02-17 | 2020-03-23 | 2021-02-28 | 2021-05-31 | City of Edinburgh | 0 | 0 | 0 | 107885 | 44340 | 278608 | 507286.91 | 938119.91 | 0 | 938119.91 | 110096.49 |  |  |  |  | 2950 |  | EC01F | 100% | bar: Regulatory Outputs OMG-18
502748 | WATER OF LEITH UIDs - BATCH 9.1 - Currie Kinleith Ind Est CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2017-10-30 | 2020-03-31 | 2020-03-31 | 2021-02-28 | 2021-05-31 | City of Edinburgh | 0 | 0 | 0 | 88031 | 28114 | 84699 | 222601.26 | 423445.26 | 0 | 423445.26 | 110096.49 |  |  |  |  | 2270 |  | EC01F | 100% | bar: Regulatory Outputs OMG-18
502765 | WATER OF LEITH UIDs - BATCH 9.2 - Currie GDN 2A Lanark Road West CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS2 | 2017-10-31 | 2020-03-31 | 2020-10-19 | 2021-04-27 | 2021-07-30 | City of Edinburgh | 0 | 0 | 0 | 130610 | 89354 | 70649 | 342969.88 | 633582.88 | 25311.15 | 658894.03 | 110096.49 |  |  |  |  | 2990 |  | EC01F | 100% | bar: Regulatory Outputs OMG-18
503256 | Water Quality Improvement - Greenock Phase 2 - Conditioning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-06-28 | 2019-09-03 | 2021-02-28 | 2021-04-30 | Inverclyde | 0 | 0 | 0 | 0 | 326478 | 180663.11 | 152368.25 | 659509.36 | -7170.37 | 652338.99 | 701384.22 | [6 empty] | DW5MC | 100% | [18 empty] | Regulatory Outputs OMG-06: 65.78
503257 | Water Quality Improvement - Greenock Phase 2 - Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-05-29 | 2019-09-06 | 2021-02-26 | 2021-06-30 | Inverclyde | 0 | 0 | 0 | 0 | 275220 | 387708.86 | 520024.49 | 1182953.35 | -4572.29 | 1178381.06 | 254657.2 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 212.3512
503355 | Water Quality Improvement- Afton RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2020-04-01 | 2020-04-01 | 2020-03-23 | 2020-03-23 | 2020-08-03 | East Ayrshire | 0 | 0 | 0 | 0 | 45627.91 | 63372.09 | 4097224.52 | 4206224.52 | 138081.48 | 4344306 | 0 | [6 empty] | DW5FS | 100%
503193 | Water Quality Improvement- Amlaird Flushing RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2018-12-21 | 2019-03-28 | 2020-07-31 | 2021-07-31 | East Ayrshire | 0 | 0 | 0 | 0 | 227645.55 | 174789.5 | 41547.97 | 443983.02 | 0 | 443983.02 | 0 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 84.152
503336 | Water Quality Improvement-Wick East DMA | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS0 | 2018-06-28 | 2020-04-13 | 2020-07-06 | 2021-02-28 | 2022-02-28 | Highland | 0 | 0 | 0 | 0 | 40498.94 | 361218.39 | 1875264.98 | 2276982.31 | 1467642.91 | 3744625.22 | 1805010.12 | [6 empty] | DW5MR | 100% | bar: Regulatory Outputs OMG-02
501184 | Water Quality Investigation into Deteriorating Cast Iron Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-04 | 2016-04-12 | 2016-04-18 | 2017-01-31 | 2017-07-31 | Scottish Water Wide | 0 | 3262 | 82693.21 | 8520.78 | 7116.56 | 0 | 1713.62 | 103306.17 | 0 | 103306.17 | 0 | [6 empty] | DW5A | 100% | bar: Regulatory Outputs OMG-47
402613 | Water Quality OPA Action Plan - Central | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-05-01 | 2014-08-04 |  | Scottish Water Wide | 9898107.1 | -238 | 0 | 0 | 0 | 0 | 238 | 0 | 0 | 9898107.1 | 0 |  |  |  |  | 156863 |  | CM_WSNI | 100%
403794 | Water Quality OPA Action Plan - Central Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-05-19 | 2014-06-25 | 2014-06-25 | 2015-09-11 |  | Scottish Water Wide | 2005500 | 149372.52 | 0 | 0 | 0 | 0 | 0 | 149372.52 | 0 | 2154872.52 | 0 | [6 empty] | CM_WSNI | 100%
402612 | Water Quality OPA Action Plan - North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-22 | 2012-03-22 | 2012-04-02 | 2015-01-23 |  | All North Unitary Authorities | 269091.86 | 281.81 | 0 | 0 | 0 | 0 | 0 | 281.81 | 0 | 269373.67 | 0 | [6 empty] | CM_WSNI | 100%
500623 | Water Service Strategy GM SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 243588.37 | 549819.68 | 931123.56 | 1140392.35 | 425620.08 | 833568.22 | 4124112.26 | 135697.13 | 4259809.39 | 0 | [6 empty] | CM_OVH | 100%
502673 | Waternish WOA - Geary DMA - Mains Renewal - WQ pH Issue | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-02 | 2028-01-25 | 2028-04-11 | 2028-11-07 | 2029-02-07 | Highland | 0 | 0 | 0 | 13509.54 | 1394.34 | 6833.84 | 13960.57 | 35698.29 | 501301.65 | 536999.94 | 0 | [6 empty] | CM_WSI | 100%
502625 | Waternish WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2027-04-02 | 2030-11-01 | 2031-01-07 | 2031-12-16 | 2032-03-17 | Highland | 0 | 0 | 20930.23 | 207.95 | 2310.72 | 23177.29 | -40195.68 | 6430.51 | 0 | 6430.51 | 136478.56 | [6 empty] | WG1 | 100%
45573 | Waternish WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-11 | 2011-07-22 | 2012-01-16 | 2012-03-14 | Highland | 183693.07 | 76.2 | 0 | 0 | 0 | 0 | 0 | 76.2 | 0 | 183769.27 | 0 | [6 empty] | DW13 | 100%
502433 | Waulkmill Glen & Ryat Linn MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-01-31 | 2018-01-31 | 2018-03-01 | 2019-01-11 | 2019-01-11 | East Renfrewshire | 0 | 0 | 0 | 63084.25 | 373377.58 | -17759.25 | 0.01 | 418702.59 | 0 | 418702.59 | 0 | [6 empty] | CM_WSI | 100%
404104 | Waulkmillglen Reservoir - Various IoS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-03-06 | 2015-12-11 | 2015-12-14 | 2016-01-05 | 2016-01-05 | East Renfrewshire | 19.98 | 340555.88 | 0 | 0 | 0 | 0 | 0 | 340555.88 | 0 | 340575.86 | 0 | [6 empty] | CM_WSI | 100%
403080 | Wellbank WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-12-10 | 2014-09-18 | 2014-11-28 | 2015-08-27 | 2015-08-28 | Angus | 829865 | 321825 | 19998.62 | 16318.66 | 0 | 0 | 102.99 | 358245.27 | 0 | 1188110.27 | 0 | [6 empty] | SG1 | 100%
503611 | Wellington WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-02-03 | 2023-09-13 | 2024-01-16 | 2025-08-11 | 2025-10-02 | Midlothian | 0 | 0 | 0 | 0 | 0 | 62675.58 | 79427.61 | 142103.19 | 1886690.81 | 2028794 | 136478.56 | [6 empty] | SG1 | 100%
504254 | W-E-NI-09122019-BADENTINAN RWI-Investigation into installing standby generator (5591) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-04-01 |  | 2020-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 2836.11 | -942.54 | 1893.57 | 0 | 1893.57 | 0 | [6 empty] | CM_WSI | 100%
403636 | West Area CMC Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-12-30 | 2013-12-30 | 2014-07-02 | 2017-03-06 |  | All West Unitary Authorities | 368488 | 32630 | -3266.53 | -16.72 | 0 | 0 | 0 | 29346.75 | 0 | 397834.75 | 0 | [6 empty] | CM_WSI | 100%
404032 | West Coast Weather Incident - Burn & River crossing & intake reinstatement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-12-05 | 2014-12-05 | 2015-01-19 | 2015-11-06 |  | Highland | 153993 | 142499 | -0.05 | -2158.28 | 0 | 0 | 0 | 140340.67 | 0 | 294333.67 | 0 | [6 empty] | CM_WSI | 100%
500766 | West John Street Arbroath Replace Gravity Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2016-06-16 | 2016-08-23 | 2017-03-23 | 2017-03-23 | Angus | 0 | 37000 | 336649 | 9353 | 1422.58 | 0 | 0.42 | 384425 | 0 | 384425 | 0 | [6 empty] | CM_WWI | 100%
400761 | West Leak Detection Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 266000 | -35171.29 | 0 | 0 | 0 | 0 | 0 | -35171.29 | 0 | 230828.71 | 0 | [6 empty] | CM_WSI | 100%
503425 | West Lewis - WG4 - Improvement to Supply-Demand Balance | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS0 | 2016-03-29 | 2021-01-18 | 2021-02-09 | 2021-12-20 | 2022-03-22 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 62500 | 81161.46 | 391629.03 | 535290.49 | 729253.51 | 1264544 | 258568.71 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
401404 | West Lewis Water Rehab Cluster Project Isle of Lewis | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-13 | 2014-03-27 | 2014-05-07 | 2015-12-01 |  | Na H-Eileanan an Iar | 353440 | 44151.24 | 2287.23 | 0 | 0 | 0 | 0 | 46438.47 | 0 | 399878.47 | 0 | [6 empty] | CM_WSI | 100%
500884 | West Lewis Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-06-11 | 2020-02-28 | Na H-Eileanan an Iar | 0 | 4355.08 | 10309.92 | 9115.35 | 40172.78 | 37288.87 | -2076.13 | 99165.87 | 0 | 99165.87 | 194558.84 | [6 empty] | DW5FS | 100%
500216 | West Lewis WI - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-15 | 2018-12-21 | Na H-Eileanan an Iar | 0 | 527.16 | 31842.97 | 28932.81 | 2913.03 | 3183.53 | 0 | 67399.5 | 0 | 67399.5 | 266208.2 | [6 empty] | DW5FS | 100%
502752 | West Lewis WOA- Linshader and bernera Undersea Pipe Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-27 | 2028-02-11 | 2028-05-02 | 2029-02-13 | 2029-05-16 | Na H-Eileanan an Iar | 0 | 0 | 0 | 42478.98 | 11674.31 | 1215.22 | 0 | 55368.51 | 1054631.49 | 1110000 | 0 | [6 empty] | CM_WSI | 100%
502619 | West Lewis WOA- Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-06 | 2027-08-19 | 2027-12-03 | 2028-09-01 | 2028-12-04 | Na H-Eileanan an Iar | 0 | 0 | 20128.53 | 3205.53 | 2009.49 | 474.63 | -199.71 | 25618.47 | 396919.83 | 422538.3 | 0 | [6 empty] | CM_WSI | 100%
402212 | West Lewis WTW and WSZ Western Isles Additional Storage Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-20 | 2013-02-11 | 2013-03-18 | 2014-06-10 |  | Na H-Eileanan an Iar | 595500 | 0 | 956.26 | 0 | 0 | 0 | 0 | 956.26 | 0 | 596456.26 | 0 | [6 empty] | CM_WSNI | 100%
502133 | West Lewis WTW CWT | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-03-24 | 2016-03-29 | 2016-03-29 | 2016-03-31 | 2016-03-31 | Na H-Eileanan an Iar | 0 | 65.42 | 0 | 0 | 0 | 0 | 0 | 65.42 | 0 | 65.42 | 1823900.39 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
402207 | West Line Heathfield SR WSZ000776 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-13 | 2012-09-13 | 2012-10-31 | 2013-05-20 |  | Highland | 279431 | -1713.3 | 0 | 0 | 0 | 0 | 0 | -1713.3 | 0 | 277717.7 | 0 | [6 empty] | CM_WSI | 100%
31772 | West Linton STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-08 | 2010-09-20 | 2010-11-29 | 2013-03-29 | 2013-05-14 | Scottish Borders | 1225231.7 | 12387.27 | 0 | 0 | 0 | 0 | 0 | 12387.27 | 0 | 1237618.97 | 136478.56 | [6 empty] | SG1 | 5% | CM_WWNI | 25% | EC10A | 70%
403972 | West Linton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2016-10-04 | 2022-01-20 | 2022-02-28 | 2022-11-10 | 2022-11-11 | Scottish Borders | 9516.54 | 12552.46 | 20498.13 | 1954.36 | 18109.88 | 29011.5 | 2257.43 | 84383.76 | 1032529.71 | 1126430.01 | 0 | [6 empty] | CM_WWNI | 41.25% | SG1 | 58.75%
501100 | West Lothian Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2015-09-30 | 2016-09-27 | 2016-09-29 | 2020-02-19 | 2019-11-30 | West Lothian | 0 | 10169 | 132650.84 | 60055.5 | 58124.66 | 10073.07 | 3926.93 | 275000 | 0 | 275000 | 0 | [6 empty] | EC10D | 100% | [18 empty] | Regulatory Outputs OMG-23: 6
403275 | West Mill Road - Lasswade | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-01-23 | 2014-10-02 | 2014-10-15 | 2015-03-30 | 2015-03-30 | Midlothian | 421690 | 25992 | 8679.56 | -3204.03 | 0 | 0 | 0 | 31467.53 | 0 | 453157.53 | 204193.13 | [6 empty] | CS11 | 100%
400634 | West Pollution Hotspots Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2013-02-13 | 2013-05-20 | 2014-05-27 |  | All West Unitary Authorities | 123734 | 0 | -1737.84 | 0 | 0 | 0 | 0 | -1737.84 | 0 | 121996.16 | 0 | [6 empty] | CM_WWI | 100%
502257 | West SPS MCC Replacements Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-09-22 | 2018-06-07 | 2018-11-12 | 2020-05-13 | 2020-05-13 | Scottish Water Wide | 0 | 0 | 52083 | 143590 | 808664 | 58397 | 0 | 1062734 | 237 | 1062971 | 0 | [6 empty] | CM_WWNI | 100%
502247 | West SPS MCC Replacements Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2020-04-01 | 2020-05-11 | 2020-03-06 | 2020-03-17 | 2020-06-08 | Scottish Water Wide | 0 | 0 | 0 | 23926.39 | 43.72 | 2592.85 | 0 | 26562.96 | 0 | 26562.96 | 0 | [6 empty] | CM_WWNI | 100%
501315 | West WWTW MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2016-10-04 | 2021-04-19 | 2021-05-24 | 2024-06-04 | 2024-06-04 | Scottish Water Wide | 0 | 0 | 4043.08 | 52875.44 | 0.01 | -0.01 | 0 | 56918.52 | 0 | 56918.52 | 0 | [6 empty] | CM_WWNI | 100%
501310 | Westburn Cambuslang PS RM | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-12-01 | 2018-01-29 | 2018-02-19 | 2018-05-25 | 2018-05-25 | South Lanarkshire | 0 | 6101 | 129172 | 287073 | 258654 | 0 | 0 | 681000 | 0 | 681000 | 0 | [6 empty] | CM_WWI | 100%
503033 | Wester Balbeggie River Ore Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2020-10-09 | 2021-07-22 | 2021-10-12 | 2022-02-24 | 2022-05-27 | Fife | 0 | 0 | 0 | 6768.75 | 16565.97 | 4624.42 | 57640.86 | 85600 | 144199.99 | 229799.99 | 0 | [6 empty] | CM_WWI | 100%
500492 | Westfield WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-25 | 2016-07-31 | West Lothian | 0 | 60228 | 1874.57 | 360 | 0 | 0 | -360 | 62102.57 | 0 | 62102.57 | 136478.56 | [6 empty] | SG1 | 100%
503228 | WestfieldWwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-15 | 2030-06-12 | 2030-09-12 | West Lothian | 0 | 0 | 0 | 0 | 78171.44 | 20941.58 | 0 | 99113.02 | 42886.99 | 142000.01 | 136478.56 | [6 empty] | SG1 | 100%
500771 | Westhill Service Reservoir | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | NONINF | Infra Charge | MS3 | 2016-08-31 | 2018-09-12 | 2019-01-08 | 2020-11-06 | 2021-02-11 | Aberdeenshire | 0 | 11045.68 | 92934.07 | 436972.33 | 500389.27 | 1095185.64 | 976116.77 | 3112643.76 | 22395.24 | 3135039 | 470181.23 |  |  |  |  | 2820 |  | WG5 | 100%
402769 | Westhills WSZ - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-09 | 2014-03-26 | 2014-03-27 | 2014-10-14 |  | Angus | 57695 | 909.09 | 0 | 0 | 0 | 0 | 0 | 909.09 | 0 | 58604.09 | 0 | [6 empty] | CM_WSI | 100%
402716 | Westhills WSZ Low Pressure Enhancement WSZ001563 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-03 | 2014-12-05 | 2014-12-16 | 2015-06-25 | 2015-03-27 | Angus | 67572.41 | 3318.57 | 0 | 0 | 0 | 0 | 0 | 3318.57 | 0 | 70890.98 | 2629 | [6 empty] | CS1 | 100%
501704 | Westmill Farm Glenrothes - Reline sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-11-17 | 2017-05-23 | 2017-07-24 | 2017-09-26 | 2017-09-26 | Fife | 0 | 0 | 11235 | 45926 | 1456.01 | 0 | 0.99 | 58618 | 0 | 58618 | 0 | [6 empty] | CM_WWI | 100%
501255 | Westray WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2016-07-29 | 2027-07-07 | 2027-08-06 | 2028-02-01 | 2028-05-03 | Orkney Islands | 0 | 2338 | 89382.98 | 0 | -5994.74 | 0 | 0 | 85726.24 | 0 | 85726.24 | 0 | [6 empty] | CM_WSNI | 100%
500720 | Weyland Bay WWPS 1997 HY458121 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-07-07 | 2018-03-28 | 2018-03-29 | 2020-07-08 | 2020-10-12 | Orkney Islands | 0 | 75025 | 33565 | 214114 | 546554 | 102761.08 | -15.08 | 972004 | 2558 | 974562 | 0 | [6 empty] | CM_WWNI | 100%
500194 | WFD Abstraction Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Water |  | SWD | Environmental Studies | MS7 | 2015-03-26 | 2016-09-30 | 2016-10-03 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 5535 | 31508 | 61181.81 | 2889.64 | -9781.79 | 0 | 91332.66 | 0 | 91332.66 | 664921.77 | [6 empty] | WR1A | 100% | [18 empty] | Regulatory Outputs OMG-23: 8
402618 | WFD CAR licence Monitoring Equipment Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-26 | 2012-10-09 | 2012-10-22 | 2014-12-02 |  | Scottish Water Wide | 632000 | -8000 | -1409.92 | 0 | 0 | 0 | 1409.92 | -8000 | 0 | 624000 | 0 | [6 empty] | CM_WSNI | 100%
500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Water |  | SWD | Environmental Studies | MS7 | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 8693 | 23241 | 126232.68 | 26517.52 | 1274.58 | 0 | 185958.78 | 0 | 185958.78 | 100684.66 | [6 empty] | WR2B | 100%
500891 | Whalsay Shetland RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-10-19 | 2018-09-21 | 2019-03-18 | 2019-05-31 | 2020-02-29 | Shetland Islands | 0 | 857.04 | 8543.79 | 4347.36 | 30780.99 | 9723.86 | 411.56 | 54664.6 | 0 | 54664.6 | 43188.25 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 14.65
403670 | Whalsay WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2014-02-17 | 2016-01-29 | 2016-03-23 | 2018-01-31 | 2018-12-31 | Shetland Islands | 57282.47 | 1497383.53 | 3113151.78 | 495600.34 | 135167.17 | -29763.84 | -0.01 | 5211538.97 | 0 | 5268821.44 | 3644365.96 |  |  |  |  | 262196 |  | DW25P | 10% | DW2 | 45% | DW23 | 45% | bar: Regulatory Outputs OMG-01
503245 | Whinnyfold ST ecological treatment system | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2028-02-16 | 2028-06-14 | 2028-10-19 | 2029-01-19 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6289 | 6289 | 288144.93 | 294433.93 | 0 | [6 empty] | CM_WWNI | 100%
500687 | Whitecraigs Court Giffnock | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-06-11 | 2020-02-18 | 2020-03-16 | 2021-04-14 | 2021-04-14 | East Renfrewshire | 0 | 6750 | 12029 | 70243 | 79577 | 297671 | 751921 | 1218191 | 39157 | 1257348 | 0 | [6 empty] | CM_WWI | 100%
502823 | Whitecross WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-03-03 | 2020-05-20 | West Lothian | 0 | 0 | 0 | 74965.67 | 37811.65 | 8822.93 | 0 | 121600.25 | 0 | 121600.25 | 136478.56 | [6 empty] | SG1 | 100%
503384 | Whiteford ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 | 2029-04-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 66450.7 | 6450.59 | 0 | 72901.29 | 69098.71 | 142000 | 136478.56 | [6 empty] | SG1 | 100%
501200 | Whitehall DSR CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2018-12-21 | 2020-04-01 | 2020-04-20 | 2021-10-31 | 2021-11-30 | Orkney Islands | 0 | 18092.93 | 30822.63 | 25151.73 | 21899.66 | 309743.4 | 1110963.66 | 1516674.01 | 73525.1 | 1590199.11 | 1277702.09 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
401293 | Whitehillocks East - DW5 Iron and Manganese Distribution WQ Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-10-05 | 2010-10-05 | 2011-02-01 | 2014-02-21 | 2014-03-28 | Angus | 9573350 | 77571 | 35856.42 | 0 | 0 | 0 | 0 | 113427.42 | 0 | 9686777.42 | 109244.7 | [6 empty] | CM_WSI | 1% | DW5 | 99%
401294 | Whitehillocks West - DW5 Iron and Manganese Distribution WQ Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-22 | 2010-09-22 | 2011-02-01 | 2014-11-24 | 2015-03-17 | Angus | 7308600.95 | 156462.05 | 13190.64 | 0 | 0 | 0 | 0 | 169652.69 | 0 | 7478253.64 | 130098.6 | [6 empty] | CM_WSI | 13% | DW5 | 87%
500023 | Whitehillocks WOA Morphie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-13 | 2016-09-12 | 2016-10-31 | 2018-01-26 | 2018-01-26 | Aberdeenshire | 0 | 44644 | 439358 | -93806.51 | 75586.42 | -13723.53 | 0 | 452058.38 | 0 | 452058.38 | 0 | [6 empty] | CM_WSI | 100%
500022 | Whitehillocks WOA Westhills WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-09 | 2016-09-12 | 2017-06-26 | 2018-03-29 | 2018-03-29 | Aberdeenshire | 0 | 54300 | 68457 | 244187 | 30983.4 | -21426.31 | -212 | 376289.09 | 0 | 376289.09 | 0 | [6 empty] | CM_WSI | 100%
502204 | Whitehillocks WTW - Causeywell SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-03-24 | 2016-07-06 | 2016-07-06 | 2019-09-30 | 2019-09-30 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 275.41 | -274.41 | 1 | 0 | 1 | 1207597.94 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501232 | Whitehillocks WTW - Quality and CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-03-31 | 2016-03-31 | 2016-03-31 |  | 2020-07-31 | Angus | 0 | 41788.23 | 395068.88 | 366498.44 | 3637769.78 | 4180968.47 | 2291307.46 | 10913401.26 | 266432.73 | 11179833.99 | 2415195.88 |  |  |  |  | 145600 |  | CM_WSNI | 12.34% | DW25P | 43.83% | DW25T | 43.83% | bar: Regulatory Outputs OMG-04
502194 | Whitehillocks WTW - Water Quality Instruments | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2016-03-22 | 2016-03-30 | 2016-03-30 | 2016-03-31 |  | Angus | 0 | 0 | 0 | 162.6 | 0 | 1496 | -1496 | 162.6 | 0 | 162.6 | 1207597.94 | [6 empty] | DW25P | 100%
45613 | Whitehillocks WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2011-05-23 | 2011-05-23 | 2013-05-01 | 2013-12-30 | Angus | 584561.51 | 508.39 | 0 | 0 | 0 | 0 | 0 | 508.39 | 0 | 585069.9 | 1768 | [6 empty] | DW1A | 100%
501220 | Whitehills 1 & 2 TWP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-07-13 | 2018-08-01 | 2018-08-21 | 2020-04-30 | 2020-06-24 | Fife | 0 | 14503.9 | 99600.94 | 236358.28 | 689280.42 | 1006258.49 | 130182.97 | 2176185 | 652 | 2176837 | 0 | [6 empty] | CM_WSNI | 100%
502899 | Whitelaw Drive Bathgate_Sewer rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-09-13 | 2017-09-13 | 2017-11-13 | 2018-06-20 | 2018-06-20 | West Lothian | 0 | 0 | 0 | 493590.4 | -44372.64 | 249.45 | -249.45 | 449217.76 | 0 | 449217.76 | 0 | [6 empty] | CM_WWI | 100%
403601 | Whiteside Cottages Bathgate | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2013-10-23 | 2019-09-06 | 2020-02-21 | 2019-09-12 | 2019-09-12 | West Lothian | 56898.06 | 65132.94 | 10973 | 47226.03 | 41769.97 | -159235.69 | 0.08 | 5866.33 | 0 | 62764.39 | 204193.13 | [6 empty] | CS11A | 100%
403870 | Whiting Bay Low Pressure | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU | [5 empty] | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49808 | [6 empty] | CS1 | 100%
402697 | Wholesale Data Improvement - Assurance Framework | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2012-06-12 | 2015-05-12 | 2015-05-12 | 2015-03-31 |  | Scottish Water Wide | 283342.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283342.07 | 5006 | [6 empty] | CS20 | 100%
503262 | Wigtown ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-15 | 2030-06-12 | 2030-09-12 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 77306.64 | 5698.35 | 0 | 83004.99 | 69095.01 | 152100 | 136478.56 | [6 empty] | SG1 | 100%
500222 | Willowgate RM Perth Railway Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-03-24 | 2016-08-04 | 2016-09-26 | 2018-04-30 | 2018-04-30 | Perth and Kinross | 0 | 89000 | 1291473 | 514159 | 68886 | 0 | 0 | 1963518 | 0 | 1963518 | 0 | [6 empty] | CM_WWI | 100%
402991 | Wilson Street Candleriggs Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-06-05 | 2013-10-25 | 2013-10-25 | Glasgow City | 47367 | -264.19 | 0 | 0 | 0 | 0 | 0 | -264.19 | 0 | 47102.81 | 201 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403967 | Winchburgh WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2018-11-07 | 2020-08-24 | 2020-08-25 | 2022-06-13 | 2022-06-14 | West Lothian | 13556.56 | 21856.44 | 16739.8 | 46917.59 | 134030.92 | 1329543.5 | 7376198.65 | 8925286.9 | 10049050.54 | 18987894 | 0 | [6 empty] | SG1 | 100%
503045 | Winchburgh WwTW - Growth Intermediate Solution Support | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS2 | 2020-01-24 | 2020-03-31 | 2020-07-20 | 2020-10-09 | 2021-01-15 | West Lothian | 0 | 0 | 0 | 41883.58 | 12804.58 | 1958265.4 | 2339686.54 | 4352640.1 | 36254.93 | 4388895.03 | 136478.56 | [6 empty] | SG1 | 100%
503125 | Winchburgh WwTW - Growth Support for SAF Package Plant | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2018-03-30 | 2018-03-30 | 2018-05-09 | 2020-08-03 | 2020-08-03 | West Lothian | 0 | 0 | 0 | 40000 | 408131.83 | 0 | 0 | 448131.83 | 0 | 448131.83 | 136478.56 |  |  |  |  | 7000 |  | SG1 | 100%
403866 | Windows Server Decommission | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-09-05 | 2014-09-05 | 2014-10-01 | 2014-12-18 |  | Scottish Water Wide | 152356 | 5942.82 | 0 | 0 | 0 | 0 | 0 | 5942.82 | 0 | 158298.82 | 0 | [6 empty] | CM_M&G | 100%
501756 | Windyfield Rhynie DSR Replacement | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-11-08 | 2029-01-19 | 2029-05-24 | 2030-01-02 | 2030-04-04 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000.03 | 700000.03 | 0 | [6 empty] | CM_WSNI | 100%
45027 | Windyfield Rhynie WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-29 | 2011-08-29 | 2013-02-28 | 2013-03-18 | Aberdeenshire | 1636912.53 | -93.97 | 0 | 0 | 0 | 0 | 0 | -93.97 | 0 | 1636818.56 | 0 | [6 empty] | DW23 | 100%
49718 | WINF - DWQ Compliance - Profile Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -7271167.39 | -7271167.39 | 7271167.39 | 0 | 0 | [6 empty] | SR15_DWQ_COM | 100%
49724 | WINF - DWQ Reliability - Profile Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -2000000 | -2000000 | 2000000 | 0 | 0 | [6 empty] | SR15_DWQ_REL | 100%
49609 | WINF - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | Water |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | RISK | 100%
50039 | WINF - SR21 Early Start - Profile Adjustment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -5710926.69 | -5710926.69 | 5710926.69 | 0 | 0 | [6 empty] | SR21_SS | 100%
503050 | Wishaw TM Water Quality | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-02 | 2028-02-03 | 2028-04-18 | 2029-05-11 | 2029-08-13 | North Lanarkshire | 0 | 0 | 0 | 27397.67 | 11643.16 | 26409.17 | 0 | 65450 | 304550 | 370000 | 0 | [6 empty] | CM_WSI | 100%
501204 | WISTON TWP NS957319 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-11-06 | 2016-09-30 | 2016-11-21 | 2019-03-15 | 2019-03-15 | South Lanarkshire | 0 | 1415.44 | 87098.37 | 130707.33 | 126394 | 11100 | 628.86 | 357344 | 371.13 | 357715.13 | 0 | [6 empty] | CM_WSNI | 100%
501004 | WMS Data Inclusion on Schematics | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2015-11-18 | 2016-02-18 | 2018-04-18 | 2018-04-18 | Scottish Water Wide | 0 | 26721 | 49408 | 43204.03 | 0 | 0 | 0 | 119333.03 | 0 | 119333.03 | 0 | [6 empty] | CM_WWNI | 20% | CM_WSNI | 80%
505804 | W-N-NI-180320-Stornoway WOA- DOMS Store | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-24 |  | 2021-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3531 | 3531 | 0 | 3531 | 0 | [6 empty] | CM_WSI | 100%
504965 | W-N-NI-310120-Drumbeg WTW- PLC Spare | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 1195 | 105 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WSNI | 100%
401091 | WOA000168 Glenconvinth Mains Rehab 2 WSZs Balnain Buntait and Kirkhill | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-03-27 | 2012-06-14 | 2013-10-09 |  | Highland | 416635 | -172.18 | 0 | 0 | 0 | 0 | 0 | -172.18 | 0 | 416462.82 | 0 | [6 empty] | CM_WSI | 100%
401309 | WOA000257 Marchbank 3 schemes within 3 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-01-11 | 2013-02-12 | 2015-04-03 |  | City of Edinburgh | 1204188 | 84008 | 703.93 | -892.04 | 0 | 0 | 0 | 83819.89 | 0 | 1288007.89 | 0 | [6 empty] | CM_WSI | 100%
401144 | WOA000332 South Uist WSZ001378 Isle of South Uist UITS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-17 | 2012-11-22 | 2012-12-17 | 2013-10-01 |  | Na H-Eileanan an Iar | 689000 | -9347.8 | 0 | 0 | 0 | 0 | 0 | -9347.8 | 0 | 679652.2 | 0 | [6 empty] | CM_WSI | 100%
401099 | WOA000341 Storr Forest Achachork DMA Torvaig Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-28 | 2012-02-22 | 2012-03-26 | 2013-08-20 |  | Highland | 300712.66 | 109.39 | 0 | 0 | 0 | 0 | 0 | 109.39 | 0 | 300822.05 | 0 | [6 empty] | CM_WSI | 100%
401145 | WOA000360 Tiree 2 Schemes Within Tiree DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-04-24 | 2012-07-23 | 2013-03-20 |  | Argyll and Bute-North Argyll | 872842 | 74.54 | 0 | 0 | 0 | 0 | 0 | 74.54 | 0 | 872916.54 | 0 | [6 empty] | CM_WSI | 100%
401100 | WOA000372 Tullich 8 schemes in 7 DMAs within Oban North and Oban South WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-04-23 | 2012-08-27 | 2013-01-25 |  | Argyll and Bute-North Argyll | 457000 | -1470.72 | 0 | 0 | 0 | 0 | 0 | -1470.72 | 0 | 455529.28 | 0 | [6 empty] | CM_WSI | 100%
401142 | WOA000396 Assynt and Newmore WOA 2 Schemes At Nigg and Shandwick | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-12-16 | 2014-01-31 | 2015-09-21 |  | Highland | 662164 | 184623 | 3976.26 | 9908.94 | 0 | 0 | 0 | 198508.2 | 0 | 860672.2 | 0 | [6 empty] | CM_WSI | 100%
501734 | Woodhead DSR Mainout | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2028-07-24 | 2029-05-09 | 2029-09-12 | 2030-01-22 | 2030-04-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.97 | 99999.97 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
501076 | Woodside Drive Calderbank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2015-11-18 | 2018-04-30 | 2018-06-18 | 2020-02-19 | 2020-04-01 | North Lanarkshire | 0 | 11437.38 | 69577.74 | 204005.88 | 1604185.1 | 748590.9 | 0 | 2637797 | 0 | 2637797 | 0 | [6 empty] | CM_WWI | 100%
500943 | Work Scheduling and Field Services Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-30 | 2016-09-23 | 2016-09-23 | 2018-07-25 |  | Scottish Water Wide | 0 | 514927 | 1576193.02 | 710046.44 | 321985.2 | 0 | 0 | 3123151.66 | 0 | 3123151.66 | 0 | [6 empty] | CM_M&G | 100%
500622 | Workplace & Property Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 2526708 | 3693138.99 | 2362727.21 | 2082201.71 | 2319851.16 | 3070368.73 | 16054995.8 | 499827.46 | 16554823.26 | 0 | [6 empty] | CM_OVH | 100%
500977 | Wormit Outfall Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-11-21 | 2017-06-27 | 2017-06-27 | 2017-06-28 | 2018-08-30 | Fife | 0 | 0 | 2106 | 190.63 | 140.65 | -139.32 | 56.86 | 2354.82 | 0 | 2354.82 | 0 | [6 empty] | CM_WWI | 100%
502611 | Wormit- Removal of Raw Discharges Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2017-02-28 | 2017-10-26 | 2017-12-12 | 2018-08-31 | 2018-11-30 | Fife | 0 | 0 | 657.01 | 15242.99 | 18986.97 | 0 | 0 | 34886.97 | 0 | 34886.97 | 101616.7 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
404063 | WQ Improvement Yr5 - Fetler RO | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-15 | 2015-10-21 | 2015-11-27 | 2016-03-29 |  | Scottish Water Wide | 10099 | 664525 | 25629.24 | 0 | 0 | 0 | 0 | 690154.24 | 0 | 700253.24 | 0 | [6 empty] | CM_WSNI | 100%
404062 | WQ Improvement Yr5 - Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2015-10-27 |  | Scottish Water Wide | 110165 | 888.73 | 0 | 0 | 0 | 0 | 0 | 888.73 | 0 | 111053.73 | 0 | [6 empty] | CM_WSI | 100%
404055 | WQ Improvement Yr5 - Tomnavoulin WTW - UV Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-15 | 2015-08-27 | 2015-10-05 | 2015-10-20 | 2017-05-22 | Scottish Water Wide | 4377 | 19685.84 | 0 | 0 | 0 | 0 | 0 | 19685.84 | 0 | 24062.84 | 0 | [6 empty] | CM_WSNI | 100%
404058 | WQ Improvements 14-15 - Non Inf SV - Man Del | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-12 | 2014-12-12 | 2015-04-14 | 2016-02-08 |  | Scottish Water Wide | 18395.68 | 318597.82 | 1656.13 | 301.35 | 0 | 0 | 0 | 320555.3 | 0 | 338950.98 | 0 | [6 empty] | CM_WSNI | 100%
404101 | WQ Improvements 14-15 Man Del Membrane Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-19 | 2015-02-19 | 2015-04-14 | 2015-10-01 |  | Scottish Water Wide | 1624583 | 298217 | -429.35 | 0 | 0 | 0 | 0 | 297787.65 | 0 | 1922370.65 | 0 | [6 empty] | CM_WSNI | 100%
404064 | WQ Improvements Yr5 - Inf Flushing SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2015-11-09 |  | Scottish Water Wide | 26712 | 564996.65 | 0 | 0 | 0 | 0 | 0 | 564996.65 | 0 | 591708.65 | 0 | [6 empty] | CM_WSI | 100%
404060 | WQ Improvements Yr5 - Membrane GAC Polishing Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2015-04-13 | 2016-01-11 |  | Scottish Water Wide | 440824.14 | 541936.76 | 0 | 0 | 0 | 0 | 0 | 541936.76 | 0 | 982760.9 | 0 | [6 empty] | CM_WSNI | 100%
404057 | WQ Improvements Yr5 - Non Inf Quick Hits - SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2018-04-25 |  | Scottish Water Wide | 3761294.75 | 1535056.25 | 452538.1 | 72321.63 | 0 | 0 | 0 | 2059915.98 | 0 | 5821210.73 | 0 | [6 empty] | CM_WSNI | 100%
404084 | WQ Improvements Yr5 - South Area SRs - SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2015-11-12 |  | Scottish Water Wide | 46750.25 | 168197.1 | 0 | 0 | 0 | 0 | 0 | 168197.1 | 0 | 214947.35 | 0 | [6 empty] | CM_WSNI | 100%
404059 | WQ Improvements Yr5 - SR Repair Programme - Man Del | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2015-02-02 | 2017-02-23 |  | Scottish Water Wide | 743945 | 2312328 | 297662.03 | 155792.09 | 3792.07 | 0 | 0 | 2769574.19 | 0 | 3513519.19 | 0 | [6 empty] | CM_WSNI | 100%
404065 | WQ Improvements Yr5 - Tullich WTW - Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-21 | 2015-09-07 | 2016-01-12 | 2016-02-15 |  | Scottish Water Wide | 19710 | 47808.21 | 17.75 | 335.81 | 0 | 0 | 0 | 48161.77 | 0 | 67871.77 | 0 | [6 empty] | CM_WSNI | 100%
403792 | WQ OPA - Automatic Coagulation Control - Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-05-09 | 2014-08-25 | 2014-10-31 | 2015-10-16 |  | Scottish Water Wide | 225271 | 42409.77 | 0 | 0 | 0 | 0 | 0 | 42409.77 | 0 | 267680.77 | 0 | [6 empty] | CM_WSNI | 100%
403906 | WQ OPA Ardrishaig Raw Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-08-15 | 2014-10-01 | 2014-10-20 | 2015-04-10 |  | Argyll and Bute-Cowal & Bute | 165023 | 55395 | -0.1 | -9182.26 | 0 | 0 | 0 | 46212.64 | 0 | 211235.64 | 0 | [6 empty] | CM_WSI | 100%
403793 | WQ OPA GAC Polishing Filters Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-05-09 | 2014-07-30 | 2014-08-01 | 2015-03-27 |  | Scottish Water Wide | 286638 | 1819.36 | 0 | 0 | 0 | 0 | 0 | 1819.36 | 0 | 288457.36 | 0 | [6 empty] | CM_WSNI | 100%
403789 | WQ OPA Network Flushing Teams Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-05-19 | 2014-06-25 | 2014-06-25 | 2015-09-10 |  | Scottish Water Wide | 1692101.66 | 6839.77 | 0 | 0 | 0 | 0 | 0 | 6839.77 | 0 | 1698941.43 | 0 | [6 empty] | CM_WSNI | 100%
403472 | WQ OPA Network Interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-05-20 | 2013-08-20 | 2013-10-01 | 2015-02-27 |  | Scottish Water Wide | 1133759.34 | 717.5 | 0 | 0 | 0 | 0 | 0 | 717.5 | 0 | 1134476.84 | 0 | [6 empty] | CM_WSI | 100%
403790 | WQ OPA Process Science Teams Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-02 | 2014-06-23 | 2014-06-23 | 2015-10-30 |  | Scottish Water Wide | 654159.4 | 3903.23 | 0 | 0 | 0 | 0 | 0 | 3903.23 | 0 | 658062.63 | 0 | [6 empty] | CM_WSNI | 100%
403469 | WQ OPA SR Repair Programme Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-05-13 | 2013-08-20 | 2013-10-17 | 2016-03-30 |  | Argyll and Bute-North Argyll | 4155573 | 104400 | 15379.12 | 18308.86 | 32164.82 | 0 | -34472.24 | 135780.56 | 0 | 4291353.56 | 0 | [6 empty] | CM_WSNI | 100%
403317 | WQ OPA THM issues - Chloramination at Western Isles Sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-02 | 2013-04-02 | 2013-05-15 | 2014-11-03 |  | Na H-Eileanan an Iar | 1713029.62 | -25240.62 | -962.34 | 0 | 0 | 0 | 0 | -26202.96 | 0 | 1686826.66 | 0 | [6 empty] | CM_WSNI | 100%
500606 | WSS Cost Intelligence SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 2789761.75 | 2292183.51 | 1719779.24 | 1766143.51 | 1147930.79 | 2453494 | 12169292.8 | 399406 | 12568698.8 | 0 | [6 empty] | CM_OVH | 100%
500619 | WSS Investment Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 138481.55 | 1311142.71 | 1277003.27 | 1284591.45 | 518467.77 | 1139487.37 | 5669174.12 | 185497.93 | 5854672.05 | 0 | [6 empty] | CM_OVH | 100%
500618 | WSS Public Health & Water Quality SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 44992.24 | 37689.53 | 169574.08 | 355933.1 | 54250.19 | 176186.23 | 838625.37 | 28681.49 | 867306.86 | 0 | [6 empty] | CM_OVH | 100%
500617 | WSS Reservoir Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 21249.19 | 38170.9 | 143819.14 | 196159.95 | 169986.1 | 119536.19 | 688921.47 | 19459.4 | 708380.87 | 0 | [6 empty] | CM_OVH | 100%
500616 | WSS Supply Demand Balance SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 48698.95 | 95837.94 | 305394.7 | 312064.75 | 121274.65 | 218019.91 | 1101290.9 | 35491.64 | 1136782.54 | 0 | [6 empty] | CM_OVH | 100%
500615 | WSS Water Risk Lifecycle Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 524767.27 | 1208106.89 | 1959818.44 | 1646061.85 | 1725477 | 1381847.19 | 8446078.64 | 224951.86 | 8671030.5 | 0 | [6 empty] | CM_OVH | 100%
500614 | WSS Water Service Strategy SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 355193.26 | 1265242.67 | 1613363.54 | 1280316.44 | 162218.53 | 1295185.35 | 5971519.79 | 210844.1 | 6182363.89 | 0 | [6 empty] | CM_OVH | 100%
401433 | WSZ000107 Badentinan WSZ Mains Rehabilitation Iron Failures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-01-11 | 2012-10-30 | 2012-12-17 | 2013-06-24 |  | Moray | 343845 | -2850.22 | 0 | 0 | 0 | 0 | 0 | -2850.22 | 0 | 340994.78 | 0 | [6 empty] | CM_WSI | 100%
34916 | WSZ000337-Carnbee WSZ-Crail to St Andrews AC Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2006-11-23 | 2008-07-31 | 2008-09-18 | 2009-04-24 |  | Fife | 1561034 | 8129 | 100696.99 | -31822.33 | 0 | 0 | 0 | 77003.66 | 0 | 1638037.66 | 0 | [6 empty] | WSI | 100%
402356 | WSZ000346 - Carse of Gowrie WSZ - Re-hab of 9inch A.C. Water Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-11-21 | 2012-12-19 | 2012-12-10 | 2014-09-01 |  | Perth and Kinross | 474225.93 | 3472.34 | 0 | 0 | 0 | 0 | 0 | 3472.34 | 0 | 477698.27 | 0 | [6 empty] | CM_WSI | 100%
402495 | WSZ000356 - Catterthun WSZ Hot Spot - Mains Re-habilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-01-30 | 2013-07-29 | 2013-10-21 | 2014-08-01 |  | Angus | 293796 | 0 | -3000.98 | 0 | 0 | 0 | 0 | -3000.98 | 0 | 290795.02 | 0 | [6 empty] | CM_WSI | 100%
402045 | WSZ000447 Crombie WSZ Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-29 | 2013-06-13 | 2013-06-18 | 2014-08-01 |  | Angus | 149226 | 55 | -17.01 | 0 | 0 | 0 | 0 | 37.99 | 0 | 149263.99 | 0 | [6 empty] | CM_WSI | 100%
401557 | WSZ001578 Whiteness and Weisdale Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-11-30 | 2013-09-25 | 2013-10-28 | 2014-12-11 |  | Shetland Islands | 633239.56 | 3642.44 | 1997.49 | 0 | 0 | 0 | 0 | 5639.93 | 0 | 638879.49 | 0 | [6 empty] | CM_WSI | 100%
503104 | WTW Performance enhancement plans (WTW PEP) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-04-27 | 2018-04-27 | 2018-05-01 | 2021-03-24 | 2021-03-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 147232.03 | 106358.25 | 246409.72 | 500000 | 0 | 500000 | 0 |  |  |  |  | 500000 |  | CM_WSNI | 100%
501338 | WTW000067 - COULTER WTW 2001 NT035276 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2017-01-26 | 2028-03-03 | 2028-07-05 | 2029-02-14 | 2029-05-15 | South Lanarkshire | 0 | 0 | 4796.35 | 0 | 1206.2 | 31.41 | 0 | 6033.96 | 841986.07 | 848020.03 | 0 | [6 empty] | CM_WSNI | 100%
500981 | WTW000078 - DAER WTW 1956 NS978092 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2015-10-23 | 2021-09-27 | 2021-11-29 | 2022-08-16 | 2022-11-16 | South Lanarkshire | 0 | 24168 | 140955.64 | 20239.45 | -4796.09 | 0 | 0 | 180567 | 0 | 180567 | 0 | [6 empty] | CM_WSI | 100%
501332 | WTW000233 - SOUTH MOORHOUSE WTW 1995 NS526511 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2027-11-12 | 2028-08-10 | 2028-12-14 | 2029-04-25 | 2029-07-26 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 62.78 | 62.78 | 99937.21 | 99999.99 | 0 | [6 empty] | CM_WSNI | 100%
501403 | WTW000476 - SPEY BADENTINAN WTW 1994 NJ282568 - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-12-09 | 2028-12-20 | 2029-04-25 | 2029-12-10 | 2030-03-12 | Moray | 0 | 5023.26 | 0 | 0 | 0 | 830.16 | 0 | 5853.42 | 405814.58 | 411668 | 0 | [6 empty] | CM_WSNI | 100%
402093 | WTW000515 Forehill WTW Pesticide Removal Stage | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2011-05-23 | 2012-03-27 | 2013-01-14 | 2014-11-13 | 2014-12-03 | Aberdeenshire | 7799342.91 | 194928.19 | 119.66 | 0 | 0 | 0 | 0 | 195047.85 | 0 | 7994390.76 | 45410 |  |  |  |  | 48825.52 |  | DW3H | 100%
501388 | WTW000626 - PATESHILL WTW NS983595 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2017-08-28 | 2020-06-22 | 2020-07-20 | 2021-06-16 | 2021-08-25 | West Lothian | 0 | 0 | 92411.23 | 149801.73 | 342302.04 | 431739.79 | 2631763.17 | 3648017.96 | 908795.04 | 4556813 | 0 | [6 empty] | CM_WSNI | 100%
501390 | WTW000627 - ROSEBERY WTW 1940 NT305570 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-11-17 | 2019-07-31 | 2019-08-19 | 2022-03-21 | 2022-07-25 | Midlothian | 0 | 0 | 101941.76 | 802311.59 | 792354.21 | 2474013.46 | 1979647.79 | 6150268.81 | 8776454.51 | 14926723.32 | 0 | [6 empty] | CM_WSNI | 100%
501382 | WTW000628 - CASTLE MOFFAT WTW 1974 NT600697 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-02 | 2028-08-10 | 2028-12-14 | 2030-03-13 | 2030-06-13 | East Lothian | 0 | 0 | 50145.3 | 46429.81 | 135995.99 | 11883.32 | 106.52 | 244560.94 | 7095330.16 | 7339891.1 | 0 | [6 empty] | CM_WSNI | 100%
501379 | WTW000640 - MARCHBANK WTW NT165645 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2017-03-31 | 2020-06-22 | 2020-06-22 | 2021-10-04 | 2022-01-03 | City of Edinburgh | 0 | 0 | 48016.79 | 221595.61 | 71804 | 375136.6 | 2111850 | 2828403 | 1361869 | 4190272 | 0 | [6 empty] | CM_WSNI | 100%
501393 | WTW000712 - HOWDEN WTW NT456275 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2017-08-29 | 2020-02-28 | 2020-02-28 | 2021-06-24 | 2021-07-07 | Scottish Borders | 0 | 0 | 66797.3 | 470262.27 | 345056.17 | 1496678.58 | 3537755.2 | 5916549.52 | 2312003.48 | 8228553 | 0 | [6 empty] | CM_WSNI | 100%
402692 | WTW500064331 Craighead WTW - Rebuild | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-20 | 2014-10-01 | 2014-10-01 | 2014-10-21 | 2014-10-01 | Aberdeenshire | 255864.54 | -5230.71 | 0 | 0 | 0 | 0 | 0 | -5230.71 | 0 | 250633.83 | 0 | [6 empty] | DW3C | 30% | CM_WSNI | 70%
34885 | WW Infra Cap Maint Hotspots - Tranche 10 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2006-12-14 | 2008-05-28 | 2008-06-23 | 2015-03-04 |  | Scottish Water Wide | 393500 | -797.71 | 0 | 0 | 0 | 0 | 0 | -797.71 | 0 | 392702.29 | 0 | [6 empty] | WWI | 100%
500611 | WW Service Strategy GM SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 80775.91 | 739686.47 | 1090212.41 | 1349659.41 | 1160672.68 | 849927.31 | 5270934.19 | 138360.28 | 5409294.47 | 0 | [6 empty] | CM_OVH | 100%
502256 | WW SR15 Temporary Chemical Dosing Upgrade Programme- Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2016-07-29 | 2019-03-29 | 2019-03-29 | 2020-05-29 | 2020-05-29 | Scottish Water Wide | 0 | 0 | 67229.35 | 93820.65 | 549394.14 | 314791.74 | 3613448.28 | 4638684.16 | 319505.86 | 4958190.02 | 0 | [6 empty] | CM_WWNI | 100%
502300 | WW SR15 Temporary Chemical Dosing Upgrade Programme- Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2017-08-16 | 2020-03-16 | 2020-03-24 | 2021-06-22 | 2021-09-22 | Scottish Water Wide | 0 | 0 | 32283.07 | 29669.36 | 240555.93 | 140499.94 | 1003027.49 | 1446035.79 | 364306.52 | 1810342.31 | 0 | [6 empty] | CM_WWNI | 100%
502301 | WW SR15 Temporary Chemical Dosing Upgrade Programme- Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2017-11-27 | 2020-03-28 | 2020-03-26 | 2021-06-24 | 2021-09-24 | Scottish Water Wide | 0 | 0 | 26294.46 | 10476.84 | 32935.08 | 128187.92 | 342167.7 | 540062 | 253152.23 | 793214.23 | 0 | [6 empty] | CM_WWNI | 100%
504178 | W-W-051219 Amlaird DAF | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-09 |  |  |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 66.18 | -66.18 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 100%
504183 | W-W-051219 Neilston WTW-H&S Measures Wash Water Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-07-31 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 24600 | 5000 | 29600 | 0 | 29600 | 0 | [6 empty] | WSNI | 100%
503983 | W-W-261119 Balmore WTW-HV Breaker | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  |  |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 21699.55 | 242.54 | 21942.09 | 0 | 21942.09 | 0 | [6 empty] | CM_WSNI | 100%
505171 | W-W-I-130220-Milngavie Commissioners Rd PRVs - Peak 42 Modifications |  | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS2 |  | 2020-02-13 |  | 2020-06-30 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 2665.68 | 8441.32 | 11107 | 0 | 11107 | 0 | [6 empty] | SR15_CMA_WSI | 100%
505285 | W-W-I-190220-Balmore WestLow Moss Prison - Control Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2020-05-01 |  | 2020-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 1295.04 | 4100.96 | 5396 | 0 | 5396 | 0 | [6 empty] | WSI | 100%
505434 | W-W-I-270220-Corrie - Outlet Flow Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 1182 | 1182 | 0 | 1182 | 0 | [6 empty] | CM_WSNI | 100%
49863 | WWINF - External Flooding - Profile Adjustment | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -24999936.16 | -24999936.16 | 24999936.16 | 0 | 0 | [6 empty] | SR15_SEW_EFR | 100%
49610 | WWINF - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | Wastewater |  | WWINF | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | RISK | 100%
49797 | WWINF - Revised Bathing Waters Directive - Profile Adjustment | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -3000000 | -3000000 | 3000000 | 0 | 0 | [6 empty] | SR15_ENV_RBWD | 100%
49809 | WWINF - Shellfish Directive - Profile Adjustment | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWD | Ring Fenced Environmental | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -1000000 | 1000000 | 0 | 0 | [6 empty] | SR15_ENV_SHEL | 100%
50040 | WWINF - SR21 Early Start - Profile Adjustment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -8750782.68 | -8750782.68 | 8750782.68 | 0 | 0 | [6 empty] | SR21_SS | 100%
49785 | WWINF - UWWTD - UID - Profile Adjustment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -2000000 | -2000000 | 2000000 | 0 | 0 | [6 empty] | SR15_UID_UWWD | 100%
504320 | W-W-INFRA-121219 - Byrehill VC - H&S Issues | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3504 | 0 | 3504 | 0 | 3504 | 0 | [6 empty] | CM_WSI | 100%
506028 | W-W-NI-010420-Castlemilk - Install VSDs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-06-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 81418 | 81418 | 0 | 81418 | 0 | [6 empty] | CM_WSNI | 100%
505482 | W-W-NI-020320-Penwhapple- DAF Recycle Pump C Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 2667.9 | 7.1 | 2675 | 0 | 2675 | 0 | [6 empty] | CM_WSNI | 100%
506063 | W-W-NI-020420-Amlaird - Refurb of Chloram Plant pipework/pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-09-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 4000 | 319 | 4319 | 0 | 4319 | 0 | [6 empty] | CM_WSNI | 100%
504522 | W-W-NI-030120 - Bradan WTW - Sludge Press 3 Hydraulic Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2943 | 53 | 2996 | 0 | 2996 | 0 | [6 empty] | CM_WSNI | 100%
504523 | W-W-NI-030120 - Colmonell TWP Ceiling Collapse | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3185.83 | 3.17 | 3189 | 0 | 3189 | 0 | [6 empty] | CM_WSNI | 100%
504525 | W-W-NI-030120 - Loch Turret Lagoons Monitoring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1498 | 0 | 1498 | 0 | 1498 | 0 | [6 empty] | CM_WSNI | 100%
504524 | W-W-NI-030120 - Muirdykes WTW DAF no. 1 - Gearbox and Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 443.81 | 6340.19 | 6784 | 0 | 6784 | 0 | [6 empty] | CM_WSNI | 100%
505500 | W-W-NI-030320-Afton- Chlorine Injector Cabinets | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 378 | 5400 | 5778 | 0 | 5778 | 0 | [6 empty] | CM_WSNI | 100%
505490 | W-W-NI-030320-Bradan- Davit For Coag Sample Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 131.04 | 1871.96 | 2003 | 0 | 2003 | 0 | [6 empty] | CM_WSNI | 100%
505492 | W-W-NI-030320-Megray WSZ - Replace Valves at Dunnotter Av & Lowwood Rd (5917) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-10 |  | 2020-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6140.46 | 0 | 6140.46 | 0 | 6140.46 | 0 | [6 empty] | CM_WSI | 100%
505495 | W-W-NI-030320-Penwhapple- Door Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 655.91 | 9370.09 | 10026 | 0 | 10026 | 0 | [6 empty] | CM_WSNI | 100%
506071 | W-W-NI-030420- Milngavie - PLC 4 Processor Card | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-09-30 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 2943 | 2943 | 0 | 2943 | 0 | [6 empty] | CM_WSNI | 100%
505517 | W-W-NI-040320-Afton-Treated Water Turbidity Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-04 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 4237.46 | 42.54 | 4280 | 0 | 4280 | 0 | [6 empty] | CM_WSNI | 100%
505516 | W-W-NI-040320-Bradan-Sludge Building Lighting Rods | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-04 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 168 | 2400 | 2568 | 0 | 2568 | 0 | [6 empty] | CM_WSNI | 100%
504163 | W-W-NI-041219 - Burncrooks WTW - UPS Rep. Sludge system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2273.31 | -596.78 | 1676.53 | 0 | 1676.53 | 0 | [6 empty] | CM_WSNI | 100%
504162 | W-W-NI-041219 - Picketlaw WTW - Rep. Headloss Meter Filter 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 814.32 | 0 | 814.32 | 0 | 814.32 | 0 | [6 empty] | WSNI | 100%
504144 | W-W-NI-041219 - Picketlaw WTW - Replacement Recirc Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2933.94 | -1108.73 | 1825.21 | 0 | 1825.21 | 0 | [6 empty] | CM_WSNI | 100%
504155 | W-W-NI-041219- Picketlaw WTW - Rep. Pressure Flow Meter Switch | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3175.63 | -1736.73 | 1438.9 | 0 | 1438.9 | 0 | [6 empty] | CM_WSNI | 100%
504145 | WW-NI-041219-Esnet Implementation Plan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 11974.11 | 81339.39 | 93313.5 | 0 | 93313.5 | 0 | [6 empty] | CM_WWNI | 100%
504150 | WW-NI-041219-Hamilton WWTW-Replace Top Level Scrappers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4673.98 | -1936.78 | 2737.2 | 0 | 2737.2 | 0 | [6 empty] | CM_WWNI | 100%
504189 | W-W-NI-051219 - Bradan WTW - PRGF 1-8 Filter Nozzle Clean (4th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 32663.81 | -16022.9 | 16640.91 | 0 | 16640.91 | 0 | [6 empty] | CM_WSNI | 100%
504166 | W-W-NI-051219 - Carron Valley Filter F rotork wash out valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2990.67 | -1130 | 1860.67 | 0 | 1860.67 | 0 | [6 empty] | CM_WSNI | 100%
504164 | W-W-NI-051219 - Helensburgh DSR - HMI replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3242.34 | 0 | 3242.34 | 0 | 3242.34 | 0 | [6 empty] | CM_WSNI | 100%
504187 | W-W-NI-051219 - Turret PACL dosing pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2517.73 | -951.31 | 1566.42 | 0 | 1566.42 | 0 | [6 empty] | CM_WSNI | 100%
504172 | W-W-NI-05129- Turret poly pump A actiflow Stream no1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4396.32 | -1684.01 | 2712.31 | 0 | 2712.31 | 0 | [6 empty] | CM_WSNI | 100%
505566 | W-W-NI-060320-Camphill- PRGF no. 2-Media and Nozzle Repl. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-06 |  | 2020-06-30 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 3500 | 50000 | 53500 | 0 | 53500 | 0 | [6 empty] | CM_WSNI | 100%
503788 | W-W-NI-061119-Blairlinnans WTW- sludge withdrawal pump refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 5055.73 | -1900.85 | 3154.88 | 0 | 3154.88 | 0 | [6 empty] | CM_WSNI | 100%
504542 | W-W-NI-070120 - Castlemilk Low PS - Refurb of Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4849.25 | 48.25 | 4897.5 | 0 | 4897.5 | 0 | [6 empty] | CM_WSNI | 100%
503791 | W-W-NI-071119-Finlas WTW-Replace recovered water pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 751.28 | 0 | 751.28 | 0 | 751.28 | 0 | [6 empty] | CM_WSNI | 100%
504585 | W-W-NI-090120 - Bradan WTW - Bird Mesh Guards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2616.94 | -96.94 | 2520 | 0 | 2520 | 0 | [6 empty] | CM_WSNI | 100%
505603 | W-W-NI-090320-Amlaird - Generator refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2020-06-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 2138.3 | -24.3 | 2114 | 0 | 2114 | 0 | [6 empty] | CM_WSNI | 100%
505594 | W-W-NI-090320-Bradan - PRGF 1-8 Filter Nozzle Clean (5th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 2358.36 | 29741.64 | 32100 | 0 | 32100 | 0 | [6 empty] | CM_WSNI | 100%
504253 | W-W-NI-091219 - Bradan WTW - 2RGF No. 1 Outlet Flow Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2258.27 | 1631.73 | 3890 | 0 | 3890 | 0 | [6 empty] | CM_WSNI | 100%
504256 | W-W-NI-091219 - Bradan WTW - Inlet Poly Pump and SCADA | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 7787.94 | 0 | 7787.94 | 0 | 7787.94 | 0 | [6 empty] | CM_WSNI | 100%
504250 | W-W-NI-091219- Bradan WTW - Site Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 8214.56 | -3102.22 | 5112.34 | 0 | 5112.34 | 0 | [6 empty] | CM_WSNI | 100%
505617 | W-W-NI-100320 - Bradan - PRGF 7 Trough Leaks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-12 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 664.07 | 4846.93 | 5511 | 0 | 5511 | 0 | [6 empty] | CM_WSNI | 100%
505630 | W-W-NI-100320 - Bradan - Turbine House SCADA Link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-12 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 7171.14 | 794.86 | 7966 | 0 | 7966 | 0 | [6 empty] | CM_WSNI | 100%
504276 | W-W-NI-101219 - Afton WTW - Sludge Conveyor Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-10 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 7005 | -159.82 | 6845.18 | 0 | 6845.18 | 0 | [6 empty] | CM_WSNI | 100%
504280 | W-W-NI-101219 - Penwhapple WTW - Poly Mixer Spool Piece | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-10 |  | 2020-04-30 |  | - | 0 | 0 | 0 | 0 | 0 | 2990 | -1120.53 | 1869.47 | 0 | 1869.47 | 0 | [6 empty] | CM_WSNI | 100%
504300 | W-W-NI-111219 - Bradan WTW - Alum Pump Power Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-11 |  | 2020-04-30 |  | - | 0 | 0 | 0 | 0 | 0 | 3645.05 | 93.88 | 3738.93 | 0 | 3738.93 | 0 | [6 empty] | CM_WSNI | 100%
504303 | W-W-NI-111219 - Lochranza WTW - Treated Water Colour Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-11 |  | 2020-04-30 |  | - | 0 | 0 | 0 | 0 | 0 | 3777 | -1440.17 | 2336.83 | 0 | 2336.83 | 0 | [6 empty] | CM_WSNI | 100%
503803 | W-W-NI-121119-Canada Hill DSR-Replace telemetry outstation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-18 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1539.75 | -578.81 | 960.94 | 0 | 960.94 | 0 | [6 empty] | CM_WSNI | 100%
503800 | W-W-NI-121119-Finlas WTW- Replace pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-18 |  | 2020-03-31 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 1268.57 | 0 | 1268.57 | 0 | 1268.57 | 0 | [6 empty] | CM_WSNI | 100%
504309 | W-W-NI-121219 - Balmichael WTW - BH No 5 Generator Reurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2650.99 | 3.01 | 2654 | 0 | 2654 | 0 | [6 empty] | CM_WSNI | 100%
504328 | W-W-NI-121219 - Balmore WTW - Rep. Main Drives | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 63761.89 | -16958.89 | 46803 | 0 | 46803 | 0 | [6 empty] | CM_WSNI | 100%
504314 | W-W-NI-121219 - Lochranza WTW - Generator Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1303.85 | 1.15 | 1305 | 0 | 1305 | 0 | [6 empty] | CM_WSNI | 100%
504306 | W-W-NI-121219 - Penwhapple WTW - DAF 2&3 Nozzle Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-04-30 |  | - | 0 | 0 | 0 | 0 | 0 | 4811 | -1806.5 | 3004.5 | 0 | 3004.5 | 0 | [6 empty] | CM_WSNI | 100%
504340 | W-W-NI-131219 - Amlaird WTW - Refurb of Soda Ash Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-06-25 | 2020-06-26 | - | 0 | 0 | 0 | 0 | 0 | 3971.85 | 0.15 | 3972 | 0 | 3972 | 0 | [6 empty] | CM_WSNI | 100%
504342 | W-W-NI-131219 - Amlaird WTW - Replacement Coag Lime Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 13163 | 0 | 13163 | 0 | 13163 | 0 | [6 empty] | CM_WSNI | 100%
504345 | W-W-NI-131219 - Finlas WTW - MCC room roof condition survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 | 2020-06-30 | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 1284 | 4066 | 5350 | 0 | 5350 | 0 | [6 empty] | WSNI | 100%
504343 | W-W-NI-131219 - Loch Eck WTW Landslide risk assessment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-29 | 2020-02-13 | 2020-11-12 | 2020-11-13 | - | 0 | 0 | 0 | 0 | 0 | 1068.4 | 0 | 1068.4 | 0 | 1068.4 | 0 | [6 empty] | WSNI | 100%
504651 | W-W-NI-150120-Cameron raw BPT - install livestock proof fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
504650 | W-W-NI-150120-Finlas WTW - main MCC relays replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 8419 | 0 | 8419 | 0 | 8419 | 0 | [6 empty] | CM_WSNI | 100%
504352 | W-W-NI-161219 - Belmore WTW - Tank mixer B replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1049.14 | 0 | 1049.14 | 0 | 1049.14 | 0 | [6 empty] | WSNI | 100%
505226 | W-W-NI-170220-Amlaird WTW - Replacement Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2020-06-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 1540.8 | 4879.2 | 6420 | 0 | 6420 | 0 | [6 empty] | WSNI | 100%
505239 | W-W-NI-170220-Loch Eck WTW - Aztec 1000 alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2020-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 3653.76 | 11570.24 | 15224 | 0 | 15224 | 0 | [6 empty] | CM_WSNI | 100%
505767 | W-W-NI-17030- Castlemilk - Reinstate Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 189 | 2700 | 2889 | 0 | 2889 | 0 | [6 empty] | CM_WSNI | 100%
505773 | W-W-NI-170320- Amlaird - Replacement Alum Pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 81.84 | 1169.16 | 1251 | 0 | 1251 | 0 | [6 empty] | CM_WSNI | 100%
505777 | W-W-NI-170320- Picketlaw - Supernatant Return Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 327.3 | 3474.98 | 3802.28 | 0 | 3802.28 | 0 | [6 empty] | CM_WSNI | 100%
505801 | W-W-NI-180320- Muirdykes - Sludge Holding Tank Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 1344 | 19200 | 20544 | 0 | 20544 | 0 | [6 empty] | CM_WSNI | 100%
505812 | W-W-NI-180320-Blairlinnans WTW - Alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 1653.18 | 23616.82 | 25270 | 0 | 25270 | 0 | [6 empty] | CM_WSNI | 100%
505793 | W-W-NI-180320-Greenbank - Replacement Sample Tap | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 1285.58 | 18365.42 | 19651 | 0 | 19651 | 0 | [6 empty] | CM_WSNI | 100%
505800 | W-W-NI-180320-Greenock - Final Water Sample Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-25 |  | 2020-06-30 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 238 | 3400 | 3638 | 0 | 3638 | 0 | [6 empty] | CM_WSNI | 100%
505787 | W-W-NI-180320-Greenock - IBC Replacement for Lime Batch Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 1600 | 5 | 1605 | 0 | 1605 | 0 | [6 empty] | CM_WSNI | 100%
503854 | W-W-NI-181119-Belmore WTW-Mn Sampling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS2 |  | 2019-11-18 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4384.35 | 0 | 4384.35 | 0 | 4384.35 | 0 | [6 empty] | CM_M&G | 100%
505809 | W-W-NI-190320 - Loch Ascog - Inlet valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 340.91 | 4870.09 | 5211 | 0 | 5211 | 0 | [6 empty] | CM_WSNI | 100%
505822 | W-W-NI-190320-Turret - Filter 3 washout rotork | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 225.11 | 3215.89 | 3441 | 0 | 3441 | 0 | [6 empty] | CM_WSNI | 100%
504437 | W-W-NI-191219 - Amlaird WTW - LED Lighting | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4114.95 | -1714.95 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WSI | 100%
504428 | W-W-NI-191219- Amlaird WTW - Replacement Washwater Actuator | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4229 | 0 | 4229 | 0 | 4229 | 0 | [6 empty] | CM_WSI | 100%
505833 | W-W-NI-200320-Muirdykes - DAF No. 1 Gearbox | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2020-06-30 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 3200.63 | 9.37 | 3210 | 0 | 3210 | 0 | [6 empty] | CM_WSNI | 100%
504442 | W-W-NI-201219 - Balmore WTW - Water Colour Monitor | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 14007.93 | 0.07 | 14008 | 0 | 14008 | 0 | [6 empty] | CM_WSI | 100%
504450 | W-W-NI-201219 - Carron Valley Replace poly dosing pumps | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 24709 | 0 | 24709 | 0 | 24709 | 0 | [6 empty] | CM_WSI | 100%
504447 | W-W-NI-201219- Carron Valley WTW Rotork valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2767.35 | 0 | 2767.35 | 0 | 2767.35 | 0 | [6 empty] | CM_WSI | 100%
505346 | W-W-NI-210220-Burncrooks WTW - Sludge Press cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 16369 | 16369 | 0 | 16369 | 0 | [6 empty] | CM_WSNI | 100%
505341 | W-W-NI-210220-Camphill - Sludge Plate Overhaul | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-25 |  | 2020-06-30 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 2814.48 | 8912.52 | 11727 | 0 | 11727 | 0 | [6 empty] | CM_WSNI | 100%
503912 | W-W-NI-211119-Bradan WTW - Sludge Press C Filter Cloth Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 11999.23 | 0 | 11999.23 | 0 | 11999.23 | 0 | [6 empty] | Wa6 | 100%
505891 | W-W-NI-230320-Gorbals Drumboyhill - Outlet Valve No 2 Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2020-06-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 8690.89 | 1.11 | 8692 | 0 | 8692 | 0 | [6 empty] | CM_WSNI | 100%
505895 | W-W-NI-230320-Turret - Lime system investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 114.16 | 1630.84 | 1745 | 0 | 1745 | 0 | [6 empty] | CM_WSNI | 100%
505379 | W-W-NI-240220-Carrick Castle - CL2 dosing pump replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 1223.28 | 260.72 | 1484 | 0 | 1484 | 0 | [6 empty] | CM_WSNI | 100%
505380 | W-W-NI-240220-Carrick Castle- Raw inlet valve actuator replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 1673 | 1673 | 0 | 1673 | 0 | [6 empty] | CM_WSNI | 100%
505382 | W-W-NI-240220-Picketlaw - Thickening sludge Pipework replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2020-06-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 1389.1 | 97.9 | 1487 | 0 | 1487 | 0 | [6 empty] | CM_WSNI | 100%
505910 | W-W-NI-240320-Carron Valley- Roof replace bullnoses | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 416.01 | 5942.99 | 6359 | 0 | 6359 | 0 | [6 empty] | CM_WSNI | 100%
503952 | W-W-NI-251119-Bradan WTW - Carrier Water Relocation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 27360.65 | 0 | 27360.65 | 0 | 27360.65 | 0 | [6 empty] | CM_WSNI | 100%
505416 | W-W-NI-260220-Balmore WTW - Replacement Thermometers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-06-30 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 1872.99 | 1872.99 | 0 | 1872.99 | 0 | [6 empty] | CM_WSNI | 100%
505427 | W-W-NI-260220-Glenhove DSR - Retrofit AK Breaker Dal No 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-06-30 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 11182 | 11182 | 0 | 11182 | 0 | [6 empty] | CM_WSNI | 100%
503986 | W-W-NI-261119-Carron Valley WTW - Interlock Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1938.16 | -650.05 | 1288.11 | 0 | 1288.11 | 0 | [6 empty] | CM_WSNI | 100%
504873 | W-W-NI-270120-Afton WTW - Lamella Feed Pumps Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3705.46 | 0 | 3705.46 | 0 | 3705.46 | 0 | [6 empty] | CM_WSNI | 100%
504870 | W-W-NI-270120-Afton WTW - Sludge Tanker Turning Area | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2904.33 | 0 | 2904.33 | 0 | 2904.33 | 0 | [6 empty] | CM_WSNI | 100%
504868 | W-W-NI-270120-Bradan WTW - Sludge Buffer Tank Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2235.36 | -492.75 | 1742.61 | 0 | 1742.61 | 0 | [6 empty] | CM_WSNI | 100%
504874 | W-W-NI-270120-Penwhapple WTW - GAC Air Scour Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-27 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2502.41 | -560.5 | 1941.91 | 0 | 1941.91 | 0 | [6 empty] | CM_WSNI | 100%
505437 | W-W-NI-270220-Crianlarich new road investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 1284 | 4066 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
505433 | W-W-NI-270220-Drumchapel WT - 2 VSDs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2020-06-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2310.99 | 2310.99 | 0 | 2310.99 | 0 | [6 empty] | WSNI | 100%
505957 | W-W-NI-270320-Carron Valley - Heaters replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 2696 | 2696 | 0 | 2696 | 0 | [6 empty] | CM_WSNI | 100%
505954 | W-W-NI-270320-Dhu Loch - post soda pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 3607 | 3607 | 0 | 3607 | 0 | [6 empty] | CM_WSNI | 100%
505955 | W-W-NI-270320-Ross Priory-Blairlinnans No2 motor cable | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-06-30 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 14980 | 14980 | 0 | 14980 | 0 | [6 empty] | CM_WSNI | 100%
505958 | W-W-NI-270320-Tyndrum Heater replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 2349 | 2349 | 0 | 2349 | 0 | [6 empty] | CM_WSNI | 100%
504014 | W-W-NI-271119-Belmore WTW - TE item Mn stage recommissioning scope | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-29 | 2020-07-10 | 2020-09-10 | 2020-10-08 | - | 0 | 0 | 0 | 0 | 0 | 10700 | 0 | 10700 | 0 | 10700 | 0 | [6 empty] | CM_WSNI | 100%
503998 | W-W-NI-271119-Penwhapple WTW - Ortho Bund Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-29 | 2020-08-26 | 2021-03-02 | 2021-03-30 | - | 0 | 0 | 0 | 0 | 0 | 1382.09 | 3967.91 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
504885 | W-W-NI-280120-Bradan WTW - Coag Lime Pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 12626.63 | -2584.31 | 10042.32 | 0 | 10042.32 | 0 | [6 empty] | CM_WSNI | 100%
504879 | W-W-NI-280120-Camphill WTW - Thickened Sludge Transfer Pump 2 R&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-29 |  | - | 0 | 0 | 0 | 0 | 0 | 2772.74 | -729.76 | 2042.98 | 0 | 2042.98 | 0 | [6 empty] | CM_WSNI | 100%
504880 | W-W-NI-280120-Castlehill TWP - Pump 2 Motor Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 8319.44 | -2190.51 | 6128.93 | 0 | 6128.93 | 0 | [6 empty] | WSNI | 100%
504881 | W-W-NI-280120-Muirdykes WTW - DAF Scraper No. 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 3644.19 | -964.53 | 2679.66 | 0 | 2679.66 | 0 | [6 empty] | CM_WSNI | 100%
504897 | W-W-NI-290120-Amlaird WTW-Chlorine Injectors replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 3492.11 | -927.74 | 2564.37 | 0 | 2564.37 | 0 | [6 empty] | CM_WSNI | 100%
504895 | W-W-NI-290120-Amlaird WTW-DAF 3 Turbidity Meter replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 5551.71 | -1474.56 | 4077.15 | 0 | 4077.15 | 0 | [6 empty] | CM_WSNI | 100%
504899 | W-W-NI-290120-Bradan WTW - PRGF 1-8 Filter Nozzle Clean (4th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-29 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 29630.51 | -6057.69 | 23572.82 | 0 | 23572.82 | 0 | [6 empty] | CM_WSNI | 100%
504084 | W-W-NI-291119 - Bradan WTW - Backwash Chamber Cover Plates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-02 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 13212.53 | -4966.54 | 8245.99 | 0 | 8245.99 | 0 | [6 empty] | CM_WSNI | 100%
504074 | W-W-NI-291119 - Brig o Turk Comms link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-02 |  | 2020-04-30 |  | - | 0 | 0 | 0 | 0 | 0 | 1915.28 | -720.35 | 1194.93 | 0 | 1194.93 | 0 | [6 empty] | CM_WSNI | 100%
504194 | W-W-NI-291119- Alloa WWTW NS887918 - SR15 Support survey (MCC) - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504067 | W-W-NI-291119-Turret WTW Poly Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2284.74 | -858.93 | 1425.81 | 0 | 1425.81 | 0 | [6 empty] | CM_WSNI | 100%
504931 | W-W-NI-300120-Bradan WTW - PRGF 5 Trough Leaks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-30 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 4224.53 | -1120.42 | 3104.11 | 0 | 3104.11 | 0 | [6 empty] | CM_WSNI | 100%
504932 | W-W-NI-300120-Penwhapple WTW - Sludge Thickener Feed Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-30 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 6006.72 | 927.79 | 6934.51 | 0 | 6934.51 | 0 | [6 empty] | CM_WSNI | 100%
504947 | W-W-NI-300120-Turret WTW PACL pump no2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-30 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 2517.73 | -668.63 | 1849.1 | 0 | 1849.1 | 0 | [6 empty] | CM_WSNI | 100%
504955 | W-W-NI-310120-Highlees SR - Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 4352.2 | 997.8 | 5350 | 0 | 5350 | 0 | [6 empty] | CM_WSNI | 100%
503781 | WW-NI-WEST-Stevenston Point WwTW- MH Cover Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2019-10-31 |  | 2019-12-31 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 4650 | 0 | 4650 | 0 | 4650 | 0 | [6 empty] | CM_M&G | 100%
500613 | WWSS Asset Intelligence SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1412797.66 | 431128.43 | 377446.24 | 269158.7 | 120916.11 | 710671.64 | 3322118.78 | 115690.71 | 3437809.49 | 0 | [6 empty] | CM_OVH | 100%
500612 | WWSS Env Reg and Climate Change SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 36843.55 | 63168.35 | 97971.08 | 88426.83 | 81261.32 | 86570.77 | 454241.9 | 14092.93 | 468334.83 | 0 | [6 empty] | CM_OVH | 100%
500608 | WWSS Flooding SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 285093.28 | 938008.92 | 900162.54 | 1165573.37 | 1366556.6 | 662702.24 | 5318096.95 | 107881.76 | 5425978.71 | 0 | [6 empty] | CM_OVH | 100%
500610 | WWSS Risk & Lifecycle Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 470815.56 | 1269075.28 | 1787261.27 | 2097023.03 | 1127310.28 | 1612855.43 | 8364340.85 | 262557.85 | 8626898.7 | 0 | [6 empty] | CM_OVH | 100%
500609 | WWSS Technical Support and Assurance SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 104390.26 | 1091334.98 | 1677472.51 | 1614271.27 | 1458930.93 | 1110015.35 | 7056415.3 | 180700.2 | 7237115.5 | 0 | [6 empty] | CM_OVH | 100%
500607 | WWSS WW Service Strategy SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 211082.55 | 337016.64 | 499915.9 | 644814.71 | 185556.72 | 491150.89 | 2369537.41 | 79954.81 | 2449492.22 | 0 | [6 empty] | CM_OVH | 100%
401326 | WWTW - Scraper Bridge Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-02-08 | 2010-08-23 | 2010-08-23 | 2015-06-02 |  | Scottish Water Wide | 309428.15 | -309428.15 | 0 | 0 | 0 | 0 | 0.01 | -309428.14 | 0 | 0.01 | 0 | [6 empty] | CM_WWNI | 100%
504034 | W-WW - NI - 211119 - Lochgoilhead WWTW - Replace Chlorine Pump - 1.6K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
505798 | W-WW-120320- ARDROSSAN WWPS 2 NS226419 - H&S- SURVEY MCC PANEL - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-03 |  | 2020-07-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 595.33 | 8504.67 | 9100 | 0 | 9100 | 0 | [6 empty] | CM_WWNI | 100%
505808 | W-WW-180320- FAST TRACK - BISHOPTON WWPS NS444700 - Refurb Submersible Pump - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2020-06-30 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 484.11 | 5139.89 | 5624 | 0 | 5624 | 0 | [6 empty] | CM_WWNI | 100%
504704 | W-WW-INFRA- 16012020- RHU LARGARIE LODGE SEP 2017 NS277835 - ABANDON SEPTIC TANK INSTALL PIPEWORK BYPASS & MANHOLES - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWI | 100%
504115 | W-WW-INFRA- 291119 - Kilbirnie CSO - Sewer Repair Milton St Kilbirnie - 27K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 28389.36 | -1389.36 | 27000 | 0 | 27000 | 0 | [6 empty] | CM_WWI | 100%
504132 | W-WW-INFRA- 291119- Charles Rodger Place Bridge of Allan - 8.5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 8972.8 | -472.8 | 8500 | 0 | 8500 | 0 | [6 empty] | CM_WWI | 100%
504989 | W-WW-INFRA- MAJOR SEWER MANHOLE REPAIR BRANSHILL SAUCHIE ALLOA - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 0 | 10500 | 0 | [6 empty] | CM_WWI | 100%
505263 | W-WW-INFRA-130220- ERSKINE WWTW NS494691 - SEWER REHAB - 43.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2020-03-31 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 43500 | 0 | 43500 | 0 | 43500 | 0 | [6 empty] | CM_WWI | 100%
504921 | W-WW-INFRA-22 Michael Drive Helensburgh - Sewer Relining Works- 36K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | 36000 | 0 | 36000 | 0 | [6 empty] | CM_WWI | 100%
505735 | W-WW-INFRA-BALMAHA WWTW NS420907- Replace gully connection to sewer network - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 163.55 | 2336.45 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWI | 100%
504197 | W-WW-N291119- GIRVAN WWTW - Replace Pipe Manifold - 3.5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 3641.81 | -141.81 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
504029 | W-WW-NI- 211119 - Stirling STC - Replace Pump Motor - 2k - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
503965 | W-WW-NI- 251119- Bonnybridge WwTW NS836811 - Replace Drive & Trailing Wheels on FST 2 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 8469.3 | -469.3 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
504136 | W-WW-NI- 291119 - Girvan WWTW NX190999 - Modify Lifting Crane - 1.9K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2007.91 | -107.91 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
504195 | W-WW-NI- Callander Park WWPS 1994 NS904792 - FAST TRACK-Replace Foul Pump Guiderails & Pump Stool - 5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
505481 | W-WW-NI- FAST TRACK - MANSFIELD HEIGHTS WWPS 2007 NS623142 - Replace Foul Transfer Pump 1 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-05-25 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 130.84 | 1869.16 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505476 | W-WW-NI- FAST TRACK 20FEB20 - BISHOPTON WWPS NS444700 - REFURBISH SUBMERSIBLE PUMP - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-05-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 10534.29 | 65.71 | 10600 | 0 | 10600 | 0 | [6 empty] | CM_WWNI | 100%
504121 | W-WW-NI- IRVINE SPORTS CLUB SPS 2012 NS314392 - New VSD in Control Panel - 8K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 8255.56 | -255.56 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
504392 | W-WW-NI- LUGGIEBANK WWPS NS763728 - Replace Submersible Pump - FAST TRACK - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
503783 | W-WW-NI-011119-Laighpark WwTW-Sludge Pump Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-01-31 | 2020-01-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 5425.53 | 0 | 5425.53 | 0 | 5425.53 | 0 | [6 empty] | CM_WWNI | 100%
506049 | W-WW-NI-020420- LOMOND IND EST WWPS 1999 NS395808 - Replace Sewage Pumps 1&2 and associated Guide Rails - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-03 |  | 2020-08-31 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504133 | W-WW-NI-021119- Erskine WWTW NS494691 - Fast Track Replace Storm Pump - 8K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
504134 | W-WW-NI-021119- ERSKINE WWTW NS494691 - REPLACE DRAIN DOWN PUMP - FAST TRACK - 4.2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-06-30 |  | - | 0 | 0 | 0 | 0 | 0 | 4460.19 | -260.19 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
504110 | W-WW-NI-021219- COWIE WWTW 1972 NS849899 - REPLACE SCRAPERS SCUMBOARDS & CENTRE COLUMN - 7K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 0 | [6 empty] | CM_WWNI | 100%
504105 | W-WW-NI-021219- DALDERSE WWTW 1966 NS903822 - REPACE PULSATION DAMPNER 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 2034.84 | -34.84 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504095 | W-WW-NI-021219- Dumbarton Distillery WWPS NS397751 - Replace Roof 7.6k - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 7600 | 0 | 7600 | 0 | 7600 | 0 | [6 empty] | CM_WWNI | 100%
504604 | W-WW-NI-030120-LUGGIEBANK WWPS NS763728- Replace Pump - FAST TRACK - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-05-31 |  | - | 0 | 0 | 0 | 0 | 0 | 8500 | 3500 | 12000 | 0 | 12000 | 0 | [6 empty] | CM_WWNI | 100%
505582 | W-WW-NI-050320- BUCHLYVIE WWTW 1996 NS574942 - EMERGENCY REFURB OF SCRAPER BRIDGE DRIVE WHEEL & GEARBOX - 7.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 7687.74 | 12.26 | 7700 | 0 | 7700 | 0 | [6 empty] | CM_WWNI | 100%
505716 | W-WW-NI-050320- CUMNOCK UNDERWOOD WWTW NS558204 -REFURB INLET SCREENS 1 & 2 - 21.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-09-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 1400 | 20000 | 21400 | 0 | 21400 | 0 | [6 empty] | CM_WWNI | 100%
505640 | W-WW-NI-050320- SHIELDHALL WWTW NS533659- Replacement VSD for aerator 2/4 - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 2178.8 | 21.2 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WWNI | 100%
505562 | W-WW-NI-05032020-HEALTH & SAFETY - IRVINE BEACH PARK WWPS NS312374 - Replace wet well covers - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-05-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 484.11 | 6915.89 | 7400 | 0 | 7400 | 0 | [6 empty] | CM_WWNI | 100%
505632 | W-WW-NI-050320-AYR SHORE ROAD WWPS NS338232- Refurb Storm Stripping Pump - 29.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 1949.53 | 27850.47 | 29800 | 0 | 29800 | 0 | [6 empty] | CM_WWNI | 100%
505718 | W-WW-NI-050320-DALDERSE WWTW 1966 NS903822- Remove trailing wheel assemble supply new wheel bearing refurb and install - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 163.55 | 2336.45 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505560 | W-WW-NI-050320-HEALTH & SAFETY- STEWARTON WWTW NS408449 - Replace mesh flooring & install Handrails - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-06-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 693.46 | 9906.54 | 10600 | 0 | 10600 | 0 | [6 empty] | CM_WWNI | 100%
505726 | W-WW-NI-050320-LAIGHPARK PAISLEY WWTW NS485655- REPLACE FST CABLE -4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 261.68 | 2778.32 | 3040 | 0 | 3040 | 0 | [6 empty] | CM_WWNI | 100%
505745 | W-WW-NI-050320-NEWFORD GROVE WWPS NS577562 - Replace Submersible Pump - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-16 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 287.85 | 3056.15 | 3344 | 0 | 3344 | 0 | [6 empty] | CM_WWNI | 100%
505646 | W-WW-NI-050320-STEWARTON WWTW NS408449- REPLACE TWO FAULTY MOTORS ON PISTA GRIT PLANT- 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 1676.73 | 23.27 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
505712 | W-WW-NI-050320-STIRLING WWTW 1968 NS808935- REPLACE SBR BLOWER SENTINEL CONTROL UNIT - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-13 |  | 2020-06-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 359.81 | 5140.19 | 5500 | 0 | 5500 | 0 | [6 empty] | CM_WWNI | 100%
505728 | W-WW-NI-050320-UNDERWOOD (CUMNOCK) STC- CHANNEL DRAIN - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 163.55 | 2336.45 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505715 | W-WW-NI-050320-UNDERWOOD (CUMNOCK) STC- REPLACE ROTORK VALVE - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 333.64 | 4766.36 | 5100 | 0 | 5100 | 0 | [6 empty] | CM_WWNI | 100%
505122 | W-WW-NI-060220- BRAEHEAD SHOPPING CENT WWPS NS523670 - Replace Guide Rails - 11K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-06-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 11000 | 5000 | 16000 | 0 | 16000 | 0 | [6 empty] | CM_WWNI | 100%
505074 | W-WW-NI-060220- COYLTON WWTW NS401200 - Replace Inlet Screen Basket - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 8100 | 0 | 8100 | 0 | 8100 | 0 | [6 empty] | CM_WWNI | 100%
505127 | W-WW-NI-060220- DALMARNOCK SLUDGE WWPS 2000 NS610624 - Replace PLC CPU - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-13 |  | 2020-03-31 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505069 | W-WW-NI-060220- DUNLOP ALLANVALE WWPS 2009 NS407497 - REPLACE 2X FOUL PUMPS - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505120 | W-WW-NI-060220- LARGS WWTW NS194624 - Replace HMI on MCC2 - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 5500 | 0 | [6 empty] | CM_WWNI | 100%
505104 | W-WW-NI-060220- LOCHWINNOCH WWTW 1971 NS356589 - Replace RAS return pump - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
505101 | W-WW-NI-060220- POLMONTHILL WWPS 2000 NS953795 - Replace Foul Pump - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505102 | W-WW-NI-060220- POWBURN WWPS NS352266- Replace Gear box on isolation valve - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505081 | W-WW-NI-060220- STEWARTON WWTW NS408449 - Fit sludge draw-off pipe - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505079 | W-WW-NI-06022020- GIRVAN HARBOUR WWPS NX818982 - REPLACE ACTUATOR - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
504768 | W-WW-NI-090120- DALRYMPLE WWTW NS353141 - Replace RAS Pump 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504757 | W-WW-NI-090120- MACINTYRE COURT WWPS NS353266 - Refurbish Control Panel - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | [6 empty] | CM_WWNI | 100%
504665 | W-WW-NI-09012020- WEST KILBRIDE FOUL WWPS NS205464 - REFURBISH FOUL PUMP - URGENT - 17.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 0 | 17500 | 0 | [6 empty] | CM_WWNI | 100%
505628 | W-WW-NI-100320- PRIORITY-DALGRAIN WWPS 1976 NS915823- REFURB 3.3KV STARTER - 15K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-10 |  | 2020-06-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 4278.81 | 12321.19 | 16600 | 0 | 16600 | 0 | [6 empty] | CM_WWNI | 100%
505621 | W-WW-NI-100320-PRIORITY-DALGRAIN WWPS 1976 NS915823- Replace Motor - 49.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 3244.86 | 46355.14 | 49600 | 0 | 49600 | 0 | [6 empty] | CM_WWNI | 100%
505697 | W-WW-NI-11032020-FAST TRACK- MEADOWHEAD WWPS NS333356 - REPLACE FOUL PUMP 2 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 130.84 | 1869.16 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505694 | W-WW-NI-110320-FAST TRACK- ARROCHAR WWPS 1 NN294036 - REPLACE FOUL PUMP 1 - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-12 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 287.85 | 4112.15 | 4400 | 0 | 4400 | 0 | [6 empty] | CM_WWNI | 100%
505670 | W-WW-NI-110320-FAST TRACK- DALDERSE STC- REPLACE FILTRATE PUMP A - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 196.26 | 2803.74 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
505665 | W-WW-NI-110320-FAST TRACK- ZETLAND PARK WWPS 2000 NS929811 - Refurb Storm Pump No3 - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 294.39 | 4205.61 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWNI | 100%
504406 | W-WW-NI-11219- AUCHANS WWPS NS358349 - Refurb damaged pump - 16.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 16500 | 0 | 16500 | 0 | 16500 | 0 | [6 empty] | CM_WWNI | 100%
505805 | W-WW-NI-120320- ARDROSSAN WWPS 1 NS226419 - REPLACE 3X DOORS - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-03 |  | 2020-07-03 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 248.6 | 3551.4 | 3800 | 0 | 3800 | 0 | [6 empty] | CM_WWNI | 100%
505807 | W-WW-NI-120320- BALMAHA WWTW NS420907 - H&S - Replace site lighting - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-06 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 170.09 | 2429.91 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WWNI | 100%
505703 | W-WW-NI-120320- CASTLEGREEN WWPS NS408745 - REPLACE DRYWELL PUMP No1 - 17K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-12 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 1112.15 | 15887.85 | 17000 | 0 | 17000 | 0 | [6 empty] | CM_WWNI | 100%
505806 | W-WW-NI-120320- GARTOCHARN WWTW NS425863 - HEALTH & SAFETY- REPLACE LIGHTING - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-06 |  | 2020-06-30 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 104.67 | 1495.33 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
505795 | W-WW-NI-120320- GIRVAN STC - REPAIR ACCESS ROAD - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-20 |  | 2020-07-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 654.21 | 9345.79 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
505753 | W-WW-NI-120320- HOPEBANK WWPS NR980700 - Replace Submersible Pump - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-06-16 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 163.55 | 1736.45 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
505786 | W-WW-NI-120320- UNDERWOOD (CUMNOCK) STC - REPLACE CONTROL PANEL DOOR - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-01 |  | 2020-06-18 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 111.21 | 1588.79 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
504476 | W-WW-NI-121219 - DOUNE WWTW NN729008 - Security fence and bio arms - 9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 9000 | 0 | [6 empty] | CM_WWNI | 100%
504454 | W-WW-NI-121219- BONESS WWTW NT022813 - Replace Control Probe - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 1954.19 | 45.81 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504555 | W-WW-NI-121219- DALMARNOCK WWTW NS611627 - Replace Aeration Motor - 2.1K - | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 2207.03 | -107.03 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
504559 | W-WW-NI-121219- DALMARNOCK WWTW NS611627 - Replace HMI Screen - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504417 | W-WW-NI-121219- ERSKINE WWTW NS494691 - replace faulty MLSS Probe - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-04-30 |  | - | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504644 | W-WW-NI-121219- FAIRLIE WWTW 1998 NS207559 - Refurbish Pump - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 10375.97 | -375.97 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504544 | W-WW-NI-121219 -GAILES WWPS NS323359 - REPLACE FOUL SUMP PUMP 3 - URGENT - 81K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | 81000 | 0 | 81000 | 0 | [6 empty] | CM_WWNI | 100%
504598 | W-WW-NI-121219- KINNING PARK WWPS NS55644 - REFURBISH PUMP 3 - 22K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 22000 | 0 | [6 empty] | CM_WWNI | 100%
504596 | W-WW-NI-121219- KINNING PARK WWPS NS575644 - Replacement Soft Start - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504550 | W-WW-NI-121219- PAISLEY LAIGHPARK INLET WWPS NS485655 - REFURBISH GEARBOX INLET PUMP 3 - URGENT - 36K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 42081.7 | -6081.7 | 36000 | 0 | 36000 | 0 | [6 empty] | CM_WWNI | 100%
504459 | W-WW-NI-121219- SHIELDHALL WWTW NS533659 - Driveshaft and sprocket assembly - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504577 | W-WW-NI-121219- SNAB LANE WWPS 1985 NS985810 - Replace Guide Poles - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 4902.29 | 97.71 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504569 | W-WW-NI-121219- STIRLING WWTW 1968 NS808935 - Replacement Actuator - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-08 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
504592 | W-WW-NI-121219- TILLICOULTRY WWTW NS917965 - Refurbish & Replace Drive Unit critical spare for FSTs - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504564 | W-WW-NI-121219-BRODIE GROVE WWPS NS680649- Replace Guide Rails - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504441 | W-WW-NI-121219-HELENSBURGH WWTW 2001 NS321800 - REPLACE WELL PLATES (H&S) - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 10521.21 | -521.21 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504619 | W-WW-NI-121219-UNDERCLIFF RD WWPS 1993 NS190698 - Replace dorrs x3 & Self closing gate x1 - H&S - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | [6 empty] | CM_WWNI | 100%
504409 | W-WW-NI-12219- DUMBARTON DISTILLERY WWPS NS397751 - Install bauer connection - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWNI | 100%
505210 | W-WW-NI-130220- AYR SHORE ROAD WWPS NS338232 - Remove overhead gantry - 11K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-17 |  | 2020-03-31 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 10631.12 | 368.88 | 11000 | 0 | 11000 | 0 | [6 empty] | CM_WWNI | 100%
505229 | W-WW-NI-130220- DALDERSE STC- 3x Gate Valves for de-watering tree - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-17 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 5100 | 0 | 5100 | 0 | [6 empty] | CM_WWNI | 100%
505309 | W-WW-NI-130220- ERSKINE WWTW NS494691 - Replace Motor & SCR Board - 20.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 8377.33 | 12222.67 | 20600 | 0 | 20600 | 0 | [6 empty] | CM_WWNI | 100%
505253 | W-WW-NI-130220- FAIRLIE WWTW 1998 NS207559 - REPLACE GUIDE RAILS X2 - 4.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2020-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 1992.67 | 2907.33 | 4900 | 0 | 4900 | 0 | [6 empty] | CM_WWNI | 100%
505227 | W-WW-NI-130220- LAIGHPARK PAISLEY WWTW NS485655 - Repair Access Road - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-17 |  | 2020-03-31 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 1717.76 | 82.24 | 1800 | 0 | 1800 | 0 | [6 empty] | CM_WWNI | 100%
505314 | W-WW-NI-130220- MAY STREET WWPS NS205585- Replace MH Covers (H&S) - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 772.67 | 1127.33 | 1900 | 0 | 1900 | 0 | [6 empty] | CM_WWNI | 100%
505268 | W-WW-NI-130220- MEADOWHEAD WWTW NS339361 - Access Platform - H&S - 6.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2020-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 2602.67 | 3797.33 | 6400 | 0 | 6400 | 0 | [6 empty] | CM_WWNI | 100%
505311 | W-WW-NI-130220- MEADOWHEAD WWTW NS339361 - New Filter for final effluent washwater - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 1504.67 | 2195.33 | 3700 | 0 | 3700 | 0 | [6 empty] | CM_WWNI | 100%
505313 | W-WW-NI-130220- MEADOWHEAD WWTW NS339361 - Screen Plates - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 1382.67 | 2017.33 | 3400 | 0 | 3400 | 0 | [6 empty] | CM_WWNI | 100%
505242 | W-WW-NI-130220- PAISLEY LAIGHPARK SLDG TFR WWPS NS485655 - refurb sludge pump no.2 - 10.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-17 |  | 2020-03-31 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 10400 | 0 | [6 empty] | CM_WWNI | 100%
505207 | W-WW-NI-130220- TILLICOULTRY WWTW NS917965 - REFURBISH AERATOR - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-14 |  | 2020-03-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 2800 | 0 | 2800 | 0 | [6 empty] | CM_WWNI | 100%
505312 | W-WW-NI-130220- WEST KILBRIDE FOUL WWPS NS205464 - Foul Pump Refurb - 11.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 4839.33 | 7060.67 | 11900 | 0 | 11900 | 0 | [6 empty] | CM_WWNI | 100%
503813 | W-WW-NI-131119-Boness WwTW- Replace Service Water Booster Pump 1 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-05-29 |  | - | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
503821 | W-WW-NI-131119-BRAEHEAD SHOPPING CENTRE WWPS-New Components for electrical & pump install- JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 | 2020-03-01 | - | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 4100 | 0 | 4100 | 0 | [6 empty] | WWNI | 100%
504646 | W-WW-NI-140120-Stevenston Point WWTW-Critical Spares-11.1k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 11140.71 | -40.71 | 11100 | 0 | 11100 | 0 | [6 empty] | CM_WWNI | 100%
503823 | W-WW-NI-141119-Kinning Park WWPS - Refurb & Install of Motor No3 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 | 2020-03-01 | - | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 4100 | 0 | 4100 | 0 | [6 empty] | CM_WWNI | 100%
503825 | W-WW-NI-141119-Paisley Laighpark SLDG TFR WWPS -Supply & Fit new Ventilation Fan - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-06-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2059.88 | -59.88 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504657 | W-WW-NI-15012020- EASTER DULLATUR WWPS 2008 NS745773 - REPLACE SUBMERSIBLE PUMP - FAST TRACK - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
504799 | W-WW-NI-16012- CAMERON HOUSE (REAR) WWPS NS375830- Replace both internal risers & fit bauer couplings - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
504756 | W-WW-NI-16012020- BONNYBRIDGE WWTW NS836811 - Portable Pump - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504707 | W-WW-NI-16012020- BONNYBRIDGE WWTW NS836811 - Replace current feed pump with a Rotary Lobe Feed Pump - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504710 | W-WW-NI-16012020- BONNYBRIDGE WWTW NS836811 - Replace failed Motor Gearbox - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504790 | W-WW-NI-160120-ABBOTSHAUGH WWPS 1975 NS900815- REPLACE FOUL PUMP - 8.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 8200 | 0 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WWNI | 100%
504896 | W-WW-NI-160120-ARDOCH WWTW 2002 NS374758- Gearbox & Wheel Replacement- 6.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WWNI | 100%
504794 | W-WW-NI-160120-ARDROSSAN WWPS 2 NS226419- REFURBISH STORM SCREEN - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
504795 | W-WW-NI-160120-BUCHANS BRIDGE WWPS NS473062- REPLACE SUBMERSIBLE PUMP - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  |  |  | - | 0 | 0 | 0 | 0 | 0 | 1917.58 | 82.42 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504798 | W-WW-NI-160120-DALMELLINGTON WWTW NS476050- Refurbish Inlet Pump - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504793 | W-WW-NI-160120-KIPPEN WWTW NS653952- REPLACE LIQUOR RETURN PUMP - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504792 | W-WW-NI-160120-STIRLING STC- BUILDING ALTERATIONS - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | [6 empty] | CM_WWNI | 100%
504766 | W-WW-NI-160120-STIRLING WWTW 1968 NS808935- Refurbish Aerator Gearbox - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 0 | 10500 | 0 | [6 empty] | CM_WWNI | 100%
504796 | W-WW-NI-160120-STIRLING WWTW 1968 NS808935- Replace actuators x2 supply only - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 0 | [6 empty] | CM_WWNI | 100%
505760 | W-WW-NI-170320 - DALDERSE STC - BOILER REPAIR - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-06 |  | 2020-06-17 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 372.9 | 5327.1 | 5700 | 0 | 5700 | 0 | [6 empty] | CM_WWNI | 100%
505764 | W-WW-NI-170320- DOLLAR WWTW NS953978 - REPLACE SBR DECANTER ARM - 8.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-19 |  | 2020-07-17 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 536.45 | 7663.55 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WWNI | 100%
505283 | W-WW-NI-190220- EAST BAY WWPS NS175767 - fast track - 8.2KReplace Pump - | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2020-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 3253.33 | 4746.67 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
505854 | W-WW-NI-190320- BALFRON WWTW NS548883 - REPLACE DISCHARGE SPIRAL SCREW - 17.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-30 |  | 2020-07-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 1144.86 | 16355.14 | 17500 | 0 | 17500 | 0 | [6 empty] | CM_WWNI | 100%
505863 | W-WW-NI-190320- GIRVAN WWTW NX190999 - Replace Actuator - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-30 |  | 2020-07-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 163.55 | 2336.45 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505858 | W-WW-NI-19032020- H&S- KELLIEBANK WWPS 1967 NS874925 - RE-ROOF PUMP HOUSE BUILDING - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-30 |  | 2020-07-30 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 405.61 | 5794.39 | 6200 | 0 | 6200 | 0 | [6 empty] | CM_WWNI | 100%
505856 | W-WW-NI-19032020- STEVENSTON POINT WWTW NS275404 - Replace Bar Screen Ties - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-30 |  | 2020-07-30 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 130.84 | 1869.16 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
503865 | W-WW-NI-191119-Kinning Park WWPS- New Hot Wash Power Washer- JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | WWNI | 100%
504667 | W-WW-NI-191219- DOLLAR WWTW NS953978 - Replace Motor & Gearbox Refurbish Jacking Sleeve - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2020-03-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504751 | W-WW-NI-191219- DUMBARTON DISTILLERY WWPS NS397751 - Line Rising Main Pipework - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504690 | W-WW-NI-191219- GIRVAN STC - Replace faulty lighting on SBR gantry walk way - 2k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504649 | W-WW-NI-191219- GRANGEBURN ROAD WWPS 1927 NS930821 - Replace Foul Pump - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504625 | W-WW-NI-191219- HOLMSTON WWPS 2 NS358214 - Replace & Reinstate Duck foot - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504616 | W-WW-NI-191219- MACINTYRE COURT WWPS NS353266 - Replace guide rails x4 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504678 | W-WW-NI-191219- PATNA WWTW NS414124 - REPLACE LIFTING GANTRY - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504581 | W-WW-NI-191219- POWBURN WWPS NS352266 - Replace Ventilation - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWNI | 100%
504653 | W-WW-NI-191219- ROTHESAY WWTW 2002 NS100637 - REPLACE 3X KNIFE VALVES & SPINDLES - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
504673 | W-WW-NI-191219- STIRLING WWTW 1968 NS808935 - REPLACE ACTUATOR - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504663 | W-WW-NI-191219- STIRLING WWTW 1968 NS808935 - Replace Scum box scrapers winches & hardware - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504677 | W-WW-NI-191219- UNDERWOOD (CUMNOCK) STC - REPLACE SUMP PUMP - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-06-01 |  | - | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
504438 | W-WW-NI-191219- UNDERWOOD (CUMNOCK) STC -Replace Mobile hoist crane - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2609.67 | -109.67 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505563 | W-WW-NI-200220- GIRVAN STC- Replace Sludge Mixer Pump - 10.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-05-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 673.83 | 9626.17 | 10300 | 0 | 10300 | 0 | [6 empty] | CM_WWNI | 100%
505402 | W-WW-NI-200220- KINNING PARK WWPS NS575644 -Replace Gas Main Extraction Fan- 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2020-05-11 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 3900 | 0 | 3900 | 0 | [6 empty] | CM_WWNI | 100%
505599 | W-WW-NI-200220- LINWOOD WWPS NS447648 - Refurb Pump - 14.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-05-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 274.77 | 3925.23 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
505535 | W-WW-NI-200220- LOCHWINNOCH WWTW 1971 NS356589 - Replace Ancillary equipment for screen - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-05-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 98.13 | 1401.87 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505572 | W-WW-NI-200220- NEILSTON WWTW NS479578 - Replace Ancillary Equipment for Screens - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-17 |  | 2020-05-20 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 111.21 | 1588.79 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
505531 | W-WW-NI-200220- UNDERCLIFF RD WWPS 1993 NS190698 - Replace In-line Pump - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-05-20 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 595.33 | 8504.67 | 9100 | 0 | 9100 | 0 | [6 empty] | CM_WWNI | 100%
505406 | W-WW-NI-200220-GIRVAN STC- REPLACE DOOR ON HIGH VOLTAGE ROOM (H&S) - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-05-11 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 1708 | 2492 | 4200 | 0 | 4200 | 0 | [6 empty] | CM_WWNI | 100%
505419 | W-WW-NI-200220-GIRVAN WWTW NX190999 - Duck Foot Replacement - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2020-05-11 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 2100 | 0 | [6 empty] | CM_WWNI | 100%
505596 | W-WW-NI-200220-MCCONNELL ROAD WWPS NS349589- Replace Pump- 8.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2020-05-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 536.45 | 7663.55 | 8200 | 0 | 8200 | 0 | [6 empty] | CM_WWNI | 100%
505581 | W-WW-NI-200220-POLMONTHILL WWPS 2000 NS953795- REFURB FOUL PUMP - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-05-20 |  | 2020-05-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 294.39 | 4205.61 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWNI | 100%
505595 | W-WW-NI-200220-STIRLING STC- Replace digester pressure relief valve - 5.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-17 |  | 2020-05-20 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 353.27 | 5046.73 | 5400 | 0 | 5400 | 0 | [6 empty] | CM_WWNI | 100%
505865 | W-WW-NI-20032020- STIRLING STC - REPLACE 2X PUMPS - 9.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-30 |  | 2020-07-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 634.58 | 9065.42 | 9700 | 0 | 9700 | 0 | [6 empty] | CM_WWNI | 100%
503896 | W-WW-NI-201119-Dunure WWPS 2 NS256163 - Replace Wet Well Pump No2 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2461.13 | -61.13 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WWNI | 100%
503893 | W-WW-NI-201119-DUNURE WwPS- Replace Wet Well Pump No1 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 | 2020-03-01 | - | 0 | 0 | 0 | 0 | 0 | 2461.13 | -61.13 | 2400 | 0 | 2400 | 0 | [6 empty] | CM_WWNI | 100%
503880 | W-WW-NI-201119-Leggate WwPS - Replace Submersible Pump No1 & Motor - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5037.64 | -37.64 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504763 | W-WW-NI-210120- KILLEARN WWTW 1971 NS517844- Replace RAS Pump 2 - 5K - | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504111 | W-WW-NI-211119 - Lomond Street WWPS NS300821 - Roof Work & Fascia Replacement - 10K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504061 | W-WW-NI-211119- Dalderse WWTW 1966 NS903822 - Replace Failed Lighting (H&S) - 5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 5197.1 | -197.1 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
503980 | W-WW-NI-211119- Dalgrain WwPS 1976 NS915823 - Storm Pumps Refurb - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 10566.21 | -566.21 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504052 | W-WW-NI-211119-Ardoch WWTW 2002 NS374758 - Refurb Gearbox - 3.2K 0 JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 3351.89 | -151.89 | 3200 | 0 | 3200 | 0 | [6 empty] | CM_WWNI | 100%
503911 | W-WW-NI-211119-Dunoon WwTW NS165745 - Replace RAS Pump A - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-02 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 2600 | 0 | [6 empty] | CM_WWNI | 100%
503921 | W-WW-NI-211119-Fallin WwTW - H&S Improvements - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 8150.74 | -450.74 | 7700 | 0 | 7700 | 0 | [6 empty] | CM_WWNI | 100%
505871 | W-WW-NI-22032020- KINNING PARK WWPS NS575644 - INLET BAR SCREEN REPAIR - 25K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-06-30 |  | 2020-06-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 1635.51 | 23364.49 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WWNI | 100%
503927 | W-WW-NI-221119- GAILES WWPS NS323359 - Replace Circuit Breaker Feeding Transformer - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-11-29 |  | 2019-12-13 |  | - | 0 | 0 | 0 | 0 | 0 | 1373.83 | 0 | 1373.83 | 0 | 1373.83 | 0 | [6 empty] | CM_WWNI | 100%
503935 | W-WW-NI-221119-Gailes WwPS NS323359 - Replace SCADA HMI - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 4722.62 | -722.62 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504943 | W-WW-NI-230120- EASTFIELD GLASGOW WWPS NS610622 - FAST TRACK: NEW PUMP & PANEL UPGRADE - 10k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504884 | W-WW-NI-230120- KILSYTH SOUTH DUMBRECK RD WWPS NS711776 - Replace Submersible Pump- FAST TRACK 2k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504904 | W-WW-NI-230120- PAISLEY LAIGHPARK SLDG TFR WWPS NS485655 - Refurbish Sludge Transfer Pump 1 - 29K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 29000 | 0 | 29000 | 0 | [6 empty] | CM_WWNI | 100%
504900 | W-WW-NI-230120-DALMELLINGTON WWTW NS476050- Supply new motor - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504929 | W-WW-NI-230120-PAISLEY LAIGHPARK SLDG TFR WWPS NS485655- Sludge Pump Replacement Survey - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 5100 | 0 | 5100 | 0 | [6 empty] | CM_WWNI | 100%
504944 | W-WW-NI-240120- MIDDLETON WWPS NS854964- FAST TRACK: PUMP REPLACEMENT - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
505921 | W-WW-NI-25032020- CHAPEL FIELD WWPS NS835896 - Replace Sump Pump 1 - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-04-03 |  | 2020-06-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 143.93 | 2056.07 | 2200 | 0 | 2200 | 0 | [6 empty] | CM_WWNI | 100%
503956 | W-WW-NI-251119- Denny WwTW NS820830 - Replacement Washwater Pump - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 1658.27 | -58.27 | 1600 | 0 | 1600 | 0 | [6 empty] | CM_WWNI | 100%
503960 | W-WW-NI-251119-Stirling WwTW 1968 NS808935- Washwater Pipework Extension - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 4360.51 | -260.51 | 4100 | 0 | 4100 | 0 | [6 empty] | CM_WWNI | 100%
505519 | W-WW-NI-260220 - UNDERWOOD (CUMNOCK) STC - Replace Rotor & Stator - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-05-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 359.81 | 5140.19 | 5500 | 0 | 5500 | 0 | [6 empty] | CM_WWNI | 100%
505961 | W-WW-NI-26032020 - KINNEIL KERSE WWTW 2001 NS960811 - Replace Liquor Pumps x2 - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 6900 | 0 | 6900 | 0 | [6 empty] | CM_WWNI | 100%
505996 | W-WW-NI-26032020- BATTERY PARK WWPS NS254779- REPLACE/REFURB CRANE PARTS - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2020-07-30 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 6068 | 6068 | 0 | 6068 | 0 | [6 empty] | CM_WWNI | 100%
505982 | W-WW-NI-26032020- BONESS WWTW NT022813 - Replace SBR probe - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 1722 | 1722 | 0 | 1722 | 0 | [6 empty] | CM_WWNI | 100%
505960 | W-WW-NI-26032020- BRAEHEAD SHOPPING CENT WWPS NS523670 - H&S - REPLACE TECHNO COVERS - 15.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 15200 | 15200 | 0 | 15200 | 0 | [6 empty] | CM_WWNI | 100%
505987 | W-WW-NI-26032020- GIRVAN STC - Renew faulty external lighting - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2214 | 2214 | 0 | 2214 | 0 | [6 empty] | CM_WWNI | 100%
505962 | W-WW-NI-26032020- KINNEIL KERSE STC - Replacement rotor - 7.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-03 |  | 2020-08-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 6794 | 6794 | 0 | 6794 | 0 | [6 empty] | CM_WWNI | 100%
505956 | W-WW-NI-26032020- PARTICK WWPS NS565664 - REPLACE ROTORK - 11.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 11300 | 0 | 11300 | 0 | [6 empty] | CM_WWNI | 100%
505993 | W-WW-NI-26032020- STIRLING STC - Replace polymer feed pump 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 1300 | 0 | 1300 | 0 | [6 empty] | CM_WWNI | 100%
503991 | W-WW-NI-26112019 - Dalgrain WWPS 1976 NS915823 - Replace Roller Door Curtain - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504193 | W-WW-NI-291119 - Girvan WWTW NX190999 - Refurb Decant Arm - 22K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 22000 | 0 | [6 empty] | CM_WWNI | 100%
504118 | W-WW-NI-291119 - North Lodge SPS 2012 NS416364 - Replace VSDs after Fire - 8K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 8255.56 | -255.56 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
504366 | W-WW-NI-291119 - Paisley LaighparkSLDG TFR WWPS NS485655 - Remove & Investigate Pump No3 complete with NRV - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-17 |  | 2020-03-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 10538.9 | -538.9 | 10000 | 0 | 10000 | 0 | [6 empty] | CM_WWNI | 100%
504154 | W-WW-NI-291119- Bonnybridge WwTW NS836811 - Refurbish Storm Screens - 9.7K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 10257.58 | -557.58 | 9700 | 0 | 9700 | 0 | [6 empty] | CM_WWNI | 100%
504196 | W-WW-NI-291119- CUMNOCK UNDERWOOD WWTW - NEW ACTUATOR - 3K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 3142.26 | -142.26 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504191 | W-WW-NI-291119- DALDERSE WWTW 1966 NS903822- New PST drive train (Critical Spare) - 6K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 5912.6 | 87.4 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504233 | W-WW-NI-291119- DALMELLINGTON WWTW NS476050 - Replace Pump & Guide Rails - 4K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 4009.08 | -9.08 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504440 | W-WW-NI-291119- DOLLAR WWTW NS953978 - Replace assist SBR lift & transfer pump - 3k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-07-30 |  | - | 0 | 0 | 0 | 0 | 0 | 3000 | 1300 | 4300 | 0 | 4300 | 0 | [6 empty] | CM_WWNI | 100%
504230 | W-WW-NI-291119- DUNOON WWTW NS165745 - Replace Sprybar Carousel bearings & proximity switch - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504282 | W-WW-NI-291119- Fintry WWTW NS614873 - Modify Gratings - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 7990.65 | -490.65 | 7500 | 0 | 7500 | 0 | [6 empty] | CM_WWNI | 100%
504227 | W-WW-NI-291119- GAILES WWPS NS323359 - Urgent Refurb of ABB Drive - 6K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-01 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 8169.1 | -169.1 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
504425 | W-WW-NI-291119- KILLEARN WWTW 1971 NS517844 - Replace bauer coupling & pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504269 | W-WW-NI-291119- KINNING PARK WWPS NS575644 - Reinstate Screen 2 - 9K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 9000 | 0 | [6 empty] | CM_WWNI | 100%
504218 | W-WW-NI-291119- LOCHEARNHEAD WWPS NN593238 - Install Safety Cage Around Ladder (Confined Space Entry H&S) - 4K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | [6 empty] | CM_WWNI | 100%
504221 | W-WW-NI-291119- LOMOND IND EST WWPS 1999 NS395808 - Remedial Work to Pump Controls - 10K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 12000 | 0 | 12000 | 0 | [6 empty] | CM_WWNI | 100%
504091 | W-WW-NI-291119- Pike Rod WWPS NS811913 - Fast track Pump Replacement 4.7K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 4958.18 | -258.18 | 4700 | 0 | 4700 | 0 | [6 empty] | CM_WWNI | 100%
504377 | W-WW-NI-291119- Rothesay WWTW 2002 NS100637 - Replace pump and guide rails - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | [6 empty] | CM_WWNI | 100%
504161 | W-WW-NI-291119 -Shieldhall WWTW NS533659 - Install Final Effluent Turbidity & PH Instruments - 30K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-07-04 |  | - | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 30000 | 0 | [6 empty] | CM_WWNI | 100%
504215 | W-WW-NI-291119- STIRLING WWTW 1968 NS808935 - Install New LED Lights (H&S) - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504234 | W-WW-NI-291119- THE MANSE WWPS NR803328 - Replace Guide rails - 5.5K JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 5500 | 0 | [6 empty] | CM_WWNI | 100%
504206 | W-WW-NI-291119-CUMNOCK UNDERWOOD WWTW - 2x Bridge Wheels - 3K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 3065.73 | -65.73 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504192 | W-WW-NI-291119-DALDERSE WWTW 1966 NS903822 - Refurbish Admin Building - Replace windows - 27K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-01 |  |  |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 21767.62 | 21767.62 | 0 | 21767.62 | 0 | [6 empty] | CM_WWNI | 100%
504200 | W-WW-NI-291119-GIRVAN WWTW NX190999 - Replace Washwater Pump - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504190 | W-WW-NI-2919- North Shore Road WWPS NS927826 - Replacement Pump - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2020-03-01 |  | - | 0 | 0 | 0 | 0 | 0 | 1944.72 | 55.28 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505025 | W-WW-NI-300120- 8 MILLFIELD DR SST PNRV 2009 NS932786 - REPLACE APNRV - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-06-29 |  | - | 0 | 0 | 0 | 0 | 0 | 10500 | 3000 | 13500 | 0 | 13500 | 0 | [6 empty] | CM_WWNI | 100%
504985 | W-WW-NI-300120- ALLOA WWTW NS887918 - Replace Screenings Handling - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 8500 | 300 | 8800 | 0 | 8800 | 0 | [6 empty] | CM_WWNI | 100%
505017 | W-WW-NI-300120- DALDERSE WWTW 1966 NS903822 - REPLACE LDO SENSOR PROBES X 16 - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | [6 empty] | CM_WWNI | 100%
504960 | W-WW-NI-300120- DALDERSE WWTW 1966 NS903822 - Replacement Autosampler - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 0 | [6 empty] | CM_WWNI | 100%
505033 | W-WW-NI-300120- LOMOND STREET WWPS NS300821 - REFURBISH ROOF - 11K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 11000 | 0 | 11000 | 0 | [6 empty] | CM_WWNI | 100%
504964 | W-WW-NI-300120- MUCKHART WWTW NO002003 - REFURBISH INLET SCREEN - 3.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 3600 | 0 | [6 empty] | CM_WWNI | 100%
504970 | W-WW-NI-300120- NEW CUMNOCK WWTW NS622140 - Replace Scum Boards & Stilling Baffles - 25K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | [6 empty] | CM_WWNI | 100%
505039 | W-WW-NI-300120- OCHILTREE WWTW NS508215 - Refurb De-watering Float Arm - 7.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 7200 | 0 | 7200 | 0 | [6 empty] | CM_WWNI | 100%
504953 | W-WW-NI-300120- PARTICK WWPS NS565664 - Refurbish Foul Pump - 17K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 17000 | 0 | 17000 | 0 | [6 empty] | CM_WWNI | 100%
505026 | W-WW-NI-300120- ROWALLAN WWPS NS440401 - REPLACE FOUL PUMP - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 | [6 empty] | CM_WWNI | 100%
505045 | W-WW-NI-300120- STIRLING WWTW 1968 NS808935 - REPLACE RAS PUMP - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 | 0 | [6 empty] | CM_WWNI | 100%
505011 | W-WW-NI-300120- STIRLING WWTW 1968 NS808935 - REPLACEMENT SCREEN BRUSH GEARBOX - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 1959.37 | 40.63 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505046 | W-WW-NI-300120- STIRLING WWTW 1968 NS808935 - Telemetry Investigations 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
505042 | W-WW-NI-300120- UNDERWOOD (CUMNOCK) STC - Replace Rotors & Stators for belt thickening feed pumps 1 & 2 - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-02-05 |  | - | 0 | 0 | 0 | 0 | 0 | 6420.3 | 79.7 | 6500 | 0 | 6500 | 0 | [6 empty] | CM_WWNI | 100%
504992 | W-WW-NI-300120-DALDERSE WWTW 1966 NS903822 - REPLACE FAILED DRIVE GEARBOX & MOTOR - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 1976.37 | 23.63 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
504938 | W-WW-NI-300120-Stirling WwTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 2300 | 0 | [6 empty] | CM_WWNI | 100%
505310 | W-WW-NI-30220- STEVENSTON POINT WWTW NS275404 - Replace Covers (H&S) and road gully - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2020-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 1952 | 2848 | 4800 | 0 | 4800 | 0 | [6 empty] | CM_WWNI | 100%
505003 | W-WW-NI-310120- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REPLACE MACERATORS X2 - 13K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 13000 | 0 | [6 empty] | CM_WWNI | 100%
505005 | W-WW-NI-310120- TILLICOULTRY WWTW NS917965 - REPAIR SCREEN - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2020-03-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 10643.71 | 1356.29 | 12000 | 0 | 12000 | 0 | [6 empty] | CM_WWNI | 100%
505862 | W-WW-NI-BONESS WWTW NT022813- Replace Obsolete Mounted Lenze Drive - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-07-30 |  | 2020-07-30 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 111.21 | 1588.79 | 1700 | 0 | 1700 | 0 | [6 empty] | CM_WWNI | 100%
503900 | W-WW-NI-FALLIN WwTW 1960 NS835823 - New Handrails H&S - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 3256.8 | -156.8 | 3100 | 0 | 3100 | 0 | [6 empty] | CM_WWNI | 100%
503904 | W-WW-NI-Fallin WWTW 1969 NS835923- Walkway Installation (H&S) - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2020-03-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | [6 empty] | CM_WWNI | 100%
504474 | W-WW-NI-FAST TRACK - KINNEIL KERSE WWTW 2001 NS960811 - Replace Storm Pump - 12K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2020-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 12000 | 0 | 12000 | 0 | [6 empty] | CM_WWNI | 100%
505942 | W-WW-NI-FAST TRACK 25032020 - DALMARNOCK WWTW NS611627 - REFURB STORM PUMP - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2214 | 2214 | 0 | 2214 | 0 | [6 empty] | CM_WWNI | 100%
505948 | W-WW-NI-FAST TRACK 26032020- DALDERSE STC - REPLACE STANDBY SLUDGE PUMP - 10.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 8364 | 8364 | 0 | 8364 | 0 | [6 empty] | CM_WWNI | 100%
504470 | W-WW-NI-FAST TRACK- DALDERSE STC - Supply a critical spare sludge circulation pump - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2020-03-31 |  | 2020-03-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 7960.64 | 39.36 | 8000 | 0 | 8000 | 0 | [6 empty] | CM_WWNI | 100%
505544 | W-WW-NI-FAST TRACK- ZETLAND PARK WWPS 2000 NS929811 - Refurb Storm Pump - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2020-06-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 294.39 | 4205.61 | 4500 | 0 | 4500 | 0 | [6 empty] | CM_WWNI | 100%
505940 | W-WW-NI-FAST TRACK-25032020- ERSKINE WWTW NS494691- Replace VSD for Launder Pump B - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2020-07-30 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 1640 | 1640 | 0 | 1640 | 0 | [6 empty] | CM_WWNI | 100%
505094 | W-WW-NI-NEWMILNS ROAD WWPS NS502368 - REPLACE 2X FOUL PUMPS - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2020-03-31 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | [6 empty] | CM_WWNI | 100%
504630 | W-WW-NI-STEWARTON WWTW NS408449 - Replacec Isolation valves x2 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2020-03-31 |  | - | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | [6 empty] | CM_WWNI | 100%
401441 | Yarrowfeus WSZ Low Pressure Enhancement WSZ001593 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-10-12 | 2011-09-06 | 2012-06-04 | 2013-06-25 | 2013-06-25 | Scottish Borders | 24267 | -94.24 | 0 | 0 | 0 | 0 | 0 | -94.24 | 0 | 24172.76 | 446 | [6 empty] | CS1 | 100%
403589 | Yarrowford WTW Site - Flood Risk mitigation | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-09-06 | 2014-02-03 | 2014-02-10 | 2014-02-25 | 2014-03-20 | Scottish Borders | 22608 | -1293.12 | 0 | 0 | 0 | 0 | 0 | -1293.12 | 0 | 21314.88 | 1027 | [6 empty] | CS16W | 100%
45042 | Yarrowford WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-26 | 2012-09-17 | 2013-03-28 | 2013-06-24 | Scottish Borders | 831099.67 | 106.27 | 0 | 0 | 0 | 0 | 0 | 106.27 | 0 | 831205.94 | 0 | [6 empty] | DW23 | 100%
503595 | Yarrowfues WTW main-out 2019 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS0 | 2013-03-18 | 2020-08-17 | 2020-09-11 | 2021-09-29 | 2022-12-11 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 226106.42 | 1145291.09 | 1371397.51 | 1404602.49 | 2776000 | 356832.64 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
502569 | Yell WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2020-08-04 | 2020-08-17 | 2020-08-26 | 2020-08-27 | 2020-08-28 | Shetland Islands | 0 | 0 | 20930.23 | 3854.89 | 73881.46 | 33197.43 | 9601 | 141465.01 | 0 | 141465.01 | 136478.56 | [6 empty] | WG1 | 100%
403709 | York Place WWPS Penstock By-Pass | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-10-23 | 2017-03-27 | 2017-03-30 | 2017-11-29 |  | Aberdeen City | 23715 | 15592 | 28869 | 56379.79 | 0 | 0 | 0 | 100840.79 | 0 | 124555.79 | 0 | [6 empty] | CM_WWI | 100%
503164 | Yr 4 Consultants OMG13 Holding Line | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS3 | 2018-05-29 | 2018-05-29 | 2019-05-07 |  | 2021-03-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 276105.36 | 236306.65 | 487588.01 | 1000000.02 | 0 | 1000000.02 | 821666.8 | [6 empty] | CS22 | 100%
503163 | Yr 4 MIOS Consultants Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-29 | 2018-05-29 | 2018-10-08 |  | 2022-12-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 368127.42 | 527711.99 | 204160.59 | 1100000 | 0 | 1100000 | 0 | [6 empty] | CM_WSI | 100%
503160 | Yr 4 OMG13 East Area Code Bulk Line | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-07-25 |  | 2021-09-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 196592.41 | 235334.46 | 495647.95 | 927574.82 | 72608.17 | 1000182.99 | 821666.8 | [6 empty] | CS22 | 100%
503158 | Yr 4 OMG13 North Area Code Bulk Line | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 |  | 2021-07-20 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 206975.37 | 280954.38 | 300626.87 | 788556.62 | 21812.05 | 810368.67 | 821666.8 | [6 empty] | CS22 | 100%
503159 | Yr 4 OMG13 South Area Code Bulk Line | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 |  | 2021-11-30 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 239844.3 | 510671.42 | 547123.52 | 1297639.24 | 202360.75 | 1499999.99 | 821666.8 | [6 empty] | CS22 | 100%
503155 | Yr 4 SVCD East Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 |  | 2021-09-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 36313.08 | 126044.06 | 107987.08 | 270344.22 | 29655.79 | 300000.01 | 0 | [6 empty] | CM_WSI | 100%
503153 | Yr 4 SVCD North Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 |  | 2021-07-28 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 13554.7 | 1177 | -177.44 | 14554.26 | 0 | 14554.26 | 0 | [6 empty] | CM_WSI | 100%
503154 | Yr 4 SVCD South Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-18 | 2018-04-18 | 2018-08-14 |  | 2021-11-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 625680.45 | 816029.89 | 282185.38 | 1723895.72 | 276104.28 | 2000000 | 0 | [6 empty] | CM_WSI | 100%
503156 | Yr 4 SVCD West Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-30 | 2018-04-30 | 2018-06-11 |  | 2021-06-21 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 700157.39 | 1131636.25 | 15000 | 1846793.64 | 0 | 1846793.64 | 0 | [6 empty] | CM_WSI | 100%
502335 | Yr 4 to Yr 6 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-15 | 2021-03-31 | 2021-03-31 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1399999.98 | 1399999.98 | 0 | 1399999.98 | 0 | [6 empty] | CM_WSI | 100%
503161 | Yr4-Yr6 OMG13 West Area Code Bulk Line | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-06-11 |  | 2021-05-19 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 519500.41 | 726429.04 | 121692.95 | 1367622.4 | 0 | 1367622.4 | 821666.8 | [6 empty] | CS22 | 100%
PH_500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_003 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2018-12-31 | 2019-01-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50710 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-28 | 2019-06-30 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Aberlour | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-28 | 2019-06-30 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500111 | Alloa DOA (DOA000269) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_002 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-02-28 | 2018-08-31 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500111 | Alloa DOA (DOA000269) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_008 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-05-31 | 2018-08-31 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508020_01 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-04-30 | 2022-02-28 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508019_01 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-04-30 | 2022-02-28 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508018_01 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-04-30 | 2022-02-28 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500114 | Annan DOA (DOA000111) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50725 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-03-31 | 2019-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500114 | Annan DOA (DOA000111) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_013 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-02-28 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500113 | Anstruther Billowness DOA (DOA000254) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50837 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-12-31 | 2019-03-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500113 | Anstruther Billowness DOA (DOA000254) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_028 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-09-30 | 2018-11-30 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500121 | Ardoch DOA (DOA000707) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_015 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2020-01-31 | 2020-01-09 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500121 | Ardoch DOA (DOA000707) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50801 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2020-01-31 | 2020-04-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_2 | OMG 07 | Water |  | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_4 | OMG 07 | Water |  | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_3 | OMG 07 | Water |  | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_500795 | Backies RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53305 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-30 | 2019-02-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 9.47
PH_500795 | Backies RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50200 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-30 | 2019-02-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 103.31
PH_500844 | Badentinan RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53206 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-31 | 2020-12-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 32.1
PH_500844 | Badentinan RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50201 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-31 | 2020-12-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 89.05
PH_500002 | Balmichael RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53187 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2020-01-17 | 2020-06-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 2.05
PH_500002 | Balmichael RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50247 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2020-01-17 | 2020-06-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 90.43
PH_500846 | Balmore A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53188 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-09-30 | 2020-09-24 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 2.01
PH_500846 | Balmore A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50248 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-09-30 | 2020-09-24 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 59.62
PH_500227 | Balmore E - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50009_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-28 | 2020-01-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500227 | Balmore E - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50009_001 | OMG 06 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-28 | 2020-03-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 19.4
PH_500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2018-06-30 | 2020-02-13 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2018-06-30 | 2019-03-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2019-03-31 | 2019-03-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500848 | Balmore F RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53190 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-31 | 2019-05-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 9.67
PH_500848 | Balmore F RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50236 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-31 | 2019-05-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 25.75
PH_500116 | Bathgate DOA (DOA000537) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_003 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2019-03-31 | 2019-12-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500116 | Bathgate DOA (DOA000537) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_026 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2018-09-30 | 2018-11-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N10 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N07 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N05 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N03 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N02 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N01 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_003 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-03-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-03-31 | 2019-06-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-07-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500797 | Black Esk RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53202 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2019-11-07 | 2021-02-26 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 253.53
PH_500797 | Black Esk RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50237 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2020-03-30 | 2021-11-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 46.23
PH_500800 | Bonnycraig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50239 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-05-31 | 2019-12-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 20
PH_500800 | Bonnycraig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53207 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-05-31 | 2019-12-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 18.57
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508044 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508042 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508041 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508040 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-31 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508046 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508047 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508045 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508039 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508048 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2022-03-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502412 | Bradan WTW Water Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50749_TE_500749_02 | OMG 01 | Water |  | NONINF | DWQ Reliability |  | 2015-07-31 | 2017-03-31 | 2017-03-31 | 2018-06-30 | 2019-09-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_502412 | Bradan WTW Water Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50091_TE_500091_02 | OMG 01 | Water |  | NONINF | DWQ Reliability |  | 2015-07-31 | 2017-03-31 | 2017-03-31 | 2018-09-30 | 2019-09-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_500123 | Brechin DOA (DOA000645) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_036 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-09-30 | 2018-11-30 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500123 | Brechin DOA (DOA000645) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Brechin | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-11-30 | 2019-03-31 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_502132 | Burncrooks WTW Quality THM Compliance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50144 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2016-03-17 | 2019-03-29 | 2019-03-29 | 2021-10-28 | 2022-01-27 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_502132 | Burncrooks WTW Quality THM Compliance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50144 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2016-03-17 | 2019-03-29 | 2019-03-29 | 2021-10-28 | 2022-01-27 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-20: 5
PH_500119 | Castle Douglas DOA (DOA000097) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_042 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-31 | 2017-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500119 | Castle Douglas DOA (DOA000097) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50803 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-31 | 2017-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500031 | Catchment Assessment Study for Drinking Water Quality Protection | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50186_TE_500186_01_N02 | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 14
PH_500031 | Catchment Assessment Study for Drinking Water Quality Protection | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50186_TE_500186_01_N01 | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_500062 | Clatto East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50000_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-30 | 2018-12-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500062 | Clatto East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50000_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-30 | 2018-12-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-06-30 | 2019-04-30 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-09-30 | 2019-07-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-12-31 | 2019-07-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_004 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-03-31 | 2019-07-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_005 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-06-30 | 2019-03-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_042 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_044 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_045 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_041 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_043 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_039 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_038 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_046 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_056 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_034 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_033 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-14 | 2021-03-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_036 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_048 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_049 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_050 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_051 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_052 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_053 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_055 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_058 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_060 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_061 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_032 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_004 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_054 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_015 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_001 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_003 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_059 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_005 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_062 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_007 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_008 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_009 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_010 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_011 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-06-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_006 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_014 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_031 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_016 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_017 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_019 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_020 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_022 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_023 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_024 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_026 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-01 | 2020-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_027 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_029 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_030 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_012 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_057 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2021-03-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500098 | Climate Change Risk Assessments | Q&S4 | Climate Change | Climate Change | 51308_TE_501308_002 | OMG 45 | General |  | SWD | Climate Change |  | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-30 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500098 | Climate Change Risk Assessments | Q&S4 | Climate Change | Climate Change | 51308_TE_501308_001 | OMG 45 | General |  | SWD | Climate Change |  | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-30 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_024 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_016 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_017 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_018 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_019 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_020 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_021 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_015 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_023 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_025 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_026 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_022 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_049 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-08-31 | 2020-01-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Corpach | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-09-30 | 2019-12-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50727 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-09-30 | 2019-12-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_027 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_023 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_024 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_026 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-10-31 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_017 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_028 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_029 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_025 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_021 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_030 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_018 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_034 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_016 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2019-07-31 | 2020-02-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_015 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_014 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_013 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-08-31 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_012 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_011 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_010 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_009 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-08-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_019 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-08-31 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_044 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_057 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2018-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_056 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_055 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-06-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_054 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_053 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_052 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-06-30 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_051 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_050 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_049 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_048 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_047 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_032 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_045 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_031 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_043 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_042 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_041 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-09-30 | 2020-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_040 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-09-30 | 2020-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_039 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_038 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_037 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_036 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_020 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_033 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_008 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_046 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_022 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-10-31 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_006 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-08-31 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_005 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_004 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_003 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-02-14 | 2020-04-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_002 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_001 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-09-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Critical Reservoir Assets (works to prevent MIOS) | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_007 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50804 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2019-01-31 | 2019-06-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_066 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2018-11-30 | 2019-01-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_065 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2018-11-30 | 2019-01-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_063 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_072 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_071 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_070 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_099 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_069 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_068 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_067 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_066 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_073 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_064 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_078 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_062 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_061 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_059 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_058 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_056 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_055 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_054 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_053 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_052 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_051 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_050 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_065 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_096 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_085 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_086 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_087 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_088 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_089 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_090 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_091 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_092 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_093 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_074 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_095 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_081 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_083 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_082 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_037 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_097 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_049 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_098 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_080 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_079 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_084 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_076 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_094 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_011 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_039 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_022 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_021 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_020 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_018 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_017 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_016 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_015 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_014 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_024 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_012 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_025 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_010 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_009 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_008 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_007 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_006 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_005 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_004 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_003 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_002 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_001 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_013 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_036 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_047 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_046 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_045 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_044 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_043 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_042 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_041 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_040 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_100 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_023 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_077 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-06-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_048 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_035 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_034 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_033 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_032 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_031 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_030 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_029 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_028 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_027 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_026 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_038 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_138 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_126 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_127 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_128 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_129 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_130 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_132 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_134 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_135 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_125 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_137 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_131 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_139 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_140 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_141 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_142 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_144 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_145 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_075 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_101 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_136 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_107 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_102 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_103 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_133 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_106 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_124 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_108 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_109 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_110 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_111 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_112 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_113 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_114 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-10-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_117 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_118 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_119 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_120 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_121 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-08-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_123 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_122 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_115 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_104 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_065 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_064 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_063 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_062 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_061 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_066 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_057 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_111 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_059 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_067 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_114 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_056 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-01-31 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_112 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_050 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_110 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_109 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_108 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_113 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_045 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-12-18 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_034 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_035 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_036 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_037 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_038 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_039 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_040 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_041 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_052 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_044 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_054 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_046 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_047 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_048 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_049 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_102 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-12-18 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_051 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_107 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_053 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_043 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_033 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_082 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_081 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-01-31 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_080 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_079 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_078 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_077 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_076 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_104 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_074 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_085 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_073 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-01-31 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_058 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-12-18 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_072 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_071 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_070 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_069 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_068 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_075 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_093 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_105 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_103 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_101 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_100 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_099 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_098 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_097 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_083 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_095 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_084 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-07-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_092 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_091 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_090 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_089 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_088 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_087 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_086 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_106 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_096 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_009 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50771_TE_500771_143 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_001 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_002 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_003 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_004 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_060 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-12-18 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_005 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_031 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_006 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_008 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_010 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_011 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_012 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_013 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_025 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_030 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_028 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_007 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_026 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_014 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_024 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_023 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_022 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_019 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_018 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_017 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_016 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_015 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_020 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_027 | OMG 47 | Water |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_501271 | Dunnswood DOA (DOA000557) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_074 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2018-09-30 | 2018-11-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501271 | Dunnswood DOA (DOA000557) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_004 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2019-03-31 | 2019-12-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500128 | Dunoon DOA (DOA002568) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_076 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-31 | 2017-07-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500128 | Dunoon DOA (DOA002568) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_075 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-31 | 2017-07-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50162 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50172 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50171 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50169 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-10-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50167 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-02-28 | 2017-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50166 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50165 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-04-30 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50163 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50170 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50173 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50164 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50175 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50176 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-04-30 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50174 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50168 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_501104 | Edinburgh DAS Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Edin | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-31 | 2019-01-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_501104 | Edinburgh DAS Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50829 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-31 | 2019-01-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-30 | 2018-06-30 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-30 | 2020-01-29 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_003 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-30 | 2018-12-31 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_003 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.07
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_002 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.01
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_004 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.028
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_005 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.01
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_006 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.05
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_008 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.046
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_007 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.07
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_001 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.044
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_009 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.15
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_010 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.0039
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_012 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.0088
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_013 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.128
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_015 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.0365
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_014 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.261
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_013 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-11-30 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.052
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_011 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.57
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_009 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-11-30 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.475
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_008 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.075
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_004 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.16
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_015 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.05
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_002 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.15
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_012 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.41
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_001 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.046
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_003 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.081
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_039 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.117
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_016 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 5.921
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_010 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.14
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_052 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.011
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_034 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.051
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_024 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 1.212
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_022 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-10-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.02
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_019 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-09-30 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.05
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_018 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.024
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_017 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.54
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-9 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-5 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-6 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-7 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-8 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-9 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-10 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-11 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-15 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-13 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-25 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-12 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-14 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-8 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-7 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-6 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-5 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-28 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-27 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-23 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-24 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-16 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-22 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-21 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-20 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-19 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-18 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-17 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-26 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_22 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_11 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-31 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_12 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_13 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_14 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-05-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_15 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_16 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_18 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_30 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-31 | 2018-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_21 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-06-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_29 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-01-31 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_23 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_24 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_25 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_26 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_27 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-06-30 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_28 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_19 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2020-03-02 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_20 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_17 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50721 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-06-26 | 2020-10-09 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_005 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-09-30 | 2021-01-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_083 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-09-30 | 2021-01-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500135 | Eyemouth DOA (DOA000070) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_084 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-02-28 | 2019-03-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500135 | Eyemouth DOA (DOA000070) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Eyemo | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-09-30 | 2019-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500823 | Fairmilehead B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50240 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-31 | 2019-07-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 12.44
PH_500823 | Fairmilehead B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53192 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-31 | 2019-07-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 46.07
PH_500241 | Fairmilehead C - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50029_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-31 | 2018-09-30 | 2018-09-30 | 2020-11-30 | 2021-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500241 | Fairmilehead C - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50029_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-31 | 2018-09-30 | 2018-09-30 | 2019-02-28 | 2019-09-30 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500824 | Fairmilehead C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53193 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-31 | 2019-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 17.7
PH_500824 | Fairmilehead C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50241 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-31 | 2019-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 36.16
PH_500074 | Final Water Sampling Programme Extension | Q&S4 | Climate Change | Climate Change | 51315 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-03-31 | 2016-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500074 | Final Water Sampling Programme Extension | Q&S4 | Climate Change | Climate Change | 51305 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-03-31 | 2016-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_203 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_205 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_202 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_116 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_148 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_207 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_201 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-25 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_154 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_153 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_152 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_150 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_147 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-07-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_145 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_144 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_204 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_143 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_139 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-09-30 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_138 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_137 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_151 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_171 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-09-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_200 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_133 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_155 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_159 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_165 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_166 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-04-01 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_167 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_168 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-12-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_188 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-04-01 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_170 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_196 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-06-30 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_172 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-25 | 2020-04-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_173 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_174 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_175 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_176 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_187 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-19 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_191 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_194 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_169 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_025 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_002 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_004 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_107 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_005 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_106 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_009 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_101 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-21 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_100 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_057 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_012 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_019 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_021 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_022 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_001 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_038 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-13 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_045 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_046 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_131 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_206 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_043 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_023 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_039 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-02-28 | 2017-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_024 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-06 | 2020-02-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_037 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_016 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_031 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_029 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_027 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_010 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-09 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_040 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_115 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_060 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_047 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_048 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_050 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_113 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_017 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-01-31 | 2017-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_053 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_068 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_054 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_114 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_055 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_117 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_119 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_123 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_124 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_056 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_126 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_130 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_011 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_082 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_018 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_098 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_070 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_094 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_090 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_085 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_095 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-12-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_073 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_071 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_078 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_080 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_087 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-02-28 | 2018-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50730 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-31 | 2018-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Fochab | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-31 | 2018-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50820 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-12-31 | 2019-12-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_006 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2018-02-28 | 2018-06-30 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_089 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-09-30 | 2019-12-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500141 | Fraserburgh Phingask DOA (DOA000360) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_091 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-31 | 2018-03-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500141 | Fraserburgh Phingask DOA (DOA000360) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Fraser | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-31 | 2019-02-28 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_014 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_019 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-31 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_017 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_018 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_015 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_013 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_012 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-07-03 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_010 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_009 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-01 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_008 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-09-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_005 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_002 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-29 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_020 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-31 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_007 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_050 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_040 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_041 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_042 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-03-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_043 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-11-30 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_044 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_045 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_047 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-06-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_004 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_049 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_001 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_051 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-09-30 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_052 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-02-28 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_053 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_055 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-05-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_056 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-07-31 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_057 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_058 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_048 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_031 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-01 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_022 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_023 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_024 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_025 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-08-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_026 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_027 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-29 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_028 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_039 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-02-28 | 2020-06-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_030 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-29 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_038 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_032 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_033 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_034 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-01 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_035 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_036 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_037 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-05-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_003 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_021 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-05-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_029 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_105 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-04-30 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_104 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_088 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_081 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-06-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_120 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_063 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_062 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_122 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_127 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_141 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_146 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_156 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_061 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_161 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_177 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-05-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_198 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_157 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_051 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_044 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_035 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-02-28 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_033 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-02-28 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_032 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-10-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_064 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-06-30 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_052 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500133 | Galashiels DOA (DOA000032) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_093 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-06-30 | 2018-08-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500133 | Galashiels DOA (DOA000032) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_007 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-02-28 | 2018-06-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500245 | Galashiels Manse Street WTW | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50113 | OMG 04 | Water |  | NONINF | SOSI |  | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2021-10-31 | 2022-01-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_500245 | Galashiels Manse Street WTW | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50113 | OMG 20 | Water |  | NONINF | SOSI |  | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2021-10-31 | 2022-01-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-20: 3
PH_500146 | Girvan DOA (DOA002467) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Girvan | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-31 | 2019-01-31 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500146 | Girvan DOA (DOA002467) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_097 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-31 | 2018-08-31 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_001 | OMG 06 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-21 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 21.58
PH_500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-17 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-21 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_04 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-03-23 | 2020-12-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_03 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-03-23 | 2020-12-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_02 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-03-23 | 2020-12-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_501574 | Greenock WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50782 | OMG 04 | Water |  | SWD | DWQ Reliability |  | 2017-03-31 | 2019-06-27 | 2019-06-27 | 2020-10-31 | 2021-01-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_501574 | Greenock WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50782 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2017-03-31 | 2019-06-27 | 2019-06-27 | 2020-10-31 | 2021-01-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500136 | Gretna DOA (DOA000114) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50807 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-12-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500136 | Gretna DOA (DOA000114) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_208 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-09-30 | 2019-02-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500137 | Halkirk DOA (DOA000726) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50819 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-02-28 | 2019-06-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500137 | Halkirk DOA (DOA000726) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_103 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-01-31 | 2019-02-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501233 | Herricks WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50781 | OMG 04 | Water |  | NONINF | DWQ Reliability |  | 2018-03-22 | 2020-02-28 | 2020-02-28 | 2020-11-30 | 2021-02-28 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_501233 | Herricks WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50781 | OMG 05 | Water |  | NONINF | DWQ Reliability |  | 2018-03-22 | 2020-02-28 | 2020-02-28 | 2020-11-30 | 2021-02-28 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500138 | Huntly DOA (DOA000367) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_108 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-02-28 | 2019-03-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500138 | Huntly DOA (DOA000367) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50821 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-03-31 | 2019-06-30 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500032 | Improvement to Supply-Demand Balance - North Hoy WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 53018 | OMG 08 | Water |  | SWMD | SOSI |  | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-08
PH_500032 | Improvement to Supply-Demand Balance - North Hoy WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 53018 | OMG 04 | Water |  | SWMD | SOSI |  | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_004 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_030 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-31 | 2020-03-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_029 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_005 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2018-12-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_028 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-31 | 2020-03-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_003 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_007 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_001 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_006 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_008 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_009 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_010 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_011 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_012 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_013 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_002 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_018 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_024 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-04-23 | 2020-08-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_050 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-02-03 | 2020-05-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_049 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_048 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_037 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-01-31 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_036 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_035 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-04-23 | 2020-07-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_022 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_021 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_019 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2021-04-30 | 2021-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_017 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_020 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_023 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2021-02-28 | 2021-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_015 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_034 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_033 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_032 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_016 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_014 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_031 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_045 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_042 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_040 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_046 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_043 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_047 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_041 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_044 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_038 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_027 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_026 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_025 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_039 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-05-29 | 2020-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_003 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.053
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_005 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.08
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_006 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.2
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_004 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.05
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_001 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.04
PH_500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_110 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-06-22 | 2020-03-24 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_008 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-06-22 | 2020-12-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50719 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-03-24 | 2020-04-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500150 | Inverness DOA (DOA002372) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_006 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-06-30 | 2019-08-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500150 | Inverness DOA (DOA002372) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_001 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-12-31 | 2020-01-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_11 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_02 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_01 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_04 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_05 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_06 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_07 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_08 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_03 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_10 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_12 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_13 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_14 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_15 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_16 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_17 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_18 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_09 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_26 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_23 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_31 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_39 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_38 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_37 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_36 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_35 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_34 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_24 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_32 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_22 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_30 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_29 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_28 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_27 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_19 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_25 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_33 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_20 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_21 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_06 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_05 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_07 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_08 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_09 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-11-30 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_03 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_04 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_02 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_01 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_14 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_11 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_12 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_10 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_13 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_503103 | IR18 Inverness and Nairn - Growth and Resilience | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 59065_01 | OMG 07 | Water |  | WINF | SOSI |  | 2018-06-26 | 2020-07-13 | 2020-07-13 | 2021-08-10 | 2021-11-11 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_503103 | IR18 Inverness and Nairn - Growth and Resilience | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 59065_01 | OMG 08 | Water |  | WINF | SOSI |  | 2018-06-26 | 2020-07-13 | 2020-07-13 | 2021-08-10 | 2021-11-11 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-08
PH_503052 | IR18 Pateshill WTW Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59129a | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2020-02-27 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_503052 | IR18 Pateshill WTW Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59017a | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2020-04-29 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50828 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-02-17 | 2020-09-22 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_009 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-31 | 2020-08-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_112 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-30 | 2020-05-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_072 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-30 | 2020-05-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50287 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-02-17 | 2020-02-17 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403975 | Kilmun Hillrig UNS SO - Kilmun Inveroch CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501120_001 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-03-31 | 2018-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403975 | Kilmun Hillrig UNS SO - Kilmun Inveroch CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501120_003 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-03-31 | 2018-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_500144 | Kirkwall DOA (DOA000561) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50824 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500144 | Kirkwall DOA (DOA000561) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_125 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2019-01-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500145 | Langholm DOA (DOA000075) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50808 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2018-12-31 | 2019-07-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500145 | Langholm DOA (DOA000075) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_128 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2019-01-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500152 | Largs DOA (DOA002517) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_129 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2017-11-30 | 2018-01-31 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500152 | Largs DOA (DOA002517) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Largs | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2018-03-31 | 2018-06-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_134 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-08-31 | 2020-11-30 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50288 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-11-20 | 2021-03-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Leven | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-11-20 | 2021-03-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_010 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2021-02-28 | 2021-06-30 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500156 | Lincluden DOA (DOA000122) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_135 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-07-31 | 2017-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500156 | Lincluden DOA (DOA000122) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50809 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-11-30 | 2018-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50291 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-03-31 | 2019-06-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_136 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2018-09-30 | 2018-11-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_011 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-01-31 | 2019-12-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501642 | Loch Eck | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50767 | OMG 04 | Water |  | SWD | DWQ Reliability |  | 2017-03-29 | 2018-12-21 | 2019-08-23 | 2020-09-30 | 2020-11-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_501642 | Loch Eck | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50767 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2017-03-29 | 2018-12-21 | 2019-08-23 | 2020-09-30 | 2020-11-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50489 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_189 | OMG 22 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_020 | OMG 22 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_086 | OMG 22 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500161 | Lockerbie DOA (DOA000076) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_140 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2018-12-31 | 2019-02-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500161 | Lockerbie DOA (DOA000076) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50810 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2019-06-30 | 2019-07-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500835 | Mannofield West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50195 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-01-23 | 2020-10-31 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 183.03
PH_500835 | Mannofield West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53194 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-01-23 | 2020-10-31 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 18.86
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-06-30 | 2020-02-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2020-03-01 | 2020-10-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_004 | OMG 06 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2020-03-03 | 2020-10-21 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 24.64
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-02-28 | 2020-02-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500165 | Melrose DOA (DOA000072) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50834 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-12-31 | 2019-03-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500165 | Melrose DOA (DOA000072) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_142 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-09-30 | 2018-10-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-03-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-30 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-30 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_005 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-31 | 2019-02-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-31 | 2019-02-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_004 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2018-05-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500009 | Milngavie C4 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50055_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-12-31 | 2018-12-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500009 | Milngavie C4 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50055_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-12-31 | 2018-12-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500010 | Milngavie M1 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50056_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2018-08-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500010 | Milngavie M1 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50056_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2018-12-31 | 2019-07-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_011 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2021-03-31 | 2022-03-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_005 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_004 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_006 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2019-03-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_007 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_008 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_009 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2021-03-31 | 2021-12-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_010 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2020-03-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500162 | Nairn DOA (DOA000470) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_149 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-11-30 | 2018-01-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500162 | Nairn DOA (DOA000470) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Nairn | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-12-31 | 2018-03-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500867 | North Lochs RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50219 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-06 | 2018-09-20 | 2018-11-20 | 2019-09-30 | 2021-01-19 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 90.16
PH_500867 | North Lochs RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53196 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-06 | 2018-09-20 | 2018-11-20 | 2019-09-30 | 2021-01-19 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 12.7
PH_500169 | Oban DOA (DOA001020) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50814 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-31 | 2018-03-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500169 | Oban DOA (DOA001020) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_158 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-31 | 2017-09-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500171 | Penicuik DOA (DOA000526) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50826 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-05-31 | 2018-01-31 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500171 | Penicuik DOA (DOA000526) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_160 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-05-31 | 2017-10-31 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500168 | Perth City DOA (DOA000674) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_162 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-04-30 | 2019-04-30 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500168 | Perth City DOA (DOA000674) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_012 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-31 | 2019-12-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500210 | Perth- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50063_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2018-12-31 | 2020-03-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500210 | Perth- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50063_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2019-03-31 | 2020-05-02 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_164 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-31 | 2019-09-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_013 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-06-30 | 2019-12-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_007 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-31 | 2019-09-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_003 | OMG 06 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-06-30 | 2020-05-31 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 6.37
PH_500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-01-31 | 2018-06-30 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-01-31 | 2018-06-30 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_403090 | QS3b AR - Kaim WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50148-OMG01 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2020-09-30 | 2020-12-31 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_403090 | QS3b AR - Kaim WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50148-OMG20 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2020-09-30 | 2020-12-31 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_045 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_040 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_028 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_030 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_031 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_032 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_033 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_034 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_035 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_036 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_037 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_026 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_039 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_027 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_041 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_042 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_044 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_046 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_047 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_048 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_049 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_050 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_043 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_001 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_038 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_013 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_002 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_003 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_004 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_005 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_006 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_007 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_008 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_009 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_010 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_029 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_012 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_025 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_022 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_024 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_011 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_023 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_014 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_021 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_020 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_019 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_018 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_017 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_016 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_015 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50492 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2020-06-08 | 2020-11-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_RiCarron | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2019-02-28 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-23: 2
PH_500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_067 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_109 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_111 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-12-31 | 2020-01-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50408 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2020-08-07 | 2020-11-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_190 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_180 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_059 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2019-07-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50490 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-02-14 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-2 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-59 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-1 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-8 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-3 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-5 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-4 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-3 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-2 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-1 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-57 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-7 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-3 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-9 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-2 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-4 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-58 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-56 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-4 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-6 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-1 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-114 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-112 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-115 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-116 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-117 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-118 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-119 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-113 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-120 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-121 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-111 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-123 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-106 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-108 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-110 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-102 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-103 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-104 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-105 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-107 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-109 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-122 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2019-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2019-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-114 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-113 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-112 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-111 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-110 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-109 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-108 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-107 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-106 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-105 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-104 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-103 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-102 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-115 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_06 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_01 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_02 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_03 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_05 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_07 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_08 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_09 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2017-12-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_04 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-132 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-133 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-134 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-135 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-137 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-131 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-136 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-116 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-123 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-118 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-120 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-122 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-119 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-124 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-125 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-126 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-117 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-127 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-128 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-129 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-130 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-121 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-08-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-08-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2020-01-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-102 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-08-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-07-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2017-12-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-109 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-108 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-107 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-106 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-105 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-104 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-103 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2020-01-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-87 | OMG 10 | Water |  | SWMD | SEMD |  |  |  |  | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-04-01 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-2 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-1 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-3 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-4 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-8 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-5 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-6 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-7 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-1 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-10 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-11 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-12 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-2 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-6 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-7 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-8 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2020-02-02 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-9 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-5 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-4 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2018-04-30 | 2018-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-3 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2020-03-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 53307 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2016-10-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50102 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-28 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50150 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50750 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50091_TE_500091_01 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-28 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50751 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500178 | Skellyton DOA (DOA002580) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Skelly | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-10-31 | 2019-03-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500178 | Skellyton DOA (DOA002580) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_179 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-11-30 | 2019-03-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_503082 | South Uist WTW New Source | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50097 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2015-11-30 | 2021-01-04 | 2021-02-12 | 2022-06-06 | 2023-08-14 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_503082 | South Uist WTW New Source | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 53019 | OMG 08 | Water |  | WINF | DWQ Compliance |  | 2015-11-30 | 2021-01-04 | 2021-02-12 | 2022-06-06 | 2022-09-05 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-08
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_8 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_6 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_9 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_7 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_4 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_3 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_2 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_10 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_1 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_5 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50161 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-09-30 | 2018-09-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_003 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_004 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50792 | OMG 04 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-03-31 | 2018-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_002 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_010 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_009 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_008 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_007 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_006 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_005 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2023-03-16 | 2023-03-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_001 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-03-31 | 2019-02-28 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_007 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_006 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_004 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_003 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_002 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_001 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_010 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-11-30 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_009 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_001 | OMG 17 | Wastewater |  | SWMD | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2021-03-31 | 2021-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_001 | OMG 18 | Wastewater |  | SWMD | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2022-10-21 | 2022-11-25 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_002 | OMG 18 | Wastewater |  | SWMD | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2022-10-21 | 2022-11-25 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_003 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-03-31 | 2018-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_002 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-05-31 | 2018-11-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_001 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-11-30 | 2018-11-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N02 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N01 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2017-06-30 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N07 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-04-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 9
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N06 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N05 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N04 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-02-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N03 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2016-07-31 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge | 51145 | OMG 24 | Wastewater |  | SWMD | Sludge |  | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2021-01-13 | 2021-04-15 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-24
PH_403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge | 59080_01 | OMG 24 | Wastewater |  | SWMD | Sludge |  | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2021-01-13 | 2021-04-15 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-24
PH_500173 | St Andrews DOA (DOA000247) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50290 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2019-03-31 | 2019-07-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500173 | St Andrews DOA (DOA000247) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_181 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2018-12-31 | 2019-02-28 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500175 | St Monans DOA (DOA000252) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_182 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-31 | 2017-07-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500175 | St Monans DOA (DOA000252) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50836 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-31 | 2018-01-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50815 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-02-17 | 2020-02-29 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_184 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-01-24 | 2020-04-24 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_014 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-02-17 | 2020-08-06 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Steven | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-12-10 | 2020-04-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50816 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2018-12-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Stewa | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-03-31 | 2019-06-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_185 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-01-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_015 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-08-31 | 2020-02-21 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_186 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-06-30 | 2019-08-31 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Stirl | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-08-31 | 2019-12-31 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403938 | Stromness UWWTW (Transfer from 400089) | Q&S3B | Completion | Non OMG180 | 403938 | OMG 48 | Wastewater |  | WWINF | Non OMG180 |  | 2009-11-30 | 2015-10-29 | 2015-11-23 | 2018-02-28 | 2018-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-48
PH_403938 | Stromness UWWTW (Transfer from 400089) | Q&S3B | Completion | Non OMG180 | 403938_WORKS | OMG 48 | Wastewater |  | WWINF | Non OMG180 |  | 2009-11-30 | 2015-10-29 | 2015-11-23 | 2018-02-28 | 2018-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-48
PH_500880 | Tarbert Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50227 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2019-03-31 | 2019-09-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 31.84
PH_500880 | Tarbert Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50905 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2020-04-01 | 2020-04-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 3.7
PH_500108 | Tay Coastal Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_TayCoast | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500108 | Tay Coastal Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50491 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_502767 | THM Study 1 - West | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59107a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502767 | THM Study 1 - West | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59106a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502768 | THM Study 2 - North A | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59122a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502768 | THM Study 2 - North A | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59108a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59112a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59111a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59105a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59109a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-04-28 | 2020-06-29 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59119a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-04-28 | 2020-06-29 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59003a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-04-28 | 2020-06-29 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500882 | Tolsta Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50229 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-06-30 | 2020-03-27 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 58.69
PH_500882 | Tolsta Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53198 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-06-30 | 2020-02-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 7.25
PH_500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Troqu | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-12-05 | 2020-04-26 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50713 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-12-05 | 2020-04-26 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_197 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-12-31 | 2019-12-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500852 | Tullich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53199 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-31 | 2018-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 4.67
PH_500852 | Tullich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50231 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-31 | 2018-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 14.5
PH_500890 | Turriff RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50198 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-30 | 2020-01-23 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 132.95
PH_500890 | Turriff RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53200 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-30 | 2020-01-17 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 5.85
PH_500186 | Underwood Cumnock DOA (DOA000144) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Under | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-28 | 2018-06-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500186 | Underwood Cumnock DOA (DOA000144) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_058 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-28 | 2018-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_UppClyde | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-03-27 | 2020-12-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-23: 2
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_041 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-11-30 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_034 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-02-24 | 2020-03-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50409 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-08-14 | 2020-12-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_502751 | WATER OF LEITH UIDs - BATCH 0 - 2 x STUDY OUTPUTS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_003 | OMG 18 | Wastewater |  | SWD | UWWTD - UID |  | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-07-31 | 2017-10-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502751 | WATER OF LEITH UIDs - BATCH 0 - 2 x STUDY OUTPUTS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_007 | OMG 18 | Wastewater |  | SWD | UWWTD - UID |  | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-05-31 | 2017-10-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_016 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-31 | 2020-03-31 | 2020-03-31 | 2021-05-31 | 2021-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_018 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-31 | 2020-03-31 | 2020-03-31 | 2021-05-31 | 2021-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502741 | WATER OF LEITH UIDs - BATCH 2 - Currie Old Mill Off Lanark Road CSO and Juniper Green | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_009 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-06-01 | 2020-01-29 | 2020-03-23 | 2020-12-31 | 2021-03-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502741 | WATER OF LEITH UIDs - BATCH 2 - Currie Old Mill Off Lanark Road CSO and Juniper Green | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_010 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-06-01 | 2020-01-29 | 2020-03-23 | 2020-12-31 | 2021-03-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_014 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-30 | 2020-10-31 | 2020-11-30 | 2021-09-30 | 2021-12-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_013 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-30 | 2020-10-31 | 2020-11-30 | 2021-09-30 | 2021-12-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_012 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-30 | 2020-10-31 | 2020-11-30 | 2021-09-30 | 2021-12-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_500884 | West Lewis Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53201 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-06-30 | 2020-01-28 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 1.55
PH_500884 | West Lewis Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50232 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-06-30 | 2020-01-28 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 56.62
PH_500216 | West Lewis WI - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50086_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-31 | 2018-12-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500216 | West Lewis WI - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50086_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-31 | 2018-12-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_008 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_012 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_013 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_014 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-12-31 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_015 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_016 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23

## G7 - Asset Maintenance
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2020
SECTION G: INVESTMENT MONITORING
Table G7: Asset maintenance
40
Line | Description | Units | Field | Estimated Report Year
Ref. |  |  | Type
2019-20
CG
1 | Responsive maintenance: water
G7.01 | Inspections and testing | £m | I | 0.22276 | C5
G7.02 | Repair | £m | I | 62.0678 | C5
G7.03 | Refurbishment | £m | I | 22.4255 | C5
G7.04 | Replacement | £m | I | 24.9755 | C5
G7.05 | Total responsive maintenance for the water service | £m | C | 109.6916 | C5
2 | Responsive maintenance: wastewater
G7.06 | Inspections and testing | £m | I | 0 | C5
G7.07 | Repair | £m | I | 62.3872 | C5
G7.08 | Refurbishment | £m | I | 14.409 | C5
G7.09 | Replacement | £m | I | 12.708 | C5
G7.10 | Total responsive maintenance for the wastewater service | £m | C | 89.5043 | C5
3 | Planned maintenance: water
G7.11 | Inspections and testing | £m | I | 1.8797 | C5
G7.12 | Repair | £m | I | 25.6803 | C5
G7.13 | Refurbishment | £m | I | 4.6748 | C5
G7.14 | Replacement | £m | I | 70.9237 | C5
G7.15 | Total planned maintenance for the water service | £m | C | 103.1584 | C5
4 | Planned maintenance: wastewater
G7.16 | Inspections and testing | £m | I | 2.1519 | C5
G7.17 | Repair | £m | I | 15.3772 | C5
G7.18 | Refurbishment | £m | I | 1.2724 | C5
G7.19 | Replacement | £m | I | 99.6752 | C5
G7.20 | Total planned maintenance for the wastewater service | £m | C | 118.4766 | C5
5 | Expenditure Totals
G7.21 | Responsive maintenance | £m | C | 199.1959 | C5
G7.22 | Planned maintenance | £m | C | 221.635 | C5
G7.23 | Total maintenance | £m | C | 420.8309 | C5
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: